## Sheet1
Rate Case Procedural Schedule Draft 19 Feb
(All discovery is rolling discovery. Objections are due 5 days after receipt. Responses due 10 calendar days after receipt of IR.)
(Opposing testimony of PREPA, LUMA, or Genera against one of the other two would be due same date as intervenor testimony)
Starting now | Participants submit requests to intervene
2025-04-01 | Applicants file rate application and direct testimony
2025-04-02 | PREB Order approving interventions
2025-04-02 | Discovery opens. Rolling discovery always applies. Responses to each set of IR due in 10 calendar days
2025-05-15 | Intervenor answering testimony
2025-06-30 | PREB consultants' expert reports
2025-08-08 | Intervenors' rebuttal to expert reports
2025-08-19 | Applicants' rebuttal to all testimony (can be separate rebuttal from each of PREPA, LUMA, or Genera)
2025-08-20 | Energy Bureau issues completeness order
2025-08-25 | Final IRs
2025-09-02 | Final responses to IRs
2025-09-03 | Prehearing conference to create final schedule for hearing: topic panels and questioning sequence
2025-09-08 | Start of evidentiary hearings
2025-09-30 | End of evidentiary hearings
Public hearing
Public comment deadline
2025-10-30 | Initial briefs
2025-11-18 | Reply briefs
2025-12-30 | Final order earliest date
2025-02-16 | Final order last possible day (180 days after completeness order)