## Sheet1
Project Name | Category | Project Filed by | Region/Municipality | Power Plant & Unit Number | NME Maintenance Activities | Filing Date | Funds |  | Estimated Cost ($M) | Contract Costs ($M) | Approval Department of Energy |  | Project Phase |  |  |  |  | Comments | Plant | RO Date
[7 empty] | Origin | Disbursement amount |  |  | Cost ($) | Date | Phase** | Permits Status | Start Date | Completion Date | % Completed
Generation Aguirre Black Start | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2021-04-28 | Federal |  | 45.2 | [9 empty] | Aguirre | 2021-06-08
FAASt Cambalache Power Plant – Flood Protection Barrier – Generation | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-04-28 | Federal |  | 4 |  |  |  | Planning | 75% |  |  | 30% | Scope on Development. Pending FEMA approval. First Delivery of design& Specs in progress. Regulatory permits pending. (Tetratech) | Cambalache | 2021-06-08
Mobile Generation Units Purchases | G | PREPA | Island Wide | Palo Seco Power Plant | N/A | 2021-04-28 | Federal |  | 59.8 |  |  |  | Completed |  | 2019-05-21 | 2020-08-22 | 100% |  | Island Wide | 2021-06-08
Palo Seco Steam Plant Repairs | G | PREPA | Cataño | Palo Seco Power Plant - units 3&4 | N/A | 2021-08-20 | Federal-Insurance |  | 2.55 | [9 empty] | Palo Seco | 2021-09-08
New Simple Cycle Gas Turbines at Yabucoa | G | PREPA | Yabucoa | Peaker site | N/A | 2021-09-08 | Federal |  | 45.2 |  |  |  | Design | [5 empty] | Yabucoa | 2021-09-28
Raw Water Tanks 1 & 2 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake/Fiona) |  | 3 | 5 | 40200000 | 2020-05-22 | Construction |  | 2022-04-12 | 2025-04-30 | 70% | In Progress | Costa Sur | 2021-12-01
Demin Water Tanks 5 & 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake) |  | 4.1 | 3.95 |  | 2020-05-22 | Completed |  | 2021-07-06 | 2022-12-16 | 100% |  | Costa Sur | 2021-12-01
Diesel Service Tank | G | PREPA | Guayanilla | Costa Sur Power Plant - peaker units | N/A | 2021-11-08 | Federal (Earthquake) |  | 1 |  |  | 2020-05-22 | Planning |  |  |  |  | The Repair of this tank may be discarded, depending on the New Lay out of the Peakers for CS Power Plant. | Costa Sur | 2021-12-01
Water Discharge Channel | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake/Fiona) |  | 6.7 | 5.7 |  | 2020-05-22 | Construction |  | 2021-03-30 | 2025-06-30 | 30% | To start pile driving on June 2024 | Costa Sur | 2021-12-01
Control Room 5 & 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake) |  | 0.41 | 0.41 |  | 2020-05-22 | Completed |  | 2020-05-11 | 2020-07-24 | 100% |  | Costa Sur | 2021-12-01
Main Power Transformers 4, 5 & 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake) |  | 0.08 | 0.08 |  | 2020-05-22 | Completed |  | 2020-06-01 | 2020-11-20 | 100% |  | Costa Sur | 2021-12-01
Boilers 5 & 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake) |  | 0.71 | 0.71 |  | 2020-05-22 | Completed |  | 2020-05-18 | 2020-11-30 | 100% | Unit 5 project has not started. | Costa Sur | 2021-12-01
Condensate Water Tank 5 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake) |  | 0.35 | 0.35 |  | 2020-05-22 | Completed |  | 2020-05-18 | 2020-07-31 | 100% |  | Costa Sur | 2021-12-01
New Condensate Water Tank 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake) |  | 0.85 | 0.85 |  | 2020-05-22 | Completed |  | 2020-09-14 | 2021-01-13 | 100% |  | Costa Sur | 2021-12-01
Structural Repairs Units 1-4 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 1-4 | N/A | 2021-11-08 | Federal (Earthquake) |  | 0.86 | 0.73 |  | 2020-05-22 | Completed |  | 2020-07-16 | 2020-09-17 | 100% |  | Costa Sur | 2021-12-01
Old Demi Plant | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2021-11-08 | Federal (Earthquake) |  | 0.21 | 0.21 |  | 2020-05-22 | Completed |  | 2020-06-08 | 2020-07-11 | 100% |  | Costa Sur | 2021-12-01
Sanitary Water Pumping System | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.06 | 0.06 |  |  | Completed |  | 2018-07-12 | 2021-01-15 | 100% |  | Cambalache | 2021-12-20
Hydraulic Equipment | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.04 | 0.04 |  |  | Completed |  | 2017-09-21 | 2018-09-30 | 100% |  | Cambalache | 2021-12-20
Different Areas | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.2 | 0.2 |  |  | Completed |  | 2017-10-13 | 2018-09-18 | 100% |  | Cambalache | 2021-12-20
Different AC units of the Plant | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.05 | 0.05 |  |  | Completed |  | 2017-12-14 | 2018-03-14 | 100% |  | Cambalache | 2021-12-20
Generation Plant Fences | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.2 | 0.2 |  |  | Completed |  | 2018-02-05 | 2018-09-18 | 100% |  | Cambalache | 2021-12-20
Storm Water Pump System | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.34 | 0.34 |  |  | Completed |  | 2018-06-05 | 2020-02-03 | 100% |  | Cambalache | 2021-12-20
Fuel Transfer Pump | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 |  |  | 0 | 0 |  |  | Completed |  | 2017-10-23 | 2017-11-14 | 100% |  | Cambalache | 2021-12-20
Cable Trays | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.06 | 0.06 |  |  | Completed |  | 2017-09-15 | 2017-09-30 | 100% |  | Cambalache | 2021-12-20
Lighting | G | PREPA | Arecibo | Cambalache / All units | N/A | 2021-12-01 | Insurance-Federal (Hurricane Maria) |  | 0.04 | 0.04 |  |  | Completed |  | 2018-07-24 | 2018-10-28 | 100% |  | Cambalache | 2021-12-20
Gas Generator | G | PREPA | Mayaguez | Mayaguez Power Turbines | Programmed Outage Maintenance | 2021-12-01 |  |  | 0.01 | [9 empty] | Mayaguez | 2021-12-20
Brush Generator | G | PREPA | Mayaguez | Mayaguez Power Turbines | Programmed Outage Maintenance | 2021-12-01 |  |  | 0.07 |  |  |  | Procurement |  |  |  |  | In Procurement Process. Evaluation Committee is being formed. CR 283264 | Mayaguez | 2021-12-20
Fuel Tank 1 | G | PREPA | Mayaguez | Mayaguez Power Turbines | Programmed Outage Maintenance | 2021-12-01 | NME |  | 0.03 |  |  |  | Design |  | 2024-11-15 | 2025-11-14 |  | Start procurement process on June 2024. Preparing Specifications. | Mayaguez | 2021-12-20
Plant Operations | G | PREPA | Mayaguez | Mayaguez Power Turbines | N/A | 2021-12-01 |  |  | 0.08 | [9 empty] | Mayaguez | 2021-12-20
Cooling Towers 3 & 4 | G | PREPA | Cataño | Palo Seco Power Plant - units 3&4 | N/A | 2021-12-01 | Federal-Insurance |  | 1.43 | 1.44 |  |  | Completed |  | 2018-02-08 | 2018-06-29 | 100% |  | Palo Seco | 2021-12-20
Boilers’ Cameras | G | PREPA | Cataño | Palo Seco Power Plant - units 3&4 | N/A | 2021-12-01 | Federal-Insurance |  | 0.03 | 0.03 |  |  | Completed |  | 2018-11-01 | 2019-02-25 | 100% |  | Palo Seco | 2021-12-20
Federal Alert System | G | PREPA | Cataño | Palo Seco Power Plant - All units | N/A | 2021-12-01 | Federal-Insurance |  | 0.01 | 0.01 |  |  | Completed |  | 2018-01-31 | 2018-04-07 | 100% |  | Palo Seco | 2021-12-20
All Generation Units | G | PREPA | Cataño | Palo Seco Power Plant - All units | N/A | 2021-12-01 | Federal-Insurance |  | 1.04 | 1.04 |  |  | Completed |  | 2018-06-25 | 2020-07-31 | 100% |  | Palo Seco | 2021-12-20
Boilers 9 & 10 | G | PREPA | San Juan | San Juan Power Plant units 9-10 | N/A | 2021-12-01 | Federal-Insurance |  | 0.34 | 0.48 |  |  | Completed |  | 2019-10-03 | 2020-02-01 | 100% |  | San Juan | 2021-12-20
Units 9 & 10 | G | PREPA | San Juan | San Juan Power Plant units 9-10 | N/A | 2021-12-01 | Federal-Insurance |  | 0.04 | 0.04 |  |  | Completed |  | 2017-10-28 | 2017-10-28 | 100% |  | San Juan | 2021-12-20
Units 7 & 8 | G | PREPA | San Juan | San Juan Power Plant units 7-8 | N/A | 2021-12-01 | Federal-Insurance |  | 0.1 | 0.1 |  |  | Completed |  | 2017-12-30 | 2019-05-20 | 100% |  | San Juan | 2021-12-20
Plant’s Emergency Notification System | G | PREPA | San Juan | San Juan Power Plant | N/A | 2021-12-01 | Federal-Insurance |  | 0.01 | 0.01 |  |  | Completed |  | 2018-05-17 | 2018-05-18 | 100% |  | San Juan | 2021-12-20
Dikes R1, R2, R3, R4 | G | PREPA | San Juan | San Juan Power Plant | N/A | 2021-12-01 | Federal-Insurance |  | 0.1 | 0.1 |  |  | Completed |  | 2019-05-18 | 2019-10-19 | 100% |  | San Juan | 2021-12-20
Boiler’s Dining Room AC | G | PREPA | San Juan | San Juan Power Plant | N/A | 2021-12-01 | Federal-Insurance |  | 0 | 0.004 |  |  | Completed |  | 2019-01-29 | 2019-01-29 | 100% |  | San Juan | 2021-12-20
NPDES office AC | G | PREPA | San Juan | San Juan Power Plant | N/A | 2021-12-01 | Federal-Insurance |  | 0 | 0.001 |  |  | Completed |  | 2018-11-30 | 2018-11-30 | 100% |  | San Juan | 2021-12-20
Units 5 & 6 | G | PREPA | San Juan | San Juan Power Plant units 5-6 | N/A | 2021-12-01 | Federal-Insurance |  | 0.02 | 0.02 |  |  | Completed |  | 2018-05-17 | 2018-05-18 | 100% |  | San Juan | 2021-12-20
General Mechanic Workshop | G | PREPA | San Juan | San Juan Power Plant | N/A | 2021-12-01 | Federal-Insurance |  | 0.19 | 0.19 |  |  | Completed |  | 2019-03-04 | 2019-04-05 | 100% |  | San Juan | 2021-12-20
Power Plant Rehabilitation contracts | G | PREPA | San Juan | San Juan Power Plant | N/A | 2021-12-01 | Federal-Insurance |  | 0.17 | 0.17 |  |  | Completed |  | 2018-11-15 | 2019-03-31 | 100% |  | San Juan | 2021-12-20
Boilers 7 & 8 | G | PREPA | San Juan | San Juan Power Plant units 7-8 | N/A | 2021-12-01 | Federal-Insurance |  | 0.41 | 0.41 |  |  | Completed |  | 2020-01-29 | 2020-01-30 | 100% |  | San Juan | 2021-12-20
Units 5 and 6 Cooling Tower Replacement | G | PREPA | San Juan | San Juan Power Plant units 5-6 | N/A | 2022-01-13 | Federal |  | 1.89 | 1.41 | 1.89 | 2022-02-10 | Completed |  | 2022-02-07 | 2022-12-22 | 100% |  | San Juan | 2022-02-10
Units 5 and 6 Condenser Repair and Coating Application | G | PREPA | San Juan | San Juan Power Plant units 5-6 | Programmed Outage Maintenance | 2022-01-13 | Federal (50%)/NME (50%) |  | 1.03 | 1.04 | 1.04 | 2022-02-10 | (1) Completed, (1) in Procurement |  | 2022-02-26 | 2024-10-22 | 50% |  | San Juan | 2022-02-10
Units 5 and 6 High Pressure Bleed Valve, Low Pressure Bleed Valve and Heat Injection Steam Valve | G | PREPA | San Juan | San Juan Power Plant units 5-6 | N/A | 2022-01-13 | Federal |  | 0.37 | 0.37 | 0.37 | 2022-02-10 | Completed |  | 2021-12-09 | 2022-05-20 | 100% |  | San Juan | 2022-02-10
Units 5 and 6 Black Start Emergency Generator Upgrade | G | PREPA | San Juan | San Juan Power Plant units 5-6 | N/A | 2022-01-13 | Federal |  | 0.35 | 0.35 | 0.35 | 2022-02-10 | Completed |  | 2022-10-24 | 2023-12-31 | 100% |  | San Juan | 2022-02-10
Units 5 and 6 1Replacement of Outlet Valves and Elbow Condenser | G | PREPA | San Juan | San Juan Power Plant units 5-6 | N/A | 2022-01-13 | Federal |  | 0.67 |  | 0.67 | 2022-02-10 | Completed |  | 2022-01-24 | 2023-01-31 | 100% |  | San Juan | 2022-02-10
Control System Upgrade units 5 & 6 | G | PREPA | San Juan | San Juan Power Plant units 5-6 | N/A | 2022-01-13 | Federal |  | 3.2 | 3.2 | 3.2 | 2022-02-10 | Completed |  | 2022-01-24 | 2023-03-14 | 100% |  | San Juan | 2022-02-10
Installation of Modules D&E HRSG Unit 5 | G | PREPA | San Juan | San Juan Power Plant unit 5 | N/A | 2022-01-13 | Federal |  | 9.75 |  | 9.75 | 2022-02-10 | Completed |  | 2022-02-17 | 2022-06-20 | 100% |  | San Juan | 2022-02-10
Replacement of the Online Condenser Cleaner Unit 5 | G | PREPA | San Juan | San Juan Power Plant unit 5 | N/A | 2022-01-13 | Federal |  | 3.6 |  | 3.6 | 2022-02-10 | Procurement |  | 2024-04-30 | 2025-12-31 |  | Evaluation panel submitted rev 1 of the technical evaluation. Procurement negotiating with selected proponent. | San Juan | 2022-02-10
Replacement of Load Center 1- 4 Condenser Circulating Water Pump | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-13 | Federal |  | 0.63 |  | 0.63 | 2022-02-10 | Awarded |  | 2024-04-15 | 2025-09-30 |  | Contract awarded $820,000. Procurement is working on it. In P3A approval. | Aguirre | 2022-02-10
Sea Water Intake Structural Repairs Work | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-13 | Federal |  | 5.27 |  | 5.27 | 2022-02-10 | Permitting |  | 2024-08-31 | 2025-08-31 |  | Project Requires a Joint Permit or a Nationwde Permit by USACOE. | Aguirre | 2022-02-10
Rehabilitation Fuel Tank Farm Liners | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-13 | Federal |  | 1.29 | 1.67 | 1.29 | 2022-02-10 | Completed |  | 2023-03-20 | 2024-02-22 | 100% | Turn Over Package in process. Expected due date on 2-23-24. | Aguirre | 2022-02-10
Two New Condenser Discharge Water Pumps Motors | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-13 | Federal |  | 0.75 | 0.64 | 0.75 | 2022-02-10 | Completed |  | 2022-02-11 | 2022-07-28 | 100% |  | Aguirre | 2022-02-10
Two New CCWP Motors | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-13 | Federal |  | 0.64 |  | 0.64 | 2022-02-10 | Procurement |  | 2024-04-25 | 2025-04-24 |  | Contract 105520 in P3A waiting for approval. | Aguirre | 2022-02-10
Aguirre Combine Cycle plant Permanent Repairs | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-13 |  |  | 0.72 |  | 0.72 | 2022-02-10 | [6 empty] | Aguirre | 2022-02-10
Aguirre CC- Hot Gas Path Inspection Work Units 1-1 and 1-2 | G | PREPA | Salinas | Aguirre Power Plant - units CC 1-1&1-2 | Programmed Outage Repair | 2022-01-13 | Federal/NME |  | 1.09 |  | 1.09 | 2022-02-10 | Construction |  | 2022-06-17 | 2023-12-31 | 50% | U1-1 was completed. U1-2 Major Inspection. Projet will be funded with Forced Outaged Account. | Aguirre | 2022-02-10
Unit 1 - Major Inspection (Replacement Turbo- Generator) | G | PREPA | Salinas | Aguirre Power Plant unit 1 | N/A | 2022-01-13 | Federal |  | 11.16 | 12.5 | 11.16 | 2022-02-10 | Completed |  | 2022-03-28 | 2023-03-07 | 100% |  | Aguirre | 2022-02-10
Unit 2 Excitation System | G | PREPA | Salinas | Aguirre Power Plant unit 2 | N/A | 2022-01-13 | Federal |  | 1.52 | 1.52 | 1.52 | 2022-02-10 | Construction |  | 2022-04-25 | 2024-04-30 | 85% | Equipment to be installed during an Environmental Schedule Outage on November 2024. | Aguirre | 2022-02-10
Design Fire Pump for Aguirre Power Complex | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-13 | Federal |  | 0.28 | 0.18 | 0.28 | 2022-02-10 | In Progress |  | 2024-02-23 | 2024-08-30 | 30% | Contractor should submit final revision for 11-11-24. | Aguirre | 2022-02-10
Procurement of Air-Preheaters Baskets, Unit 5 | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-01-13 | Federal |  | 1.97 | 1.1 | 1.97 | 2022-02-10 | Completed |  | 2021-12-20 | 2022-06-22 | 100% |  | Costa Sur | 2022-02-10
Procurement of Condenser Circulating Water Pump (CCWP) and Boiler Circulating Water Pump (BCWP) Spare Motors for Units 5 and 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-01-13 | Federal |  | 0.87 |  | 0.87 | 2022-02-10 | Procurement |  | 2024-03-31 | 2025-05-31 | 50% | Contract signed by the contractor. The CEO's signature is missing. 120 days of execution $417,657.00 | Costa Sur | 2022-02-10
Replacement of Unit 5 Electric Load Center | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-01-13 | Federal |  | 0.29 | 0.29 | 0.29 | 2022-02-10 | Construction |  | 2022-11-30 | 2025-06-30 | 25% | 12/13/2024 CPA 127857 $124,703.25 Waiting an outage for installation. Meeting with contractor and plant personnel to begin partial installation. 11/15/2024 Load Center was delivered on 11/12/24. | Costa Sur | 2022-02-10
BFWP Inner Barrel Bundle | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | Programmed Outage Maintenance | 2022-01-13 | NME |  | 1.63 | 1.63 | 1.63 | 2022-02-10 | Completed |  | 2021-09-15 | 2024-03-22 | 100% |  | Costa Sur | 2022-02-10
Mega-Gens Environmental Commissioning | G | PREPA | Cataño | Palo Seco Power Plant - Mega Gen units | Programmed Outage Environmental Maintenance | 2022-01-13 | NME |  | 1.04 | 1.38 |  |  | Completed |  | 2021-08-30 | 2022-12-31 | 100% |  | Palo Seco | 2022-02-10
Unit 1A, 1B and 4A Rehabilitation | G | PREPA | Mayaguez | Mayaguez Power Turbines - units 1A, 1B&4A | N/A | 2022-01-13 | Federal |  | 18 | 18 | 18 | 2022-02-10 | Completed | [5 empty] | Mayaguez | 2022-02-10
Inner Barrel Bundle | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-25 | Federal |  | 1.63 | 1.63 | 1.63 | 2022-02-18 | Construction |  | 2022-10-17 | 2024-07-31 | 70% | In manufacturing. A site visit by Operations is being coordinated for assembly of the Bundle. Expected equipment July 2024 | Aguirre | 2022-02-18
Replacement of Excitation System Units 5 and 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-01-25 | Federal |  | 2.76 | 1.56 | 2.76 | 2022-02-18 | Execution |  | 2024-09-01 | 2025-08-31 | 40% | 01/17/2025 Shop drawings were received and approved. Equipment expected to be on site by 8/22/25. | Costa Sur | 2022-02-18
Unit 6 LP-B Installation Work (Failure) | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 6 | N/A | 2022-01-25 | Federal |  | 2.09 | 2.08 | 2.08 | 2022-02-18 | Completed |  | 2021-10-13 | 2021-12-22 | 100% |  | Costa Sur | 2022-02-18
Fuel Tanks Level Measurement System | G | PREPA | Cataño | Palo Seco Power Plant - All units | N/A | 2022-01-25 | Federal |  | 0.55 | 1.56 | 0.55 | 2022-02-18 | Completed |  | 2023-06-13 | 2024-02-05 | 100% | Substantial completion was accepted. Punch list was send to contractor. Contractor is working on the punch list. | Palo Seco | 2022-02-18
Water Retention Tank Num. 3 | G | PREPA | Cataño | Palo Seco Power Plant - All units | N/A | 2022-01-25 | Federal |  | 0.8 | 0.65 | 0.8 | 2022-02-18 | Completed |  | 2022-12-12 | 2023-05-31 | 100% |  | Palo Seco | 2022-02-18
Contract, on request, for Crane Services PS4 | G | PREPA | Cataño | Palo Seco Power Plant - Unit 4 | Programmed Outage Maintenance | 2022-01-25 | NME |  | 0.7 | 0.7 | 0.7 | 2022-02-18 | In Progress |  | 2022-08-19 | 2024-06-30 |  | This is a Services Upon Request Contract based on necessities. | Palo Seco | 2022-02-18
Upgrade OSI DCS | G | PREPA | Cataño | Palo Seco Power Plant - units 3&4 | N/A | 2022-01-25 | Federal |  | 1.15 |  | 1.15 | 2022-02-18 | Awarded |  | 2024-10-01 | 2024-06-30 |  | 1/30/2025 Contract was signed by Genera PR. 1/17/2025 Contractor signed contract, waiting for Genera PR signature. 12/13/2024 P3A approval was issued. Contract signature in process. | Palo Seco | 2022-02-18
Procurement of Water Heater 5 (Deaerator) Spare Pump | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-02-02 | Federal |  | 0.4 | 0.4 | 0.4 | 2022-02-24 | Completed |  | 2022-10-07 | 2023-04-14 | 100% |  | Costa Sur | 2022-02-28
Procurement of Induced Draft Fan (IDF) and Forced Draft Fan (FDF) Spare Motors for Units 5 and 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-02-02 | Federal |  | 1.16 |  | 1.16 | 2022-02-24 | Procurement |  | 2024-04-30 | 2025-05-31 | 75% | In Procurement Process. IDF CR-252640 RFP-4217, FDF CR-252642 RFP-4206. | Costa Sur | 2022-02-28
Procurement of Condensate Pump (CP) Motor for Units 5 and 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-02-02 | Federal |  | 0.87 |  | 0.87 | 2022-02-24 | Procurement |  | 2024-05-31 | 2025-04-15 | 75% | In Procurement Process CR-255079 RFP-4224 Contract issued C-103095. | Costa Sur | 2022-02-28
Replacement of 4160 V Electric Cable Normal Transformer 5A, 5B | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-02-02 | Federal |  | 0.38 |  | 0.38 | 2022-02-24 | Completed |  | 2022-07-20 | 2023-12-17 | 100% |  | Costa Sur | 2022-02-28
AGC - Replacement Project | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | Programmed Outage Maintenance | 2022-02-02 | NME |  | 0.4 | 0.4 | 0.4 | 2022-02-24 | Completed |  |  |  | 100% | Plant personnel carried out the project with Genera's budget. | Costa Sur | 2022-02-28
Fuel Igniters Procurement and Replacement Work | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | Programmed Outage Maintenance | 2022-02-02 | Federal/NME |  | 2.36 | 2.03 | 2.36 | 2022-02-24 | Construction |  | 2021-03-01 | 2025-12-31 | 75% | First Project (Unit 6) completed. Second Project (Unit 5) to be completed on December 2024. The Second project will depend on a Schedule outage on Unit 5. | Costa Sur | 2022-02-28
New Water Condensate 1-2 Tank | G | PREPA | Cataño | Palo Seco Power Plant - All units | N/A | 2022-02-02 | Federal |  | 1 | 1.66 | 1 | 2022-02-24 | Completed |  | 2023-01-25 | 2023-12-27 | 100% | Final Acceptance accomplished on 02-12-2024. | Palo Seco | 2022-02-28
Unit PS3 - Major Outage - Boiler Sections Replacement and Repairs; MPT, Generator and Turbine Repair & Auxiliary Equipment Inspection Work | G | PREPA | Cataño | Palo Seco Power Plant - Unit 3 | N/A | 2022-02-02 | Federal |  | 15 | 15 | 15 | 2022-02-24 | Construction |  | 2024-01-03 | 2024-06-15 | 95% | Construction in Progress. | Palo Seco | 2022-02-28
Automatic Voltage Regulator & SFC Upgrade for 2 Units | G | PREPA | Arecibo | Cambalache / units 2&3 | N/A | 2022-02-02 | Federal |  | 1.04 | 1.04 | 1.043 | 2022-02-24 | Construction |  | 2022-03-10 | 2025-06-30 | 90% | Contractor waiting for Genera PR to replace the starting transformer. | Cambalache | 2022-02-28
LTSA Units Camb 1-2-3 | G | PREPA | Arecibo | Cambalache / units 2&3 | Programmed Outage maintenance | 2022-02-02 | NME |  | 12 |  | 12 | 2022-02-24 | Completed |  |  |  |  | Contract expired on December 31, 2023. | Cambalache | 2022-02-28
Unit 5 SCR - Ammonium Procurement | G | PREPA | San Juan | San Juan Power Plant unit 5 | N/A | 2022-02-02 | Operational |  | 0.5 | 0.5 | 0.5 | 2022-02-24 | In Progress |  |  |  |  | Operational Contract. | San Juan | 2022-02-28
Units 5 and 6 New High Pressure Pumps | G | PREPA | San Juan | San Juan Power Plant units 5-6 | N/A | 2022-01-28 | Federal |  | 1.6 | 1.6 | 1.6 | 2022-03-09 | Construction |  | 2023-02-09 | 2024-07-31 | 70% | In delivery process, expected July 2024. | San Juan | 2022-03-09
Unit 7 Air Preheater Maintenance and Replacement | G | PREPA | San Juan | San Juan Power Plant unit 7 | N/A | 2022-01-28 | Federal |  | 0.6 | 0.4 | 0.6 | 2022-03-09 | Completed |  | 2023-06-05 | 2023-08-15 | 100% | All documents were received. DCMC Partners has already started requesting documents for the claim 02/22/2024. | San Juan | 2022-03-09
Repairs to Nautilus Water Treatment System | G | PREPA | San Juan | San Juan Power Plant | N/A | 2022-01-28 | Federal |  | 0.25 | 0.1 | 0.25 | 2022-03-09 | Completed |  | 2022-10-04 | 2023-03-24 | 100% | Working the technical specifications. | San Juan | 2022-03-09
Replacement of Two Uninterruptible Power Supply Systems for Units 7 and 8 | G | PREPA | San Juan | San Juan Power Plant units 7-8 | N/A | 2022-01-28 | Federal |  | 0.45 | 0.74 | 0.45 | 2022-03-09 | Completed |  | 2023-03-15 | 2024-06-30 | 100% | Waiting for contractor closing documents. Project completed. | San Juan | 2022-03-09
Units 7-10 New Raw Water Tank | G | PREPA | San Juan | San Juan Power Plant units 7-10 | N/A | 2022-01-28 | Federal |  | 1 | 1.47 | 1 | 2022-03-09 | Completed |  | 2022-10-31 | 2023-06-30 | 100% |  | San Juan | 2022-03-09
Units 5-10 Heavy Equipment Rental Services | G | PREPA | San Juan | San Juan Power Plant | Programmed Outage Maintenance | 2022-01-28 | NME |  | 0.85 | 0.85 | 0.85 | 2022-03-09 | In Progress |  | 2022-01-21 | 60/30/24 |  | Operational Contract. | San Juan | 2022-03-09
Water Treatment and Technical Assistance Cooling Water System | G | PREPA | San Juan | San Juan Power Plant | N/A | 2022-01-28 |  |  | 0.23 |  | 0.23 | 2022-03-09 | [5 empty] | Operational Contract. | San Juan | 2022-03-09
Unit 6 - Major Overhaul (CT Repairs) | G | PREPA | San Juan | San Juan Power Plant unit 6 | N/A | 2022-01-28 | Federal |  | 12.77 |  | 12.77 | 2022-03-09 | Procurement |  | 2024-11-15 | 2025-03-02 |  | CTG6 Major completed on 1/3/2025. Unit startup and performance tests will be performed upon completion of STG6 & HRSG works. | San Juan | 2022-03-09
Procurement of Stages 1, 2, 3 Turbine Rotor Bucket Set, Aguirre Combined Cycle | G | PREPA | Salinas | Aguirre Power Plant, CC units | N/A | 2022-01-28 | Federal |  | 0.5 |  | 0.5 | 2022-03-09 | Completed |  | 2022-06-17 | 2022-07-07 | 100% |  | Aguirre | 2022-03-09
New Water Condensate Tank for the Aguirre Combined Cycle | G | PREPA | Salinas | Aguirre Power Plant, CC units | N/A | 2022-01-28 | Federal |  | 0.41 | 1.35 | 0.41 | 2022-03-09 | Completed |  | 2023-01-30 | 2024-04-22 | 100% | Project completed and in operations. | Aguirre | 2022-03-09
Major inspection Unit 1-3 | G | PREPA | Salinas | Aguirre Power Plant, CC unit 1-3 | N/A | 2022-01-28 | Federal |  | 2.56 |  | 2.56 | 2022-03-09 | Execution |  | 2024-09-16 | 2024-12-30 |  | Project in progress. Evaluating shell hook fit repair options. Potential delay due to casing stage 4 hookfit failure. Awaiting OEM reccomendations for repairs. Contract work will need to be extended. Waiting for contractor recommendation on repair solution for the compressor caising. Project started on 9-9-2024. | Aguirre | 2022-03-09
Purchase and Installation Breakers 480 V | G | PREPA | Salinas | Aguirre Power Plant | N/A | 2022-01-28 | Federal |  | 0.35 |  | 0.31 | 2022-03-09 | Procurement |  | 2024-04-15 | 2024-06-30 |  |  | Aguirre | 2022-03-09
Travelling Screens Replacement | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-01-28 | Federal |  | 5 |  | 5 | 2022-03-09 | Procurement |  | 2025-04-01 | 09/23/226 | 50% | 2/27/25 RFP be approved by 2/13/25. 1/13/25 RFP will be submitted by 1/30/24. Contract pending need to be addressed in order to continue procurement process. Expected comencement date on 4-1-2025. With 540 days since NTP were emited. | Costa Sur | 2022-03-09
Procurement and Replacement of Regulator Valves for Boiler Feed Water Units 5 & 6 | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-01-28 | Federal |  | 0.3 | 0.3 | 0.3 | 2022-03-09 | Completed |  | 2024-07-01 | 2025-06-30 |  | Unit 5 completed. In Planning Unit 6/ Contract U6 102043. | Costa Sur | 2022-03-09
Low Pressure Water Heater 3 Repair Work | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-01-28 | Federal |  | 0.4 | 0.91 | 0.4 | 2022-03-09 | Completed |  | 2022-02-17 | 2023-11-21 | 100% |  | Costa Sur | 2022-03-09
CS 5 Major Outage Unit 5 - Boiler Sections Replacement and Repairs & Auxiliary Equipment Repairs | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-01-28 | Federal |  | 9 | 0.65 | 9 | 2022-03-09 | Procurement |  | 2023-08-01 | 2025-12-31 |  | Contracts 100997, 101262 which are two projects covered under this FEMA project. This two projects are completed. Genera is doing planning and design of specs for the procurement of auxiliary equipment, such as compressors, motors, pumps and boiler parts for this units for future replacement. | Costa Sur | 2022-03-09
Water Heater 6 Replacement Work | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-01-28 | Federal |  | 2 |  | 2 | 2022-03-09 | Planning |  | 2023-08-01 | 2025-06-30 |  | This item will be managed by CPM Major Equipment Replacement (Critical Components) | Costa Sur | 2022-03-09
Upgrade to Mark VI | G | PREPA | Cataño | Palo Seco Power Plant - units 3&4 | N/A | 2022-01-28 | Federal |  | 0.5 |  | 0.5 | 2022-03-09 | Awarded |  | 2024-05-15 | 2025-05-14 |  | Procurement working on terms & condition with GE. | Palo Seco | 2022-03-09
Replacement of Air-Preheaters Baskets, Unit 5 | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-02-08 | Federal |  | 0.7 |  | 0.7 | 2022-04-13 | Design |  | 2024-12-01 | 2025-01-12 |  | SOW to be Redefine. | Costa Sur | 2022-04-13
CS 5Major Inspection Unit 5 - HP/IP/LP Turbine Rotor Replacement | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 5 | N/A | 2022-02-08 | Federal |  | 5.9 | 13.78 | 5.9 | 2022-04-13 | Completed |  | 2024-04-01 | 6/62/24 | 100% | Project completed. Only waiting for Balance Man from MD&A and unit to be ready for start up. | Costa Sur | 2022-04-13
Caustic Soda and Acid Tanks Replacement Works | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-02-08 | Federal |  | 0.75 | 0.48 | 0.75 | 2022-04-13 | Execution |  | 2024-10-18 | 2024-12-22 | 70% | 2/5/2025 Project substantially completed. Final acceptance shall be issue on 02/07/2025. | Costa Sur | 2022-04-13
Unit 6 - HP/IP/LP Inspection (Failure) | G | PREPA | Guayanilla | Costa Sur Power Plant - unit 6 | Programmed Outage Maintenance | 2022-02-08 | NME |  | 1.06 | 0 | 1.06 | 2022-04-13 | Completed |  | 2021-10-31 | 2021-12-22 | 100% | This Project was performed under Unit 6 LP-B Installation Work (Failure). Completed | Costa Sur | 2022-04-13
Unit 6 - Major Overhaul (Steam Turbine) | G | PREPA | San Juan | San Juan Power Plant unit 6 | N/A | 2022-01-28 | Federal |  | 12.77 |  | 12.77 | 2022-03-09 | In Progress |  | 2024-09-23 | 2025-03-02 | 40% | Steam path parts in MD&A shop for repairs.. | San Juan | 2022-03-09
Steam Rotor Replacement Unit 5 & CT Repairs | G | PREPA | San Juan | San Juan Power Plant unit 5 | N/A | 2022-02-14 | Federal |  | 12.06 | 12.06 | 12.06 | 2022-04-13 | Completed |  | 2022-04-15 | 2022-06-15 | 100% |  | San Juan | 2022-04-13
LTSA SJ5 | G | PREPA | San Juan | San Juan Power Plant unit 5 | Programmed Outage Maintenance | 2022-02-14 | NME |  | 8 | 8 | 8 | 2022-04-13 | Construction |  |  |  | 40% | In use for SJ major outage. 25% | San Juan | 2022-04-13
LTSA SJ6 | G | PREPA | San Juan | San Juan Power Plant unit 6 | Programmed Outage Maintenance | 2022-02-14 | NME |  | 8 | 8 | 8 | 2022-04-13 | Construction |  |  |  | 60% | In use for SJ major outage. 25% | San Juan | 2022-04-13
Procurement of Spare Generator Breakers for Frame 5000 Hitachi Gas Turbines | G | PREPA | Hydrogas | Peakers All units | Programmed Maintenance | 2022-02-14 |  |  | 0.65 |  | 0.65 | 2022-04-13 | [6 empty] | Hydrogas | 2022-04-13
Procurement of Turbo- Compressors for Frame 5000 Gas Turbines | G | PREPA | Hydrogas | Peakers All units | Programmed Maintenance | 2022-02-14 |  |  | 7.8 |  | 7.8 | 2022-04-13 | [6 empty] | Hydrogas | 2022-04-13
Procurement of Spare Speed Reduction Gear for Frame 5000 Gas Turbines | G | PREPA | Hydrogas | Peakers All units | Programmed Maintenance | 2022-02-14 |  |  | 1.56 |  | 1.56 | 2022-04-13 | [6 empty] | Hydrogas | 2022-04-13
New Spare Three Exhaust Plenums for Frame 5000 Gas Turbines | G | PREPA | Hydrogas | Peakers All units | Programmed Maintenance | 2022-02-14 |  |  | 0.78 |  | 0.78 | 2022-04-13 | [6 empty] | Hydrogas | 2022-04-13
Procurement of Three Exhaust Gas Diffusion Ducts for Frame 5000 Gas Turbines | G | PREPA | Hydrogas | Peakers All units | Programmed Outage Maintenance | 2022-02-14 |  |  | 0.39 |  | 0.39 | 2022-04-13 | [6 empty] | Hydrogas | 2022-04-13
Major Outage Turbo - compressor (CT) 15 units | G | PREPA | Hydrogas | Peakers All units | Programmed Outage Maintenance | 2022-02-14 |  |  | 39 |  | 39 | 2022-04-13 | [6 empty] | Hydrogas | 2022-04-13
Stamp R- Mechanical Repairs Works for Boilers and Turbo Generator Contract | G | PREPA | Island wide | All Power Plants | Programmed Maintenance and Emergency Repairs | 2022-02-14 | NME |  | 1.95 | 2.93 | 1.95 | 2022-04-13 | In Progress |  | 2022-05-05 | 2024-06-30 | 75% | P3A approval. | Island wide | 2022-04-13
Hydro Blasting Service for Condenser | G | PREPA | Island wide | All Power Plants | Programmed Maintenance | 2022-02-14 | NME |  | 0.65 | 1.3 | 0.95 | 2022-07-11 | In Progress |  | 2022-03-17 | 2024-06-30 | 65% | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Interior Dry Cleaning Service for Boilers Environmental Compliance Cleaning of Boiler Interior | G | PREPA | Island wide | All Power Plants | Programmed Outage Maintenance | 2022-02-14 | NME |  | 0.85 | 0.85 | 0.85 | 2022-04-13 | In Progress |  | 2022-03-22 | 2024-06-30 | 55% | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Electrical and Instrumentation Works in Power Plants | G | PREPA | Island wide | All Power Plants | Programmed Maintenance and Emergency Repairs | 2022-02-14 | NME |  | 0.85 | 1.8 | 0.85 | 2022-04-13 | In Progress |  | 2022-04-11 | 2024-06-30 | 65% | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Procurement Acid for all power plants | G | PREPA | Island wide | All Power Plants | Programmed Maintenance | 2022-02-14 |  |  | 1 |  | 1 | 2022-04-13 | [5 empty] | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Refractory, Insulation, Stack, and Painting Application Works | G | PREPA | Island wide | All Power Plants | Programmed Maintenance and Emergency Repairs | 2022-02-14 | NME |  | 1.95 | 3.3 | 1.95 | 2022-04-13 | In Progress |  | 2022-03-23 | 2024-06-30 | 65% | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Scaffolding Inside and Outside Boilers Works | G | PREPA | Island wide | All Power Plants | Programmed Maintenance and Emergency Repairs | 2022-02-14 | NME |  | 1.99 | 4.8 | 1.99 | 2022-04-13 | In Progress |  | 2022-03-29 | 2024-06-30 | 79% | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Waste management Services contract for power plants | G | PREPA | Island wide | All Power Plants | Maintenance | 2022-02-14 |  |  | 1 |  | 1 | 2022-04-13 | [5 empty] | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Non Destructive Examinations and Inspection Services | G | PREPA | Island wide | All Power Plants | Programmed Maintenance and Emergency Repairs | 2022-02-14 | NME |  | 0.75 | 0.75 | 0.75 | 2022-04-13 | In Progress |  | 2022-06-02 | 2024-06-30 | 60% | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Inspection and Maintenance Cargo Elevator | G | PREPA | Island wide | All Power Plants | Programmed Maintenance and Emergency Repairs | 2022-02-14 | NME |  | 0.9 | 0.9 | 0.9 | 2022-04-13 | In Progress |  | 2022-03-23 | 2024-06-30 | 60% | Contract for Services Upon Request for Power Plants | Island wide | 2022-04-13
Coating application Boilers Structures and Chimneys All Power Plants | G | PREPA | Island wide | All Power Plants | Programmed Outage Maintenance | 2022-02-14 | NME |  | 3.6 |  | 3.6 | 2022-04-13 | Design |  | 2024-07-31 | 2024-06-30 |  |  | Island wide | 2022-04-13
Cooling tower Unit 10 Repairs (SJ PP) | G | PREPA | San Juan | San Juan Power Plant unit 10 | N/A | 2022-02-08 | Federal |  | 0.39 |  | 0.39 | 2022-06-04 | Design |  | 2024-07-01 | 2025-02-15 |  |  | San Juan | 2022-06-04
Structural Repairs Fuel Service Tank 10 (SJ PP) | G | PREPA | San Juan | San Juan Power Plant units 7-10 | N/A | 2022-02-02 | Federal |  | 0.65 | 0.95 | 0.65 | 2022-06-04 | Completed |  | 2022-10-17 | 2023-09-01 | 100% |  | San Juan | 2022-06-04
Unit PS 3 & 4 Refractory Insulation, Scaffolding and Painting Application Works | G | PREPA | Cataño | Palo Seco Power Plant - units 3&4 | N/A | 2022-01-25 | Federal |  | 0.7 | 1.5 | 0.7 | 2022-06-04 | In Progress |  | 2023-04-10 | 2024-06-30 |  | This is a Services Upon Request Contract based on necessities. | Palo Seco | 2022-06-04
Procurement Turning Gear Sytem Units 3&4 (PS SP) | G | PREPA | Cataño | Palo Seco Power Plant - units 3&4 | N/A | 2022-01-25 | Federal |  | 0.3 |  | 0.3 | 2022-06-04 | Procurement |  | 2024-10-01 | 2025-06-30 |  | Project has no started. The contract has been sent to the contractor for signature. The procurement department and the contractor are working on the terms and conditions agreement. | Palo Seco | 2022-06-04
Unit 4 Superheater header Num 5 Material and Installation (PS SP) | G | PREPA | Cataño | Palo Seco Power Plant - Unit 4 | N/A | 2022-01-25 | Federal |  | 2.24 |  | 2.24 | 2022-06-04 | Procurement |  | 2024-10-01 | 2025-06-30 |  | MR 871757 approved | Palo Seco | 2022-06-04
Unit 1 South Wall Boiler Tubing Replacement and Boilers repairsAguirre PP | G | PREPA | Salinas | Aguirre Power Plant unit 1 | N/A | 2022-06-24 | Federal |  | 5.98 | 5.4 | 5.98 | 2022-07-21 | Completed |  | 2022-03-28 | 2022-06-19 | 100% |  | Aguirre | 2022-07-21
PS 3 Procurement and Delivery of Water Wall Boiler Tubes and Economizer Unit PS3 | G | PREPA | Cataño | Palo Seco Power Plant - Unit 3 | N/A | 2022-06-24 | Federal |  | 4.03 | 4 | 4.03 | 2022-07-21 | Completed |  | 2022-09-22 | 2023-06-01 | 100% |  | Palo Seco | 2022-07-21
PS 3 Low Pressure Turbine Rotor Refurbished, Unit 3 | G | PREPA | Cataño | Palo Seco Power Plant - Unit 3 | N/A | 2022-06-24 | Federal |  | 3.5 | 0.7 | 3.5 | 2022-07-21 | Construction |  | 2024-01-03 | 2024-05-30 | 90% | Construction in Progress. Schedule to finish July 2024. | Palo Seco | 2022-07-21
Unit 7 Rehabilitation (Turbine) SJ PP | G | PREPA | San Juan | San Juan Power Plant unit 7 | N/A | 2022-06-24 | Federal |  | 10 | 10 | 10 | 2022-10-21 | Procurement |  | 2025-03-16 | 2025-07-20 |  | Contract under regulatory agencies aproval. | San Juan | 2022-10-21
Unit 7 Major Outage- Boiler section Replacement and Repairs & Auxiliary Equipment Inspection Work SJ PP | G | PREPA | San Juan | San Juan Power Plant unit 7 | N/A | 2022-06-24 | Federal |  | 8 | 8 | 8 | 2022-10-21 | Procurement |  | 2024-10-29 | 2025-02-28 |  | In Procurement Process PO 99910 Parts order authorized under PW 11085. Plan to perform work during the outage. | San Juan | 2022-10-21
San Juan Central Plant Unit 6: Installation of Modules D&E HRSG Unit 6 | G | PREPA | San Juan | San Juan Power Plant unit 6 | N/A | 2023-03-10 | Federal |  | 12.15 |  | 12.15 | 2023-03-20 | Procurement |  | 2024-11-01 | 2025-02-15 | 50% | In Procurement Process. Awarded. | San Juan | 2023-03-20
Mayaguez Unit 3B Gas Generators Inspections and Repairs | G | PREPA | Mayaguez | Mayaguez Power Turbines - units 3B | Programmed Outage Maintenance | 2023-06-22 | NME |  | 4.05 |  |  |  | Planning |  | 2024-05-01 | 2024-08-01 |  |  | Mayaguez | 2023-07-06
Fuel Efficiency Improvement- first group | G | Genera | Island wide | All Power Plants | N/A | 2023-10-15 | Federal |  | 106.76 | [9 empty] | Island wide | 2023-11-08
Critical components Replacements | G | Genera | Island wide | All Power Plants | N/A | 2023-10-15 | Federal |  | 127.32 |  |  |  | Procurement/Design |  |  |  | 50% | Specification Process & Procurement Process. | Island wide | 2023-11-08
Generation Fleet Battery Energy Storage System (BESS) project (430 MW) | G | Genera | Various Municipalities | All Power Plants sites | N/A | 2023-10-27 | Federal |  | 647.58 |  |  |  | Procurement |  |  |  | 70% |  | Various Municipalities | 2024-02-01
Control System Power Plant Maintenance -Generator and Technical Services | G | PREPA | Arecibo | Cambalache / All units | Programmed Maintenance | 2022-02-02 | NME |  | 2.5 | 2.5 | 2.5 | 2022-02-24 | In Progress |  | 2022-07-01 | 2024-06-30 | 75% | Central is working with this Service Contract | Cambalache | 2022-02-28
Upgrade to Foxboro Simulation System | G | PREPA | Guayanilla | Costa Sur Power Plant - units 5&6 | N/A | 2022-02-14 | Federal |  | 0.5 | 0.5 | 0.5 | 2022-04-13 | Procurement |  | 2024-10-01 | 2025-06-30 | 10% | 02/13/25 Project on execution. 2/7/25 Working on data adquisition of existing logics on DS. 1/17/25 Kickoff meeting will be ext week on 1/22/25. 12/13/24 Contract was signed. | Costa Sur | 2022-04-13
* Category | [12 empty] | ** Phase
G |  | Generation | Generation |  |  | Generation | [6 empty] | D | Design
T |  | Transmission | Transmission |  |  | Transmission | [6 empty] | P | Permitting
D |  | Distribution | Distribution |  |  | Distribution | [6 empty] | S | Auction
S |  | Substations | Substations |  |  | Substations | [6 empty] | C | Construction
H |  | Hydroelectric plants | Hydroelectric plants |  |  | Hydroelectric plants
IT |  | IT/Telecom | IT/Telecom |  |  | IT/Telecom
Edif. |  | Buildings | Buildings |  |  | Buildings
AA |  | Environmental Matters | Environmental Matters |  |  | Environmental Matters