## Sheet1
Attachment H
Genera Monthly Reporting Requirements - Generation Maintenance
Thermal Generation Facility Maintenance Report
Aguirre, Costa Sur, Palo Seco, San Juan Power Plants
Monthly Reporting
As of August 31, 2024
NO. | POWER PLANT | UNIT NUMBER | PROJECT ACTIVITY | CATEGORY | ACTIVITY BUDGET | START DATE | COMPLETION DATE | ACTIVITY STATUS - PERCENTAGE FOR COMPLETION | PROCUREMENT / BID (S) NUMBER | POC - MAINTENANCE ACTIVITY | CONTRACTOR/SUPPLIER | APPROVED FOR PAYMENT
1 | Costa Sur |  | Repair of the Water Treatment System for Water of Process | NME | 1390000 | 2024-12-01 | 2025-06-30 | PROCUREMENT |  | Operations | ICT
2 | Costa Sur |  | Water Treatment Plant Maintenance Services (Sewer and Processed Waters) | NME | 50000 | 2024-12-01 | 2025-06-30 | PROCUREMENT |  | Operations
3 | Costa Sur |  | Water Pretreatment and Treatment (DEMI) Reverse Osmosis & Electrodionization System Maintenance Services | NME | 50000 | 2024-12-01 | 2025-06-30 | PLANNING |  | Operations
4 | Costa Sur | 5 | Repair Cooling Tower Unit 5 | NME | 210565 | 2025-03-02 | 2025-04-20 | PROCUREMENT | C-106561 | Fernando Rivera | International Cooling Tower | 709959
5 | Costa Sur | 5&6 | Manufacture and Delivery of Hot Sections Baskets Unit 5&6 Air Heaters | NME | 516000 | 2024-07-01 | 2024-11-30 | PROCUREMENT | C-103707 | Operations
6 | San Juan | 5&6 | LTSA Units 5&6 | NME | 159940846 | 2024-07-01 | 2025-06-30 | EXECUTION | C-74903 | José Vázquez | MSA | 128439067.4
7 | San Juan | 6 | HRSG Hot Spots Mitigations U6 | NME | 75375 | 2024-10-03 | 2025-02-16 | PROCUREMENT |  | Operations
8 | San Juan | 5&6 | Safety Valves Rehabilitation and Certification U5-6 | NME | 49000 | 2024-10-03 | 2025-02-16 | EXECUTION |  | Operations | Ensysa
9 | San Juan | 5&6 | Upgrade Communication Profibus U5-6 | NME | 100000 | 2024-10-03 | 2025-02-16 | PROCUREMENT |  | Operations
10 | San Juan | 7-10 | Replacement Battery Banks CTGs Units 7-10 | NME | 593482.96 | 2023-05-01 | 2024-09-30 | EXECUTION | C-97839 | Darisabel Traverzo | RG Engineering | 853068
11 | San Juan |  | Water Treatment Plant Nautilus Tank # 1 and # 2 Rehabilitation & Repair | NME | 600000 | 2024-10-03 | 2025-06-30 | PLANNING |  | Operations
12 | San Juan |  | DEMI Water Treatment Resin Purchase | NME | 150000 | 2024-10-03 | 2025-06-30 | PROCUREMENT |  | Operations
13 | Palo Seco |  | WTP Acid & Soda Pumps Replacement | NME | 100000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
14 | Palo Seco | 4 | Unit #4 Economizer Water Inlet Valve | NME | 150000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
15 | Palo Seco | 3&4 | Instrumentation for Performance Test of Units 3 & 4 | NME | 600000 | 2024-07-01 | 2025-06-30 | PROCUREMENT | C-103437 | Operations |  | 152003.75
16 | Palo Seco |  | Manufacture and Delivery of a Deaerator Pump | NME | 412000 | 2024-04-01 | 2025-09-01 | EXECUTION | C-101706 | Fernando Rivera | Camfer | 114346.75
17 | Aguirre | 2 | Aguirre Unit 2 - Environmental Maintenance Project | NME | 4573694 | 2024-11-08 | 2024-12-21 | EXECUTION | C-102537 | Manuel Cortés | Astro Pak Caribe Inc.
18 | Aguirre | 1 | HP & IP Rotors Rehabilitation & Trip block & H2 seals replacement U1 | NME | 1311368 | 2024-07-01 | 2025-06-30 | COMPLETED | C-102073 | Roberto Rosario | GE Steam Power Caribe Inc. | 2198846.22
19 | Aguirre |  | Improvements to the pier and replacement of sections of lines for fuel | NME | 2504728 | 2025-01-01 | 2025-12-31 | EXECUTION | C-102348 | Manuel Cortés | CSA Artchitects Engineers | 1286122.86
20 | Aguirre |  | Generator Spare Rotor Rewind | NME | 1800000 | 2024-11-01 | 2025-12-31 |  |  | Operations | GE Steam Power Caribe Inc.
21 | Aguirre |  | Structural Rehabilitation Nautilus Water Tank, Water Treatment Plant | NME | 2504728 | 2025-01-01 | 2025-06-30 | EXECUTION | C-102348 | Manuel Cortés | CSA Artchitects Engineers | 1286122.86
22 | Aguirre | 1 | Replacement Battery Banks Units 1 | NME | 295491 | 2024-11-15 | 2025-02-28 | EXECUTION | C-100244 | Manuel Cortés | 5 Senses Solutions | 280716.15
23 | Aguirre | 2 | Replacement Battery Banks Units 2 | NME | 295491 | 2024-11-15 | 2025-01-15 | EXECUTION | C-100246 | Manuel Cortés | 5 Senses Solutions | 280716.15
24 | Aguirre |  | Manufacture and Delivery of Flow Control Valves DCV-1 | NME | 503692 | 2024-07-20 | 2025-06-30 | COMPLETED | C-102822 | Operations | Control Associates | 499942
25 | Aguirre CC | 1-4 | HGPI 1-4 (Hot Gas Inspection) | NME | 2282742 | 2024-11-03 | 2025-03-03 | PROCUREMENT | C-106760 | José Vázquez | MD&A | 637211.1
26 | Aguirre CC |  | Steam Path, Steam Pipes & Auxiliar Repair and Rehabilitation | NME | 1000000 | 2024-07-01 | 2025-06-30 | AWARDED |  | Operations
27 | Aguirre CC |  | Gas Turbine Rotor Refurbish MS7001B/AE | NME | 1094955 | 2025-02-01 | 2025-06-30 | PROCUREMENT | REQ. 285540 | José Vázquez | MD&A
28 | Aguirre | 1 or 2 | Turbine Driven Boiler Feed Pumps Bundle Acquisition | NME | 500000 |  |  | PROCUREMENT | REQ. 288015 | Carlos Negrón | Siemens
29 | Aguirre |  | Replace Cable 4/0 AWG/4.16Kv/8Kv - Bunker C SP1-1 Pumps | NME | 250000 | 2024-10-15 | 2024-12-31 | COMPLETED | C-106533 | Robert Rosario | Continental Lord | 224200
30 | Aguirre |  | Manufacture and Delivery BFWP 5,000 HP Motor | NME | 500000 |  |  | CANCELLED - TO BE FEDERAL | C-102822 |  |  | 499942
31 | Mayagüez | 2B | Reparación & Remplazo Componentes Combustores Unidad 2B | NME | 550000 | 2024-07-01 | 2025-06-30 | EXECUTION |  | Operations
32 | Mayagüez |  | Multi Media Filter Demi Plant | NME | 300000 | 2024-07-01 | 2025-06-30 | PLANNING |  | Operations
33 | Mayagüez |  | Washer RO (3) Demi Plant | NME | 40000 | 2024-07-01 | 2025-06-30 | PLANNING |  | Operations
34 | Mayagüez | 3A | Repair & Replace Combustors Components Unit 3A | NME | 550000 | 2024-07-01 | 2025-06-30 | PLANNING |  | Operations
35 | Mayagüez |  | 4 Generator (Brush) Major Inspection | NME | 1850000 | 2024-10-06 | 2025-02-28 | PROCUREMENT | C-104923 | Darisabel Traverzo | GESA
36 | Mayagüez |  | Demi Plant Services & Hydro Test | NME | 40000 | 2024-07-01 | 2025-06-30 | PLANNING |  | Operations
37 | Cambalache | 2 | Inspection C | NME | 7000000 | 2024-12-01 | 2025-06-30 | PROCUREMENT |  | José Vázquez | GE
38 | Cambalache |  | Generator Inspection & Maintenance | NME | 300000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
39 | Cambalache |  | Compressor Inspection & Maintenance | NME | 100000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
40 | Cambalache |  | Structural Rehabilitation Fuel #2 | NME | 1500000 | 2024-06-10 | 2025-06-11 | EXECUTION | C-101295 | Luis López | All Contractors | 811546.87
41 | Cambalache | 2-3 | AVR Replacement Work 2-3 | NME | 1151683 | 2022-06-30 | 2025-06-30 | EXECUTION | C-91900 | Robert Rosario | ABB | 992700
42 | Peakers |  | Fuel Nozzle Repair & Replacement Frame 5000 | NME | 150000 | 2024-07-01 | 2025-06-30 | PLANNING |  | Jaime López
43 | Peakers |  | Combustion Inspection & Repair Frame 5000 | NME | 200000 | 2024-09-01 | 2025-06-30 | PLANNING |  | Jaime López
44 | Peakers |  | Major Inspection Frame 5000 (PS1-1, PS 2-1, Jobos 1-2) | NME | 3500000 | 2024-09-01 | 2025-06-30 | PLANNING |  | Jaime López
45 | Peakers |  | Mobil Pac Borescope Inspection & Turbine Alignment (6 inspections) | NME | 870000 | 2024-07-01 | 2025-06-30 | PLANNING | C-101644 | Jaime López | Mitsubishi | 869236.71
46 | Peakers |  | Mobil Pac Annual Audit | NME | 335306 | 2024-07-01 | 2024-06-30 | PLANNING | C-101644 | Jaime López | Mitsubishi | 869236.71
47 | Aguirre |  | Auxiliary Equipment (Services and Parts) | NME | 1000000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
48 | Costa Sur |  | Auxiliary Equipment (Services and Parts) | NME | 1000000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
49 | Palo Seco |  | Auxiliary Equipment (Services and Parts) | NME | 1000000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
50 | San Juan | 6 | Replacement of the Online Condenser Cleaner Unit 6 | NME | 2394350 | 2023-03-21 | 2024-09-30 | EXECUTION | C-98349 | Luis López | RG Engineering | 2394350
51 | San Juan |  | Auxiliary Equipment (Services and Parts) | NME | 1000000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
52 | Aguirre CC |  | HMI'S Replacement | Federal |  | 2024-11-01 | 2025-04-30 | PROCUREMENT |  | José Vázquez | GE
53 | Aguirre |  | Reconstruction of the discharge channel pumping station structure | Federal | 300000 | 2025-01-01 | 2025-07-30 | PLANNING | REQ.284037 | Manuel Cortés
54 | Aguirre | 4 | FAASt Fire Protection System Rehabilitation -Design & Phase 1 (AG-004) | Federal | 175000 | 2024-03-01 | 2024-09-30 | COMPLETED | C-101960 | Luis López | BR&A | 175000
55 | Aguirre CC | 1-3 | Major inspection Unit 1-3 | Federal | 2731000 | 2024-09-16 | 2024-12-30 | EXECUTION | C-104889 | José Vázquez | RG | 196300
56 | Aguirre | 1-4 | Replacement of Load Center 1-4 Condenser Circulating Water Pump | Federal | 630000 | 2024-09-15 | 2025-06-30 | EXECUTION | C-101421 | Robert Rosario | Allied Power
57 | Aguirre | 1&2 | One New CCWP 1,000 HP Motor | Federal | 640150 |  |  | PROCUREMENT | C-105520 | Robert Rosario | Cortés Industrial
58 | Aguirre |  | 316B Traveling screen project | Federal | 5300000 | 2025-03-01 | 2026-11-21 | PROCUREMENT | C-98328 | Manuel Cortés |  | 739091.69
59 | San Juan |  | Natural Gas Manufacturing Surcharge | NME | 10000000 | 2024-07-01 | 2025-06-30 | EXECUTION |  | PMO HQ
60 | San Juan | 5 | Replacement of the Online Condenser Cleaner Unit 5 | Federal | 1117328 | 2024-10-15 | 2025-12-31 | AWARDED |  | Luis López | Malnat
61 | San Juan | 7&8 | Replacement of Two Uninterruptible Power Supply Systems for Units 7 and 8 | Federal | 739091.69 | 2023-03-15 | 2024-07-01 | CLOSED | C-98328 | Darisabel Traverzo | RG Engineering | 739091.69
62 | San Juan |  | Unit 6 - Major Overhaul (CT Repairs) | Federal | 12768425 | 2024-11-15 | 2025-03-02 | EXECUTION |  | José Vázquez | Various
63 | San Juan |  | Unit 6 - Major Overhaul (ST Repairs) | Federal | 12619593 | 2024-09-23 | 2025-03-02 | EXECUTION |  | José Vázquez | Various
64 | San Juan | 7 | SJ 7 Major overhaul | Federal | 8000000 | 2024-11-08 | 2025-02-28 | PROCUREMENT |  | Darisabel Traverzo
65 | San Juan | 7 | Unit 7 Rehabilitation ( Turbine) | Federal | 10000000 | 2025-03-16 | 2025-07-20 | PROCUREMENT | C-108148 | Darisabel Traverzo |  | 2843707.78
66 | San Juan | 5&6 | Liner Rehabilitation Fuel Service Tanks Units 5&6 | Federal | 2504728 | 2025-02-18 | 2025-08-01 | EXECUTION | C- 102348 | Fernando Rivera | CSA | 1196122.86
67 | San Juan |  | Multimedia Filters | Federal | 2567000 | 2022-03-10 | 2024-09-30 | EXECUTION | C-89638 | Luis López | Enersys | 2567000
68 | Palo Seco | 3&4 | Procurement Turning Gear System, Units 3 and 4 | Federal | 295382 | 2024-10-01 | 2025-06-30 | PROCUREMENT | C-103521 | Robert Rosario | Siemens
69 | Palo Seco | 3 | Update Voltage Regulation System Unit 3, Palo Seco Power Plant | Federal | 294082 | 2024-04-15 | 2025-03-31 | EXECUTION | C-101258 | Robert Rosario | ESI | 119103.21
70 | Palo Seco | 4 | Unit 4, Superheater Header Num. 5 Material and Installation | Federal | 2243385 | TBD | TBD | PROCUREMENT |  | Fernando Rivera
71 | Palo Seco |  | Upgrade OSI DCS | Federal | 2445496 | 2024-10-01 | 2025-06-30 | AWARDED | C- 103154 | Robert Rosario | Emerson | 733678.76
72 | Costa Sur | 5 | Unit 5 Boiler Replace and Repairs & Auxiliary Equipment Repairs | Federal | 8350545 |  |  | PROCUREMENT |  | Fernando Rivera
73 | Costa Sur | 5&6 | Procurement of BCWP 700 HP Two Spare Motors for Units 5 and 6 | Federal | 368454 | 2024-03-11 | 2024-11-07 | COMPLETED | C-101391 | Robert Rosario | ESI | 364554
74 | Costa Sur | 5 | Replacement of Excitation System Units 5 | Federal | 1583848 | 2024-09-01 | 2025-06-30 | EXECUTION | C-102867 | Robert Rosario | ESI | 791924
75 | Costa Sur |  | Replacement of Unit 5 Electric Load Center | Federal | 285000 | 2022-11-30 | 2025-06-30 | EXECUTION | C-97578 | Robert Rosario | Allied Power | 213777
76 | Costa Sur |  | Traveling Screens Replacement | Federal | 5000000 | 2025-04-01 | 2026-09-23 | PROCUREMENT |  | Manuel Cortés
77 | Costa Sur | 6-1 | CCWP 6-1 Repair Works | Federal | 300000 | 2024-11-01 | 2025-02-28 | EXECUTION | C-107189 | Darisabel Traverzo | Reliable Industrial | 75125
78 | Cambalache |  | Flood Protection Barrier | Federal | 30000000 | 2024-07-01 | 2025-06-30 | PROCUREMENT | C-102184 | Manuel Cortés | Sargent Lundy | 32336040.49
79 | Aguirre |  | ASP Phase 4 Stage 1 - Demineralized Water System (Design) | Federal | 2504728 | 2024-05-07 | 2024-11-25 | EXECUTION | C-102062 | Luis López | Integra | 2173193
80 | Aguirre |  | ASP Phase 4 Stage 2 - Advanced Water Treatment System, Pump Stations, Piping Interconnections & Integration | Federal | 784612 | 2024-10-01 | 2025-06-30 | PLANNING | C-102062 | Luis López |  | 73092.5
81 | San Juan |  | Phase IV - Advance Water Treatment System (Safbon) | Federal | 3000000 | 2023-04-25 | 2025-01-31 | EXECUTION | C-94790 | José Vázquez | Safbon | 3459463.71
82 | Costa Sur |  | Caustic Soda and Acid tanks replacement works | Federal | 521800 | 2022-10-18 | 2024-12-22 | COMPLETED | C-96561 | Greg Hernández | Alonso & Carus | 550100
83 | Costa Sur |  | Upgrade to Foxboro Simulation System | Federal | 1053215 | 2024-10-01 | 2025-06-30 | EXECUTION | C-103503 | Robert Rosario | LT Automation | 421286
84 | Aguirre-Costa Sur-Cambalache |  | Procurement of Main Power Transformers AGSP, ACC, Costa Sur, Cambalache | Federal | 29000000 |  |  | PROCUREMENT |  | PMO HQ
85 | Aguirre | 2-1&2-2 | Procurement of a Main Power Transformer Units 2-1&2-2 | Federal | 3500000 |  |  | PROCUREMENT |  | PMO HQ
86 | Aguirre |  | Procurement of Distribution Transformers ACC | Federal | 3000000 |  |  | PROCUREMENT |  | PMO HQ
87 | All Power Plants |  | BESS | Federal | FED | 2024-11-08 | 2025-06-30 |  |  | PMO HQ
88 | All Power Plants |  | Peakers | Federal | FED |  |  |  |  | PMO HQ
89 | All Power Plants |  | Critical Components | Federal | FED |  |  |  |  | PMO HQ
90 | All Power Plants |  | Fuel Efficiency | Federal | FED |  |  |  |  | PMO HQ
91 | San Juan |  | Procurement of Main Power Transformers SJSP | Federal | 12500000 |  |  | PROCUREMENT |  | PMO HQ
92 | San Juan | 7&9 | Hanger Assessment (Unit 7 & 9) | Federal | 300000 | 2024-10-03 | 2025-02-16 | PROCUREMENT | C-104735 | Darisabel Traverzo | Enersys
93 | Costa Sur | 5 | Manufacture and Delivery of Bifurcate (Boiler) Tubes Unit 5 | NME | 255110 | 2024-09-01 | 2025-05-31 | PROCUREMENT | MR-871412 | Fernando Rivera | GE | 255110
94 | Palo Seco |  | New Demi Water Tank #2 | NME | 1600000 | 2024-09-03 | 2025-09-03 | EXECUTION | C-102570 | Luis López | Alonso & Carus | 1143412.2
95 | Palo Seco |  | Replacement Multi-Media Filters WTP | NME | 739818 | 2024-03-08 | 2025-01-12 | EXECUTION | C-101296 | Luis López | EPS | 739818
96 | Aguirre CC |  | Generator Rotor Full Rewind | NME | 3275580 | 2023-05-01 | 2024-10-31 | COMPLETED | C-100239 | José Vázquez | MD&A | 3194923.41
97 | Aguirre CC | GT 2-3 | Major inspection of units GT 2-3. | NME | 6400000 | 2024-12-30 | 2025-07-31 | PROCUREMENT | REQ. 285838 | José Vázquez
98 | Aguirre CC |  | Relocate Transformer | NME | 975000 | 2024-09-15 | 2024-11-15 | EXECUTION | C-103640 | Operations | Beta Electric Corp | 1025120
99 | Mayagüez | 4A | Hot Section Inspection Unit 4A | NME | 4500000 | 2024-10-06 | 2024-11-30 | AWARDED |  | Luis López
100 | Cambalache | 2 | Purchase of Materials for Turbo Compressor Inspection C | NME | 7000000 | 2024-12-01 | 2025-12-31 | PROCUREMENT |  | José Vázquez
101 | Temp Pwr/ SJ |  | O&M - Temporary Power (TM 2500) | NME | 1820000 | 2024-07-01 | 2025-06-30 | EXECUTION |  | Operations
102 | System |  | Manufacture & Delivery Traveling Screen | NME | 1000000 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | PMO HQ
103 | System |  | Unexpected Maintenance/Emergency Blackstart System list | NME | 10134913 | 2024-07-01 | 2025-06-30 | PROCUREMENT |  | Operations
104 | Aguirre |  | One BFWP 5,000 HP Spare Motor | Federal | 1560000 |  |  | PROCUREMENT |  | Robert Rosario
105 | Costa Sur | 5&6 | Procurement of CCWP 1,000 HP Two Spare Motors for Units 5 and 6 | Federal | 1365868 |  |  | PROCUREMENT | CR-252638 | Robert Rosario
|  | **** | NME MAINTENANCE ACTIVITY COULD INCLUDE DIFERENT CONTRACTS | [5 empty] | C- CONTRACT
REQ. - REQUISITION
MR- MATERIAL REQUEST
106 | Aguirre CC |  | Manufacture and Delivery of 2 Breakers 245kV | NME | 250000 | 2024-09-30 | 2026-03-31 | PROCUREMENT | REQ. 285101 | Robert Rosario
107 | Palo Seco |  | Upgrade to Mark VI | Federal | 500000 | 2024-10-01 | 2025-06-30 | PROCUREMENT | C-103504 | Robert Rosario | GE Caribe
108 | Palo Seco |  | Conversion Tanque R3 | Federal | 3057000 | 2022-09-12 | 2024-12-30 | EXECUTION | C-94699 | Manuel Cortés | Homeca | 2755649.1