## Summary
Summary for Q4 - FY2025 Report:
| FY2025 Q4 Miles |  |  | FY2025 YTD Miles |  |  | FY2025 Q4 Acres* |  |  | FY2025 YTD Acres*
Voltage | Federally Funded Clearing** | OpEx Maintenance | Total Miles | Federally Funded Clearing** | OpEx Maintenance | Total Miles | Federally Funded Clearing** | OpEx Maintenance | Total Acres | Federally Funded Clearing** | OpEx Maintenance | Total Acres
Distribution | 36.6 | 231 | 267.6 | 105.6 | 730 | 835.6 | 53.2364 | 336 | 389.2364 | 153.6 | 1061.8182 | 1215.4182
38 kV | 0 | 14 | 14 | 0 | 76 | 76 | 0 | 42.4242 | 42.4242 | 0 | 230.303 | 230.303
115 kV | 0 | 144 | 144 | 0 | 497 | 497 | 0 | 1745.4545 | 1745.4545 | 0 | 6024.2424 | 6024.2424
230 kV | 0 | 50 | 50 | 0 | 308 | 308 | 0 | 606.0606 | 606.0606 | 0 | 3733.3333 | 3733.3333
Total | 36.6 | 439 | 475.6 | 105.6 | 1611 | 1716.6 | 53.2364 | 2729.9394 | 2783.1758 | 153.6 | 11049.697 | 11203.297
*To calculate acres from miles, the miles are converted to feet by multiplying by 5,280. Then the width of the right of way is assumed for each voltage level (distribution = 12’, 38 kV = 25’, and 115 & 230 kV = 100’). The miles (in feet) are multiplied by the ROW width (in feet) to determine the square feet completed. Finally, the square feet are converted to acres by dividing by 43,560 sq feet per acre. Note: Figures may not add up due to rounding. **For federally funded miles and acres, the figure includes both completed work and miles assessed as clear spans.
Vegetation Management Progress Report

## Primary Transmission Lines
etro
Primary Transmission Lines
Line Voltage (kV) | Transmission Lines ID # | Impacted Zone1 | Circuit Miles Maintained / Cleared | # of Towers / Poles Impacted | Urban or Rural Site | Right of Way (ROWs) Width | ROW Acres Maintained / Cleared | Name of Contractor | Resources Assigned & Their Clasifications (Luma Employees and Contractors) | Type of Response2 | Type of VM Implemented 3 | Type of VM Disposal Clasification4 | Recommendations for Future VM5 | VM Activity Point of Contact (POC) | Funding Source
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Wright Tree Service |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | Wright Tree Service |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Wright Tree Service |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Wright Tree Service |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Wright Tree Service |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3300 | Wire/Border/Strike | 0.09 | 3 | Urban | 25 | 0.27273 | Wright Tree Service |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 7100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 7100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 7100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 1.08 | 6 | Rural | 100 | 13.0909 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 1.62 | 9 | Rural | 100 | 19.6364 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.72 | 4 | Rural | 100 | 8.7273 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.72 | 4 | Rural | 100 | 8.7273 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 1.08 | 6 | Rural | 100 | 13.0909 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 3.6 | 20 | Rural | 100 | 43.6364 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 3.6 | 20 | Rural | 100 | 43.6364 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 50900 | Wire/Border/Strike | 1.26 | 7 | Rural | 100 | 15.2727 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 50900 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 1.44 | 8 | Rural | 100 | 17.4545 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 1.44 | 8 | Rural | 100 | 17.4545 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 4.86 | 27 | Rural | 100 | 58.9091 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 4.86 | 27 | Rural | 100 | 58.9091 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 5.94 | 33 | Rural | 100 | 72 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 5.94 | 33 | Rural | 100 | 72 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 1.98 | 11 | Rural | 100 | 24 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 1.98 | 11 | Rural | 100 | 24 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 2.34 | 13 | Rural | 100 | 28.3636 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 1.8 | 10 | Rural | 100 | 21.8182 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 2.16 | 12 | Rural | 100 | 26.1818 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 1.98 | 11 | Rural | 100 | 24 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 9 | 50 | Rural | 100 | 109.0909 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 1.8 | 10 | Rural | 100 | 21.8182 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 2.88 | 16 | Rural | 100 | 34.9091 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 2.16 | 12 | Rural | 100 | 26.1818 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 1.44 | 8 | Rural | 100 | 17.4545 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100-7700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100-7700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100-7700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.9 | 5 | Rural | 100 | 10.9091 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.72 | 4 | Rural | 100 | 8.7273 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2700 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300/1400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300/1400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300/1400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300/1400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300/1400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300/1400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300/1400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.09 | 3 | Urban | 25 | 0.27273 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.54 | 3 | Rural | 100 | 6.5455 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.3636 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 1.44 | 8 | Rural | 100 | 17.4545 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 1.08 | 6 | Rural | 100 | 13.0909 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 1.44 | 8 | Rural | 100 | 17.4545 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 1.08 | 6 | Rural | 100 | 13.0909 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18182 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.090909 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.17 | 5.6667 | Urban | 25 | 0.51515 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.17 | 5.6667 | Urban | 25 | 0.51515 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.48 | 16 | Urban | 25 | 1.4545 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.48 | 16 | Urban | 25 | 1.4545 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.54 | 18 | Urban | 25 | 1.6364 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.54 | 18 | Urban | 25 | 1.6364 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.43 | 14.3333 | Urban | 25 | 1.303 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.43 | 14.3333 | Urban | 25 | 1.303 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.09 | 3 | Urban | 25 | 0.27273 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.09 | 3 | Urban | 25 | 0.27273 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
|  | Total | 207.42 |  |  |  | 2389.2727
1 IMPACTED ZONE - WIRE ZONE, BORDER ZONE, STRIKE ZONE
2 TYPE OF RESPONSE - REACTIVE, CORRECTIVE, PREVENTIVE
3 TYPE OF VM IMPLEMENTED - BIOLOGICAL, PHYSICAL OR CHEMICAL CONTROL
4 TYPE OF VM DISPOSAL CLASIFICATION - CHIP & HAUL, CHIP & BLOW, PILE / WINDROW, LOP & SCATTER, MULCHIN
5 RECOMMENDATIONS FOR FUTURE Describe recommended species, cadence of any herbicide application
Vegetation Management Progress Report Q4 FY2025

## Substations
Substations
Substations ID | Primary Voltages | Secondary Voltages | KVA | Maintained Area | Urban or Rural Site | Municipalities Impacted | Name of Contractor | Resources Assigned & Their Classifications (LUMA Employees and Contractors) | Type of Response1 | Type of VM Implemented2 | Type of VM Disposal Clasification3 | Recomendations for Future VM4 | VM Activity Point of Contact (POC) | Funding Source | Photos Before/After
1403/1404 | 115000 | 38000 | 60/80/100/112 MVA | 0.33 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp |  | Federal PA Obligated Funds
VIEQUES CABLE TAKE OFF -MOD | 13000 | 480 | 2.5KVA | 0.05 | Urban | Vieques | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp |  | Nonfederal Funds
VIEQUES CABLE TERMINAL | 13000 | 480 | 2.5KVA | 0.05 | Urban | Vieques | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp |  | Operation Exp
VIEQUES-CULEBRA TAKE-OFF | 13000 | 480 | 2.5KVA | 0.07 | Urban | Vieques | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
ZONA LIBRE | 13000 | 480 | 2.5KVA | 0.35 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2602/2603 | 230000 | 13200 | 75/100/125 MVA | 2.42 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2906 | 115000 | 4800 | 5000/6250 | 0.58 | Urban | Yabucoa | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1520 | 38000 | 4160 | 7500/11300 | 0.25 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1802 | 38000 | 4800 | 5000/6250 | 0.16 | Urban | Catano | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3016 | 115000 | 4800 | 5000/6250 | 0.74 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3005 | 38000 | 4800 | 5000/6250 | 0.12 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3010 | 38000 | 4800 | 5000/6250 | 0.73 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3013 | 38000 | 4800 | 5000/6250 | 0.55 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2604 | 115000 | 4800 | 5000/6250 | 2.48 | Urban | Yabucoa | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3007/3015 | 230000 | 13200 | 75/100/125 MVA | 0.37 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3014 | 38000 | 4800 | 5000/6250 | 0.5 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9203/9207 | 230000 | 13200 | 75/100/125 MVA | 1.25 | Urban | Dorado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9001/9003/9004 | 230000 | 13200 | 75/100/125 MVA | 1.15 | Urban | Vega Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3301 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | San Lorenzo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3101 | 38000 | 4800 | 5000/6250 | 0.13 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3102 | 38000 | 4800 | 5000/6250 | 0.18 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3701 | 38000 | 8320 | 7500 | 0.19 | Urban | Aguas Buenas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3202 | 38000 | 4800 | 5000/6250 | 0.14 | Urban | Juncos | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3103 | 38000 | 4800 | 5000/6250 | 0.49 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3601 | 38000 | 4800 | 5000/6250 | 0.24 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3302 | 38000 | 4800 | 5000/6250 | 0.38 | Urban | San Lorenzo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8301/8302 | 230000 | 13200 | 75/100/125 MVA | 0.6 | Urban | Jayuya | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3602 | 38000 | 8320 | 7500 | 0.6 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3603/3604 | 230000 | 13200 | 75/100/125 MVA | 0.33 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1718 | 38000 | 4800 | 5000/6250 | 1.1 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6004 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.2 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AES Power Plant | 230000 | 13200 | 75/100/125 MVA | 3.3 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4006 | 38000 | 8320 | 7500 | 0.74 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1717 | 38000 | 4800 | 5000/6250 | 0.51 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1709/1720 | 115000 | 38000 | 60/80/100/112 MVA | 0.78 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6015 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.41 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6008 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.49 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4001 | 38000 | 8320 | 7500 | 0.5 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3403 | 38000 | 4800 | 5000/6250 | 0.02 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4101 | 38000 | 8320 | 7500 | 0.22 | Urban | Arroyo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3405 | 38000 | 4800 | 5000/6250 | 0.15 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2302 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2306 | 38000 | 4800 | 5000/6250 | 0.2 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2301 | 38000 | 4800 | 5000/6250 | 0.17 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6102 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.19 | Urban | Anasco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1713 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.62 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1801 | 38000 | 4800 | 5000/6250 | 0.52 | Urban | Catano | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1803 | 38000 | 4800 | 5000/6250 | 0.44 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1907/1909 | 115000 | 38000 | 60/80/100/112 MVA | 0.58 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1901/1904 | 115000 | 38000 | 60/80/100/112 MVA | 0.26 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9901 | 38000 | 4160 | 5000/5600/7500 | 0.06 | Urban | Orocovis | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9902 | 38000 | 13200 | 12/16/20/22.4 MVA | 0.16 | Urban | Orocovis | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9801/9802 | 230000 | 13200 | 75/100/125 MVA | 0.23 | Urban | Naranjito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5902 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.18 | Urban | Villalba | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5901 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Villalba | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4602 | 38000 | 8320 | 7500 | 0.25 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4603 | 38000 | 8320 | 7500 | 0.19 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4601 | 38000 | 8320 | 7500 | 0.21 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4401 | 38000 | 8320 | 7500 | 0.23 | Urban | Santa Isabel | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5817 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.27 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5801 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.29 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1607 | 38000 | 4160 | 7500/11300 | 0.31 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5802 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.39 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5805 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.03 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5804 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.04 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2401 | 38000 | 4800 | 5000/6250 | 0.23 | Urban | Canovanas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2403 | 38000 | 4800 | 5000/6250 | 0.32 | Urban | Loiza | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
JUANA DIAZ TC | 115000 | 38000 | 30/40/50/56 MVA | 1.6 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9403/9405 | 230000 | 13200 | 75/100/125 MVA | 0.68 | Urban | Toa Alta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5013 | 38000 | 8320 | 7500 | 0.12 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5803 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.28 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
CULEBRA CABLE TERMINAL | 115000 | 38000 | 30/40/50/56 MVA | 0.05 | Urban | Culebra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6501 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.31 | Urban | Sabana Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6404 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.59 | Urban | San German | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6401 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.39 | Urban | San German | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6406 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.36 | Urban | San German | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6005 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.03 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AQUIRRE CC | 230000 | 13200 | 75/100/125 MVA | 2.44 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2305 | 38000 | 4800 | 5000/6250 | 0.89 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2901 | 38000 | 4800 | 5000/6250 | 0.17 | Urban | Yabucoa | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AGUIRRE 230kV switchyard | 230000 | 13200 | 75/100/125 MVA | 1.46 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4503 | 38000 | 8320 | 7500 | 0.09 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4504 | 38000 | 8320 | 7500 | 0.17 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
Horizon SY | 115000 | 38000 | 30/40/50/56 MVA | 0.38 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4502 | 38000 | 8320 | 7500 | 0.23 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4501 | 38000 | 8320 | 7500 | 0.22 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5005 | 38000 | 8320 | 7500 | 0.37 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AGUIRRE 115kV switchyard | 230000 | 13200 | 75/100/125 MVA | 2.71 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1806 | 38000 | 4800 | 5000/6250 | 2.81 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5006/5009 | 230000 | 13200 | 75/100/125 MVA | 0.27 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5012 | 38000 | 8320 | 7500 | 0.31 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5021 | 38000 | 8320 | 7500 | 0.09 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1100/1115 | #N/A | #N/A | #N/A | 1.16 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1908 | 38000 | 4800 | 5000/6250 | 1.65 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5001/5011 | 230000 | 13200 | 75/100/125 MVA | 2.23 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4201 | 38000 | 8320 | 7500 | 0.21 | Urban | Patillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
MAUNABO TC | 115000 | 38000 | 30/40/50/56 MVA | 0.82 | Urban | Maunabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5007 | 38000 | 8320 | 7500 | 0.38 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5003/5004 | 230000 | 13200 | 75/100/125 MVA | 0.78 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4301 | 38000 | 8320 | 7500 | 0.15 | Urban | Maunabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5019 | 38000 | 8320 | 7500 | 0.15 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5008 | 38000 | 8320 | 7500 | 0.14 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5016 | 38000 | 8320 | 7500 | 0.5 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2803 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Naguabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
PUNTA LIMA T.O. | 13000 | 480 | 2.5KVA | 0.05 | Urban | Naguabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2801 | 38000 | 4800 | 5000/6250 | 0.24 | Urban | Las Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5403 | 38000 | 8320 | 7500 | 0.15 | Urban | Penuelas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5402 | 38000 | 8320 | 7500 | 0.36 | Urban | Penuelas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2201 | 38000 | 4800 | 5000/6250 | 0.24 | Urban | Luquillo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2605 | 38000 | 4800 | 5000/6250 | 0.23 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2006 | 38000 | 4800 | 5000/6250 | 0.54 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5401 | 38000 | 8320 | 7500 | 0.26 | Urban | Penuelas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4002 | 38000 | 8320 | 7500 | 0.18 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5808 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.26 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6801/6802 | 230000 | 13200 | 75/100/125 MVA | 1.95 | Urban | Hormigueros | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3401 | 38000 | 4800 | 5000/6250 | 1.89 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3406/3402 | #N/A | 13200 | 75/100/125 MVA | 0.44 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
COSTA SUR 115kV | 115000 | 38000 | 30/40/50/56 MVA | 2.52 | Urban | Guayanilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3501 | 38000 | 4800 | 5000/6250 | 0.09 | Urban | Aibonito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3502 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Aibonito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
COSTA SUR 230kV | 115000 | 38000 | 30/40/50/56 MVA | 2.56 | Urban | Guayanilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6702 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.28 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6705 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9605 | 38000 | 4160 | 7500/11300 | 0.11 | Urban | Barranquitas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6704 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.24 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9703 | 38000 | 4160 | 7500/11300 | 0.18 | Urban | Comerio | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
COMERIO TC | 115000 | 38000 | 30/40/50/56 MVA | 1.82 | Urban | Comerio | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2003 | 38000 | 4800 | 5000/6250 | 0.13 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2002 | 38000 | 4800 | 5000/6250 | 0.08 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2001/2005 | 115000 | 38000 | 60/80/100/112 MVA | 0.92 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3870 | 38000 | 8320 | 7500 | 0.05 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2601 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9601/9602 | 230000 | 13200 | 75/100/125 MVA | 1.67 | Urban | Barranquitas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2101 | 38000 | 4800 | 5000/6250 | 2.02 | Urban | Ceiba | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4402 | 38000 | 8320 | 7500 | 1.34 | Urban | Santa Isabel | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1330/1346 | 115000 | 38000 | 60/80/100/112 MVA | 2.48 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2501 | 38000 | 4800 | 5000/6250 | 0.51 | Urban | Vieques | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2525 | 38000 | 4800 | 5000/6250 | 0.85 | Urban | Vieques | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3801 | 38000 | 8320 | 7500 | 0.24 | Urban | Culebra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1343 | 38000 | 4160 | 7500/11300 | 0.28 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
PATTERN | 13000 | 480 | 2.5KVA | 0.41 | Urban | Santa Isabel | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
|  |  | Total | 85.51
1 TYPE OF RESPONSE - REACTIVE, CORRECTIVE, PREVENTIVE
2 TYPE OF VM IMPLEMENTED - BIOLOGICAL, PHYSICAL OR CHEMICAL CONTROL
3 TYPE OF VM DISPOSAL CLASIFICATION - CHIP & HAUL, CHIP & BLOW, PILE / WINDROW, LOP & SCATTER, MULCHIN
4 RECOMMENDATIONS FOR FUTURE VM - Describe recommended species, cadence of any herbicide application
Vegetation Management Progress Report Q4 FY2025

## Distribution Lines
Distribution Lines
Line Voltage (kV) | Primary Distribution Line ID # | Impacted Zone1 | Circuit Miles Maintained / Cleared | # of Poles Impacted | Urban or Rural Site | Municipalities Impacted | Right of Way (Rows) Width | Name of Contractor | Resources Assigned & Their Clasifications (Luma Employees and Contractors) | Type of Response2 | Type of VM Implemented 3 | Type of VM Disposal Clasification4 | Recommendations for Future VM5 | Luma Labor Required | VM Activity Point of Contact (POC) | Funding Source | Photos Before/After
4.16 | 8203-02 | Wire Zone / Border Zone | 1.7 | 56.6667 | Urban | Adjuntas | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp |  | Federal PA Obligated Funds
4.16 | 7403-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Camuy | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp |  | Nonfederal Funds
4.16 | 8104-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp |  | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9003-06 | Wire Zone / Border Zone | 0.06 | 2 | Urban | VegaBaja | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8103-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8602-03 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Arecibo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9105-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | VegaAlta | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8405-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Manati | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 8010-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Camuy | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8011-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8602-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Florida | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-05 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | Utuado | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 8010-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Arecibo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9103-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Vega Alta | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8005-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8701-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Ciales | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Utuado | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8015-09 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Arecibo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8203-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-04 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8701-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ciales | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-05 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 8010-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8203-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8401-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Manati | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8203-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8701-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Ciales | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9003-06 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Manati | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8001-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Hatillo | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | Jayuya | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 8007-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Arecibo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9003-06 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Manati | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Utuado | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-05 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9003-06 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Vega Baja | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 8010-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 8010-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8401-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Manati | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 8010-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8005-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Ciales | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8203-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8014-06 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arecibo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Vega Alta | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8103-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Camuy | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Vega Baja | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8203-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8701-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Ciales | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-08 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Vega Baja | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7402-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Camuy | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8013-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hatillo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8008-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8504-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | BARCELONETA | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | HATILLO | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | VEGA ALTA | 10 |  |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | MOROVIS | 10 |  |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | JAYUYA | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | ADJUNTAS | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | HATILLO | 10 |  |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | UTUADO | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8405-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | MANATI | 10 |  |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | JAYUYA | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8005-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | ARECIBO | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | ARECIBO | 10 |  |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | HATILLO | 10 |  |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | UTUADO | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7601-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | CAMUY | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | UTUADO | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | JAYUYA | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8202-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | ADJUNTAS | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.51 | 17 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9201-02 | Wire Zone / Border Zone | 0.99 | 33 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 2.98 | 99.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.08 | 36 | Urban | BARCELONETA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9201-02 | Wire Zone / Border Zone | 1.34 | 44.6667 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 1.82 | 60.6667 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.14 | 38 | Urban | BARCELONETA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9201-02 | Wire Zone / Border Zone | 1.59 | 53 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 0.82 | 27.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.08 | 36 | Urban | BARCELONETA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9201-02 | Wire Zone / Border Zone | 1.31 | 43.6667 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 1.42 | 47.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.08 | 36 | Urban | BARCELONETA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9201-02 | Wire Zone / Border Zone | 0.63 | 21 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 2.53 | 84.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | MANATI | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9201-02 | Wire Zone / Border Zone | 1.62 | 54 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 1.14 | 38 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 0.99 | 33 | Urban | MANATI | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 2.02 | 67.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.02 | 34 | Urban | MANATI | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.51 | 17 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.82 | 27.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 1.56 | 52 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.22 | 40.6667 | Urban | MANATI | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9004-10 | Wire Zone / Border Zone | 1.28 | 42.6667 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.05 | 35 | Urban | MANATI | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | SAN JUAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.54 | 18 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.28 | 42.6667 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.14 | 38 | Urban | MANATI | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.85 | 28.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8501-02 | Wire Zone / Border Zone | 1.05 | 35 | Urban | MANATI | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.85 | 28.3333 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 1.14 | 38 | Urban | MANATI | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.51 | 17 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | MANATI | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1710-05 | Wire Zone / Border Zone | 4.09 | 136.3333 | Urban | Toa Alta | 10 |  |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1343-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guaynabo | 10 |  |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9501-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Corozal | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9403-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1706-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1707-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Naranjito | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1707-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1707-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1710-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1705-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1525-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guaynabo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1806-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Toa Baja | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1903-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guaynabo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1717-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9501-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Corozal | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1907-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1705-02 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Corozal | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9605-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9403-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Corozal | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9502-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9503-06 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1717-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9403-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1710-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1707-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1903-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1707-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1717-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1734-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Dorado | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9202-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Catano | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1801-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Corozal | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9503-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9403-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1706-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Naranjito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9801-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1719-15 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1714-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Catano | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1801-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guaynabo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9403-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1717-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Dorado | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1704-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1707-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1529-12 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1719-15 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1710-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1714-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Catano | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1801-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Naranjito | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9801-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1707-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guaynabo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.68 | 22.6667 | Urban | GUAYNABO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.45 | 15 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | GUAYNABO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.51 | 17 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | GUAYNABO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.57 | 19 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.57 | 19 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.63 | 21 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.63 | 21 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.51 | 17 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.77 | 25.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.6 | 20 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.68 | 22.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.85 | 28.3333 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1705-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1705-02 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1705-02 | Wire Zone / Border Zone | 0.54 | 18 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1705-02 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.74 | 24.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.6 | 20 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.85 | 28.3333 | Urban | GUAYNABO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1901-04 | Wire Zone / Border Zone | 0.8 | 26.6667 | Urban | GUAYNABO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1705-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | BAYAMON | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1705-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | BAYAMON | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3502-02 | Wire Zone / Border Zone | 4.69 | 156.3333 | Urban | QUEBRADILLAS | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3008-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | QUEBRADILLAS | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2601-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | VEGA ALTA | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2601-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | VEGA BAJA | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-07 / 3601-04 | Wire Zone / Border Zone | 0.6 | 20 | Urban | SAN JUAN | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2803--02 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | TOA BAJA | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | CAROLINA | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2901-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | GUAYNABO | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | CAROLINA | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 2901-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | GUAYNABO | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3301-01 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | SAN JUAN | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2601-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | TOA BAJA | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | GUAYNABO | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | GUAYNABO | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3009-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | SAN JUAN | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | GUAYNABO | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3009-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | SAN JUAN | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | TRUJILLO ALTO | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2603-09 | Wire Zone / Border Zone | 0.06 | 2 | Urban | SAN JUAN | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 6.82 | 227.3333 | Urban | SAN JUAN | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 2901-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | SAN JUAN | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2801-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | GUAYNABO | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3502-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | SAN JUAN | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3014-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | BAYAMON | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3205-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | GUAYNABO | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | GUAYNABO | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | GUAYNABO | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3103-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | GUAYNABO | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2602-02 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | SAN JUAN | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3301-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | TRUJILLO ALTO | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3601-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | BAYAMON | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9602-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | SAN JUAN | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2906-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | BAYAMON | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-02 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | BAYAMON | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3009-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | SAN JUAN | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3007-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | GUAYNABO | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | SAN JUAN | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | BAYAMON | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3205-07 | Wire Zone / Border Zone | 0.09 | 3 | Urban | GUAYNABO | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2602-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | GUAYNABO | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | SAN JUAN | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2601-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | SAN JUAN | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Aguas Buenas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3005-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2803-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Humacao | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2801-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Humacao | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3302-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2906-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yabucoa | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2906-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yabucoa | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2702-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Naguabo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3004-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3005-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3302-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3402-05 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Cayey | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3004-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3007-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3103-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9601-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Barranquitas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3302-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Juncos | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3202-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Juncos | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3009-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Gurabo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Gurabo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3014-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Caguas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3004-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3004-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3405-03 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | Cayey | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3007-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1205-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2701-02 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | Naguabo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3406-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3009-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3604-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguas Buenas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3601-02 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | Comerio | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2101-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Naguabo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3103-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3008-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9601-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Barranquitas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3004-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2901-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yabucoa | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3302-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2603-08 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Las Piedras | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Gurabo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aibonito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Naguabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3004-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3005-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3302-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3004-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3401-01 | Wire Zone / Border Zone | 0.6 | 20 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3402-05 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3401-01 | Wire Zone / Border Zone | 0.63 | 21 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3402-05 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3101-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3402-05 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3401-01 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3401-01 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3402-05 | Wire Zone / Border Zone | 0.6 | 20 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3401-01 | Wire Zone / Border Zone | 0.82 | 27.3333 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3501-01 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | AIBONITO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3101-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3402-05 | Wire Zone / Border Zone | 0.51 | 17 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3402-05 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3402-05 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3402-05 | Wire Zone / Border Zone | 0.45 | 15 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3401-01 | Wire Zone / Border Zone | 0.48 | 16 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-07 | Wire Zone / Border Zone | 0.48 | 16 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | AIBONITO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3101-02 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3401-01 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | AIBONITO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3604-07 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3405-03 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3402-05 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-07 | Wire Zone / Border Zone | 0.51 | 17 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.54 | 18 | Urban | AIBONITO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-07 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | GURABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3604-07 | Wire Zone / Border Zone | 0.45 | 15 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3604-07 | Wire Zone / Border Zone | 0.48 | 16 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | AIBONITO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3401-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | JUNCOS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-07 | Wire Zone / Border Zone | 0.06 | 2 | Urban | CANOVANAS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3402-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3101-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.51 | 17 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-07 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3405-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | TOA BAJA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3402-05 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3402-05 | Wire Zone / Border Zone | 0.54 | 18 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3604-07 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3405-03 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3101-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | CAGUAS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3401-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | JUNCOS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7503-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6801-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7502-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7805-11 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7104-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6014-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7502-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7104-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7503-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7802-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6101-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7902-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6010-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6406-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cabo Rojo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6801-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Hormigueros | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6801-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6101-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Añasco | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6401-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7101-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7403-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7901-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7802-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7012-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Aguadilla | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-08 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Moca | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 7008-08 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Aguadilla | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6802-05 | Wire Zone / Border Zone | 1.08 | 36 | Urban | Cabo Rojo | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7301-04 | Wire Zone / Border Zone | 1.7 | 56.6667 | Urban | Rincon | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6702-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6406-04 | Wire Zone / Border Zone | 1.99 | 66.3333 | Urban | San German | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6101-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Añasco | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6401-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6305-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Maricao | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 7903-07 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7003-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7004-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8010-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-08 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6101-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6101-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6305-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maricao | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6401-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7103-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7103-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7805-13 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7303-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7003-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguadilla | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7012-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6201-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7903-06 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | Lares | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7201-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7005-03 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Aguadilla | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7301-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Rincon | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6201-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 7303-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-08 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7901-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6705-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7502-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7011-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6801-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Hormigueros | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6101-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Añasco | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Mayaguez | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6401-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7004-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7302-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Rincon | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6001-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7502-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7103-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Moca | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7103-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Moca | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7902-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 7802-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7011-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguadilla | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6702-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cabo Rojo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7012-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7303-02 | Wire Zone / Border Zone | 1.53 | 51 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.65 | 21.6667 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6303-01 | Wire Zone / Border Zone | 0.54 | 18 | Urban | MAYAGÜEZ | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.11 | 37 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7303-02 | Wire Zone / Border Zone | 0.74 | 24.6667 | Urban | CABO ROJO | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN SEBASTIAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6303-01 | Wire Zone / Border Zone | 1.51 | 50.3333 | Urban | TOA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.65 | 21.6667 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6303-01 | Wire Zone / Border Zone | 2.27 | 75.6667 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7303-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 7901-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6703-01 | Wire Zone / Border Zone | 1.7 | 56.6667 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 1.53 | 51 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.05 | 35 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 1.79 | 59.6667 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.54 | 18 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 1.16 | 38.6667 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7801-01 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | CAMUY | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 7901-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6703-01 | Wire Zone / Border Zone | 2.24 | 74.6667 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.05 | 35 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 1.42 | 47.3333 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.99 | 33 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 1.28 | 42.6667 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 1.05 | 35 | Urban | SAN JUAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 1.28 | 42.6667 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.08 | 36 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 0.51 | 17 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-03 | Wire Zone / Border Zone | 1.45 | 48.3333 | Urban | CAGUAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 0.8 | 26.6667 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-03 | Wire Zone / Border Zone | 2.36 | 78.6667 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.11 | 37 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.19 | 39.6667 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-03 | Wire Zone / Border Zone | 1.65 | 55 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-03 | Wire Zone / Border Zone | 2.1 | 70 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.82 | 27.3333 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5007-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5802-02 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5302-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Yauco | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6601-03 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | Lajas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5007-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Patillas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4501-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Salinas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4504-03 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Salinas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6601-03 | Wire Zone / Border Zone | 0.54 | 18 | Urban | Lajas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5804-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5501-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guayanilla | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5302-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5007-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Ponce | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5804-02 | Wire Zone / Border Zone | 0.48 | 16 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-04 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Yauco | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Sabana Grande | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5001-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4402-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Coamo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guayama | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5501-03 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | Guayanilla | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5002-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4602-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Coamo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4504-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Salinas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5501-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Guayanilla | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5005-03 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5001-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Sabana Grande | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | Patillas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4301-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Maunabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6406-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Sabana Grande | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5803-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Juana Diaz | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Ponce | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-02 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | Sabana Grande | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Sabana Grande | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4504-02 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | Salinas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5501-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-04 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Sabana Grande | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Patillas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4101-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Arroyo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5304-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Yauco | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Guayama | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5018-03 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4501-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Salinas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-02 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | Sabana Grande | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6601-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Lajas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5302-04 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Patillas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5002-04 | Wire Zone / Border Zone | 0.82 | 27.3333 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Guayama | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5016-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4101-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arroyo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5802-04 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Juana Diaz | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5302-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5004-07 | Wire Zone / Border Zone | 0.43 | 14.3333 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5004-07 | Wire Zone / Border Zone | 0.63 | 21 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4201-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | PATILLAS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5004-07 | Wire Zone / Border Zone | 0.09 | 3 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | PATILLAS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.68 | 22.6667 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5805-01 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | JUANA DIAZ | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5004-07 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.57 | 19 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.6 | 20 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | PATILLAS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5301-01 | Wire Zone / Border Zone | 0.82 | 27.3333 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-02 | Wire Zone / Border Zone | 0.45 | 15 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.65 | 21.6667 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5805-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | JUANA DIAZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1335-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1421-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1301-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2101-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1334-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Ceiba | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1416-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1519-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1346-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1520-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1423-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1531-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3014-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1414-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1301-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1301-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2002-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1118-09 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Luquillo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1328-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2101-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Rio Grande | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1530-09 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Fajardo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1525-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3014-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2101-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Carolina | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1329-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Ceiba | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1205-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Trujillo Alto | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 5.11 | 170.3333 | Urban | Trujilo Alto | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 4.12 | 137.3333 | Urban | Carolina | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1620-05 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1421-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3014-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1342-02/1901-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1342-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1531-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2404-08 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1620-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1908-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1334-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Canovanas | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2404-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1335-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Carolina | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1421-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1520-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-04 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1114-01/1133-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Carolina | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1620-01/1336-07 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Trujillo Alto | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.01 | 0.33333 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1421-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Fajardo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2001-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1526-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ceiba | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2101-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 2404-08 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1421-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1422-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1336-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Carolina | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.01 | 0.33333 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3014-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1342-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1602-03 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | LUQUILLO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 2201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | LUQUILLO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1602-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 2201-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | CEIBA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5805-2 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3008-04 High | Wire Zone / Border Zone | 3.78 | 126 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6004-02 High | Wire Zone / Border Zone | 0.22 | 7 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5003-02 High | Wire Zone / Border Zone | 1.9 | 63 | Urban | Ponce A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6001-01 High | Wire Zone / Border Zone | 1.21 | 40 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6002-03 High | Wire Zone / Border Zone | 0.4 | 13 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6001-05 High | Wire Zone / Border Zone | 1.16 | 39 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8003-03 High | Wire Zone / Border Zone | 0.61 | 20 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6003-03 High | Wire Zone / Border Zone | 1.29 | 43 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7802-01 High | Wire Zone / Border Zone | 0.55 | 18 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8401-04 High | Wire Zone / Border Zone | 0.64 | 21 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6002-04 High | Wire Zone / Border Zone | 0.83 | 28 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6001-02 High | Wire Zone / Border Zone | 1.29 | 43 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7802-03 High | Wire Zone / Border Zone | 0.64 | 21 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7801-01 High | Wire Zone / Border Zone | 2.61 | 87 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 7012-02 High | Wire Zone / Border Zone | 1.52 | 51 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 6201-02 High | Wire Zone / Border Zone | 1.38 | 46 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8015-07 High | Wire Zone / Border Zone | 1.43 | 48 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 6201-01 High | Wire Zone / Border Zone | 0.59 | 20 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8014-07 High | Wire Zone / Border Zone | 1.21 | 40 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7504-01 High | Wire Zone / Border Zone | 1.81 | 60 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 6201-03 High | Wire Zone / Border Zone | 0.31 | 10 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 7903-07 High | Wire Zone / Border Zone | 2.59 | 86 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8103-02 High | Wire Zone / Border Zone | 0.77 | 26 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 3601-04 High | Wire Zone / Border Zone | 2.04 | 68 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 9605-02 High | Wire Zone / Border Zone | 1.62 | 54 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 3008-03 High | Wire Zone / Border Zone | 1.55 | 52 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 3401-02 High | Wire Zone / Border Zone | 0.66 | 22 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7701-04 High | Wire Zone / Border Zone | 0.33 | 11 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8014-06 High | Wire Zone / Border Zone | 1.73 | 58 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
|  | Total | 267.34
1 IMPACTED ZONE - REMOVAL/REDUCTION ZONE, EDGE ZONE, STRIKE ZONE
2 TYPE OF RESPONSE - REACTIVE, CORRECTIVE, PREVENTIVE
3 TYPE OF VM IMPLEMENTED - BIOLOGICAL, PHYSICAL OR CHEMICAL CONTROL
4 TYPE OF VM DISPOSAL CLASIFICATION - CHIP & HAUL, CHIP & BLOW, PILE / WINDROW, LOP & SCATTER, MULCHIN
5 RECOMMENDATIONS FOR FUTURE VM - Describe recommended species, cadence of any herbicide application
Vegetation Management Progress Report Q4 FY2025