## LUMA - Annex A
[13 empty] | Note: 1 For Non-Federally Funded projects, the “Estimated Cost ($)” column reflects the estimated Total Cost of the Project as part of the Long-Term Investment Plan estimates and for Federally Funded projects, the “Estimated Cost ($)” column reflects the obligated amount approved by FEMA. 2 The “Cost ($)” column reflects either the estimated cost of the Initial Scope of Work approved by the Energy Bureau for Federally-Funded projects, or, for Non-Federally Funded projects, the funding allocated to the project in the current Fiscal Year Budget approved by the Energy Bureau. 3The "Starting Date" refers to the date the project received a FAASt number for federally funded projects and for non-federally funded projects, it refers to the date a budget is assigned in LUMA's Oracle Accounting System. 4For federally funded projects, completion dates reflect all field activities that must be completed before a project can effectively be closed out and are aligned with the % complete. The energized column does not imply overall project completion. | Control Center & Buildings | FF | Federally Funded | Initiation
NEPR-MI-2024-0001 | [13 empty] | Customer Experience | NFF | Non-Federally Funded | Plan
PREB Approved Investments as of: | [13 empty] | Distribution |  |  | Design
2025-06-30 | [13 empty] | Enabling |  |  | Execution
[14 empty] | Substations |  |  | Close Out
Support Services
|  |  |  | Funding |  | PREB's Approval Date |  | Project Phase | [5 empty] | Transmission
Unique ID (FAASt No. or Project ID) | Project Title | Portfolio* | Improvement Program | Source** | Estimated Cost ($M)1 | Cost ($M)2 | Date | Phase*** | Starting Date3 | Completion Date4 | Energized4 | % Complete4
PBCS4.01 | Wheeling | Customer Experience | Retail Wheeling | NFC | 49.299 | 3 | 2024-06-26 | Initiation | 2024-07-01 | 2029-12-31 | N/A | 0%
PBFM1.169576 | FAASt Arecibo Regional Office Building (Building) | Control Center & Buildings | Facilities Development & Implementation | FF | Pending Obligation | 1.8 | 2021-06-08 | Plan | 2021-01-29 | Pending Obligation | Pending Obligation | 0%
PBFM1.169798 | FAASt Arecibo Electric Service Center (Building) | Control Center & Buildings | Facilities Development & Implementation | FF | Pending Obligation | 2.32 | 2021-06-08 | Plan | 2021-02-01 | Pending Obligation | Pending Obligation | 0%
PBFM1.551247 | FAASt [Palo Seco South Building Repairs] (Building) | Control Center & Buildings | Facilities Development & Implementation | FF | Pending Obligation | 11.17 | 2021-10-14 | Plan | 2021-12-16 | Pending Obligation | Pending Obligation | 0%
PBIT1.551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | 7.6 | 30 | 2021-09-22 | Execution | 2021-12-22 | 2025-12-26 | No | 2%
PBIT1.551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Design | 2021-12-22 | Pending Obligation | Pending Obligation | 0%
PBIT1.551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Design | 2021-12-22 | Pending Obligation | Pending Obligation | 0%
PBIT1.551963 | FAASt [Transport Network] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 185 | 2021-09-22 | Design | 2021-12-22 | Pending Obligation | Pending Obligation | 0%
PBIT1.662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 6 | 2021-09-22 | Design | 2022-02-14 | Pending Obligation | Pending Obligation | 0%
PBIT1.673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 96.5 | 2021-09-22 | Design | 2022-05-17 | Pending Obligation | Pending Obligation | 0%
PBIT1.675345 | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 35.7 | 2022-08-25 | Design | 2022-06-14 | Pending Obligation | Pending Obligation | 0%
PBIT1.675406 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 46.2 | 2021-09-22 | Plan | 2022-06-15 | Pending Obligation | Pending Obligation | 0%
PBIT1.678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Design | 2022-07-22 | Pending Obligation | Pending Obligation | 0%
PBIT1.679006 | FAASt [Test and Technology Laboratory] (Building) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 11.88 | 2022-07-11 | Design | 2022-07-26 | Pending Obligation | Pending Obligation | 0%
PBIT1.679035 | FAASt [Telecom Infrastructure – Group A] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Plan | 2022-07-27 | Pending Obligation | Pending Obligation | 0%
PBIT1.682331 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Plan | 2022-09-12 | Pending Obligation | Pending Obligation | 0%
PBIT1.704805 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Plan | 2023-02-02 | Pending Obligation | Pending Obligation | 0%
PBIT1.744072 | FAASt [IT OT Technology Systems Reparations] Group 2 (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2022-08-25 | Plan | 2024-02-09 | Pending Obligation | Pending Obligation | 0%
PBIT1.746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 146 | 2024-05-07 | Design | 2024-04-04 | Pending Obligation | Pending Obligation | 0%
PBIT1.753301 | FAASt [Telecom Infrastructure Group H] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Plan | 2024-08-15 | Pending Obligation | Pending Obligation | 0%
PBIT1.753302 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Plan | 2024-08-15 | Pending Obligation | Pending Obligation | 0%
PBIT2.668665 | FAASt [Cybersecurity Program Implementation] (Telecommunication) | Support Services | IT OT Cybersecurity Program | FF | Pending Obligation | 24.5 | 2022-03-15 | Design | 2022-03-30 | Pending Obligation | Pending Obligation | 0%
PBOP7.723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 18.1 | 1200 | 2023-05-05 | Execution | 2023-06-26 | 2024-12-31 | No | 10%
PBOP7.727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727530 | FAASt [Region 6 -Ponce Group C] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727540 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727558 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727562 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | Pending Obligation | Pending Obligation | 0%
PBOP7.727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-04 | Pending Obligation | Pending Obligation | 0%
PBOP7.727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-04 | Pending Obligation | Pending Obligation | 0%
PBOP7.727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-04 | Pending Obligation | Pending Obligation | 0%
PBOP7.727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-04 | Pending Obligation | Pending Obligation | 0%
PBOP7.727694 | FAASt [Region 4 -Caguas Group C] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-04 | Pending Obligation | Pending Obligation | 0%
PBOP7.728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-17 | Pending Obligation | Pending Obligation | 0%
PBOP7.728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-17 | Pending Obligation | Pending Obligation | 0%
PBOP7.740406 | FAASt [Region 1-San Juan Group B] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-08 | Pending Obligation | Pending Obligation | 0%
PBOP7.740408 | FAASt [Region 3-Bayamon Group B] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-08 | Pending Obligation | Pending Obligation | 0%
PBOP7.740409 | FAASt [Region 4-Caguas Group B] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-08 | Pending Obligation | Pending Obligation | 0%
PBOP7.740410 | FAASt [Region 2-Arecibo Group B] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-08 | Pending Obligation | Pending Obligation | 0%
PBOP7.740411 | FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-08 | Pending Obligation | Pending Obligation | 0%
PBOP7.740414 | FAASt [Region 6-Ponce Group B] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-08 | Pending Obligation | Pending Obligation | 0%
PBOP7.741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | Pending Obligation | Pending Obligation | 0%
PBOP7.741098 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | Pending Obligation | Pending Obligation | 0%
PBOP7.741100 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | Pending Obligation | Pending Obligation | 0%
PBOP7.741101 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | Pending Obligation | Pending Obligation | 0%
PBOP7.741102 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | Pending Obligation | Pending Obligation | 0%
PBOP7.741104 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | Pending Obligation | Pending Obligation | 0%
PBOP7.741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | Pending Obligation | Pending Obligation | 0%
PBOP7.750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | Pending Obligation | Pending Obligation | 0%
PBUT1.04 | Fire Mitigation | Enabling | Compliance and Studies | NFC | 6.32 | 1.96 | 2024-06-26 | Execution | 2024-07-01 | 2025-06-30 | N/A | 75%
PBUT13.01 | Capital Work Trans PoleReplace | Transmission | Transmission Priority Pole Replacements | NFC | 5 | 5 | 2024-06-26 | Execution | 2021-10-01 | 2025-06-30 | N/A | 99%
PBUT13.334468 | FAASt [Transmission Priority Pole Replacements – Line 2200] (Transmission) | Transmission | Transmission Line Rebuild | FF | 1.22 | Program Cost Included in PBUT13.681672 | 2021-08-20 | Close Out | 2021-09-10 | 2024-11-13 | No | 100%
PBUT13.550896 | FAASt [Transmission Priority Pole Replacements – Line 6700] (Transmission) | Transmission | Transmission Line Rebuild | FF | 0.69 | Program Cost Included in PBUT13.681672 | 2021-10-18 | Close Out | 2021-12-14 | 2024-06-17 | Yes | 100%
PBUT13.668583 | FAASt [Transmission Priority Pole Replacements – Line 13300] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.45 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Close Out | 2022-03-29 | 2024-06-17 | Yes | 100%
PBUT13.668592 | FAASt [Transmission Priority Pole Replacement – Line 9800] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.42 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Close Out | 2022-03-29 | 2024-01-05 | Yes | 100%
PBUT13.681672 | FAASt Transmission Priority Pole Replacements –38kV Line 2300 (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.22 | 378.8 | 2021-09-22 | Close Out | 2022-08-31 | 2024-06-17 | Yes | 100%
PBUT13.708637 | FAASt [T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.37 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-03-03 | 2024-12-18 | No | 40%
PBUT13.711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.12 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-03-31 | 2024-11-12 | No | 98%
PBUT13.711819 | FAASt [TL 13400 TC-San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2023-04-03 | Pending Obligation | Pending Obligation | 0%
PBUT13.712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.631 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-04-04 | 2025-01-20 | No | 35%
PBUT13.750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-06-20 | Pending Obligation | Pending Obligation | 0%
PBUT13.750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-06-20 | Pending Obligation | Pending Obligation | 0%
PBUT13.750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-06-20 | Pending Obligation | Pending Obligation | 0%
PBUT13.753781 | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-08-23 | Pending Obligation | Pending Obligation | 0%
PBUT13.753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-08-23 | Pending Obligation | Pending Obligation | 0%
PBUT13.753785 | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-08-23 | Pending Obligation | Pending Obligation | 0%
PBUT13.753786 | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-08-23 | Pending Obligation | Pending Obligation | 0%
PBUT13.753787 | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-08-23 | Pending Obligation | Pending Obligation | 0%
PBUT13.753788 | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-08-23 | Pending Obligation | Pending Obligation | 0%
PBUT17.01 | TWACS Subst.Comm.Eq.Hardw.Upgr | Customer Experience | Meter Replacement & Maintenance | NFC | 7.4 | 1.6 | 2024-06-26 | Execution | 2021-07-01 | 2030-07-01 | N/A | 95%
PBUT17.02 | Non-NEM Meter Replacement | Customer Experience | Meter Replacement & Maintenance | NFC | 3 | 2.5 | 2024-06-26 | Execution | 2021-07-01 | 2033-07-01 | N/A | 45%
PBUT17.03 | New Connections | Customer Experience | Meter Replacement & Maintenance | NFC | 27.031 | 3.73 | 2024-06-26 | Execution | 2023-07-01 | 2033-07-01 | N/A | 45%
PBUT17.04 | Net Metering Meter change | Customer Experience | Meter Replacement & Maintenance | NFC | 33.51 | 7.5 | 2024-06-26 | Execution | 2023-07-01 | 2033-07-01 | N/A | 45%
PBUT18.549764 | FAASt [Physical Security - Group 2] (Substation) | Substation | Substation Security | FF | 2.38 | 53.8 | 2021-10-18 | Design | 2021-12-03 | 2025-06-13 | No | 0%
PBUT18.550910 | FAASt [Physical Security - Group 1] (Substation) | Substation | Substation Security | FF | 6.69 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2021-12-14 | 2025-02-28 | No | 55%
PBUT18.551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Security | FF | 4.13 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2021-12-21 | 2025-06-20 | No | 25%
PBUT18.660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Security | FF | 3.82 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Design | 2022-01-27 | 2025-08-08 | No | 0%
PBUT22.657300 | FAASt [ENERGY MANAGEMENT SYSTEM (EMS)] (Telecommunication) | Control Center & Buildings | Critical Energy Management System Upgrades | FF | 48.94 | 126 | 2021-09-22 | Execution | 2022-01-19 | 2026-03-30 | No | 41%
PBUT29.01 | Meter Test Boards | Customer Experience | Standardized Metering & Meter Shop Setup | NFC | 1.92 | 0.19 | 2024-06-26 | Execution | 2021-08-01 | 2026-06-01 | N/A | 95%
PBUT30.334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.39 | 600 | 2021-08-20 | Execution | 2021-09-08 | 2025-01-31 | Yes | 89%
PBUT30.334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.38 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-08 | 2024-12-31 | Yes | 96%
PBUT30.334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.12 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-10 | 2025-02-28 | Yes | 93%
PBUT30.542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2021-10-26 | 2024-12-31 | Yes | 97%
PBUT30.673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.37 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2024-12-31 | No | 94%
PBUT30.673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 4.12 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2025-04-16 | No | 80%
PBUT30.673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2025-05-26 | No | 59%
PBUT30.673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 4.43 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2025-07-10 | No | 87%
PBUT30.673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.79 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2025-01-14 | No | 85%
PBUT30.673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.79 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2025-02-28 | No | 91%
PBUT30.673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.75 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2025-02-28 | No | 94%
PBUT30.673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.36 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2025-02-28 | Yes | 92%
PBUT30.673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-05-25 | 2023-09-05 | Yes | 100%
PBUT30.673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.13 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2025-01-31 | No | 89%
PBUT30.673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.39 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2025-04-30 | No | 83%
PBUT30.673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2025-04-30 | No | 34%
PBUT30.673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2025-02-28 | No | 53%
PBUT30.674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2024-12-03 | No | 97%
PBUT30.674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2025-03-30 | No | 85%
PBUT30.674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.7 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2025-01-15 | No | 97%
PBUT30.674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.53 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2025-06-30 | No | 76%
PBUT30.674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2024-12-30 | No | 86%
PBUT30.674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-05-27 | 2023-05-04 | Yes | 100%
PBUT30.678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-26 | 2025-01-31 | No | 78%
PBUT30.678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.12 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-26 | 2025-01-31 | No | 96%
PBUT30.679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2025-05-31 | No | 48%
PBUT30.679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.59 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2025-08-31 | No | 78%
PBUT30.679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.91 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2024-12-31 | Yes | 99%
PBUT30.679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.22 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2024-12-31 | Yes | 97%
PBUT30.679133 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.02 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2022-07-28 | 2025-06-30 | No | 0%
PBUT30.679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.56 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2025-01-31 | Yes | 96%
PBUT30.679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.16 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2025-01-31 | Yes | 97%
PBUT30.679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.22 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2025-01-31 | Yes | 97%
PBUT30.679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.75 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-08-03 | 2025-01-31 | No | 93%
PBUT30.679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.59 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-08-03 | 2024-12-31 | Yes | 98%
PBUT30.682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.54 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-06 | 2025-06-30 | No | 62%
PBUT30.682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.63 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-06 | 2025-06-30 | No | 20%
PBUT30.682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.69 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-07 | 2025-02-28 | No | 92%
PBUT30.682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.57 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-07 | 2025-02-28 | No | 94%
PBUT30.682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.27 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2025-02-28 | Yes | 92%
PBUT30.682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole and Conductor Repair | FF | 0.26 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2025-02-28 | No | 79%
PBUT30.682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2025-04-11 | No | 49%
PBUT30.682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2025-03-31 | Yes | 89%
PBUT30.682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.95 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2025-02-12 | No | 92%
PBUT30.682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.71 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-12 | 2025-03-30 | No | 86%
PBUT30.682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-09-12 | 2023-10-27 | Yes | 100%
PBUT30.682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2025-03-31 | No | 80%
PBUT30.682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2025-02-21 | No | 99%
PBUT30.682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.66 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2025-03-04 | No | 91%
PBUT30.682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.61 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2025-01-31 | Yes | 97%
PBUT30.682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.74 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2025-01-31 | No | 92%
PBUT30.682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.62 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2025-01-31 | Yes | 97%
PBUT30.685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.67 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-11 | 2025-01-31 | Yes | 96%
PBUT30.685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-10-12 | 2023-11-01 | Yes | 100%
PBUT30.685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-13 | 2025-03-31 | No | 80%
PBUT30.685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.32 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-18 | 2024-12-31 | Yes | 98%
PBUT30.686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-10-20 | 2023-07-18 | Yes | 100%
PBUT30.686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.32 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-20 | 2024-12-31 | Yes | 96%
PBUT30.686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.63 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-20 | 2025-02-28 | No | 92%
PBUT30.688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Close Out | 2022-11-02 | 2023-10-27 | Yes | 100%
PBUT30.688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.56 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-02 | 2025-01-17 | Yes | 96%
PBUT30.688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-03 | 2025-01-31 | Yes | 95%
PBUT30.688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.18 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-04 | 2025-04-30 | No | 85%
PBUT30.688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.9 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2024-12-31 | Yes | 96%
PBUT30.688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.38 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2025-01-31 | No | 84%
PBUT30.688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.13 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-07 | 2025-01-31 | No | 97%
PBUT30.688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-07 | 2025-03-31 | No | 49%
PBUT30.688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.54 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2025-03-31 | No | 86%
PBUT30.689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-11-09 | 2023-10-25 | Yes | 100%
PBUT30.691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.25 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-28 | 2025-04-18 | No | 83%
PBUT30.701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-01-03 | 2023-10-31 | Yes | 100%
PBUT30.701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.19 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-01-03 | 2023-10-25 | Yes | 100%
PBUT30.701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.62 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2025-01-31 | Yes | 93%
PBUT30.701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2024-12-31 | Yes | 99%
PBUT30.701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.65 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2025-02-28 | No | 86%
PBUT30.701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-04 | 2025-03-27 | No | 58%
PBUT30.704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.58 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2025-04-30 | No | 87%
PBUT30.704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.44 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2025-04-30 | No | 90%
PBUT30.704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.52 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2025-01-31 | No | 91%
PBUT30.704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2025-01-31 | No | 93%
PBUT30.704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-03 | 2025-01-31 | Yes | 90%
PBUT30.704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.43 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-03 | 2025-07-08 | No | 44%
PBUT30.705503 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-02-08 | Pending Obligation | Pending Obligation | 0%
PBUT30.705527 | FAASt [Distribution Pole and Conductor Repair – San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-08 | 2025-08-18 | No | 50%
PBUT30.705584 | FAASt [Pole and Conductor Repair - Ponce Groups 14 & 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.84 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-09 | 2025-07-31 | No | 90%
PBUT30.708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.15 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-03 | 2025-07-31 | No | 88%
PBUT30.710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 7.2 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-20 | 2025-06-05 17:00 | No | 6%
PBUT30.710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-03-20 | Pending Obligation | Pending Obligation | 0%
PBUT30.710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-20 | 2025-01-31 | Yes | 99%
PBUT30.711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 11.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-03 | 2025-12-31 | No | 45%
PBUT30.711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.5 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-03 | 2025-06-06 | No | 91%
PBUT30.712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.8 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-04-04 | 2025-06-06 | No | 0%
PBUT30.738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-11-15 | Pending Obligation | Pending Obligation | 0%
PBUT30.738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-11-15 | 2025-10-15 | No | 0%
PBUT30.738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 10.6 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-11-15 | 2025-10-15 | No | 0%
PBUT30.738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-11-15 | Pending Obligation | Pending Obligation | 0%
PBUT30.738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2023-11-15 | Pending Obligation | Pending Obligation | 0%
PBUT30.738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2023-11-17 | Pending Obligation | Pending Obligation | 0%
PBUT30.742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2024-01-04 | 2025-08-31 | No | 83%
PBUT30.742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.6 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2024-01-05 | 2025-11-28 | No | 74%
PBUT30.749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2024-06-05 | Pending Obligation | Pending Obligation | 0%
PBUT30.749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2024-06-05 | Pending Obligation | Pending Obligation | 0%
PBUT30.750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2024-07-02 | Pending Obligation | Pending Obligation | 0%
PBUT30.752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2024-08-01 | Pending Obligation | Pending Obligation | 0%
PBUT30.757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2024-10-01 | Pending Obligation | Pending Obligation | 0%
PBUT30.759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2024-10-10 | Pending Obligation | Pending Obligation | 0%
PBUT30.759051 | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2024-10-11 | Pending Obligation | Pending Obligation | 0%
PBUT33.01 | Line40600 Baymn-Monac(UG Loop) | Transmission | Transmission Line Rebuild | NFC | 0.8625 | 0.86 | 2024-06-26 | Plan | 2022-07-01 | 2026-06-30 | N/A | 0%
PBUT33.165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 73.06 | 2021-06-08 | Design | 2020-12-18 | Pending Obligation | Pending Obligation | 0%
PBUT33.166707 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 24.84 | 2021-06-08 | Design | 2021-01-06 | Pending Obligation | Pending Obligation | 0%
PBUT33.166860 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 49.51 | 2021-06-08 | Design | 2021-01-07 | Pending Obligation | Pending Obligation | 0%
PBUT33.166904 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 32.4 | 2021-06-08 | Design | 2021-01-07 | Pending Obligation | Pending Obligation | 0%
PBUT33.167168 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 87.59 | 2021-06-08 | Design | 2021-01-11 | Pending Obligation | Pending Obligation | 0%
PBUT33.167443 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 40.69 | 2021-06-08 | Design | 2021-01-13 | Pending Obligation | Pending Obligation | 0%
PBUT33.167446 | FAASt - Line 36100 (115kV) - Dos Bocas HP to Monacillos TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 109.97 | 2021-06-08 | Design | 2021-01-13 | Pending Obligation | Pending Obligation | 0%
PBUT33.167508 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 41.39 | 2021-06-08 | Design | 2021-01-13 | Pending Obligation | Pending Obligation | 0%
PBUT33.168226 | FAASt San Juan 115kV Underground Transmission Loop (Transmission) | Transmission | Transmission Line Rebuild | FF | 14.75 | 11.6 | 2021-06-08 | Design | 2021-01-20 | 2027-02-08 | No | 0%
PBUT33.168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 83.26 | 2021-06-08 | Design | 2021-01-22 | Pending Obligation | Pending Obligation | 0%
PBUT33.176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 6.71 | 2021-06-08 | Design | 2021-03-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 3.58 | 2021-06-08 | Design | 2021-03-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 8.07 | 2021-06-08 | Design | 2021-03-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 25.28 | 2021-06-08 | Design | 2021-03-24 | Pending Obligation | Pending Obligation | 0%
PBUT33.177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 9.7 | 2021-06-08 | Design | 2021-03-24 | Pending Obligation | Pending Obligation | 0%
PBUT33.180052 | FAASt Ponce TC to Jobos TC - 38kV 100 & 200 (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 87.28 | 2021-06-08 | Design | 2021-04-14 | Pending Obligation | Pending Obligation | 0%
PBUT33.180326 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 56.13 | 2021-06-08 | Design | 2021-04-16 | Pending Obligation | Pending Obligation | 0%
PBUT33.334331 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 51.2 | 2021-08-20 | Design | 2021-09-08 | Pending Obligation | Pending Obligation | 0%
PBUT33.334470 | FAASt [Line 3100 Monacillos TC to Daguao TC] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 113.33 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT33.547160 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 55.37 | 2021-10-18 | Plan | 2021-11-15 | Pending Obligation | Pending Obligation | 0%
PBUT33.547226 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 13.81 | 2021-10-18 | Plan | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT33.547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 21.47 | 2021-10-18 | Plan | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT33.547259 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 41.27 | 2021-09-22 | Design | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT33.547269 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 3.14 | 2021-09-22 | Design | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT33.547350 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 5.39 | 2021-09-22 | Plan | 2021-11-17 | Pending Obligation | Pending Obligation | 0%
PBUT33.548598 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 44.31 | 2021-10-18 | Design | 2021-12-01 | Pending Obligation | Pending Obligation | 0%
PBUT33.550019 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 10.11 | 2021-10-18 | Design | 2021-12-07 | Pending Obligation | Pending Obligation | 0%
PBUT33.550902 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 2.32 | 2021-10-18 | Plan | 2021-12-14 | Pending Obligation | Pending Obligation | 0%
PBUT33.551067 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 3.79 | 2021-10-18 | Plan | 2021-12-15 | Pending Obligation | Pending Obligation | 0%
PBUT33.551911 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 5.05 | 2021-10-18 | Plan | 2021-12-21 | Pending Obligation | Pending Obligation | 0%
PBUT33.715610 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 78.3 | 2023-02-22 | Design | 2023-04-28 | Pending Obligation | Pending Obligation | 0%
PBUT33.718951 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 161.13 | 2023-05-05 | Design | 2023-05-11 | Pending Obligation | Pending Obligation | 0%
PBUT33.718955 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 279.24 | 2023-05-05 | Design | 2023-05-11 | Pending Obligation | Pending Obligation | 0%
PBUT33.718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 173.63 | 2023-05-05 | Design | 2023-05-11 | Pending Obligation | Pending Obligation | 0%
PBUT33.730657 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 103.81 | 2021-08-20 | Plan | 2023-09-08 | Pending Obligation | Pending Obligation | 0%
PBUT33.750729 | FAASt [Transmission Line 3700 GOAB 3797 to Arroyo Substation 4101] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 2 | 2024-05-07 | Plan | 2024-07-02 | Pending Obligation | Pending Obligation | 0%
PBUT33.750730 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 36.5 | 2021-08-20 | Plan | 2024-07-02 | Pending Obligation | Pending Obligation | 0%
PBUT33.752039 | FAASt [Transmission Line 10000 Sierra Linda TO to Magnolia TO] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 7 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752041 | FAASt [Transmission Line 1000 Venezuela Sect to Capuchinos Sect] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 7.7 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752047 | FAASt [Transmission Line 3300 Chardon Sect to Egozcue Sect] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 6.9 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752048 | FAASt [Transmission Line 3500 Las Lomas Sect to Monacillos TC] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 8.1 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752049 | FAASt [Transmission Line 5600 Hotel Rincon to Rincon Substation7301] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 5.1 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752050 | FAASt [Transmission Line 9300 Gautier Benitez Sect to ACB 9323] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 20.3 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752051 | FAASt [Transmission Line 9300 Juncos TC to ACB 9301] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 16.2 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752052 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 32.1 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.752053 | FAASt [Transmission Line 13400 Boqueron TO to Acacias TC] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 33.3 | 2024-05-07 | Plan | 2024-07-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.753777 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 58.6 | 2021-10-18 | Plan | 2024-08-23 | Pending Obligation | Pending Obligation | 0%
PBUT33.756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 40.1 | 2024-08-22 | Design | 2024-09-25 | Pending Obligation | Pending Obligation | 0%
PBUT33.756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 36.5 | 2024-08-22 | Design | 2024-09-25 | Pending Obligation | Pending Obligation | 0%
PBUT36.714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Customer Experience | AMI Implementation Program | FF | 873.85 | 780 | 2023-04-05 | Design | 2023-04-20 | 2027-12-20 | No | 0%
PBUT37.748180 | FAASt [Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC)] (Telecommunication) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | 49.7 | 2024-03-27 | Design | 2024-05-09 | Pending Obligation | Pending Obligation | 0%
PBUT4.07 | Optical Sensors | Distribution | Distribution Automation | NFC | 2.999 | 2.2 | 2024-06-26 | Execution | 2025-01-09 | 2026-06-30 | N/A | 40%
PBUT4.688623 | FAASt [Automation Program Group 1] Group 1A-8 Feeders (TL/Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | 230.37 | 2022-08-25 | Design | 2022-11-07 | Pending Obligation | Pending Obligation | 0%
PBUT4.705657 | FAASt [Automation Program Group 3] (TL/Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2023-02-09 | Pending Obligation | Pending Obligation | 0%
PBUT4.740662 | FAASt [Automation Program Group 2] (TL/ Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2023-12-11 | Pending Obligation | Pending Obligation | 0%
PBUT4.741678 | FAASt [Automation Program Group 4: San Juan/ Bayamón] (TL/Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2023-12-22 | Pending Obligation | Pending Obligation | 0%
PBUT4.745851 | FAASt [Automation Program Group 11: DAR - BAYAMON 1901, 1907 - FY24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-03-22 | Pending Obligation | Pending Obligation | 0%
PBUT4.745852 | FAASt [Automation Program Group 13: DAR – ARECIBO 8010- 8013, 8015- FY24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-03-22 | Pending Obligation | Pending Obligation | 0%
PBUT4.745854 | FAASt [ Automation Program Group 9: DAR - BAYAMON 1703, 1704 -FY24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-03-22 | Pending Obligation | Pending Obligation | 0%
PBUT4.745856 | FAASt [Automation Program Group 14 DAR ARECIBO 8404- FY24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-03-22 | Pending Obligation | Pending Obligation | 0%
PBUT4.745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Distribution | Distribution Automation | FF | 0.46 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-03-22 | 2024-10-24 | No | 50%
PBUT4.745861 | FAASt [Automation Program Group 12: DAR – ARECIBO 7402, 7403, 7702 FY24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-03-22 | Pending Obligation | Pending Obligation | 0%
PBUT4.745871 | FAASt [Automation Program Group 10: DAR - BAYAMON 1717, 9503 -FY24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-03-22 | Pending Obligation | Pending Obligation | 0%
PBUT4.746309 | FAASt [Automation Program Group 30- DAR – Bayamon 9203 - FY24] (TL/Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-04-02 | Pending Obligation | Pending Obligation | 0%
PBUT4.749124 | FAASt [Automation Program Group 7- DAR - BAYAMON 1709, 1719 - FY24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-06-05 | Pending Obligation | Pending Obligation | 0%
PBUT4.752500 | FAASt [Automation Program Group 1B-6 Feeders] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-08-01 | Pending Obligation | Pending Obligation | 0%
PBUT4.752502 | FAASt [Automation Program Group 1C-7 Feeders] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-08-01 | Pending Obligation | Pending Obligation | 0%
PBUT4.752503 | FAASt [Automation Program Group 1D-7 Feeders] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-08-01 | Pending Obligation | Pending Obligation | 0%
PBUT4.752808 | FAASt [Automation Program Group 19: Arecibo] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-08-07 | Pending Obligation | Pending Obligation | 0%
PBUT4.752810 | FAASt [Automation Program Group 20: Caguas] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-08-07 | Pending Obligation | Pending Obligation | 0%
PBUT4.755211 | FAASt [Automation Program Group 15] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-05 | Pending Obligation | Pending Obligation | 0%
PBUT4.757662 | FAASt [Automation Program Group 21] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757687 | FAASt [Automation Program Group 22] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757689 | FAASt [Automation Program Group 24] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757692 | FAASt [Automation Program Group 26] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757694 | FAASt [Automation Program Group 27] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757696 | FAASt [Automation Program Group 31] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757697 | FAASt [Automation Program Group 32] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757698 | FAASt [Automation Program Group 33] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757699 | FAASt [Automation Program Group 34] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.757700 | FAASt [Automation Program Group 35] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-09-27 | Pending Obligation | Pending Obligation | 0%
PBUT4.800286 | FAASt [Automation Program Group 36] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-12-30 | Pending Obligation | Pending Obligation | 0%
PBUT4.800361 | FAASt [Automation Program Group 37] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-12-31 | Pending Obligation | Pending Obligation | 0%
PBUT4.800369 | FAASt [Automation Program Group 38] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-12-31 | Pending Obligation | Pending Obligation | 0%
PBUT4.800394 | FAASt [Automation Program Group 39] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-12-31 | Pending Obligation | Pending Obligation | 0%
PBUT4.800399 | FAASt [Automation Program Group 40] (Distribution) | Distribution | Distribution Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-12-31 | Pending Obligation | Pending Obligation | 0%
PBUT5.542517 | FAASt [Luquillo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.81 | 1220 | 2021-09-22 | Execution | 2021-10-25 | 2025-02-03 | No | 86%
PBUT5.542687 | FAASt [Lajas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2025-09-29 | No | 92%
PBUT5.542688 | FAASt [Aguada Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 18.57 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2025-12-23 | No | 83%
PBUT5.542690 | FAASt [Maunabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 6.44 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2025-01-27 | No | 96%
PBUT5.542756 | FAASt [Guánica Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.06 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2025-06-18 | No | 86%
PBUT5.659623 | FAASt [Cataño Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 17.56 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-20 | 2025-04-02 | No | 57%
PBUT5.659625 | FAASt [Dorado Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 24.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-20 | 2025-06-30 | No | 76%
PBUT5.659715 | FAASt [Aibonito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 7.25 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-21 | 2025-04-11 | No | 88%
PBUT5.659968 | FAASt [San Germán Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 34.88 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-24 | 2027-09-24 | No | 49%
PBUT5.660227 | FAASt [Hatillo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 20.33 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-26 | 2026-08-04 | No | 68%
PBUT5.660239 | FAASt [Villalba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.87 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-26 | 2026-03-03 | No | 78%
PBUT5.660437 | FAASt [Manati Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 28.64 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-27 | 2026-03-12 | No | 57%
PBUT5.666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-03-16 | Pending Obligation | Pending Obligation | 0%
PBUT5.671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-04-25 | Pending Obligation | Pending Obligation | 0%
PBUT5.671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-04-25 | Pending Obligation | Pending Obligation | 0%
PBUT5.671502 | FAASt [Yabucoa Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.88 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-04-26 | 2025-11-06 | No | 58%
PBUT5.673504 | FAASt [Gurabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 20.74 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-05-19 | 2026-12-14 | No | 57%
PBUT5.678789 | FAASt [Carolina Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.02 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-22 | 2025-05-16 | No | 64%
PBUT5.678793 | FAASt [Mayagüez Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 12.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-22 | 2025-10-22 | No | 53%
PBUT5.678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-07-22 | Pending Obligation | Pending Obligation | 0%
PBUT5.678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-07-22 | Pending Obligation | Pending Obligation | 0%
PBUT5.679039 | FAASt [Caguas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 75.59 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-27 | 2025-10-13 | No | 42%
PBUT5.679780 | FAASt [Bayamón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 21.89 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-08-08 | 2025-11-12 | No | 76%
PBUT5.686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-11-21 | Pending Obligation | Pending Obligation | 0%
PBUT5.690483 | FAASt [Cayey Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-11-21 | Pending Obligation | Pending Obligation | 0%
PBUT5.690545 | FAASt [Aguadilla Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 21.09 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-11-21 | 2025-08-18 | No | 42%
PBUT5.690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-11-22 | Pending Obligation | Pending Obligation | 0%
PBUT5.691702 | FAASt [Trujillo Alto Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 26.29 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-11-30 | 2025-10-29 | No | 35%
PBUT5.693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-08 | Pending Obligation | Pending Obligation | 0%
PBUT5.693615 | FAASt [Rio Grande Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-08 | Pending Obligation | Pending Obligation | 0%
PBUT5.693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-09 | Pending Obligation | Pending Obligation | 0%
PBUT5.697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-15 | Pending Obligation | Pending Obligation | 0%
PBUT5.698424 | FAASt [Florida Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.31 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-10-27 | No | 56%
PBUT5.698427 | FAASt [Maricao Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.698439 | FAASt [Las Marias Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.36 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-11-02 | No | 53%
PBUT5.698458 | FAASt [Guaynabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.62 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-04-07 | No | 68%
PBUT5.698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 1.3 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-01-01 | No | 70%
PBUT5.698522 | FAASt [Vieques Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.698570 | FAASt [Corozal Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.95 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2027-03-17 | No | 66%
PBUT5.698579 | FAASt [Orocovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 9.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2027-01-21 | No | 37%
PBUT5.699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2022-12-23 | Pending Obligation | Pending Obligation | 0%
PBUT5.701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 7.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-01-03 | 2026-08-25 | No | 44%
PBUT5.701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-01-03 | Pending Obligation | Pending Obligation | 0%
PBUT5.703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.1 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-01-23 | 2025-10-08 | No | 45%
PBUT5.704679 | FAASt [Coamo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-01 | 2026-08-05 | No | 54%
PBUT5.704741 | FAASt [Moca Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-02-02 | Pending Obligation | Pending Obligation | 0%
PBUT5.704744 | FAASt [San Sebastian Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-02-02 | Pending Obligation | Pending Obligation | 0%
PBUT5.704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-02-02 | Pending Obligation | Pending Obligation | 0%
PBUT5.704793 | FAASt [Yauco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-02-02 | Pending Obligation | Pending Obligation | 0%
PBUT5.704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.2 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-02 | 2027-02-22 | No | 57%
PBUT5.704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-02-02 | Pending Obligation | Pending Obligation | 0%
PBUT5.704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 5.8 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-02 | 2026-05-12 | No | 52%
PBUT5.704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 11 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2026-12-14 | No | 51%
PBUT5.704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.9 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-05-12 | No | 13%
PBUT5.704929 | FAASt [San Lorenzo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-02-03 | Pending Obligation | Pending Obligation | 0%
PBUT5.704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-02-03 | Pending Obligation | Pending Obligation | 0%
PBUT5.704938 | FAASt [Las Piedras Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-04-30 | No | 54%
PBUT5.704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-06-22 | No | 45%
PBUT5.709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.2 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-03-15 | 2027-02-16 | No | 58%
PBUT5.713795 | FAASt [Lares Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-04-12 | Pending Obligation | Pending Obligation | 0%
PBUT5.714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-04-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.724599 | FAASt [Sabana Grande Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-03 | Pending Obligation | Pending Obligation | 0%
PBUT5.724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-03 | 2026-11-26 | No | 40%
PBUT5.724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-03 | 2027-04-28 | No | 26%
PBUT5.724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-03 | Pending Obligation | Pending Obligation | 0%
PBUT5.724605 | FAASt [Guayanilla Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-03 | Pending Obligation | Pending Obligation | 0%
PBUT5.724669 | FAASt [Ciales Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-05 | Pending Obligation | Pending Obligation | 0%
PBUT5.724670 | FAASt [Patillas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-05 | Pending Obligation | Pending Obligation | 0%
PBUT5.724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 12.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-05 | 2027-06-24 | No | 51%
PBUT5.724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-05 | 2026-07-01 | No | 57%
PBUT5.724716 | FAASt [Quebradillas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-05 | Pending Obligation | Pending Obligation | 0%
PBUT5.724781 | FAASt [Penuelas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-06 | Pending Obligation | Pending Obligation | 0%
PBUT5.724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 14.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-06 | 2027-08-20 | No | 11%
PBUT5.724828 | FAASt [Loiza Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-06 | Pending Obligation | Pending Obligation | 0%
PBUT5.724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-07 | 2027-03-26 | No | 50%
PBUT5.724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-07-07 | Pending Obligation | Pending Obligation | 0%
PBUT5.734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-11 | Pending Obligation | Pending Obligation | 0%
PBUT5.734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-11 | Pending Obligation | Pending Obligation | 0%
PBUT5.734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-13 | Pending Obligation | Pending Obligation | 0%
PBUT5.734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-13 | Pending Obligation | Pending Obligation | 0%
PBUT5.734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-13 | Pending Obligation | Pending Obligation | 0%
PBUT5.734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-13 | Pending Obligation | Pending Obligation | 0%
PBUT5.734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-16 | Pending Obligation | Pending Obligation | 0%
PBUT5.734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-16 | Pending Obligation | Pending Obligation | 0%
PBUT5.734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-16 | Pending Obligation | Pending Obligation | 0%
PBUT5.734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Plan | 2023-10-16 | Pending Obligation | Pending Obligation | 0%
PBUT5.735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-18 | Pending Obligation | Pending Obligation | 0%
PBUT5.735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-19 | Pending Obligation | Pending Obligation | 0%
PBUT5.735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-19 | Pending Obligation | Pending Obligation | 0%
PBUT5.735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-19 | Pending Obligation | Pending Obligation | 0%
PBUT5.735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Plan | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Plan | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Plan | 2023-10-20 | Pending Obligation | Pending Obligation | 0%
PBUT5.735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-23 | Pending Obligation | Pending Obligation | 0%
PBUT5.735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-23 | Pending Obligation | Pending Obligation | 0%
PBUT5.735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-23 | Pending Obligation | Pending Obligation | 0%
PBUT5.735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-25 | Pending Obligation | Pending Obligation | 0%
PBUT5.735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-25 | Pending Obligation | Pending Obligation | 0%
PBUT5.735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-25 | Pending Obligation | Pending Obligation | 0%
PBUT5.735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Plan | 2023-10-25 | Pending Obligation | Pending Obligation | 0%
PBUT5.735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-10-25 | Pending Obligation | Pending Obligation | 0%
PBUT5.737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Plan | 2023-11-07 | Pending Obligation | Pending Obligation | 0%
PBUT5.737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-11-07 | Pending Obligation | Pending Obligation | 0%
PBUT5.737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-11-07 | Pending Obligation | Pending Obligation | 0%
PBUT5.737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-11-07 | Pending Obligation | Pending Obligation | 0%
PBUT5.737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-11-07 | Pending Obligation | Pending Obligation | 0%
PBUT5.738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 11.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-11-09 | 2025-11-27 | No | 0%
PBUT5.746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2024-03-27 | Pending Obligation | Pending Obligation | 0%
PBUT5.746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2024-03-27 | Pending Obligation | Pending Obligation | 0%
PBUT6.01 | UGWPF - Cables (Short Term) | Distribution | Distribution Line Rebuild | NFC | 9.5251 | 0.69607 | 2024-06-26 | Plan | N/A | Under assessment | N/A | 0%
PBUT6.02 | Mid Term (Expand UGWPF ST) | Distribution | Distribution Line Rebuild | NFC | 15.3577 | 4.0217 | 2024-06-26 | Plan | N/A | Under assessment | N/A | 0%
PBUT6.03 | Customers long secondary connections. | Distribution | Distribution Line Rebuild | NFC | 1.213 | 0.23202 | 2024-06-26 | Plan | N/A | Under assessment | N/A | 0%
PBUT6.04 | Capacity expansion | Distribution | Distribution Line Rebuild | NFC | 10.9735 | 1.8175 | 2024-06-26 | Plan | N/A | Under assessment | N/A | 0%
PBUT6.07 | U/G Cable Injection | Distribution | Distribution Line Rebuild | NFC | 2.3627 | 0.61873 | 2024-06-26 | Initiation | N/A | Under assessment | N/A | 0%
PBUT6.08 | U/G Switch Replacements | Distribution | Distribution Line Rebuild | NFC | 1.0583 | 0.077341 | 2024-06-26 | Initiation | N/A | Under assessment | N/A | 0%
PBUT6.165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 31.13 | 2021-06-08 | Design | 2020-12-18 | Pending Obligation | Pending Obligation | 0%
PBUT6.334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 134.67 | 2021-08-20 | Design | 2021-09-07 | Pending Obligation | Pending Obligation | 0%
PBUT6.334285 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 108.84 | 2021-08-20 | Design | 2021-09-08 | Pending Obligation | Pending Obligation | 0%
PBUT6.334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 98.49 | 2021-08-20 | Design | 2021-09-08 | Pending Obligation | Pending Obligation | 0%
PBUT6.334308 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 74.17 | 2021-08-20 | Design | 2021-09-08 | Pending Obligation | Pending Obligation | 0%
PBUT6.334420 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 59.85 | 2021-08-20 | Design | 2021-09-09 | Pending Obligation | Pending Obligation | 0%
PBUT6.334443 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 111.97 | 2021-08-20 | Design | 2021-09-09 | Pending Obligation | Pending Obligation | 0%
PBUT6.334452 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 82.07 | 2021-08-20 | Design | 2021-09-09 | Pending Obligation | Pending Obligation | 0%
PBUT6.334471 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 40.69 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 10.56 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334473 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 85 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334474 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 10.35 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334475 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 65.68 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 40.5 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334477 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 60.76 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.15 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-10 | 2025-02-14 | Yes | 97%
PBUT6.334491 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 72.35 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334497 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 76.65 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.334518 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 49.18 | 2021-08-20 | Design | 2021-09-10 | Pending Obligation | Pending Obligation | 0%
PBUT6.436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 53.58 | 2021-08-20 | Design | 2021-10-12 | Pending Obligation | Pending Obligation | 0%
PBUT6.546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 27.28 | 2021-09-22 | Design | 2021-11-09 | Pending Obligation | Pending Obligation | 0%
PBUT6.546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 14.6 | 2021-09-22 | Design | 2021-11-09 | Pending Obligation | Pending Obligation | 0%
PBUT6.730513 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 44.71 | 2021-09-22 | Design | 2023-09-07 | Pending Obligation | Pending Obligation | 0%
PBUT6.730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 23.64 | 2021-09-22 | Design | 2023-09-07 | Pending Obligation | Pending Obligation | 0%
PBUT6.730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 40.61 | 2021-09-22 | Design | 2023-09-08 | Pending Obligation | Pending Obligation | 0%
PBUT6.730821 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 73.9 | 2021-09-22 | Design | 2023-09-11 | Pending Obligation | Pending Obligation | 0%
PBUT6.730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 42.38 | 2021-09-22 | Design | 2023-09-11 | Pending Obligation | Pending Obligation | 0%
PBUT6.754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 250 | 2024-03-13 | Design | 2024-08-26 | Pending Obligation | Pending Obligation | 0%
PBUT6.754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.754351 | 2024-03-13 | Design | 2024-08-26 | Pending Obligation | Pending Obligation | 0%
PBUT6.760568 | FAASt [Distribution Feeder Rebuild # 1710-01] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.760568 | 2021-08-20 | Plan | 2024-10-24 | Pending Obligation | Pending Obligation | 0%
PBUT6.760571 | FAASt [Distribution Feeder Rebuild # 1720-07] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.760571 | 2021-08-20 | Plan | 2024-10-24 | Pending Obligation | Pending Obligation | 0%
PBUT6.760575 | FAASt [Distribution Feeder Rebuild # 1716-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.760575 | 2021-08-20 | Plan | 2024-10-24 | Pending Obligation | Pending Obligation | 0%
PBUT6.760577 | FAASt [Distribution Feeder Rebuild # 1718-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.760577 | 2021-08-20 | Plan | 2024-10-24 | Pending Obligation | Pending Obligation | 0%
PBUT6.760579 | FAASt [Distribution Feeder Rebuild # 1717-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.760579 | 2021-08-20 | Plan | 2024-10-24 | Pending Obligation | Pending Obligation | 0%
PBUT6.764705 | FAASt [Distribution Feeder Rebuild # 6014-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.764705 | 2021-08-20 | Plan | 2024-11-04 | Pending Obligation | Pending Obligation | 0%
PBUT6.764706 | FAASt [Distribution Feeder Rebuild # 7011-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.764706 | 2021-08-20 | Plan | 2024-11-04 | Pending Obligation | Pending Obligation | 0%
PBUT6.764707 | FAASt [Distribution Feeder Rebuild # 6012-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.764707 | 2021-08-20 | Plan | 2024-11-04 | Pending Obligation | Pending Obligation | 0%
PBUT6.764708 | FAASt [Distribution Feeder Rebuild # 5602-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.764708 | 2021-08-20 | Plan | 2024-11-04 | Pending Obligation | Pending Obligation | 0%
PBUT6.764709 | FAASt [Distribution Feeder Rebuild # 1204-05] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.764709 | 2021-08-20 | Plan | 2024-11-04 | Pending Obligation | Pending Obligation | 0%
PBUT6.767005 | FAASt [Distribution Feeder Rebuild # 1303-05] | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.767005 | 2021-08-20 | Plan | 2024-11-21 | Pending Obligation | Pending Obligation | 0%
PBUT6.767139 | FAASt [Distribution Feeder Rebuild # 2906-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.767139 | 2021-08-20 | Plan | 2024-11-21 | Pending Obligation | Pending Obligation | 0%
PBUT6.767381 | FAASt [Distribution Feeder Rebuild # 1204-04] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.767381 | 2021-08-20 | Plan | 2024-11-22 | Pending Obligation | Pending Obligation | 0%
PBUT6.767387 | FAASt [Distribution Feeder Rebuild # 1303-01] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.767387 | 2021-08-20 | Plan | 2024-11-22 | Pending Obligation | Pending Obligation | 0%
PBUT6.797148 | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.797148 | 2021-08-20 | Plan | 2024-12-06 | Pending Obligation | Pending Obligation | 0%
PBUT6.798275 | FAASt [Distribution Feeder Rebuild # 1620-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | Program Cost Included in PBUT6.798275 | 2021-09-22 | Plan | 2024-12-11 | Pending Obligation | Pending Obligation | 0%
PBUT7.01 | GuanicaTC H.Vol.Eq.Repl.MinRep | Substation | Substation Reliability | NFC | 0.34912 | 0.34912 | 2024-06-26 | Execution | 2021-09-01 | 2025-12-31 | N/A | 20%
PBUT7.02 | Monacillo TCBreak&TransforRep | Substation | Substation Reliability | NFC | 1.4991 | 1.4991 | 2024-06-26 | Execution | 2022-07-01 | 2025-08-26 | N/A | 80%
PBUT7.03 | Reliability HumacaoTC | Substation | Substation Reliability | NFC | 0.19912 | 0.19912 | 2024-06-26 | Close Out | 2023-07-01 | 2025-06-15 | N/A | 100%
PBUT7.04 | Reliability ManatiTC | Substation | Substation Reliability | NFC | 0.19912 | 0.19912 | 2024-06-26 | Close Out | 2023-07-01 | 2025-06-06 | N/A | 100%
PBUT7.05 | Reliability VegaAlta9105 | Substation | Substation Reliability | NFC | 0.099115 | 0.099115 | 2024-06-26 | Close Out | 2023-07-01 | 2025-02-14 | N/A | 100%
PBUT7.06 | Reliability Verdemar | Substation | Substation Reliability | NFC | 0.099115 | 0.099115 | 2024-06-26 | Close Out | 2023-07-01 | 2025-01-28 | N/A | 100%
PBUT7.07 | Reliability YaucoPueb1 | Substation | Substation Reliability | NFC | 0.099115 | 0.099115 | 2024-06-26 | Close Out | 2023-07-01 | 2025-01-29 | N/A | 100%
PBUT7.08 | L 51100 prot EcoElec to C Sur | Substation | Substation Reliability | NFC | 0.069115 | 0.069115 | 2024-06-26 | Execution | 2023-07-01 | 2025-08-01 | N/A | 50%
PBUT7.09 | Reliability CanovanasTC | Substation | Substation Reliability | NFC | 0.21412 | 0.21412 | 2024-06-26 | Execution | 2023-07-01 | 2025-12-30 | N/A | 40%
PBUT7.10 | Reliability BerwindTC | Substation | Substation Reliability | NFC | 0.17912 | 0.17912 | 2024-06-26 | Execution | 2023-07-01 | 2025-12-30 | N/A | 80%
PBUT7.11 | Reliability Aguada | Substation | Substation Reliability | NFC | 0.11912 | 0.11912 | 2024-06-26 | Close Out | 2023-07-01 | 2025-03-06 | N/A | 100%
PBUT7.12 | SJ Steam Plant Circuit Brakers | Substation | Substation Reliability | NFC | 0.6 | 0.6 | 2024-06-26 | Close Out | 2024-07-01 | 2025-07-01 | N/A | 100%
PBUT7.13 | PBUT7.02 Power Transformers | Substation | Substation Reliability | NFC | 32.6741 | 2.6991 | 2024-06-26 | Execution | 2024-07-01 | 2026-06-30 | N/A | 65%
PBUT7.14 | PBUT7.03 PAC | Substation | Substation Reliability | NFC | 25.0771 | 2.0255 | 2024-06-26 | Execution | 2024-07-01 | 2026-06-30 | N/A | 40%
PBUT7.15 | PBUT7.05 HV Equipment | Substation | Substation Reliability | NFC | 103.0133 | 9.1991 | 2024-06-26 | Execution | 2024-07-01 | 2026-06-30 | N/A | 75%
PBUT7.746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation Reliability | FF | Pending Obligation | Program Cost Included in PBUT7.746660 | 2021-09-22 | Design | 2024-04-08 | Pending Obligation | Pending Obligation | 0%
PBUT8.165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Substation Rebuilds | FF | 1.46 | 39.1 | 2021-06-08 | Execution | 2020-12-18 | 2028-06-28 | No | 1%
PBUT8.165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Substation Rebuilds | FF | 1.39 | 37.91 | 2021-06-08 | Execution | 2020-12-18 | 2028-06-28 | No | 1%
PBUT8.165268 | FAASt Rio Grande Estate Substation CH-2306 (Substation) | Substation | Substation Rebuilds | FF | 11.68 | 3.97 | 2021-06-08 | Execution | 2020-12-18 | 2026-11-16 | No | 55%
PBUT8.169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Design | 2021-01-27 | Pending Obligation | Pending Obligation | 0%
PBUT8.169266 | FAASt Centro Medico 1327/1359 Equipment Repair & Replacement (Substation) | Substation | Substation Rebuilds | FF | 21.33 | 11.7 | 2021-06-08 | Execution | 2021-01-28 | 2027-01-14 | No | 1%
PBUT8.169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement [Substation] | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Design | 2021-01-28 | Pending Obligation | Pending Obligation | 0%
PBUT8.169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | Substation | Substation Rebuilds | FF | 15.34 | 23 | 2021-06-08 | Design | 2021-01-29 | 2027-09-30 | No | 0%
PBUT8.169500 | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | FF | 6.37 | 5.7 | 2021-06-08 | Execution | 2021-01-29 | 2026-04-30 | No | 11%
PBUT8.169896 | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | Substation | Substation Rebuilds | FF | 23.25 | 3.6 | 2021-06-08 | Execution | 2021-02-02 | 2025-08-06 | No | 19%
PBUT8.174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation Rebuilds | FF | 23.26 | 11.3 | 2021-06-08 | Execution | 2021-03-04 | 2026-08-27 | No | 6%
PBUT8.178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation Rebuilds | FF | Pending Obligation | 4.1 | 2021-06-08 | Design | 2021-03-31 | Pending Obligation | Pending Obligation | 0%
PBUT8.178503 | FAASt [Aguirre TC - BKRS] (Substations) | Substation | Substation Rebuilds | FF | 39.03 | 12.2 | 2021-06-08 | Execution | 2021-04-01 | 2026-03-18 | No | 29%
PBUT8.178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Design | 2021-04-01 | Pending Obligation | Pending Obligation | 0%
PBUT8.179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | FF | 1.59 | 1.8 | 2021-06-08 | Close Out | 2021-04-09 | 2022-12-12 | Yes | 100%
PBUT8.542758 | FAASt [Minor Repairs -Group B] (Substation) | Substation | Substation Rebuilds | FF | 3.41 | 400 | 2021-09-22 | Execution | 2021-10-26 | 2025-05-16 | No | 40%
PBUT8.546370 | FAASt - Substation Minor Repairs Group A (Substation) | Substation | Substation Rebuilds | FF | 4.9 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-11-09 | 2025-06-06 | No | 55%
PBUT8.546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | FF | 3.03 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-11-09 | 2025-05-16 | No | 40%
PBUT8.547187 | FAASt - [Substation Component Replacement Program] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 17.1 | 2021-10-18 | Plan | 2021-11-15 | Pending Obligation | Pending Obligation | 0%
PBUT8.547241 | FAASt Tallaboa 5402 (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 6.9 | 2021-10-18 | Design | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT8.547243 | FAASt Egozcue - 1109 (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 10.5 | 2021-10-18 | Design | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT8.547247 | FAASt Cambalache TC Relocation (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 30.7 | 2021-10-18 | Design | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT8.547273 | FAASt Charco Hondo Substation 8008 Relocation (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 16.3 | 2021-10-18 | Plan | 2021-11-16 | Pending Obligation | Pending Obligation | 0%
PBUT8.547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 5.5 | 2021-10-18 | Design | 2021-11-17 | Pending Obligation | Pending Obligation | 0%
PBUT8.547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 29.1 | 2021-10-18 | Design | 2021-11-17 | Pending Obligation | Pending Obligation | 0%
PBUT8.549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | FF | 2.8 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Design | 2021-12-03 | 2025-09-05 | No | 0%
PBUT8.549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation Rebuilds | FF | 4.5 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Design | 2021-12-03 | 2025-09-05 | No | 0%
PBUT8.550099 | FAASt [Esc. Industrial M. Such - 1423] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 10.6 | 2021-10-18 | Design | 2021-12-07 | Pending Obligation | Pending Obligation | 0%
PBUT8.550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 5.1 | 2021-10-18 | Design | 2021-12-07 | Pending Obligation | Pending Obligation | 0%
PBUT8.550162 | FAASt [Berwind TC - 1336] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 12.4 | 2021-10-18 | Design | 2021-12-07 | Pending Obligation | Pending Obligation | 0%
PBUT8.550498 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 16.3 | 2021-10-18 | Plan | 2021-12-10 | Pending Obligation | Pending Obligation | 0%
PBUT8.550894 | FAASt [Baldrich - 1422] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 10.5 | 2021-10-18 | Design | 2021-12-14 | Pending Obligation | Pending Obligation | 0%
PBUT8.550950 | FAASt - EPC - [Monacillo TC] (Substations) | Substation | Substation Rebuilds | FF | 88.1 | 105.23 | 2024-01-18 | Execution | 2021-12-14 | 2028-07-19 | No | 2%
PBUT8.550980 | FAASt [Parques y Recreos - 1002] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 7.7 | 2021-10-18 | Design | 2021-12-14 | Pending Obligation | Pending Obligation | 0%
PBUT8.550986 | FAASt [Condado - 1133] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 10.6 | 2021-10-18 | Design | 2021-12-14 | Pending Obligation | Pending Obligation | 0%
PBUT8.551260 | FAASt [Guaynabo Pueblo Substation] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 17.2 | 2021-10-18 | Design | 2021-12-16 | Pending Obligation | Pending Obligation | 0%
PBUT8.551912 | FAASt [Puerto Nuevo - 1520] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 10.6 | 2021-10-18 | Design | 2021-12-21 | Pending Obligation | Pending Obligation | 0%
PBUT8.551914 | FAASt [Caparra 1911 & 1924] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 6.6 | 2021-10-18 | Design | 2021-12-21 | Pending Obligation | Pending Obligation | 0%
PBUT8.551918 | FAASt [Crematorio - 1512] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 10.6 | 2021-10-18 | Design | 2021-12-21 | Pending Obligation | Pending Obligation | 0%
PBUT8.682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | FF | 90.5 | 192.27 | 2022-08-25 | Design | 2022-09-07 | 2029-09-12 | No | 0%
PBUT8.682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 124.5 | 2024-06-28 | Design | 2022-09-12 | Pending Obligation | Pending Obligation | 0%
PBUT8.682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | Program Cost Included in PBUT8.542758 | 2021-09-22 | Plan | 2022-09-15 | Pending Obligation | Pending Obligation | 0%
PBUT8.682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Substation | Substation Rebuilds | FF | 61.4 | 161.98 | 2022-08-25 | Design | 2022-09-16 | 2029-08-01 | No | 0%
PBUT8.684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | FF | 6.93 | 75.7 | 2022-08-25 | Execution | 2022-10-06 | 2026-03-30 | Yes | 81%
PBUT8.685869 | FAASt [Mayagüez TC] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | Program Cost Included in PBUT8.542758 | 2021-09-22 | Plan | 2022-10-17 | Pending Obligation | Pending Obligation | 0%
PBUT8.723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 42.9 | 2022-12-10 | Design | 2023-06-15 | Pending Obligation | Pending Obligation | 0%
PBUT8.723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | FF | 100.69 | 125.5 | 2022-12-10 | Execution | 2023-06-16 | 2028-11-22 | No | 5%
PBUT8.723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | FF | 61.56 | 89.7 | 2022-12-10 | Execution | 2023-06-16 | 2028-12-19 | No | 2%
PBUT8.729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation Rebuilds | FF | 15.4 | Program Cost Included in PBUT8.542758 | 2022-08-25 | Execution | 2023-08-23 | 2026-12-01 | No | 19%
PBUT8.743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation Rebuilds | FF | 17.3 | Program Cost Included in PBUT8.542758 | 2022-08-25 | Design | 2024-01-29 | 2027-03-01 | No | 0%
PBUT8.752275 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | Program Cost Included in PBUT8.542758 | 2024-05-07 | Plan | 2024-07-29 | Pending Obligation | Pending Obligation | 0%
PBUT8.752276 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | Program Cost Included in PBUT8.542758 | 2024-05-07 | Plan | 2024-07-29 | Pending Obligation | Pending Obligation | 0%
PBUT8.752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | Program Cost Included in PBUT8.542758 | 2024-05-07 | Design | 2024-07-29 | Pending Obligation | Pending Obligation | 0%
PBUT8.761563 | FAASt [San Jose Relocation] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | Program Cost Included in PBUT8.761563 | 2021-10-18 | Plan | 2024-11-01 | Pending Obligation | Pending Obligation | 0%
PUBT37.738671 | FAASt [4 x 25 MW BESS Interconnections on LUMA System] (Substation) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | 196.58 | 2023-08-30 | Plan | 2023-11-15 | Pending Obligation | Pending Obligation | 0%
PUBT37.750502 | FAASt [4 x 25 MW BESS Interconnections Aguadilla TC] (Substation) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750502 | 2023-08-30 | Plan | 2024-06-27 | Pending Obligation | Pending Obligation | 0%
PUBT37.750503 | FAASt [4 x 25 MW BESS Interconnections Monacillos TC] (Substation) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2023-08-30 | Plan | 2024-06-27 | Pending Obligation | Pending Obligation | 0%
PUBT37.751655 | FAASt [Vieques Microgrid] (Transmission) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2024-02-15 | Design | 2024-07-18 | Pending Obligation | Pending Obligation | 0%
PUBT37.751656 | FAASt [Culebra Microgrid] (Transmission) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2024-02-15 | Design | 2024-07-18 | Pending Obligation | Pending Obligation | 0%
PUBT37.752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2023-08-30 | Plan | 2024-08-09 | Pending Obligation | Pending Obligation | 0%
Annex A