## Federally Funded (FEMA)
FY26 FEMA Total
Subsequent Periods
Program Brief | Portfolio | Program Brief Name | Project Name | FY26 FEMA Total | 2027-06-01 | 2028-06-01 | 2029-06-01 | 2030-06-01 | 2031-06-01 | 2032-06-01 | 2033-06-01 | 2034-06-01 | 2035-06-01 | Total 29+
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS - Primary Contact Centre | 1339836 | 1339836 | 1339836 | 1339836 | 0 | 0 | 0 | 0 | 0 | 0 | 1339836
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Test and Technology Laboratory | 1411548 | 774794 | 774794 | 774794 | 0 | 0 | 0 | 0 | 0 | 0 | 774794
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Ponce Regional Repairs | 928524 | 2500000 | 1500000 | 928526 | 928526 | 528526 | 400000 | 0 | 0 | 0 | 2785578
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Mayaguez Regional Repairs | 928524 | 2500000 | 928526 | 928526 | 928526 | 490558 | 0 | 0 | 0 | 0 | 2347610
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Bayamon Regional Repairs | 928524 | 928526 | 928526 | 928526 | 928526 | 928526 | 928526 | 928526 | 0 | 0 | 4642630
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Palo Seco South | 773136 | 2600000 | 2500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Caguas Regional Repairs | 446208 | 928526 | 928526 | 2143797 | 2000000 | 928526 | 500000 | 0 | 0 | 0 | 5572323
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | San Juan Regional Repairs | 928524 | 928526 | 928526 | 928526 | 928526 | 928526 | 928526 | 928526 | 0 | 0 | 4642630
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FAASt Arecibo Regional Off | 199428 | 915211 | 915212 | 1115211 | 915211 | 915211 | 915211 | 915211 | 0 | 0 | 4776055
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FAASt Arecibo Electric Serv | 922488 | 943797 | 1800000 | 1800000 | 1200000 | 915211 | 0 | 0 | 0 | 0 | 3915211
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Arecibo Regional Repairs | 928524 | 943797 | 1800000 | 1800000 | 1200000 | 915211 | 0 | 0 | 0 | 0 | 3915211
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FAASt Aguadilla Electric Serv | 0 | 1800000 | 1600000 | 915211 | 915211 | 456204 | 0 | 0 | 0 | 0 | 2286626
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS Hormigerous Contact Cent | 726124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS-LUMA EmerOperCentNewBldng | 600000 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Transport Network | 17203734.5852 | 39475823.6798 | 39475823.6798 | 39475823.6798 | 39475823.6798 | 39475823.6798 | 39475823.6798 | 26176866.9113 | 12239361.4401 | 0 | 196319523.0705
PBIT1 | Transmission | OT Telecom Systems & Network | Telecom Infrast-Cerro Puntas | 504830.91 | 8173193.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | El Gato - Group B | 273147.6 | 2258219.803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | La Santa - Group B | 295147.6 | 746538 | 1828739.1895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Microwave Network Upgrade | 799708.63 | 2114103.3591 | 1657093.0433 | 1657093.0433 | 2025335.9418 | 1728916.8284 | 1657093.0433 | 1559550.8907 | 0 | 0 | 8627989.7476
PBIT1 | Transmission | OT Telecom Systems & Network | FIELD AREA NETWORK (FAN). | 1419200 | 7518968.3203 | 22536263.5128 | 22299127.4452 | 20328057.0344 | 18930477.0136 | 18711141.9833 | 18745861.969 | 0 | 0 | 99014665.4455
PBIT1 | Transmission | OT Telecom Systems & Network | Santurce Luchetti - Group A | 224367.6 | 1040080.995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Fajardo Tecnica-Group D | 224367.6 | 43031.25 | 1467769.6406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Isabela - Group B | 273147.6 | 1770133.058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Atalaya - Group B | 273147.6 | 2598642.1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Manati TC - Group B | 273147.6 | 762696.1855 | 1404272.5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | El Yunque - Group A | 244467.6 | 307844.5 | 1337996.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Humacao Tecnica-Group D | 224367.6 | 28687.5 | 1413889.9788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Mayaguez (Mckinley)-Group D | 224367.6 | 1514108.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Santa Ana - Group A | 244467.6 | 28687.5 | 371875 | 1266317.7706 | 0 | 0 | 0 | 0 | 0 | 0 | 1266317.7706
PBIT1 | Transmission | OT Telecom Systems & Network | Fiber Optics Replacement -FEMA | 3407623.4 | 21642243.8678 | 48822316.6669 | 50381503.903 | 46418508.2713 | 44226529.2135 | 40984868.8876 | 0 | 0 | 0 | 182011410.2754
PBIT1 | Transmission | OT Telecom Systems & Network | Quebradillas Técnica-Group E | 218405 | 35859.375 | 1535122.5887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra Guanica Group F | 209197 | 251812.5 | 1137696.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Mora TC-Group E | 249605 | 1539698.9144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | San Sebastián TC-Group E | 237993 | 28687.5 | 1483791.0144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Juana Diaz Loma - Group C | 131040 | 28687.5 | 28687.5 | 28687.5 | 781531.2363 | 0 | 0 | 0 | 0 | 0 | 810218.7363
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra Barceloneta GroupF | 20311 | 28687.5 | 762140.1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra Barranquita GroupF | 217877 | 28687.5 | 1373855.5312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra AguasBuenasGroup H | 3808 | 28687.5 | 26296.875 | 1750618.5726 | 0 | 0 | 0 | 0 | 0 | 0 | 1750618.5726
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra Utuado Tec Group H | 156509 | 28687.5 | 241108.875 | 1524390.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 1524390.0063
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra Manati Tec Group H | 3748 | 28687.5 | 26296.875 | 1731911.6878 | 0 | 0 | 0 | 0 | 0 | 0 | 1731911.6878
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra Canov TC Group G | 4350 | 28687.5 | 1773779.371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Telco Infra Juncos TC Group G | 4350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | TelcoInfraS.IsabelTecnicaGrpG | 156509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | PBIT1 - Program Wedge | -4159712.1188 | -40000000 | -30000000 | -4000000 | 15000000 | 0 | 0 | 30000000 | 33159712.119 | 0 | 74159712.119
PBIT1 | Transmission | OT Telecom Systems & Network | G - Juncos TC | 0 | 28687.5 | 28687.5 | 1651110.142 | 0 | 0 | 0 | 0 | 0 | 0 | 1651110.142
PBIT1 | Transmission | OT Telecom Systems & Network | G - Santa Isabel Tecnica | 0 | 28687.5 | 28687.5 | 2733914.4745 | 0 | 0 | 0 | 0 | 0 | 0 | 2733914.4745
PBIT1 | Transmission | OT Telecom Systems & Network | D - Sabana Llana Tecnica | 8471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT2 | Support Services | IT OT Cybersecurity Program | CYBERSECURITY PROGRAM IMPL
PBIT4 | Support Services | IT OT Asset Management | HW Upg legacy equip-CPEX FEMA | 2333328 | 2300000 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Map Mgtion-Gtch OMS CPEX FMA | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | WFMS Intermediate Comms | 0 | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | New Project Cyber Security Systems - CIP Segmentation, licenses, plan
PBIT4 | Support Services | IT OT Asset Management | Dummy Project - Compliance Software (NERC-CIP ) | 0 | 250000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Mass Storage&Backup Appliances | 3055392 | 3055394 | 3055394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | DR (IT) Facility Reloc FEMA | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | DR(IT)Syst Mig to Cloud-FEMA | 0 | 393750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Situational Awrness CAPEX FEMA | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Ntwk Prof OMS CAPEX FEMA | 393204 | 400000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | New Project DA/AMI Integration | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | GPS Clock install - CAPEX FEMA | 64740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Netwk Enhancmts - CAPEX FEMA | 0 | 200000 | 200000 | 200000 | 280000 | 300000 | 0 | 0 | 0 | 0 | 780000
PBIT4 | Support Services | IT OT Asset Management | WiFi 6 Integration- CAPEX | 0 | 300000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 1500000
PBIT4 | Support Services | IT OT Asset Management | Replace CDC RTU's with DNP | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 0 | 2100000
PBOP6 | Enabling | Materials Management | OPMAT8 Fed WOilFiEqOilC(Small) | 130680 | 135907.2 | 141343.488 | 146997.2275 | 152877.1166 | 121000 | 121000 | 121000 | 121000 | 0 | 783874.3441
PBOP6 | Enabling | Materials Management | OPMAT16 Fed-WarFacImpr CapPlan | 118800 | 123552 | 128494.08 | 133633.8432 | 138979.1969 | 110000 | 110000 | 110000 | 110000 | 0 | 712613.0401
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Arecibo - Group A | 21372706 | 939500.1452 | 7004000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Bayamon - Group A | 21498427.8 | 39089080.5155 | 9630500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Caguas - Group A | 6914699 | 22232298.7699 | 6128500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation-Mayaguez -Group A | 9177691.4 | 14337022.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Ponce - Group A | 6914699 | 30800779.894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -San Juan-Group A | 28790292.2 | 56416630.9381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | PBOP7 Program Wedge | -23537616.87 | -300000000 | -76462383.13 | -140000000 | 405000000 | 135000000 | 0 | 0 | 0 | 0 | 400000000
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -San Juan - 115kV | 0 | 0 | 20073564.4841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -SJ - Group B | 0 | 2964800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -SJ - Group C | 0 | 5100000 | 32300000 | 89709000 | 0 | 0 | 0 | 0 | 0 | 0 | 89709000
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Ponce - 115kV | 0 | 0 | 33622600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Ponce - Group B | 0 | 7674928.8408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Ponce - Group C | 0 | 6375000 | 16830000 | 68148750 | 0 | 0 | 0 | 0 | 0 | 0 | 68148750
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Mayaguez - 115kV | 0 | 0 | 14099800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Mayaguez -Group B | 0 | 1463482.1671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Mayaguez-Group C | 0 | 6885000 | 22567500 | 89444650 | 0 | 0 | 0 | 0 | 0 | 0 | 89444650
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Caguas - 115kV | 0 | 0 | 21035247.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Caguas - Group B | 0 | 14731350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Caguas - Group C | 0 | 6800000 | 26520000 | 82552000 | 0 | 0 | 0 | 0 | 0 | 0 | 82552000
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Bayamon - 115kV | 0 | 0 | 14219560.6551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Bayamon - Group B | 0 | 6485500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Bayamon - Group C | 0 | 19380000 | 23970000 | 102894200 | 0 | 0 | 0 | 0 | 0 | 0 | 102894200
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Arecibo - 115kV | 0 | 0 | 24503227.9369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Arecibo - Group B | 0 | 2699597.3429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vegetation -Arecibo - Group C | 0 | 2550000 | 22567500 | 79449500 | 0 | 0 | 0 | 0 | 0 | 0 | 79449500
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | MAYAGUEZ GROUP B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vgtn - Bayamon - Group A (HD) | 17601052 | 58626893.5841 | 9630500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vgtn - Caguas - Group A (HD) | 10057744 | 53942218.8759 | 52179800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vgtn - Arecibo - Group A (HD) | 16720999.4 | 27424746.3883 | 23200750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vgtn - Mayaguez - Group A (HD) | 5028872 | 51233568.3996 | 19261000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Vgtn - Ponce - Group A (HD) | 4400263 | 56393618.8759 | 16459400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | Asset Verification | 8440000 | 9460000 | 9460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT1 | Enabling | Compliance & Studies | T Subs Sys Asset Plan & Size | 3000000 | 2250000 | 1125000 | 281250 | 0 | 0 | 0 | 0 | 0 | 0 | 281250
PBUT1 | Enabling | Compliance & Studies | Dist Line-Sys Lev Plan & Size | 3000000 | 2250000 | 1125000 | 281250 | 0 | 0 | 0 | 0 | 0 | 0 | 281250
PBUT1 | Enabling | Compliance & Studies | T Line-Sys Lev A. Plan & Size | 3000000 | 2250000 | 1125000 | 281250 | 0 | 0 | 0 | 0 | 0 | 0 | 281250
PBUT1 | Enabling | Compliance & Studies | D Subs Sys Asset Plan & Size | 3000000 | 2250000 | 1125000 | 281250 | 0 | 0 | 0 | 0 | 0 | 0 | 281250
PBUT1 | Enabling | Compliance & Studies | Dist Planning - Area Plans | 1020000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT1 | Enabling | Compliance & Studies | PBUT1 FEMA Funding Alignment | -1953000 | 0 | 0 | 1953000 | 0 | 0 | 0 | 0 | 0 | 0 | 1953000
PBUT13 | Transmission | Transmission Priority Pole Replacements | Trans PriorityPoleRepl-Ln2200 | 0 | 8600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPoleL13400AcaciasSGermanPargu | 285000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | T-Pole Program L3000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | PBUT13 Program Wedge | -3373740.075 | 0 | 3373740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 9600 Bayamon-Cataño | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 7800 Dorado-Vega Alta | 364000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 6700 SeborucoTO-TapiaTO | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 7500 3Monjitas-PuertNu | 107000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 10700 HTejas-HTejas | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole2700AGUADILLAH-MORA | 279000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole36200MncillosJuncos | 0 | 595200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole37800CaguasBuenPtSt | 0 | 989000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole14700Manati-ManatiSe | 1549750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 2800 Tbone-RameyField2 | 0 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 3500 Cachete-Caparra | 0 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 18400 - BARRANQUITAS TC-EL ABANICO | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 6900MidorAzu-Hatllo | 1500250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 8100 - YAUCO 1 HP-ADJUNTAS TO | 0 | 1188900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 10500 Chardon Las Monjas | 140250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole14100 BarcelonetaTC-Merck | 219500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 9900 - RIO BLANCO HP-HUMACAO SECT | 0 | 9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 1600 - SAN GERMAN SECT-SAN GERMAN TC | 0 | 9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 1600 - SAN GERMAN TC-YAUCO 1 HP | 0 | 1603200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 36800 Canovanas TC - Palmer TC | 0 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 10300 Canovanas TC-Sect | 0 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 10700 - HATO TEJAS SECT-BAYAMON PUEBLO SECT | 0 | 201000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole10900JOBOSTC-PFIZERGUAYMA | 0 | 274250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 13200 DoraHatoT-HatoTS | 0 | 1717500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole TL 4900QBRSec-QBRTo | 0 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 15900-VICTTC-ADATO | 0 | 324500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 1800 - Ponce TC - Villa Del Carmen TO | 0 | 912500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 3400 - MONACILLOS TC-GUAYNABO SEC | 0 | 201000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 2900 Toro Negro 1 HP -Toro Negro 2 HP | 0 | 604500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 300 - JUANA DIAZ TC-LA RAMBLA SECT | 0 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 300 - TORO NEGRO 1 HP-JUANA DIAZ TC | 0 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TL 400 Caguas TC -Gautier Benitez Sect | 0 | 102200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 4800 StaIsabel-ToroNegro | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 700CostaSur-Yauco2HP | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 800-COMSAT SECT-CIDRA SE | 1386000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole3100MONCILLOSS.LLANA | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 3300 SGerardo-Venezuela | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 5900SJSP-Crematori | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 13700 Mora-Isabela | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 19002Bocas-SSbstian | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole16500Fajardo-2Marina | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole2000 11AgostoSt-SSTC | 2165750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole1600LeonSectAcacias | 593500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole 2400 DBocas-Caonill | 789000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Floodprone area descopes | 0 | 0 | 13500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Known Planned Projects PBUT13 | 10056600.5 | 25825450 | 21770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Tpole5600 VictTcAÑASCOTC | 1214000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | TPole 4800Sta.Isabel-Aibo | 449000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | Physical Sec.Group 4-Ponce TC | 775000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | PHYS SEC Group 1 - Manati TC | 725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | PHYS SEC Group1 - Hato Rey TC | 557000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | PHYS SEC Group 2 - Mora TC | 1166000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | Physical Sec.Group2-Mayagu.TC | 965000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | Physical SecGroup3-Aguas B.GIS | 1266000 | 2075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | Physical Sec.Group 5-Bayamo.TC | 230000 | 966000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | PHYS SEC Group 3 - Juncos TC | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | PHYS SEC GRP 4 - Vega Baja TC | 884000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | PHYS SEC Group 3 - Yabucoa TC | 448000 | 957000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | PHYS SEC GRP 1-Sabana Llana TC | 448000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT22 | Control Center & Buildings | Critical Energy Management System Upgrades | ENERGY MANAGEMENT SYSTEM (EMS) | 8913848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT22 | Control Center & Buildings | Critical Energy Management System Upgrades | Advance Distribution Management System (ADMS)/DERMS | 6009374 | 6033411 | 11174927.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT24 | Control Center & Buildings | Control Center Construction & Refurbishment | New Primary&Backup Ctrl Centrs | 8946437 | 33947830 | 40139273 | 40139273 | 0 | 0 | 0 | 0 | 0 | 0 | 40139273
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 3 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 6 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 11 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 5 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 6 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 7 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 13 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 8 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 11 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 11 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 1 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 4 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 3 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 1 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 3 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 5 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 6 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 7 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 8 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 11 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 12 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 9 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 1 -Ph. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 2 -Ph. 2 | 1317500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 2 -Ph. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 1 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 5 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 9 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 15-to-19 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 17-to-21 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 13-to-16 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 11 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 1 -Ph. 2 | 6236000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 20 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Dpole Caguas Grp. 2 -Ph. 2 | 18995900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 1 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 3 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 10 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 14 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 12 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 16-to-19 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 14-15 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 16-to-20 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 3 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 7 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 5 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Carolina Grp. 3 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 9 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 5 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 4 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 4 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 7 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 12 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 8 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 7 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 8 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 15 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Carolina Grp. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 4 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 6 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 4 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 9 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 13 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 11 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 12 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Dpole Caguas Grp. 3 -Ph 2 | 17712500 | 8085000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 4 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 5 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 6 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 8 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 9 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 14 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 10 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 7 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 13 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 12 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 12-13-14 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 10 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 17 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 1 -Ph. 2 | 5251500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 6 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 8 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 1 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Grp. 3 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Grp. 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 1 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 9 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 10 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Arecibo Grp. 10 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Grp. 10 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Grp. 13-to-16 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Bayamon Grp. 3 -Ph. 2 | 661500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DistPole&CondRepairMayagG1Ph2 | 4595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Group 4 Ph 2 | 6000 | 4795000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Group 5 Ph 2 | 6000 | 14840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Group 6 Ph 2 | 6000 | 16870000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Group 7 Ph 2 | 6000 | 9800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Caguas Group 8 Ph 2 | 6000 | 3885000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Carolina Group 1 Ph 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Carolina Group 2 Ph 2 | 9186000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Carolina Group 3 Ph 2 | 6000 | 5145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Group 2 Ph 2 | 8530500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Group 3 Ph 2 | 14925000 | 3080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Mayaguez Group 4 Ph 2 | 6000 | 10675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Group 1 Ph2 | 825500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole Ponce Group 2 Ph2 | 15746000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Group 1 Ph 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Group 2 Ph 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DPole San Juan Group 3 Ph 2 | 267900 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | PBUT30 Program Wedge | -15750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15750000 | 15750000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Dist.Pole&Cond.Rep.Are.Grp3Ph2 | 6000 | 4095000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Bayamon Group 4 - Phase 2 | 0 | 4340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Arecibo Group 4 - Phase 2 | 0 | 8890000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Ponce Group 3 - Phase 2 | 0 | 11165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE (FY28) | 0 | 0 | 52500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE (FY29) | 0 | 0 | 0 | 52500000 | 0 | 0 | 0 | 0 | 0 | 0 | 52500000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE (FY30) | 0 | 0 | 0 | 0 | 52500000 | 0 | 0 | 0 | 0 | 0 | 52500000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE(FY31) | 0 | 0 | 0 | 0 | 0 | 52500000 | 0 | 0 | 0 | 0 | 52500000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE(FY32) | 0 | 0 | 0 | 0 | 0 | 0 | 52500000 | 0 | 0 | 0 | 52500000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE(FY33) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500000 | 0 | 0 | 52500000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE(FY34) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500000 | 0 | 52500000
PBUT30 | Distribution | - | Dpole&Cond.Rep.-Arec.Grp4Phs2 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | Dpole&Cond.Rep.-Mayag.Grp5Phs2 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | Dpole&Cond.Rep.-Baya.Grp4Phs2 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | Dpole&Cond.Rep.-SJ.Grp4Phs2 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | Dpole&Cond.Rep.-Pnce.Grp3Phs2 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole Arecibo 18-21 Phase 3 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole Bayamon 17-25 Phase 3 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole Caguas 21-25 Phase 3 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole Mayaguez 24-27 Phase 3 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole Ponce 20-28 Phase 3 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole San Juan 22-29 Phase 3 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole San Juan 30-39 Phase 3 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | - | DPole San Juan 40-54 Phase 3 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | D-POLE(FY35) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500000 | 52500000
PBUT33 | Transmission | Transmission Line Rebuild | 36100 DOS BOCAS MONACILLOS | 442838.5029 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 13609365.5427 | 7845664.595 | 22055030.1377
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 500 Ponc | 162685 | 26078352.4245 | 33937688.6928 | 10797476.9927 | 50000 | 0 | 0 | 0 | 0 | 0 | 10847476.9927
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 1500 May | 1396833.2594 | 1396833.2594 | 439208.3148 | 19259314.1151 | 36896518.1773 | 36896518.1773 | 20821913.9103 | 80000 | 0 | 0 | 113954264.38
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 2200 Dos | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 33642625.9143 | 13811745.0411 | 50000 | 47984370.9554
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 3000 Mon | 398907.6 | 120000 | 12599033.5703 | 28792283.023 | 18702606.3714 | 90000 | 0 | 0 | 0 | 0 | 47584889.3944
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 2700 Vic | 0 | 10000 | 10000 | 10000 | 4725000 | 0 | 0 | 0 | 0 | 0 | 4735000
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 3100 Mon | 596703.6 | 120000 | 120000 | 120000 | 120000 | 742592.2269 | 16025066.7658 | 17711858.7744 | 2650188.013 | 30000 | 37399705.78
PBUT33 | Transmission | Transmission Line Rebuild | 36400 DOS BOCAS PONCE | 621107.9549 | 13300975.7929 | 25508578.6607 | 14443317.7562 | 80000 | 0 | 0 | 0 | 0 | 0 | 14523317.7562
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38kV - Line 1200 May | 1314140.5243 | 1314140.5243 | 120000 | 120000 | 12386451.5102 | 34806881.267 | 34806881.267 | 25431003.1958 | 100000 | 0 | 107651217.24
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 1900 Dos | 120000 | 14079732.2257 | 16511044.7073 | 3917232.8739 | 40000 | 0 | 0 | 0 | 0 | 0 | 3957232.8739
PBUT33 | Transmission | Transmission Line Rebuild | 36200 MONACILLOS JUNCOS | 358461.7899 | 120000 | 9631567.305 | 5540054.3412 | 60000 | 0 | 0 | 0 | 0 | 0 | 5600054.3412
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 2800 Agu | 1928579.7692 | 120000 | 120000 | 16029411.1666 | 18644254.4736 | 4278531.1798 | 40000 | 0 | 0 | 0 | 38992196.82
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV Line 100 Ponce | 120000 | 29413754.5208 | 48896130.6705 | 48896130.6705 | 23667053.7056 | 70000 | 0 | 0 | 0 | 0 | 72633184.3761
PBUT33 | Transmission | Transmission Line Rebuild | Existing 115 kV - Line 36200 F | 1025721.4222 | 120000 | 120000 | 20965720.0788 | 16588206.5079 | 70000 | 0 | 0 | 0 | 0 | 37623926.5867
PBUT33 | Transmission | Transmission Line Rebuild | 9500 PALO SECO SP CATANO S | 498283.2706 | 12672899.1178 | 10039013.3901 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 9100 Gua | 150518.055 | 120000 | 2810154.6794 | 5561932.8206 | 100000 | 0 | 0 | 0 | 0 | 0 | 5661932.8206
PBUT33 | Transmission | Transmission Line Rebuild | 5400 RIO BLANCO HP DAGUAO | 120000 | 1190756.3702 | 28536519.8296 | 31650008.507 | 4790233.016 | 30000 | 0 | 0 | 0 | 0 | 36470241.523
PBUT33 | Transmission | Transmission Line Rebuild | Existing 115kV Line 36800 Pa | 490196.0844 | 490196.0844 | 150849.6737 | 120000 | 11661665.7148 | 15460230.5388 | 5196917.3688 | 50000 | 0 | 0 | 32488813.6224
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 11100 Ca | 0 | 0 | 0 | 0 | 0 | 10000 | 1665000 | 0 | 0 | 0 | 1675000
PBUT33 | Transmission | Transmission Line Rebuild | Existing 38 kV - Line 2400 Dos | 120000 | 16631168.9058 | 21612486.7536 | 6892358.4106 | 50000 | 0 | 0 | 0 | 0 | 0 | 6942358.4106
PBUT33 | Transmission | Transmission Line Rebuild | 8200 SAN JUAN SP CATANO SE | 338987.2941 | 9372032.7588 | 7428287.1864 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
PBUT33 | Transmission | Transmission Line Rebuild | 4100 GUARAGUO TC COMERIO T | 120000 | 120000 | 13724142.0995 | 17795953.0224 | 5664807.0081 | 50000 | 0 | 0 | 0 | 0 | 23510760.0305
PBUT33 | Transmission | Transmission Line Rebuild | H MariaL700 Costa Sur-Yauco P | 771751.7647 | 174312.6471 | 120000 | 33870070.5462 | 9196099.9538 | 40000 | 0 | 0 | 0 | 0 | 43106170.5
PBUT33 | Transmission | Transmission Line Rebuild | PBUT33-Wedge | -3493901.5021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3493901.5021 | 3493901.5021
PBUT33 | Transmission | Transmission Line Rebuild | 36100 - DOS BOCAS - MONACILLOS ​/ (2) Monterrey to Barrio Pina​ | 341598.4341 | 9475554.7801 | 13948206.6668 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
PBUT33 | Transmission | Transmission Line Rebuild | 36100 - DOS BOCAS - MONACILLOS ​/ (1) Unibon to Monterrey​ | 276422.424 | 120000 | 1665990.6478 | 8392558.4719 | 120000 | 0 | 0 | 0 | 0 | 0 | 8512558.4719
PBUT33 | Transmission | Transmission Line Rebuild | 36100 - DOS BOCAS - MONACILLOS ​/ (8) Morovis to Unibon​ | 263387.222 | 120000 | 120000 | 603216.3347 | 12360612.575 | 2052604.9677 | 30000 | 0 | 0 | 0 | 15046433.8774
PBUT33 | Transmission | Transmission Line Rebuild | 36100 - DOS BOCAS - MONACILLOS ​/ (7) Ciales to Morovis​ | 311182.9627 | 120000 | 120000 | 120000 | 120000 | 12636458.8917 | 7258786.2781 | 60000 | 0 | 0 | 20195245.1698
PBUT33 | Transmission | Transmission Line Rebuild | 36100 - DOS BOCAS - MONACILLOS ​/ (6) Dos Bocas to Ciales​ | 754379.8308 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 14138074.1746 | 14858074.1746
PBUT33 | Transmission | Transmission Line Rebuild | 36100 - DOS BOCAS - MONACILLOS ​/ (5) Cana to Bayamon​ | 380704.0401 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 840000
PBUT33 | Transmission | Transmission Line Rebuild | 36100 - Cana to Bayamon | 65000 | 10000 | 10000 | 5900000 | 0 | 0 | 0 | 0 | 0 | 0 | 5900000
PBUT33 | Transmission | Transmission Line Rebuild | 36400 - DOS BOCAS - PONCE​/ (2) Jayuya - Ponce​ | 750440.6735 | 120000 | 16709871.5236 | 32077937.3617 | 18151227.285 | 80000 | 0 | 0 | 0 | 0 | 50309164.6467
PBUT33 | Transmission | Transmission Line Rebuild | 1900 - Dos Bocas HP to San Sebastian TC​/ (3) Lares - San Sebastian​ | 120000 | 120000 | 120000 | 120000 | 9383720.1811 | 19282038.8586 | 100000 | 0 | 0 | 0 | 28885759.0397
PBUT33 | Transmission | Transmission Line Rebuild | 2200 - Dos Bocas HP to Dorado TC/ (4) Manati to Vega Baja​ | 120000 | 120000 | 7555738.8002 | 17929785.4097 | 11978195.3936 | 90000 | 0 | 0 | 0 | 0 | 29997980.8034
PBUT33 | Transmission | Transmission Line Rebuild | 2200 - Barceloneta to Manati | 270000 | 10000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | 2200 - Vega Baja Sect to Dorado | 275000 | 10000 | 10000 | 4725000 | 0 | 0 | 0 | 0 | 0 | 0 | 4725000
PBUT33 | Transmission | Transmission Line Rebuild | 2200 - Cambalache to Factor Sect | 280000 | 10000 | 10000 | 10000 | 2685000 | 0 | 0 | 0 | 0 | 0 | 2695000
PBUT33 | Transmission | Transmission Line Rebuild | 2200 - Dos Bocas HP to Dorado TC/ (6) Vega Baja to San Demetrio​ | 120000 | 120000 | 120000 | 120000 | 2141565.067 | 11016848.0795 | 120000 | 0 | 0 | 0 | 13398413.1465
PBUT33 | Transmission | Transmission Line Rebuild | 36800 - Palmer Fajardo to Sabana Llana/ (2) Palmer to Fajardo​ | 450883.2259 | 450883.2259 | 147573.6022 | 120000 | 120000 | 120000 | 6971331.1161 | 13742676.8538 | 8026568.8088 | 80000 | 29180576.7787
PBUT33 | Transmission | Transmission Line Rebuild | TL 4800 - Santa Isabel to Toro Negro HP | 4005352.9412 | 443779.4118 | 120000 | 26014710 | 30228360 | 6842680 | 40000 | 0 | 0 | 0 | 63125750
PBUT33 | Transmission | Transmission Line Rebuild | 36200 - Fajardo to Rio Blanco​/ (2) Fajardo - Daguao​ | 1269401.4074 | 120000 | 120000 | 120000 | 8058706.3965 | 22452665.2853 | 16375014.3292 | 100000 | 0 | 0 | 47106386.0111
PBUT33 | Transmission | Transmission Line Rebuild | 5400 - Rio Blanco HP - Daguao TC​/ (1) Vieques ​ | 120000 | 120000 | 120000 | 120000 | 17078876.316 | 22157088.3569 | 7034636.0706 | 50000 | 0 | 0 | 46440600.7435
PBUT33 | Transmission | Transmission Line Rebuild | 5400 - Rio Blanco HP - Daguao TC​/ (2) Culebra | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1103125.508 | 984412.0384 | 80000 | 0 | 2527537.5465
PBUT33 | Transmission | Transmission Line Rebuild | 3000 - Monacillos TC to Juncos TC​/ (4) Bairoa - Caguas TC​ | 162908.8615 | 120000 | 120000 | 120000 | 1617475.3889 | 6957435.8364 | 120000 | 0 | 0 | 0 | 8814911.2253
PBUT33 | Transmission | Transmission Line Rebuild | 36200 - MONACILLOS - JUNCOS​/ (3) Villa Betina - Quebrada Negritos​ | 481350.0743 | 120000 | 120000 | 9357560.6307 | 13657780.1459 | 90000 | 0 | 0 | 0 | 0 | 23105340.7766
PBUT33 | Transmission | Transmission Line Rebuild | 36200 - MONACILLOS - JUNCOS​/ (2) Quebrada Negrito - Juncos​ | 1138948.6913 | 120000 | 120000 | 120000 | 6000787.5592 | 31455002.1395 | 28185464.7586 | 120000 | 0 | 0 | 65881254.4572
PBUT33 | Transmission | Transmission Line Rebuild | 100 & 200 - Salinas Urbano to Jobos TC | 0 | 0 | 0 | 0 | 10000 | 4300000 | 0 | 0 | 0 | 0 | 4310000
PBUT33 | Transmission | Transmission Line Rebuild | 100 & 200 - Jobos TC to Guayama | 0 | 0 | 0 | 0 | 0 | 4300000 | 0 | 0 | 0 | 0 | 4300000
PBUT36 | Customer Experience | AMI Implementation Program | Advanced Metering Infrastructu | 141467318.14 | 290600641.89 | 230158616.87 | 40000000 | 35000000 | 22000000 | 0 | 0 | 0 | 0 | 97000000
PBUT36 | Customer Experience | AMI Implementation Program | PBUT36 Program Wedge | -21220097.721 | 0 | 0 | 0 | 0 | 21220097.721 | 0 | 0 | 0 | 0 | 21220097.721
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | PBUT37 Program Wedge | -6197731.4269 | -70000000 | 0 | 0 | 70000000 | 0 | 0 | 0 | 6197731.4269 | 0 | 76197731.4269
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 25 MW BESS Instn & Intn Barcel | 371000 | 12282095.466 | 5814242.01 | 25166464.59 | 13805805.5006 | 0 | 0 | 0 | 0 | 0 | 38972270.0906
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 25 MW BESS Instn & Intn Manati | 329000 | 9405589.213 | 5698874.66 | 23824394.37 | 13883566.8297 | 0 | 0 | 0 | 0 | 0 | 37707961.1996
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 25 MW BESS INST & INTE AGUADIL | 319400 | 11829023.962 | 5727590.01 | 25331882.71 | 13884467.4867 | 0 | 0 | 0 | 0 | 0 | 39216350.1966
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 25 MW BESS Instn & Intn San Ju | 336398 | 12852087.27 | 5773363.17 | 25184560.36 | 13804354.8686 | 0 | 0 | 0 | 0 | 0 | 38988915.2286
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 2501-01 | 11173853.3154 | 20478417.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 2501-02 (L) | 8052001.6764 | 16067156.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 3801-02 | 3543215.8822 | 13797241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 3801-01 | 1988578.4809 | 5933237.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | 2501-03 | 3171612.1575 | 6031003.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | TSM, Adv.Sensors & WAMPAC Syst | 1671694 | 4946542 | 5102341 | 4784017 | 5072988 | 4716657 | 5164871 | 5318118 | 9043155 | 0 | 34099806
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | Vieques Microgrid | 9500134 | 19922950.03 | 42542410.48 | 26521642.01 | 0 | 0 | 0 | 0 | 0 | 0 | 26521642.01
PBUT37 | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | Culebra Microgrid | 861322 | 13210513.65 | 15131343.19 | 14898385.2 | 0 | 0 | 0 | 0 | 0 | 0 | 14898385.2
PBUT4 | Distribution | Grid Automation | Arecibo Short Term Group 2 - D | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | Caguas ST G-3 Dist Autom | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | San Juan Short TermGroup9 Aut | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | San Juan ST1 Dist Automa | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | Caguas ST G-6 Distr Automation | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | PBUT4Program Wedge | -15848849.994 | 0 | 0 | 0 | 0 | 0 | 15848850 | 0 | 0 | 0 | 15848850
PBUT4 | Distribution | Grid Automation | DAR 2001-02 | 52812.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1646-02 San Juan | 67541.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAR 9203-03 | 589673.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1803-03 Bayamon | 312000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1806-03 Bayamon | 867005.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1711-01 Bayamon | 186000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1711-04 Bayamon | 288000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1713-03 Bayamon | 612000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1708-05 Bayamon | 117500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1909-07 Bayamon | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1909-08 Bayamon | 636000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1909-09 Bayamon | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9501-01 Bayamon | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9502-03 Bayamon | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1717-04 Bayamon | 106920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9503-06 Bayamon | 282150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1907-04 Bayamon | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1907-05 Bayamon | 106920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3010-01 Caguas | 579000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3013-01 Caguas | 813000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3013-02 Caguas | 387000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3013-03 Caguas | 689535.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2603-09 Caguas | 328500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2601-01 Caguas | 10232.298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2601-03 Caguas | 55668.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2602-02 Caguas | 58542.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2701-03 Caguas | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2702-01 Caguas | 65681.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2901-01 Caguas | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2901-02 Caguas | 237000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2901-03 Caguas | 684000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2901-04 Caguas | 417000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3006-05 Caguas | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3405-02 Caguas | 383130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3501-01 Caguas | 968220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3501-03 Caguas | 466290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3601-02 Caguas | 687000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3601-03 Caguas | 345000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3601-04 Caguas | 1140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3602-01 Caguas | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3701-02 Caguas | 876656.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4601-01 Ponce | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5013-01 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5016-01 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5018-01 Ponce | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5018-03 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5019-01 Ponce | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAR 8404-03 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7402-01 Arecibo | 130706.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7403-02 Arecibo | 96341.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7702-02 Arecibo | 111196.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7702-03 Arecibo | 64972.432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8801-01 Arecibo | 114854.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8801-02 Arecibo | 113210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8801-03 Arecibo | 77149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9004-08 Arecibo | 1182060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8701-02 Arecibo | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8701-03 Arecibo | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9001-01 Arecibo | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8010-03 Arecibo | 78210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8013-01 Arecibo | 156420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8013-02 Arecibo | 156420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8015-08 Arecibo | 106920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9101-03 Arecibo | 489000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9101-04 Arecibo | 597000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9105-06 Arecibo | 489000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9201-02 Arecibo | 789000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8005-01 Arecibo | 807000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8101-02 Arecibo | 174000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8101-03 Arecibo | 426000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8103-01 Arecibo | 768000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8202-02 Arecibo | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers Tline 4800 | 2346000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers Tline 1500 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 3700 | 1596000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 1900 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 2100 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 7800 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 800 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 13400 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 12600 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 100 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 8100 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 1600 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 2000 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 2200 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 3100 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 3000 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 3600 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 6500 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 5600 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 8200 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kV Reclosers TLine 3200 | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1705-02 Bayamon | 117500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1705-05 Bayamon | 117500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1343-05 San Juan | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1437-05 San Juan | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1709-02 Bayamon | 127710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1709-05 Bayamon | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1719-15 Bayamon | 321750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1719-18 Bayamon | 243540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1703-01 Bayamon | 78210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1703-02 Bayamon | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1703-04 Bayamon | 57420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1703-05 Bayamon | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1704-01 Bayamon | 71280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1704-02 Bayamon | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3201-02 Caguas | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3201-04 Caguas | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4001-03 Ponce | 828000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6601-03 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4003-02 Ponce | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4003-03 Ponce | 855000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4401-04 Ponce | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5002-03 Ponce | 579000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5004-06 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5004-09 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5007-01 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5302-01 Ponce | 705000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5302-04 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5304-01 Ponce | 855000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5304-03 Ponce | 831000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5501-04 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5802-03 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5901-01 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5901-02 Ponce | 714000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3004-01 Caguas | 767250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3205-07 Caguas | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3401-02 Caguas | 963000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3502-01 Caguas | 785250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9601-01 Caguas | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1204-03 San Juan | 558000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2201-01 San Juan | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2201-02 San Juan | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2305-02 San Juan | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8010-02 Arecibo | 537000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8015-09 Arecibo | 756000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8101-01 Arecibo | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8101-04 Arecibo | 564000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8101-05 Arecibo | 237000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8104-02 Arecibo | 524250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8301-01 Arecibo | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8404-01 Arecibo | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8405-01 Arecibo | 456750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7403-03 Arecibo | 256500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8501-01 Arecibo | 416250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8801-04 Arecibo | 167250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9001-02 Arecibo | 852000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1704-05 Bayamon | 287250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1734-02 Bayamon | 207750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1901-02 Bayamon | 176250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1711-05 Bayamon | 296250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1717-03 Bayamon | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1718-01 Bayamon | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1718-02 Bayamon | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4602-01 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9003-05 Arecibo | 573000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9003-06 Arecibo | 1065000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1118-10 San Juan | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1646-01 San Juan | 629000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2403-01 San Juan | 117500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2404-05 San Juan | 553500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9801-03 Bayamon | 1025859.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT-5303-01 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT-5401-02 Ponce | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT-3501-02 Caguas | 299250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT-1706-01 Bayamon | 117500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT-1711-02 Bayamon | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT-1901-03 Bayamon | 167250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7402-05 ARECIBO | 611500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7601-04 ARECIBO | 504500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7701-02 ARECIBO | 562838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7701-04 ARECIBO | 186500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8002-05 ARECIBO | 232500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3005-02 CAGUAS | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3010-04 CAGUAS | 91500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1102-03 SAN JUAN | 237000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1106-05 SAN JUAN | 288000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2201-04 SAN JUAN | 368250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8401-03 ARECIBO | 714000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1924-05 BAYAMON | 123500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2801-01 CAGUAS | 295500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3008-04 CAGUAS | 43500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1658-13 SAN JUAN | 321750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5803-02 PONCE | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5010-06 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5005-02 PONCE | 186500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4502-01 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4301-04 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7901-02 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7503-05 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7502-02 MAYAGUEZ | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7101-06 MAYAGUEZ | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7101-04 MAYAGUEZ | 23250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7101-03 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7012-01 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6012-05 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6002-05 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6002-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3406-01 CAGUAS | 292108.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3101-04 CAGUAS | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3007-04 CAGUAS | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7403-01 ARECIBO | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9105-08 ARECIBO | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9004-11 ARECIBO | 65250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8504-01 ARECIBO | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8013-03 ARECIBO | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7702-01 ARECIBO | 64500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1102-02 SAN JUAN | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1203-01 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1203-02 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1657-02 SAN JUAN | 515250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2501-01 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2701-02 CAGUAS | 367432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2906-02 CAGUAS | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3005-01 CAGUAS | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3101-01 CAGUAS | 100500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3402-05 CAGUAS | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3602-03 CAGUAS | 426833.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4301-03 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4501-01 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4501-02 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4501-04 PONCE | 627000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4503-02 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5002-01 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5002-02 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5002-04 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5305-03 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5602-01 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6001-02 MAYAGUEZ | 20460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6005-01 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6008-02 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6401-02 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6401-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6404-03 MAYAGUEZ | 115630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6404-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 6601-01 PONCE | 383000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7003-05 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7503-01 MAYAGUEZ | 46500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7503-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7801-02 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7801-03 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7802-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1647-08 SAN JUAN | 296250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2005-10 SAN JUAN | 578919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2602-01 CAGUAS | 185250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2604-01 CAGUAS | 197500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3016-03 CAGUAS | 258000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5005-03 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5018-05 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5802-02 PONCE | 123500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5902-02 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7502-03 MAYAGUEZ | 218000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7502-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7503-02 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7601-01 ARECIBO | 203500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8011-04 ARECIBO | 588750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9103-01 ARECIBO | 636000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9103-02 ARECIBO | 185250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9103-04 ARECIBO | 223500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9703-01 CAGUAS | 592500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2003-01 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2001-04 SAN JUAN | 180500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2001-03 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1620-02 SAN JUAN | 309000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1618-02 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1607-04 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1416-04 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1334-02 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1301-04 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1301-03 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1301-02 SAN JUAN | 456403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1301-01 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1102-04 SAN JUAN | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5010-03 PONCE | 117500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5003-03 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5003-02 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 5003-01 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4503-01 PONCE | 361000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 4002-01 PONCE | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7303-03 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7303-02 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7201-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7101-02 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7002-04 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 7002-03 MAYAGUEZ | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3201-01 CAGUAS | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 3013-04 CAGUAS | 56250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 2603-10 CAGUAS | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9207-09 BAYAMON | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 9207-05 BAYAMON | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 1903-02 BAYAMON | 65250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8014-06 ARECIBO | 250500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT 8002-01 ARECIBO | 65250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 2400 | 876000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 6000 | 501000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 500 | 876000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 4700 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 700 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 2700 | 126000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 10000 | 126000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 8900 | 126000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 2800 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 9400 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 300 | 126000 | 1125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 7100 | 126000 | 1125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 5200 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 5400 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 13700 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT Future | 0 | 123000000 | 136258304.5 | 136258304.5 | 136258304.5 | 136258304.5 | 123000000 | 0 | 0 | 0 | 531774913.5
PBUT4 | Distribution | Grid Automation | DAUT COMM | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 20000000
PBUT4 | Distribution | Grid Automation | Known Planned Projects PBUT4 | 14519575.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT/COMM ARECIBO G-12 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT/COMM ARECIBO G-14 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT/COMM SAN JUAN G-15 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT/COMM ARECIBO G-19 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT/COMM CAGUAS G-20 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1110-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1110-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1110-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1111-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1117-08 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1117-09 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1401-06 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1401-07 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1401-08 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1401-10 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1512-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1512-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1530-06 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1530-07 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN1530-08 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1530-09 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1113-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1113-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1113-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1113-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1115-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAGUEZ 7103-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAGÜEZ 7103-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAGUEZ 7103-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAGÜEZ 7504-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAGÜEZ 7505-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1335-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1335-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1335-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1335-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1335-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1602-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1602-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1602-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1602-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1602-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 2301-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 2305-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 2305-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1119-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1119-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1343-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1343-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1343-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAG. 6702-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAG. 6703-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT MAYAG. 6705-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1421-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1421-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1421-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1421-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1421-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1404-07 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1404-09 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1420-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1420-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 2401-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 2401-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1526-01 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1526-02 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1526-03 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1526-04 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | DAUT SAN JUAN 1526-05 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 2600 | 126000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT4 | Distribution | Grid Automation | 38kv Reclosures TLine 8500 | 126000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program- Aguada | 41675.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog - Luquillo | 192833.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Dorado | 13357.416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | PBUT5 Program Wedge | -24914054.3955 | 0 | 24914054.3955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog - Peñuelas | 2696148.4807 | 652008.5808 | 2960954.0742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Gurabo | 5243713.2132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-San German | 7110577.6676 | 3259624.2645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Hatillo | 1762277.8578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Cataño | 16207.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Cidra | 4550124.699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Salinas | 4829978.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Caguas | 293829.934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Naguabo | 2438796.356 | 3551101.7407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Arecibo | 817953.078 | 4808305.2729 | 1002.6321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Lajas | 12677.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Yabucoa | 62508.528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Manatí | 20069.6314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progra-Mayaguez | 20088.996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Quebradill | 3360773.1797 | 396226.9806 | 4982341.0433 | 1358288.7817 | 0 | 0 | 0 | 0 | 0 | 0 | 1358288.7817
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog - Patillas | 3068259.1523 | 680279.901 | 3182278.365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Fajardo | 163104.8733 | 1964505.782 | 1888911.3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progr-Adjuntas | 4908968.7099 | 2415746.1741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progr-Orocovis | 5871786.4949 | 1381703.6873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progra-Toa Alta | 360597.729 | 1706785.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Lares | 3156490.8068 | 2195012.0589 | 4822742.7021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | StreetlightingProg-Barceloneta | 1230925.524 | 3472920.0262 | 187896.4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Corozal | 5882783.9267 | 376458.5372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Camuy | 2849325.003 | 2644571.2742 | 5875373.082 | 516450.0989 | 0 | 0 | 0 | 0 | 0 | 0 | 516450.0989
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-San Sebast | 3953278.1592 | 2239083.8553 | 5884219.724 | 5884219.724 | 0 | 0 | 0 | 0 | 0 | 0 | 5884219.724
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Aibonit | 12702.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Aguadilla | 14468.2735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Hormiguero | 806809.623 | 2879204.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Ponce | 816521.616 | 3254059.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Naranjito | 7840814.8185 | 2600359.5712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Guayama | 232796.151 | 1395736.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Ciales | 5483356.59 | 432669.4073 | 4808305.2729 | 1002.6321 | 0 | 0 | 0 | 0 | 0 | 0 | 1002.6321
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Coamo | 2643774.2721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Comerio | 3386496.3539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Sábana Gra | 3835115.7285 | 772687.7867 | 5881004.9846 | 165475.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 165475.1537
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Utuado | 1577679.6535 | 4016283.1415 | 4591470.6427 | 4827754.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 4827754.2923
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Juana Diaz | 2099665.239 | 3231488.4114 | 3818972.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progr - Guánica | 6839.9498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Rio Grande | 423715.047 | 1634638.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlight Prog-Trujillo Alto | 28413.762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Arroyo | 2655417.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Las Marias | 1645604.6223 | 2554898.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Florida | 4146436.9729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting ProgR-Guaynabo | 385949.8155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Sta Isabel | 1462311.969 | 2073665.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Cayey | 1563940.637 | 1946362.7235 | 2555470.3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Humacao | 823113.549 | 2631959.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Morovis | 4376857.8907 | 1217559.0173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Maricao | 183306.7377 | 2234044.6315 | 2480572.2849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progra-Carolina | 11909.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Vieques | 822200.667 | 1595127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog - Maunabo | 12107.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlightng Prog-Las Piedras | 3780454.4248 | 2182507.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Villalb | 21142.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-SanLorenzo | 93524.4207 | 5985185.9373 | 3163877.0203 | 5883436.2135 | 0 | 0 | 0 | 0 | 0 | 0 | 5883436.2135
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Jayuya | 3739521.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Bayamon | 1391944.6007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Isabela | 537388.593 | 2671426.0707 | 411.6543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Loíza | 806073.231 | 2655886.455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Vega Alta | 5349935.6822 | 2016002.6918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Añasco | 7493157.5166 | 712277.6739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-San Juan | 2125838.97 | 2435106.3957 | 5802702.5599 | 2007333.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 2007333.9997
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Cabo Rojo | 879133.98 | 3501233.7135 | 70.0515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Juncos | 2161941.51 | 4255788.4766 | 960276.8134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Aguas Buen | 5008151.5288 | 62172.3834 | 5274955.2374 | 611063.3926 | 0 | 0 | 0 | 0 | 0 | 0 | 611063.3926
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progr-Canovanas | 1326966.0811 | 2049157.5792 | 4138853.4137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Culebra | 7760.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Moca | 6239054.2797 | 2014082.4827 | 5879537.1429 | 3679127.5482 | 0 | 0 | 0 | 0 | 0 | 0 | 3679127.5482
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Prog-Guayanilla | 3127266.8947 | 302850.103 | 3501527.792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progra-Toa Baja | 4672.674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program-Rincon | 3943983.765 | 2711570.5398 | 4490427.8652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlghtng Prog-Barranquitas | 3341423.3353 | 1821011.5895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Progr-Vega Baja | 703722.318 | 3394166.006 | 633529.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Ceiba | 1657925.1315 | 512423.6835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlighting Program - Yauco | 125274.4659 | 2338545.4072 | 5434538.2549 | 72.652 | 0 | 0 | 0 | 0 | 0 | 0 | 72.652
PBUT5 | Customer Experience | Distribution Streetlighting | PBUT5 FEMA Funding Alignment | 0 | 36231401.34 | -68202223.3373 | -24934224.4886 | 0 | 0 | 0 | 0 | 0 | 0 | -24934224.4886
PBUT6 | Distribution | Distribution Line Rebuild | Alturas De Mayag 6012-02 (L) | 321003.25 | 10800 | 11927256.7879 | 8380487.8788 | 0 | 0 | 0 | 0 | 0 | 0 | 8380487.8788
PBUT6 | Distribution | Distribution Line Rebuild | Rio Bayamón Ii 1720-07 | 30000 | 30000 | 5892680 | 8824020 | 12500 | 0 | 0 | 0 | 0 | 0 | 8836520
PBUT6 | Distribution | Distribution Line Rebuild | Crea 1717-03 | 24000 | 24000 | 8719680 | 845680 | 0 | 0 | 0 | 0 | 0 | 0 | 845680
PBUT6 | Distribution | Distribution Line Rebuild | Bayamón Tc 13kV #2 1716-03 | 30000 | 30000 | 10815596.4 | 7220397.6 | 2500 | 0 | 0 | 0 | 0 | 0 | 7222897.6
PBUT6 | Distribution | Distribution Line Rebuild | Combate 6704-03 | 676266.8182 | 10800 | 10800 | 17468374.8252 | 4714295.8 | 0 | 0 | 0 | 0 | 0 | 22182670.6252
PBUT6 | Distribution | Distribution Line Rebuild | Candelaria Arenas 1718-02 | 24000 | 16793499.92 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Conquistador 1204-05 | 24000 | 24000 | 8951108.9274 | 10397750.9274 | 4000 | 0 | 0 | 0 | 0 | 0 | 10401750.9274
PBUT6 | Distribution | Distribution Line Rebuild | Villa Betina 1303-05 | 24000 | 12311341.75 | 1155910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Canovanas T.C. #1 2402-02 | 36000 | 36000 | 29114522.98 | 2725898 | 0 | 0 | 0 | 0 | 0 | 0 | 2725898
PBUT6 | Distribution | Distribution Line Rebuild | Villa Betina 1303-01 | 24000 | 24000 | 7616681.2325 | 6891985.7375 | 0 | 0 | 0 | 0 | 0 | 0 | 6891985.7375
PBUT6 | Distribution | Distribution Line Rebuild | Cana 1710-01 (L) | 24000 | 24000 | 17588719.6 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
PBUT6 | Distribution | Distribution Line Rebuild | Levittown 1806-02 | 30000 | 30000 | 30000 | 10129370.42 | 11047495 | 933124.58 | 0 | 0 | 0 | 0 | 22109990
PBUT6 | Distribution | Distribution Line Rebuild | Conquistador 1204-04 | 24000 | 24000 | 6229598.9118 | 7721263.9118 | 2000 | 0 | 0 | 0 | 0 | 0 | 7723263.9118
PBUT6 | Distribution | Distribution Line Rebuild | Canovanas T.C. #2 2404-06 | 63000 | 36000 | 36000 | 20295278.51 | 1887043 | 0 | 0 | 0 | 0 | 0 | 22182321.51
PBUT6 | Distribution | Distribution Line Rebuild | Conquistador 1204-02 (L) | 24000 | 24000 | 24000 | 27025904 | 7633210.54 | 0 | 0 | 0 | 0 | 0 | 34659114.54
PBUT6 | Distribution | Distribution Line Rebuild | Parguera Pds 6603-01 | 1087309.6648 | 11714404.6477 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | San Germán 13kV 6406-02 (L) | 99898.5529 | 14861275.2353 | 1260527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | T - Bone 7011-03 | 159789.7965 | 10800 | 10800 | 9573852.381 | 3600 | 0 | 0 | 0 | 0 | 0 | 9577452.381
PBUT6 | Distribution | Distribution Line Rebuild | Lajas 6601-03 | 3270138.8034 | 19566832.8205 | 1865064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Once De Agosto 13kV 6014-02 | 3112603.6561 | 18860289.1086 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Villa Betina 1303-02 | 344965 | 3174525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | 2906-02 | 117754.625 | 48000 | 27954399.96 | 2714400 | 0 | 0 | 0 | 0 | 0 | 0 | 2714400
PBUT6 | Distribution | Distribution Line Rebuild | Unibon 9501-02 | 24000 | 4416676 | 19709584 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
PBUT6 | Distribution | Distribution Line Rebuild | Utuado Pueblo 8101-03 (L) | 3095319.08 | 314477.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | 3502-02 | 3336410.96 | 11134017.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Guanica Tc 5602-02 | 52000 | 46000 | 18048800 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
PBUT6 | Distribution | Distribution Line Rebuild | Grana Pds Ii 1909-09 | 36000 | 44000 | 28000 | 5283780 | 0 | 0 | 0 | 0 | 0 | 0 | 5283780
PBUT6 | Distribution | Distribution Line Rebuild | Cachete 13kV 1529-15 | 2143625 | 2642125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | 2603-08 | 48000 | 44500 | 18652266.64 | 12036533.32 | 0 | 0 | 0 | 0 | 0 | 0 | 12036533.32
PBUT6 | Distribution | Distribution Line Rebuild | Indiera Alta 6305-03 | 10800 | 2501613.2 | 11126175.61 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800
PBUT6 | Distribution | Distribution Line Rebuild | Parque Escorial 1620-02 | 3087747.9286 | 6330009.4814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Berwind 13kV 1336-08 | 24000 | 24000 | 8441492.0588 | 17609405.9412 | 2428703 | 0 | 0 | 0 | 0 | 0 | 20038108.9412
PBUT6 | Distribution | Distribution Line Rebuild | San Sebastian 7805-11 | 172674.6 | 10800 | 10800 | 30758386.9 | 900 | 0 | 0 | 0 | 0 | 0 | 30759286.9
PBUT6 | Distribution | Distribution Line Rebuild | San Sebastian 7805-13 | 344058.1333 | 10800 | 7086260.5292 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600
PBUT6 | Distribution | Distribution Line Rebuild | Cerro Las Mesas 6010-01 | 83600 | 10800 | 10800 | 9862846.67 | 3600 | 0 | 0 | 0 | 0 | 0 | 9866446.67
PBUT6 | Distribution | Distribution Line Rebuild | Acacias 13.2 kV 6802-04 | 10800 | 26773481.44 | 2532388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Las Vegas 6306-02 | 175592 | 10800 | 26275170 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800
PBUT6 | Distribution | Distribution Line Rebuild | 1801-03 (L) | 10800 | 1361807.3 | 2312881.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | 3701-03 | 48000 | 48000 | 5518600.02 | 6577800.02 | 0 | 0 | 0 | 0 | 0 | 0 | 6577800.02
PBUT6 | Distribution | Distribution Line Rebuild | Barrio Piñas 9403-03 | 24000 | 24000 | 3671250 | 1684950 | 0 | 0 | 0 | 0 | 0 | 0 | 1684950
PBUT6 | Distribution | Distribution Line Rebuild | 3006-05 | 48000 | 48000 | 5083564.87 | 2142504.08 | 0 | 0 | 0 | 0 | 0 | 0 | 2142504.08
PBUT6 | Distribution | Distribution Line Rebuild | 3007-03 | 48000 | 3020622.22 | 17883733.32 | 7441244.44 | 0 | 0 | 0 | 0 | 0 | 0 | 7441244.44
PBUT6 | Distribution | Distribution Line Rebuild | PBUT6 Program Wedge | -4113824.3361 | -100000000 | -180000000 | -100000000 | -90000000 | -63000000 | 223000000 | 234113824.34 | 80000000 | -0.0039066 | 284113824.3361
PBUT6 | Distribution | Distribution Line Rebuild | UG Feeder 1115-02 Santurce | 741069.5611 | 2175804.2202 | 563896.203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | UG Feeder 1115-03 Santurce | 787386.4087 | 2311791.984 | 599139.7157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | UG Feeder 1115-04 - Santurce | 602119.0184 | 1767840.9289 | 458165.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | UG Feeder 1117-07 - Santurce | 409132.1535 | 1201225.2466 | 311317.6954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | UG Feeder 1117-08 - Santurce | 563521.6454 | 1654517.7924 | 428796.071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | UG Feeder 1424-07 - Santurce | 1198554.1923 | 2910530.4689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | UG Feeder 1424-08 - Santurce | 729554.7257 | 1771627.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | New Tier 1 | 0 | 24767280 | 24767280 | 40659618 | 266041866 | 262945956 | 0 | 0 | 0 | 0 | 569647440
PBUT7 | Substation | Substation Reliability | SCADA accesRTU Repl.Group 3 | 4164679.79 | 5431916.7893 | 7933977.95 | 7271050.48 | 2858536.84 | 0 | 0 | 0 | 0 | 0 | 10129587.32
PBUT7 | Substation | Substation Reliability | SCADA Access & RTU Repl.Group2 | 3080481.86 | 4115640.42 | 717640.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCADA Access & RTU Repl.Group1 | 2863234.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | PBUT7 Program Wedge | -7986836.0279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7986836.0278 | 7986836.0278
PBUT7 | Substation | Substation Reliability | AMELIA SECT PAC Upgrade | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SAN GERMAN SECT PAC Upgrade | 330000 | 1338000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | LAS LOMAS TC PAC Upgrade | 943000.48 | 1423000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | CIALES PAC Upgrade | 0 | 423000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | CONQUISTADOR PAC Upgrade | 45000 | 1437000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | PALMER TC PAC Upgrade | 1293000 | 1402000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | DAGUAO TC PAC Upgrade | 951454.56 | 2592909.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | ARECIBO SECT PAC Upgrade | 0 | 478000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | VEGA ALTA SECT PAC Upgrade | 60000 | 2180500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | COVADONGA TC PAC Upgrade | 1378898.01 | 2702552.45 | 990000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
PBUT7 | Substation | Substation Reliability | ANASCO TC PAC Upgrade | 315000 | 2259000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Daguao TC 72101 | 694387.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | San Sebastian TC 77805 | 944556.8667 | 521024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Guaraguao Sect 61707 | 971002.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | GuanicaTC 75602 | 677956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Colegio Sect 66006 | 690000 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Grana 71907 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Guayama PDS 64006 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Villa Betina 71303 | 260000 | 4735000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Yauco Plaza 65305 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Humacao TC 2602 | 1969550.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | PAC upgrade #2 - Colegio SECT | 0 | 0 | 30000000.73 | 31000095 | 28218000 | 0 | 0 | 0 | 0 | 0 | 59218095
PBUT7 | Substation | Substation Reliability | ALTURAS DE MAYAGUEZ 0050T | 744178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | BAIROA 3030 | 585852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | HATO TEJAS SECT 13330 | 224491.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | CAGUAX SECT 3052 | 101000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | HOGAR CREA 0050T | 744178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | JUAN DOMINGO SECT 4350 | 0 | 1037902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | LAS PIEDRAS SECT 5336 | 1037902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | MIRAMAR SECT 5032 | 457634.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SAN FERNANDO SECT 0050T | 938432.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SAN GERMAN 1270 | 585852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | T-BONE 0050T | 585852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | VISTAMAR 0050T | 585852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | YABUCOA TC 36332 | 638222.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 - Transformer | 0 | 35000000 | 72000000 | 72000000 | 72000000 | 72000000 | 52000000 | 0 | 0 | 0 | 268000000
PBUT7 | Substation | Substation Reliability | SCR Group #2 - Circuit Breakers | 0 | 7865000 | 4800000 | 9810500 | 9120000 | 9120000 | 9120000 | 20281166.68 | 18166666.68 | 18166666.68 | 93785000.04
PBUT7 | Substation | Substation Reliability | SCR Group #2 - MetalClad | 0 | 0 | 18000000 | 18000000 | 19000000 | 7000000 | 7000000 | 7000000 | 7000000 | 6000000 | 71000000
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - ALTURAS DE MAYAGUEZ 36701 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Island Wide Testing | 12416972.3 | 10310600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SubMinorRepair Planned Group | 0 | 3000000 | 6500000 | 9500000 | 10500000 | 11000000 | 13000000 | 15000000 | 0 | 0 | 59000000
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - ALTURAS DE MAYAGUEZ 36703 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - COAMO PDS | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - COSTA SUR SP | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - HERMANAS DAVILA | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - JAYUYA | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - LAJAS | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - LOMAS VERDES | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - MONTEREY | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - QUINTANA | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - REPARTO METROPOLITANO | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - SAN GERMAN TC | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - TAFT | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - UNIBON | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - VILLA DEL REY | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - VISTAMAR | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SCR Group #2 MOD - Remaining | 0 | 4000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1500000 | 500000 | 0 | 0 | 8000000
PBUT7 | Substation | Substation Reliability | San Germán ESC. | 1489953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Bayview Sectionalizer 1802 Rel | 24000 | 0 | 0 | 0 | 0 | 275000 | 1535000 | 6035000 | 5885000 | 2931912 | 16661912
PBUT8 | Substation | Substation Rebuilds | New Guayanilla TC | 120000 | 30994932 | 23306865 | 7930732 | 7930732 | 7625416 | 0 | 0 | 0 | 0 | 23486880
PBUT7 | Substation | Substation Reliability | SubMinorRepair GRP F-Añasco TC | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Manati TC BRKS - Phase II | 12000 | 20000 | 20000 | 20000 | 1020000 | 18300000 | 15250000 | 15350000 | 0 | 0 | 49940000
PBUT8 | Substation | Substation Rebuilds | Bayamón TC - Part 2 | 120000 | 30370706 | 17474690 | 17474690 | 17474690 | 3858675 | 0 | 0 | 0 | 0 | 38808055
PBUT8 | Substation | Substation Rebuilds | Morovis | 473545.44 | 4028093 | 206062.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | CULEBRA SUB 3801 | 3056832.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SubMinorRepr GRP G-Bo PiñasGIS | 915000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | SubMinrReprGRP G-Matin PeñaGIS | 786000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Palo Seco | 24000 | 20000 | 120000 | 520000 | 15120000 | 20120000 | 15220000 | 8270000 | 0 | 0 | 59250000
PBUT7 | Substation | Substation Reliability | SubMinorRepr GRP G-Chardon GIS | 1044000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Monterey | 35660.76 | 35660.76 | 8253694.02 | 9682466.53 | 9682466.53 | 10689563.4 | 0 | 0 | 0 | 0 | 30054496.46
PBUT8 | Substation | Substation Rebuilds | Añasco TC | 12000 | 20000 | 20000 | 20000 | 20000 | 300000 | 1050000 | 13300000 | 14950000 | 10350000 | 39990000
PBUT8 | Substation | Substation Rebuilds | Mayaguez | 310000 | 50000 | 50000 | 10270000 | 15070000 | 12170000 | 0 | 0 | 0 | 0 | 37510000
PBUT7 | Substation | Substation Reliability | SubMinorRepr GRP G-SanJuan GIS | 1045000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | New Salinas TC | 120000 | 40656402 | 10404101 | 10404101 | 10404101 | 29652311 | 0 | 0 | 0 | 0 | 50460513
PBUT7 | Substation | Substation Reliability | SubMinorRepar GRP F-Guanica TC | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation GRP D Sabana Gr | 915000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Dorado TC Relocation | 24000 | 0 | 0 | 50000 | 1050000 | 2050000 | 13075000 | 14175000 | 8101362 | 1525000 | 40026362
PBUT7 | Substation | Substation Reliability | Substation GRP E Coamo | 396000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation GRP E Guayama | 526000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation GRP D Punta Del | 845000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation GRP C Cana | 266000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation GRP E Salinas Urb | 656000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation GRP D Capa | 915000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Caguas TC BKRS 115kV | 24000 | 0 | 25000 | 25000 | 50000 | 18600000 | 26600000 | 22124000 | 12550000 | 0 | 79949000
PBUT8 | Substation | Substation Rebuilds | JUANA DIAZ TC | 0 | 0 | 25000 | 25000 | 1050000 | 13600000 | 26600000 | 23100000 | 15550000 | 50000 | 79975000
PBUT8 | Substation | Substation Rebuilds | Costa Sur TC - Phase II | 3165780 | 12263121 | 21373129 | 12385788 | 6314227 | 5793569 | 0 | 0 | 0 | 0 | 24493584
PBUT8 | Substation | Substation Rebuilds | Conquistador - CH | 90000 | 3184782.32 | 3173282.34 | 3173282.34 | 0 | 0 | 0 | 0 | 0 | 0 | 3173282.34
PBUT8 | Substation | Substation Rebuilds | Aguirre TC - Phase II | 4274707 | 8409414 | 20843535 | 8529414 | 8529414 | 8469414 | 23848246 | 0 | 0 | 0 | 49376488
PBUT8 | Substation | Substation Rebuilds | Egozcue - Metalclad - 1109 | 1718526 | 10325046 | 7599150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Guaynabo Pueblo Subst. Rebuild | 585000 | 132265 | 12429267 | 11564151 | 0 | 0 | 0 | 0 | 0 | 0 | 11564151
PBUT8 | Substation | Substation Rebuilds | Jobos TC | 190000 | 25790000 | 18490000 | 14540000 | 12070000 | 0 | 0 | 0 | 0 | 0 | 26610000
PBUT8 | Substation | Substation Rebuilds | Acacias 6801 TC Relocation | 2724140.56 | 5321794.7489 | 74360.7489 | 36509451.687 | 28091500.5035 | 12500000 | 12500000 | 0 | 0 | 0 | 89600952.1905
PBUT8 | Substation | Substation Rebuilds | New Substation Vieques | 1920000 | 7520000 | 7260000 | 6308931.82 | 7200000 | 0 | 0 | 0 | 0 | 0 | 13508931.82
PBUT8 | Substation | Substation Rebuilds | New Substation Culebra | 3620000 | 4390000 | 5890000 | 5816863 | 4400000 | 0 | 0 | 0 | 0 | 0 | 10216863
PBUT8 | Substation | Substation Rebuilds | Punta Lima Sect. | 180000 | 3839289.55 | 6481532.43 | 12353183.26 | 6187949.88 | 6187949.88 | 0 | 0 | 0 | 0 | 24729083.02
PBUT8 | Substation | Substation Rebuilds | Unibon (Corozal) | 10101.24 | 10101.24 | 2307478.3 | 2707468.36 | 6733326.86 | 0 | 0 | 0 | 0 | 0 | 9440795.22
PBUT7 | Substation | Substation Reliability | Substation GRP B Islabela | 246000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Ponce TC | 0 | 0 | 25000 | 25000 | 50000 | 18600000 | 26600000 | 23100000 | 15550000 | 15550000 | 99475000
PBUT8 | Substation | Substation Rebuilds | Canas TC BKRS 115kV | 24000 | 1530000 | 3026573.15 | 10100000 | 10100000 | 28994014.9 | 15100000 | 16457721.6 | 50000 | 0 | 80801736.5
PBUT8 | Substation | Substation Rebuilds | VIEQUES SUB 2501 | 3340778.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | San Jose Relocation | 706804.0073 | 6211263.9247 | 7419228.438 | 2267053.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2267053.6
PBUT8 | Substation | Substation Rebuilds | Venezuela | 1024000 | 1020000 | 520000 | 15070000 | 15070000 | 10050000 | 170000 | 0 | 0 | 0 | 40360000
PBUT7 | Substation | Substation Reliability | Substation GRP B Jayuya | 396000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | MAUNABO TC | 1097576.2 | 574572.95 | 41617568.98 | 47708795.38 | 4138087.49 | 0 | 0 | 0 | 0 | 0 | 51846882.87
PBUT8 | Substation | Substation Rebuilds | Victoria TC 7008 (Elevated Con | 778492.57 | 695888.2525 | 16551897.185 | 16551897.185 | 16551897.185 | 1608207.25 | 15856008.9325 | 0 | 0 | 0 | 50568010.5525
PBUT8 | Substation | Substation Rebuilds | Berwind TC- Metalclad - 1336 | 127501.56 | 10834018.7875 | 28688132.28 | 10834018.7875 | 10834018.7875 | 15359764.7925 | 0 | 0 | 0 | 0 | 37027802.3675
PBUT8 | Substation | Substation Rebuilds | Charco Hondo 8008 Reloc | 751864.24 | 6162413.8987 | 6162413.8987 | 6162413.8987 | 0 | 0 | 0 | 0 | 0 | 0 | 6162413.8987
PBUT8 | Substation | Substation Rebuilds | Puerto Nuevo Metalclad 15 | 480000 | 3796260.688 | 3796260.688 | 3041246.365 | 2921246.365 | 0 | 0 | 0 | 0 | 0 | 5962492.73
PBUT8 | Substation | Substation Rebuilds | Esc. Industrial M. Such - Meta | 360000 | 7448148.39 | 3432846.39 | 3432846.39 | 0 | 0 | 0 | 0 | 0 | 0 | 3432846.39
PBUT8 | Substation | Substation Rebuilds | CACHETE MC 1526 | 2120000.04 | 13105188.6 | 10873190 | 7205188.24 | 6962530.12 | 0 | 0 | 0 | 0 | 0 | 14167718.36
PBUT8 | Substation | Substation Rebuilds | VIADUCTO TC MC 1100 | 129000 | 7412104.95 | 13624867.08 | 13624867.08 | 11624867.08 | 11624867.08 | 11624867.08 | 11624867.08 | 3397159.6 | 0 | 63521495
PBUT8 | Substation | Substation Rebuilds | LLORENS TORRES MC 1106 | 60000 | 12947591 | 8199355 | 1828856 | 1971155 | 0 | 0 | 0 | 0 | 0 | 3800011
PBUT8 | Substation | Substation Rebuilds | BAYAMON TC MC BRKRS Y1 | 1449213 | 655377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | TAPIA GIS REBUILT -1102 | 3429676.85 | 7886601.47 | 1548521.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | RIO GRANDE ESTATES - CH - 2306 | 6963688.84 | 11559200.85 | 4365440.85 | 4365440.86 | 0 | 0 | 0 | 0 | 0 | 0 | 4365440.86
PBUT8 | Substation | Substation Rebuilds | Cambalache TC Relocation | 920000 | 15204670.63 | 16338192.1 | 15204666.3 | 15204655.3 | 0 | 0 | 0 | 0 | 0 | 30409321.6
PBUT8 | Substation | Substation Rebuilds | San Juan SP TC | 7400000 | 15431779.65 | 25455778.61 | 18455779.24 | 13600779.24 | 2000 | 0 | 0 | 0 | 0 | 32058558.48
PBUT8 | Substation | Substation Rebuilds | CENTRO MEDICO 1 & 2 1327 & 1 | 8420000 | 6471034 | 6471034 | 4821034 | 0 | 0 | 0 | 0 | 0 | 0 | 4821034
PBUT8 | Substation | Substation Rebuilds | Monacillo TC - Breakers | 12690000 | 29020000 | 24870000 | 12550000 | 4150000 | 0 | 0 | 0 | 0 | 0 | 16700000
PBUT8 | Substation | Substation Rebuilds | Sabana Llana TC | 15888675 | 28920000 | 38320000 | 11035500 | 4700000 | 4700000 | 0 | 0 | 0 | 0 | 20435500
PBUT8 | Substation | Substation Rebuilds | COSTA SUR BKRS P001 | 9291768 | 3871580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | AGUIRRE BKRS T018 | 5415948 | 5415948 | 5415948 | 5415948 | 1504018 | 0 | 0 | 0 | 0 | 0 | 6919966
PBUT8 | Substation | Substation Rebuilds | CATANO MODER & HARD 1801 (Ele | 12978928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | PBUT8 Program Wedge | -17906152.5791 | -200000000 | -250000000 | -200000000 | 0 | 0 | 100000000 | 150000000 | 317906152.5791 | 100000000 | 467906152.5791
PBUT8 | Substation | Substation Rebuilds | Substation Rebuild-Fajardo TC | 692142.37 | 3281166.06 | 14924013.55 | 22333098.4 | 11219471.25 | 10584406.89 | 0 | 0 | 0 | 0 | 44136976.54
PBUT8 | Substation | Substation Rebuilds | Santa Isabel | 0 | 25000 | 25000 | 25000 | 1050000 | 18600000 | 26600000 | 26100000 | 26050000 | 50000 | 98475000

## Non-Federal Capital
FY26 NFC Total
Subsequent Periods
Program Brief | Portfolio | Program Brief Name | Project Name | FY26 NFC Total | 2027-06-01 | 2028-06-01 | 2029-06-01 | 2030-06-01 | 2031-06-01 | 2032-06-01 | 2033-06-01 | 2034-06-01 | 2035-06-01 | Total 29+
PBCS4 | Customer Experience | Retail Wheeling | Wheeling | 3073641.0256 | 15509586.6667 | 15512650.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP5 | Enabling | Tools Repair & Management | Operations Tools&Equip-Substat | 4222800 | 4391712 | 4567380.48 | 4750075.6992 | 4940078.7272 | 1900000 | 1900000 | 1900000 | 1900000 | 0 | 17290154.4264
PBOP5 | Enabling | Tools Repair & Management | Tools Repair & Management | 3201120.1231 | 3387554.6284 | 3583905.8627 | 3762406.9849 | 3938924.7612 | 3938924.7612 | 3938924.7612 | 3938924.7612 | 3938924.7612 | 3938924.7612 | 27395955.5518
PBOP6 | Enabling | Materials Management | OPMAT8 NME WOilFiEqOilC(Large) | 521640 | 542505.6 | 564205.824 | 586774.057 | 610245.0192 | 165000 | 165000 | 165000 | 165000 | 0 | 1857019.0762
PBOP6 | Enabling | Materials Management | TAShelix Mobile Platf.Implem. | 1501075.7576 | 325918.7879 | 130955.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP6 | Enabling | Materials Management | Warehouse Racks | 575000 | 598000 | 621920 | 646796.8 | 672668.67 | 0 | 0 | 0 | 0 | 0 | 1319465.47
PBOP6 | Enabling | Materials Management | Respooling Cable Machine | 529829.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP6 | Enabling | Materials Management | Pallet Jack and Loader Attachment | 53730.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT17 | Customer Experience | Meter Replacement & Maintenance | Net Metering Meter change | 6600000 | 5130000 | 3375000 | 2500000 | 1875000 | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 10375000
PBUT17 | Customer Experience | Meter Replacement & Maintenance | New Connections | 3504000 | 3000000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0 | 14400000
PBUT17 | Customer Experience | Meter Replacement & Maintenance | Non-NEM Meter Replacement | 2160000 | 1600000 | 1200000 | 911000 | 411000 | 205000 | 205000 | 0 | 0 | 0 | 1732000
PBUT17 | Customer Experience | Meter Replacement & Maintenance | TWACS Subst.Comm.Eq.Hardw.Upgr | 1745916.6667 | 1292553.3333 | 1320255.4667 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 3600000
PBUT22 | Control Center & Buildings | Critical Energy Management System Upgrades | Switch Order Management System | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT22 | Control Center & Buildings | Critical Energy Management System Upgrades | Data Center Backup/EMS La Torre Phisical Space | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT22 | Control Center & Buildings | Critical Energy Management System Upgrades | La Torre SSCA Group Reallocation | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT29 | Customer Experience | Standardized Metering & Meter Shop Setup | Meter Test Boards | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 0 | 1152000
PBIT2 | Support Services | IT OT Cybersecurity Program | Vulnerability Discovery (OT)
PBIT2 | Support Services | IT OT Cybersecurity Program | Cloud-based external attack surface management (EASM) solutions
PBIT2 | Support Services | IT OT Cybersecurity Program | Structured Data Protection Implementation`- High Priority
PBIT2 | Support Services | IT OT Cybersecurity Program | Network Segmentation - Phase 2
PBIT2 | Support Services | IT OT Cybersecurity Program | Network Detection & Response (NDR) - Next Generation IDS
PBIT2 | Support Services | IT OT Cybersecurity Program | Unstruc.DataProtec.&Classif.
PBIT3 | Support Services | IT OT Enablement Program | End User Device Management | 6090000 | 4030000 | 1900000 | 4000000 | 4000000 | 3954000 | 4000000 | 4000000 | 3954000 | 0 | 23908000
PBIT4 | Support Services | IT OT Asset Management | UPS de PBX Room | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 100000
PBIT4 | Support Services | IT OT Asset Management | Network Materials | 263755.5556 | 268305.7778 | 273038.0089 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000
PBIT4 | Support Services | IT OT Asset Management | CAT6A Replacement | 399999.96 | 400000 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 800000
PBIT4 | Support Services | IT OT Asset Management | FIBER Santurce and NEOM Complex Star | 150000 | 150000 | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000
PBIT4 | Support Services | IT OT Asset Management | FM200 | 158755.5556 | 163305.7778 | 168038.0089 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 90000
PBIT4 | Support Services | IT OT Asset Management | Racks for Secure Equipment | 80000 | 60000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 60000
PBIT4 | Support Services | IT OT Asset Management | UPS Communications Rooms | 349999.998 | 200000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
PBIT4 | Support Services | IT OT Asset Management | Network Tools for Troubleshooting | 263755.5556 | 218305.7778 | 223038.0089 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
PBIT4 | Support Services | IT OT Asset Management | Network Switches 100 | 810000 | 810000 | 810000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 800000
PBIT4 | Support Services | IT OT Asset Management | IT ProductionMigration toCloud | 458755.5556 | 118305.7778 | 123038.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | VDI For Azure Virtual Desktop | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Workforce Management System | 5013755.5556 | 10118305.7778 | 5123038.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | AVEVA Pi Hardware Tag Points Additions | 199999.98 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Compliance Management Software | 113755.5556 | 118305.7778 | 323038.0089 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 400000
PBIT4 | Support Services | IT OT Asset Management | SCADA EMS Hardware Lifecycle | 0 | 100000 | 200000 | 100000 | 300000 | 0 | 0 | 0 | 0 | 0 | 400000
PBIT4 | Support Services | IT OT Asset Management | SCADA Upgrade | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
PBIT4 | Support Services | IT OT Asset Management | IoT platform and Site monitoring solution | 199999.98 | 50000 | 50000 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 150000
PBIT4 | Support Services | IT OT Asset Management | DA Hardware lifecycle | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Infrastructure Legacy Hardware Replacement | 2499999.96 | 3640000 | 2940000 | 3360000 | 3640000 | 0 | 0 | 0 | 0 | 0 | 7000000
PBIT4 | Support Services | IT OT Asset Management | Mass Storage | 999999.96 | 1000000 | 7000000 | 1400000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 2800000
PBIT4 | Support Services | IT OT Asset Management | Consolidation Box | 170000.0004 | 170000 | 80000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 160000
PBIT4 | Support Services | IT OT Asset Management | SFp GBICS 10 GB | 60000 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 50000
PBIT4 | Support Services | IT OT Asset Management | KRONOS/ UKG Migration to Cloud | 1113755.5556 | 118305.7778 | 123038.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Starlink Satellite Enterprise Hardware | 1065195.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | OSI (Aveva) PI Hardware Replacement | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT4 | Support Services | IT OT Asset Management | Contract Management System | 2613755.5556 | 2618305.7778 | 123038.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT5 | Support Services | IT OT Collaboration & Analytics | Enterprise Document Management System | 2113755.5556 | 2118305.7778 | 2123038.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT5 | Support Services | IT OT Collaboration & Analytics | Record Retention/Data Management | 266755.5556 | 118305.7778 | 123038.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT5 | Support Services | IT OT Collaboration & Analytics | Data Strategy and Governance | 863755.5556 | 830805.7778 | 835538.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT5 | Support Services | IT OT Collaboration & Analytics | Datalake Expansion | 3113755.5556 | 2118305.7778 | 123038.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT5 | Support Services | IT OT Collaboration & Analytics | LINUX 8 Upgrade | 400000 | 300000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT5 | Support Services | IT OT Collaboration & Analytics | ORACLE DATABASE UPGRADE | 600000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT5 | Support Services | IT OT Collaboration & Analytics | Implementation of Process Mining and Automation Tools | 400000 | 700000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBHE8 | Enabling | Emergency Response Preparedness | Establish Emergency Op Center | 1350000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
PBFM4 | Support Services | Critical Financial Systems | AR/Revenue management module | 696075.7576 | 525918.7879 | 530955.5394 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 800000
PBFM4 | Support Services | Critical Financial Systems | Oracle EBS Version Upgrade | 621075.7576 | 125918.7879 | 130955.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM4 | Support Services | Critical Financial Systems | Grant Management | 1046075.7576 | 625918.7879 | 530955.5394 | 400000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0 | 1900000
PBFM4 | Support Services | Critical Financial Systems | Oracle Expense Module Implem. | 301075.7576 | 140918.7879 | 130955.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM4 | Support Services | Critical Financial Systems | Oracle Supporting Tools | 271075.7576 | 175918.7879 | 180955.5394 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 100000
PBFM4 | Support Services | Critical Financial Systems | Procure to Pay-ORACLE Implem. | 2121075.7576 | 725918.7879 | 630955.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM4 | Support Services | Critical Financial Systems | Time Rec. & Process Enhancem. | 1021075.7576 | 1625918.7879 | 1130955.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM4 | Support Services | Critical Financial Systems | Oracle enhancements and ERP replacement | 10121075.7576 | 10125918.7879 | 40130955.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT1 | Enabling | Compliance & Studies | Wildfire Mitigation | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT1 | Enabling | Compliance & Studies | DG Interconnect & Net Metering | 3824360.2782 | 4260520.9192 | 4746424.8089 | 5287745.0656 | 5890801.8148 | 6562635.9802 | 7311091.4884 | 8144906.8505 | 9073817.187 | 10108667.8895 | 52379666.2759
PBUT1 | Enabling | Compliance & Studies | PSSE Dynamic Data Collection | 632500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT1 | Enabling | Compliance & Studies | Substation Grounding AntiTheft | 2875000 | 3450000 | 3450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT1 | Enabling | Compliance & Studies | D Subs Sys Asset Plan & Size | 0 | 1437500 | 2875000 | 4312500 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 38812500
PBUT1 | Enabling | Compliance & Studies | Dist Line-Sys Lev Plan & Size | 0 | 1437500 | 2875000 | 4312500 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 38812500
PBUT1 | Enabling | Compliance & Studies | T Line-Sys Lev A. Plan & Size | 0 | 1437500 | 2875000 | 4312500 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 38812500
PBUT1 | Enabling | Compliance & Studies | T Subs Sys Asset Plan & Size | 0 | 1437500 | 2875000 | 4312500 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 38812500
PBUT13 | Transmission | Transmission Priority Pole Replacements | Capital Work Trans PoleReplace | 10000000 | 12053092.5858 | 16241881.1633 | 24908992.0758 | 26809291.979 | 21882220.5072 | 21882220.5072 | 21882220.5072 | 21882220.5072 | 21882220.5072 | 161129386.591
PBUT13 | Transmission | Transmission Priority Pole Replacements | 700-COSTA SUR SP-YAUCO 2 HP- | 166750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 800-COMSAT SECT - CIDRA SECT | 805000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 1700-GUANICA TC-YAUCO 2 HP- | 1380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3000-CAGUAS TC-CAGUAX SECT-F | 132250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3000-CAGUAX SECT-JUNCOS TC-F | 345000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3000-JUNCOS TC-RIO BLANCO HP-F | 1058000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3100-CAROLINA-CANOVANAS TC- | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 4500-CANAS TC - LA RAMBLA SECT | 1610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 10700-HATO TEJAS SECT-BAYAMON PUEBLO SECT- | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 16500-FAJARDO TC-DOS MARINAS- | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3200-Monacillos TC-Venezuela SECT | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 2300-Arecibo SECT-Cambalache TC | 253000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3600-Llorens Torres SECT-Martin Peña | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 7400-Hato Rey TC-Tres Monjitas SECT | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3300-Viaducto TC-Egozcue SECT | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3600-Sabana Llana TC-Los Ángeles SECT | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 10000-Bayamon Pueblo SECT-Magnolia TO | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3100-Canovanas SECT-Rio Grande TO | 805000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 3600-Monacillos TC-Sabana Llana TC | 345000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | 9400-Dorado TC-Toa Alta | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT13 | Transmission | Transmission Priority Pole Replacements | Engineering Transmission Corrective Maintenance (Priority 2) | 2875000 | 8625000 | 17825000 | 35075000 | 50025000 | 42550000 | 31625000 | 31625000 | 31625000 | 31625000 | 254150000
PBUT13 | Transmission | Transmission Priority Pole Replacements | Engineering Transmission Out of Service (Priority 2) | 0 | 12650000 | 15525000 | 21850000 | 21850000 | 21850000 | 21850000 | 21850000 | 21850000 | 21850000 | 152950000
PBUT13 | Transmission | Transmission Priority Pole Replacements | Engineering Transmission Corrective Maintenance (Priority 1) | 2875000 | 8625000 | 17825000 | 35075000 | 50025000 | 42550000 | 31625000 | 31625000 | 31625000 | 31625000 | 254150000
PBUT13 | Transmission | Transmission Priority Pole Replacements | Engineering Transmission Out of Service (Priority 1) | 0 | 12650000 | 15525000 | 21850000 | 21850000 | 21850000 | 21850000 | 21850000 | 21850000 | 21850000 | 152950000
PBUT27 | Enabling | Asset Data Integrity | Asset Tagging | 1725000 | 2605440 | 2605440 | 934724.6 | 172500 | 0 | 0 | 0 | 0 | 0 | 1107224.6
PBUT27 | Enabling | Asset Data Integrity | Asset Mgmt Info System Implementation | 2300000 | 2300000 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT27 | Enabling | Asset Data Integrity | GIS Improvements | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 2415000
PBUT27 | Enabling | Asset Data Integrity | Engineering Tools | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Programmable Repairs | 5531499 | 5642129 | 5754972 | 5870071 | 5987473 | 6107222 | 6229367 | 6353954 | 6481033 | 6610654 | 43639774
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Pole Replacement | 34500000 | 120750000 | 120750000 | 120750000 | 120750000 | 120750000 | 120750000 | 120750000 | 120750000 | 120750000 | 845250000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Engineering Distribution Corrective Maintenance (Priority 2) | 9200000 | 28750000 | 43125000 | 57500000 | 66125000 | 71300000 | 78775000 | 78775000 | 78775000 | 78775000 | 510025000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Engineering Distribution Out of Service (Priority 2) | 2875000 | 5750000 | 9200000 | 10350000 | 10350000 | 9775000 | 9775000 | 9775000 | 9775000 | 9775000 | 69575000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Engineering Distribution Corrective Maintenance (Priority 1) | 9200000 | 28750000 | 43125000 | 57500000 | 66125000 | 71300000 | 78775000 | 78775000 | 78775000 | 78775000 | 510025000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Engineering Distribution Out of Service (Priority 1) | 2875000 | 5750000 | 9200000 | 10350000 | 10350000 | 9775000 | 9775000 | 9775000 | 9775000 | 9775000 | 69575000
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Non Strutural Repairs Priority 1 | 5922499.977 | 17940000 | 17940000 | 17940000 | 12017500 | 0 | 0 | 0 | 0 | 0 | 29957500
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Non Strutural Repairs Priority 2 | 5922499.977 | 17940000 | 17940000 | 17940000 | 12017500 | 0 | 0 | 0 | 0 | 0 | 29957500
PBUT30 | Distribution | Distribution Pole & Conductor Repair | PRW-Distr.Pole.Repl.Mar-22-FWD | 20883308.4047 | 21196558.0307 | 21514506.4012 | 21837223.9972 | 22164782.3572 | 22497254.0925 | 22834712.9039 | 23177233.5975 | 23524892.1014 | 23877765.483 | 159913864.5327
PBUT30 | Distribution | Distribution Pole & Conductor Repair | 3rdPartyDamageUrgentPoleRepair | 1978198.2 | 2078906.472 | 2162062.7309 | 2226508.8315 | 1968233.8071 | 1853167.8306 | 1732711.9217 | 1606696.5092 | 1638830.4394 | 1671607.0481 | 12697756.3875
PBUT30 | Distribution | Distribution Pole & Conductor Repair | Dummy- System Stabilization | 0 | 106570 | 6185135 | 8084222 | 9227707 | 9739525 | 9318135 | 8893567 | 8301967 | 7700697 | 61265820
PBUT30 | Distribution | Distribution Pole & Conductor Repair | DISTRIBUTION- (PLAN-CM/PLAN-00S/Emergency) | 73254.5948 | -1603.1608 | 3721.6839 | -242321.9471 | -342219.3876 | -376262.8049 | -294020.7073 | -210544.9884 | -125816.4225 | -39817.4128 | -1631003.6706
PBUT33 | Transmission | Transmission Line Rebuild | Line 40600 Bayamon-Monacillos (UG Loop) | 3679990.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 2100 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 8700 | 11500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 16800 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 40700 | 287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 40500 | 287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 39300 | 287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 40000 | 287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 39200 | 287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 100/200 out of service segment | 287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Transmission Current Capacity Constraints | 2300000 | 4600000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 40250000
PBUT33 | Transmission | Transmission Line Rebuild | Transmission System Improvement (DER) | 2300000 | 4600000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 40250000
PBUT33 | Transmission | Transmission Line Rebuild | Line 1100 | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 9100 | 1725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Transmission Wildfire Mitigation Infrastructure Hardening | 5111111.1111 | 10222222.2222 | 16905000 | 28750000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 304750000
PBUT33 | Transmission | Transmission Line Rebuild | Line 41600 San Juan GIS to Palo Seco SP (UG Loop) | 0 | 3300500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Line 2200 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT33 | Transmission | Transmission Line Rebuild | Transmission OOS Lines - OH | 0 | 4600000 | 6900000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 80500000
PBUT33 | Transmission | Transmission Line Rebuild | Transmission OOS Lines - Underground | 0 | 5750000 | 9200000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 80500000
PBUT33 | Transmission | Transmission Line Rebuild | Transmission Capacity Upgrade (New Business) | 2300000 | 4600000 | 6900000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 64400000
PBUT39 | Distribution | Distribution Grid Reliability | Regional Reliability Improvements | 3450000 | 4025000 | 4600000 | 5175000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 39675000
PBUT39 | Distribution | Distribution Grid Reliability | Worst Performing Feeders | 9200000 | 10925000 | 12650000 | 14375000 | 16100000 | 17825000 | 19550000 | 21275000 | 23000000 | 23000000 | 135125000
PBUT4 | Distribution | Grid Automation | DA Test Equipment | 240350 | 249251 | 123740 | 27140 | 27140 | 27140 | 27140 | 27140 | 27140 | 27140 | 189980
PBUT4 | Distribution | Grid Automation | DA Replacement Reclosure Equipment (Emergent) | 619045 | 910800 | 1311920 | 1967420 | 1967420 | 1967420 | 1967420 | 1967420 | 1967420 | 1967420 | 13771940
PBUT4 | Distribution | Grid Automation | Distribution Automation (Wildfire Mitigation Infrastructure Hardening) | 1277777.7778 | 2555555.5556 | 7666666.6667 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 80500000
PBUT4 | Distribution | Grid Automation | Feeder Management System (FMS) | 896972.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlight Program Remaining work | 3866875 | 11931250 | 13627500 | 16962500 | 19801275 | 25012500 | 25012500 | 25012500 | 25012500 | 22136062.5 | 158949837.5
PBUT5 | Customer Experience | Distribution Streetlighting | UG Componet w Pole Replacement (No Aerial) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14806250 | 14806250 | 13503300 | 43115800
PBUT5 | Customer Experience | Distribution Streetlighting | Streetlight Poles with TPA (Octagonal poles ) | 416875 | 1667500 | 2084375 | 1634150 | 0 | 0 | 0 | 0 | 0 | 0 | 1634150
PBUT5 | Customer Experience | Distribution Streetlighting | Dusk To Dawn- LED requiered by Law | 172500 | 1725000 | 5175000 | 5002500 | 0 | 0 | 0 | 0 | 0 | 0 | 5002500
PBUT5 | Customer Experience | Distribution Streetlighting | Provisional Overhead (UG Secondary) | 0 | 0 | 0 | 17250000 | 34500000 | 57500000 | 57500000 | 57500000 | 57500000 | 57500000 | 339250000
PBUT6 | Distribution | Distribution Line Rebuild | UG System Repairs - NME | 5015739.8005 | 5165743.7543 | 5243500.1755 | 5560771.9755 | 5741874.2803 | 5861835.9429 | 5861835.9429 | 5861835.9429 | 5861835.9429 | 5861835.9429 | 40611825.9702
PBUT6 | Distribution | Distribution Line Rebuild | Distribution Capacity Constraints | 2300000 | 4600000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 40250000
PBUT6 | Distribution | Distribution Line Rebuild | Distribution New Business (50kvA or more) | 8050000 | 8050000 | 8050000 | 8050000 | 8050000 | 8050000 | 8050000 | 8050000 | 8050000 | 8050000 | 56350000
PBUT6 | Distribution | Distribution Line Rebuild | Distribution system improvement (DER) | 11500000 | 17250000 | 17250000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 80500000
PBUT6 | Distribution | Distribution Line Rebuild | UGWPF - Cables | 517483.9 | 517483.9 | 517483.9 | 517483.9 | 517483.9 | 517483.9 | 517483.9 | 517483.9 | 517483.9 | 517483.9 | 3622387.3
PBUT6 | Distribution | Distribution Line Rebuild | UGWPF - Switches | 1149995.4 | 1149995.4 | 1149995.4 | 1149995.4 | 1149995.4 | 1149995.4 | 1149995.4 | 1149995.4 | 1149995.4 | 1149995.4 | 8049967.8
PBUT6 | Distribution | Distribution Line Rebuild | Strategic Voltage Conversion | 3450000 | 3450000 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT6 | Distribution | Distribution Line Rebuild | Provisional OH (UG Primary) | 5532656.256 | 11500000 | 16100000 | 16100000 | 16100000 | 16100000 | 16100000 | 16100000 | 16100000 | 16100000 | 112700000
PBUT6 | Distribution | Distribution Line Rebuild | UG D Lines Repaired | 2300000 | 4600000 | 6900000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 80500000
PBUT6 | Distribution | Distribution Line Rebuild | Distribution (Wildfire Mitigation Infrastructure Hardening) | 2300000 | 5750000 | 11500000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 161000000
PBUT7 | Substation | Substation Reliability | Guanica TC - Transformer Replacement | 1770856.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Monacillo TC - Transformer Replacement Bank 1 and 3 | 6179715.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Bayamon TC - Transformer Replacement (Energize) | 2418620.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Caguas TC - Transformer Replacement (Energize) | 2143666.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Costa Sur - Transformer Replacement (Energize) | 2284050.673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Factor - Transformer Replacement (Energize) | 2530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Sabana Llana TC - Transformer Replacement (Energize) | 4203837.374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Fajardo - Transformer Replacement (Energize) | 3335000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Cybersecurity platform | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Grounding & Gravel | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 8050000
PBUT7 | Substation | Substation Reliability | PAC - RTU Costa Sur | 345000 | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Reliability (New Top WPS) | 862500 | 1725000 | 2990000 | 2990000 | 2990000 | 2990000 | 2990000 | 2990000 | 2990000 | 2990000 | 20930000
PBUT7 | Substation | Substation Reliability | Settings Repository | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation Batteries | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 4025000
PBUT7 | Substation | Substation Reliability | Substation Transformer Upgrades (Current Capacity Constraints) | 0 | 3450000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 48300000
PBUT7 | Substation | Substation Reliability | Substation Capacity Upgrades (New Business) | 2300000 | 4600000 | 6900000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 80500000
PBUT7 | Substation | Substation Reliability | Transformers "On-site" Preparation Costs | 45540000 | 19205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Maunabo - Transformer Replacement (Energize) | 1056154.273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Substation System Upgrades (DER) | 0 | 11500000 | 17250000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 161000000
PBUT7 | Substation | Substation Reliability | PAC - T Relays OOO Replacement | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 4025000
PBUT7 | Substation | Substation Reliability | PAC - RTU OOS Replacement | 920000 | 920000 | 920000 | 920000 | 920000 | 920000 | 920000 | 920000 | 920000 | 920000 | 6440000
PBUT7 | Substation | Substation Reliability | DFR - Digital Fault Recorder | 1725000 | 1725000 | 1725000 | 1725000 | 1725000 | 1725000 | 1725000 | 1725000 | 1725000 | 1725000 | 12075000
PBUT7 | Substation | Substation Reliability | D Breaker Programmatic Replacement | 0 | 0 | 0 | 5175000 | 5175000 | 5175000 | 5175000 | 5175000 | 5175000 | 5175000 | 36225000
PBUT7 | Substation | Substation Reliability | D Breaker OOS Replacement | 5175000 | 5175000 | 5175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | LTC Program - OOS | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 8050000
PBUT7 | Substation | Substation Reliability | T Breakers OOS Replacement | 5750000 | 5750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | T Breaker Programmatic Replacement | 0 | 0 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 40250000
PBUT7 | Substation | Substation Reliability | Transformers Programmatic Replacement | 345000 | 17250000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 161000000
PBUT7 | Substation | Substation Reliability | Distribution Transformers - OOS | 0 | 5750000 | 11500000 | 17250000 | 17250000 | 17250000 | 17250000 | 17250000 | 17250000 | 17250000 | 120750000
PBUT7 | Substation | Substation Reliability | Transmission Transformers - OOS | 0 | 5750000 | 11500000 | 17250000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 155250000
PBUT7 | Substation | Substation Reliability | Voltage Regulation / Optimiation (ie - Capacitor Banks) | 1437500 | 2300000 | 2875000 | 2875000 | 2875000 | 2875000 | 2875000 | 2875000 | 2875000 | 2875000 | 20125000
PBUT7 | Substation | Substation Reliability | Engineering Substation Corrective Maintenance (Priority 2) | 1150000 | 4025000 | 6900000 | 8625000 | 9775000 | 9775000 | 9775000 | 9775000 | 9775000 | 9775000 | 67275000
PBUT7 | Substation | Substation Reliability | Engineering Substation Corrective Maintenance (Priority 1) | 1150000 | 4025000 | 6900000 | 8625000 | 9775000 | 9775000 | 9775000 | 9775000 | 9775000 | 9775000 | 67275000
PBUT7 | Substation | Substation Reliability | Optical Sensors - Contracted | 3438500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Optical Sensors - Additional | 461943.96 | 3925368.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT7 | Substation | Substation Reliability | Emergent Replacements and Minor proactive replacements (Bucket) | 10000000 | 15973957.2 | 21143643 | 24934893 | 25693143 | 25807893 | 25807893 | 25807893 | 25807893 | 25807893 | 179667501
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation Aguirre | 150000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation Cambalache | 100000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation Costa Sur | 250000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation Hydro | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation Mayaguez | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation Palo Seco | 250000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation Peakers | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T & G Demarcation San Juan | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | T&G Demarcation | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT8 | Substation | Substation Rebuilds | Substation (Wildfire Mitigation Infrastructure Hardening) | 2555555.5556 | 5111111.1111 | 15333333.3333 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 23000000 | 161000000
PBUT38 | Customer Experience | New Business Connections | 14-01 New Transformers Instal | 2289720 | 2289720 | 2289720 | 2289720 | 2289720 | 2289720 | 2289720 | 2289720 | 2289720 | 2289720 | 16028040
PBUT38 | Customer Experience | New Business Connections | D&T-NB Evaluations | 5373566.6705 | 5373566.6705 | 5642245.004 | 5924357.2542 | 6220575.1169 | 6531603.8728 | 6858184.0664 | 7201093.2697 | 7561147.9332 | 7939205.3299 | 48236166.8432
PBUT38 | Customer Experience | New Business Connections | D&T-NB Endorsements | 1913600 | 1913600 | 2009280 | 2109744 | 2215231.2 | 2325992.76 | 2442292.398 | 2564407.0179 | 2692627.3688 | 2827258.7372 | 17177553.4819
PBUT38 | Customer Experience | New Business Connections | D&T-NB Inspections | 2945533.3295 | 2945533.3295 | 3092809.996 | 3247450.4958 | 3409823.0206 | 3580314.1716 | 3759329.8802 | 3947296.3742 | 4144661.1929 | 4351894.2525 | 26440769.3877
PBUT38 | Customer Experience | New Business Connections | D&T-NB System Upgrades | 1540080 | 1540080 | 1617084 | 1697938.2 | 1782835.11 | 1871976.8655 | 1965575.7088 | 2063854.4942 | 2167047.2189 | 2275399.5799 | 13824627.1773
PBUT38 | Customer Experience | New Business Connections | Electric Certifications | 862500 | 862500 | 905625 | 950906.25 | 998451.5625 | 1048374.1406 | 1100792.8477 | 1155832.49 | 1213624.1145 | 1274305.3203 | 7742286.7256
PBUT38 | Customer Experience | New Business Connections | Customer Portal - Applications | 575000 | 575000 | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBCS1 | Customer Experience | Modernize Customer Service Technology | Contact Center Platform (IVR | 125000 | 131250 | 137812.5 | 144703.125 | 151938.2813 | 159535.1953 | 167511.9551 | 175887.5528 | 184681.9305 | 193916.027 | 1178174.0669
PBCS1 | Customer Experience | Modernize Customer Service Technology | 15N006940000 Mi LUMA Website Redesign (Carimus) Cap Portion | 125000 | 131250 | 137812.5 | 144703.125 | 151938.2813 | 159535.1953 | 167511.9551 | 175887.5528 | 184681.9305 | 193916.027 | 1178174.0669
PBCS3 | Customer Experience | Billing Accuracy & Back Office | CC&B Upgrade to Cloud | 1083261.9048 | 1661592.381 | 1834728.0762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS- Furniture Projects Monacillo | 2900000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS- Furniture and Small Projects Arecibo Region | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS- Furniture and Small Projects Caguas Region | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Decommissioning Project (Luma Eqipment) | 500000.04 | 250000 | 250000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Decommissioning Project (Prepa Eqipment/Documents) | 500000.04 | 250000 | 250000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS - Furniture Projects | 5000000.04 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 35000000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS - HVAC Replacements | 6330036 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 3000000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS - Water Cisterns | 960000 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 150000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS Arecibo Region Projects | 2831199.96 | 75000 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 225000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS Bayamón Region Projects | 3951999.96 | 75000 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 225000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS Generator Acquisitions | 2959167.96 | 1000000 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 225000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS Mayaguez Region Projects | 1359999.96 | 75000 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 225000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS Ponce Region Projects | 8259999.96 | 75000 | 144000 | 144000 | 144000 | 144000 | 0 | 0 | 0 | 0 | 432000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS San Juan Region Projects | 14012799.96 | 144000 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 225000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS-CAGUAS REGIONAL PROJECT II | 8139999.96 | 75000 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 225000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Hormigerous Contact Cent NME | 1500000 | $- | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Women Bathrooms with showers in Operation Buildings | 180000 | $- | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Caparra CX consolidation with Guaynabo OPS | 600000 | $- | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Carolina CX consolidation with Carolina OPS | 600000 | $- | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | CIM to Plaza Carolina Lease Property | 249999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | DOC and Dispatch relocation to NEOM 1rst Floor | 1500000 | 0 | 200000 | 200000 | 200000 | 150000 | 150000 | 150000 | 150000 | 0 | 1000000
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Employees Ergonomic chairs | 1749999.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP1 | Enabling | T&D Fleet | helicopter repairs and inspections | 14800000 | 6000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBOP1 | Enabling | T&D Fleet | Fleet Capital Vehicle Purch. | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 322000000
PBOP1 | Enabling | T&D Fleet | Drone Project | 8923872.5 | 4738000 | 4612960.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBUT18 | Substation | Substation Physical Security | Locks for Distribution switche | 294000 | 294000 | 294000 | 294000 | 294000 | 294000 | 294000 | 294000 | 294000 | 0 | 1764000
PBUT18 | Substation | Substation Physical Security | Locks - 15 CIP LOW BES Sites | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 36000
PBUT19 | Control Center & Buildings | Regional Operations Physical Security | CCTV&accessCustomerExpFacility | 30000 | 30000 | 30000 | 30000 | 30000 | 36000 | 36000 | 36000 | 36000 | 0 | 204000
PBUT19 | Control Center & Buildings | Regional Operations Physical Security | CCTV&accessReg&Tech Facility | 99999.96 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 0 | 720000
PBUT19 | Control Center & Buildings | Regional Operations Physical Security | CCTV SatelliteWarehouses | 24999.96 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 0 | 180000
PBUT19 | Control Center & Buildings | Regional Operations Physical Security | CCTV&accessPaloSeco | 99999.96 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 0 | 360000
PBUT19 | Control Center & Buildings | Regional Operations Physical Security | CCTV&accessRegionalWarehouses | 24999.96 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 0 | 180000
PBUT19 | Control Center & Buildings | Regional Operations Physical Security | Fence SatelliteWarehouses | 30000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 0 | 144000
PBIT1 | Transmission | OT Telecom Systems & Network | Microwave Enhancements | 287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Pre-Substation-Rebuild Transport Network Enhance | 575000 | 1150000 | 1150000 | 1150000 | 1150000 | 575000 | 0 | 0 | 0 | 0 | 2875000
PBIT1 | Transmission | OT Telecom Systems & Network | Structural analysis for Telecom Structure | 322064.0796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBIT1 | Transmission | OT Telecom Systems & Network | Fiber - FY26 - Repair/Replace/DB | 2875000 | 2875000 | 2875000 | 1725000 | 1725000 | 862500 | 0 | 0 | 0 | 0 | 4312500
PBUT39 | Distribution | Distribution Grid Reliability | Reliability System Upgrades | 8050000 | 8050000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9775000 | 10350000 | 11500000 | 68425000

## O&M
FY26 O&M Total
|  |  |  | 200892329.7215 | Subsequent Periods
Program Brief | Portfolio | Program Brief Name | Project Name | FY26 O&M Total | 2027-06-01 | 2028-06-01 | 2029-06-01 | 2030-06-01 | 2031-06-01 | 2032-06-01 | 2033-06-01 | 2034-06-01 | 2035-06-01 | Total 29+
PBCS1 | Customer Experience | Modernize Customer Service Technology | First Call Resolution | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBCS2 | Customer Experience | Voice of the Customer | VOC Speech & Text Analytics | 333261.9048 | 336592.381 | 336592.381 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 500000
PBCS2 | Customer Experience | Voice of the Customer | VOC Customer Surveys | 313261.9048 | 306592.381 | 316592.381 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 500000
PBCS3 | Customer Experience | Billing Accuracy & Back Office | New Project CC&B Optimization | 3600000 | 6000000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | Facilities Empl.Training & Dev | 169820 | 174916 | 177540 | 180203 | 182906 | 0 | 0 | 0 | 0 | 0 | 363109
PBFM4 | Support Services | Critical Financial Systems | Artemis Reporting Tool (Splash BI reporting Tool) | 120000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
PBFM4 | Support Services | Critical Financial Systems | EBS Reporting Tool - Ad Hoc Reporting Tool (License/Subscription) | 180000 | 100000 | 100000 | 100000 | 60000 | 60000 | $ - | $ - | $ - | 0 | 220000
PBHE1 | Enabling | HSEQ and Technical Training | Safety at Heights | 412344.84 | 540000 | 540000 | 540000 | 540000 | 0 | 0 | 0 | 0 | 0 | 1080000
PBHE1 | Enabling | HSEQ and Technical Training | Lineman Excellence | 223353.48 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 54000
PBHE1 | Enabling | HSEQ and Technical Training | Switching Course | 206172.36 | 245000 | 245000 | 245000 | 245000 | 0 | 0 | 0 | 0 | 0 | 490000
PBHE1 | Enabling | HSEQ and Technical Training | Line Worker Program | 154629.36 | 170000 | 170000 | 170000 | 170000 | 0 | 0 | 0 | 0 | 0 | 340000
PBOP3 | Enabling | Workflow Processes & Tracking | Workforce Management O&M | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBRE2 | Support Services | Update to Third Party Use, Audit, Contract and Billing Procedures | Dummy TPA O&M TOTAL | 7640733.0688 | 7946000 | 8778000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBRE7 | Support Services | Electric Vehicle Implementation Support | Deploy.Electr.Veh.Charg.Infra. | 744861 | 744861 | 744861 | 744861 | 0 | 0 | 0 | 0 | 0 | 0 | 744861
PBUT7 | Substation | Substation Reliability | SUBSTATION- (PLAN-PM) | 20947900 | 20947900 | 20947900 | 20947900 | 20947900 | 20947900 | 20947900 | 20947900 | 20947900 | 20947900 | 146635300
PBUT32 | Transmission | Assessment of Transmission Lines | TRANSMISSION- (PLAN-PM) | 4184143.2 | 5811310 | 8135834 | 13107746 | 13107746 | 13107746 | 13107746 | 13107746 | 13107746 | 13107746 | 91754222
PBUT34 | Distribution | Distribution Lines Assessment | DISTRIBUTION- (PLAN-PM) | 3752787.9 | 8506319.24 | 14992483.05 | 21655808.85 | 29984966.1 | 33316629 | 33316629 | 33026055 | 33026055 | 33026055 | 217352197.95
PBOP6 | Enabling | Materials Management | The project should be deleted spend will be impacting at the CC. | 414720 | 431308.8 | 448561.152 | 466503.5981 | 485163.742 | 389000 | 389000 | 389000 | 389000 | 389000 | 2896667.3401
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS Facilit Tech Devel&Imp-II | 273641.0656 | 326586.6667 | 329650.1333 | 266200 | 292820 | 0 | 0 | 0 | 0 | 0 | 559020
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS-Facilities CapTeam Develop | 61000 | 51500 | 52272 | 53056 | 53852 | 0 | 0 | 0 | 0 | 0 | 106908
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS- DEEP CLEANNING ACTIVITIES | 500004 | 515000 | 522725 | 530565 | 538524 | 0 | 0 | 0 | 0 | 0 | 1069089
PBFM1 | Control Center & Buildings | Facilities Development & Implementation | FMS - Facilities Drawings | 200000 | 200006 | 203006.09 | 206051.1813 | 209141.9491 | 0 | 0 | 0 | 0 | 0 | 415193.1304
PBFM2 | Support Services | Critical Financial Controls | Finance & Accounting Policies (Citrin Cooperman) | 1200000 | 600000 | 450000 | 200000 | 150000 | $ - | $ - | $ - | $ - | $ - | 350000
PBFM2 | Support Services | Critical Financial Controls | Int Audit-Role & Resp and Res | 1321075.7576 | 1425918.7879 | 1430955.5394 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 9100000
PBFM2 | Support Services | Critical Financial Controls | Financial Systems Control (GRC Tool) | 150000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 700000
PBFM2 | Support Services | Critical Financial Controls | ERM & Insurance Tool - CC: 421 | 250000 | 150000 | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000
PBHE3 | Support Services | Public Safety | Public Safety Progr. Develop. | 101799.96 | 508500 | 508500 | 508500 | 689100 | 0 | 0 | 0 | 0 | 0 | 1197600
PBHE4 | Support Services | Waste Management | Waste Management | 1400000.92 | 1400000 | 1400000 | 1400000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 2800000
PBOP1 | Enabling | T&D Fleet | PBOP1 O&M | 22000000 | 24000000 | 24000000 | 24000000 | 24000000 | 0 | 0 | 0 | 0 | 0 | 48000000
PBOP7 | Enabling | Vegetation Management and Capital Clearing Implementation | OPVEG2 Reclamation T&D Sys ROW | 125000000 | 131250000 | 137812500 | 144703125 | 151938281.25 | 159535195.3125 | 167511955.0781 | 175887552.832 | 184681930.4736 | 193916026.9973 | 1178174066.9436
PBRE1 | Enabling | Lands & Permit Processes and Management | Develop Land and Permits Quality Mangement System | 836108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBRE5 | Support Services | Land Records Management | Land Record System | 600711 | 2027-06-01: 200000 | 0
PBUT31 | Customer Experience | Loss Recovery Program | NTL RedLosRecProg(Residential) | 1700000 | 1785000 | 1874250 | 1967962.5 | 2066360.625 | 2169678.6563 | 2278162.5891 | 2392070.7185 | 2511674.2544 | 2637257.9672 | 16023167.3104
PBUT31 | Customer Experience | Loss Recovery Program | Theft Detect Field Ins Com Ind | 0 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 2555000
PBUT31 | Customer Experience | Loss Recovery Program | NTL (Commercial & Industrial) | 0 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 3360000
PBUT31 | Customer Experience | Loss Recovery Program | TheftDetectFieldInspResidentia | 0 | 1410000 | 1410000 | 1410000 | 1410000 | 1410000 | 1410000 | 1410000 | 1410000 | 1410000 | 9870000
PBUT18 | Substation | Substation Physical Security | Landscaping &Veget.Control | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 |  |  |  | 5200000

## Model >>
#REF!

## 5.4 Imp Prog Summary
Improvement Portfolio and Program Summary
($ in 000s)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 15 | 16 | 17 | 18 | 19
[5 empty] | FY2026 |  |  |  |  | FY2027 |  |  |  |  | FY2028
|  | Portfolio | Program | PBCode | FY2026 Federal Funded CapEx | FY2026 Non-Federal Funded CapEx | FY2026 OpEx | Total |  | FY2027 Federal Funded CapEx | FY2027 Non-Federal Funded CapEx | FY2027 OpEx | Total |  | FY2028 Federal Funded CapEx | FY2028 Non-Federal Funded CapEx | FY2028 OpEx | Total
| 1 | Customer Experience |  |  | 261426861.9935 | 38565069.5971 | 6446523.8095 | 306438455.4001 |  | 434668515.0188 | 59471982.381 | 11183184.7619 | 505323682.1617 |  | 280072671.27 | 63128897.6762 | 11282434.7619 | 354484003.7081
| 2 |  | Distribution Streetlighting | PBUT5 | 141179641.5745 | 4456250 | 0 | 145635891.5745 |  | 144067873.1288 | 15323750 | 0 | 159391623.1288 |  | 49914054.4 | 20886875 | 0 | 70800929.4
| 3 |  | Billing Accuracy & Back Office | PBCS3 | 0 | 1083261.9048 | 3600000 | 4683261.9048 |  | 0 | 1661592.381 | 6000000 | 7661592.381 |  | 0 | 1834728.0762 | 6000000 | 7834728.0762
| 4 |  | Standardized Metering & Meter Shop Setup | PBUT29 | 0 | 192000 | 0 | 192000 |  | 0 | 192000 | 0 | 192000 |  | 0 | 192000 | 0 | 192000
| 5 |  | Modernize Customer Service Technology | PBCS1 | 0 | 250000 | 500000 | 750000 |  | 0 | 262500 | 500000 | 762500 |  | 0 | 275625 | 500000 | 775625
| 6 |  | Voice of the Customer | PBCS2 | 0 | 0 | 646523.8095 | 646523.8095 |  | 0 | 0 | 643184.7619 | 643184.7619 |  | 0 | 0 | 653184.7619 | 653184.7619
| 7 |  | Meter Replacement & Maintenance | PBUT17 | 0 | 14009916.6667 | 0 | 14009916.6667 |  | 0 | 11022553.3333 | 0 | 11022553.3333 |  | 0 | 8295255.4667 | 0 | 8295255.4667
| 8 |  | AMI Implementation Program | PBUT36 | 120247220.419 | 0 | 0 | 120247220.419 |  | 290600641.89 | 0 | 0 | 290600641.89 |  | 230158616.87 | 0 | 0 | 230158616.87
| 9 |  | Loss Recovery Program | PBUT31 | 0 | 0 | 1700000 | 1700000 |  | 0 | 0 | 4040000 | 4040000 |  | 0 | 0 | 4129250 | 4129250
| 10 |  | New Business Connections | PBUT38 | 0 | 15500000 | 0 | 15500000 |  | 0 | 15500000 | 0 | 15500000 |  | 0 | 16131764 | 0 | 16131764
| 11 |  | Retail Wheeling | PBCS4 | 0 | 3073641.0256 | 0 | 3073641.0256 |  | 0 | 15509586.6667 | 0 | 15509586.6667 |  | 0 | 15512650.1333 | 0 | 15512650.1333
| 12 | Distribution |  |  | 202371821.2039 | 164811280.51 | 3752787.9 | 370935889.6139 |  | 344740716.4965 | 343401389.9518 | 8506319.24 | 696648425.6883 |  | 326493912.6075 | 409513703.9581 | 14992483.05 | 751000099.6156
| 13 |  | Distribution Line Rebuild | PBUT6 | 23311671.2379 | 42115875.3565 | 0 | 65427546.5944 |  | 95045716.4965 | 62033223.0543 | 0 | 157078939.5509 |  | 132735608.1075 | 77060979.4755 | 0 | 209796587.5829
| 14 |  | Distribution Pole & Conductor Repair | PBUT30 | 89250000 | 98961260.1535 | 0 | 188211260.1535 |  | 105945000 | 254652560.3419 | 0 | 360597560.3419 |  | 52500000 | 296900397.816 | 0 | 349400397.816
| 15 |  | Grid Automation | PBUT4 | 89810149.966 | 3034145 | 0 | 92844294.966 |  | 143750000 | 3715606.5556 | 0 | 147465606.5556 |  | 141258304.5 | 9102326.6667 | 0 | 150360631.1667
| 16 |  | Distribution Grid Reliability | PBUT39 | 0 | 20700000 | 0 | 20700000 |  | 0 | 23000000 | 0 | 23000000 |  | 0 | 26450000 | 0 | 26450000
| 17 |  | Distribution Lines Assessment | PBUT34 | 0 | 0 | 3752787.9 | 3752787.9 |  | 0 | 0 | 8506319.24 | 8506319.24 |  | 0 | 0 | 14992483.05 | 14992483.05
| 18 | Transmission |  |  | 62488337.61 | 68850665.9907 | 4184143.2 | 135523146.8007 |  | 227072620.2457 | 96300814.8081 | 5811310 | 329184745.0538 |  | 417698016.7155 | 138371881.1633 | 8135834 | 564205731.8788
| 19 |  | OT Telecom Systems & Network | PBIT1 | 23571702.0064 | 4059564.0796 | 0 | 27631266.086 |  | 52137248.1964 | 4025000 | 0 | 56162248.1964 |  | 98762189.9413 | 4025000 | 0 | 102787189.9413
| 20 |  | Transmission Line Rebuild | PBUT33 | 19798775.1786 | 40416101.9111 | 0 | 60214877.0897 |  | 139415372.0493 | 37672722.2222 | 0 | 177088094.2715 |  | 280292086.7743 | 51405000 | 0 | 331697086.7743
| 21 |  | Transmission Priority Pole Replacements | PBUT13 | 19117860.425 | 24375000 | 0 | 43492860.425 |  | 35520000 | 54603092.5858 | 0 | 90123092.5858 |  | 38643740 | 82941881.1633 | 0 | 121585621.1633
| 22 |  | Assessment of Transmission Lines | PBUT32 | 0 | 0 | 4184143.2 | 4184143.2 |  | 0 | 0 | 5811310 | 5811310 |  | 0 | 0 | 8135834 | 8135834
| 23 | Substations |  |  | 154196935.4398 | 115177900.4946 | 22247900 | 291622735.9344 |  | 287348461.4695 | 123985437.1066 | 22247900 | 433581798.5762 |  | 340455028.4385 | 150511976.3333 | 22247900 | 513214904.7719
| 24 |  | Substation Rebuilds | PBUT8 | 101468197.9482 | 3755555.5556 | 0 | 105223753.5038 |  | 186861416.7202 | 6611111.1111 | 0 | 193472527.8313 |  | 197498409.0985 | 15333333.3333 | 0 | 212831742.4319
| 25 |  | Substation Reliability | PBUT7 | 45258737.4916 | 111122344.939 | 20947900 | 177328982.4306 |  | 96483044.7493 | 117074325.9955 | 20947900 | 234505270.7448 |  | 142956619.34 | 134878643 | 20947900 | 298783162.34
| 26 |  | Substation Physical Security | PBUT18 | 7470000 | 300000 | 1300000 | 9070000 |  | 4004000 | 300000 | 1300000 | 5604000 |  | 0 | 300000 | 1300000 | 1600000
| 27 | Control Center & Buildings |  |  | 34931047 | 67465203.31 | 1204465.0656 | 103600715.3756 |  | 58784254 | 8363000 | 1268008.6667 | 68415262.6667 |  | 67258146.73 | 7638000 | 1285193.2233 | 76181339.9533
| 28 |  | Facilities Development & Implementation | PBFM1 | 11061388 | 64205203.47 | 1204465.0656 | 76471056.5356 |  | 18803013 | 8069000 | 1268008.6667 | 28140021.6667 |  | 15943946 | 7344000 | 1285193.2233 | 24573139.2233
| 29 |  | Critical Energy Management System Upgrades | PBUT22 | 14923222 | 2950000 | 0 | 17873222 |  | 6033411 | 0 | 0 | 6033411 |  | 11174927.73 | 0 | 0 | 11174927.73
| 30 |  | Control Center Construction & Refurbishment | PBUT24 | 8946437 | 0 | 0 | 8946437 |  | 33947830 | 0 | 0 | 33947830 |  | 40139273 | 0 | 0 | 40139273
| 32 |  | Regional Operations Physical Security | PBUT19 | 0 | 309999.84 | 0 | 309999.84 |  | 0 | 294000 | 0 | 294000 |  | 0 | 294000 | 0 | 294000
| 33 | Enabling |  |  | 179816787.0155 | 96370928.2288 | 149347328.04 | 425535043.2844 |  | 290021334.3421 | 84794651.9355 | 156663308.8 | 531479295.0776 | 0 | 439361069.2073 | 90128193.0151 | 163243061.152 | 692732323.3744
| 34 |  | Vegetation Management and Capital Clearing Implementation | PBOP7 | 133379828.93 | 0 | 125000000 | 258379828.93 |  | 204006016.8211 | 0 | 131250000 | 335256016.8211 |  | 348801067.1193 | 0 | 137812500 | 486613567.1193
| 35 |  | T&D Fleet | PBOP1 | 0 | 69723872.5 | 22000000 | 91723872.5 |  | 0 | 56738000 | 24000000 | 80738000 |  | 0 | 55612960.5 | 24000000 | 79612960.5
| 36 |  | Tools Repair & Management | PBOP5 | 0 | 7423920.1231 | 0 | 7423920.1231 |  | 0 | 7779266.6284 | 0 | 7779266.6284 |  | 0 | 8151286.3427 | 0 | 8151286.3427
| 37 |  | HSEQ and Technical Training | PBHE1 | 0 | 0 | 996500.04 | 996500.04 |  | 0 | 0 | 982000 | 982000 |  | 0 | 0 | 982000 | 982000
| 38 |  | Project Management Software and Tools | PBCP4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 39 |  | Asset Data Integrity | PBUT27 | 0 | 5060000 | 0 | 5060000 |  | 0 | 5250440 | 0 | 5250440 |  | 0 | 5250440 | 0 | 5250440
| 40 |  | Emergency Response Preparedness | PBHE8 | 0 | 1350000 | 0 | 1350000 |  | 0 | 100000 | 0 | 100000 |  | 0 | 100000 | 0 | 100000
| 41 |  | Workflow Processes & Tracking | PBOP3 | 0 | 0 | 100000 | 100000 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 42 |  | Materials Management | PBOP6 | 249480 | 3181275.3276 | 414720 | 3845475.3276 |  | 259459.2 | 1466424.3879 | 431308.8 | 2157192.3879 |  | 269837.568 | 1317081.3634 | 448561.152 | 2035480.0834
| 43 |  | Lands & Permit Processes and Management | PBRE1 | 0 | 0 | 836108 | 836108 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 44 |  | Compliance & Studies | PBUT1 | 11067000 | 9631860.2782 | 0 | 20698860.2782 |  | 9000000 | 13460520.9192 | 0 | 22460520.9192 |  | 4500000 | 19696424.8089 | 0 | 24196424.8089
| 45 |  | Microgrid Installation and Integration | PBUT37 | 35120478.0855 | 0 | 0 | 35120478.0855 |  | 76755858.321 | 0 | 0 | 76755858.321 |  | 85790164.52 | 0 | 0 | 85790164.52
| 46 | 1: Support Services | 0
| 47 |  | Electric Vehicle Implementation Support | PBRE7 | 0 | 0 | 744861 | 744861 |  | 0 | 0 | 744861 | 744861 |  | 0 | 0 | 744861 | 744861
| 49 | 2: IT OT Asset Management; 3: PBIT4; 5: 18085240.2429; 6: 0; 11: 20896446.2222; 17: 18664304.0711; 18: 0
| 50 |  | Critical Financial Controls | PBFM2 | 0 | 0 | 2921075.7576 | 2921075.7576 |  | 0 | 0 | 2275918.7879 | 2275918.7879 |  | 0 | 0 | 2130955.5394 | 2130955.5394
| 51 |  | Public Safety | PBHE3 | 0 | 0 | 101799.96 | 101799.96 |  | 0 | 0 | 508500 | 508500 |  | 0 | 0 | 508500 | 508500
| 52 |  | IT OT Collaboration & Analytics | PBIT5 | 0 | 7758022.2222 | 0 | 7758022.2222 |  | 0 | 6685723.1111 | 0 | 6685723.1111 |  | 0 | 4704652.0356 | 0 | 4704652.0356
| 53 |  | Update to Third Party Use, Audit, Contract and Billing Procedures | PBRE2 | 0 | 0 | 7640733.0688 | 7640733.0688 |  | 0 | 0 | 7946000 | 7946000 |  | 0 | 0 | 8778000 | 8778000
| 55 |  | Land Record Management | PBRE5 | 0 | 0 | 600711 | 600711 |  | 0 | 0 | 200000 | 200000 |  | 0 | 0 | 0 | 0
| 56 |  | Critical Financial Systems | PBFM4 | 0 | 16198606.0606 | 300000 | 16498606.0606 |  | 0 | 14072350.303 | 175000 | 14247350.303 |  | 0 | 43397644.3152 | 175000 | 43572644.3152
| 57 |  | Waste Management | PBHE4 | 0 | 0 | 1400000.92 | 1400000.92 |  | 0 | 0 | 1400000 | 1400000 |  | 0 | 0 | 1400000 | 1400000
| 58 | 2: IT OT Cybersecurity Program; 3: PBIT2
| 59 |  | IT OT Enablement Program | PBIT3 | 0 | 6090000 | 0 | 6090000 |  | 0 | 4030000 | 0 | 4030000 |  | 0 | 1900000 | 0 | 1900000
60
| 61 | 1: Total

## Portfolio Summary
Portfolio Budget Summary
2026 Budget by Portfolio
$ in dollars
| Row Labels | FY2026 Federal Funded CapEx | FY2026 Non-Federal Funded CapEx | FY2026 OpEx CapEx
| Customer Experience | 261426861.9935 | 38565069.5971 | 6446523.8095
| Distribution | 202371821.2039 | 164811280.51 | 3752787.9
| Enabling | 179816787.0155 | 96370928.2288 | 149347328.04
| Substation | 154196935.4398 | 115177900.4946 | 22247900
Support Services
| Transmission | 62488337.61 | 68850665.9907 | 4184143.2
| Control Center & Buildings | 34931047 | 67465203.31 | 1204465.0656
Grand Total
2027 Budget by Portfolio
$ in dollars
| Row Labels | FY2027 Federal Funded CapEx | FY2027 Non-Federal Funded CapEx | FY2027 OpEx CapEx
| Customer Experience | 434668515.0188 | 59471982.381 | 11183184.7619
| Distribution | 344740716.4965 | 343401389.9518 | 8506319.24
| Enabling | 290021334.3421 | 84794651.9355 | 156663308.8
| Substation | 287348461.4695 | 123985437.1066 | 22247900
Support Services
| Transmission | 227072620.2457 | 96300814.8081 | 5811310
| Control Center & Buildings | 58784254 | 8363000 | 1268008.6667
Grand Total
2028 Budget by Portfolio
$ in dollars
| Row Labels | FY2028 Federal Funded CapEx | FY2028 Non-Federal Funded CapEx | FY2028 OpEx CapEx
| Customer Experience | 280072671.27 | 63128897.6762 | 11282434.7619
| Distribution | 326493912.6075 | 409513703.9581 | 14992483.05
| Enabling | 439361069.2073 | 90128193.0151 | 163243061.152
| Substation | 340455028.4385 | 150511976.3333 | 22247900
Support Services
| Transmission | 417698016.7155 | 138371881.1633 | 8135834
| Control Center & Buildings | 67258146.73 | 7638000 | 1285193.2233
Grand Total
2029+ Total Portfolio Spend
$ in dollars
| Row Labels | FY2029+ Federal Funded CapEx | FY2029+ Non-Federal Funded CapEx | FY2029+ OpEx CapEx
| Customer Experience | 118220097.721 | 711017079.2497 | 32808167.3104
| Distribution | 2066941315.3188 | 3261522312.3199 | 217352197.95
| Enabling | 1223375648.7367 | 581214485.4003 | 1231034734.2837
| Substation | 2572467280.7661 | 1364012501 | 151835300
Support Services
| Transmission | 1780878814.9606 | 1593166886.591 | 91754222
| Control Center & Buildings | 77637777 | 43120000 | 2513319.1304
Grand Total
Portfolio Summary by Spending Type 2026-2028
| Federal Funded Portfolio Summary |  |  |  |  | Non-Federal Funded Portfolio Summary |  |  |  |  | OpEx Portfolio Summary
| $ in dollars |  |  |  |  | $ in dollars |  |  |  |  | $ in dollars
| Row Labels | FY2026 Federal Funded CapEx | FY2027 Federal Funded CapEx | FY2028 Federal Funded CapEx |  | Row Labels | FY2026 Non-Federal Funded CapEx | FY2027 Non-Federal Funded CapEx | FY2028 Non-Federal Funded CapEx |  | Row Labels | FY2026 OpEx CapEx | FY2027 OpEx CapEx | FY2028 OpEx CapEx
| Customer Experience | 261426861.9935 | 434668515.0188 | 280072671.27 |  | Customer Experience | 38565069.5971 | 59471982.381 | 63128897.6762 |  | Customer Service | 6446523.8095 | 11183184.7619 | 11282434.7619
| Distribution | 202371821.2039 | 344740716.4965 | 326493912.6075 |  | Distribution | 164811280.51 | 343401389.9518 | 409513703.9581 |  | Distribution | 3752787.9 | 8506319.24 | 14992483.05
| Enabling | 179816787.0155 | 290021334.3421 | 439361069.2073 |  | Enabling | 96370928.2288 | 84794651.9355 | 90128193.0151 |  | Enabling | 149347328.04 | 156663308.8 | 163243061.152
| Substation | 154196935.4398 | 287348461.4695 | 340455028.4385 |  | Substation | 115177900.4946 | 123985437.1066 | 150511976.3333 |  | Substations
| Support Services |  |  |  |  | Support Services |  |  |  |  | Support Services | 13709181.7064 | 13250279.7879 | 13737316.5394
| Transmission | 62488337.61 | 227072620.2457 | 417698016.7155 |  | Transmission | 68850665.9907 | 96300814.8081 | 138371881.1633 |  | Transmission | 4184143.2 | 5811310 | 8135834
| Control Center & Buildings | 34931047 | 58784254 | 67258146.73 |  | Control Center & Buildings | 67465203.31 | 8363000 | 7638000 |  | Control Center & Buildings | 1204465.0656 | 1268008.6667 | 1285193.2233
| Grand Total |  |  |  |  | Grand Total |  |  |  |  | Grand Total
Intial Budget Tables for Regulatory Filing
Initial Budget Spending Estimate
$ in dollars
| Row Labels | FY2026 Federal Funded CapEx | FY2026 Non-Federal Funded CapEx | FY2026 OpEx CapEx | FY2027 Federal Funded CapEx | FY2027 Non-Federal Funded CapEx | FY2027 OpEx CapEx | FY2028 Federal Funded CapEx | FY2028 Non-Federal Funded CapEx | FY2028 OpEx CapEx
| Customer Experience | 261426861.9935 | 38565069.5971 | 6446523.8095 | 434668515.0188 | 59471982.381 | 11183184.7619 | 280072671.27 | 63128897.6762 | 11282434.7619
| Distribution | 202371821.2039 | 164811280.51 | 3752787.9 | 344740716.4965 | 343401389.9518 | 8506319.24 | 326493912.6075 | 409513703.9581 | 14992483.05
| Enabling | 179816787.0155 | 96370928.2288 | 149347328.04 | 290021334.3421 | 84794651.9355 | 156663308.8 | 439361069.2073 | 90128193.0151 | 163243061.152
| Substation | 154196935.4398 | 115177900.4946 | 22247900 | 287348461.4695 | 123985437.1066 | 22247900 | 340455028.4385 | 150511976.3333 | 22247900
Support Services
| Transmission | 62488337.61 | 68850665.9907 | 4184143.2 | 227072620.2457 | 96300814.8081 | 5811310 | 417698016.7155 | 138371881.1633 | 8135834
| Control Center & Buildings | 34931047 | 67465203.31 | 1204465.0656 | 58784254 | 8363000 | 1268008.6667 | 67258146.73 | 7638000 | 1285193.2233
Grand Total
Initial Budget Spending Summary
$ in millions
Fiscal Year 2026-2028 Total Portfolio Spending
| Portfolio | Federal Funded-Funded Capital | Non-Federal Funded Funded Capital | O&M | Total
| Customer Experience | 976168048.2823 | 161165949.6542 | 28912143.3333 | 1166246141.2699
| Distribution | 873606450.3079 | 917726374.4199 | 27251590.19 | 1818584414.9178
| Enabling | 909199190.5649 | 271293773.1794 | 469253697.992 | 1649746661.7363
| Substation | 782000425.3479 | 389675313.9345 | 66743700 | 1238419439.2824
Support Services
| Transmission | 707258974.5712 | 303523361.962 | 18131287.2 | 1028913623.7332
| Control Center & Buildings | 160973447.73 | 83466203.31 | 3757666.9556 | 248197317.9956
Grand Total