## Sheet1
Attachment H
Genera Monthly Reporting Requirements - Generation Maintenance
Thermal Generation Facility Maintenance Report
Aguirre, Costa Sur, Palo Seco, San Juan Power Plants
Monthly Reporting
As of August 31, 2024
NO. | POWER PLANT | UNIT NUMBER | PROJECT ACTIVITY | CATEGORY | ACTIVITY BUDGET | START DATE | COMPLETION DATE | ACTIVITY STATUS - PERCENTAGE FOR COMPLETION | PROCUREMENT / BID (S) NUMBER | POC - MAINTENANCE ACTIVITY | CONTRACTOR/SUPPLIER | APPROVED FOR PAYMENT
1 | Costa Sur |  | Repair of the Water Treatment System for Water of Process | NME | 1390000 | 2024-12-01 | 2025-12-31 | PROCUREMENT |  | Operations | ICT
2 | Aguirre |  | Generator Spare Rotor Rewind | NME | 295382 | TBD | TBD | PROCUREMENT |  | Operations | Siemens
3 | Aguirre |  | Structural Rehabilitation Nautilus Water Tank, Water Treatment Plant | Federal | 1550000 | TBD | TBD | PLANNING | C-102348 | Manuel Cortés | CSA Artchitects Engineers | 1308605.14
4 | Aguirre CC | 1-4 | Hot Gas Inspection 1-4 (HGPI 1-4) | NME | 2282742 | 2025-07-14 | 2025-11-11 | EXECUTION | C-106760 | José Vázquez | MD&A | 637211.1
5 | Aguirre CC |  | Gas Turbine Rotor Refurbish MS7001B/AE | NME | 2000900 | TBD | TBD | PROCUREMENT | C-105235 | José Vázquez | MD&A
6 | Mayagüez |  | Inspection and Maintenance 4 Generator Brush | NME | 1847478 | 2025-02-06 | 2025-12-31 | EXECUTION | C-104923 | José Vázquez | GESA
7 | Cambalache | 2 | Unit 2 Inspection C - Manpower and Spare Parts | NME | 37500000 | TBD | TBD | PROCUREMENT |  | José Vázquez | GE
8 | Cambalache |  | Structural Rehabilitation Fuel Tank D-2 | NME | 1598000 | 2024-06-10 | 2025-12-31 | EXECUTION | C-101295 | Luis López | All Contractors | 811546.87
9 | San Juan | 6 | Replacement of the Online Condenser Cleaner Unit 6 | NME | 2394350 | 2023-03-21 | 2025-12-15 | EXECUTION | C-98349 | Luis López | RG Engineering | 2394350
10 | Aguirre |  | Reconstruction of the Discharge Channel Pumping Station Structure | NME | 7840078.47 | TBD | TBD | PLANNING | REQ.284037 | Manuel Cortés
11 | Aguirre CC | 1-3 | Major inspection Unit 1-3 | Federal | 3750000 | 2024-09-16 | TBD | EXECUTION | C-104889 | José Vázquez | RG Engineering | 593260.75
12 | Aguirre | 1-4 | Replacement of Load Center 1-4 Condenser Circulating Water Pump | Federal | 820000 | 2024-09-15 | 2026-06-30 | EXECUTION | C-101421 | Luis Ortiz | Allied Power
13 | Aguirre |  | Traveling Screen Project 316B | EPA | 5300000 | 2025-03-01 | 2026-11-21 | PROCUREMENT | C-98328 | Manuel Cortés | RG Engineering | 739091.69
14 | San Juan | 5 | Replacement of the Online Condenser Cleaner Unit 5 | Federal | 1117328 | 2025-05-31 | 06/31/2026 | AWARDED |  | Luis López | Malnat
15 | San Juan | 6 | Unit 6 - Major Overhaul (ST Repairs) | Federal | 13692168.2 | 2025-01-14 | 2025-10-15 | EXECUTION | C-105509 | José Vázquez | MD&A | 4290284.64
16 | San Juan | 7 | SJ7 Mayor Maintenance (Boiler & Aux) | NME/Federal | 4743347 | 2025-02-24 | 2025-07-31 | EXECUTION |  | Fernando Rivera | Various | 827856
17 | San Juan | 7 | Unit 7 Rehabilitation ( Turbine) | Federal | 16169151.67 | 2025-04-01 | 2025-10-17 | EXECUTION | C-108148 | Fernando Rivera | MD&A | 2896437.78
18 | San Juan | 5&6 | Liner Rehabilitation Fuel Service Tanks Units 5&6 | Federal | 2504728 | TBD | TBD | PROCUREMENT | C- 102348 | Fernando Rivera | CSA | 1308605.14
19 | Palo Seco | 3 | Update Voltage Regulation System Unit 3, Palo Seco Power Plant | Federal | 294082 | 2024-04-15 | Next Env Outage | EXECUTION | C-101258 | Robert Rosario | ESI | 119103.21
20 | Palo Seco |  | Upgrade OSI DCS | Federal | 2445496 | 2024-10-01 | 2025-11-13 | EXECUTION | C- 103154 | Robert Rosario | Emerson | 733678.76
21 | Costa Sur | 5 | Replacement of Excitation System Units 5 | Federal | 1583848 | 2024-09-01 | 2025-12-31 | EXECUTION | C-102867 | Robert Rosario | ESI | 791924
22 | Costa Sur |  | Replacement of Unit 6 Electric Load Center | NME | 265000 | 2022-11-30 | 2025-11-25 | EXECUTION | C-97578 | Luis Ortiz | Allied Power | 213777
23 | Costa Sur |  | Traveling Screens Replacement | Federal | 5000000 | TBD | TBD | PLANNING |  | Manuel Cortés
24 | Costa Sur | 6-1 | CCWP 6-1 Repair Works | Federal | 417657 | 2024-12-30 | 2025-07-30 | EXECUTION | C-107189 | Luis Ortiz | Reliable Industrial | 194605
25 | Aguirre |  | ASP Phase 4 Stage 1 - Demineralized Water System (Design) | EPA | 4039947.71 | TBD | TBD | PROCUREMENT | C-102062 | Luis López | Integra | 2173193
26 | Aguirre |  | ASP Phase 4 Stage 2 - Advanced Water Treatment System, Pump Stations, Piping Interconnections & Integration | NME | 784612 | 2025-10-28 | 2025-12-13 | PLANNING | C-102062 | Luis López | Integra | 73092.5
27 | Costa Sur |  | Upgrade to Foxboro Simulation System | Federal | 1053215 | 2025-01-21 | 2025-09-30 | EXECUTION | C-103503 | Robert Rosario | LT Automation | 874708.5
28 | San Juan | 7&9 | Hanger Assessment (Unit 7 & 9) | Federal | 249094 | 2024-12-02 | 2025-12-31 | ISSUED | C-104735 | Fernando Rivera | Enersys | 74728
29 | Costa Sur | 5 | Manufacture and Delivery of Bifurcate (Boiler) Tubes Unit 5 | NME | 255110 | TBD | TBD | PROCUREMENT | MR-871412 | Fernando Rivera | GE | 255110
30 | Palo Seco |  | New Demineralized Water Tank #2 | Federal | 2450000 | 2024-09-03 | 2025-09-03 | EXECUTION | C-102570 | Manuel Cortés | Alonso & Carus | 1356199.56
31 | Aguirre CC | GT 2-3 | Major inspection of units GT 2-3. | NME | 6400000 | TBD | TBD | PROCUREMENT | REQ. 285838 | José Vázquez
32 | Palo Seco | 4 | Major & Environment Maintenance PS4 | Federal | 9000000 | 2023-08-06 | 2025-08-04 | EXECUTION |  | Fernando Rivera | Varios | 18089869
33 | Palo Seco | 4 | Generator Repair PS4 | Federal | 15200000 | 2024-07-31 | 2024-08-04 | EXECUTION | C-104814 | Robert Rivera | Ethos Energy Power | 10298196.17
34 | San Juan | 9 | Major Overhaul SJ9 | Federal | 34579912.99 | TBD | TBD | PLANNING |  | José Vázquez
35 | San Juan | 7 | Condenser Rehabilitation SJ7 | NME | 150000 | TBD | TBD | PROCUREMENT |  | Fernando Rivera
36 | Costa Sur |  | Tanques Raw Water 1&2 | Federal | 4065000 | 2023-03-08 | 2025-07-30 | CANCELLED | C-98193 | Greg Hernández | Alonso & Carus | 4275457.01
37 | Costa Sur |  | Administrative Building Structural Retrofit & Interior Design and Office Equip | Federal | 6391783.22 | 2022-07-06 | 2025-07-30 | EXECUTION | C-93555 | Carlos Negrón | Del Valle Group | 6131212.32
38 | Mayagüez |  | Waste Water Tank 1&2 | NME | 338600 | TBD | TBD | EXECUTION | C-107651 | Luis Ortiz | Alonso & Carus
39 | Mayagüez | 4A | Hot Section Inspection Unit 4A | NME | 9000000 | TBD | TBD | EXECUTION | C-108663 | Roberto Rosario | ARG Precision | 6994584.43
|  | **** | NME MAINTENANCE ACTIVITY COULD INCLUDE DIFERENT CONTRACTS