## ER1 Program Questions
Request for information for the Energy Grid Rehabilitation and Reconstruction Cost Share Program (ER1) of the Puerto Rico Department of Housing (PRDOH):
How many projects have you submitted to PRDOH under the ER1 program to cover the non-federal share to date? | [8 empty] | 1 | Example
For each project, provide the following details:
FEMA Project No. (Not Project Worksheet) | Submission Date to PRDOH | Total Amount Requested to PRDOH | Approved by PRDOH? | PRDOH Approval Date | Amount Disbursed by PRDOH | FEMA PW Status | Project Status | Total Project Amount (100% including cost share) | Federal Share | State Cost Share | Are the requested PRDOH cost share funds related to a FEMA RFCA/RFA? | If so, please provide the amount requested in the RFA or RFCA. |  |  | If so, please provide the subsequently submitted RFRs that reconciled said RFCA/RFA. | [43 empty] | Total
[15 empty] | RFR #1 |  |  |  | RFR #2 |  |  |  | RFR #3 |  |  |  | RFR #4 |  |  |  | RFR #5 |  |  |  | RFR #6 |  |  |  | RFR #7 |  |  |  | RFR #8 |  |  |  | RFR #9 |  |  |  | RFR #10 |  |  |  | RFR #11
[12 empty] | Requested Amount | Disbursed Amount | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | RFR Stage | Disbursement Date | Requested Amount | Validated Amount | CDBG Funds Available to Request
| PRDOH |  |  |  |  | FEMA | [5 empty] | FEMA
Example Project No. XXXX | 2025-05-25 | 400000 | No | N/A | 0 | Obligated | Completed | 20000000 | 18000000 | 2000000 | Yes | 4500000 | 4500000 | 2025-01-01 | 1000000 | 0 | Returned to RFR Preparation | N/A | 1000000 | 1000000 | Payment Complete | 2025-01-01 | 1000000 | 1000000 | Payment Complete | 2025-02-01 | 1000000 | 1000000 | Payment Complete | 2025-03-01 | 1000000 | 1000000 | Payment Complete | 2025-04-01 | [24 empty] | 5000000 | 4000000 | 400000
180692 | 2024-05-21 | 5974047 | No | N/A |  | Obligated | Completed | 59740470 | 53766423 | 5974047 | No |  |  |  | 59740469.92 | 59740469.92 | Payment Complete | 2023-02-01 | [40 empty] | 59740469.92 | 59740469.92 | 5974046.992
334509 | 2024-05-21 | 288335.23 | Yes | 2025-04-02 | 288335.23 | Obligated | Completed | 2890937.33 | 2601843.597 | 289093.733 | No |  |  |  | 2890937.33 | 2883352.33 | Payment Complete | 2023-06-12 | [40 empty] | 2890937.33 | 2883352.33 | 288335.233
663385 | 2024-05-21 | 2190110.55 | Yes | 2025-04-02 | 2190110.55 | Obligated | Completed | 22238212.58 | 20014391.322 | 2223821.258 | No |  |  |  | 15060960.08 | 15026460.0778 | Payment Complete | 2022-06-22 | 2690535.77 | 2690535.7667 | Payment Complete | 2022-08-19 | 47081.65 | 47081.65 | Payment Complete | 2023-02-27 | 110597.76 | 110597.74 | Payment Complete | 2023-08-09 | 4026430.14 | 4026430.14 | Payment Complete | 2024-04-26 | 0.01 | 0.01 | Payment Complete | 2024-12-10 | [20 empty] | 21935605.41 | 21901105.3844 | 2190110.5384
669498 | 2024-05-21 | 129897.45 | Yes | 2025-08-08 | 129897.45 | Obligated | Completed | 1381975 | 1243777.5 | 138197.5 | No |  |  |  | 667000 | 667000 | Payment Complete | 2023-01-18 | 320940 | 320940 | Payment Complete | 2023-05-16 | 311034.6 | 311034.6 | Payment Complete | 2023-08-24 | [32 empty] | 1298974.6 | 1298974.6 | 129897.46
669233 | 5/21/24-7/30/25 | 1543122.79 | Yes | 2025-08-08 | 1543122.79 | Obligated | Completed | 19539860.92 | 17585874.828 | 1953986.092 | No |  |  |  | 10045028.52 | 10044628.5222 | Payment Complete | 2022-11-02 | 350240 | 350240 | Payment Complete | 2022-12-12 | 7258072.7 | 4719314.45 | Payment Complete | 2023-06-15 | 317045 | 317045 | Payment Complete | 2024-12-23 | [28 empty] | 17970386.22 | 15431227.9722 | 1543122.7972
669815 | 5/21/24-7/30/25 | 342433.36 | Yes | 2025-08-08 | 342433.36 | Obligated | Completed | 3819020.68 | 3437118.612 | 381902.068 | No |  |  |  | 138749 | 138749 | Payment Complete | 2023-01-26 | 181815.52 | 156168.33 | Payment Complete | 2023-06-29 | 1908187.38 | 1387264.67 | Payment Complete | 2023-06-09 | 779567.14 | 592884.74 | Payment Complete | 2023-09-21 | 627823.8 | 463843.8 | Payment Complete | 2023-10-24 | 537828.08 | 524026.14 | Payment Complete | 2024-02-09 | 161397 | 161397 | Payment Complete | 2024-10-24 | [16 empty] | 4335367.92 | 3424333.68 | 342433.368
662957 | 2024-05-21 | 400000 | Yes | 2025-08-08 | 400000 | Obligated | Completed | 6507604.8 | 5856844.32 | 650760.48 | No |  |  |  | 2400000 | 2400000 | Payment Complete | 2023-06-14 | 1600000 | 1600000 | Payment Complete | 2023-09-12 | [36 empty] | 4000000 | 4000000 | 400000
671481 | 2024-05-21 | 122224 | Yes | 2025-08-08 | 116734.14 | Obligated | Completed | 1172831.25 | 1055548.125 | 117283.125 | No |  |  |  | 289349.1 | 289349.1 | Payment Complete | 2023-06-14 | 811925.2 | 811925.2 | Payment Complete | 2023-10-23 | 71556.95 | 71556.95 | Payment Complete | 2024-05-09 | [32 empty] | 1172831.25 | 1172831.25 | 117283.125
663383 | 5/21/24-7/30/25 | 123552.08 | Yes | 2025-08-08 | 123552.08 | Obligated | Completed | 2007587.81 | 1806829.029 | 200758.781 | No |  |  |  | 242820.8 | 242820.8 | Payment Complete | 2024-08-12 | 882400 | 882400 | Payment Complete | 2023-04-25 | 110300 | 110300 | Payment Complete | 2023-10-27 | [32 empty] | 1235520.8 | 1235520.8 | 123552.08
662947 | 5/21/24-7/30/25 | 2727743.67 | Yes | 2025-08-08 | 2727743.67 | Obligated | Completed | 29654228.77 | 26688805.893 | 2965422.877 | No |  |  |  | 12571725.68 | 8286895.68 | Payment Complete | 2023-02-27 | 12571725.68 | 3821330 | Payment Complete | 2023-01-10 | 11539220.32 | 11539220.32 | Payment Complete | 2023-06-27 | 1264290 | 1264290 | Payment Complete | 2023-08-14 | 840048.05 | 85827.8 | Payment Complete | 2023-11-08 | 673573.62 | 333573.62 | Payment Complete | 2023-12-08 | 340000 | 340000 | Payment Complete | 2024-02-09 | 412185.15 | 292341.53 | Payment Complete | 2024-04-19 | 488766.9 | 488766.9 | Payment Complete | 2024-05-31 | 754220.25 | 754220.25 | Payment Complete | 2024-10-07 | 123500 | 123500 | Payment Complete | 2025-02-18 | 40212768.5 | 27329966.1 | 2732996.61
687480 | 2024-05-21 | 65230.16 | Yes | 2025-08-08 | 65230.16 | Obligated | Completed | 1189095.58 | 1070186.022 | 118909.558 | No |  |  |  | 84072.42 | 56048.28 | Payment Complete | 2023-10-30 | 596253.3 | 596253.3 | Payment Complete | 2024-04-30 | [36 empty] | 680325.72 | 652301.58 | 65230.158
667744 | 2024-05-21 | 242123.9 | Yes | 2025-08-08 | 242123.9 | Obligated | Completed | 3142486 | 2828237.4 | 314248.6 | No |  |  |  | 805478.2 | 763640.55 | Payment Complete | 2023-05-16 | 616843.2 | 616813.2 | Payment Complete | 2023-06-21 | 249524.33 | 249524.33 | Payment Complete | 2023-08-30 | 693692.03 | 693692.03 | Payment Complete | 2023-11-01 | 97568.9 | 97568.9 | Payment Complete | 2024-01-19 | [24 empty] | 2463106.66 | 2421239.01 | 242123.901
672950 | 5/21/24-7/30/25 | 1508495 | Yes | 2025-08-08 | 1508494.26 | Obligated | Completed | 16105860.71 | 14495274.639 | 1610586.071 | No |  |  |  | 2076415 | 2076415 | Payment Complete | 2023-03-06 | 8286907.98 | 2405459 | Payment Complete | 2023-05-19 | 691800.75 | 238572 | Payment Complete | 2023-09-12 | 2497281.56 | 2447083.81 | Payment Complete | 2023-10-24 | 6297879.6 | 6297879.6 | Payment Complete | 2024-02-26 | 593762.75 | 593762.75 | Payment Complete | 2024-06-07 | 1025770.55 | 1025770.55 | Payment Complete | 2024-07-23 | [16 empty] | 21469818.19 | 15084942.71 | 1508494.271
725535 | 2025-07-30 | 133525.35 | Yes | 2025-08-08 | 285595.63 | Obligated | In Progress | 11423825 | 10281442.5 | 1142382.5 | Yes | 2570360.63 | 2570360.63 | 2024-04-26 | 1483615 | 1483615 | Payment Complete | 2025-06-02 | 1078174.75 |  | RFR under review |  | 735945 |  | RFR under review | [33 empty] | 3297734.75 | 1483615 | 148361.5
| *See document " |  |  |  | *Amount approved for reimbursement.Payment in process by PRDOH as of 8/28/2025
3297734.75
Of the obligated projects, how many are you planning to submit in next 12 months to PRDOH under the ER1 program?
For each project, provide the following details:
Project No. (NOT PROJECT WOKSHEET) | Expected Submission Date to PRDOH | Expected Requested Amount to PRDOH | FEMA PW Status | Project Status | Total Project Amount (100% including cost share) | Federal Share | State Cost Share
| PRDOH |  | FEMA
Example Project No. XXXX | 2025-09-01 | 5000000 | Obligated | In Progress | 20000000 | 18000000 | 2000000
725535 | FY 25-26 | 856786.87 | Obligated | In Progress | 11423825 | 10281442.5 | 1142382.5
669233 | FY 25-26 | 410863.2 | Obligated | In Progress | 19539860.92 | 17585874.828 | 1953986.092
662957 | 2025-12-31 | 250760.5 | Obligated | Completed | 6507604.8 | 5856844.32 | 650760.48
663383 | 2025-12-31 | 75276.7 | Obligated | Completed | 2007587.81 | 1806829.029 | 200758.781
687480 | 2025-12-31 | 53679.4 | Obligated | Completed | 1189095.58 | 1070186.022 | 118909.558
667744 | 2025-12-31 | 57125 | Obligated | Completed | 3142486 | 2828237.4 | 314248.6
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PRDOH date for invoice # ER1AEE2503001. Disbursement received on 5/15/2025
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PRDOH date for invoice # ER1AEE2507001. Invoice payment in process as of 8/28/2025