## PSP Matrix
| FEMA FAASt Number | PW Number | FEMA Project Name | Asset | PSP Activity # | Tier | Federal Funding Status | ISOW Submission to FEMA | DSOW Submission to FEMA | DOE Statement of Project Objectives (SOPO) Inclusion | Total Esimated Cost | LUMA Status | Initial Obligation Date | PSP Acitivity Compliance Check
1 | 165209 | 10626 | Culebra Substations 3801/3802 rebuilds | Substation | Activity #21 | Tier 1 | Active | 2020-12-18 | 2022-04-04 | N/A | 14259420 | Obligated | 2022-06-09 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
2 | 165268 | 11045 | FAASt Rio Grande Estate Substation CH-2306 (Substation) | Substation | Activity #21 | N/A | Active | 2021-01-29 | 2022-05-31 | N/A | 11683614.71 | Obligated | 2022-12-20 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
3 | 169058 | 107220 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Activity #17 | Tier 1 | Active | 2021-01-27 | 2022-05-04 | N/A | 37821483.21 | Pending Scope & Cost Completion by Applicant | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
4 | 169266 | 11489 | Centro Medico: Equipment replacements | Substation | Activity #21 | N/A | Active | 2021-01-28 | 2022-05-26 | N/A | 23143279 | Obligated | 2023-11-03 | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
5 | 169276 | 107222 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Substation | Activity #17 | Tier 1 | Active | 2021-01-28 | 2023-03-31 | N/A | 84687466.18 | Pending Scope & Cost Completion by Applicant | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
6 | 169495 | 11479 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | Substation | Activity #21 | N/A | Active | 2021-04-01 | 2022-10-31 | N/A | 15339932.33 | Obligated | 2023-08-21 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
7 | 169500 | 11347 | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | Substation | Activity #17 | N/A | Active | 2021-02-02 | 2022-06-07 | N/A | 6372063 | Obligated | 2023-06-15 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
8 | 169896 | 10788 | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | Substation | Activity #17 | N/A | Active | 2020-12-18 | 2022-05-20 | N/A | 23251835 | Obligated | 2022-08-01 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
9 | 174422 | 10496 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Activity #21 | N/A | Active | 2021-03-04 | 2021-10-28 | N/A | 23255048.94 | Obligated | 2022-05-17 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
10 | 178503 | 11100 | FAASt Aguirre TC - BKRS (Substations) | Substation | Activity #21 | N/A | Active | 2021-01-29 | 2022-07-25 | N/A | 39034592 | Obligated | 2022-12-23 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
11 | 178577 | 11507 | FAASt [Cachete – MC 1526] (Substations) | Substation | Activity #21 | Tier 1 | Active | 2021-04-01 | 2023-10-02 | N/A | 43898139.21 | Pending Scope & Cost Completion by Applicant | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
12 | 547187 | 107690 | FAASt - [Substation Component Replacement Program] (Substation) | Substation | Activity #17 | Tier 1 | Active | 2021-11-16 | 2025-03-10 | N/A | 8929767.78 | Pending Scope & Cost Completion by Applicant | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
13 | 550106 | 107714 | FAASt [Conquistador CH] (Substation) | Substation | Activity #21 | Tier 1 | Active | 2021-12-07 | 2023-06-30 | N/A | 12406993.05 | Pending Scope & Cost Completion by Applicant | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
14 | 550950 | 11557 | FAASt - EPC - [Monacillo TC] (Substations) | Substation | Activity #21 | Tier 1 | Active | 2021-12-14 | 2023-05-31 | N/A | 15252700.61 | Obligated | 2023-12-18 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
15 | 551914 | 11470 | FAASt [Caparra 1912 & 1924] (Substation) | Substation | Activity #21 | Tier 1 | Active | 2022-01-31 | 2024-06-28 | N/A | 15135968.77 | Pending Scope & Cost Completion by Applicant | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
16 | 551926 | Pending PW | SCADA/RTU Replacements Group 2 | Telecomm - IT/OT | Activity #15 | Tier 1 | Active | 2022-01-10 | 2023-09-29 | N/A | 7537936.57 | Pending Final FEMA Review | Pending Obligation | The project will implement critical protection automation and control (PAC) and supervisory control and data acquisition (SCADA) maintenance enhancement and upgrades.
17 | 551963 | Pending PW | Transport Network 1 | Telecomm - IT/OT | Activity #15 | Tier 1 | Active | 2022-02-01 | 2023-07-29 | N/A | 7469879.23 | Pending Large Project Review | Pending Obligation | The project aims to restore impacted transport network equipment while ensuring compliance with program guidelines and industry standards.
18 | 662238 | Pending PW | Microwave point-to-point backbone | Telecomm - IT/OT | Activity #15 | Tier 1 | Active | 2022-02-14 | 2023-05-23 | N/A | 20356074.98 | Pending Scope & Cost Completion by Applicant | Pending Obligation | The project will restore the Transmission and Distribution Transport Network system, which allows the operation and monitoring of the devices within its substations providing stability and reliability to their operation.
19 | 673292 | Pending PW | Telecomm Cerra Puntas (Tower Replacement) | Telecomm - IT/OT | Activity #15 | Tier 1 | Active | 2022-05-17 | 2024-02-05 | N/A | 9253921.27 | Pending EHP Review | Pending Obligation | The project scope includes direct tower replacement to include asscoiated communications equipment and function to hardden grid command and control functions.
20 | 678800 | Pending PW | Telecom Infrastructure Group B | Telecomm - IT/OT | Activity #15 | Tier 1 | Active | 2022-07-22 | 2024-05-14 | N/A | 16033618.38 | Pending EHP Review | Pending Obligation | The project will restore the transmission and distribution Transport Network system, which allows the operation and monitoring of the devices within its substations providing stability and reliability to their operation.
21 | 682121 | 11652 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Activity #21 | N/A | Active | 2023-06-16 | 2023-06-16 | N/A | 90515773.82 | Obligated | 2024-03-21 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
22 | 682328 | 11876 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Activity #21 | Tier 1 | Active | 2022-09-12 | 2023-11-27 | N/A | 10262107.97 | Pending EHP Review | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
23 | 682645 | 107779 | FAASt [Maunabo TC] (Substation) | Substation | Activity #21 | Tier 1 | Active | 2022-09-15 | 2025-04-24 | N/A | 14621458.61 | Pending Large Project Review | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
24 | 682834 | 11402 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Substation | Activity #21 | Tier 1 | Active | 2022-09-16 | 2023-03-31 | N/A | 12328089.11 | Obligated | 2024-02-12 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
25 | 711819 | Pending PW | TL 13400: Tpole replacements | Transmission | Activity #10 | Tier 1 | Active | 2023-03-09 | 2023-12-21 | N/A | 2748394.67 | Pending Scope & Cost Completion by Applicant | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
26 | 723002 | 107888 | FAASt - EPC - Jobos TC (Substation) | Substation | Activity #21 | Tier 1 | Active | 2023-06-16 | 2023-06-15 | N/A | 76096512.83 | Pending EHP Review | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
27 | 723077 | 11556 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Activity #21 | N/A | Active | 2022-09-07 | 2023-06-01 | N/A | 100686731.41 | Obligated | 2023-12-18 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
28 | 723078 | 11555 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Activity #21 | N/A | Active | 2023-06-16 | 2023-06-16 | N/A | 61558468.95 | Obligated | 2023-12-18 | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
29 | 723883 | 11696 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-05-10 | 2023-07-18 | N/A | 145069437.94 | Obligated | 2024-06-04 | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
30 | 727522 | 107892 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-08-03 | 2023-07-31 | N/A | 19467722.13 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
31 | 727529 | 107893 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-07-31 | 2023-07-31 | N/A | 57429412.88 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
32 | 727531 | 11715 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Vegetation | Activity #20 | N/A | Active | 2023-07-31 | 2023-08-03 | N/A | 42520736.92 | Obligated | 2025-04-28 | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
33 | 727572 | 11720 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-07-31 | 2023-08-03 | N/A | 80353343.34 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
34 | 727606 | 107898 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-07-31 | 2023-07-31 | N/A | 32019956.73 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
35 | 727608 | 107899 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-07-31 | 2023-07-31 | N/A | 27408406.83 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
36 | 727657 | 107900 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-07-31 | 2023-07-31 | N/A | 22914442.28 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
37 | 727659 | 107901 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-07-31 | 2023-07-31 | N/A | 19548562.05 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
38 | 727692 | 11724 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Vegetation | Activity #20 | N/A | Active | 2023-07-31 | 2023-08-04 | N/A | 28052090 | Obligated | 2025-04-28 | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
39 | 728827 | 11714 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Vegetation | Activity #20 | N/A | Active | 2023-07-31 | 2023-08-17 | N/A | 18194309 | Obligated | 2025-04-28 | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
40 | 728832 | 11718 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Vegetation | Activity #20 | N/A | Active | 2023-07-31 | 2023-08-17 | N/A | 23418437.42 | Obligated | 2025-04-28 | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
41 | 741105 | 107946 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2023-12-15 | 2023-12-18 | N/A | 157385518.05 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
42 | 746660 | 107960 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Activity #15 | Tier 1 | Active | 2024-04-08 | 2024-04-11 | N/A | 17280359.87 | Pending Scope & Cost Completion by Applicant | Pending Obligation | The project scope includes the restoration of the Transmission and Distribution Transport Network system, which allows the operation and monitoring of the devices within its substations providing stability and reliability to their operation.
43 | 749072 | Pending PW | TL 2700: Tpole replacements | Transmission | Activity #10 | Tier 1 | Active | 2023-11-27 | 2024-06-05 | N/A | 956559.58 | Pending FEMA 406 HMP Completion | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
44 | 750063 | 107965 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2024-06-18 | 2024-11-21 | N/A | 113327804.46 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
45 | 750065 | 107966 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2024-06-18 | 2024-11-21 | N/A | 132424167.91 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
46 | 750066 | 107967 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2024-06-18 | 2024-11-21 | N/A | 3142832.19 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
47 | 750067 | 107968 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2024-06-18 | 2024-11-21 | N/A | 107170415.13 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
48 | 750068 | 107969 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2024-06-18 | 2024-11-21 | N/A | 98723529.73 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
49 | 750150 | Pending PW | TL 4800 (Santa Isabel-Toro Negro) : Tpole replacements | Transmission | Activity #10 | Tier 1 | Active | 2024-06-20 | 2024-06-20 | N/A | 159972.42 | Pending Peer Review | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
50 | 750151 | Pending PW | TL 700: Tpole replacements | Transmission | Activity #10 | Tier 1 | Active | 2024-06-20 | 2024-06-20 | N/A | 334535.28 | Pending Scope & Cost Completion by Applicant | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
51 | 750168 | Pending PW | TL 4800 (Santa Isabel-Aibonito) Tpole replacements | Transmission | Activity #10 | Tier 1 | Active | 2024-06-20 | 2024-06-20 | N/A | 574424.91 | Pending Scope & Cost Completion by Applicant | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
52 | 753782 | Pending PW | TL 3100 : Tpole replacements | Transmission | Activity #10 | Tier 1 | Active | 2024-08-23 | 2024-08-23 | N/A | 158052.38 | Pending FEMA 406 HMP Completion | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
53 | 825843 | 108134 | FAASt [Guanica TC] (Substation) | Substation | Activity #21 | Tier 1 | Active | 2025-04-09 | 2025-04-09 | N/A | 7348078.61 | Pending Final FEMA Review | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
54 | 956330 | 108145 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 7985860.15 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
55 | 956331 | 108146 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 8021552.35 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
56 | 956332 | 108147 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 11304742.47 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
57 | 956335 | 108148 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 7503713.1 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
58 | 956337 | 108149 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 7303974.78 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
59 | 956339 | 108150 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 12004333.95 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
60 | 956340 | 108151 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 6589894.87 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
61 | 956341 | 108152 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-27 | N/A | 97672.18 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
62 | 956342 | 108153 | FAASt [Arecibo Region 2 Transmission Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 44397505.6 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
63 | 956343 | 108154 | FAASt [Ponce Region 6 Transmission Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 21381353.56 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
64 | 956345 | 108155 | FAASt [Arecibo Region 2 Transmission Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 7324652.17 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
65 | 956348 | 108156 | FAASt [Bayamon Region 3 Transmission Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 1193764.73 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
66 | 956349 | 108157 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 13853576.48 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
67 | 956353 | 108158 | FAASt [Arecibo Region 2 Transmission Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 37008593.33 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
68 | 956356 | 108159 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 1019517.55 | Pending EHP Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
69 | 956357 | 108160 | FAASt [Mayaguez Region 5 Transmission Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Activity #20 | Tier 1 | Active | 2025-06-18 | 2025-06-26 | N/A | 12705648.39 | Pending Scope & Cost Completion by Applicant | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
70 | 956593 | 108161 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Activity #17 | Tier 1 | Active | 2025-06-23 | 2025-06-23 | N/A | 5907319.61 | Pending Final FEMA Review | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
71 | 957578 | Pending PW | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Activity #17 | Tier 1 | Active | 2025-07-07 | 2025-07-15 | N/A | 1250845.76 | Pending Recipient Final Review | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment
72 | 7537868 | Pending PW | TL 5900: Tpole replacements | Transmission | Activity #10 | Tier 2 | Inactive | 2024-08-23 | 2024-08-23 | N/A | 531235.74 | Pending Issue for approval Design | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
73 | 7537878 | Pending PW | TL 13700: Tpole replacements | Transmission | Activity #10 | Tier 2 | Inactive | 2024-08-23 | 2024-08-23 | N/A | 623574.49 | 100% Issue For Construction Design completed | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
74 | 8119138 | Pending PW | TL 9600 : Tpole replacements | Transmission | Activity #10 | Tier 2 | Inactive | 2025-02-17 | 2025-02-17 | N/A | 463977.49 | 100% Issue For Construction Design completed | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
75 | 8119238 | Pending PW | TL 16500: Tpole replacements | Transmission | Activity #10 | Tier 2 | Inactive | 2025-02-17 | 2025-02-17 | N/A | 283000.41 | 100% Issue For Construction Design completed | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
76 | 547247* | Pending PW | Cambalache TC: Rebuild | Substation | Activity #21 | Tier 2 | Inactive | 2021-11-16 | 2024-07-31 | N/A | 90196791.96 | Currenty on 60% Engineering | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
77 | 550099* | Pending PW | Industrial Such: Equipment/Component replacements | Substation | Activity #17 | Tier 2 | Inactive | 2021-12-07 | 2023-06-30 | N/A | 16767794.21 | Rebuild currently on 30% Engineering/Components Replacement not started | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
78 | 550894* | Pending PW | Baldrich: Equipment/Component replacements | Substation | Activity #17 | Tier 2 | Inactive | 2021-12-14 | 2023-09-29 | N/A | 29642961 | Rebuild currently on 30% Engineering/Components Replacement not started | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
79 | 550980* | Pending PW | Perques y Recreos: Equipment/Component replacements | Substation | Activity #17 | Tier 2 | Inactive | 2021-12-14 | 2023-06-30 | N/A | 20700231.13 | Rebuild currently on 60% Engineering/Components Replacement not started | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
80 | 550986* | Pending PW | Condado: Equipment/Component replacements | Substation | Activity #17 | Tier 2 | Inactive | 2021-12-14 | 2023-06-30 | N/A | 16077078 | Rebuild currently on 30% Engineering/Components Replacement not started | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
81 | 551912* | Pending PW | Puerto Nuevo: Equipment/Component replacements | Substation | Activity #17 | Tier 2 | Inactive | 2021-12-21 | 2023-06-30 | N/A | 18227585 | Rebuild currently on 30% Engineering/Components Replacement not started | Pending Obligation | Project designed to modernize transmission and distribution substations and includes the replacement of circuit breakers, power transformers, distribution metal-clad switchgear, and ancillary equipment.
82 | 679035* | Pending PW | Telecomm Infrastructure Group A | Telecomm - IT/OT | Activity #15 | Tier 2 | Inactive | 2022-07-27 | Pending Submission | N/A | 5900000 | ----- | Pending Obligation | The project will restore the transmission and distribution Transport Network system, which allows the operation and monitoring of the devices within its substations providing stability and reliability to their operation.
83 | 704805* | Pending PW | Telecomm Infrastructure Group D | Telecomm - IT/OT | Activity #15 | Tier 2 | Inactive | 2023-02-02 | Pending Submission | N/A | 6905000 | ----- | Pending Obligation | The project will restore the transmission and distribution Transport Network system, which allows the operation and monitoring of the devices within its substations providing stability and reliability to their operation.
84 | 727530* | 107894 | FAASt [Region 6 -Ponce Group C] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-07-31 | 2023-07-31 | N/A | 70421923.26 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
85 | 727540* | 107895 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-07-31 | 2023-07-31 | N/A | 66510486.76 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
86 | 727558* | 107896 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-07-31 | 2023-07-31 | N/A | 16374246.76 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
87 | 727562* | 107897 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-07-31 | 2023-07-31 | N/A | 84411128.06 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
88 | 727691* | 107902 | FAASt [Region 1 -San Juan Group C] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-07-31 | 2023-07-31 | N/A | 44200121.5 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
89 | 727694* | 107903 | FAASt [Region 4 -Caguas Group C] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-07-31 | 2023-07-31 | N/A | 76781710.48 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
90 | 738671* | Pending PW | FAASt [4 x 25 MW BESS Interconnections Barceloneta] (Substation) | Substation | Activity #14 | Tier 2 | Inactive | 2023-10-25 | 2025-04-25 | N/A | 55941767.5 | 30% Engineering Complete. Pending EPC. | Pending Obligation | The BESS projects will enhance system inertia, support voltage regulation, and provide fast frequency response capability consistent with the approved activity. Additionally, they will expand the portfolio of utility-scale storage solutions, and address stability issues.
91 | 740406* | 107933 | FAASt [Region 1-San Juan Group B] High Density (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-12-08 | 2023-12-11 | N/A | 5894785.29 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
92 | 740408* | 107934 | FAASt [Region 3-Bayamon Group B] High Density (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-12-08 | 2023-12-11 | N/A | 11782088.78 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
93 | 740409* | 107935 | FAASt [Region 4-Caguas Group B] High Density (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-12-08 | 2023-12-11 | N/A | 23846154.02 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
94 | 740410* | 107936 | FAASt [Region 2-Arecibo Group B] High Density (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-12-08 | 2023-12-11 | N/A | 5425376.76 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
95 | 740411* | 107937 | FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-12-08 | 2023-12-11 | N/A | 3777166.88 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
96 | 740414* | 107938 | FAASt [Region 6-Ponce Group B] High Density (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | 2023-12-08 | 2023-12-19 | N/A | 13788400.37 | Pending Applicant Project Review | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
97 | 744072* | Pending PW | Network and Communications Infrastructure Group 2 | Telecomm - IT/OT | Activity #15 | Tier 2 | Inactive | 2024-02-09 | 2025-03-21 | N/A | 2565020.45 | ----- | Pending Obligation | The project will restore the transmission and distribution Transport Network system, which allows the operation and monitoring of the devices within its substations providing stability and reliability to their operation.
98 | 748180* | Pending PW | Transmission WAMPAC (Wide Area Monitoring, Protection And Control) | Transmission | Activity #10 | Tier 2 | Inactive | 2024-04-01 | 2024-10-01 | N/A | 52804979.05 | Under Formulation | Pending Obligation | The project will implement critical protection automation and control (PAC) and supervisory control and data acquisition (SCADA) maintenance enhancement and upgrades.
99 | 750502* | Pending PW | FAASt [4 x 25 MW BESS Interconnections Aguadilla TC] (Substation) | Substation | Activity #14 | Tier 2 | Inactive | 2024-06-27 | 2025-06-06 | N/A | 52720520.35 | 30% Engineering Complete. Pending EPC. | Pending Obligation | The BESS projects will enhance system inertia, support voltage regulation, and provide fast frequency response capability consistent with the approved activity. Additionally, they will expand the portfolio of utility-scale storage solutions, and address stability issues.
100 | 750503* | Pending PW | FAASt [4 x 25 MW BESS Interconnections Monacillos TC] (Substation) | Substation | Activity #14 | Tier 2 | Inactive | 2024-06-27 | 2025-06-06 | N/A | 55503065.56 | 30% Engineering Complete. Pending EPC. | Pending Obligation | The BESS projects will enhance system inertia, support voltage regulation, and provide fast frequency response capability consistent with the approved activity. Additionally, they will expand the portfolio of utility-scale storage solutions, and address stability issues.
101 | 752972* | Pending PW | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Activity #14 | Tier 2 | Inactive | 2024-08-09 | 2025-04-25 | N/A | 57640005.67 | 30% Engineering Complete. Pending EPC. | Pending Obligation | The BESS projects will enhance system inertia, support voltage regulation, and provide fast frequency response capability consistent with the approved activity. Additionally, they will expand the portfolio of utility-scale storage solutions, and address stability issues.
102 | 753781* | Pending PW | TL 800: Tpole replacements | Transmission | Activity #10 | Tier 2 | Inactive | 2024-08-23 | 2024-08-23 | N/A | 759888.2 | 100% Issue For Construction Design completed | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
103 | 753785* | Pending PW | TL 3300 : Tpole replacements | Transmission | Activity #10 | Tier 2 | Inactive | 2024-08-23 | 2024-08-23 | N/A | 336678.78 | 100% Issue For Construction Design completed | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
104 | DOE | N/A | TL 2100: Transmission hardening | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole, Insulator, hardware repairs | See SOPO Costs | (Tier 2 project: 805517: 38kV reclosers) | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
105 | DOE | N/A | TL 4500: Transmission hardening | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole, Insulator, hardware repairs | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
106 | DOE | N/A | TL 9100: Transmission hardening | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole, Insulator, hardware repairs | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
107 | DOE | N/A | TL 9400: Transmission hardening | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole, Insulator, hardware repairs | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
108 | DOE | N/A | TL 12600: Transmission hardening | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole, Insulator, hardware repairs | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
109 | DOE | N/A | TL 13600: Transmission hardening | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole, Insulator, hardware repairs | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
110 | DOE | N/A | TL 36100: T-Pole replacements | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole replacements | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
111 | DOE | N/A | TL 38200: T-Pole Replacements | Transmission | Activity #10 | N/A | Active | N/A | N/A | DOE: Transmission Pole replacements | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
112 | DOE | N/A | Caguas TC - Transformer Replacement (Energize) | Substation | Activity #17 | N/A | Active | N/A | N/A | DOE: Transformer replacement project | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | Projects with the objective to complete and energize new large power transformers at substations and transmission centers, replacing failed and aging units that pose significant risks to customers and serviceability across Puerto Rico.
113 | DOE | N/A | Fajardo - Transformer Replacement (Energize) | Substation | Activity #17 | N/A | Active | N/A | N/A | DOE: Transformer replacement project | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | Projects with the objective to complete and energize new large power transformers at substations and transmission centers, replacing failed and aging units that pose significant risks to customers and serviceability across Puerto Rico.
114 | DOE | N/A | Mora TC - Transformer Replacement (Energize) | Substation | Activity #17 | N/A | Active | N/A | N/A | DOE: Transformer replacement project | See SOPO Costs | Pending SOPO Grant Approval | Pending SOPO Grant Approval | Projects with the objective to complete and energize new large power transformers at substations and transmission centers, replacing failed and aging units that pose significant risks to customers and serviceability across Puerto Rico.
115 | Pending FAASt Number | Pending PW | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
116 | Pending FAASt Number | Pending PW | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
117 | Pending FAASt Number | Pending PW | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
118 | Pending FAASt Number | Pending PW | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
119 | Pending FAASt Number | Pending PW | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
120 | Pending FAASt Number | Pending PW | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | Vegetation | Activity #20 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | This project is part of the vegetation clearing workstream related to the full rollout of the vegetation clearing program and reclamation efforts.
121 | Pending FAASt Number | Pending PW | Line 8700 - Transmisison Hardening | Transmission | Activity #10 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | The objective of this project is to stabilize, modernize, and repair existing and aging transmission line poles, segments and infrastructure to restore system redundancy, enhance grid resilience, and meet current serviceability standards.
122 | Pending FAASt Number | Pending PW | Juncos - Transformer Replacement (Energize) | Substation | Activity #17 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
123 | Pending FAASt Number | Pending PW | Veredas Transformer | Substation | Activity #17 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | Project scope to improve system reliability with the rebuilding and replacement of aged and deteriorated electrical equipment, currently in a higher risk of failure, subsequently affecting the reliability of the delivery of critical service to the customers.
124 | Pending FAASt Number | Pending PW | Transport Network 2 | Telecomm - IT/OT | Activity #15 | Tier 2 | Inactive | Pending Submission | Pending Submission | N/A | Under Formulation | Under Formulation | Pending Obligation | The project aims to restore impacted transport network equipment while ensuring compliance with program guidelines and industry standards.
*FAASt Number for inactive projects
DOE SOPO Project costs:
These costs are for the specific DOE projects as related in the PREB response for Transformers, Transmission, Substations and grid enhancements.
P2: Transformers: $13,106,837
P3: Transmission: $15,660,622
P4: Sitchgear/GIS: $6,569,737
P5: Grid Mod/DA: $19,501,677
P6: Stabilization Mods: $19,417,785
PSP-FEMA/DOE Traceability Matrix