## FAASt - Obligations Summary
FAASt-Consolidated Plan Summary
| Summary | 10510983791.54
|  | Reductions (Obligations) | Selected Projects under Formulation * | Estimated FAASt Total | -47156720
A | A&E - Mat | -4209258262.63 |  | -4209258262.63 |  | 0
B | PREPA | -301938311.47 | -1290199550.23 | -1592137861.7 | 39119195.21
C | LUMA | -1714393436.3922 | -1380565578.75 | -3094959015.1422 | 2775542505.67
D | Genera | -383105962.34 | -594713756.84 | -977819719.18 | 1347439841.75
| Total Reductions | -6608695972.8322 | -3265478885.82 | -9874174858.6522 |  | 9874174858.6522
| Remaining Balance 6099 | 3902287818.7078 | 636808932.8878 | 636808932.8878 | Remaining Estimated Balance | 636808932.8878
|  |  | * See each respective tab for project details |  |  | 10510983791.54
| Shared PWs-Obligated |  | 428 | 406 | Total Shared
9510 | PA-02-PR-4339-PW-09510 | FAASt A&E (PREPA/LUMA/Genera) | 1133563562.43 | 0 | 1133563562.43
10710 | PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 656101430 | 0 | 656101430
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 141081695.2 | 0 | 141081695.2
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 709006610 | 0 | 709006610
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 33478328 | 0 | 33478328
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 1536026637 | 0 | 1536026637
|  |  | 4209258262.63 | 0 | 4209258262.63
A
Child PWs
PW | PREPA -Obligated | Project Name | 428 | 406 | Total Child
9312 | PA-02-PR-4339-PW-09312 | FAASt Mobile Generation Units Purchases | 59740469.92 | 0 | 59740469.92 | Generation
10080 | PA-02-PR-4339-PW-10080 | FAASt Palo Seco Demin Water Tank 4 | 2890937.33 | 0 | 2890937.33 | Generation
10455 | PA-02-PR-4339-PW-10455 | FAASt Mayaguez Hydro-Gas Power Plant | 22238212.58 | 0 | 22238212.58 | Generation
10568 | PA-02-PR-4339-PW-10568 | FAASt Aguirre Power Plant 002 Units 1 &2 | 20905908.95 | 0 | 20905908.95 | Generation
10571 | PA-02-PR-4339-PW-10571 | FAASt Aguirre Power Plant 001 Infrastructure | 3031265.05 | 0 | 3031265.05 | Generation
10606 | PA-02-PR-4339-PW-10606 | FAASt Palo Seco Power Plant 001 Units 3 & 4 | 28774422.64 | 0 | 28774422.64 | Generation
10607 | PA-02-PR-4339-PW-10607 | FAASt Cambalache Power Plant | 2007587.81 | 0 | 2007587.81 | Generation
10608 | PA-02-PR-4339-PW-10608 | FAASt San Juan Power Plant - Auxiliary Infras | 3192936 | 0 | 3192936 | Generation
10609 | PA-02-PR-4339-PW-10609 | FAASt Palo Seco 002- Auxiliary Infrastructure | 3482468 | 0 | 3482468 | Generation
10615 | PA-02-PR-4339-PW-10615 | FAASt San Juan 001  Units 5 &amp;amp; | 73453828.76 | 0 | 73453828.76 | Generation
10622 | PA-02-PR-4339-PW-10622 | FAASt Aguirre Power Plant 003 Combined Cycle | 6384965.36 | 0 | 6384965.36 | Generation
10694 | PA-02-PR-4339-PW-10694 | FAASt Costa Sur 002 -Infrastructure projects ( | 1021800 | 0 | 1021800 | Generation
10702 | PA-02-PR-4339-PW-10702 | FAASt Costa Sur Power Plant Permanent | 42429619.54 | 0 | 42429619.54 | Generation
11085 | PA-02-PR-4339-PW-11085 | FAASt San Juan Power Plant 002 Units 7 & 8 | 19558770 | 0 | 19558770 | Generation
11510 | PA-02-PR-4339-PW-11510 | FAASt - IT/0T System Upgrade for all Power Plants | 11423825 | 0 | 11423825 | Generation
11860 | PA-02-PR-4339-PW-11860 | FAASt – BONUS Nuclear Power Plant Repairs (Dams/Hydro) | 1401294.53 | 178320.9 | 1579615.43 | (Dams/Hydro)
| TOTAL PREPA |  | 301938311.47 | 178320.9 | 302116632.37 | 0
B
PW | LUMA - Obligated | Project Name | 428 | 406 | Total Child | Asset
10496 | PA-02-PR-4339-PW-10496 | FAASt - Catano-Rebuild 1801(Substation) | 16359899.17 | 6895149.77 | 23255048.94 | Substation
10499 | PA-02-PR-4339-PW-10499 | FAASt Maunabo Streetlighting (Distribution) | 6199877.07 | 243880.33 | 6443757.4 | Distribution
10515 | PA-02-PR-4339-PW-10515 | FAASt -Luquillo Distribution Streetlighting | 8628667.29 | 181658.08 | 8810325.37 | Distribution
10521 | PA-02-PR-4339-PW-10521 | FAASt Lajas Streetlighting (Distribution) | 10278336.09 | 426332.48 | 10704668.57 | Distribution
10538 | PA-02-PR-4339-PW-10538 | FAASt Streetlighting - Guánica (Distribution | 9687238 | 370808 | 10058046 | Distribution
10539 | PA-02-PR-4339-PW-10539 | FAASt Aguada Streetlighting (Distribution) | 17764494.34 | 807222.04 | 18571716.38 | Distribution
10624 | PA-02-PR-4339-PW-10624 | FAASt-Substation 2501 Vieques (Substation) | 1209111 | 178309 | 1387420 | Substation
10626 | PA-02-PR-4339-PW-10626 | FAASt-Substation 3801 Culebra (Substation) | 1282218 | 177391 | 1459609 | Substation
10629 | PA-02-PR-4339-PW-10629 | FAASt Distribution Feeders - Ponce Short Term | 316119 | 64134 | 380253 | Distribution
10630 | PA-02-PR-4339-PW-10630 | FAASt Distribution Feeders - Ponce Short Term | 323692 | 69130 | 392822 | Distribution
10632 | PA-02-PR-4339-PW-10632 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 1593443 | 0 | 1593443 | Substation
10635 | PA-02-PR-4339-PW-10635 | FAASt Distribution Feeders - Caguas Short Ter | 142917 | 10826 | 153743 | Distribution
10679 | PA-02-PR-4339-PW-10679 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | 1217429 | 0 | 1217429 | Transmission
10690 | PA-02-PR-4339-PW-10690 | FAASt Distribution Feeders - Arecibo Short Te | 610448 | 157420 | 767868 | Distribution
10701 | PA-02-PR-4339-PW-10701 | FAASt Distribution Feeders - Caguas Short Term | 108847 | 14874 | 123721 | Distribution
10742 | PA-02-PR-4339-PW-10742 | FAASt Distribution Pole and Conductor Repair- | 20468 | 5830 | 26298 | Distribution
10751 | PA-02-PR-4339-PW-10751 | FAASt Distribution Pole and Conductor Repair- | 43725 | 5620 | 49345 | Distribution
10764 | PA-02-PR-4339-PW-10764 | FAASt Distribution Pole and Conductor Repair | 284349 | 73265 | 357614 | Distribution
10773 | PA-02-PR-4339-PW-10773 | FAASt Distribution Pole and Conductor Repair | 1408531 | 358420 | 1766951 | Distribution
10777 | PA-02-PR-4339-PW-10777 | FAASt Distribution Pole and Conductor Repair - | 1425163 | 368954 | 1794117 | Distribution
10788 | PA-02-PR-4339-PW-10788 | FAASt - Costa Sur SP TC  Equipment Repair and | 23251835 | 0 | 23251835 | Substation
10800 | PA-02-PR-4339-PW-10800 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | 453597 | 0 | 453597 | Transmission
10812 | PA-02-PR-4339-PW-10812 | FAASt Distribution Pole and Conductor Repair- | 190570 | 49943 | 240513 | Distribution
10821 | PA-02-PR-4339-PW-10821 | FAASt Distribution Pole and Conductor Repair | 621804 | 171614 | 793418 | Distribution
10824 | PA-02-PR-4339-PW-10824 | FAASt Distribution Pole and Conductor Repair | 84433 | 23322 | 107755 | Distribution
10827 | PA-02-PR-4339-PW-10827 | FAASt Distribution Pole and Conductor Repair | 1747929 | 362533 | 2110462 | Distribution
10837 | PA-02-PR-4339-PW-10837 | FAASt Line 6700 Martin Peña TC to Villamar Se | 690703 | 0 | 690703 | Transmission
10841 | PA-02-PR-4339-PW-10841 | FAASt Physical Security - Group 1 (Substatio | 6025270.22 | 665958.96 | 6691229.18 | Substation
10857 | PA-02-PR-4339-PW-10857 | FAASt Streetlighting - Villalba (Distributio | 10190536.05 | 681865.66 | 10872401.71 | Distribution
10858 | PA-02-PR-4339-PW-10858 | FAASt - Substation Minor Repairs Group A (Subs | 4482972.51 | 488202.58 | 4971175.09 | Substation
10864 | PA-02-PR-4339-PW-10864 | FAASt Distribution Pole and Conductor Repair | 1072850.98 | 319213.9 | 1392064.88 | Distribution
10876 | PA-02-PR-4339-PW-10876 | FAASt Distribution Streetlighting - Aibonito | 7074498 | 178787 | 7253285 | Distribution
10884 | PA-02-PR-4339-PW-10884 | FAASt Distribution Streetlighting - Cataño ( | 16996758 | 565289 | 17562047 | Distribution
10891 | PA-02-PR-4339-PW-10891 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | 420866 | 0 | 420866 | Transmission
10893 | PA-02-PR-4339-PW-10893 | FAASt Distribution Pole and Conductor Repair | 441308 | 90422 | 531730 | Distribution
10906 | PA-02-PR-4339-PW-10906 | FAASt Distribution Pole and Conductor Repair | 872891 | 238203 | 1111094 | Distribution
10909 | PA-02-PR-4339-PW-10909 | FAASt Distribution Pole and Conductor Repair | 1894033.53 | 472527 | 2366560.53 | Distribution
10919 | PA-02-PR-4339-PW-10919 | FAASt Distribution Pole and Conductor Repair | 3286536 | 835984 | 4122520 | Distribution
10922 | PA-02-PR-4339-PW-10922 | FAASt Distribution Pole and Conductor Repair- | 904194 | 227661 | 1131855 | Distribution
10933 | PA-02-PR-4339-PW-10933 | FAASt Distribution Pole and Conductor Repair | 1412368 | 289653 | 1702021 | Distribution
10935 | PA-02-PR-4339-PW-10935 | FAASt Distribution Pole and Conductor Repair | 1773428 | 318852 | 2092280 | Distribution
10957 | PA-02-PR-4339-PW-10957 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Teleco | 48941484 | 0 | 48941484 | Telecommunications
10962 | PA-02-PR-4339-PW-10962 | FAASt Distribution Pole and Conductor Repair | 3575454.81 | 857193.1 | 4432647.91 | Distribution
10978 | PA-02-PR-4339-PW-10978 | FAASt San Juan 115kV Underground Transmission | 14746039.57 | 0 | 14746039.57 | Transmission
11041 | PA-02-PR-4339-PW-11041 | FAASt Distribution Pole and Conductor Repair- | 4686914.68 | 1064121.8 | 5751036.48 | Distribution
11045 | PA-02-PR-4339-PW-11045 | FAASt Rio Grande Estate Substation CH-2306 (Su | 7098243.76 | 4585370.95 | 11683614.71 | Substation
11089 | PA-02-PR-4339-PW-11089 | FAASt Distribution Pole and Conductor Repair - | 129744 | 27443 | 157187 | Distribution
11090 | PA-02-PR-4339-PW-11090 | FAASt Distribution Pole and Conductor Repair | 20729 | 633 | 21362 | Distribution
11095 | PA-02-PR-4339-PW-11095 | FAASt Hatillo Streetlight (Distribution) | 18570095.25 | 1764387.7 | 20334482.95 | Distribution
11096 | PA-02-PR-4339-PW-11096 | FAASt Distribution Pole and Conductor Repair | 171152.23 | 46010.58 | 217162.81 | Distribution
11097 | PA-02-PR-4339-PW-11097 | FAASt Manati Streetlight (Distribution) | 27067865 | 1568964 | 28636829 | Distribution
11098 | PA-02-PR-4339-PW-11098 | FAASt Distribution Pole and Conductor Repair | 729040 | 179902 | 908942 | Distribution
11099 | PA-02-PR-4339-PW-11099 | FAASt Distribution Streetlighting - Dorado | 22864972 | 1505645 | 24370617 | Distribution
11100 | PA-02-PR-4339-PW-11100 | FAASt Aguirre TC - BKRS (Substations) | 39034592 | 0 | 39034592 | Substation
11101 | PA-02-PR-4339-PW-11101 | FAASt Distribution Pole and Conductor Repair | 243073 | 55558 | 298631 | Distribution
11103 | PA-02-PR-4339-PW-11103 | FAASt Distribution Pole and Conductor Repair- | 353628 | 54317.84 | 407945.84 | Distribution
11105 | PA-02-PR-4339-PW-11105 | FAASt Distribution Pole and Conductor Repair | 589335 | 157153 | 746488 | Distribution
11106 | PA-02-PR-4339-PW-11106 | FAASt Distribution Pole and Conductor Repair | 163846.51 | 51337.5 | 215184.01 | Distribution
11107 | PA-02-PR-4339-PW-11107 | FAASt Distribution Pole and | 483786 | 106510 | 590296 | Distribution
11109 | PA-02-PR-4339-PW-11109 | FAASt Distribution Pole and Conductor Repair | 452956.93 | 110600.22 | 563557.15 | Distribution
11113 | PA-02-PR-4339-PW-11113 | FAASt Distribution Pole and Conductor Repair- | 911136.76 | 206650.4 | 1117787.16 | Distribution
11114 | PA-02-PR-4339-PW-11114 | FAASt Distribution Pole and Conductor Repair | 498436 | 95482 | 593918 | Distribution
11116 | PA-02-PR-4339-PW-11116 | FAASt Distribution Pole and Conductor Repair | 250906 | 68700 | 319606 | Distribution
11123 | PA-02-PR-4339-PW-11123 | FAASt Distribution Pole and Conductor Repair | 70683 | 21148 | 91831 | Distribution
11130 | PA-02-PR-4339-PW-11130 | FAASt Distribution Pole and Conductor Repair | 545661.24 | 113378.16 | 659039.4 | Distribution
11136 | PA-02-PR-4339-PW-11136 | FAASt Distribution Pole and Conductor Repair | 510067.96 | 102310.67 | 612378.63 | Distribution
11137 | PA-02-PR-4339-PW-11137 | FAASt Distribution Pole and Conductor Repair | 85921.77 | 17491 | 103412.77 | Distribution
11138 | PA-02-PR-4339-PW-11138 | FAASt Distribution Pole and Conductor Repair P | 254972.22 | 63260 | 318232.22 | Distribution
11143 | PA-02-PR-4339-PW-11143 | FAASt Distribution Pole and Conductor Repair - | 537688 | 134695 | 672383 | Distribution
11145 | PA-02-PR-4339-PW-11145 | FAASt Distribution Pole and Conductor Repair | 573047.24 | 136182.31 | 709229.55 | Distribution
11149 | PA-02-PR-4339-PW-11149 | FAASt Distribution Pole and Conductor Repair | 577000.79 | 116779.74 | 693780.53 | Distribution
11150 | PA-02-PR-4339-PW-11150 | FAASt Distribution Pole and Conductor Repair | 68823 | 14986 | 83809 | Distribution
11152 | PA-02-PR-4339-PW-11152 | FAASt Distribution Pole and Conductor Repair | 20584 | 4995 | 25579 | Distribution
11165 | PA-02-PR-4339-PW-11165 | FAASt Distribution Pole and Conductor Repair | 65944 | 11661 | 77605 | Distribution
11166 | PA-02-PR-4339-PW-11166 | FAASt Distribution Pole and Conductor Repair | 431381.68 | 105743.62 | 537125.3 | Distribution
11168 | PA-02-PR-4339-PW-11168 | FAASt Distribution Pole and Conductor Repair | 43374 | 11028 | 54402 | Distribution
11169 | PA-02-PR-4339-PW-11169 | FAASt Distribution Pole and Conductor Repair - | 198050.74 | 41796.87 | 239847.61 | Distribution
11171 | PA-02-PR-4339-PW-11171 | FAASt Distribution Pole and Conductor Repair - | 355178 | 58304 | 413482 | Distribution
11181 | PA-02-PR-4339-PW-11181 | FAASt Distribution Pole and Conductor Repair | 516951 | 108247 | 625198 | Distribution
11182 | PA-02-PR-4339-PW-11182 | FAASt Distribution Pole and Conductor Repair | 208400 | 57671.35 | 266071.35 | Distribution
11183 | PA-02-PR-4339-PW-11183 | FAASt Distribution Pole and Conductor Repair | 635326.93 | 108700.19 | 744027.12 | Distribution
11184 | PA-02-PR-4339-PW-11184 | FAASt Transmission Priority Pole Replacements | 214124 | 2243 | 216367 | Distribution
11193 | PA-02-PR-4339-PW-11193 | FAASt Distribution Pole and Conductor Repair | 303774 | 72188.49 | 375962.49 | Distribution
11196 | PA-02-PR-4339-PW-11196 | FAASt Distribution Pole and Conductor Repair - | 775779 | 176882.42 | 952661.42 | Distribution
11201 | PA-02-PR-4339-PW-11201 | FAASt Distribution Pole and Conductor Repair | 208544.25 | 53746.06 | 262290.31 | Distribution
11203 | PA-02-PR-4339-PW-11203 | FAASt Distribution Pole and Conductor Repair- | 469650.95 | 95954.05 | 565605 | Distribution
11207 | PA-02-PR-4339-PW-11207 | FAASt Distribution Pole and Conductor Repair | 443331 | 98484 | 541815 | Distribution
11212 | PA-02-PR-4339-PW-11212 | FAASt Distribution Pole and Conductor Repair | 517156 | 105667 | 622823 | Distribution
11214 | PA-02-PR-4339-PW-11214 | FAASt Distribution Pole and Conductor Repair | 21408.25 | 5830.39 | 27238.64 | Distribution
11217 | PA-02-PR-4339-PW-11217 | FAASt Distribution Pole and Conductor Repair - | 164908.86 | 14986 | 179894.86 | Distribution
11229 | PA-02-PR-4339-PW-11229 | FAASt Distribution Pole and Conductor Repair - | 523404 | 108652 | 632056 | Distribution
11231 | PA-02-PR-4339-PW-11231 | FAASt Distribution Pole and Conductor Repair | 211622.76 | 33717.31 | 245340.07 | Distribution
11256 | PA-02-PR-4339-PW-11256 | FAASt Distribution Pole and Conductor Repair | 59545.08 | 17491.16 | 77036.24 | Distribution
11257 | PA-02-PR-4339-PW-11257 | FAASt Distribution Pole and Conductor Repair | 186321 | 51841 | 238162 | Distribution
11263 | PA-02-PR-4339-PW-11263 | FAASt Distribution Pole and Conductor Repair | 19848.36 | 5830.39 | 25678.75 | Distribution
11264 | PA-02-PR-4339-PW-11264 | FAASt Distribution Pole and Conductor Repair | 448719.06 | 114710.2 | 563429.26 | Distribution
11267 | PA-02-PR-4339-PW-11267 | FAASt Distribution Pole and Conductor Repair | 64425.44 | 16226.16 | 80651.6 | Distribution
11268 | PA-02-PR-4339-PW-11268 | FAASt Distribution Pole and Conductor Repair | 150345 | 37878 | 188223 | Distribution
11269 | PA-02-PR-4339-PW-11269 | FAASt Distribution Pole and Conductor Repair | 487190 | 129039 | 616229 | Distribution
11273 | PA-02-PR-4339-PW-11273 | FAASt Distribution Pole and Conductor | 42728.41 | 9990.97 | 52719.38 | Distribution
11275 | PA-02-PR-4339-PW-11275 | FAASt Distribution Pole and Conductor Repair | 547010 | 102417 | 649427 | Distribution
11276 | PA-02-PR-4339-PW-11276 | FAASt Distribution Pole and Conductor Repair - | 60838.48 | 16023.76 | 76862.24 | Distribution
11277 | PA-02-PR-4339-PW-11277 | FAASt Distribution Pole and Conductor Repair | 106941.99 | 27886.93 | 134828.92 | Distribution
11279 | PA-02-PR-4339-PW-11279 | FAASt Distribution Pole and Conductor Repair | 710014.69 | 191275.59 | 901290.28 | Distribution
11311 | PA-02-PR-4339-PW-11311 | FAASt Distribution Pole and Conductor Repair - | 338491 | 96676 | 435167 | Distribution
11312 | PA-02-PR-4339-PW-11312 | FAASt [Distribution Pole and Conductor Repair | 273996 | 29974 | 303970 | Distribution
11314 | PA-02-PR-4339-PW-11314 | FAASt Distribution Pole and Conductor Repair - | 486385 | 92244 | 578629 | Distribution
11317 | PA-02-PR-4339-PW-11317 | FAASt [Distribution Streetlighting - Gurabo] | 19208994 | 1533300 | 20742294 | Distribution
11318 | PA-02-PR-4339-PW-11318 | FAASt [San Germán Streetlighting] (Distributio | 30849348 | 4033578 | 34882926 | Distribution
11319 | PA-02-PR-4339-PW-11319 | FAASt Aguadilla Streetlight (Distribution) | 19796809 | 1295775 | 21092584 | Distribution
11326 | PA-02-PR-4339-PW-11326 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | 25277347 | 1009578 | 26286925 | Distribution
11340 | PA-02-PR-4339-PW-11340 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 320740 | 88558 | 409298 | Distribution
11344 | PA-02-PR-4339-PW-11344 | FAASt Streetlight Florida Distribution | 9311841.53 | 997190 | 10309031.53 | Distribution
11347 | PA-02-PR-4339-PW-11347 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | 2796182 | 3575881 | 6372063 | Substation
11350 | PA-02-PR-4339-PW-11350 | FAASt Physical Security - Group 2 (Substation) | 2159012.31 | 224680.68 | 2383692.99 | Substation
11351 | PA-02-PR-4339-PW-11351 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | 73737224.58 | 1849344.06 | 75586568.64 | Distribution
11352 | PA-02-PR-4339-PW-11352 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 438209.69 | 86181.92 | 524391.61 | Distribution
11365 | PA-02-PR-4339-PW-11365 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | 1464496 | 378483 | 1842979 | Distribution
11372 | PA-02-PR-4339-PW-11372 | FAASt [Physical Security - Group 3] (Substation) | 3696956.6 | 436383.23 | 4133339.83 | Substation
11385 | PA-02-PR-4339-PW-11385 | FAASt Substation Minor Repairs -Group B (Substation) | 2973035 | 439541 | 3412576 | Substation
11402 | PA-02-PR-4339-PW-11402 | FAASt [Costa Sur TC - Phase II &amp;amp; III ] (Substation) | 61444255.52 | 0 | 61444255.52 | Substation
11449 | PA-02-PR-4339-PW-11449 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | 642721 | 125133 | 767854 | Distribution
11465 | PA-02-PR-4339-PW-11465 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 1201420 | 224731 | 1426151 | Distribution
11478 | PA-02-PR-4339-PW-11478 | FAASt- Substation Minor Repairs Group C (Substation) | 2648259.06 | 384632.14 | 3032891.2 | Substation
11479 | PA-02-PR-4339-PW-11479 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | 8180049.03 | 7159883.3 | 15339932.33 | Substation
11489 | PA-02-PR-4339-PW-11489 | FAASt Centro Medico 1327/1359 Equipment Repair &amp;amp; Replacement (Substation) | 14795324 | 6537037 | 21332361 | Substation
11508 | PA-02-PR-4339-PW-11508 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 16, 17, 18 &amp;amp; 19] (Distribution) | 1764568.92 | 389437.84 | 2154006.76 | Distribution
11518 | PA-02-PR-4339-PW-11518 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | 9762754.59 | 853056.42 | 10615811.01 | Distribution
11522 | PA-02-PR-4339-PW-11522 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | 14918381.07 | 1965608.26 | 16883989.33 | Distribution
11524 | PA-02-PR-4339-PW-11524 | FAASt Coamo Streetlight (Distribution) | 14311922.45 | 2060901.35 | 16372823.8 | Distribution
11526 | PA-02-PR-4339-PW-11526 | FAASt Streetlight - Las Marías (Distribution) | 7073217 | 1287705 | 8360922 | Distribution
11532 | PA-02-PR-4339-PW-11532 | FAASt [Streetlighting - Mayagüez] (Distribution) | 11019180.1 | 1352204.36 | 12371384.46 | Distribution
11533 | PA-02-PR-4339-PW-11533 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | 14865613.02 | 1158946.56 | 16024559.58 | Distribution
11534 | PA-02-PR-4339-PW-11534 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 85296.74 | 2478.06 | 87774.8 | Distribution
11537 | PA-02-PR-4339-PW-11537 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 5962412.52 | 1701923.62 | 7664336.14 | Telecommunications
11540 | PA-02-PR-4339-PW-11540 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | 20710527 | 1176376 | 21886903 | Distribution
11555 | PA-02-PR-4339-PW-11555 | FAASt - EPC - [San Juan SP TC] (Substation) | 61558468.95 | 0 | 61558468.95 | Substation
11556 | PA-02-PR-4339-PW-11556 | FAASt - EPC - [Sabana Llana TC] (Substation) | 46643078.39 | 0 | 46643078.39 | Substation
11557 | PA-02-PR-4339-PW-11557 | FAASt - EPC - [Monacillo TC] (Substations) | 88096455.74 | 0 | 88096455.74 | Substation
11560 | PA-02-PR-4339-PW-11560 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | 13720208.31 | 2225873.62 | 15946081.93 | Distribution
11566 | PA-02-PR-4339-PW-11566 | FAASt [Physical Security - Group 4] (Substation) | 3478518 | 338280 | 3816798 | Substation
11573 | PA-02-PR-4339-PW-11573 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 6929384 | 0 | 6929384 | Substation
11583 | PA-02-PR-4339-PW-11583 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 332062581 | 544207595 | 876270176 | Telecommunications
11627 | PA-02-PR-4339-PW-11627 | FAASt [Morovis Streetlighting] (Distribution) | 13486398.85 | 1744482.27 | 15230881.12 | Distribution
11629 | PA-02-PR-4339-PW-11629 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | 8070964.96 | 1339801.28 | 9410766.24 | Distribution
11633 | PA-02-PR-4339-PW-11633 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | 13807923.4 | 1807601.11 | 15615524.51 | Distribution
11636 | PA-02-PR-4339-PW-11636 | FAASt [Toa Baja Streetlighting] (Distribution) | 9529190.37 | 620134.69 | 10149325.06 | Distribution
11639 | PA-02-PR-4339-PW-11639 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 7096249.5 | 195136.32 | 7291385.82 | Distribution
11640 | PA-02-PR-4339-PW-11640 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 5425810.57 | 165903.3 | 5591713.87 | Distribution
11650 | PA-02-PR-4339-PW-11650 | FAASt [Ceiba Streetlighting] (Distribution) | 5152111.14 | 716918.6 | 5869029.74 | Distribution
11652 | PA-02-PR-4339-PW-11652 | FAASt - EPC -Aguirre TC-Phase II (Substation) | 82726096.38 | 0 | 82726096.38 | Substation
11658 | PA-02-PR-4339-PW-11658 | FAASt [Naguabo Streetlighting] (Distribution) | 11620676.42 | 1669736.97 | 13290413.39 | Distribution
11664 | PA-02-PR-4339-PW-11664 | FAASt [Naranjito Streetlighting] (Distribution) | 11644048.43 | 2115538.38 | 13759586.81 | Distribution
11666 | PA-02-PR-4339-PW-11666 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 5629060 | 178712.97 | 5807772.97 | Distribution
11671 | PA-02-PR-4339-PW-11671 | FAASt [Arroyo Streetlighting] (Distribution) | 5314332 | 740394.01 | 6054726.01 | Distribution
11673 | PA-02-PR-4339-PW-11673 | FAASt [Vega Alta Streetlighting] (Distribution) | 12445015.33 | 1869089.52 | 14314104.85 | Distribution
11675 | PA-02-PR-4339-PW-11675 | FAASt [Barranquitas Streetlighting] (Distribution) | 9430329.22 | 1577046.09 | 11007375.31 | Distribution
11680 | PA-02-PR-4339-PW-11680 | FAASt [Culebra Streetlighting] (Distribution) | 1155804 | 153603 | 1309407 | Distribution
11682 | PA-02-PR-4339-PW-11682 | FAASt Substation Minor Repairs - Group D (Substation) | 2583133.54 | 288123.63 | 2871257.17 | Substation
11686 | PA-02-PR-4339-PW-11686 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 10313627 | 306131.37 | 10619758.37 | Distribution
11696 | PA-02-PR-4339-PW-11696 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 0 | 18151116.72 | 18151116.72 | Vegetation
11707 | PA-02-PR-4339-PW-11707 | FAASt [Substation Minor Repairs - Group E] (Substation) | 3924015.69 | 579767.52 | 4503783.21 | Substation
11711 | PA-02-PR-4339-PW-11711 | FAASt [Añasco Streetlighting] (Distribution) | 12087876.17 | 1820361.92 | 13908238.09 | Distribution
11712 | PA-02-PR-4339-PW-11712 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 4926640.11 | 147870.9 | 5074511.01 | Distribution
11714 | PA-02-PR-4339-PW-11714 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 4807675.47 | 13386633.34 | 18194308.81 | Vegetation
11715 | PA-02-PR-4339-PW-11715 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 6849050.26 | 19064883.85 | 25913934.11 | Vegetation
11716 | PA-02-PR-4339-PW-11716 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 1033375.81 | 84035.96 | 1117411.77 | Distribution
11718 | PA-02-PR-4339-PW-11718 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 3767690.42 | 10493001.48 | 14260691.9 | Vegetation
11719 | PA-02-PR-4339-PW-11719 | FAASt [T-Pole Program Line 100] (Transmission) | 94787.57 | 23372.71 | 118160.28 | Transmission
11723 | PA-02-PR-4339-PW-11723 | FAASt T-Pole Program Line 3700] (Transmission) | 303960.92 | 73393.66 | 377354.58 | Transmission
11724 | PA-02-PR-4339-PW-11724 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 7414164.75 | 20637925.62 | 28052090.37 | Vegetation
11725 | PA-02-PR-4339-PW-11725 | FAASt [Cidra Streetlighting] (Distribution) | 12812478.84 | 1838229.6 | 14650708.44 | Distribution
11726 | PA-02-PR-4339-PW-11726 | FAASt HV Equipment Replacement Group 2 (Substation) | 15413889.89 | 0 | 15413889.89 | Substation
11727 | PA-02-PR-4339-PW-11727 | FAASt [Comerio Streetlighting] (Distribution) | 6538769.44 | 862125.75 | 7400895.19 | Distribution
11734 | PA-02-PR-4339-PW-11734 | FAASt [Adjuntas Streetlighting] (Distribution) | 10742462 | 1891152 | 12633614 | Distribution
11735 | PA-02-PR-4339-PW-11735 | FAASt [Jayuya Streetlighting] (Distribution) | 7277670.2 | 1350541.32 | 8628211.52 | Distribution
11739 | PA-02-PR-4339-PW-11739 | FAASt [Salinas Streetlighting] (Distribution) | 12097203.53 | 1611020.9 | 13708224.43 | Distribution
11746 | PA-02-PR-4339-PW-11746 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 10940320.91 | 395663.43 | 11335984.34 | Distribution
11753 | PA-02-PR-4339-PW-11753 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 5461200.05 | 205587.38 | 5666787.43 | Distribution
11754 | PA-02-PR-4339-PW-11754 | FAASt [T-Pole Program Line 3000] (Transmission) | 559076.77 | 72117.49 | 631194.26 | Transmission
11764 | PA-02-PR-4339-PW-11764 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 17307539.01 | 0 | 17307539.01 | Substation
11839 | PA-02-PR-4339-PW-11839 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | 467287.6 | 0 | 467287.6 | Distribution
11850 | PA-02-PR-4339-PW-11850 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 11041271 | 409899.81 | 11451170.81 | Distribution
11667 | PA-02-PR-4339-PW-11667 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 6704421.6922 | 239376.93 | 6943798.6222 | Distribution
11812 | PA-02-PR-4339-PW-11812 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 13884126 | 377123.67 | 14261249.67 | Distribution
108001 | PA-02-PR-4339-PW-108001 | FAASt [Automation Program Group 20] (TL/Distribution) | 2623262.08 | 0 | 2623262.08 | Distribution
108000 | PA-02-PR-4339-PW-108000 | FAASt [Automation Program Group 19] (TL/Distribution) | 2753627.24 | 0 | 2753627.24 | Distribution
108022 | PA-02-PR-4339-PW-108022 | FAASt [Automation Program Group 15] (TL/Distribution) | 643560.85 | 0 | 643560.85 | Distribution
107956 | PA-02-PR-4339-PW-107956 | FAASt [Automation Program Group 14] (TL/Distribution) | 1640186.96 | 0 | 1640186.96 | Distribution
107957 | PA-02-PR-4339-PW-107957 | FAASt [Automation Program Group 12] (TL/Distribution) | 3664210.1 | 0 | 3664210.1 | Distribution
11721 | PA-02-PR-4339-PW-11721 | FAASt - [Taft - MC 1105] (Substations) | 9362729.93 | 4123842.4 | 13486572.33 | Substation
| TOTAL LUMA |  | 1714393436.3922 | 734259141.97 | 2448652578.3622 | 0
C
PW | Genera - Obligated | Project Name | 428 | 406 | Total Child | Asset |  | Obligated by PREPA- Transferred | Total Obligated by Genera
10568 | PA-02-PR-4339-PW-10568 | FAASt Aguirre Power Plant 002 Units 1 &2 | 1366048.03 | 0 | 1366048.03 | Generation |  | -1366048.03 | 0
10571 | PA-02-PR-4339-PW-10571 | FAASt Aguirre Power Plant 001 Infrastructure | 2020619.28 | 0 | 2020619.28 | Generation |  | -1649290.05 | 371329.23
10606 | PA-02-PR-4339-PW-10606 | FAASt Palo Seco Power Plant 001 Units 3 & 4 | 22266817.84 | 0 | 22266817.84 | Generation |  | -22266817.84 | 0
10607 | PA-02-PR-4339-PW-10607 | FAASt Cambalache Power Plant Permanent Repair | 0 | 0 | 0 | Generation |  | 0 | 0
10608 | PA-02-PR-4339-PW-10608 | FAASt San Juan Power Plant - Auxiliary Infras | 50450 | 0 | 50450 | Generation |  | -50450 | 0
10609 | PA-02-PR-4339-PW-10609 | FAASt Palo Seco 002- Auxiliary Infrastructure | 4012636.75 | 0 | 4012636.75 | Generation |  | -2309636.75 | 1703000
10615 | PA-02-PR-4339-PW-10615 | FAASt San Juan 001  Units 5 &amp;amp; 6 (Generation | 45439729.74 | 0 | 45439729.74 | Generation |  | -43799599.99 | 1640129.75
10622 | PA-02-PR-4339-PW-10622 | FAASt Aguirre Power Plant 003 Combined Cycle | 2565944.68 | 0 | 2565944.68 | Generation |  | -2565944.68 | 0
10694 | PA-02-PR-4339-PW-10694 | FAASt Costa Sur 002 -Infrastructure projects ( | 899000 | 0 | 899000 | Generation |  | -899000 | 0
10702 | PA-02-PR-4339-PW-10702 | FAASt Costa Sur Power Plant Permanent | 31242323.9 | 0 | 31242323.9 | Generation |  | -26323758.83 | 4918565.07
11085 | PA-02-PR-4339-PW-11085 | FAASt San Juan Power Plant 002 Units 7 & 8 | 18658766.12 | 0 | 18658766.12 | Generation |  | -18369674.42 | 289091.7
11510 | PA-02-PR-4339-PW-11510 | FAASt - IT/0T System Upgrade for all Power Plants | 0 | 0 | 0 | Generation |  | 0 | 0
11855 | PA-02-PR-4339-PW-11855 | FAASt Generation Fleet Project (Generation) | 235670650 | 0 | 235670650 | Generation |  | 0 | 235670650
108066 | PA-02-PR-4339-PW-108066 | FAASt [Auxiliary Equipment] (Generation) | 18912976 | 0 | 18912976 | Generation |  | 0 | 18912976
|  |  | 383105962.34 | 0 | 383105962.34 | 0 |  | -119600220.59 | 263505741.75
D
| GRAND TOTAL |  | 2399437710.2022 | 734437462.87 | 3133875173.0722
Selected Projects under Formulation *
PRJ | PREPA -Under Formulation | Project Name | 428 | 406 | Total Child | Asset
178722 | PA-02-PR-4339-PRJ-178722 | FAASt [Caonillas Reservoir - Dredging] (Dams/Hydro) | 81557757 |  | 81557757 | Water/Hydro
180723 | PA-02-PR-4339-PRJ-180723 | FAASt [Rio Blanco Hydroelectric System] (Dams/Hydro) | 22911551 | 26094024.55 | 49005575.55 | Water/Hydro
334769 | PA-02-PR-4339-PRJ-334769 | FAASt [Garzas Reservoir – Dredging] (Dams/Hydro) | 11154286 |  | 11154286 | Water/Hydro
334770 | PA-02-PR-4339-PRJ-334770 | FAASt [Guajataca Dam – Permanent Repairs] (Dams/Hydro) & Dredging | 566085576 | 520884424 | 1086970000 | Water/Hydro
334772 | PA-02-PR-4339-PRJ-334772 | FAASt [Guayabal Reservoir – Dredging] (Dams/Hydro) | 20606934 |  | 20606934 | Water/Hydro
334773 | PA-02-PR-4339-PRJ-334773 | FAASt [Lucchetti Reservoir – Dredging] (Dams/Hydro) | 35810000 |  | 35810000 | Water/Hydro
334798 | PA-02-PR-4339-PRJ-334798 | FAASt [Guerrero Reservoir – Dredging] (Dams/Hydro) | 3918132 |  | 3918132 | Water/Hydro
334803 | PA-02-PR-4339-PRJ-334803 | FAASt [Loco Reservoir Dredging] (Dams/Hydro) | 2730000 |  | 2730000 | Water/Hydro
334811 | PA-02-PR-4339-PRJ-334811 | FAASt [Dos Bocas Reservoir Dredging] (Dams/Hydro) | 79831592 |  | 79831592 | Water/Hydro
334813 | PA-02-PR-4339-PRJ-334813 | FAASt [Guayo Reservoir Dredging] (Dams/Hydro) | 17260000 |  | 17260000 | Water/Hydro
335206 | PA-02-PR-4339-PRJ-335206 | FAASt [Matrullas Reservoir–Dredging] (Dams/Hydro) | 8055082 |  | 8055082 | Water/Hydro
335207 | PA-02-PR-4339-PRJ-335207 | FAASt Guineo Reservoir – Dredging (Dams/Hydro) | 4271000 |  | 4271000 | Water/Hydro
344771 | PA-02-PR-4339-PRJ-344771 | FAASt [Guajataca Dam Dredging | 40334479 |  | 40334479 | Water/Hydro
435769 | PA-02-PR-4339-PRJ-435769 | FAASt [South Coast Irrigation District - Canals] (Dams/Hydro) | 117758206.89 | 27093224.61 | 144851431.5 | Water/Hydro
436462 | PA-02-PR-4339-PRJ-436462 | FAASt [Lajas Irrigation Canals] (Dams/Hydro) | 37270276.12 | 5302995.4 | 42573271.52 | Water/Hydro
436467 | PA-02-PR-4339-PRJ-436467 | FAASt [Isabela Irrigation District - Canals] (Dams/Hydro) | 15000000 |  | 15000000 | Water/Hydro
436468 | PA-02-PR-4339-PRJ-436468 | FAASt [Toro Negro Hydroelectric System Connection](Dams/Hydro) | 43483764.17 | 13760297.54 | 57244061.71 | Water/Hydro
436621 | PA-02-PR-4339-PRJ-436621 | FAASt [Dams Minor Repairs] (Dams/Hydro) | 15309227 | 9298063.48 | 24607290.48 | Water/Hydro
721184 | PA-02-PR-4339-PRJ-721184 | FAASt Guayabal Dam Repairs and Mitigation (Dams/Hydro) | 163240107.05 | 162914788.74 | 326154895.79 | Water/Hydro
728260 | PA-02-PR-4339-PRJ-728260 | FAASt [Caonillas HydroElectric Power Plant No. 1] (Dams/Hydro) | 3611152 |  | 3611152 | Water/Hydro
|  |  | 1290199550.23 | 765348224.32 | 2055546940.55 | 0
B-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal. Subject to change after FEMA validation
PRJ | LUMA - Under Formulation | Project Name | 428 | 406 | Total Child | Asset
165209 | PA-02-PR-4339-PRJ-165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | 12765828 | 177391 | 12943219 | Vieques and Culebra Projects
165225 | PA-02-PR-4339-PW-10624 | FAASt-Substation 2501 Vieques (Substation) & New 2502 Substation | 13495526.25 |  | 13495526.25 | Vieques and Culebra Projects
165226 | PA-02-PR-4339-PRJ-165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | 86759244 |  | 86759244 | Vieques and Culebra Projects
167446 | PA-02-PR-4339-PRJ-167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | 34329274.96 |  | 34329274.96 | Priority Transmission
169058 | PA-02-PR-4339-PRJ-169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 18279001 |  | 18279001 | Substation
169276 | PA-02-PR-4339-PRJ-169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | 20425907 |  | 20425907 | Substation
176913 | PA-02-PR-4339-PRJ-176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 34395876.55 | 7376901 | 41772777.55 | Priority Transmission
176971 | PA-02-PR-4339-PRJ-176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 22273190.89 | 4723291 | 26996481.89 | Priority Transmission
178577 | PA-02-PR-4339-PRJ-178577 | FAASt [Cachete – MC 1526] (Substations) |  |  | 0 | Substation
180052 | PA-02-PR-4339-PRJ-180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | 85971750.2 |  | 85971750.2 | Priority Transmission
334470 | PA-02-PR-4339-PRJ-334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 46064675.98 |  | 46064675.98 | Priority Transmission
547187 | PA-02-PR-4339-PRJ-547187 | FAASt - [Substation Component Replacement Program] (Substation) | 4790316.92 |  | 4790316.92 | Substation
550106 | PA-02-PR-4339-PRJ-550106 | FAASt [Conquistador CH] (Substation) | 11639958 |  | 11639958 | Substation
550950 | PA-02-PR-4339-PRJ-550950 | FAASt - EPC - [Monacillo TC] (Substations) | -29901321.56 |  | -29901321.56 | Priority Substation | PW Version
551914 | PA-02-PR-4339-PRJ-551914 | FAASt [Caparra 1912 & 1924] (Substation) |  |  | 0 | Substation
682328 | PA-02-PR-4339-PRJ-682328 | FAASt [Bayamón TC - Rebuild] (Substation) | 2637502.74 |  | 2637502.74 | Substation
682645 | PA-02-PR-4339-PRJ-682645 | FAASt [Maunabo TC] (Substation) | 8292124.95 |  | 8292124.95 | Priority Substation
682834 | PA-02-PR-4339-PRJ-682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | -24526745.94 |  | -24526745.94 | Priority Substation | PW Version
711819 | PA-02-PR-4339-PRJ-711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | 1705844 | 158417 | 1864261 | Transmission
723883 | PA-02-PR-4339-PRJ-723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 6584889.61 | 18404524.67 | 24989414.28 | Vegetation
727522 | PA-02-PR-4339-PRJ-727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 18031093.89 | 53608045.16 | 71639139.05 | Vegetation
727529 | PA-02-PR-4339-PRJ-727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 18318077.75 | 54661273.75 | 72979351.5 | Vegetation
727572 | PA-02-PR-4339-PRJ-727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 12945985.39 | 36028872.38 | 48974857.77 | Vegetation
727606 | PA-02-PR-4339-PRJ-727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 36846766.07 | 109548711.44 | 146395477.51 | Vegetation
727608 | PA-02-PR-4339-PRJ-727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 8206527.54 | 24398735.91 | 32605263.45 | Vegetation
727657 | PA-02-PR-4339-PRJ-727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 30865299.08 | 91765278.3 | 122630577.38 | Vegetation
727659 | PA-02-PR-4339-PRJ-727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 18265704.46 | 54305563.22 | 72571267.68 | Vegetation
735474 | PA-02-PR-4339-PRJ-735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 14075641.42 |  | 14075641.42 | Distribution
741105 | PA-02-PR-4339-PRJ-741105 | FAASt [All Regions TL - 230kV] (Vegetation) | 154791845.18 |  | 154791845.18 | Vegetation
749060 | PA-02-PR-4339-PRJ-749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | 717817.65 | 142335 | 860152.65 | Transmission
749072 | PA-02-PR-4339-PRJ-749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | 158495.32 | 30755.87 | 189251.19 | Transmission
750150 | PA-02-PR-4339-PRJ-750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | 58488 | 5771.31 | 64259.31 | Transmission
750151 | PA-02-PR-4339-PRJ-750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | 123160.67 | 11027.93 | 134188.6 | Transmission
750168 | PA-02-PR-4339-PRJ-750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | 404349.3 | 28538.88 | 432888.18 | Transmission
750692 | PA-02-PR-4339-PRJ-750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 12921047 | 0 | 12921047 | Distribution
752540 | PA-02-PR-4339-PRJ-752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 7111613.91 | 0 | 7111613.91 | Distribution
753782 | PA-02-PR-4339-PRJ-753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | 124593.02 | 14809.67 | 139402.69 | Transmission
757689 | PA-02-PR-4339-PRJ-757689 | FAASt [Automation Program Group 24] (TL/ Distribution) | 1774822.4 | 0 | 1774822.4 | 428 Distribution Automation
757692 | PA-02-PR-4339-PRJ-757692 | FAASt [Automation Program Group 26] (TL / Distribution) | 938783.63 | 0 | 938783.63 | 428 Distribution Automation
757696 | PA-02-PR-4339-PRJ-757696 | FAASt [Automation Program Group 31] (Distribution) | 1145457.61 | 0 | 1145457.61 | 428 Distribution Automation
757700 | PA-02-PR-4339-PRJ-757700 | FAASt [Automation Program Group 35] (TL / Distribution) | 1318515.66 | 0 | 1318515.66 | 428 Distribution Automation
790443 | PA-02-PR-4339-PRJ-790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 186697 | 0 | 186697 | Distribution
797148 | PA-02-PR-4339-PRJ-797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | 2359895.63 | 0 | 2359895.63 | Distribution
798275 | PA-02-PR-4339-PRJ-798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | 6711420.9 | 0 | 6711420.9 | Distribution
800286 | PA-02-PR-4339-PRJ-800286 | FAASt [Automation Program Group 36] (TL / Distribution) | 1703712.83 | 0 | 1703712.83 | 428 Distribution Automation
800361 | PA-02-PR-4339-PRJ-800361 | FAASt [Automation Program Group 37] (Distribution) | 1596192.73 | 0 | 1596192.73 | 428 Distribution Automation
801166 | PA-02-PR-4339-PRJ-801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | 19191185.67 |  | 19191185.67 | Distribution
801172 | PA-02-PR-4339-PRJ-801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | 2285961.13 | 0 | 2285961.13 | Distribution
825843 | PA-02-PR-4339-PRJ-825843 | FAASt [Guanica TC] (Substation) | 2320373.96 | 0 | 2320373.96 | Priority Substation
956330 | PA-02-PR-4339-PRJ-956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | 1968823.15 | 5853486.17 | 7822309.32 | Vegetation
956331 | PA-02-PR-4339-PRJ-956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | 1977622.66 | 5879647.9 | 7857270.56 | Vegetation
956332 | PA-02-PR-4339-PRJ-956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | 2787055.9 | 8286164.87 | 11073220.77 | Vegetation
956335 | PA-02-PR-4339-PRJ-956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | 1849955.27 | 5500081.4 | 7350036.67 | Vegetation
956337 | PA-02-PR-4339-PRJ-956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | 1800712.05 | 5353676.97 | 7154389.02 | Vegetation
956339 | PA-02-PR-4339-PRJ-956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | 2959532.24 | 8798952.37 | 11758484.61 | Vegetation
956340 | PA-02-PR-4339-PRJ-956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | 1624663.76 | 4830269.73 | 6454933.49 | Vegetation
956341 | PA-02-PR-4339-PRJ-956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | 24080 | 71591.83 | 95671.83 | Vegetation
956342 | PA-02-PR-4339-PRJ-956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | 10945700.85 | 32542541.69 | 43488242.54 | Vegetation
956343 | PA-02-PR-4339-PRJ-956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | 5271329.93 | 15672132.45 | 20943462.38 | Vegetation
956345 | PA-02-PR-4339-PRJ-956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | 1805809.83 | 5368833.09 | 7174642.92 | Vegetation
956348 | PA-02-PR-4339-PRJ-956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | 294309.16 | 875007.19 | 1169316.35 | Vegetation
956349 | PA-02-PR-4339-PRJ-956349 | FAASt [San Juan Region 1 Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | 3415441.98 | 10154412.56 | 13569854.54 | Vegetation
956353 | PA-02-PR-4339-PRJ-956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | 9124048.44 | 27126607.1 | 36250655.54 | Vegetation
956356 | PA-02-PR-4339-PRJ-956356 | FAASt [Ponce Region 6 Line 39000 – Aguas Buenas to Hacienda San Jose] (Vegetation) | 843405.43 | 2626357.86 | 3469763.29 | Vegetation
956357 | PA-02-PR-4339-PRJ-956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | 3415441.98 | 9313002.71 | 12728444.69 | Vegetation
551963 | PA-02-PR-4339-PRJ-551963 | FAASt [Transport Network Group 1] (Telecommunication) | 5490296.88 | 0 | 5490296.88 | Telecommunication
755211 | PA-02-PR-4339-PRJ-755211 | FAASt [Automation Program Group 15] (Distribution) | 643560.85 | 0 | 643560.85 | 428 Distribution Automation
679133 | PA-02-PR-4339-PRJ-679133 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 4] (Distribution) | -20729 |  | -20729 | Distribution
168483 | PA-02-PR-4339-PRJ-168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) |  |  | 0 | Transmission
757687 | PA-02-PR-4339-PRJ-757687 | FAASt [Automation Program Group 22] (Distribution) | 2356733.87 | 0 | 2356733.87 | 428 Distribution Automation
757697 | PA-02-PR-4339-PRJ-757697 | FAASt [Automation Program Group 32] (TL / Distribution) | 1996678.58 | 0 | 1996678.58 | 428 Distribution Automation
812569 | PA-02-PR-4339-PRJ-812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | 10217566.54 |  | 10217566.54 | Distribution
817956 | PA-02-PR-4339-PRJ-817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 2054461.78 |  | 2054461.78 | Distribution
714641 | PA-02-PR-4339-PRJ-714641 | FAASt [Rincón Streetlighting] (Distribution) | 10915553.24 | 1211588.91 | 12127142.15 | Distribution | PW Version
723002 | PA-02-PR-4339-PRJ-723002 | FAASt - EPC - Jobos TC (Substation) | 70586386.39 |  | 70586386.39 | Substation
551926 | PA-02-PR-4339-PRJ-551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 5267467.99 | 1073462.61 | 6340930.6 | Telecommunication | PW Version
673292 | PA-02-PR-4339-PRJ-673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 8124106.79 | 49577.82 | 8173684.61 | Telecommunication | PW Version
547251 | PA-02-PR-4339-PRJ-547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 50289473.68 |  | 50289473.68 | Transmission
756997 | PA-02-PR-4339-PRJ-756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | 40557533.61 |  | 40557533.61 | Transmission
756999 | PA-02-PR-4339-PRJ-756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | 29319358.78 |  | 29319358.78 | Transmission
750063 | PA-02-PR-4339-PRJ-750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 18254467.11 | 50797296.22 | 69051763.33 | Vegetation
750065 | PA-02-PR-4339-PRJ-750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 21333819.52 | 59366309.82 | 80700129.34 | Vegetation
750066 | PA-02-PR-4339-PRJ-750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 32703357.23 | 90995446.51 | 123698803.74 | Vegetation
750067 | PA-02-PR-4339-PRJ-750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 17267191.18 | 48049971.59 | 65317162.77 | Vegetation
750068 | PA-02-PR-4339-PRJ-750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 15900537.4 | 44246939.88 | 60147477.28 | Vegetation
956593 | PA-02-PR-4339-PRJ-956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | 3751193.63 |  | 3751193.63 | Substation
746309 | PA-02-PR-4339-PRJ-746309 | FAASt [Automation Program Group 30] (Distribution) | 425975.74 |  | 425975.74 | Distribution
757662 | PA-02-PR-4339-PRJ-757662 | FAASt [Automation Program Group 21] (Distribution) | 1710547.94 | 0 | 1710547.94 | 428 Distribution Automation
757694 | PA-02-PR-4339-PRJ-757694 | FAASt [Automation Program Group 27] (Distribution) | 2314733.78 | 0 | 2314733.78 | 428 Distribution Automation
757698 | PA-02-PR-4339-PRJ-757698 | FAASt [Automation Program Group 33] (Distribution) | 1888928.21 | 0 | 1888928.21 | 428 Distribution Automation
757699 | PA-02-PR-4339-PRJ-757699 | FAASt [Automation Program Group 34] (Distribution) | 2755938.99 | 0 | 2755938.99 | 428 Distribution Automation
957578 | PA-02-PR-4339-PRJ-957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | 1108989.51 |  | 1108989.51 | Substation
165213 | PA-02-PR-4339-PRJ-165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 83734340.49 | 33182392.65 | 116916733.14 | Vieques and Culebra Projects
751655 | PA-02-PR-4339-PRJ-751655 | FAASt [Vieques Microgrid] (Transmission) | 0 | 105481956 | 105481956 | Vieques and Culebra Projects
751656 | PA-02-PR-4339-PRJ-751656 | FAASt [Culebra Microgrid] (Transmission) | 0 | 39954081 | 39954081 | Vieques and Culebra Projects
678800 | PA-02-PR-4339-PRJ-678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 13148929.44 | 55895.84 | 13204825.28 | Telecommunication
662238 | PA-02-PR-4339-PRJ-662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 14142413.06 | 3014559.92 | 17156972.98 | Telecommunication
746545 | PA-02-PR-4339-PRJ-746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 115638378 | 15530896 | 131169274 | Telecommunication
746660 | PA-02-PR-4339-PRJ-746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 15096658.56 | 1617375.6 | 16714034.16 | Substation
|  |  | 1380565578.75 | 603643415.38 | 1984208994.13 | 0
C-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal. Subject to change after FEMA validation
PW | Genera - Under Formulation | Project Name | 428 | 406 | Total Child | Asset
164988 | PA-02-PR-4339-PRJ-164988 | FAASt Generation Fleet Project (Generation) | 406717776.67 |  | 406717776.67 | Priority Generation
662957 | PA-02-PR-4339-PRJ-662957 | FAASt [Palo Seco Power Plant –001 Units 3 & 4] (Generation) | 5691871.22 |  | 5691871.22 | Generation
663383 | PA-02-PR-4339-PRJ-663383 | FAASt [Cambalache Power Plant Permanent Repairs] (Generation) | 30000000 | 33059916 | 63059916 | Generation
663385 | PA-02-PR-4339-PRJ-663385 | CLOSEOUT - FAASt [Mayaguez Hydro-Gas Power Plant Permanent Repairs] (Generation) | -337107.18 |  | -337107.18 | Generation
670036 | PA-02-PR-4339-PRJ-670036 | FAASt [Design Fire Pump for Aguirre Power Complex] (Generation) | 25000000 |  | 25000000 | Generation
672950 | PA-02-PR-4339-PRJ-672950 | FAASt [Costa Sur Power Plant Permanent Repairs CS-001] (Generation) | 67252 |  | 67252 | Priority Generation
687480 | PA-02-PR-4339-PRJ-687480 | FAASt [San Juan Power Plant 002 Units 7 & 8] (Generation) | -289091.69 |  | -289091.69 | Generation
754801 | PA-02-PR-4339-PRJ-754801 | FAASt [Repair Unit 9 San Juan Steam Plant] (Generation) | 27432038.24 |  | 27432038.24 | Generation
816612 | PA-02-PR-4339-PRJ-816612 | FAASt [Continuous Emission Monitoring Systems (CEMS)] (Generation) | 5000000 |  | 5000000 | Generation
817248 | PA-02-PR-4339-PRJ-817248 | FAASt [Power Plant Repairs & System Restoration] (Generation) | 89680589.58 |  | 89680589.58 | Priority Generation
948766 | PA-02-PR-4339-PRJ-948766 | FAASt [Physical Security] (Generation) | 5750000 |  | 5750000 | Generation
|  |  | 594713756.84 |  | 594713756.84 | 0
D-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal

## PREPA Consolidated List
Project # | Title | Asset | SUB ASSET | Process Step | Project Estimated Cost | Current PW Version Gross Cost | 428 Allocation | 406 Allocation | A&E-PW 9510 | E&M-PW 10710 | A&E Costs Incurred | E&M Cost Incurred | Estimated Installation Cost Incurred | Total Estimate Incurred Cost | Project Status | Project Status as of 10/10/25 | Project Scope
334770 | FAASt [Guajataca Dam – Permanent Repairs] (Dams/Hydro) & Dredging | Priority Dams/Hydro | Dam | Pending Scope & Cost Completion by Applicant | 1086970000 | 566085576 | 566085576 | 520884424 |  |  | 54000000 | 0 |  | 54000000 | Studies and design being executed by USACE | Studies and design being executed by USACE-DSOW and CE to be submitted to FEMA Decemeber 2026 | Construction works to provide a new stabilization berm, repair of the outlet works improving hydraulic efficiency by installing new gates at the intake tower, enlarge existing water control gates, replacing and realigning the outlet works conduits and construction of a new emergency spillway.
436621 | FAASt [Dams Minor Repairs] (Dams/Hydro) | Dams/Hydro | Dam | Pending EHP Review | 24607290.48 | 15309227 | 15309227 | 9298063.48 | [5 empty] | 0 | Status as 06.17.2025 HM RFI closed- DSOW submitted on June 18th | Project FEMA Under EHP Review | Minor repair work required across 16 dams managed by PREPA. This includes repair and replacement of storm damaged items, repair, and replacement of components with pre-existing damage, security upgrades to sites, and hazard mitigation.
344771 | FAASt [Guajataca Dam Dredging | Priority Dams/Hydro | Dam | Pending Scope & Cost Completion by Applicant | 40334479 | 40334479 | 40334479 |  |  |  | 500212.83 |  |  | 500212.83 | 30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by October 2025 | Restore the water storage capacity of the Guajataca Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
178722 | FAASt [Caonillas Reservoir - Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 81557757 | 81557757 | 81557757 |  |  |  | 792010.65 |  |  | 792010.65 | Status as of 06.17.2025 : DSOW and CE estimated delivery date in September 2025. 30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW unde development. Updated DSOW and CE to be submitted by October/November 2025 | Restore the water storage capacity of the Caonillas Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
334811 | FAASt [Dos Bocas Reservoir Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 79831592 | 79831592 | 79831592 |  |  |  | 809508.44 |  |  | 809508.44 | Status as of 06.17.2024 Updated DSOW and CE date is June 2025. 30% design being reviewed by USACE for submittal | DSOW and CE to be submitted October 15 | Restore the water storage capacity of the Dos Bocas Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
334769 | FAASt [Garzas Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 11154286 | 11154286 | 11154286 |  |  |  | 422565.17 |  |  | 422565.17 | Status as of 06.17.2025 DSOW and CE delivery is scheduled in June 2025. 30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by October 2025 | Restore the water storage capacity of the Garzas Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
334772 | FAASt [Guayabal Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 20606934 | 20606934 | 20606934 |  |  |  | 340514.03 |  |  | 340514.03 | Status as of 06.17.2025 : DSOW and CE estimated delivery date in September 2025.30% design being reviewed by USACE for submittal.30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW unde development. Updated DSOW and CE to be submitted by October/November 2025 | Restore the water storage capacity of the Guayabal Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
334813 | FAASt [Guayo Reservoir Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 17260000 | 17260000 | 17260000 |  |  |  | 611466.73 |  |  | 611466.73 | Status as of 06.17.2025: According to PREPA 2025 Q2 the DSOW and CE estimated delivery date in September 2025.30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Restore the water storage capacity of the Guayo Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
334798 | FAASt [Guerrero Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 3918132 | 3918132 | 3918132 |  |  |  | 359697.37 |  |  | 359697.37 | Status as of 06.17.2025 DSOW and CE estimated delivery date in June 2025. 30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Restore the water storage capacity of the Guerrero Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
334803 | FAASt [Loco Reservoir Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 8080000 | 2730000 | 2730000 |  |  |  | 639344.75 |  |  | 639344.75 | Status as of 06.17.2025: DSOW and CE estimated delivery date in July 2025. 30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Restore the water storage capacity of the Loco Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
334773 | FAASt [Lucchetti Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 40020000 | 35810000 | 35810000 |  |  |  | 802328.98 |  |  | 802328.98 | "Status as of 06.17.2025: Estimated DSOW and CE estimated delivery date in July 2025.Status as of 06.17.2025: 30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Restore the water storage capacity of the Lucchetti Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
335207 | FAASt Guineo Reservoir – Dredging (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 4271000 | 4271000 | 4271000 |  |  |  | 322603.88 |  |  | 322603.88 | 30% design in process for DSOW submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Restore the water storage capacity of the Guineo Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
335206 | FAASt [Matrullas Reservoir–Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 8055082 | 8055082 | 8055082 |  |  |  | 326423.98 |  |  | 326423.98 | Status as of 06.17.2025: According to PREPA 2025 Q2 the DSOW and CE estimated delivery date in September 2025. 30% design being reviewed by USACE for submittal | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Restore the water storage capacity of the Matrulla Reservoir by removing and disposing of sediment material from critical operational zones within the active water storage regions of the reservoir.
180723 | FAASt [Rio Blanco Hydroelectric System] (Dams/Hydro) | Dams/Hydro | Hydro | Pending Scope & Cost Completion by Applicant | 49005575.55 | 22911551 | 22911551 | 26094024.55 |  |  | 358512.53 |  |  | 358512.53 | Status as 06.17.2025 Revised DSOW and CE for the project. Estimated submission date: June 2025 | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Rio Blanco Conveyance System from Sabana Dam to Prieto Dam, Water conveyance pipeline system repairs, collapsed bridges reconstruction, Sabana Dam, Icacos Dam, Rio Blanco Hydroelectric Power Plant, Rio Blanco Penstock repairs.
436468 | FAASt [Toro Negro Hydroelectric System Connection](Dams/Hydro) | Dams/Hydro | Hydro | Pending Scope & Cost Completion by Applicant | 57244061.71 | 43483764.17 | 43483764.17 | 13760297.54 |  |  | 553416.46 |  |  | 553416.46 | "Status as of 06.17.2025 DSOW and CE submission date: October 2025 | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Full replacement of the penstock pipe. Matrullas Channel Sections will be repaired with in-kind materials and point repairs. Replace sluice valves and stoplogs at diversion dams.
436462 | FAASt [Lajas Irrigation Canals] (Dams/Hydro) | Dams/Hydro | Canals | Pending Scope & Cost Completion by Applicant | 42573271.52 | 37270276.12 | 37270276.12 | 5302995.4 |  |  | 518412.41 |  |  | 518412.41 | Status as 06.17.2025 DSOW and CE estimated submission date: December, 2025 | 30% design being reviewed by USACE for submittal/ DSOW under development. Updated DSOW and CE to be submitted by | Restore the existing channel functionality by repairing ruptures, patching cracks, and where required, total replacement, of damaged concrete lining along the Lajas Irrigation Channel and the Lajas Lateral Channels
436467 | FAASt [Isabela Irrigation District - Canals] (Dams/Hydro) | Dams/Hydro | Canals | Pending Scope & Cost Completion by Applicant | 15000000 | 15000000 | 15000000 |  |  |  | 226636.88 |  |  | 226636.88 | Status as of 6.17.2025: Pending DSOW | DSOW under development. Geotechnical investigations to commence towards final 30% Design Completion | Test boring will be performed within the project site area
435769 | FAASt [South Coast Irrigation District - Canals] (Dams/Hydro) | Dams/Hydro | Canals | Pending Scope & Cost Completion by Applicant | 144851431.5 | 117758206.89 | 117758206.89 | 27093224.61 |  |  | 1442355.81 |  |  | 1442355.81 | Status as of 06.17.2025 DSOW and CE delivery is scheduled in June 2025. | Geotechnical investigations are ongoing towards final 30% Design Completion - Designs to be provided in segments (DSOW submission to occur in batches) | The scope of work will consist of strategic repair or replacement of channel linings, structures, foundations, fences, gates, supports, slopes, etc. as required to provide a safe, consistent, and reliable water source for the South Coast Irrigation System. The works will cover Juana Diaz Channel, Guamini Channel and Patillas Chanel Cost Details (per Channel).
728260 | FAASt [Caonillas HydroElectric Power Plant No. 1] (Dams/Hydro) | Dams/Hydro | Hydro | Pending Scope & Cost Completion by Applicant | 3611152 | 3611152 | 3611152 |  |  |  | 329066.4 |  |  | 329066.4 | Status as of 06.17.2025 :According to PREPA 2025 Q2 the DSOW and CE submission is in September 2025 Design taken by USACE" | Draft DSOW Submitted-Pending Follow Up Design Information | Removing debris and sediment in tailrace areas and surroundings, removal of sediment in the vicinity of the plant, and construction of a temporary removable barrier to thoroughly inspect and enable the restoration of, as necessary, turbines, draft tubes, tailrace structure, and isolation gates.
721184 | FAASt Guayabal Dam Repairs and Mitigation (Dams/Hydro) | Dams/Hydro | Dam | Pending Scope & Cost Completion by Applicant | 326154895.79 | 163240107.05 | 163240107.05 | 162914788.74 | [5 empty] | 0 | Status as of 06.17.2025 DSOW and CE submission date scheduled in September 2025. | PREPA coordinating amongst Federal Design Groups(USBR & USACE) for DSOW formulation and completion | Road/pavement repairs. Fencing, swing gates, repair steel arch shed building. Ceiling, interior and exterior walls & steel plate windows from the concrete office building. Steel plate, signage & electrical conduit fronm the facility site/grounds.
[6 empty] | 1290199122.23 |  | 765347818.32
*Amount is subject to change due to FEMA Validation Analysis. Costs presented herein are based on scope of work developed by PREPA
54000000
0
500212.83
792010.65
809508.44
422565.17
340514.03
611466.73
359697.37
639344.75
802328.98
322603.88
326423.98
358512.53
553416.46
518412.41
226636.88
1442355.81
329066.4
0

## PREPA's Inactive Projects
Item | Project # | Title | FEMA Allocation | Asset | Project Status | DSOW was submitted to FEMA? | Estimated A&E Cost Incurred | Estimated E&M Cost Incurred | Other Cost Incurred | Total Estimate Incurred Cost | Is PW included in the Priority Stabilization Plan? | Additional comments
1 |  |  |  |  | Inactive |  | 0 | 0 | 0 | 0 | No
2 | [6 empty] | 0 | 0 | 0 | 0
3 | [6 empty] | 0 | 0 | 0 | 0
4 | [6 empty] | 0 | 0 | 0 | 0
5 | [6 empty] | 0 | 0 | 0 | 0
6 | [6 empty] | 0 | 0 | 0 | 0
7 | [6 empty] | 0 | 0 | 0 | 0
8 | [6 empty] | 0 | 0 | 0 | 0
9 | [6 empty] | 0 | 0 | 0 | 0
10 | [6 empty] | 0 | 0 | 0 | 0
11 | [6 empty] | 0 | 0 | 0 | 0
12 | [6 empty] | 0 | 0 | 0 | 0
13 | [6 empty] | 0 | 0 | 0 | 0
14 | [6 empty] | 0 | 0 | 0 | 0
15 | [6 empty] | 0 | 0 | 0 | 0
16 | [6 empty] | 0 | 0 | 0 | 0
17 | [6 empty] | 0 | 0 | 0 | 0
18 | [6 empty] | 0 | 0 | 0 | 0
19 | [6 empty] | 0 | 0 | 0 | 0
20 | [6 empty] | 0 | 0 | 0 | 0
21 | [6 empty] | 0 | 0 | 0 | 0
22 | [6 empty] | 0 | 0 | 0 | 0
23 | [6 empty] | 0 | 0 | 0 | 0
24 | [6 empty] | 0 | 0 | 0 | 0
25 | [6 empty] | 0 | 0 | 0 | 0
26 | [6 empty] | 0 | 0 | 0 | 0
27 | [6 empty] | 0 | 0 | 0 | 0
28 | [6 empty] | 0 | 0 | 0 | 0
29 | [6 empty] | 0 | 0 | 0 | 0
30 | [6 empty] | 0 | 0 | 0 | 0
31 | [6 empty] | 0 | 0 | 0 | 0
32 | [6 empty] | 0 | 0 | 0 | 0
33 | [6 empty] | 0 | 0 | 0 | 0
34 | [6 empty] | 0 | 0 | 0 | 0
35 | [6 empty] | 0 | 0 | 0 | 0
36 | [6 empty] | 0 | 0 | 0 | 0
37 | [6 empty] | 0 | 0 | 0 | 0
38 | [6 empty] | 0 | 0 | 0 | 0
39 | [6 empty] | 0 | 0 | 0 | 0
40 | [6 empty] | 0 | 0 | 0 | 0
41 | [6 empty] | 0 | 0 | 0 | 0
42 | [6 empty] | 0 | 0 | 0 | 0
43 | [6 empty] | 0 | 0 | 0 | 0
44 | [6 empty] | 0 | 0 | 0 | 0
45 | [6 empty] | 0 | 0 | 0 | 0
46 | [6 empty] | 0 | 0 | 0 | 0
47 | [6 empty] | 0 | 0 | 0 | 0
48 | [6 empty] | 0 | 0 | 0 | 0
49 | [6 empty] | 0 | 0 | 0 | 0
50 | [6 empty] | 0 | 0 | 0 | 0
51 | [6 empty] | 0 | 0 | 0 | 0
52 | [6 empty] | 0 | 0 | 0 | 0
53 | [6 empty] | 0 | 0 | 0 | 0
54 | [6 empty] | 0 | 0 | 0 | 0
55 | [6 empty] | 0 | 0 | 0 | 0
56 | [6 empty] | 0 | 0 | 0 | 0
57 | [6 empty] | 0 | 0 | 0 | 0
58 | [6 empty] | 0 | 0 | 0 | 0
59 | [6 empty] | 0 | 0 | 0 | 0
60 | [6 empty] | 0 | 0 | 0 | 0
61 | [6 empty] | 0 | 0 | 0 | 0
62 | [6 empty] | 0 | 0 | 0 | 0
63 | [6 empty] | 0 | 0 | 0 | 0
64 | [6 empty] | 0 | 0 | 0 | 0
65 | [6 empty] | 0 | 0 | 0 | 0
66 | [6 empty] | 0 | 0 | 0 | 0
67 | [6 empty] | 0 | 0 | 0 | 0
68 | [6 empty] | 0 | 0 | 0 | 0
69 | [6 empty] | 0 | 0 | 0 | 0
70 | [6 empty] | 0 | 0 | 0 | 0
71 | [6 empty] | 0 | 0 | 0 | 0
72 | [6 empty] | 0 | 0 | 0 | 0
73 | [6 empty] | 0 | 0 | 0 | 0
74 | [6 empty] | 0 | 0 | 0 | 0
75 | [6 empty] | 0 | 0 | 0 | 0
76 | [6 empty] | 0 | 0 | 0 | 0
77 | [6 empty] | 0 | 0 | 0 | 0
78 | [6 empty] | 0 | 0 | 0 | 0
79 | [6 empty] | 0 | 0 | 0 | 0
80 | [6 empty] | 0 | 0 | 0 | 0
81 | [6 empty] | 0 | 0 | 0 | 0
82 | [6 empty] | 0 | 0 | 0 | 0
83 | [6 empty] | 0 | 0 | 0 | 0
84 | [6 empty] | 0 | 0 | 0 | 0
85 | [6 empty] | 0 | 0 | 0 | 0
86 | [6 empty] | 0 | 0 | 0 | 0
87 | [6 empty] | 0 | 0 | 0 | 0
88 | [6 empty] | 0 | 0 | 0 | 0
89 | [6 empty] | 0 | 0 | 0 | 0
90 | [6 empty] | 0 | 0 | 0 | 0
91 | [6 empty] | 0 | 0 | 0 | 0
92 | [6 empty] | 0 | 0 | 0 | 0
93 | [6 empty] | 0 | 0 | 0 | 0
94 | [6 empty] | 0 | 0 | 0 | 0
95 | [6 empty] | 0 | 0 | 0 | 0
96 | [6 empty] | 0 | 0 | 0 | 0
97 | [6 empty] | 0 | 0 | 0 | 0
98 | [6 empty] | 0 | 0 | 0 | 0
99 | [6 empty] | 0 | 0 | 0 | 0
100 | [6 empty] | 0 | 0 | 0 | 0
101 | [6 empty] | 0 | 0 | 0 | 0
102 | [6 empty] | 0 | 0 | 0 | 0
103 | [6 empty] | 0 | 0 | 0 | 0
104 | [6 empty] | 0 | 0 | 0 | 0
105 | [6 empty] | 0 | 0 | 0 | 0
106 | [6 empty] | 0 | 0 | 0 | 0
107 | [6 empty] | 0 | 0 | 0 | 0
108 | [6 empty] | 0 | 0 | 0 | 0
109 | [6 empty] | 0 | 0 | 0 | 0
110 | [6 empty] | 0 | 0 | 0 | 0
111 | [6 empty] | 0 | 0 | 0 | 0
112 | [6 empty] | 0 | 0 | 0 | 0
113 | [6 empty] | 0 | 0 | 0 | 0
114 | [6 empty] | 0 | 0 | 0 | 0
115 | [6 empty] | 0 | 0 | 0 | 0
116 | [6 empty] | 0 | 0 | 0 | 0
117 | [6 empty] | 0 | 0 | 0 | 0
118 | [6 empty] | 0 | 0 | 0 | 0
119 | [6 empty] | 0 | 0 | 0 | 0
120 | [6 empty] | 0 | 0 | 0 | 0
121 | [6 empty] | 0 | 0 | 0 | 0
122 | [6 empty] | 0 | 0 | 0 | 0
123 | [6 empty] | 0 | 0 | 0 | 0
124 | [6 empty] | 0 | 0 | 0 | 0
125 | [6 empty] | 0 | 0 | 0 | 0
126 | [6 empty] | 0 | 0 | 0 | 0
127 | [6 empty] | 0 | 0 | 0 | 0
128 | [6 empty] | 0 | 0 | 0 | 0
129 | [6 empty] | 0 | 0 | 0 | 0
130 | [6 empty] | 0 | 0 | 0 | 0
131 | [6 empty] | 0 | 0 | 0 | 0
132 | [6 empty] | 0 | 0 | 0 | 0
133 | [6 empty] | 0 | 0 | 0 | 0
134 | [6 empty] | 0 | 0 | 0 | 0
135 | [6 empty] | 0 | 0 | 0 | 0
136 | [6 empty] | 0 | 0 | 0 | 0
137 | [6 empty] | 0 | 0 | 0 | 0
138 | [6 empty] | 0 | 0 | 0 | 0
139 | [6 empty] | 0 | 0 | 0 | 0
140 | [6 empty] | 0 | 0 | 0 | 0
141 | [6 empty] | 0 | 0 | 0 | 0
142 | [6 empty] | 0 | 0 | 0 | 0
143 | [6 empty] | 0 | 0 | 0 | 0
144 | [6 empty] | 0 | 0 | 0 | 0
145 | [6 empty] | 0 | 0 | 0 | 0
146 | [6 empty] | 0 | 0 | 0 | 0
147 | [6 empty] | 0 | 0 | 0 | 0
148 | [6 empty] | 0 | 0 | 0 | 0
149 | [6 empty] | 0 | 0 | 0 | 0
150 | [6 empty] | 0 | 0 | 0 | 0
151 | [6 empty] | 0 | 0 | 0 | 0
152 | [6 empty] | 0 | 0 | 0 | 0
153 | [6 empty] | 0 | 0 | 0 | 0
154 | [6 empty] | 0 | 0 | 0 | 0
155 | [6 empty] | 0 | 0 | 0 | 0
156 | [6 empty] | 0 | 0 | 0 | 0
157 | [6 empty] | 0 | 0 | 0 | 0
158 | [6 empty] | 0 | 0 | 0 | 0
159 | [6 empty] | 0 | 0 | 0 | 0
160 | [6 empty] | 0 | 0 | 0 | 0
161 | [6 empty] | 0 | 0 | 0 | 0
162 | [6 empty] | 0 | 0 | 0 | 0
163 | [6 empty] | 0 | 0 | 0 | 0
164 | [6 empty] | 0 | 0 | 0 | 0
165 | [6 empty] | 0 | 0 | 0 | 0
166 | [6 empty] | 0 | 0 | 0 | 0
167 | [6 empty] | 0 | 0 | 0 | 0
168 | [6 empty] | 0 | 0 | 0 | 0
169 | [6 empty] | 0 | 0 | 0 | 0
170 | [6 empty] | 0 | 0 | 0 | 0
171 | [6 empty] | 0 | 0 | 0 | 0
172 | [6 empty] | 0 | 0 | 0 | 0
173 | [6 empty] | 0 | 0 | 0 | 0
174 | [6 empty] | 0 | 0 | 0 | 0
175 | [6 empty] | 0 | 0 | 0 | 0
176 | [6 empty] | 0 | 0 | 0 | 0
177 | [6 empty] | 0 | 0 | 0 | 0
178 | [6 empty] | 0 | 0 | 0 | 0
179 | [6 empty] | 0 | 0 | 0 | 0
180 | [6 empty] | 0 | 0 | 0 | 0
181 | [6 empty] | 0 | 0 | 0 | 0
182 | [6 empty] | 0 | 0 | 0 | 0
183 | [6 empty] | 0 | 0 | 0 | 0
184 | [6 empty] | 0 | 0 | 0 | 0
185 | [6 empty] | 0 | 0 | 0 | 0
186 | [6 empty] | 0 | 0 | 0 | 0
187 | [6 empty] | 0 | 0 | 0 | 0
188 | [6 empty] | 0 | 0 | 0 | 0
189 | [6 empty] | 0 | 0 | 0 | 0
190 | [6 empty] | 0 | 0 | 0 | 0
191 | [6 empty] | 0 | 0 | 0 | 0
192 | [6 empty] | 0 | 0 | 0 | 0
193 | [6 empty] | 0 | 0 | 0 | 0
194 | [6 empty] | 0 | 0 | 0 | 0
195 | [6 empty] | 0 | 0 | 0 | 0
196 | [6 empty] | 0 | 0 | 0 | 0
197 | [6 empty] | 0 | 0 | 0 | 0
198 | [6 empty] | 0 | 0 | 0 | 0
199 | [6 empty] | 0 | 0 | 0 | 0
200 | [6 empty] | 0 | 0 | 0 | 0
201 | [6 empty] | 0 | 0 | 0 | 0
202 | [6 empty] | 0 | 0 | 0 | 0
203 | [6 empty] | 0 | 0 | 0 | 0
204 | [6 empty] | 0 | 0 | 0 | 0
205 | [6 empty] | 0 | 0 | 0 | 0
206 | [6 empty] | 0 | 0 | 0 | 0
207 | [6 empty] | 0 | 0 | 0 | 0
208 | [6 empty] | 0 | 0 | 0 | 0
209 | [6 empty] | 0 | 0 | 0 | 0
210 | [6 empty] | 0 | 0 | 0 | 0
211 | [6 empty] | 0 | 0 | 0 | 0
212 | [6 empty] | 0 | 0 | 0 | 0
213 | [6 empty] | 0 | 0 | 0 | 0
214 | [6 empty] | 0 | 0 | 0 | 0
215 | [6 empty] | 0 | 0 | 0 | 0

## Project Costs Reimbursed
Project # | Title | Asset | SUB ASSET | Process Step | Project Estimated Cost | Current PW Version Gross Cost | 428 Allocation | 406 Allocation | A&E-PW 9510 | E&M-PW 10710 | A&E Costs Incurred | E&M Cost Incurred | Estimated Installation Cost Incurred | Total Incurred Cost | Reimbursed Expenses | Reimbursement in process
334770 | FAASt [Guajataca Dam – Permanent Repairs] (Dams/Hydro) & Dredging | Priority Dams/Hydro | Dam | Pending Scope & Cost Completion by Applicant | 1086970000 | 566085576 | 566085576 | 520884424 |  |  | 54000000 | 0 |  | 54000000 | 4656192.94 |  | $54,000,000 were received via Working capital Advance and paid to USACE in advance, as requested under their contract terms and condittions. $4,656,192 have been reconciled by COR3 with actual expenses support
436621 | FAASt [Dams Minor Repairs] (Dams/Hydro) | Dams/Hydro | Dam | Pending EHP Review | 24607290.48 | 15309227 | 15309227 | 9298063.48 | [5 empty] | 0
344771 | FAASt [Guajataca Dam Dredging | Priority Dams/Hydro | Dam | Pending Scope & Cost Completion by Applicant | 40334479 | 40334479 | 40334479 |  |  |  | 500212.83 |  |  | 500212.83 | 366994.54 | 131997.6
178722 | FAASt [Caonillas Reservoir - Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 81557757 | 81557757 | 81557757 |  |  |  | 505196.62 |  |  | 792010.65 | 505196.62 | 270698.4
334811 | FAASt [Dos Bocas Reservoir Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 79831592 | 79831592 | 79831592 |  |  |  | 516252.01 |  |  | 809508.44 | 516252.01 | 279085.8
334769 | FAASt [Garzas Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 11154286 | 11154286 | 11154286 |  |  |  | 422565.17 |  |  | 422565.17 | 326488.35 | 81582.2
334772 | FAASt [Guayabal Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 20606934 | 20606934 | 20606934 |  |  |  | 340514.03 |  |  | 340514.03 | 326425.55
334813 | FAASt [Guayo Reservoir Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 17260000 | 17260000 | 17260000 |  |  |  | 611466.73 |  |  | 611466.73 | 369509.36 | 227868.9
334798 | FAASt [Guerrero Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 3918132 | 3918132 | 3918132 |  |  |  | 359697.37 |  |  | 359697.37 | 327109.74 | 18417
334803 | FAASt [Loco Reservoir Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 8080000 | 2730000 | 2730000 |  |  |  | 639344.75 |  |  | 639344.75 | 382950.81 | 227437.74
334773 | FAASt [Lucchetti Reservoir – Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 40020000 | 35810000 | 35810000 |  |  |  | 802328.98 |  |  | 802328.98 | 428148.95 | 372980.36
335207 | FAASt Guineo Reservoir – Dredging (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 4271000 | 4271000 | 4271000 |  |  |  | 322603.88 |  |  | 322603.88 | 321364.9
335206 | FAASt [Matrullas Reservoir–Dredging] (Dams/Hydro) | Dams/Hydro | Dredging | Pending Scope & Cost Completion by Applicant | 8055082 | 8055082 | 8055082 |  |  |  | 326423.98 |  |  | 326423.98 | 325224.3
180723 | FAASt [Rio Blanco Hydroelectric System] (Dams/Hydro) | Dams/Hydro | Hydro | Pending Scope & Cost Completion by Applicant | 49005575.55 | 22911551 | 22911551 | 26094024.55 |  |  | 358512.53 |  |  | 358512.53 | 357833.33
436468 | FAASt [Toro Negro Hydroelectric System Connection](Dams/Hydro) | Dams/Hydro | Hydro | Pending Scope & Cost Completion by Applicant | 57244061.71 | 43483764.17 | 43483764.17 | 13760297.54 |  |  | 553416.46 |  |  | 553416.46 | 382385.49
436462 | FAASt [Lajas Irrigation Canals] (Dams/Hydro) | Dams/Hydro | Canals | Pending Scope & Cost Completion by Applicant | 42573271.52 | 37270276.12 | 37270276.12 | 5302995.4 |  |  | 518412.41 |  |  | 518412.41 | 188294.1 | 330118.31
436467 | FAASt [Isabela Irrigation District - Canals] (Dams/Hydro) | Dams/Hydro | Canals | Pending Scope & Cost Completion by Applicant | 15000000 | 15000000 | 15000000 |  |  |  | 226636.88 |  |  | 226636.88 | 191767.6 | 16938.5
435769 | FAASt [South Coast Irrigation District - Canals] (Dams/Hydro) | Dams/Hydro | Canals | Pending Scope & Cost Completion by Applicant | 144851431.5 | 117758206.89 | 117758206.89 | 27093224.61 |  |  | 1442355.81 |  |  | 1442355.81 | 568973.6 | 870558.2
728260 | FAASt [Caonillas HydroElectric Power Plant No. 1] (Dams/Hydro) | Dams/Hydro | Hydro | Pending Scope & Cost Completion by Applicant | 3611152 | 3611152 | 3611152 |  |  |  | 329066.4 |  |  | 329066.4 | 280825.9 | 48240.5
721184 | FAASt Guayabal Dam Repairs and Mitigation (Dams/Hydro) | Dams/Hydro | Dam | Pending Scope & Cost Completion by Applicant | 326154895.79 | 163240107.05 | 163240107.05 | 162914788.74 | [5 empty] | 0

## Revisions 7-7 (hidden)
723883 | Project Duplicated on previous list- To be removed
727572 | Project Duplicated on previous list- To be removed
790443 | Project to be Included- Already approved pending Obligation (Applicant Signed Project) To be included in the list because the amount has not yet been debited from the FAASt funds.
165209 | Project to be Included-Project Previously Obligated but PW version is in progress.Project Missing on previous list submitted
757700 | Project to be included- Project in Pipeline Pending Recipient Final Review
800286 | Project to be Included-Project in Pipeline Pending Recipient Final Review (Pending COR3 Approval)
Project # | Title | Asset | SUB ASSET | Process Step | Project costs - Submitted to FEMA * | Current PW Version 428 Gross Cost * | 428 Allocation * | 406 Allocation * | A&E-PW 9510 * | E&M-PW 10710 * | A&E Costs Incurred-Luma Provided * | E&M Cost - Luma Provided * | Project Status | Project Scope | Additional comments
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Vegetation | Pending Applicant Project Review (Pending LUMA Approval- Last step) | 25072092.11 | 6584889.61 | 6584889.61 | 18404524.67 | 82677.83 | 0 |  |  | Project Version 1 obligation in process- | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 1 (San Juan). | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Vegetation | Pending Applicant Project Review- On Hold Pending Expert R. | 48974857.77 | 12945985.39 | 12945985.39 | 36028872.38 | 0 | 0 | 5950 | 0 | 6/17/2025 - The project is under review by Expert review since 4/14/2025. | Vegetation Clearing for Region Bayamon High Density | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Poles | Applicant Signed Project( Project Approved- Pending Obligation) | 248306 | 186697 | 186697 | 0 | 25985 | 35624 | 14074 | 35624 | Pending Recipient Final Review since 5/22/2025. | Planned to replace poles in San Juan region | Project included in list since its already in Pipeline, soon to be Obligated.
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Vieques and Culebra Projects (6) | Substation | Pending Scope & Cost Completion by Applicant | 16241388 | 12765828 | 14048046 | 177391 | 2015951 | 0 |  |  |  | Repair and replacement of the control house HVAC, building waterproofing, protection & control features, auxiliary equipment, conduits, control cables, batteries, lights, grounding, finish grades, perimeter fence, and other components to restore functionality.
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | 428 Distribution Automation | Automation | Pending Recipient Final Review (Pending COR3 Approval) | 1988436.16 | 1318515.66 | 1318515.66 | 0 | 245359.86 | 424560.64 | 11070 | 424560.64 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | 428 Distribution Automation | Automation | Pending Recipient Final Review (Pending COR3 Approval) | 2601467.86 | 1703712.83 | 1703712.83 | 0 | 300364.95 | 597390.08 | 0 | 597390 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects