## FAASt - Obligations Summary
FAASt-Consolidated Plan Summary
| Summary | 10510983791.54
|  | Reductions (Obligations) | Selected Projects under Formulation * | Estimated FAASt Total | -47156720
A | A&E - Mat | -4209258262.63 |  | -4209258262.63 |  | 0
B | PREPA | -301938311.47 | -1290199550.23 | -1592137861.7 | 39119195.21
C | LUMA | -1714393436.3922 | -1126719249.1 | -2841112685.4922 | 2775542505.67
D | Genera | -383105962.34 | -594713756.84 | -977819719.18 | 1347439841.75
| Total Reductions | -6608695972.8322 | -3011632556.17 | -9620328529.0022 |  | 9874174858.6522
| Remaining Balance 6099 | 3902287818.7078 | 890655262.5378 | 890655262.5378 | Remaining Estimated Balance | 636808932.8878
|  |  | * See each respective tab for project details |  |  | 10510983791.54
| Shared PWs-Obligated |  | 428 | 406 | Total Shared
9510 | PA-02-PR-4339-PW-09510 | FAASt A&E (PREPA/LUMA/Genera) | 1133563562.43 | 0 | 1133563562.43
10710 | PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 656101430 | 0 | 656101430
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 141081695.2 | 0 | 141081695.2
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 709006610 | 0 | 709006610
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 33478328 | 0 | 33478328
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 1536026637 | 0 | 1536026637
|  |  | 4209258262.63 | 0 | 4209258262.63
A
Child PWs
PW | PREPA -Obligated | Project Name | 428 | 406 | Total Child
9312 | PA-02-PR-4339-PW-09312 | FAASt Mobile Generation Units Purchases | 59740469.92 | 0 | 59740469.92 | Generation
10080 | PA-02-PR-4339-PW-10080 | FAASt Palo Seco Demin Water Tank 4 | 2890937.33 | 0 | 2890937.33 | Generation
10455 | PA-02-PR-4339-PW-10455 | FAASt Mayaguez Hydro-Gas Power Plant | 22238212.58 | 0 | 22238212.58 | Generation
10568 | PA-02-PR-4339-PW-10568 | FAASt Aguirre Power Plant 002 Units 1 &2 | 20905908.95 | 0 | 20905908.95 | Generation
10571 | PA-02-PR-4339-PW-10571 | FAASt Aguirre Power Plant 001 Infrastructure | 3031265.05 | 0 | 3031265.05 | Generation
10606 | PA-02-PR-4339-PW-10606 | FAASt Palo Seco Power Plant 001 Units 3 & 4 | 28774422.64 | 0 | 28774422.64 | Generation
10607 | PA-02-PR-4339-PW-10607 | FAASt Cambalache Power Plant | 2007587.81 | 0 | 2007587.81 | Generation
10608 | PA-02-PR-4339-PW-10608 | FAASt San Juan Power Plant - Auxiliary Infras | 3192936 | 0 | 3192936 | Generation
10609 | PA-02-PR-4339-PW-10609 | FAASt Palo Seco 002- Auxiliary Infrastructure | 3482468 | 0 | 3482468 | Generation
10615 | PA-02-PR-4339-PW-10615 | FAASt San Juan 001  Units 5 &amp;amp; | 73453828.76 | 0 | 73453828.76 | Generation
10622 | PA-02-PR-4339-PW-10622 | FAASt Aguirre Power Plant 003 Combined Cycle | 6384965.36 | 0 | 6384965.36 | Generation
10694 | PA-02-PR-4339-PW-10694 | FAASt Costa Sur 002 -Infrastructure projects ( | 1021800 | 0 | 1021800 | Generation
10702 | PA-02-PR-4339-PW-10702 | FAASt Costa Sur Power Plant Permanent | 42429619.54 | 0 | 42429619.54 | Generation
11085 | PA-02-PR-4339-PW-11085 | FAASt San Juan Power Plant 002 Units 7 & 8 | 19558770 | 0 | 19558770 | Generation
11510 | PA-02-PR-4339-PW-11510 | FAASt - IT/0T System Upgrade for all Power Plants | 11423825 | 0 | 11423825 | Generation
11860 | PA-02-PR-4339-PW-11860 | FAASt – BONUS Nuclear Power Plant Repairs (Dams/Hydro) | 1401294.53 | 178320.9 | 1579615.43 | (Dams/Hydro)
| TOTAL PREPA |  | 301938311.47 | 178320.9 | 302116632.37 | 0
B
PW | LUMA - Obligated | Project Name | 428 | 406 | Total Child | Asset
10496 | PA-02-PR-4339-PW-10496 | FAASt - Catano-Rebuild 1801(Substation) | 16359899.17 | 6895149.77 | 23255048.94 | Substation
10499 | PA-02-PR-4339-PW-10499 | FAASt Maunabo Streetlighting (Distribution) | 6199877.07 | 243880.33 | 6443757.4 | Distribution
10515 | PA-02-PR-4339-PW-10515 | FAASt -Luquillo Distribution Streetlighting | 8628667.29 | 181658.08 | 8810325.37 | Distribution
10521 | PA-02-PR-4339-PW-10521 | FAASt Lajas Streetlighting (Distribution) | 10278336.09 | 426332.48 | 10704668.57 | Distribution
10538 | PA-02-PR-4339-PW-10538 | FAASt Streetlighting - Guánica (Distribution | 9687238 | 370808 | 10058046 | Distribution
10539 | PA-02-PR-4339-PW-10539 | FAASt Aguada Streetlighting (Distribution) | 17764494.34 | 807222.04 | 18571716.38 | Distribution
10624 | PA-02-PR-4339-PW-10624 | FAASt-Substation 2501 Vieques (Substation) | 1209111 | 178309 | 1387420 | Substation
10626 | PA-02-PR-4339-PW-10626 | FAASt-Substation 3801 Culebra (Substation) | 1282218 | 177391 | 1459609 | Substation
10629 | PA-02-PR-4339-PW-10629 | FAASt Distribution Feeders - Ponce Short Term | 316119 | 64134 | 380253 | Distribution
10630 | PA-02-PR-4339-PW-10630 | FAASt Distribution Feeders - Ponce Short Term | 323692 | 69130 | 392822 | Distribution
10632 | PA-02-PR-4339-PW-10632 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 1593443 | 0 | 1593443 | Substation
10635 | PA-02-PR-4339-PW-10635 | FAASt Distribution Feeders - Caguas Short Ter | 142917 | 10826 | 153743 | Distribution
10679 | PA-02-PR-4339-PW-10679 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | 1217429 | 0 | 1217429 | Transmission
10690 | PA-02-PR-4339-PW-10690 | FAASt Distribution Feeders - Arecibo Short Te | 610448 | 157420 | 767868 | Distribution
10701 | PA-02-PR-4339-PW-10701 | FAASt Distribution Feeders - Caguas Short Term | 108847 | 14874 | 123721 | Distribution
10742 | PA-02-PR-4339-PW-10742 | FAASt Distribution Pole and Conductor Repair- | 20468 | 5830 | 26298 | Distribution
10751 | PA-02-PR-4339-PW-10751 | FAASt Distribution Pole and Conductor Repair- | 43725 | 5620 | 49345 | Distribution
10764 | PA-02-PR-4339-PW-10764 | FAASt Distribution Pole and Conductor Repair | 284349 | 73265 | 357614 | Distribution
10773 | PA-02-PR-4339-PW-10773 | FAASt Distribution Pole and Conductor Repair | 1408531 | 358420 | 1766951 | Distribution
10777 | PA-02-PR-4339-PW-10777 | FAASt Distribution Pole and Conductor Repair - | 1425163 | 368954 | 1794117 | Distribution
10788 | PA-02-PR-4339-PW-10788 | FAASt - Costa Sur SP TC  Equipment Repair and | 23251835 | 0 | 23251835 | Substation
10800 | PA-02-PR-4339-PW-10800 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | 453597 | 0 | 453597 | Transmission
10812 | PA-02-PR-4339-PW-10812 | FAASt Distribution Pole and Conductor Repair- | 190570 | 49943 | 240513 | Distribution
10821 | PA-02-PR-4339-PW-10821 | FAASt Distribution Pole and Conductor Repair | 621804 | 171614 | 793418 | Distribution
10824 | PA-02-PR-4339-PW-10824 | FAASt Distribution Pole and Conductor Repair | 84433 | 23322 | 107755 | Distribution
10827 | PA-02-PR-4339-PW-10827 | FAASt Distribution Pole and Conductor Repair | 1747929 | 362533 | 2110462 | Distribution
10837 | PA-02-PR-4339-PW-10837 | FAASt Line 6700 Martin Peña TC to Villamar Se | 690703 | 0 | 690703 | Transmission
10841 | PA-02-PR-4339-PW-10841 | FAASt Physical Security - Group 1 (Substatio | 6025270.22 | 665958.96 | 6691229.18 | Substation
10857 | PA-02-PR-4339-PW-10857 | FAASt Streetlighting - Villalba (Distributio | 10190536.05 | 681865.66 | 10872401.71 | Distribution
10858 | PA-02-PR-4339-PW-10858 | FAASt - Substation Minor Repairs Group A (Subs | 4482972.51 | 488202.58 | 4971175.09 | Substation
10864 | PA-02-PR-4339-PW-10864 | FAASt Distribution Pole and Conductor Repair | 1072850.98 | 319213.9 | 1392064.88 | Distribution
10876 | PA-02-PR-4339-PW-10876 | FAASt Distribution Streetlighting - Aibonito | 7074498 | 178787 | 7253285 | Distribution
10884 | PA-02-PR-4339-PW-10884 | FAASt Distribution Streetlighting - Cataño ( | 16996758 | 565289 | 17562047 | Distribution
10891 | PA-02-PR-4339-PW-10891 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | 420866 | 0 | 420866 | Transmission
10893 | PA-02-PR-4339-PW-10893 | FAASt Distribution Pole and Conductor Repair | 441308 | 90422 | 531730 | Distribution
10906 | PA-02-PR-4339-PW-10906 | FAASt Distribution Pole and Conductor Repair | 872891 | 238203 | 1111094 | Distribution
10909 | PA-02-PR-4339-PW-10909 | FAASt Distribution Pole and Conductor Repair | 1894033.53 | 472527 | 2366560.53 | Distribution
10919 | PA-02-PR-4339-PW-10919 | FAASt Distribution Pole and Conductor Repair | 3286536 | 835984 | 4122520 | Distribution
10922 | PA-02-PR-4339-PW-10922 | FAASt Distribution Pole and Conductor Repair- | 904194 | 227661 | 1131855 | Distribution
10933 | PA-02-PR-4339-PW-10933 | FAASt Distribution Pole and Conductor Repair | 1412368 | 289653 | 1702021 | Distribution
10935 | PA-02-PR-4339-PW-10935 | FAASt Distribution Pole and Conductor Repair | 1773428 | 318852 | 2092280 | Distribution
10957 | PA-02-PR-4339-PW-10957 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Teleco | 48941484 | 0 | 48941484 | Telecommunications
10962 | PA-02-PR-4339-PW-10962 | FAASt Distribution Pole and Conductor Repair | 3575454.81 | 857193.1 | 4432647.91 | Distribution
10978 | PA-02-PR-4339-PW-10978 | FAASt San Juan 115kV Underground Transmission | 14746039.57 | 0 | 14746039.57 | Transmission
11041 | PA-02-PR-4339-PW-11041 | FAASt Distribution Pole and Conductor Repair- | 4686914.68 | 1064121.8 | 5751036.48 | Distribution
11045 | PA-02-PR-4339-PW-11045 | FAASt Rio Grande Estate Substation CH-2306 (Su | 7098243.76 | 4585370.95 | 11683614.71 | Substation
11089 | PA-02-PR-4339-PW-11089 | FAASt Distribution Pole and Conductor Repair - | 129744 | 27443 | 157187 | Distribution
11090 | PA-02-PR-4339-PW-11090 | FAASt Distribution Pole and Conductor Repair | 20729 | 633 | 21362 | Distribution
11095 | PA-02-PR-4339-PW-11095 | FAASt Hatillo Streetlight (Distribution) | 18570095.25 | 1764387.7 | 20334482.95 | Distribution
11096 | PA-02-PR-4339-PW-11096 | FAASt Distribution Pole and Conductor Repair | 171152.23 | 46010.58 | 217162.81 | Distribution
11097 | PA-02-PR-4339-PW-11097 | FAASt Manati Streetlight (Distribution) | 27067865 | 1568964 | 28636829 | Distribution
11098 | PA-02-PR-4339-PW-11098 | FAASt Distribution Pole and Conductor Repair | 729040 | 179902 | 908942 | Distribution
11099 | PA-02-PR-4339-PW-11099 | FAASt Distribution Streetlighting - Dorado | 22864972 | 1505645 | 24370617 | Distribution
11100 | PA-02-PR-4339-PW-11100 | FAASt Aguirre TC - BKRS (Substations) | 39034592 | 0 | 39034592 | Substation
11101 | PA-02-PR-4339-PW-11101 | FAASt Distribution Pole and Conductor Repair | 243073 | 55558 | 298631 | Distribution
11103 | PA-02-PR-4339-PW-11103 | FAASt Distribution Pole and Conductor Repair- | 353628 | 54317.84 | 407945.84 | Distribution
11105 | PA-02-PR-4339-PW-11105 | FAASt Distribution Pole and Conductor Repair | 589335 | 157153 | 746488 | Distribution
11106 | PA-02-PR-4339-PW-11106 | FAASt Distribution Pole and Conductor Repair | 163846.51 | 51337.5 | 215184.01 | Distribution
11107 | PA-02-PR-4339-PW-11107 | FAASt Distribution Pole and | 483786 | 106510 | 590296 | Distribution
11109 | PA-02-PR-4339-PW-11109 | FAASt Distribution Pole and Conductor Repair | 452956.93 | 110600.22 | 563557.15 | Distribution
11113 | PA-02-PR-4339-PW-11113 | FAASt Distribution Pole and Conductor Repair- | 911136.76 | 206650.4 | 1117787.16 | Distribution
11114 | PA-02-PR-4339-PW-11114 | FAASt Distribution Pole and Conductor Repair | 498436 | 95482 | 593918 | Distribution
11116 | PA-02-PR-4339-PW-11116 | FAASt Distribution Pole and Conductor Repair | 250906 | 68700 | 319606 | Distribution
11123 | PA-02-PR-4339-PW-11123 | FAASt Distribution Pole and Conductor Repair | 70683 | 21148 | 91831 | Distribution
11130 | PA-02-PR-4339-PW-11130 | FAASt Distribution Pole and Conductor Repair | 545661.24 | 113378.16 | 659039.4 | Distribution
11136 | PA-02-PR-4339-PW-11136 | FAASt Distribution Pole and Conductor Repair | 510067.96 | 102310.67 | 612378.63 | Distribution
11137 | PA-02-PR-4339-PW-11137 | FAASt Distribution Pole and Conductor Repair | 85921.77 | 17491 | 103412.77 | Distribution
11138 | PA-02-PR-4339-PW-11138 | FAASt Distribution Pole and Conductor Repair P | 254972.22 | 63260 | 318232.22 | Distribution
11143 | PA-02-PR-4339-PW-11143 | FAASt Distribution Pole and Conductor Repair - | 537688 | 134695 | 672383 | Distribution
11145 | PA-02-PR-4339-PW-11145 | FAASt Distribution Pole and Conductor Repair | 573047.24 | 136182.31 | 709229.55 | Distribution
11149 | PA-02-PR-4339-PW-11149 | FAASt Distribution Pole and Conductor Repair | 577000.79 | 116779.74 | 693780.53 | Distribution
11150 | PA-02-PR-4339-PW-11150 | FAASt Distribution Pole and Conductor Repair | 68823 | 14986 | 83809 | Distribution
11152 | PA-02-PR-4339-PW-11152 | FAASt Distribution Pole and Conductor Repair | 20584 | 4995 | 25579 | Distribution
11165 | PA-02-PR-4339-PW-11165 | FAASt Distribution Pole and Conductor Repair | 65944 | 11661 | 77605 | Distribution
11166 | PA-02-PR-4339-PW-11166 | FAASt Distribution Pole and Conductor Repair | 431381.68 | 105743.62 | 537125.3 | Distribution
11168 | PA-02-PR-4339-PW-11168 | FAASt Distribution Pole and Conductor Repair | 43374 | 11028 | 54402 | Distribution
11169 | PA-02-PR-4339-PW-11169 | FAASt Distribution Pole and Conductor Repair - | 198050.74 | 41796.87 | 239847.61 | Distribution
11171 | PA-02-PR-4339-PW-11171 | FAASt Distribution Pole and Conductor Repair - | 355178 | 58304 | 413482 | Distribution
11181 | PA-02-PR-4339-PW-11181 | FAASt Distribution Pole and Conductor Repair | 516951 | 108247 | 625198 | Distribution
11182 | PA-02-PR-4339-PW-11182 | FAASt Distribution Pole and Conductor Repair | 208400 | 57671.35 | 266071.35 | Distribution
11183 | PA-02-PR-4339-PW-11183 | FAASt Distribution Pole and Conductor Repair | 635326.93 | 108700.19 | 744027.12 | Distribution
11184 | PA-02-PR-4339-PW-11184 | FAASt Transmission Priority Pole Replacements | 214124 | 2243 | 216367 | Distribution
11193 | PA-02-PR-4339-PW-11193 | FAASt Distribution Pole and Conductor Repair | 303774 | 72188.49 | 375962.49 | Distribution
11196 | PA-02-PR-4339-PW-11196 | FAASt Distribution Pole and Conductor Repair - | 775779 | 176882.42 | 952661.42 | Distribution
11201 | PA-02-PR-4339-PW-11201 | FAASt Distribution Pole and Conductor Repair | 208544.25 | 53746.06 | 262290.31 | Distribution
11203 | PA-02-PR-4339-PW-11203 | FAASt Distribution Pole and Conductor Repair- | 469650.95 | 95954.05 | 565605 | Distribution
11207 | PA-02-PR-4339-PW-11207 | FAASt Distribution Pole and Conductor Repair | 443331 | 98484 | 541815 | Distribution
11212 | PA-02-PR-4339-PW-11212 | FAASt Distribution Pole and Conductor Repair | 517156 | 105667 | 622823 | Distribution
11214 | PA-02-PR-4339-PW-11214 | FAASt Distribution Pole and Conductor Repair | 21408.25 | 5830.39 | 27238.64 | Distribution
11217 | PA-02-PR-4339-PW-11217 | FAASt Distribution Pole and Conductor Repair - | 164908.86 | 14986 | 179894.86 | Distribution
11229 | PA-02-PR-4339-PW-11229 | FAASt Distribution Pole and Conductor Repair - | 523404 | 108652 | 632056 | Distribution
11231 | PA-02-PR-4339-PW-11231 | FAASt Distribution Pole and Conductor Repair | 211622.76 | 33717.31 | 245340.07 | Distribution
11256 | PA-02-PR-4339-PW-11256 | FAASt Distribution Pole and Conductor Repair | 59545.08 | 17491.16 | 77036.24 | Distribution
11257 | PA-02-PR-4339-PW-11257 | FAASt Distribution Pole and Conductor Repair | 186321 | 51841 | 238162 | Distribution
11263 | PA-02-PR-4339-PW-11263 | FAASt Distribution Pole and Conductor Repair | 19848.36 | 5830.39 | 25678.75 | Distribution
11264 | PA-02-PR-4339-PW-11264 | FAASt Distribution Pole and Conductor Repair | 448719.06 | 114710.2 | 563429.26 | Distribution
11267 | PA-02-PR-4339-PW-11267 | FAASt Distribution Pole and Conductor Repair | 64425.44 | 16226.16 | 80651.6 | Distribution
11268 | PA-02-PR-4339-PW-11268 | FAASt Distribution Pole and Conductor Repair | 150345 | 37878 | 188223 | Distribution
11269 | PA-02-PR-4339-PW-11269 | FAASt Distribution Pole and Conductor Repair | 487190 | 129039 | 616229 | Distribution
11273 | PA-02-PR-4339-PW-11273 | FAASt Distribution Pole and Conductor | 42728.41 | 9990.97 | 52719.38 | Distribution
11275 | PA-02-PR-4339-PW-11275 | FAASt Distribution Pole and Conductor Repair | 547010 | 102417 | 649427 | Distribution
11276 | PA-02-PR-4339-PW-11276 | FAASt Distribution Pole and Conductor Repair - | 60838.48 | 16023.76 | 76862.24 | Distribution
11277 | PA-02-PR-4339-PW-11277 | FAASt Distribution Pole and Conductor Repair | 106941.99 | 27886.93 | 134828.92 | Distribution
11279 | PA-02-PR-4339-PW-11279 | FAASt Distribution Pole and Conductor Repair | 710014.69 | 191275.59 | 901290.28 | Distribution
11311 | PA-02-PR-4339-PW-11311 | FAASt Distribution Pole and Conductor Repair - | 338491 | 96676 | 435167 | Distribution
11312 | PA-02-PR-4339-PW-11312 | FAASt [Distribution Pole and Conductor Repair | 273996 | 29974 | 303970 | Distribution
11314 | PA-02-PR-4339-PW-11314 | FAASt Distribution Pole and Conductor Repair - | 486385 | 92244 | 578629 | Distribution
11317 | PA-02-PR-4339-PW-11317 | FAASt [Distribution Streetlighting - Gurabo] | 19208994 | 1533300 | 20742294 | Distribution
11318 | PA-02-PR-4339-PW-11318 | FAASt [San Germán Streetlighting] (Distributio | 30849348 | 4033578 | 34882926 | Distribution
11319 | PA-02-PR-4339-PW-11319 | FAASt Aguadilla Streetlight (Distribution) | 19796809 | 1295775 | 21092584 | Distribution
11326 | PA-02-PR-4339-PW-11326 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | 25277347 | 1009578 | 26286925 | Distribution
11340 | PA-02-PR-4339-PW-11340 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 320740 | 88558 | 409298 | Distribution
11344 | PA-02-PR-4339-PW-11344 | FAASt Streetlight Florida Distribution | 9311841.53 | 997190 | 10309031.53 | Distribution
11347 | PA-02-PR-4339-PW-11347 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | 2796182 | 3575881 | 6372063 | Substation
11350 | PA-02-PR-4339-PW-11350 | FAASt Physical Security - Group 2 (Substation) | 2159012.31 | 224680.68 | 2383692.99 | Substation
11351 | PA-02-PR-4339-PW-11351 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | 73737224.58 | 1849344.06 | 75586568.64 | Distribution
11352 | PA-02-PR-4339-PW-11352 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 438209.69 | 86181.92 | 524391.61 | Distribution
11365 | PA-02-PR-4339-PW-11365 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | 1464496 | 378483 | 1842979 | Distribution
11372 | PA-02-PR-4339-PW-11372 | FAASt [Physical Security - Group 3] (Substation) | 3696956.6 | 436383.23 | 4133339.83 | Substation
11385 | PA-02-PR-4339-PW-11385 | FAASt Substation Minor Repairs -Group B (Substation) | 2973035 | 439541 | 3412576 | Substation
11402 | PA-02-PR-4339-PW-11402 | FAASt [Costa Sur TC - Phase II &amp;amp; III ] (Substation) | 61444255.52 | 0 | 61444255.52 | Substation
11449 | PA-02-PR-4339-PW-11449 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | 642721 | 125133 | 767854 | Distribution
11465 | PA-02-PR-4339-PW-11465 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 1201420 | 224731 | 1426151 | Distribution
11478 | PA-02-PR-4339-PW-11478 | FAASt- Substation Minor Repairs Group C (Substation) | 2648259.06 | 384632.14 | 3032891.2 | Substation
11479 | PA-02-PR-4339-PW-11479 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | 8180049.03 | 7159883.3 | 15339932.33 | Substation
11489 | PA-02-PR-4339-PW-11489 | FAASt Centro Medico 1327/1359 Equipment Repair &amp;amp; Replacement (Substation) | 14795324 | 6537037 | 21332361 | Substation
11508 | PA-02-PR-4339-PW-11508 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 16, 17, 18 &amp;amp; 19] (Distribution) | 1764568.92 | 389437.84 | 2154006.76 | Distribution
11518 | PA-02-PR-4339-PW-11518 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | 9762754.59 | 853056.42 | 10615811.01 | Distribution
11522 | PA-02-PR-4339-PW-11522 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | 14918381.07 | 1965608.26 | 16883989.33 | Distribution
11524 | PA-02-PR-4339-PW-11524 | FAASt Coamo Streetlight (Distribution) | 14311922.45 | 2060901.35 | 16372823.8 | Distribution
11526 | PA-02-PR-4339-PW-11526 | FAASt Streetlight - Las Marías (Distribution) | 7073217 | 1287705 | 8360922 | Distribution
11532 | PA-02-PR-4339-PW-11532 | FAASt [Streetlighting - Mayagüez] (Distribution) | 11019180.1 | 1352204.36 | 12371384.46 | Distribution
11533 | PA-02-PR-4339-PW-11533 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | 14865613.02 | 1158946.56 | 16024559.58 | Distribution
11534 | PA-02-PR-4339-PW-11534 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 85296.74 | 2478.06 | 87774.8 | Distribution
11537 | PA-02-PR-4339-PW-11537 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 5962412.52 | 1701923.62 | 7664336.14 | Telecommunications
11540 | PA-02-PR-4339-PW-11540 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | 20710527 | 1176376 | 21886903 | Distribution
11555 | PA-02-PR-4339-PW-11555 | FAASt - EPC - [San Juan SP TC] (Substation) | 61558468.95 | 0 | 61558468.95 | Substation
11556 | PA-02-PR-4339-PW-11556 | FAASt - EPC - [Sabana Llana TC] (Substation) | 46643078.39 | 0 | 46643078.39 | Substation
11557 | PA-02-PR-4339-PW-11557 | FAASt - EPC - [Monacillo TC] (Substations) | 88096455.74 | 0 | 88096455.74 | Substation
11560 | PA-02-PR-4339-PW-11560 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | 13720208.31 | 2225873.62 | 15946081.93 | Distribution
11566 | PA-02-PR-4339-PW-11566 | FAASt [Physical Security - Group 4] (Substation) | 3478518 | 338280 | 3816798 | Substation
11573 | PA-02-PR-4339-PW-11573 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 6929384 | 0 | 6929384 | Substation
11583 | PA-02-PR-4339-PW-11583 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 332062581 | 544207595 | 876270176 | Telecommunications
11627 | PA-02-PR-4339-PW-11627 | FAASt [Morovis Streetlighting] (Distribution) | 13486398.85 | 1744482.27 | 15230881.12 | Distribution
11629 | PA-02-PR-4339-PW-11629 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | 8070964.96 | 1339801.28 | 9410766.24 | Distribution
11633 | PA-02-PR-4339-PW-11633 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | 13807923.4 | 1807601.11 | 15615524.51 | Distribution
11636 | PA-02-PR-4339-PW-11636 | FAASt [Toa Baja Streetlighting] (Distribution) | 9529190.37 | 620134.69 | 10149325.06 | Distribution
11639 | PA-02-PR-4339-PW-11639 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 7096249.5 | 195136.32 | 7291385.82 | Distribution
11640 | PA-02-PR-4339-PW-11640 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 5425810.57 | 165903.3 | 5591713.87 | Distribution
11650 | PA-02-PR-4339-PW-11650 | FAASt [Ceiba Streetlighting] (Distribution) | 5152111.14 | 716918.6 | 5869029.74 | Distribution
11652 | PA-02-PR-4339-PW-11652 | FAASt - EPC -Aguirre TC-Phase II (Substation) | 82726096.38 | 0 | 82726096.38 | Substation
11658 | PA-02-PR-4339-PW-11658 | FAASt [Naguabo Streetlighting] (Distribution) | 11620676.42 | 1669736.97 | 13290413.39 | Distribution
11664 | PA-02-PR-4339-PW-11664 | FAASt [Naranjito Streetlighting] (Distribution) | 11644048.43 | 2115538.38 | 13759586.81 | Distribution
11666 | PA-02-PR-4339-PW-11666 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 5629060 | 178712.97 | 5807772.97 | Distribution
11671 | PA-02-PR-4339-PW-11671 | FAASt [Arroyo Streetlighting] (Distribution) | 5314332 | 740394.01 | 6054726.01 | Distribution
11673 | PA-02-PR-4339-PW-11673 | FAASt [Vega Alta Streetlighting] (Distribution) | 12445015.33 | 1869089.52 | 14314104.85 | Distribution
11675 | PA-02-PR-4339-PW-11675 | FAASt [Barranquitas Streetlighting] (Distribution) | 9430329.22 | 1577046.09 | 11007375.31 | Distribution
11680 | PA-02-PR-4339-PW-11680 | FAASt [Culebra Streetlighting] (Distribution) | 1155804 | 153603 | 1309407 | Distribution
11682 | PA-02-PR-4339-PW-11682 | FAASt Substation Minor Repairs - Group D (Substation) | 2583133.54 | 288123.63 | 2871257.17 | Substation
11686 | PA-02-PR-4339-PW-11686 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 10313627 | 306131.37 | 10619758.37 | Distribution
11696 | PA-02-PR-4339-PW-11696 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 0 | 18151116.72 | 18151116.72 | Vegetation
11707 | PA-02-PR-4339-PW-11707 | FAASt [Substation Minor Repairs - Group E] (Substation) | 3924015.69 | 579767.52 | 4503783.21 | Substation
11711 | PA-02-PR-4339-PW-11711 | FAASt [Añasco Streetlighting] (Distribution) | 12087876.17 | 1820361.92 | 13908238.09 | Distribution
11712 | PA-02-PR-4339-PW-11712 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 4926640.11 | 147870.9 | 5074511.01 | Distribution
11714 | PA-02-PR-4339-PW-11714 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 4807675.47 | 13386633.34 | 18194308.81 | Vegetation
11715 | PA-02-PR-4339-PW-11715 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 6849050.26 | 19064883.85 | 25913934.11 | Vegetation
11716 | PA-02-PR-4339-PW-11716 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 1033375.81 | 84035.96 | 1117411.77 | Distribution
11718 | PA-02-PR-4339-PW-11718 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 3767690.42 | 10493001.48 | 14260691.9 | Vegetation
11719 | PA-02-PR-4339-PW-11719 | FAASt [T-Pole Program Line 100] (Transmission) | 94787.57 | 23372.71 | 118160.28 | Transmission
11723 | PA-02-PR-4339-PW-11723 | FAASt T-Pole Program Line 3700] (Transmission) | 303960.92 | 73393.66 | 377354.58 | Transmission
11724 | PA-02-PR-4339-PW-11724 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 7414164.75 | 20637925.62 | 28052090.37 | Vegetation
11725 | PA-02-PR-4339-PW-11725 | FAASt [Cidra Streetlighting] (Distribution) | 12812478.84 | 1838229.6 | 14650708.44 | Distribution
11726 | PA-02-PR-4339-PW-11726 | FAASt HV Equipment Replacement Group 2 (Substation) | 15413889.89 | 0 | 15413889.89 | Substation
11727 | PA-02-PR-4339-PW-11727 | FAASt [Comerio Streetlighting] (Distribution) | 6538769.44 | 862125.75 | 7400895.19 | Distribution
11734 | PA-02-PR-4339-PW-11734 | FAASt [Adjuntas Streetlighting] (Distribution) | 10742462 | 1891152 | 12633614 | Distribution
11735 | PA-02-PR-4339-PW-11735 | FAASt [Jayuya Streetlighting] (Distribution) | 7277670.2 | 1350541.32 | 8628211.52 | Distribution
11739 | PA-02-PR-4339-PW-11739 | FAASt [Salinas Streetlighting] (Distribution) | 12097203.53 | 1611020.9 | 13708224.43 | Distribution
11746 | PA-02-PR-4339-PW-11746 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 10940320.91 | 395663.43 | 11335984.34 | Distribution
11753 | PA-02-PR-4339-PW-11753 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 5461200.05 | 205587.38 | 5666787.43 | Distribution
11754 | PA-02-PR-4339-PW-11754 | FAASt [T-Pole Program Line 3000] (Transmission) | 559076.77 | 72117.49 | 631194.26 | Transmission
11764 | PA-02-PR-4339-PW-11764 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 17307539.01 | 0 | 17307539.01 | Substation
11839 | PA-02-PR-4339-PW-11839 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | 467287.6 | 0 | 467287.6 | Distribution
11850 | PA-02-PR-4339-PW-11850 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 11041271 | 409899.81 | 11451170.81 | Distribution
11667 | PA-02-PR-4339-PW-11667 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 6704421.6922 | 239376.93 | 6943798.6222 | Distribution
11812 | PA-02-PR-4339-PW-11812 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 13884126 | 377123.67 | 14261249.67 | Distribution
108001 | PA-02-PR-4339-PW-108001 | FAASt [Automation Program Group 20] (TL/Distribution) | 2623262.08 | 0 | 2623262.08 | Distribution
108000 | PA-02-PR-4339-PW-108000 | FAASt [Automation Program Group 19] (TL/Distribution) | 2753627.24 | 0 | 2753627.24 | Distribution
108022 | PA-02-PR-4339-PW-108022 | FAASt [Automation Program Group 15] (TL/Distribution) | 643560.85 | 0 | 643560.85 | Distribution
107956 | PA-02-PR-4339-PW-107956 | FAASt [Automation Program Group 14] (TL/Distribution) | 1640186.96 | 0 | 1640186.96 | Distribution
107957 | PA-02-PR-4339-PW-107957 | FAASt [Automation Program Group 12] (TL/Distribution) | 3664210.1 | 0 | 3664210.1 | Distribution
11721 | PA-02-PR-4339-PW-11721 | FAASt - [Taft - MC 1105] (Substations) | 9362729.93 | 4123842.4 | 13486572.33 | Substation
| TOTAL LUMA |  | 1714393436.3922 | 734259141.97 | 2448652578.3622 | 0
C
PW | Genera - Obligated | Project Name | 428 | 406 | Total Child | Asset |  | Obligated by PREPA- Transferred | Total Obligated by Genera
10568 | PA-02-PR-4339-PW-10568 | FAASt Aguirre Power Plant 002 Units 1 &2 | 1366048.03 | 0 | 1366048.03 | Generation |  | -1366048.03 | 0
10571 | PA-02-PR-4339-PW-10571 | FAASt Aguirre Power Plant 001 Infrastructure | 2020619.28 | 0 | 2020619.28 | Generation |  | -1649290.05 | 371329.23
10606 | PA-02-PR-4339-PW-10606 | FAASt Palo Seco Power Plant 001 Units 3 & 4 | 22266817.84 | 0 | 22266817.84 | Generation |  | -22266817.84 | 0
10607 | PA-02-PR-4339-PW-10607 | FAASt Cambalache Power Plant Permanent Repair | 0 | 0 | 0 | Generation |  | 0 | 0
10608 | PA-02-PR-4339-PW-10608 | FAASt San Juan Power Plant - Auxiliary Infras | 50450 | 0 | 50450 | Generation |  | -50450 | 0
10609 | PA-02-PR-4339-PW-10609 | FAASt Palo Seco 002- Auxiliary Infrastructure | 4012636.75 | 0 | 4012636.75 | Generation |  | -2309636.75 | 1703000
10615 | PA-02-PR-4339-PW-10615 | FAASt San Juan 001  Units 5 &amp;amp; 6 (Generation | 45439729.74 | 0 | 45439729.74 | Generation |  | -43799599.99 | 1640129.75
10622 | PA-02-PR-4339-PW-10622 | FAASt Aguirre Power Plant 003 Combined Cycle | 2565944.68 | 0 | 2565944.68 | Generation |  | -2565944.68 | 0
10694 | PA-02-PR-4339-PW-10694 | FAASt Costa Sur 002 -Infrastructure projects ( | 899000 | 0 | 899000 | Generation |  | -899000 | 0
10702 | PA-02-PR-4339-PW-10702 | FAASt Costa Sur Power Plant Permanent | 31242323.9 | 0 | 31242323.9 | Generation |  | -26323758.83 | 4918565.07
11085 | PA-02-PR-4339-PW-11085 | FAASt San Juan Power Plant 002 Units 7 & 8 | 18658766.12 | 0 | 18658766.12 | Generation |  | -18369674.42 | 289091.7
11510 | PA-02-PR-4339-PW-11510 | FAASt - IT/0T System Upgrade for all Power Plants | 0 | 0 | 0 | Generation |  | 0 | 0
11855 | PA-02-PR-4339-PW-11855 | FAASt Generation Fleet Project (Generation) | 235670650 | 0 | 235670650 | Generation |  | 0 | 235670650
108066 | PA-02-PR-4339-PW-108066 | FAASt [Auxiliary Equipment] (Generation) | 18912976 | 0 | 18912976 | Generation |  | 0 | 18912976
|  |  | 383105962.34 | 0 | 383105962.34 | 0 |  | -119600220.59 | 263505741.75
D
| GRAND TOTAL |  | 2399437710.2022 | 734437462.87 | 3133875173.0722
Selected Projects under Formulation *
PRJ | PREPA -Under Formulation | Project Name | 428 | 406 | Total Child | Asset
178722 | PA-02-PR-4339-PRJ-178722 | FAASt [Caonillas Reservoir - Dredging] (Dams/Hydro) | 81557757 |  | 81557757 | Water/Hydro
180723 | PA-02-PR-4339-PRJ-180723 | FAASt [Rio Blanco Hydroelectric System] (Dams/Hydro) | 22911551 | 26094024.55 | 49005575.55 | Water/Hydro
334769 | PA-02-PR-4339-PRJ-334769 | FAASt [Garzas Reservoir – Dredging] (Dams/Hydro) | 11154286 |  | 11154286 | Water/Hydro
334770 | PA-02-PR-4339-PRJ-334770 | FAASt [Guajataca Dam – Permanent Repairs] (Dams/Hydro) & Dredging | 566085576 | 520884424 | 1086970000 | Water/Hydro
334772 | PA-02-PR-4339-PRJ-334772 | FAASt [Guayabal Reservoir – Dredging] (Dams/Hydro) | 20606934 |  | 20606934 | Water/Hydro
334773 | PA-02-PR-4339-PRJ-334773 | FAASt [Lucchetti Reservoir – Dredging] (Dams/Hydro) | 35810000 |  | 35810000 | Water/Hydro
334798 | PA-02-PR-4339-PRJ-334798 | FAASt [Guerrero Reservoir – Dredging] (Dams/Hydro) | 3918132 |  | 3918132 | Water/Hydro
334803 | PA-02-PR-4339-PRJ-334803 | FAASt [Loco Reservoir Dredging] (Dams/Hydro) | 2730000 |  | 2730000 | Water/Hydro
334811 | PA-02-PR-4339-PRJ-334811 | FAASt [Dos Bocas Reservoir Dredging] (Dams/Hydro) | 79831592 |  | 79831592 | Water/Hydro
334813 | PA-02-PR-4339-PRJ-334813 | FAASt [Guayo Reservoir Dredging] (Dams/Hydro) | 17260000 |  | 17260000 | Water/Hydro
335206 | PA-02-PR-4339-PRJ-335206 | FAASt [Matrullas Reservoir–Dredging] (Dams/Hydro) | 8055082 |  | 8055082 | Water/Hydro
335207 | PA-02-PR-4339-PRJ-335207 | FAASt Guineo Reservoir – Dredging (Dams/Hydro) | 4271000 |  | 4271000 | Water/Hydro
344771 | PA-02-PR-4339-PRJ-344771 | FAASt [Guajataca Dam Dredging | 40334479 |  | 40334479 | Water/Hydro
435769 | PA-02-PR-4339-PRJ-435769 | FAASt [South Coast Irrigation District - Canals] (Dams/Hydro) | 117758206.89 | 27093224.61 | 144851431.5 | Water/Hydro
436462 | PA-02-PR-4339-PRJ-436462 | FAASt [Lajas Irrigation Canals] (Dams/Hydro) | 37270276.12 | 5302995.4 | 42573271.52 | Water/Hydro
436467 | PA-02-PR-4339-PRJ-436467 | FAASt [Isabela Irrigation District - Canals] (Dams/Hydro) | 15000000 |  | 15000000 | Water/Hydro
436468 | PA-02-PR-4339-PRJ-436468 | FAASt [Toro Negro Hydroelectric System Connection](Dams/Hydro) | 43483764.17 | 13760297.54 | 57244061.71 | Water/Hydro
436621 | PA-02-PR-4339-PRJ-436621 | FAASt [Dams Minor Repairs] (Dams/Hydro) | 15309227 | 9298063.48 | 24607290.48 | Water/Hydro
721184 | PA-02-PR-4339-PRJ-721184 | FAASt Guayabal Dam Repairs and Mitigation (Dams/Hydro) | 163240107.05 | 162914788.74 | 326154895.79 | Water/Hydro
728260 | PA-02-PR-4339-PRJ-728260 | FAASt [Caonillas HydroElectric Power Plant No. 1] (Dams/Hydro) | 3611152 |  | 3611152 | Water/Hydro
|  |  | 1290199550.23 | 765348224.32 | 2055546940.55 | 0
B-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal. Subject to change after FEMA validation
PRJ | LUMA - Under Formulation | Project Name | 428 | 406 | Total Child | Asset
165209 | PA-02-PR-4339-PRJ-165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | 12765829 | 0 | 12765829 | Vieques and Culebra Projects
165225 | PA-02-PR-4339-PW-10624 | FAASt-Substation 2501 Vieques (Substation) & New 2502 Substation | 13495526 | 0 | 13495526.25 | Vieques and Culebra Projects
165226 | PA-02-PR-4339-PRJ-165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | 59069587.62 | 27689656.16 | 86759243.78 | Vieques and Culebra Projects
167446 | PA-02-PR-4339-PRJ-167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | 32863940.58 | 0 | 32863940.58 | Priority Transmission
169058 | PA-02-PR-4339-PRJ-169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 23342346.17 | 13265333.34 | 36607679.51 | Substation
169276 | PA-02-PR-4339-PRJ-169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | 75107786 | 3661876.82 | 78769662.82 | Substation
176913 | PA-02-PR-4339-PRJ-176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 40504745.14 | 0 | 40504745.14 | Priority Transmission
176971 | PA-02-PR-4339-PRJ-176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 23193643.55 | 0 | 23193643.55 | Priority Transmission
178577 | PA-02-PR-4339-PRJ-178577 | FAASt [Cachete – MC 1526] (Substations) | 24361713.92 | 16340158.71 | 40701872.63 | Substation
180052 | PA-02-PR-4339-PRJ-180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | 17796351.55 | 0 | 17796351.55 | Priority Transmission
334470 | PA-02-PR-4339-PRJ-334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 51867865.42 | 0 | 51867865.42 | Priority Transmission
547187 | PA-02-PR-4339-PRJ-547187 | FAASt - [Substation Component Replacement Program] (Substation) | 6551618.4 | 308929.24 | 6860547.64 | Substation
550106 | PA-02-PR-4339-PRJ-550106 | FAASt [Conquistador CH] (Substation) | 9827316 | 1101071.22 | 10928387.22 | Substation
550950 | PA-02-PR-4339-PRJ-550950 | FAASt - EPC - [Monacillo TC] (Substations) | 13072870.61 | 0 | 13072870.61 | Priority Substation | PW Version
551914 | PA-02-PR-4339-PRJ-551914 | FAASt [Caparra 1912 & 1924] (Substation) | 8228185.09 | 5838512.8 | 14066697.89 | Substation
682328 | PA-02-PR-4339-PRJ-682328 | FAASt [Bayamón TC - Rebuild] (Substation) | 9126057.99 | 0 | 9126057.99 | Substation
682645 | PA-02-PR-4339-PRJ-682645 | FAASt [Maunabo TC] (Substation) | 13016336.93 | 0 | 13016336.93 | Priority Substation
682834 | PA-02-PR-4339-PRJ-682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | 10983086.42 | 0 | 10983086.42 | Priority Substation | PW Version
711819 | PA-02-PR-4339-PRJ-711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | 2349734.4 | 197625.13 | 2547359.53 | Transmission
723883 | PA-02-PR-4339-PRJ-723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 0 | 145069437.94 | 145069437.94 | Vegetation
727522 | PA-02-PR-4339-PRJ-727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 897595.83 | 3098128.05 | 3995723.88 | Vegetation
727529 | PA-02-PR-4339-PRJ-727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 12967819.92 | 44340770.67 | 57308590.59 | Vegetation
727572 | PA-02-PR-4339-PRJ-727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 0 | 80353343.34 | 80353343.34 | Vegetation
727606 | PA-02-PR-4339-PRJ-727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 7230250.37 | 24722341.5 | 31952591.87 | Vegetation
727608 | PA-02-PR-4339-PRJ-727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 1161449.55 | 4008841.52 | 5170291.07 | Vegetation
727657 | PA-02-PR-4339-PRJ-727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 665799.1 | 2298062.02 | 2963861.12 | Vegetation
727659 | PA-02-PR-4339-PRJ-727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 1098979.51 | 3793220.88 | 4892200.39 | Vegetation
735474 | PA-02-PR-4339-PRJ-735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 16785005 | 0 | 16785005 | Distribution
741105 | PA-02-PR-4339-PRJ-741105 | FAASt [All Regions TL - 230kV] (Vegetation) | 0 | 157385518.05 | 157385518.05 | Vegetation
749060 | PA-02-PR-4339-PRJ-749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | 1316781.32 | 140677.54 | 1457458.86 | Transmission
749072 | PA-02-PR-4339-PRJ-749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | 823313.44 | 59629.8 | 882943.24 | Transmission
750150 | PA-02-PR-4339-PRJ-750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | 131895.22 | 8224.8 | 140120.02 | Transmission
750151 | PA-02-PR-4339-PRJ-750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | 261446.49 | 13024.96 | 274471.45 | Transmission
750168 | PA-02-PR-4339-PRJ-750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | 468439.49 | 37472.84 | 505912.33 | Transmission
750692 | PA-02-PR-4339-PRJ-750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 15430664 | 0 | 15430664 | Distribution
752540 | PA-02-PR-4339-PRJ-752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 8487643 | 0 | 8487643 | Distribution
753782 | PA-02-PR-4339-PRJ-753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | 135332.58 | 2218.84 | 137551.42 | Transmission
757689 | PA-02-PR-4339-PRJ-757689 | FAASt [Automation Program Group 24] (TL/ Distribution) | 2337650.4 | 0 | 2337650.4 | 428 Distribution Automation
757692 | PA-02-PR-4339-PRJ-757692 | FAASt [Automation Program Group 26] (TL / Distribution) | 1369120.11 | 0 | 1369120.11 | 428 Distribution Automation
757696 | PA-02-PR-4339-PRJ-757696 | FAASt [Automation Program Group 31] (Distribution) | 1515001.61 | 0 | 1515001.61 | 428 Distribution Automation
757700 | PA-02-PR-4339-PRJ-757700 | FAASt [Automation Program Group 35] (TL / Distribution) | 1743076.28 | 0 | 1743076.28 | 428 Distribution Automation
790443 | PA-02-PR-4339-PRJ-790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 222321 | 0 | 222321 | Distribution
797148 | PA-02-PR-4339-PRJ-797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | 2605318.99 | 0 | 2605318.99 | Distribution
798275 | PA-02-PR-4339-PRJ-798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | 7464273.83 | 0 | 7464273.83 | Distribution
800286 | PA-02-PR-4339-PRJ-800286 | FAASt [Automation Program Group 36] (TL / Distribution) | 2301102.91 | 0 | 2301102.91 | 428 Distribution Automation
800361 | PA-02-PR-4339-PRJ-800361 | FAASt [Automation Program Group 37] (Distribution) | 2069863.13 | 0 | 2069863.13 | 428 Distribution Automation
801166 | PA-02-PR-4339-PRJ-801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | 21962621.6 | 0 | 21962621.6 | Distribution
801172 | PA-02-PR-4339-PRJ-801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | 2529247.52 | 0 | 2529247.52 | Distribution
825843 | PA-02-PR-4339-PRJ-825843 | FAASt [Guanica TC] (Substation) | 6521097.48 | 0 | 6521097.48 | Priority Substation
956330 | PA-02-PR-4339-PRJ-956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | 1968823.15 | 5853486.17 | 7822309.32 | Vegetation
956331 | PA-02-PR-4339-PRJ-956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | 164281.79 | 5879647.9 | 6043929.69 | Vegetation
956332 | PA-02-PR-4339-PRJ-956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | 2787055.9 | 8286164.87 | 11073220.77 | Vegetation
956335 | PA-02-PR-4339-PRJ-956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | 1849955.27 | 5500081.4 | 7350036.67 | Vegetation
956337 | PA-02-PR-4339-PRJ-956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | 1800712.05 | 5353676.97 | 7154389.02 | Vegetation
956339 | PA-02-PR-4339-PRJ-956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | 245849.34 | 8798952.37 | 9044801.71 | Vegetation
956340 | PA-02-PR-4339-PRJ-956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | 134961.38 | 4830269.73 | 4965231.11 | Vegetation
956341 | PA-02-PR-4339-PRJ-956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | 24080 | 71591.83 | 95671.83 | Vegetation
956342 | PA-02-PR-4339-PRJ-956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | 10945700.85 | 32542541.69 | 43488242.54 | Vegetation
956343 | PA-02-PR-4339-PRJ-956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | 5271329.93 | 15672132.45 | 20943462.38 | Vegetation
956345 | PA-02-PR-4339-PRJ-956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | 1805809.83 | 5368833.09 | 7174642.92 | Vegetation
956348 | PA-02-PR-4339-PRJ-956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | 294309.16 | 875007.19 | 1169316.35 | Vegetation
956349 | PA-02-PR-4339-PRJ-956349 | FAASt [San Juan Region 1 Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | 3415441.98 | 10154412.56 | 13569854.54 | Vegetation
956353 | PA-02-PR-4339-PRJ-956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | 9124048.44 | 27126607.1 | 36250655.54 | Vegetation
956356 | PA-02-PR-4339-PRJ-956356 | FAASt [Ponce Region 6 Line 39000 – Aguas Buenas to Hacienda San Jose] (Vegetation) | 988951.38 | 0 | 988951.38 | Vegetation
956357 | PA-02-PR-4339-PRJ-956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | 3132433.36 | 9313002.71 | 12445436.07 | Vegetation
551963 | PA-02-PR-4339-PRJ-551963 | FAASt [Transport Network Group 1] (Telecommunication) | 6633463.21 | 0 | 6633463.21 | Telecommunication
755211 | PA-02-PR-4339-PRJ-755211 | FAASt [Automation Program Group 15] (Distribution) | 643560.85 | 0 | 643560.85 | 428 Distribution Automation
679133 | PA-02-PR-4339-PRJ-679133 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 4] (Distribution) | 20729 | 633 | 21362 | Distribution
168483 | PA-02-PR-4339-PRJ-168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | 96749488 | 8111071 | 104860559 | Transmission
757687 | PA-02-PR-4339-PRJ-757687 | FAASt [Automation Program Group 22] (Distribution) | 2768746.03 | 0 | 2768746.03 | 428 Distribution Automation
757697 | PA-02-PR-4339-PRJ-757697 | FAASt [Automation Program Group 32] (TL / Distribution) | 2663099.41 | 0 | 2663099.41 | 428 Distribution Automation
812569 | PA-02-PR-4339-PRJ-812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | 10978061.1 | 0 | 10978061.1 | Distribution
817956 | PA-02-PR-4339-PRJ-817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 2184086.98 | 0 | 2184086.98 | Distribution
714641 | PA-02-PR-4339-PRJ-714641 | FAASt [Rincón Streetlighting] (Distribution) | 11592957.26 | 694470.58 | 12287427.84 | Distribution | PW Version
723002 | PA-02-PR-4339-PRJ-723002 | FAASt - EPC - Jobos TC (Substation) | 69904580.54 | 0 | 69904580.54 | Substation
551926 | PA-02-PR-4339-PRJ-551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 5664186.55 | 1073462.61 | 6737649.16 | Telecommunication | PW Version
673292 | PA-02-PR-4339-PRJ-673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 8129023.86 | 49577.82 | 8178601.68 | Telecommunication | PW Version
547251 | PA-02-PR-4339-PRJ-547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 6482242.86 | 0 | 6482242.86 | Transmission
756997 | PA-02-PR-4339-PRJ-756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | 41068188.09 | 0 | 41068188.09 | Transmission
756999 | PA-02-PR-4339-PRJ-756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | 30407203.69 | 0 | 30407203.69 | Transmission
750063 | PA-02-PR-4339-PRJ-750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 0 | 113327804.46 | 113327804.46 | Vegetation
750065 | PA-02-PR-4339-PRJ-750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 0 | 132424167.91 | 132424167.91 | Vegetation
750066 | PA-02-PR-4339-PRJ-750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 0 | 3142832.19 | 3142832.19 | Vegetation
750067 | PA-02-PR-4339-PRJ-750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 0 | 107170415.13 | 107170415.13 | Vegetation
750068 | PA-02-PR-4339-PRJ-750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 0 | 98723529.73 | 98723529.73 | Vegetation
956593 | PA-02-PR-4339-PRJ-956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | 5492458.5 | 0 | 5492458.5 | Substation
746309 | PA-02-PR-4339-PRJ-746309 | FAASt [Automation Program Group 30] (Distribution) | 379772.1 | 251311.27 | 631083.37 | Distribution
757662 | PA-02-PR-4339-PRJ-757662 | FAASt [Automation Program Group 21] (Distribution) | 2223344.42 | 0 | 2223344.42 | 428 Distribution Automation
757694 | PA-02-PR-4339-PRJ-757694 | FAASt [Automation Program Group 27] (Distribution) | 3292670.74 | 0 | 3292670.74 | 428 Distribution Automation
757698 | PA-02-PR-4339-PRJ-757698 | FAASt [Automation Program Group 33] (Distribution) | 2483045.65 | 0 | 2483045.65 | 428 Distribution Automation
757699 | PA-02-PR-4339-PRJ-757699 | FAASt [Automation Program Group 34] (Distribution) | 3439728.11 | 0 | 3439728.11 | 428 Distribution Automation
957578 | PA-02-PR-4339-PRJ-957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | 1108989.51 | 0 | 1108989.51 | Substation
165213 | PA-02-PR-4339-PRJ-165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 67974026.1 | 19118456.86 | 87092482.96 | Vieques and Culebra Projects
751655 | PA-02-PR-4339-PRJ-751655 | FAASt [Vieques Microgrid] (Transmission) | 605646.11 | 124703389.13 | 125309035.24 | Vieques and Culebra Projects
751656 | PA-02-PR-4339-PRJ-751656 | FAASt [Culebra Microgrid] (Transmission) | 46260.79 | 73445001.67 | 73491262.46 | Vieques and Culebra Projects
678800 | PA-02-PR-4339-PRJ-678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 13148929.44 | 55895.84 | 13204825.28 | Telecommunication
662238 | PA-02-PR-4339-PRJ-662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 3014559.92 | 3199102 | 6213661.92 | Telecommunication
746545 | PA-02-PR-4339-PRJ-746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 115638378 | 0 | 115638378 | Telecommunication
746660 | PA-02-PR-4339-PRJ-746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) |  | 564455.36 | 564455.36 | Substation
|  |  | 1126719249.1 | 679360890.2 | 1806080139.3 | 0
C-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal. Subject to change after FEMA validation
PW | Genera - Under Formulation | Project Name | 428 | 406 | Total Child | Asset
164988 | PA-02-PR-4339-PRJ-164988 | FAASt Generation Fleet Project (Generation) | 406717776.67 |  | 406717776.67 | Priority Generation
662957 | PA-02-PR-4339-PRJ-662957 | FAASt [Palo Seco Power Plant –001 Units 3 & 4] (Generation) | 5691871.22 |  | 5691871.22 | Generation
663383 | PA-02-PR-4339-PRJ-663383 | FAASt [Cambalache Power Plant Permanent Repairs] (Generation) | 30000000 | 33059916 | 63059916 | Generation
663385 | PA-02-PR-4339-PRJ-663385 | CLOSEOUT - FAASt [Mayaguez Hydro-Gas Power Plant Permanent Repairs] (Generation) | -337107.18 |  | -337107.18 | Generation
670036 | PA-02-PR-4339-PRJ-670036 | FAASt [Design Fire Pump for Aguirre Power Complex] (Generation) | 25000000 |  | 25000000 | Generation
672950 | PA-02-PR-4339-PRJ-672950 | FAASt [Costa Sur Power Plant Permanent Repairs CS-001] (Generation) | 67252 |  | 67252 | Priority Generation
687480 | PA-02-PR-4339-PRJ-687480 | FAASt [San Juan Power Plant 002 Units 7 & 8] (Generation) | -289091.69 |  | -289091.69 | Generation
754801 | PA-02-PR-4339-PRJ-754801 | FAASt [Repair Unit 9 San Juan Steam Plant] (Generation) | 27432038.24 |  | 27432038.24 | Generation
816612 | PA-02-PR-4339-PRJ-816612 | FAASt [Continuous Emission Monitoring Systems (CEMS)] (Generation) | 5000000 |  | 5000000 | Generation
817248 | PA-02-PR-4339-PRJ-817248 | FAASt [Power Plant Repairs & System Restoration] (Generation) | 89680589.58 |  | 89680589.58 | Priority Generation
948766 | PA-02-PR-4339-PRJ-948766 | FAASt [Physical Security] (Generation) | 5750000 |  | 5750000 | Generation
|  |  | 594713756.84 |  | 594713756.84 | 0
D-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal

## LUMA Consolidated List
Grants Portal- Project Costs Allocation
Project # | Title | FEMA Allocation | Asset | SUB ASSET | Process Step (as of 10/09/2025 8:20am) | Project costs - Submitted to FEMA * | Current PW Version 428 Gross Cost * | 428 Allocation * | 406 Allocation * | A&E-PW 9510 * | E&M-PW 10710 * | A&E Costs Incurred | E&M Cost Incurred | Construction Cost Incurred | Total Estimate Incurred Cost | Project Status | Project Scope | Additional comments
757692 | FAASt [Automation Program Group 26] (TL / Distribution) | Priority-Pipeline | 428 Distribution Automation | Automation | Obligated | 1544445.44 | 938783.63 | 938783.63 | 0 | 175325.33 | 430336.48 | 38673.52 | 209048.7401 | 2093.03 | 249815.2901 | Pending COR3 review and approval | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
757689 | FAASt [Automation Program Group 24] (TL/ Distribution) | Priority-Pipeline | 428 Distribution Automation | Automation | Obligated | 2636949.72 | 1774822.4 | 1774822.4 | 0 | 299299.32 | 562828 | 90144.9 | 458434.3377 | 2771.4 | 551350.6377 | Pending COR3 review and approval | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
800361 | FAASt [Automation Program Group 37] (Distribution) | Priority-Pipeline | 428 Distribution Automation | Automation | Obligated | 2367851.22 | 1596192.73 | 1596192.73 | 0 | 297988.09 | 473670.4 | 125054.02 | 340308.6176 | 561.91 | 465924.5476 | Project in Final FEMA Review since 6/12/2025. | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
757696 | FAASt [Automation Program Group 31] (Distribution) | Priority | 428 Distribution Automation | Automation | Obligated | 1710177.27 | 1145457.61 | 1145457.61 | 0 | 195175.66 | 369544 | 56017.1 | 262670.8354 | 4033.49 | 322721.4254 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | Priority | 428 Distribution Automation | Automation | Obligated | 2601467.86 | 1703712.83 | 1703712.83 | 0 | 300364.95 | 597390.08 | 63716.05 | 122408.2003 | 0 | 186124.2503 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | Priority | 428 Distribution Automation | Automation | Obligated | 1988436.16 | 1318515.66 | 1318515.66 | 0 | 245359.86 | 424560.64 | 69865.55 | 54222.255 | 490.28 | 124578.085 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Priority-Pipeline | Vegetation | Vegetation | Pending Large Project Review | 25072092.11 | 6584889.61 | 6584889.61 | 18404524.67 | 82677.83 | 0 | 45864.06 | 0 | 12213046.06 | 12258910.12 | Project Version 1 obligation in process- | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 1 (San Juan). | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Priority-Pipeline | Vegetation | Vegetation | Pending Applicant Project Review | 48974857.77 | 12945985.39 | 12945985.39 | 36028872.38 | 0 | 0 | 0 | 0 | 627738.06 | 627738.06 | 6/17/2025 - The project is under review by Expert review since 4/14/2025. | Vegetation Clearing for Region Bayamon High Density | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Priority-Pipeline | Priority Substation | Substation | Obligated | 78862691.85 | -24526745.94 | 36917509.58 | 0 | 6435349.91 | 35509832.36 | 3810069.76 | 2229261.1 | 271586.29 | 6310917.15 | Obligated EPC Portion- Version in process to include transformer costs and remove equipment costs already obligated under PW 10710 and A&E under PW 9510 | Costa Sur Transformer Replacement -Replacement of the existing infrastructure and transmission breakers according to the new proposed 115 kV single line diagram with a gas insulated switchgear (GIS) in breaker-and-a-half configuration. Replace the 230 supply cables for autotransformer Bank #1.Flood mitigation for 115 kV and 38 kV sites due to flood zone location (ABFE Flood Zone A).Construction of new control facilities for 115 kV and 38 kV to include protection, control, and metering equipment. (60 FT x 30 FT) Replace the existing Bank #1: 115/38 kV, 60/80/100/112 MVA transformer with a new one since it has been in service since 1991 and is reaching the end of its useful life. The impedance of this transformer shall be like the existing one. Replace the existing Bank #2: 115/38 kV, 60/80/100/112 MVA transformer with a new one. This bank has 30 years of service and will be kept as an on-site spare in a pad. H.Provide a spare 230/115 kV transformer on a pad on site. Emergency Generator needed at site. (Generator pad size 7FT x 4 FT). | Project included in list since its already in Pipeline, soon to be Obligated. Project poart of LUMA Priority Projects P3A list and PREPA Presentation
682645 | FAASt [Maunabo TC] (Substation) | Priority-Pipeline | Priority Substation | Substation | Obligated | 14621458.61 | 8292124.95 | 8292124.95 | 0 | 1605121.68 | 4724211.98 | 2435755.36 | 1551782.29 | 113432.08 | 4100969.73 | Project approved- Pending obligation- Currently Pending Large Project Review | Will install transformer, 115kV GE Breaker, 38kV GE Breaker.Transformer & Breaker foundations.PAC Systems Installation. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list and PREPA Presentation
735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Pipeline | Distribution | Poles | Obligated | 18747102.15 | 14075641.42 | 14075641.42 | 0 | 1962096.73 | 2709364 | 345648.23 | 1588894.6198 | 5145.16 | 1939688.0098 | Pending EHP review.Waiting for revised DSOW package without brushing to be able to move project forward, | Planned to replace poles in Caguas region | Project included in list since its already in Pipeline, soon to be Obligated.
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Pipeline | Distribution | Poles | Obligated | 248306 | 186697 | 186697 | 0 | 25985 | 35624 | 15962.43 | 20132.4 | 273.81 | 36368.64 | Pending Recipient Final Review since 5/22/2025. | Planned to replace poles in San Juan region | Project included in list since its already in Pipeline, soon to be Obligated.
798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | Pipeline | Distribution | Feeders | Obligated | 8418694.51 | 6711420.9 | 6711420.9 | 0 | 954420.68 | 752852.93 | 1202388.96 | 199559.0598 | 36188.99 | 1438137.0098 | Project moving through the queues. | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines). | Project included in list since its already in Pipeline, soon to be Obligated.
797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | Pipeline | Distribution | Feeders | Obligated | 3383166.23 | 2359895.63 | 2359895.63 | 0 | 777847.24 | 245423.36 | 1789592.23 | 126860.4375 | 109948.15 | 2026400.8175 | Project moving through the queues. | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines). | Project included in list since its already in Pipeline, soon to be Obligated.
750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Pipeline | Distribution | Poles | Obligated | 17230407 | 12921047 | 12921047 | 0 | 1799743 | 2509617 | 329386.02 | 1479407.0199 | 247.9 | 1809040.9399 | Pending EHP review. Waiting for revised DSOw package without brushing to be able to move project forward. | Planned to replace poles in Mayagüez region | Project included in list since its already in Pipeline, soon to be Obligated.
752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Pipeline | Distribution | Poles | Obligated | 9478854.81 | 7111613.91 | 7111613.91 | 0 | 991211.9 | 1376029 | 243940.67 | 434861.9299 | 682.2 | 679484.7999 | Pending EHP review. Waiting for revised DSOw package without brushing to be able to move project forward. | Replacement of poles and the repair of conductors for specific feeders in Mayagüez region to be performed under the “Proposed 428 Public Assistance Scope of Work”. | Project included in list since its already in Pipeline, soon to be Obligated.
801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | Pipeline | Distribution | Feeders | Obligated | 3038024.53 | 2285961.13 | 2285961.13 | 0 | 508777.01 | 243286.39 | 1013367.23 | 104987.1823 | 3698.6 | 1122053.0123 | Project moving through the queues. | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines). | Project included in list since its already in Pipeline, soon to be Obligated.
825843 | FAASt [Guanica TC] (Substation) | Priority | Priority Substation | Substation | Obligated | 7348078.61 | 2320373.96 | 2320373.96 | 0 | 826981.13 | 4200723.52 | 0 | 1305535.44 | 0 | 1305535.44 | 6/17/2025- (Stabilization Projects) EHP is requesting additional information for the subject project. Response Received on 5/8/2025 -Process Step: Field EHP: ESA Consultation process initiated; drafting ongoing. ECD 8/04/2025." | Replace the out-of-service transformer at Guánica. Also, the installation of this transformer will aid and stabilize the transmission and distribution feeders interconnected and related to the function of the substation.
550950 | FAASt - EPC - [Monacillo TC] (Substations) | Priority | Priority Substation | Substation | Obligated | 103349156.37 | -29901321.56 | 58195134.17 | 0 | 2179830 | 42974192.2 | 4210529.76 | 6199138 | 4908549 | 15318216.76 | Obligated EPC Portion- Version in process $88,096,456 | Monacillos Transformer Replacement - Stabilization phase- Need to clarify - Work identified under the scope and also under DOE Grant funds
167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | Priority | Priority Transmission | Transmission | Pending Applicant Project Review | 38031104.5 | 34329274.96 | 34329274.96 | 0 | 3616821.54 | 85008 | 8488856.85 | 0 | 1120713.72 | 9609570.57 | "7/8/2024 - The Version 0 Boring Plan Evaluation was not Completed, additional information necessary. - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development." | Replace structures and reconductor the entire line from Bayamon TC to Monacillos TC.
334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Priority | Priority Transmission | Transmission | Pending Large Project Review | 52098415.55 | 46064675.98 | 46064675.98 | 0 | 5039982.61 | 993756.96 | 4768004.84 | 0 | 21945.02 | 4789949.86 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entire line from Monacillos TC to Sabana Llana TC.
180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | Priority | Priority Transmission | Transmission | Pending Applicant Project Review | 104967422.32 | 85971750.2 | 85971750.2 | 0 | 9582455.16 | 9413216.96 | 5302957.86 | 178562 | 80311.36 | 5561831.22 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entire line from Ponce TC to Salinas Urbano TC. | El proyecto inlcuye remocion de vegetacion. FEMA notifico 6-30-25 que la cuantia de millas solicitada en el scope esta incorrrecta.La mayoria no necesita vegetacion
176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Priority | Priority Transmission | Transmission | Pending EHP Review | 46888195.25 | 34395876.55 | 34395876.55 | 7376901 | 4817554.82 | 297862.88 | 1867030.19 | 0 | 73599.38 | 1940629.57 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entire line from Palo Seco SP to Catano Sect | El proyecto inlcuye remocion de vegetacion. FEMA notifico 6-30-25 que la cuantia de millas solicitada en el scope esta incorrrecta.La mayoria no necesita vegetacion
176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Priority | Priority Transmission | Transmission | Pending EHP Review | 26444537.92 | 22273190.89 | 22273190.89 | 4723291 | 3250894.37 | 120403.36 | 1497895.03 | 8101.3782 | 62971.09 | 1568967.4982 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entireline from SAN JUAN SP to Catano Sect
165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Priority | Vieques and Culebra Projects (6) | Feeders | Pending PDMG Scope & Cost Routing | 86759244 | 86759244 | 86759244 |  |  |  | 3948214 | 3237620.1979 | 760400.65 | 7946234.8479 | Pending 5th HM RFI Responses. On February 14, 2025, the applicant requested an extension until February 28, 2025, to provide responses for the 5th RFI. On February 27, 2025, they requested further time until March 14, 2025, and on March 14, 2025, they sought an additional extension until March 31, 2025.On march 31, 2025 additional extension requested for April 30, 2025. On May 28, 2025 additional extension requested for June 30, 2025. | Reconstruction of feeders across Vieques and Culebra.
551914 | FAASt [Caparra 1912 & 1924] (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | [6 empty] | 1757341.73 | 222662.22 | 3303.67 | 1983307.62 | "4/6/2025- Email was sent to the applicant with the HM RFI response remarks, after evaluating the data submitted by the subrecipient, we still need more information to finalize our evaluation. 6/10/2025- Follow up email was sent to the applicant reuqesting update/forecast regarding the HM RFI #2 -LUMA forecast: pending" | Soil borings and geotechnical testing.The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing. | No construction Scope- Soil borings and geotechnical testing.The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing.
547187 | FAASt - [Substation Component Replacement Program] (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | 8929767 | 4790316.92 | 4790316.92 |  | 2135844 | 2333225.36 | 939146.21 | 229882.64 | 11496.2 | 1180525.05 | "6/17/2025 - Applicant submit HM RFI response on 6/6/2025. Currently under HM review -HM Forecast: 6/18/2025" | Project will involve designing and constructing a new substation to replace a flooded facility, including various electrical components and site development
550106 | FAASt [Conquistador CH] (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | 11639958 | 11639958 |  |  |  |  | 2894958.74 | 0 | 772606.85 | 3667565.59 | " 2/25/2025 - HM RFI Subs Matrix response send to the applicant on 2/26/2025(concluded that we can move forward with this tool. However, it is important that the subrecipient, when submitting a project, ensure that it contains all necessary information related to the mitigation measure, including a brief description of why it is considered mitigation and cost updates if it necessary 6/10/2025- Follow up email sent on 3/25/2025, 4/14/2025, 4/21/2025, and 6/2/25 requesting an update-LUMA forecast: pending" | Replacing the damaged control house and functionally dependent elements.
169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | 20425907 | 20425907 |  |  |  |  | 3388651.17 | 915542.32 | 655231.01 | 4959424.5 | " 2/25/2025 - HM RFI Subs Matrix response send to the applicant on 2/26/2025(concluded that we can move forward with this tool. However, it is important that the subrecipient, when submitting a project, ensure that it contains all necessary information related to the mitigation measure, including a brief description of why it is considered mitigation and cost updates if it necessary 6/17/2025- Applicant update forecast date for DSOW submission to -LUMA forecast: 12/30/2025" | Replacement of the metalclad switchgear, feeder cables, conduits and corresponding foundations, grounding, and other related components as necessary | NO DSOW submitted by LUMA- Forecast 12/30/25
178577 | FAASt [Cachete – MC 1526] (Substations) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | [6 empty] | 2119451.09 | 365667.03 | 4322.65 | 2489440.77 | " 2/25/2025 - HM RFI Subs Matrix response send to the applicant on 2/26/2025(concluded that we can move forward with this tool. However, it is important that the subrecipient, when submitting a project, ensure that it contains all necessary information related to the mitigation measure, including a brief description of why it is considered mitigation and cost updates if it necessary 6/10/2025- Follow up email sent on 3/25/2025, 4/14/2025, 4/21/2025, 5/20/2025 and 6/2/2025 requesting an update -LUMA forecast: pending" | Replace this switchgear to PREPA and industry standards, improve system resiliency, and to mitigate safety hazards due to equipment age and environmental concerns. | NO DSOW submitted by LUMA- Forecast Pending. No construction Scope- Soil borings and geotechnical testing.The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing.
753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Phase 2 | Transmission | Transmission | Pending Award | 162748.65 | 124593.02 | 124593.02 | 14809.67 | 17120.17 | 6225.79 | 73300.2 | 0 | 0 | 73300.2 | "6/6/2025 - The 1st HM RFI has been sent to the applicant on February 27, 2025, for their action. FEMA received communication that Project is under applicant QA/QC and the new forecast is set for 6/26/2025. " | Transmission Pole Replacement and Critical Repairs 38 KV L 3100 Monacillos TC to Sabana Llana TC, FAAST#: 753782
750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Phase 2 | Transmission | Poles | Pending Award | 71874.31 | 58488 | 58488 | 5771.31 | 7615 | 0 | 23704.22 | 0 | 0 | 23704.22 | 6/17/2025 - The 2nd HM RFI has been sent to the applicant on February 26, 2025, for their action. FEMA received communication that Project is under applicant QA/QC and the new forecast is set for 6/26/2025. | Replace structures that are critically damaged
750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Phase 2 | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 150223.28 | 123160.67 | 123160.67 | 11027.93 | 16034.68 |  | 18541.41 | 0 | 0 | 18541.41 | 6/9/2025 - The project is under Applicant revision and modification (open ended language EHP request and required corrections). New deadline set by the Applicant 6/19/2025. | Replacement of hardware, several structures, guys anchoring and foundations for TL700.
749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Phase 2 | Transmission | Poles | Pending Award | 209886.2 | 158495.32 | 158495.32 | 30755.87 | 20635.01 | 0 | 284188.06 | 0 | 0 | 284188.06 | 6/17/2025 - Applicant new forecast for the response for the informal EHP RFI clarification the new deadline for response is 6/26/2025. | Replace structures that are critically damaged
749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Phase 2 | Transmission | Poles | Pending EHP Review | 953607.59 | 717817.65 | 717817.65 | 142335 | 93454.94 | 0 | 285445.42 | 4395.0182 | 0 | 289840.4382 | 6/17/2025 - Applicant submitted on December 19, 2025, partial response for the EHP-RFI-PRJ-106924. LUMA Forecast 6/20/2025. | Replace structures that are critically damaged
711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Phase 2 | Transmission | Poles | Pending PDMG Project Review | 2086350 | 1705844 | 1705844 | 158417 | 222089 | 0 | 593102.66 | 0 | 807980.14 | 1401082.8 | 6/17/2025 - The project was reworked, needs additional corrections, including 406/428 E&M, A&E allocation in both document DSOW and LPCE. Project is under applicant QA/QC and the new forecast is set for 6/26/2025. | Replace structures that are critically damaged
682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | 2905296.08 | 2637502.74 | 2637502.74 | 0 | 267793.34 | 0 | 2712040.26 | 15305049.39 | 14826874.56 | 32843964.21 | "6/17/2025 -PREB Resolution and Approval received on 4/11/2025. Pending DSOW and CE -LUMA forecast: 7/3/2025" | 230 kV Transformer Transportation & Installation.
169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | 18737178 | 18279001 | 18279001 | 0 | 458177 | 0 | 1974281.01 | 380001.1 | 13230.12 | 2367512.23 | Pending DSOW submittal by LUMA. Luma forecast pending | Repair and replacement of the metalclad switchgear, feeder cables & conduits and corresponding foundations, grounding, and other related components as necessary.
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | Pending Large Project Review | 157385518.05 | 154791845.18 |  |  | 2593672.87 |  | 0 | 0 | -5.6843e-14 | -5.6843e-14 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. Forecast: TBD- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 230kV and below power transmission and distribution lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within All Regions Transmission - 230kV of Puerto Rico.
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | Pending Large Project Review | 33286982.49 | 8206527.54 | 8206527.54 | 24398735.91 | 681719.03 |  | 80.96 | 0 | 27533.8 | 27614.76 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV and below power transmission and distribution lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 1 (SJ) of Puerto Rico.
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | Pending Large Project Review | 74088605.9 | 18265704.46 | 18265704.46 | 54305563.22 | 1517338.23 |  | -9.0949e-13 | 0 | 127791 | 127791 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 2 (Arecibo) of Puerto Rico.
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | Pending Large Project Review | 73136988.1 | 18031093.89 | 18031093.89 | 53608045.16 | 1497849.05 |  | 14.3 | 0 | 0 | 14.3 | 6/17/2025 - Follow up email sent on 5/16/2025 and 6/10/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV and below power transmission and distribution lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 3 (Bayamon) of Puerto Rico.
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | Pending Large Project Review | 149456350.77 | 36846766.07 | 36846766.07 | 109548711.44 | 3060873.27 |  | 0 | 0 | 18381.82 | 18381.82 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule.DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 4 (Caguas) of Puerto Rico.
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | Pending Large Project Review | 125194568.18 | 30865299.08 | 30865299.08 | 91765278.3 | 2563990.79 |  | -4.5475e-13 | 0 | 0 | -4.5475e-13 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 5 (Mayaguez) of Puerto Rico.
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | Pending Large Project Review | 74301040.39 | 18318077.75 | 18318077.75 | 54661273.75 | 1521688.89 |  | 4.5475e-13 | 0 | 0 | 4.5475e-13 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 6 (Ponce) of Puerto Rico.
956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending QA Review | 7985860.15 | 1968823.15 | 1968823.15 | 5853486.17 | 163550.83 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 60.23 miles- Entire Line
956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending EHP Review | 8021552.35 | 1977622.66 | 1977622.66 | 5879647.9 | 164281.79 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 60.5 miles- Entire Line
956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending EHP Review | 11304742.47 | 2787055.9 | 2787055.9 | 8286164.87 | 231521.7 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 85.26 miles- Entire Line
956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending EHP Review | 7503713.1 | 1849955.27 | 1849955.27 | 5500081.4 | 153676.43 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 56.59 miles- Entire Line
956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending EHP Review | 7303974.78 | 1800712.05 | 1800712.05 | 5353676.97 | 149585.76 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 55.09 miles- Entire Line
956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending Insurance Completion | 12004333.95 | 2959532.24 | 2959532.24 | 8798952.37 | 245849.34 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 90.54 miles- Entire Line
956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending EHP Review | 6589894.87 | 1624663.76 | 1624663.76 | 4830269.73 | 134961.38 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 49.7 miles- Entire Line
956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | Pending EHP Review | 97672.18 | 24080 | 24080 | 71591.83 | 2000.35 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 0.73 miles- Segment of Line
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | New Project | Vegetation | Vegetation-TL | Obligated | 44397505.6 | 10945700.85 | 10945700.85 | 32542541.69 | 909263.06 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 36.78 miles- Segment of Line- Line included in DOE Emergency Order
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | New Project | Vegetation | Vegetation-TL | Pending Scope & Cost Completion by Applicant | 21381353.56 | 5271329.93 | 5271329.93 | 15672132.45 | 437891.18 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 39.77 miles- Segment of Line
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | New Project | Vegetation | Vegetation-TL | Pending Scope & Cost Completion by Applicant | 7324652.17 | 1805809.83 | 1805809.83 | 5368833.09 | 150009.25 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 12.96 miles- Segment of Line
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | New Project | Vegetation | Vegetation-TL | Pending Scope & Cost Completion by Applicant | 1193764.73 | 294309.16 | 294309.16 | 875007.19 | 24448.38 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 2.43 miles
956349 | FAASt [San Juan Region 1 Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | New Project | Vegetation | Vegetation-TL | Obligated | 13853576.48 | 3415441.98 | 3415441.98 | 10154412.56 | 283721.94 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 11.13 miles- Segment of the Line-Line included in DOE Emergency Order
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | New Project | Vegetation | Vegetation-TL | Obligated | 37008593.33 | 9124048.44 | 9124048.44 | 27126607.1 | 757937.79 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 30.97 miles- Segment of the Line-Line included in DOE Emergency Order
956356 | FAASt [Ponce Region 6 Line 39000 – Aguas Buenas to Hacienda San Jose] (Vegetation) | New Project | Vegetation | Vegetation-TL | Obligated | 3583135.14 | 843405.43 | 843405.43 | 2626357.86 | 113371.85 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 2.81 miles- Segment of the Line-Line included in DOE Emergency Order
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | New Project | Vegetation | Vegetation-TL | Pending Scope & Cost Completion by Applicant | 12705648.38 | 3415441.98 | 3132433.35 | 9313002.71 | 260212.32 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 22.35 miles- Segment of the Line
750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Phase 2 | Transmission | Poles | Pending Scope and Cost Development | 453277.24 | 404349.3 | 375810.42 | 28538.88 | 48927.94 | 0 | 15396.26 | 0 | 0 | 15396.26 | 6/17/2025 - The 3rd HM RFI has been sent to the applicant on May 30, 2025, for their action. The deadline is set 6/27/2025. | Replace structures that are critically damaged
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Priority | Vieques and Culebra Projects (6) | Substation | Pending Scope & Cost Completion by Applicant | 16241388 | 12765828 | 12765828 | 177391 | 2015951 | 0 | 1616014.42 | 191887.6 | 805798.03 | 2613700.05 |  | Repair and replacement of the control house HVAC, building waterproofing, protection & control features, auxiliary equipment, conduits, control cables, batteries, lights, grounding, finish grades, perimeter fence, and other components to restore functionality.
801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | Phase 2 | Distribution | Feeders | Pending EHP Review | 24121551.35 | 19191185.67 | 19191185.67 |  | 2734512.13 | 2195853.55 | 1446152.65 | 1466048.5351 | 75764.35 | 2987965.5351 | RFI response received on 6/12/2025.Under FEMA review | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines).
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Pipeline | Telecommunication | Telecomm | Obligated | 7469879.13 | 5490296.88 | 5490296.88 | 0 | 836416.02 | 1143166.23 | 11643381.74 | 0 | 251121.15 | 11894502.89 | Pending Recipient Review- Pending LUMA information regarding A&E COSTS | Project involves assessing sites and designing/installing "Make-Ready" infrastructure and Transport/ITOT network equipment, followed by commissioning and transitioning substation OT services.
755211 | FAASt [Automation Program Group 15] (Distribution) | Pipeline | 428 Distribution Automation | Automation | Pending Amendment Request Approval | 725419.42 | 643560.85 | 643560.85 | 0 | 81858.57 | 0 | 67345.1 | 107145.3691 | 302923.71 | 477414.1791 | Pending Obligation | Installation of smart reclosers with microprocessor-based controllers and the remote monitoring, communications ready and control capabilities in transmission and distribution lines. Installation of cutout type single phase reclosers, with microprocessor-based controllers. Installation of fault current indicators (communications ready).
679133 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 4] (Distribution) | Pipeline | Distribution | Poles | Process Discontinued | 0 | -20729 |  |  |  |  | 7401.31 | 0 | 424.24 | 7825.55 | Project De-Obligated | The applicant intents to replace damage and update structures to current standards of poles and conductors for the feeders within the Arecibo Group 4 (Mirador Azul -8007-01, 8007-03; Dominguito - 8010-02, 8010-03; Factor 1 -8011-01 and San Daniel - 8013-02).
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Phase 2 | Transmission | Transmission | Pending Scope & Cost Completion by Applicant | 0 | [5 empty] | 3565613.95 | 0 | 69711.17 | 3635325.12 | The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing that require vegetation removal, opening of access roads and other impacts that are closer to construction activities | "3/18/2025 - The Version 0 Boring Plan Evaluation start on March 18, 2025. 6/9/2025 - Field EHP: (ESA) Consultation process initiated; drafting ongoing. ECD 7/30/2025. 6/3/2025 - Follow up email sent to the Applicant on May 29, 2025, requesting new forecast for submission of dimensions (list of structures) of concrete foundations and revise FEMA OPGW Resolution. The project is under line priority evaluation forecasted TBD. Forecast was established for April 2025."
757687 | FAASt [Automation Program Group 22] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending Award | 2792415 | 2356733.87 | 2356733.87 | 0 | 359230.44 | 412012.16 | 85291.07 | 443874.7131 | 559.72 | 529725.5031 | EHP - Environmental: Initial review. Expected Completion Date (ECD) 07/31/2025. System Glitch: Project waiting to be sent back to make corrections to DSOW. | Deployment of grid automation technologies in feeders.
757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Priority | 428 Distribution Automation | Automation | Obligated | 2663099 | 1996678.58 | 1996678.58 | 0 | 339647.19 | 666420.83 | 117899.74 | 526409.7143 | 1466.21 | 645775.6643 | EHP - Environmental: In Review. Expected Completion Date (ECD) 08/01/2025. | Deployment of grid automation technologies in feeders.
812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Phase 2 | Distribution | Feeders | Obligated | 12381703.28 | 10217566.54 |  |  | 1403642.18 | 760494.56 | 1084400.71 | 411859.4948 | 6106.39 | 1502366.5948 | Field EHP: In review. Expected Completion Date (ECD) updated to 7/15/2025. | The project consists of the removal and replacement of 104 poles, the installation of 13 new poles that will be located within the easement, and work on 10 existing poles to comply with codes and standard.
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Phase 2 | Distribution | Feeders | Obligated | 3560609.24 | 2054461.78 |  |  | 1376522.26 | 129625.2 | 1010218.88 | 62608.0319 | 10961.27 | 1083788.1819 | Field EHP: In review. Expected Completion Date (ECD) updated to 7/15/2025. | The work to be performed includes but is not limited to; repair/replace poles/structures, damaged crossarms, broken and obsolete hardware, primary and secondary overhead and/or underground distribution lines, and porcelain insulation.
714641 | FAASt [Rincón Streetlighting] (Distribution) | Phase 2 | Distribution | Streetlights | Pending Large Project Review | 14055391.76 | 10915553.24 | 10915553.24 | 1211588.91 | 1928249.61 | 753614 | 416730.91 | 0 | 307.56 | 417038.47 | Waiting for LUMA to submit DSOW and CE revision as per Vegetation PA 428 Incidental Meeting held 04.22.2025, LUMA forecast 6/19/2025. 6/30/2025 PDMG call with LUMA team to clarify buffer zone for locations duplicated in Vegetation project.Waiting on response from applicant. | Streetlight repairs by replacing lightning components, poles, underground circuits and material disposal.
723002 | FAASt - EPC - Jobos TC (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant |  | 70586386.39 | 70586386.39 |  | 5724710.26 |  | 1739194.78 | 1100210.2 | 15989.76 | 2855394.74 | "7/9/2025 EHP RFI-PRJ-116045 response received on 7/4/2025. Project will continue GM flow. -Process Step: Pending Insurance Completion " | Construction of the facilities, reconfiguration and replacement of disaster-related damaged components and electrical systems into these new facilities, and the addition of new components to restore the facility to the pre-disaster functions with the applicable codes and standards
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Large Project Review | 6753699.16 | 5267467.99 | 5267467.99 | 1073462.61 |  |  | 1021302.13 | 0 | 186846.07 | 1208148.2 | Before moving the project forward to the CRC, LUMA must update the “Legend Sites” tab of the Cost Estimate, as it includes the substations that were removed from this new version. | SCADA Remote Access and RTU Replacements
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Pipeline | Telecommunication | Telecomm | Pending Award | 9249004.2 | 8124106.79 | 8124106.79 | 49577.82 | 1075319.59 |  | 562200.86 | 0 | 56242.57 | 618443.43 | "Field EHP - Historic: SHPO consultation process initiated; drafting ongoing. Expected Completion Date: 06/27/2025. " | Update the tower facilities and telecommunication building to current codes and standards via repair. This will be achieved by performing the engineering and structural assessments necessary to establish the amount of damage and the necessary repairs or rebuild to update or replace the structure. The engineering assessment shall include the field mapping of structure and appurtenances, geotechnical study, and foundation exploratory. A run rigorous tower structural analysis will be done and with results determined if the tower needs a minor repair or a major repair.
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Phase 2 | Transmission | Transmission | Pending Scope & Cost Completion by Applicant | 54042908.97 | 50289473.68 | 50289473.68 |  | 3753435.29 | 975659.88 | 2230168.28 | 0 | 35575.37 | 2265743.65 | 4/10/2025 - The Version 0 Boring Plan Evaluation was Completed as of April 8, 2025. 7/15/2025 - The project is running in the Grant Manager queue. The project is Pending EHP Review | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles.
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Phase 2 | Transmission | Transmission | Pending Scope & Cost Completion by Applicant | 43739699.88 | 40557533.61 | 40557533.61 |  |  |  | 0 | 0 | 0 | 0 | 7/15/2025 - The project is running in the Grant Manager queue. The project is Pending EHP Review. | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles. This line primarily traverses forested and urban areas between Dos Bocas HP substation and San Sebastian TC substation.
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Phase 2 | Transmission | Transmission | Pending Scope & Cost Completion by Applicant | 32495692.2 | 29319358.78 | 29319358.78 |  | 2088488.51 | 1087844.91 | 0 | 0 | 0 | 0 | 7/152025 - The project is running in the Grant Manager queue. The project is Pending EHP Review. | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles. This line primarily traverses forested and urban areas between Dos Bocas HP substation and San Sebastian TC substation.
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending Applicant Project Review | 69341045.82 | 18254467.11 | 18254467.11 | 50797296.22 | 289282.49 | 0 | 0 | 0 | 119896.91 | 119896.91 | 7/15/2025 - Field EHP: (ESA) Consultation letter submitted to (USFWS) on 05/29/2025. Waiting for response. (Updated ECD to 08/08/2025). | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 6 (Ponce).
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending Applicant Project Review | 81038211 | 21333819.52 | 21333819.52 | 59366309.82 | 338081.66 | 0 | 0 | 0 | 45858.06 | 45858.06 | 7/15/2025 - Field EHP: ESA Consultation letter submitted to USFWS on 05/29/2025. Waiting for response. ECD 7/28/2025. | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 3 (Bayamon).
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending Applicant Project Review | 124213686.46 | 32703357.23 | 32703357.23 | 90995446.51 | 514882.72 | 0 | 0 | 0 | 14236.87 | 14236.87 | 7/15/2025 - Field EHP - Environmental: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/12/2025. | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 4 (Caguas).
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending Applicant Project Review | 65590799.69 | 17267191.18 | 17267191.18 | 48049971.59 | 273636.92 | 0 | 0 | 0 | 49339.51 | 49339.51 | 7/15/2025 - Field EHP: ESA and CBRA Consultation letter submitted to USFWS on 06/05/2025. Waiting for response. ECD 08/19/2025 | Project is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 2 (Arecibo).
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending Applicant Project Review | 60147477.28 | 15900537.4 | 15900537.4 | 44246939.88 | 251979.26 | 0 | 0 | 0 | 47093.44 | 47093.44 | 7/15/2025 -Field EHP: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/19/2025. | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 5 (Mayaguez).
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Phase 2 | Substation | Substation | Obligated | 5907319.61 | 3751193.63 | 3751193.63 |  | 1741264.87 | 414861.11 | 0 | 0 | 0 | 0 | Field EHP - Environmental: In review. Amended Expected Completion Date (07/25/2025) | Factor Sectionalizer has two 38/13.2kV transformers, but one is out of service. The purpose of this project is to stabilize the distribution and transmission grids around the Factor Sectionalizer by replacing the out-of-service transformer.
746309 | FAASt [Automation Program Group 30] (Distribution) | Phase 2 | Distribution | Automation | Pending Award | 668110 | 425975.74 |  |  |  |  | 32095.77 | 127306.1083 | 0 | 159401.8783 | On 7/14/2025 Project moved to FEMA 406 HMP completion. | Deployment of grid automation technologies in feeders.
757662 | FAASt [Automation Program Group 21] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending Award | 2216560 | 1710547.94 | 1710547.94 | 0 | 280516.59 | 512796.48 | 117212.72 | 393808.7079 | 813.32 | 511834.7479 | On 7/15/2025 Project moived to FEMA Final Review. | Deployment of grid automation technologies in feeders.
757694 | FAASt [Automation Program Group 27] (Distribution) | Priority | 428 Distribution Automation | Automation | Obligated | 3271077 | 2314733.78 | 2314733.78 | 0 | 419922.13 | 977936.96 | 103662.78 | 594955.7558 | 641.46 | 699259.9958 | On 7/7/2025 Project moved to Final FEMA Review. | Deployment of grid automation technologies in feeders.
757698 | FAASt [Automation Program Group 33] (Distribution) | Priority | 428 Distribution Automation | Automation | Obligated | 2250901 | 1888928.21 | 1888928.21 | 0 | 311582.64 | 594117.44 | 52619.47 | 448371.606 | 293.55 | 501284.626 | On 7/7/2025 Project moved to Final FEMA Review. | Deployment of grid automation technologies in feeders.
757699 | FAASt [Automation Program Group 34] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending PDMG Project Review | 3507467 | 2755938.99 | 2755938.99 | 0 | 462362.68 | 683789.12 | 174934.21 | 514020.5748 | 1835.85 | 690790.6348 | EHP - Initial review. ECD 6/24/2025. 2nd System Glitch: Project waiting to system glitch to make corrections to project facility description. | Deployment of grid automation technologies in feeders.
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Phase 2 | Substation | Substation | Obligated | 1250845.76 | 1108989.51 | 1108989.51 |  | 141856.25 |  | 0 | 0 | 0 | 0 | "7/15/2025- (Stabilization Projects) Project created as part of the Stabilization Projects. Applicant upload DSOW with corrections. -Process Step: Pending Insurance Completion
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Priority | Vieques and Culebra Projects (6) | Transmission | Pending Scope & Cost Completion by Applicant | 122806969.07 | 83734340.49 | 83734340.49 | 33182392.65 | 5890235.93 |  | 4695185.39 | 182727.638 | 27774.97 | 4905687.998 | 7/8/2024 - The Version 0 Boring Plan Evaluation was Completed as of June23, 2023. 6/9/2025 - The 4th HM RFI was submitted to the Applicant for their action. New Deadline is established by the Applicant for 6/26/2025." | Repair/Replace insulators, guy wires; anchors, structure connections, structure foundations or portions of the foundations; ground of the structure and overhead ground conductor; communications associated with the transmission line; conductor spans, bird caged, pitting, burns, kinks, or stretched conductor; and/or drag dampers, armor rods; and other hardware.
751655 | FAASt [Vieques Microgrid] (Transmission) | Priority | Vieques and Culebra Projects (6) | Microgrid | Pending Scope & Cost Completion by Applicant | 105481956 | 0 | 0 | 105481956 |  |  | 56150.07 | 383831.1974 | 0 | 439981.2674 | "6/27/2025 - Pending form Applicant to submit the DSOW with all the necessary information. Also, 1st HM RFI was submitted to the applicant on September 13, 2024, for their action. The initial strategy for both projects was submitted on July 19, 2024. Subsequently, the first mitigation RFI was issued on September 13, 2024, with a deadline of September 27, 2024. Since then, FEMA has not received any further information.As noted, the applicant has now proposed a new deadline of April 24, 2025. FOllow up email sent on 4/8/2025. -Applicant forecast date:7/24/2025." | Construct a new microgrid system to provide resiliency, power quality, energy redundancy, stand-alone and black start capabilities to the island of Vieques. | Projects were included in the Consolidated Plan with the condition that as establihsed by FEMA, funding will be through 406 Funds
751656 | FAASt [Culebra Microgrid] (Transmission) | Priority | Vieques and Culebra Projects (6) | Microgrid | Pending Scope & Cost Completion by Applicant | 39954081 | 0 | 0 | 39954081 |  |  | 30728.97 | 137248 | 0 | 167976.97 | "6/27/2025 - Pending form Applicant to submit the DSOW with all the necessary information. Also, 1st HM RFI was submitted to the applicant on September 13, 2024, for their action. The initial strategy for both projects was submitted on July 19, 2024. Subsequently, the first mitigation RFI was issued on September 13, 2024, with a deadline of September 27, 2024. Since then, FEMA has not received any further information.As noted, the applicant has now proposed a new deadline of April 24, 2025. FOllow up email sent on 4/8/2025. -Applicant forecast date:7/24/2025." | Construct a new microgrid system to provide resiliency, power quality, energy redundancy, stand-alone and black start capabilities to the island of Culebra. | Projects were included in the Consolidated Plan with the condition that as establihsed by FEMA, funding will be through 406 Funds
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Large Project Review | 16033618.38 | 13148929.44 | 13148929.44 | 55895.84 | 2828793.1 |  | 1217780.55 | 0 | 244332.31 | 1462112.86 | HM ph2 RFI sent on 7/7/2025 | Atalaya, El Gato, Isabela Plata 1, La Santa, and Manatí TC boring & self-supported tower.
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Phase 2 | Telecommunication |  | Pending PDMG Scope & Cost Routing | 34875800.66 | 14142413.06 | 14142413.06 | 3014559.92 | 3576414.62 |  | 967053.02 | 0 | 1656.83 | 968709.85 | DSOW was submitted to FEMA on 7/25
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Priority | Vieques and Culebra Projects (6) | Substation | Pending Scope & Cost Completion by Applicant | 16374033.72 | 13495526.25 | 14704637.25 | 178309 | 1491087.47 | 0 | 2036500.58 | 191887.6 | 141042.85 | 2369431.03 | Still Pending Scope and Cost by LUMA | N/A | Repair and replacement of the control house, building waterproofing, protection & control features, auxiliary equipment, 38 kV circuit breaker & steel structure, foundations, conduit, control cables, batteries, lights, grounding, finish grade, perimeter fence and other components to restore functionality.
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending PDMG Scope & Cost Routing | 131169274 | 115638378 | 115638378 | 15530896 |  |  | 9250102.31 | 0 | 477754.67 | 9727856.98 | The formulation of this project will depend on the resulution or modification of the actual Environmental & Historic Preservation(EHP) determination. Project formualtion process needs to be revised. If no corrections are executed, Project to be removed from the FAAST Consolidated Plan List | Relocation of existing Operations teams and equipment, as well as the removal / relocation of electrical infrastructure from the Monacillos campus. The project has three areas of scope. The scope of work description is organized by the area of work. The three areas include (1) the Guaynabo ESC building rehabilitation in Guaynabo, (2) the Durotex Building rehabilitation on the Monacillos campus, (3) and the new PCC building construction / site improvements on the Monacillos campus. | The formulation of this project will depend on the resulution or modification of the actual Environmental & Historic Preservation(EHP) determination. Project formualtion process needs to be revised. If no corrections are executed, Project to be removed from the FAAST Consolidated Plan List
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | 16713944.15 | 15096658.56 | 15096658.56 | 1617375.6 | N/A | N/A | 2255799.45 | 0 | 30058.15 | 2285857.6 | LUMA submitted DSOW/LPCE on 05.07.2025. Project is under FEMA HM review with an RFI related to 428/406 scope and cost splits. Current deadline for RFI is 08.26.2025. Luma agreed to complete request by July 31,2025. If RFI response is not completed, Project to be removed form FFAST Consolidated List | Increase protection and Control System that protect the electrical components such as Transmission Lines, Transformers, Bus Bar, Breakers, etc | Luma agreed to complete request by July 31,2025. If RFI response is not completed or the response doesn't suffice FEMA request, Project to be removed from the FAAST Consolidated Plan List
[7 empty] | 1380565150.75 | *Amount is subject to change due to FEMA Validation Analysis. Costs presented herein are based on scope of work developed by LUMA

## LUMA's Inactive Projects
Item | Project # | Title | FEMA Allocation | Asset | Project Status | DSOW was submitted to FEMA? | Date DSOW was submitted to FEMA? | Estimated A&E Cost Incurred | Estimated E&M Cost Incurred | Other Cost Incurred | Total Estimate Incurred Cost | Is PW included in the Priority Stabilization Plan? | Additional comments
1 | 727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 73.42 | 0 | 38256.04 | 38329.46 | Yes
2 | 724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 651946.92 | 0 | 4529.61 | 656476.53 | No
3 | 724828 | FAASt [Loiza Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 312602.26 | 0 | 1133540.07 | 1446142.33 | No | Includes Work Completed
4 | 724781 | FAASt [Penuelas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 279875.5 | 0 | 3359.76 | 283235.26 | No
5 | 724716 | FAASt [Quebradillas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 369806.37 | 0 | 9160.84 | 378967.21 | No
6 | 724670 | FAASt [Patillas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 312699.26 | 0 | 4239.71 | 316938.97 | No
7 | 724669 | FAASt [Ciales Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 427398.31 | 0 | 5187.38 | 432585.69 | No
8 | 724605 | FAASt [Guayanilla Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 543528.13 | 0 | 5932.84 | 549460.97 | No
9 | 724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 565636.49 | 0 | 1831023.24 | 2396659.73 | No | Includes Work Completed
10 | 724599 | FAASt [Sabana Grande Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 472883.44 | 0 | 3708.63 | 476592.07 | No
11 | 718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3136106.46 | 0 | 102391.27 | 3238497.73 | No
12 | 718955 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2099429.08 | 0 | 64311.62 | 2163740.7 | No
13 | 718951 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1322132.33 | 0 | 31755.4 | 1353887.73 | No
14 | 715610 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 0 | 26514.9 | 0 | 26514.9 | No
15 | 713795 | FAASt [Lares Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 320287.03 | 0 | 8878.15 | 329165.18 | No
16 | 705657 | FAASt [Automation Program Group 3] (TL/Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 4787279.92 | 7291.5844 | 14022874.48 | 18817445.9844 | No | Includes Work Completed
17 | 705503 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 86247.26 | 0 | 201490.02 | 287737.28 | No
18 | 704931 | FAASt [Camuy Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 704757.7 | 0 | 2127836.67 | 2832594.37 | No | Includes Work Completed
19 | 704929 | FAASt [San Lorenzo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 684564.35 | 0 | 1045452.1 | 1730016.45 | No | Includes Work Completed
20 | 704862 | FAASt [Fajardo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 597812.07 | 0 | 2129118.43 | 2726930.5 | No | Includes Work Completed
21 | 704793 | FAASt [Yauco Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 664346.69 | 0 | 2913727.16 | 3578073.85 | No | Includes Work Completed
22 | 704757 | FAASt [Santa Isabel Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 384802.43 | 0 | 2232814.52 | 2617616.95 | No | Includes Work Completed
23 | 704744 | FAASt [San Sebastian Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 754342.03 | 0 | 2721453.75 | 3475795.78 | No | Includes Work Completed
24 | 704741 | FAASt [Moca Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 563643.62 | 0 | 5430.15 | 569073.77 | No
25 | 701473 | FAASt [Canovanas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 535383.63 | 0 | 1615651.85 | 2151035.48 | No | Includes Work Completed
26 | 699814 | FAASt [Juana Diaz Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 617773.72 | 0 | 2240078.89 | 2857852.61 | No | Includes Work Completed
27 | 698522 | FAASt [Vieques Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 228080.82 | 0 | 1004763.81 | 1232844.63 | No | Includes Work Completed
28 | 698432 | FAASt [Hormigueros Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 366766.64 | 0 | 905135.06 | 1271901.7 | No | Includes Work Completed
29 | 698427 | FAASt [Maricao Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 181912.82 | 0 | 511210.78 | 693123.6 | No | Includes Work Completed
30 | 697183 | FAASt [Vega Baja Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 323918.02 | 0 | 1266013.74 | 1589931.76 | No | Includes Work Completed
31 | 693788 | FAASt [Toa Alta Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 398835.84 | 0 | 1432807.09 | 1831642.93 | No | Includes Work Completed
32 | 693615 | FAASt [Rio Grande Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 327961.04 | 0 | 633015.94 | 960976.98 | No | Includes Work Completed
33 | 693543 | FAASt [Juncos Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 496914.61 | 0 | 1638293.83 | 2135208.44 | No | Includes Work Completed
34 | 690721 | FAASt [Guayama Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 369654.84 | 0 | 1207346.17 | 1577001.01 | No | Includes Work Completed
35 | 690483 | FAASt [Cayey Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 750424.25 | 0 | 2230229.35 | 2980653.6 | No | Includes Work Completed
36 | 690480 | FAASt [Humacao Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 364243.46 | 0 | 839448.25 | 1203691.71 | No | Includes Work Completed
37 | 688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 1113619.27 | 381308.9303 | 1082773.67 | 2577701.8703 | No | Includes Work Completed
38 | 686482 | FAASt [Isabela Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 335755.45 | 0 | 753235.29 | 1088990.74 | No | Includes Work Completed
39 | 685869 | FAASt [Mayagüez TC] (Substation) |  | Substation | Inactive | No |  | 1498455.38 | 1324498.9 | 94654.81 | 2917609.09 | No
40 | 679006 | FAASt [Test and Technology Laboratory] (Building) |  | Building | Inactive | Yes | #REF! | 747339.67 | 0 | 70121.49 | 817461.16 | No
41 | 678795 | FAASt [Arecibo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 767004.91 | 0 | 1934700.14 | 2701705.05 | No | Includes Work Completed
42 | 678794 | FAASt [Ponce Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 765473.52 | 0 | 2684972.1 | 3450445.62 | No | Includes Work Completed
43 | 675345 | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) |  | Telecommunications | Inactive | Yes | #REF! | 0 | 0 | 0 | 0 | No
44 | 671400 | FAASt [Barceloneta Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 524140.74 | 0 | 1356777.25 | 1880917.99 | No | Includes Work Completed
45 | 671396 | FAASt [Utuado Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 772706.37 | 0 | 1827017.56 | 2599723.93 | No | Includes Work Completed
46 | 668665 | FAASt [Cybersecurity Program Implementation] (Telecommunication) |  | Telecommunications | Inactive | Yes | #REF! | 1.53 | 0 | 0.27 | 1.8 | No
47 | 666894 | FAASt [San Juan Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 2499986.19 | 0 | 6779878.71 | 9279864.9 | No | Includes Work Completed
48 | 551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) |  | Substation | Inactive | Yes | #REF! | 1001723.4 | 0 | 171414.24 | 1173137.64 | No
49 | 551918 | FAASt [Crematorio - 1512] (Substation) |  | Substation | Inactive | Yes | #REF! | 929559.92 | 0 | 42289.23 | 971849.15 | No
50 | 551912 | FAASt [Puerto Nuevo - 1520] (Substation) |  | Substation | Inactive | Yes | #REF! | 874727.96 | 0 | 41567.14 | 916295.1 | Yes
51 | 551911 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) |  | Transmission | Inactive | No |  | 1300502.63 | 26514.9 | 56415.86 | 1383433.39 | No
52 | 551260 | FAASt [Guaynabo Pueblo Substation] (Substation) |  | Substation | Inactive | Yes | #REF! | 1033630.56 | 1022889.52 | 34879.82 | 2091399.9 | No
53 | 551247 | FAASt [Palo Seco South Building Repairs] (Building) |  | Building | Inactive | No |  | 859793.52 | 0 | 35673.15 | 895466.67 | No
54 | 551067 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) |  | Transmission | Inactive | No |  | 1413859.02 | 1100357.8182 | 26664.26 | 2540881.0982 | No
55 | 550986 | FAASt [Condado - 1133] (Substation) |  | Substation | Inactive | Yes | #REF! | 1021451.58 | 0 | 42118.98 | 1063570.56 | Yes
56 | 550980 | FAASt [Parques y Recreos - 1002] (Substation) |  | Substation | Inactive | Yes | #REF! | 894655.2 | 0 | 20004.28 | 914659.48 | Yes
57 | 550902 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) |  | Transmission | Inactive | No |  | 1064893.34 | 39772.35 | 20412.45 | 1125078.14 | No
58 | 550894 | FAASt [Baldrich - 1422] (Substation) |  | Substation | Inactive | Yes | #REF! | 934456.18 | 0 | 11439.36 | 945895.54 | Yes
59 | 550498 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) |  | Substation | Inactive | No |  | 126915.84 | 0 | 68529.59 | 195445.43 | No
60 | 550162 | FAASt [Berwind TC - 1336] (Substation) |  | Substation | Inactive | Yes | #REF! | 1447385.34 | 0 | 51252.49 | 1498637.83 | No
61 | 550099 | FAASt [Esc. Industrial M. Such - 1423] (Substation) |  | Substation | Inactive | Yes | #REF! | 691038.79 | 0 | 43921.94 | 734960.73 | Yes
62 | 550019 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 945634.82 | 0 | 39185.68 | 984820.5 | No
63 | 548598 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1082636.93 | 0 | 68164.84 | 1150801.77 | No
64 | 547350 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) |  | Transmission | Inactive | No |  | 1521473.79 | 0 | 8371.81 | 1529845.6 | No
65 | 547344 | FAASt [Acacias 6801 TC Relocation] (Substation) |  | Substation | Inactive | Yes | #REF! | 1625433.19 | 898630 | 60220.95 | 2584284.14 | No
66 | 547343 | FAASt [Victoria TC 7008 Relocation] (Substation) |  | Substation | Inactive | Yes | #REF! | 2508826.39 | 0 | 434647.36 | 2943473.75 | No
67 | 547273 | FAASt Charco Hondo Substation 8008 Relocation (Substation) |  | Substation | Inactive | No |  | 613309.81 | 0 | 23662.68 | 636972.49 | No
68 | 547269 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1279409.56 | 0 | 89512.15 | 1368921.71 | No
69 | 547259 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1616166.57 | 0 | 140659.68 | 1756826.25 | No
70 | 547247 | FAASt Cambalache TC Relocation (Substation) |  | Substation | Inactive | Yes | #REF! | 3815420.63 | 604250 | 79715.36 | 4499385.99 | Yes
71 | 547243 | FAASt Egozcue - 1109 (Substation) |  | Substation | Inactive | Yes | #REF! | 1128223.69 | 723116.82 | 23670.42 | 1875010.93 | No
72 | 547241 | FAASt Tallaboa 5402 (Substation) |  | Substation | Inactive | Yes | #REF! | 922655.66 | 198861.75 | 72711.6 | 1194229.01 | No
73 | 547226 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) |  | Transmission | Inactive | No |  | 985966.86 | 0 | 22411.86 | 1008378.72 | No
74 | 547160 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) |  | Transmission | Inactive | No |  | 3732057.59 | 0 | 97223.32 | 3829280.91 | No
75 | 546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1609417.88 | 0 | 31225.13 | 1640643.01 | No
76 | 546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2485192.97 | 0 | 78308.39 | 2563501.36 | No
77 | 436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2562116.59 | 296945.8291 | 190901.94 | 3049964.3591 | No
78 | 334518 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 817708.4 | 191915.5987 | 27139.53 | 1036763.5287 | No
79 | 334497 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 3284447.24 | 80776.2262 | 332656.49 | 3697879.9562 | No
80 | 334491 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 749293.91 | 0 | 168615.61 | 917909.52 | No
81 | 334477 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 572777.57 | 831634.261 | 14383.79 | 1418795.621 | No
82 | 334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2094612.85 | 193322.6327 | 62071.2 | 2350006.6827 | No
83 | 334475 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2117849.36 | 471736.6618 | 113559.71 | 2703145.7318 | No
84 | 334474 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 420575.65 | 0 | 41060.71 | 461636.36 | No
85 | 334473 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 931456.09 | 37063.6 | 90278.79 | 1058798.48 | No
86 | 334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2815475.62 | 958532.3149 | 83104.83 | 3857112.7649 | No
87 | 334471 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 539799.34 | 127943.7325 | 7576.78 | 675319.8525 | No
88 | 334452 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1105038.15 | 351845.2643 | 84910.57 | 1541793.9843 | No
89 | 334443 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 3918554.07 | 372411.7382 | 153418.7 | 4444384.5082 | No
90 | 334420 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2466044.98 | 792484.0911 | 92445.64 | 3350974.7111 | No
91 | 334331 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3373474.81 | 0 | 451250.44 | 3824725.25 | No
92 | 334308 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1708578.2 | 0 | 94679.16 | 1803257.36 | No
93 | 334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 4868204.67 | 619697.5703 | 274204.5 | 5762106.7403 | No
94 | 334285 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 3970385.77 | 531797.2057 | 117889.93 | 4620072.9057 | No
95 | 334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 5717025.17 | 3863896.9283 | 108889.99 | 9689812.0883 | No
96 | 180326 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2738961.97 | 0 | 197639.44 | 2936601.41 | No
97 | 177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1860551.68 | 0 | 486694.87 | 2347246.55 | No
98 | 177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2825116.95 | 0 | 155611.14 | 2980728.09 | No
99 | 176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) |  | Transmission | Inactive | Yes | #REF! | 803736.24 | 0 | 164175.64 | 967911.88 | No
100 | 167508 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1487923.99 | 0 | 27464.43 | 1515388.42 | No
101 | 167443 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1946817.06 | 0 | 107036.18 | 2053853.24 | No
102 | 167168 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3713271.18 | 0 | 106074.99 | 3819346.17 | No
103 | 166904 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) |  | Transmission | Inactive | Yes | #REF! | 1701248.61 | 0 | 174713.68 | 1875962.29 | No
104 | 166860 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3529391.09 | 0 | 55770.17 | 3585161.26 | No
105 | 166707 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2885457.37 | 0 | 668485.68 | 3553943.05 | No
106 | 730821 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2015105.41 | 167040.7236 | 83429.02 | 2265575.1536 | No
107 | 730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2432367.96 | 0 | 32196.37 | 2464564.33 | No
108 | 730513 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 823250.66 | 0 | 4473.25 | 827723.91 | No
109 | 730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2328548.5 | 216619.9383 | 78239.56 | 2623407.9983 | No
110 | 730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2385628.07 | 20375.2655 | 94994.92 | 2500998.2555 | No
111 | 730657 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) |  | Transmission | Inactive | No |  | 9142055.58 | 0 | 110975.62 | 9253031.2 | No
112 | 738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 377477.04 | 0 | 9701.73 | 387178.77 | No
113 | 738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 137975.62 | 11119.08 | 11329.66 | 160424.36 | No
114 | 738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 57166.28 | 0 | 9719.02 | 66885.3 | No
115 | 734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 364960.59 | 0 | 3471.55 | 368432.14 | No
116 | 734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 270658.3 | 0 | 8748.7 | 279407 | No
117 | 735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 253410.27 | 0 | 11658.84 | 265069.11 | No
118 | 734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 691037.11 | 0 | 9952.94 | 700990.05 | No
119 | 735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 671635.88 | 0 | 262763.16 | 934399.04 | No
120 | 734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 572254.77 | 0 | 3733 | 575987.77 | No
121 | 735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 328248.22 | 0 | 2071.71 | 330319.93 | No
122 | 734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 314304.66 | 0 | 10808.57 | 325113.23 | No
123 | 734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 304601.84 | 0 | 2371.66 | 306973.5 | No
124 | 735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 273446.16 | 0 | 8558.92 | 282005.08 | No
125 | 734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 424480.22 | 0 | 7121.24 | 431601.46 | No
126 | 735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 321233.51 | 0 | 3596.94 | 324830.45 | No
127 | 734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 277617.77 | 0 | 7596.94 | 285214.71 | No
128 | 735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 668286.36 | 0 | 16505.22 | 684791.58 | No
129 | 735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 358119.53 | 0 | 17166.9 | 375286.43 | No
130 | 735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 789946.93 | 0 | 5475.82 | 795422.75 | No
131 | 735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 746347.26 | 0 | 6288.06 | 752635.32 | No
132 | 735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 348065.75 | 0 | 36726.09 | 384791.84 | No
133 | 735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 304376.42 | 0 | 9074.69 | 313451.11 | No
134 | 735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 357078.1 | 0 | 12507.41 | 369585.51 | No
135 | 735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 244352.23 | 0 | 6105.95 | 250458.18 | No
136 | 735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 286913.59 | 0 | 13577.42 | 300491.01 | No
137 | 735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 305288.21 | 0 | 6496.32 | 311784.53 | No
138 | 737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 213368.24 | 0 | 7769.11 | 221137.35 | No
139 | 737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 350733.15 | 0 | 13839.46 | 364572.61 | No
140 | 737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 1098114.69 | 0 | 5171.84 | 1103286.53 | No
141 | 737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 230006.04 | 0 | 9087.61 | 239093.65 | No
142 | 737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 274947.63 | 0 | 3609.94 | 278557.57 | No
143 | 735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 497360.7 | 0 | 5734.08 | 503094.78 | No
144 | 734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 558092.62 | 0 | 11937.43 | 570030.05 | No
145 | 734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 290922.13 | 0 | 7232.9 | 298155.03 | No
146 | 735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 693761.38 | 0 | 11729.21 | 705490.59 | No
147 | 735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 692749.72 | 0 | 10725.02 | 703474.74 | No
148 | 735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 300143.9 | 0 | 13477.82 | 313621.72 | No
149 | 738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 699102.04 | 0 | 72636.86 | 771738.9 | Yes
150 | 740406 | FAASt [Region 1-San Juan Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 92.31 | 0 | 14456.27 | 14548.58 | Yes
151 | 740408 | FAASt [Region 3-Bayamon Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 28.58 | 0 | 4197.38 | 4225.96 | Yes
152 | 740409 | FAASt [Region 4-Caguas Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 1.819e-12 | 0 | 8084.15 | 8084.15 | Yes
153 | 740410 | FAASt [Region 2-Arecibo Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 4.5475e-13 | 0 | 8296.79 | 8296.79 | Yes
154 | 740411 | FAASt [Region 5-Mayaguez Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 9.0949e-13 | 0 | 5962.2 | 5962.2 | Yes
155 | 740414 | FAASt [Region 6-Ponce Group B] High Density (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | -216.88 | 0 | 7780.43 | 7563.55 | Yes
156 | 740662 | FAASt [Automation Program Group 2] (TL/ Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 6969935.9 | 0 | 16219867.09 | 23189802.99 | No | Includes Work Completed
157 | 741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 9.0949e-13 | 0 | 8787.49 | 8787.49 | Yes
158 | 745854 | FAASt [ Automation Program Group 9] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 65312.07 | 118359.1407 | 1215.31 | 184886.5207 | No
159 | 745871 | FAASt [Automation Program Group 10] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 0 | 290967.3491 | 0 | 290967.3491 | No
160 | 745851 | FAASt [Automation Program Group 11] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 52762.1 | 201844.4227 | 829.93 | 255436.4527 | No
161 | 745852 | FAASt [Automation Program Group 13] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 0 | 837283.816 | 0 | 837283.816 | No
162 | 741678 | FAASt [Automation Program Group 4] (TL/Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 5490227.99 | 1765011.9281 | 14921572.96 | 22176812.8781 | No | Includes Work Completed
163 | 744072 | FAASt [IT OT Technology Systems Reparations] Group 2 (Telecommunication) |  | Telecommunications | Inactive | Yes | #REF! | 0 | 0 | 0 | 0 | Yes
164 | 746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 820059.08 | 0 | 4139.83 | 824198.91 | No
165 | 746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 504585.9 | 0 | 3703.07 | 508288.97 | No
166 | 748180 | FAASt [Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC)] (Telecommunication) |  | Grid Modernization | Inactive | Yes | #REF! | 458759.67 | 0 | 119714.78 | 578474.45 | Yes
167 | 750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 727189.77 | 106059.6 | 84267.7 | 917517.07 | Yes
168 | 750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 740551.14 | 79544.7 | 113250.67 | 933346.51 | Yes
169 | 750730 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) |  | Transmission | Inactive | No |  | 2645964.16 | 0 | 57509.11 | 2703473.27 | No
170 | 752052 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) |  | Transmission | Inactive | No |  | 815006.65 | 0 | 40075.35 | 855082 | No
171 | 752277 | FAASt [Substation Ciales 8701] (Substation) |  | Substation | Inactive | Yes | #REF! | 419830.42 | 0 | 16607.05 | 436437.47 | No
172 | 752276 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) |  | Substation | Inactive | No |  | 699860.15 | 557718.26 | 73612.09 | 1331190.5 | No
173 | 752275 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) |  | Substation | Inactive | No |  | 742932.1 | 0 | 63265.84 | 806197.94 | No
174 | 752500 | FAASt [Automation Program Group 1B-6 Feeders] (Distribution) |  | Grid Automation | Inactive | No |  | 744990.84 | 139695.5176 | 1605282.86 | 2489969.2176 | No | Includes Work Completed
175 | 752502 | FAASt [Automation Program Group 1C-7 Feeders] (Distribution) |  | Grid Automation | Inactive | No |  | 1058497.11 | 340359.5987 | 1058114.52 | 2456971.2287 | No | Includes Work Completed
176 | 752503 | FAASt [Automation Program Group 1D-7 Feeders] (Distribution) |  | Grid Automation | Inactive | No |  | 1124553.03 | 50309.8182 | 3443551.68 | 4618414.5282 | No | Includes Work Completed
177 | 752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 728229.81 | 79544.7 | 69630.44 | 877404.95 | Yes
178 | 753302 | FAASt [Telecom Infrastructure Group G] (Telecommunication) |  | Telecommunications | Inactive | No |  | 19771.47 | 0 | 9534.67 | 29306.14 | No
179 | 753788 | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 266480.89 | 0 | 11898.74 | 278379.63 | No
180 | 753787 | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 42672.97 | 0 | 4423.26 | 47096.23 | No
181 | 753786 | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 78163.5 | 0 | 8904.48 | 87067.98 | No
182 | 753785 | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 12461.09 | 0 | 14841.31 | 27302.4 | Yes
183 | 753781 | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 331670.13 | 0 | 14773.53 | 346443.66 | Yes
184 | 753777 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) |  | Transmission | Inactive | No |  | 4211801.41 | 0 | 57120.95 | 4268922.36 | No
185 | 754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) |  | Distribution – Underground | Inactive | Yes | #REF! | 567000.45 | 0 | 155562.85 | 722563.3 | No
186 | 754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) |  | Distribution – Underground | Inactive | Yes | #REF! | 667130.1 | 0 | 163703.39 | 830833.49 | No
187 | 800369 | FAASt [Automation Program Group 38] (Distribution) |  | Grid Automation | Inactive | No |  | 61845.16 | 279038.2036 | 6823.21 | 347706.5736 | No
188 | 800394 | FAASt [Automation Program Group 39] (Distribution) |  | Grid Automation | Inactive | No |  | 89687.2 | 285030.5685 | 9958.04 | 384675.8085 | No
189 | 800399 | FAASt [Automation Program Group 40] (Distribution) |  | Grid Automation | Inactive | No |  | 218712.06 | 590462.1371 | 9950.63 | 819124.8271 | No
190 | 757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 53378.86 | 0 | 6658.57 | 60037.43 | No
191 | 759051 | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) |  | Distribution | Inactive | No |  | 30058.16 | 0 | 10722.37 | 40780.53 | No
192 | 759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) |  | Distribution | Inactive | No |  | 81705.29 | 0 | 56028.17 | 137733.46 | No
193 | 761563 | FAASt [San Jose Relocation] (Substation) |  | Substation | Inactive | No |  | 662865.05 | 0 | 13450.81 | 676315.86 | No
194 | 811923 | FAASt [Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) |  | Transmission – Pole Replacement | Inactive | Yes | #REF! | 51079.42 | 0 | 15787.34 | 66866.76 | No
195 | 811913 | FAASt [Transmission Priority Pole Replacement Program Line 9600 Bayamon TC – Catano Sect] (Transmission) |  | Transmission – Pole Replacement | Inactive | Yes | #REF! | 33407.6 | 0 | 8978.4 | 42386 | No
196 | 805521 | FAASt [38kV Recloser TL 7800 Dorado TC to Vega Alta Sect.] (Transmission) |  | Transmission – Pole Replacement | Inactive | Yes | #REF! | 142174.45 | 64775.2 | 15034.64 | 221984.29 | No
197 | 801432 | FAASt [Automation Program Group 41] (Distribution) |  | Grid Automation | Inactive | No |  | 45668.3 | 571816.0095 | 1347.82 | 618832.1295 | No
198 | 801437 | FAASt [Automation Program Group 42] (Distribution) |  | Grid Automation | Inactive | No |  | 19879.2 | 201413.4785 | 3224.35 | 224517.0285 | No
199 | 801438 | FAASt [Automation Program Group 43] (Distribution) |  | Grid Automation | Inactive | No |  | 75315.28 | 329467.884 | 2482.77 | 407265.934 | No
200 | 801440 | FAASt [Automation Program Group 44] (Distribution) |  | Grid Automation | Inactive | No |  | 39944.71 | 228127.4774 | 2752.72 | 270824.9074 | No
201 | 801441 | FAASt [Automation Program Group 45] (Distribution |  | Grid Automation | Inactive | No |  | 38926.6 | 479180.0277 | 1467.61 | 519574.2377 | No
202 | 806935 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 14869.09 | 0 | 9379.3 | 24248.39 | No
203 | 806936 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 200585.92 | 0 | 6803.91 | 207389.83 | No
204 | 805519 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 101897.17 | 77960.2547 | 17772.02 | 197629.4447 | No
205 | 805517 | FAASt [38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect.] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 110178.42 | 69170.2182 | 21463.67 | 200812.3082 | No
206 | 790427 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) |  | Distribution | Inactive | Yes | #REF! | 608897.76 | 0 | 8524.87 | 617422.63 | No
207 | 790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) |  | Distribution | Inactive | Yes | #REF! | 112030.52 | 0 | 9397.13 | 121427.65 | No
208 | 812041 | FAASt [Distribution Feeder Rebuild 9501-02] |  | Distribution | Inactive | Yes | #REF! | 1336858.37 | 226284 | 76362.85 | 1639505.22 | No
209 | 814792 | FAASt [Telecom Infrastructure – Group E] |  | Telecommunications | Inactive | No |  | 562641.94 | 0 | 113659.6 | 676301.54 | No
210 | 814793 | FAASt [Telecom Infrastructure – Group F] |  | Telecommunications | Inactive | No |  | 464395.59 | 0 | 87687.56 | 552083.15 | No
211 | 817961 | FAASt [Feeder Rebuild # 2404-06] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1213724.13 | 0 | 33726.8 | 1247450.93 | No
212 | 818006 | FAASt [Feeder Rebuild #2402-02] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1497224.17 | 0 | 61748.27 | 1558972.44 | No
213 | 817993 | FAASt [Feeder Rebuild # 1801-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1135718.34 | 0 | 64565.73 | 1200284.07 | No
214 | 818056 | FAASt [Feeder Rebuild # 6305-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1635991.21 | 667144.8 | 50902.28 | 2354038.29 | No
215 | 818055 | FAASt [Feeder Rebuild # 3006-05] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1702257.95 | 48534.08 | 352833.21 | 2103625.24 | No
216 | 818041 | FAASt [Feeder Rebuild # 3701-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1750126.44 | 507812 | 80295.93 | 2338234.37 | No
217 | 817962 | FAASt [Feeder Rebuild # 9403-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 699973.75 | 30087.9091 | 44787.96 | 774849.6191 | No
218 | 817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 181431.75 | 0 | 8030.24 | 189461.99 | No
219 | 817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 79895.01 | 0 | 6878.01 | 86773.02 | No
220 | 817247 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 289257.2 | 0 | 31827.44 | 321084.64 | No
221 | 817250 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 55326.72 | 0 | 57494.46 | 112821.18 | No
222 | 954184 | FAASt [Carolina ESC Building Repairs] (Buildings) |  | Building | Inactive | Yes | #REF! | 0 | 0 | 0 | 0 | No
223 | 956782 | Feeder Rebuild #6802-04 (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1544468.19 | 51889.04 | 30020.13 | 1626377.36 | No
224 | 958367 | FAASt [Feeder Rebuild #6603-01] (Distribution) |  | Distribution | Inactive | Yes | #REF! | 1663612.58 | 111190.8 | 85949.86 | 1860753.24 | No

## Additional Inactive Projects
Item | Project # | Title | FEMA Allocation | Asset | Project Status | DSOW was submitted to FEMA? | Estimated A&E Cost Incurred | Estimated E&M Cost Incurred | Other Cost Incurred | Total Estimate Incurred Cost | Is PW included in the Priority Stabilization Plan?
1 | 801197 | FAASt [Feeder Rebuild # 1204-02] (Distribution) |  | Distribution | Inactive | No | 2103499.01 | 0 | 151842.26 | 2255341.27 | No
2 | 767387 | FAASt [Feeder Rebuild # 1303-01] (Distribution) |  | Distribution | Inactive | No | 1179308.99 | 0 | 28901.55 | 1208210.54 | No
3 | 767381 | FAASt [Feeder Rebuild # 1204-04] (Distribution) |  | Distribution | Inactive | No | 1309560.99 | 0 | 38539.49 | 1348100.48 | No
4 | 767139 | FAASt [Feeder Rebuild # 2906-02] (Distribution) |  | Distribution | Inactive | No | 1123715.04 | 0 | 82872.58 | 1206587.62 | No
5 | 767005 | FAASt [Feeder Rebuild # 1303-05] (Distribution) |  | Distribution | Inactive | No | 1743167.04 | 0 | 41233.4 | 1784400.44 | No
6 | 764709 | FAASt [Feeder Rebuild # 1204-05] (Distribution) |  | Distribution | Inactive | No | 1481296.5 | 0 | 39967.68 | 1521264.18 | No
7 | 764708 | FAASt [Feeder Rebuild # 5602-02] (Distribution) |  | Distribution | Inactive | No | 1585056.59 | 0 | 44641.15 | 1629697.74 | No
8 | 764707 | FAASt [Feeder Rebuild # 6012-02] (Distribution) |  | Distribution | Inactive | No | 2196478.75 | 0 | 665763.83 | 2862242.58 | No
9 | 764706 | FAASt [Feeder Rebuild # 7011-03] (Distribution) |  | Distribution | Inactive | No | 1262101.61 | 0 | 51644.44 | 1313746.05 | No
10 | 764705 | FAASt [Feeder Rebuild # 6014-02] (Distribution) |  | Distribution | Inactive | No | 2706956.07 | 0 | 91824.86 | 2798780.93 | No
11 | 760579 | FAASt [Feeder Rebuild # 1717-03] (Distribution) |  | Distribution | Inactive | No | 1433427.14 | 0 | 91441.86 | 1524869 | No
12 | 760577 | FAASt [Feeder Rebuild # 1718-02] (Distribution) |  | Distribution | Inactive | No | 1383289.97 | 0 | 70755.42 | 1454045.39 | No
13 | 760575 | FAASt [Feeder Rebuild # 1716-03] (Distribution) |  | Distribution | Inactive | No | 1716332.57 | 0 | 61592.88 | 1777925.45 | No
14 | 760571 | FAASt [Feeder Rebuild # 1720-07] (Distribution) |  | Distribution | Inactive | No | 2179405.45 | 0 | 81879.13 | 2261284.58 | No
15 | 760568 | FAASt [Feeder Rebuild # 1710-01] (Distribution) |  | Distribution | Inactive | No | 1441005.22 | 0 | 70032.79 | 1511038.01 | No
16 | 741104 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 4492.45 | 4492.45 | Yes
17 | 741102 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 7244.12 | 7244.12 | Yes
18 | 741101 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 6352.17 | 6352.17 | Yes
19 | 741100 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 3733.86 | 3733.86 | Yes
20 | 741098 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 8365.17 | 8365.17 | Yes
21 | 730784 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) |  | Vegetation | Inactive | No | 525765.41 | 0 | 28929.28 | 554694.69 | Yes
22 | 727694 | FAASt [Region 4 -Caguas Group C] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 6393.72 | 6393.72 | Yes
23 | 727562 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 5599.08 | 5599.08 | Yes
24 | 727558 | FAASt [Region 3 -Bayamon Group C] (Vegetation) |  | Vegetation | Inactive | Yes | 5.8 | 0 | 3245.69 | 3251.49 | Yes
25 | 727540 | FAASt [Region 2 -Arecibo Group C] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 4692.54 | 4692.54 | Yes
26 | 727530 | FAASt [Region 6 -Ponce Group C] (Vegetation) |  | Vegetation | Inactive | Yes | 0 | 0 | 5115.75 | 5115.75 | Yes
27 | 712982 | FAASt [Distribution Pole and Conductor Repair “ Mayaguez Group 23] (Distribution) |  | Distribution | Inactive | No | 661.16 | 0 | 315.14 | 976.3 | No
28 | 712981 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) |  | Distribution | Inactive | No | 2345.91 | 0 | 1326.52 | 3672.43 | No
29 | 712978 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) |  | Transmission | Inactive | No | 407363 | 0 | 54877.67 | 462240.67 | Yes
30 | 711962 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) |  | Distribution | Inactive | No | 1096.25 | 0 | 315.14 | 1411.39 | No
31 | 711862 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) |  | Transmission | Inactive | No | 85232.45 | 0 | 291.89 | 85524.34 | No
32 | 711829 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) |  | Transmission | Inactive | No | 17397.59 | 0 | 430.81 | 17828.4 | No
33 | 710498 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) |  | Distribution | Inactive | No | 3799.05 | 0 | 1299.86 | 5098.91 | No
34 | 710363 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) |  | Distribution | Inactive | No | 3294.1 | 0 | 1699.56 | 4993.66 | No
35 | 710045 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) |  | Distribution | Inactive | No | 2335.09 | 0 | 604.17 | 2939.26 | No
36 | 710026 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) |  | Distribution | Inactive | No | 5226.96 | 0 | 157.58 | 5384.54 | No
37 | 704805 | FAASt [Telecom Infrastructure Group D] (Telecommunication) |  | Telecommunication | Inactive | No | 431102.52 | 0 | 105452.23 | 536554.75 | Yes
38 | 704763 | FAASt [Telecom Infrastructure Group C] (Telecommunication) |  | Telecommunication | Inactive | No | 46180.29 | 0 | 5278.66 | 51458.95 | Yes
39 | 682331 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) |  | Telecommunication | Inactive | No | 182826.68 | 0 | 12185.42 | 195012.1 | No
40 | 679035 | FAASt [Telecom Infrastructure Group A] (Telecommunication) |  | Telecommunication | Inactive | No | 502650.4 | 0 | 120554.95 | 623205.35 | Yes
41 | 675406 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) |  | Telecommunication | Inactive | No | 501568.24 | 0 | 4411.78 | 505980.02 | No
42 | 674506 | FAASt [Field Area Network (FAN)] (Telecommunication) |  | Telecommunication | Inactive | No | 2712234.72 | 0 | 73435.5 | 2785670.22 | No
43 | 673920 | FAASt [Isla Grande 1101] (Substation) |  | Substation | Inactive | No | 38798.95 | 0 | 1453.22 | 40252.17 | No
44 | 668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) |  | Transmission | Inactive | Yes | 73848.99 | 0 | 144.3 | 73993.29 | No
45 | 551916 | FAASt [Dorado TC Relocation] (Substation) |  | Substation | Inactive | No | 125355.36 | 0 | 3247.67 | 128603.03 | Yes
46 | 551827 | FAASt [San Juan Region Repair] (Building) |  | Building | Inactive | No | 11296.69 | 0 | 5366.13 | 16662.82 | No
47 | 551242 | FAASt [Bayamon Region Repairs] (Building) |  | Building | Inactive | No | 49186.07 | 0 | 143.66 | 49329.73 | No
48 | 551100 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) |  | Substation | Inactive | No | 79538.63 | 0 | 1504.25 | 81042.88 | No
49 | 550998 | FAASt [Santurce Planta (Sect) 1116] (Substation) |  | Substation | Inactive | No | 63360 | 0 | 6182.23 | 69542.23 | No
50 | 550972 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) |  | Substation | Inactive | No | 58296.84 | 0 | 686.5 | 58983.34 | No
51 | 550771 | FAASt [Caguas TC] (Substation) |  | Substation | Inactive | No | 133373.95 | 0 | 342875.37 | 476249.32 | Yes
52 | 550500 | FAASt - Ponce Region Repairs (Building) |  | Building | Inactive | No | 28655.05 | 0 | 406.47 | 29061.52 | No
53 | 550070 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) |  | Transmission | Inactive | No | 768773.86 | 0 | 42083.67 | 810857.53 | No
54 | 550060 | FAASt [Caguas Region Repairs] (Building) |  | Building | Inactive | No | 11229.44 | 0 | 2947.02 | 14176.46 | No
55 | 549768 | FAASt Physical Security - Group 5 (Substation) |  | Substation | Inactive | No | 46923.64 | 0 | 8742.26 | 55665.9 | No
56 | 548596 | FAASt [San German Electrical Service Center] (Building) |  | Building | Inactive | No | 26808.42 | 0 | 0.27 | 26808.69 | No
57 | 548440 | FAASt [Mayaguez Region Repairs] (Building) |  | Building | Inactive | No | 14819.87 | 0 | 5833.61 | 20653.48 | No
58 | 548393 | FAASt Arecibo Region Repairs (Buildings) |  | Building | Inactive | No | 7699.92 | 0 | 41.99 | 7741.91 | No
59 | 547248 | FAASt Canas TC 5002 5018 (Substation) |  | Substation | Inactive | No | 63855.03 | 0 | 1626.49 | 65481.52 | No
60 | 547221 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) |  | Transmission | Inactive | No | 1189223.27 | 0 | 47395.41 | 1236618.68 | Yes
61 | 334482 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) |  | Transmission | Inactive | No | 3569124.6 | 0 | 105871.13 | 3674995.73 | Yes
62 | 334469 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) |  | Transmission | Inactive | No | 773297.26 | 0 | 18409.58 | 791706.84 | Yes
63 | 179988 | FAASt [Las Lomas XFMR 1525] (Substation) |  | Substation | Inactive | No | 12555.33 | 0 | 0.27 | 12555.6 | No
64 | 169804 | FAASt Aguadilla Electric Service Center (Building) |  | Building | Inactive | No | 3144.26 | 0 | 0.27 | 3144.53 | No
65 | 169503 | FAASt [Ceiba Baja TRF 7012] (Substation) |  | Substation | Inactive | No | 2133.95 | 0 | 692.15 | 2826.1 | No