## Sheet1
Attachment H
Genera Monthly Reporting Requirements - Generation Maintenance
Thermal Generation Facility Maintenance Report
Aguirre, Costa Sur, Palo Seco, San Juan Power Plants
Monthly Reporting
As of August 31, 2024
NO. | POWER PLANT | UNIT NUMBER | PROJECT ACTIVITY | CATEGORY | ACTIVITY BUDGET | START DATE | COMPLETION DATE | ACTIVITY STATUS - PERCENTAGE FOR COMPLETION | PROCUREMENT / BID (S) NUMBER | POC - MAINTENANCE ACTIVITY | CONTRACTOR/SUPPLIER | APPROVED FOR PAYMENT
1 | Aguirre | 1 & 2 | Generator Spare Rotor Rewind | Federal |  |  |  | PLANNING |  | Robert Rosario
2 | Aguirre |  | ASP Rehabilitation WTP Nautilis Tank 1B | Federal | 387500 | 2025-11-24 | 2026-07-24 | PLANNING | C-102348 | Manuel Cortés | CSA Artchitects Engineers | 1308605.14
3 | Aguirre CC | 1-4 | Hot Gas Inspection 1-4 (HGPI 1-4) | Federal | 2124037 | 2025-06-16 | 2025-10-15 | EXECUTION | C-106760 | José Vázquez | MD&A | 1274422.2
4 | Aguirre CC |  | Gas Turbine Rotor Refurbish MS7001B/AE | Federal | 1094955 | 2025-11-01 | 2026-04-30 | PROCUREMENT | C-105235 | José Vázquez | MD&A
5 | Mayagüez |  | Inspection and Maintenance 4 Generator Brush | NME | 1847478 | 2025-03-01 | 2025-08-31 | EXECUTION | C-104923 | José Vázquez | GESA | 646617.3
6 | Cambalache | 2 & 3 | Inspection C - Manpower and Spare Parts | Federal | 22000000 | 2025-10-15 | 2026-12-31 | PROCUREMENT | REQ. 289229 | José Vázquez
8 | Cambalache |  | Structural Rehabilitation Fuel Tank D-2 | Federal | 2000000 | 2024-06-10 | 2025-12-31 | EXECUTION | 101295 | Manuel Cortés | All Contractors | 811546.87
9 | Aguirre CC | 1-3 | Major inspection Unit 1-3 | Federal | 3750000 | 2024-09-09 | 2026-01-30 | EXECUTION | C-104889 | José Vázquez | RG Engineering | 1059560.75
10 | Aguirre | 1-4 | Replacement of Load Center 1-4 Condenser Circulating Water Pump | Federal | 820000 | 2025-02-03 | 2026-05-30 | EXECUTION | C-101421 | Luis Ortiz | Allied Power
11 | Aguirre |  | Traveling Screen Project 316B | Federal | 13500000 |  |  | PLANNING |  | Luis Ortiz
12 | San Juan | 5 | Replacement of the Online Condenser Cleaner Unit 5 | Federal | 3600000 | 2026-01-01 | 2026-12-31 | PROCUREMENT | 106758 | Manuel Cortés | Malnat
13 | San Juan | 6 | Unit 6 - Major Overhaul (ST Repairs) | Federal | 13692168.2 | 2025-01-20 | 2026-01-15 | EXECUTION | C-105509 | José Vázquez | MD&A | 4446454.64
14 | San Juan | 7 | SJ7 Mayor Overhaul (Boiler & Aux) | Federal | 2567090 | 2025-04-01 | 2025-09-30 | CLOSING |  | Fernando Rivera | Various | 3438404.31
15 | San Juan | 7 | Unit 7 Rehabilitation ( Turbine) | Federal | 22380974.33 | 2025-03-21 | 2025-12-10 | EXECUTION | C-108148 | Fernando Rivera | MD&A | 4180813.68
18 | Palo Seco | 3 | Update Voltage Regulation System Unit 3, Palo Seco Power Plant | Federal | 294082 | 2026-01-12 | 2026-02-28 | EXECUTION | C-101258 | Robert Rosario | ESI | 119103.21
19 | Palo Seco |  | Upgrade OSI DCS | Federal | 2445496 | 2025-03-14 | 2026-04-30 | EXECUTION | C- 103154 | Robert Rosario | Emerson | 733678.76
20 | Costa Sur | 5 | Replacement of Excitation System Units 5 | Federal | 1583848 | 2024-09-17 | 2026-12-31 | EXECUTION | C-102867 | Robert Rosario | ESI | 791924
21 | Costa Sur |  | Replacement of Unit 6 Electric Load Center | Federal | 356295 | 2023-01-10 | 2025-09-30 | CLOSING | C-97578 | Roberto Rosario | Allied Power | 320665.5
22 | Costa Sur |  | Traveling Screens Replacement | Federal | 5000000 | 2025-09-30 | 2027-03-24 | PLANNING |  | Luis Ortiz
23 | Costa Sur | 6-1 | Rehabilitation Condenser Circulating Water Pump (CCWP) 6-1 | Federal | 865670 | 2025-02-17 | 2025-12-31 | EXECUTION | C-107189 | Luis Ortiz | Reliable Industrial | 224192.5
24 | Aguirre |  | ASP Phase IV Stage 1 - Advanced Water Treatment System (Design) | NME | 784612 | 2025-01-01 | 2025-12-13 | EXECUTION | C-102062 (T6-R7) | Luis Ortiz | Integra | 755838.35
25 | Aguirre |  | ASP Phase 4 Stage 2 - Advanced Water Treatment System (Desgin) | NME | 413000 | 2025-06-01 | 2025-12-13 | EXECUTION | C-102062 (T8-R9) | Luis Ortiz | Integra | 86902.5
26 | Costa Sur |  | Upgrade to Foxboro Simulation System | Federal | 1215173 | 2024-12-04 | 2025-11-30 | EXECUTION | C-103503 | Robert Rosario | LT Automation | 1190673
27 | Costa Sur | 5 | Manufacture and Delivery of Bifurcate (Boiler) Tubes Unit 5 | Federal | 255110 | 2026-01-05 | 2026-08-31 | PROCUREMENT | MR-871412 | Fernando Rivera | GE | 255110
28 | Palo Seco |  | New Demineralized Water Tank #2 | Federal | 2500000 | 2024-09-03 | 2025-09-03 | EXECUTION | C-102570 | Manuel Cortés | Alonso & Carus | 1740762.9
29 | Aguirre CC | GT 2-3 | Major inspection of units GT 2-3. | Federal | 10000000 | 2026-02-01 | 2026-06-30 | PROCUREMENT | REQ. 285838 | José Vázquez
32 | Palo Seco | 4 | Major & Environment Maintenance PS4 | Federal | 9000000 | 2024-09-01 | 2025-08-20 | CLOSING | Varios | Fernando Rivera | Varios | 2262185.81
33 | Palo Seco | 4 | Generator Repair PS4 | Forced Outage | 15200000 | 2024-07-31 | 2025-09-30 | CLOSING | C-104814 | Robert Rivera | Ethos Energy Power | 10298196.17
34 | San Juan | 9 | Major Overhaul SJ9 | Federal | 28000000 | 2026-01-15 | 2026-06-15 | PROCUREMENT | Various | José Vázquez | Various
35 | San Juan | 7 | Condenser Rehabilitation SJ7 | Federal | 5700000 | 2025-10-10 | 2026-01-18 | PROCUREMENT |  | Fernando Rivera
36 | Costa Sur |  | Tanques Raw Water 1&2 | Federal | 4713865 | 2023-03-08 | 2025-07-30 | COMPLETED | C-98193 | Greg Hernández | Alonso & Carus | 4713865
37 | Mayagüez |  | Waste Water Tank 1&2 | NME | 379600 | 2025-07-23 | 2025-12-29 | EXECUTION | C-107651 | Luis Ortiz | Alonso & Carus | 99333
39 | Mayagüez | 4A | Hot Section Inspection Unit 4A | Federal | 9000000 | 2025-07-03 | 2025-12-29 | EXECUTION | C-108663 | Luis Ortiz | ARG Precision | 6994584.43
40 | Aguirre | 2 | Environmental Outage and APH Basket Replacement | NME | 1762000 | 2026-03-01 | 2026-05-01 | PLANNING |  | Roberto Rosario
41 | Aguirre | 1 | Generator Stator & Generator Rotor Rewind | Federal |  |  |  | PLANNING |  | Roberto Rosario
42 | Aguirre |  | ASP Phase IV Demineralized Water System | EPA | 4039947.71 | 2026-01-01 | 2026-08-30 | PROCUREMENT | REQ. 306588 | Luis Ortiz
43 | Aguirre |  | New WTP Retention Tank #1 | Federal | 6000000 | 2026-01-01 | 2026-12-31 | PLANNING |  | Luis Ortiz
44 | Aguirre |  | New WTP Retention Tank #2 | Federal | 6000000 | 2026-01-01 | 2026-12-31 | PLANNING |  | Luis Ortiz
45 | Aguirre | 1 | Forced Outage and APH Basket Replacement |  |  |  |  | PLANNING |  | Fernando Rivera
47 | Aguirre | 2-1 & 2-2 | Procurement of a Main Power Transformer | Federal |  |  |  | PROCUREMENT |  | PMO HQ
48 | Aguirre |  | Procurement of Distribution Transformers ACC | Federal |  |  |  | PROCUREMENT |  | PMO HQ
49 | Aguirre CC |  | Manufacture and Delivery of Power Circuit Breaker 245kV SF6 | NME | 823006 | 2025-09-01 | 2028-05-31 | PROCUREMENT | C-108519 | Robert Rosario | Pro-Energy
50 | Aguirre CC |  | New Condensate Tank #2 | Federal | 2500000 | 2025-12-01 | 2026-12-01 | PROCUREMENT | C-110325 | Luis Ortiz | Alonso & Carus
52 | Cambalache |  | Camba Design Flood Protection Barrier | Federal | 385000 | 2024-04-12 | 2027-07-30 | EXECUTION | C-102184 (T7-R2) | Manuel Cortés | Sargent & Lundy | 343263
53 | Costa Sur | 6 | Replacement Load Center 6-2A & 6-2B | NME | 265000 | 2022-11-30 | 2025-12-31 | EXECUTION | C-97582 | Luis Ortiz | Allied Power | 159000
54 | Costa Sur | 5 & 6 | Fabrication and Delivery of Steam Coils | Federal | 1275993 | 2025-09-10 | 2026-12-01 | EXECUTION | C-109034 | Luis Ortiz | Antilles Power Depor Inc.
55 | Costa Sur |  | Structural Rehabilitation Water Discharge Channel | Federal | 5700000 | 2024-10-30 | 2025-06-30 | COMPLETED | 89554 | Greg Hernández | Gabriel Fuentes Construction | 5309787.8
56 | Costa Sur |  | Caustic Soda and Acid Tanks Replacement Works | Federal | 307000 | 2022-10-18 | 2025-01-31 | COMPLETED | 96561 | Greg Hernández | Alonso & Carus | 550100
57 | Costa Sur | 6 | Environmental Inspection | Federal/NME | 6000000 | 2025-11-10 | 2025-12-29 | PLANNING
58 | Mayagüez | 3B | Repair & Replace Combustors Components | NME |  |  |  | EXECUTION | C-108663 | Luis Ortiz | ARG Precision
59 | Palo Seco | 3 & 4 | Upgrade to Mark IV | Federal | 5000000 | 2025-08-30 | 2026-02-28 | PROCUREMENT | C-103504 | Robert Rosario | GE
60 | Palo Seco | 4 | Economizer Water Inlet Valve | Federal | 150000 | 2025-11-01 | 2026-12-31 | PROCUREMENT | REQ. 295748 | Robert Rosario
61 | Palo Seco | 3 | Environmental Maintenance | Federal/NME | 1762000 | 2026-01-05 | 2026-03-02 | PLANNING |  | Robert Rosario
62 | Palo Seco |  | New Multimedia Filters | Federal | 1000000 | 2024-03-08 | 2025-06-30 | CLOSING | C-101296 | Manuel Cortés | EPS | 822020
63 | Palo Seco |  | Tank R3 Interconnection System | Federal | 12000000 |  |  | PLANNING |  | Manuel Cortés
64 | Palo Seco | 4 | Superheater Header (material and installation) | Federal | 1206123 | 2026-03-23 | 2027-03-23 | PROCUREMENT |  | Fernando Rivera | GE
65 | Palo Seco |  | Deaerator Pump | NME | 343040.25 | 2024-02-16 | 2025-12-31 | EXECUTION | C-101706 | Fernando Rivera | Camfer | 114346.75
66 | San Juan |  | Rehabilitation WTP Retention Tank #1 | Federal | 1500000 | 2026-01-01 | 2026-12-31 | PLANNING | REQ. 298191 | Manuel Cortés
67 | San Juan |  | Procurement of Main Transformers | Federal |  |  |  | PROCUREMENT |  | PMO HQ
68 | San Juan |  | Natural Gas Manufacturing Surchange | NME | 10000000 | 2025-07-01 | 2026-06-30 | EXECUTION |  | PMO HQ
69 | Aguirre | 1 & 2 | ASP U1&U2 Manufacture & Installation of Service Elevators | Federal | 438790 |  |  | PROCUREMENT |  | Greg Hernández
70 | Aguirre | 1 | ASP U1 Forced Outage and APH Basket Replacement | Federal/NME |  | 2026-01-12 | 2026-04-30 | PLANNING |  | Fernando Rivera
71 | Palo Seco | 3&4 | PSSP U3&U4 Manufacture & Installation of Service Elevators | Federal | 387894 |  |  | PROCUREMENT | REQ. 293151 | Manuel Cortés | VERTECH
72 | San Juan | 5&6 | SJSP U5&U6 Purchase & Installation 2 UPS & 4 Battery Chargers | Federal | 939750 | 2025-09-17 | 2026-06-30 | EXECUTION | C-106978 | Manuel Cortés | MALNAT
73 | San Juan | 7 | SJSP U7 Manufacture & Installation of Service Elevators | Federal | 219800 |  |  | PROCUREMENT | REQ. 293151 | Fernando Rivera | VERTECH
74 | San Juan | 5 | SJSP U5 CT Turbine Inspection | NME |  |  |  | EXECUTION |  | José Vázquez
|  | **** | NME MAINTENANCE ACTIVITY COULD INCLUDE DIFERENT CONTRACTS