## LUMA - Annex A
[15 empty] | Note: 1 For Non-Federally Funded projects, the “Estimated Cost ($)” column reflects the estimated Total Cost of the Project as part of the Long-Term Investment Plan estimates and for Federally Funded projects, the “Estimated Cost ($)” column reflects the obligated amount approved by FEMA. 2 The “Cost ($)” column reflects either the estimated cost of the Initial Scope of Work approved by the Energy Bureau for Federally-Funded projects, or, for Non-Federally Funded projects, the funding allocated to the project in the current Fiscal Year Budget approved by the Energy Bureau. 3For federally funded projects, completion dates reflect all field activities that must be completed before a project can effectively be closed out and are aligned with the % complete. The energized column does not imply overall project completion. | Control Center & Buildings | FF | Federally Funded | Initiation
NEPR-MI-2024-0001 | [15 empty] | Customer Experience | NFF | Non-Federally Funded | Plan
PREB Approved Investments as of: | [15 empty] | Distribution |  |  | Design
2025-12-31 | [15 empty] | Enabling |  |  | Execution
[16 empty] | Substations |  |  | Close Out
Support Services
|  |  |  | Funding |  | PREB's Approval Date |  | Project Phase | [7 empty] | Transmission
Unique ID (FAASt No. or Project ID) | Project Title | Portfolio* | Improvement Program | Source** | Estimated Cost ($M)1 | Cost ($M)2 | Date | Phase*** | Starting Date3 | Completion Date | Energized | % Complete | Department | Executive
PBCS4.01 | Wheeling | Customer Experience | Retail Wheeling | NFC | 0 | 0.12 | 2025-07-31 | Initiation | On Hold | On Hold | N/A | 0% | Operations | Kevin Burgemeister
PBFM1.01 | FMS Santurce Parking Rehab | Control Center & Buildings | Facilities Development & Implementation | NFC | 0 | 0.4 | 2025-07-31 | Execution | 2025-03-01 | 2026-02-27 | N/A | 98% | Corporate Services | Ivonne Gomez Mendez
PBIT1.01 | GuayaToJob.Fib.Enh-AguiToJobTC | Transmission | OT Telecom Systems & Network | NFC | 0 | 0.43 | 2025-07-31 | Close Out | 2025-05-01 | 2025-06-20 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBIT1.551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Support Services | OT Telecom Systems & Network | FF | 7.6 | 30 | 2021-09-22 | Execution | 2021-12-22 | 2025-09-26 17:00 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBIT1.551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Support Services | OT Telecom Systems & Network | FF | Pending Obligation | Program Cost Included in PBIT1.551925 | 2021-09-22 | Plan | 2021-12-22 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBIT1.551963 | FAASt [Transport Network] (Telecommunication) | Support Services | OT Telecom Systems & Network | FF | 5.4 | 185 | 2021-09-22 | Design | 2021-12-22 | 2029-05-04 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBIT1.662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Support Services | OT Telecom Systems & Network | FF | Pending Obligation | 6 | 2021-09-22 | Plan | 2022-02-14 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBIT1.673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Support Services | OT Telecom Systems & Network | FF | 8.1 | 96.5 | 2021-09-22 | Design | 2022-05-17 | 2027-10-27 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBIT1.678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Support Services | OT Telecom Systems & Network | FF | 13.2 | Program Cost Included in PBIT1.551925 | 2021-09-22 | Design | 2022-07-22 | 2028-08-31 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBIT1.746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Support Services | OT Telecom Systems & Network | FF | Pending Obligation | 146 | 2024-05-07 | Plan | 2024-04-04 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 18.1 | 1200 | 2023-05-05 | Execution | 2023-06-26 | 2027-06-01 | No | 11% | Engineering & Asset Management | Pedro Melendez
PBOP7.727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-08-03 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-08-03 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 25.9 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-03 | 2028-05-23 | No | 47% | Engineering & Asset Management | Pedro Melendez
PBOP7.727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-08-03 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-08-03 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-08-03 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-08-04 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-08-04 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 28.05 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-04 | 2028-06-06 | No | 58% | Engineering & Asset Management | Pedro Melendez
PBOP7.728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 18.1 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-17 | 2028-01-25 | No | 64% | Engineering & Asset Management | Pedro Melendez
PBOP7.728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 14.2 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-17 | 2027-12-06 | No | 45% | Engineering & Asset Management | Pedro Melendez
PBOP7.741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2023-12-15 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2024-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2024-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2024-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2024-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Plan | 2024-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956330 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956331 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956332 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956335 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956337 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956339 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956340 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956341 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956342 | FAASt [Arecibo Region 2 Transmission Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 4 | Program Cost Included in PBOP7.956342 | 2023-05-05 | Design | 2025-06-18 | 46827 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956345 | FAASt [Arecibo Region 2 Transmission Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956345 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956348 | FAASt [Bayamon Region 3 Transmission Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956348 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 1.3 | Program Cost Included in PBOP7.956349 | 2023-05-05 | Design | 2025-06-18 | 46106 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956353 | FAASt [Arecibo Region 2 Transmission Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 3.7 | Program Cost Included in PBOP7.956353 | 2023-05-05 | Design | 2025-06-18 | 46841 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 0.325 | Program Cost Included in PBOP7.956356 | 2023-05-05 | Design | 2025-06-18 | 46080 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBOP7.956357 | FAASt [Mayaguez Region 5 Transmission Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956357 | 2023-05-05 | Plan | 2025-06-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.01 | 10000-Bayamon Pueblo SECT-Magnolia TO | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.02 | 10700-HATO TEJAS SECT-BAYAMON PUEBLO SECT- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.5 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.03 | 16500-FAJARDO TC-DOS MARINAS- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.2 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.04 | 1700-GUANICA TC-YAUCO 2 HP- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 1.2 | 2025-07-31 | Design | 2025-11-09 | 2026-02-28 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.05 | 2300-Arecibo SECT-Cambalache TC | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.22 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.06 | 3000-CAGUAS TC-CAGUAX SECT-F | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.12 | 2025-07-31 | Plan | 2026-03-01 | 2026-03-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.07 | 3000-CAGUAX SECT-JUNCOS TC-F | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.3 | 2025-07-31 | Plan | 2026-04-01 | 2026-04-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.08 | 3000-JUNCOS TC-RIO BLANCO HP-F | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.92 | 2025-07-31 | Plan | 2026-02-01 | 2026-03-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.09 | 3100-Canovanas SECT-Rio Grande TO | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.7 | 2025-07-31 | Plan | 2026-05-01 | 2026-05-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.10 | 3100-CAROLINA-CANOVANAS TC- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-04-01 | 2026-04-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.11 | 3200-Monacillos TC-Venezuela SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.12 | 3300-Viaducto TC-Egozcue SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.13 | 3600-Llorens Torres SECT-Martin Peña | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.14 | 3600-Monacillos TC-Sabana Llana TC | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.3 | 2025-07-31 | Plan | 2026-05-01 | 2026-05-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.15 | 3600-Sabana Llana TC-Los Ángeles SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.16 | 4500-CANAS TC - LA RAMBLA SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 1.4 | 2025-07-31 | Plan | 2026-04-01 | 2026-05-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.17 | 700-COSTA SUR SP-YAUCO 2 HP- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.15 | 2025-07-31 | Plan | 2026-03-01 | 2026-03-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.18 | 7400-Hato Rey TC-Tres Monjitas SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.19 | 800-COMSAT SECT - CIDRA SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.7 | 2025-07-31 | Design | 2025-12-01 | 2026-02-28 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.20 | 9400-Dorado TC-Toa Alta | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Plan | 2026-06-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.334468 | FAASt [Transmission Priority Pole Replacements – Line 2200] (Transmission) | Transmission | Transmission Line Rebuild | FF | 1.22 | Program Cost Included in PBUT13.681672 | 2021-08-20 | Execution | 2021-09-10 | 2025-10-26 | No | 93% | Engineering & Asset Management | Pedro Melendez
PBUT13.550896 | FAASt [Transmission Priority Pole Replacements – Line 6700] (Transmission) | Transmission | Transmission Line Rebuild | FF | 0.69 | Program Cost Included in PBUT13.681672 | 2021-10-18 | Execution | 2021-12-14 | 2025-12-22 | Yes | 90% | Engineering & Asset Management | Pedro Melendez
PBUT13.668583 | FAASt [Transmission Priority Pole Replacements – Line 13300] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.45 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2022-03-29 | 2025-11-19 | Yes | 91% | Engineering & Asset Management | Pedro Melendez
PBUT13.668592 | FAASt [Transmission Priority Pole Replacement – Line 9800] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.42 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2022-03-29 | 2026-01-08 | Yes | 94% | Engineering & Asset Management | Pedro Melendez
PBUT13.681672 | FAASt Transmission Priority Pole Replacements –38kV Line 2300 (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.22 | 378.8 | 2021-09-22 | Execution | 2022-08-31 | 2025-07-22 | Yes | 90% | Engineering & Asset Management | Pedro Melendez
PBUT13.708637 | FAASt [T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.37 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-03-03 | 2026-02-26 | No | 90% | Engineering & Asset Management | Pedro Melendez
PBUT13.711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.12 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-03-31 | 2026-01-30 | No | 93% | Engineering & Asset Management | Pedro Melendez
PBUT13.711819 | FAASt [TL 13400 TC-San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Plan | 2023-04-03 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.631 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-04-04 | 2026-04-04 | No | 77% | Engineering & Asset Management | Pedro Melendez
PBUT13.750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.134 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-06-20 | 2026-05-05 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.255 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-06-20 | 46650 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.469 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-06-20 | 2026-05-05 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT13.753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.131 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Design | 2024-08-23 | 2026-06-10 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT18.549764 | FAASt [Physical Security - Group 2] (Substation) | Substation | Substation Physical Security | FF | 2.38 | 53.8 | 2021-10-18 | Execution | 2021-12-03 | 2025-12-05 | No | 79% | Corporate Services | Michael Granata
PBUT18.550910 | FAASt [Physical Security - Group 1] (Substation) | Substation | Substation Physical Security | FF | 6.69 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2021-12-14 | 2025-11-05 | No | 81% | Corporate Services | Michael Granata
PBUT18.551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Physical Security | FF | 4.13 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2021-12-21 | 2026-05-30 | No | 47% | Corporate Services | Michael Granata
PBUT18.660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Physical Security | FF | 3.82 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2022-01-27 | 2026-07-24 | No | 33% | Corporate Services | Michael Granata
PBUT19.01 | CCTV&accessReg&Tech Facility | Substation | Regional Operationas Physical Security | NFC | 0 | 0.04 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 36% | Corporate Services | Michael Granata
PBUT19.02 | CCTV&accessCustomerExpFacility | Substation | Regional Operationas Physical Security | NFC | 0 | 0.02 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 47% | Corporate Services | Michael Granata
PBUT19.03 | CCTV&accessPaloSeco | Substation | Regional Operationas Physical Security | NFC | 0 | 0.16 | 2025-07-31 | Execution | 2022-07-01 | 2026-06-30 | N/A | 95% | Corporate Services | Michael Granata
PBUT19.04 | CCTV SatelliteWarehouses | Substation | Regional Operationas Physical Security | NFC | 0 | 0.19 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 21% | Corporate Services | Michael Granata
PBUT19.05 | CCTV&accessRegionalWarehouses | Substation | Regional Operationas Physical Security | NFC | 0 | 0.15 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 50% | Corporate Services | Michael Granata
PBUT22.657300 | FAASt [ENERGY MANAGEMENT SYSTEM (EMS)] (Telecommunication) | Control Center & Buildings | Critical Energy Management System Upgrades | FF | 48.94 | 126 | 2021-09-22 | Execution | 2022-01-19 | 2026-03-24 09:36 | No | 65% | Operations | Kevin Burgemeister
PBUT30.334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.39 | 600 | 2021-08-20 | Execution | 2021-09-08 | 2026-03-31 | Yes | 91% | Engineering & Asset Management | Pedro Melendez
PBUT30.334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.38 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-08 | 2026-03-31 | Yes | 87% | Engineering & Asset Management | Pedro Melendez
PBUT30.334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.12 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-10 | 2025-10-31 | Yes | 97% | Engineering & Asset Management | Pedro Melendez
PBUT30.542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2021-10-26 | 2026-03-31 | Yes | 97% | Engineering & Asset Management | Pedro Melendez
PBUT30.673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 2.37 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 86% | Engineering & Asset Management | Pedro Melendez
PBUT30.673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 4.12 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 83% | Engineering & Asset Management | Pedro Melendez
PBUT30.673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-04-30 | No | 62% | Engineering & Asset Management | Pedro Melendez
PBUT30.673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 4.43 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.79 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.79 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-03-31 | No | 87% | Engineering & Asset Management | Pedro Melendez
PBUT30.673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 5.75 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 46112 | No | 86% | Engineering & Asset Management | Pedro Melendez
PBUT30.673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.36 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 46112 | Yes | 85% | Engineering & Asset Management | Pedro Melendez
PBUT30.673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-05-25 | 2023-09-05 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.13 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 46112 | No | 80% | Engineering & Asset Management | Pedro Melendez
PBUT30.673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.39 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 46112 | No | 87% | Engineering & Asset Management | Pedro Melendez
PBUT30.673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 46080 | No | 78% | Engineering & Asset Management | Pedro Melendez
PBUT30.673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 46097 | No | 56% | Engineering & Asset Management | Pedro Melendez
PBUT30.674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 46112 | No | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 2.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 46112 | No | 80% | Engineering & Asset Management | Pedro Melendez
PBUT30.674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.7 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 46112 | No | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.53 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 46112 | No | 78% | Engineering & Asset Management | Pedro Melendez
PBUT30.674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 2.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 46112 | No | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-05-27 | 2023-05-04 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-26 | 2026-03-31 | No | 79% | Engineering & Asset Management | Pedro Melendez
PBUT30.678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.12 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-26 | 2026-03-31 | No | 87% | Engineering & Asset Management | Pedro Melendez
PBUT30.679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2026-03-31 | No | 80% | Engineering & Asset Management | Pedro Melendez
PBUT30.679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.59 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2026-03-31 | No | 78% | Engineering & Asset Management | Pedro Melendez
PBUT30.679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.91 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2026-03-31 | Yes | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.22 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-03-31 | Yes | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.56 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-02-27 | Yes | 94% | Engineering & Asset Management | Pedro Melendez
PBUT30.679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.16 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-03-31 | Yes | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.22 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-03-31 | Yes | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.75 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-08-03 | 46112 | No | 86% | Engineering & Asset Management | Pedro Melendez
PBUT30.679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.59 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-08-03 | 2026-03-31 | Yes | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.54 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-06 | 45991 | No | 75% | Engineering & Asset Management | Pedro Melendez
PBUT30.682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.63 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-06 | 46080 | No | 26% | Engineering & Asset Management | Pedro Melendez
PBUT30.682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.69 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-07 | 2026-03-31 | No | 86% | Engineering & Asset Management | Pedro Melendez
PBUT30.682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.57 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-07 | 2026-03-31 | No | 95% | Engineering & Asset Management | Pedro Melendez
PBUT30.682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.27 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-31 | Yes | 83% | Engineering & Asset Management | Pedro Melendez
PBUT30.682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole & Conductor Repair | FF | 0.26 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-31 | No | 80% | Engineering & Asset Management | Pedro Melendez
PBUT30.682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-16 | No | 51% | Engineering & Asset Management | Pedro Melendez
PBUT30.682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 46112 | Yes | 81% | Engineering & Asset Management | Pedro Melendez
PBUT30.682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.95 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-31 | No | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.71 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-12 | 2026-03-31 | No | 82% | Engineering & Asset Management | Pedro Melendez
PBUT30.682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-12 | 2026-03-31 | Yes | 90% | Engineering & Asset Management | Pedro Melendez
PBUT30.682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-16 | No | 82% | Engineering & Asset Management | Pedro Melendez
PBUT30.682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.66 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | No | 85% | Engineering & Asset Management | Pedro Melendez
PBUT30.682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.61 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | Yes | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.74 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.62 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | Yes | 97% | Engineering & Asset Management | Pedro Melendez
PBUT30.685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.67 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-11 | 2026-03-31 | Yes | 86% | Engineering & Asset Management | Pedro Melendez
PBUT30.685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-10-12 | 2023-08-17 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-13 | 2026-03-31 | No | 81% | Engineering & Asset Management | Pedro Melendez
PBUT30.685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.32 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-18 | 2026-03-31 | Yes | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-10-20 | 2023-07-18 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.32 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-20 | 2026-03-31 | Yes | 97% | Engineering & Asset Management | Pedro Melendez
PBUT30.686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.63 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-20 | 2026-03-31 | No | 87% | Engineering & Asset Management | Pedro Melendez
PBUT30.688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Close Out | 2022-11-02 | 2023-10-27 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.56 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-02 | 2026-03-31 | Yes | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-03 | 2026-03-31 | Yes | 85% | Engineering & Asset Management | Pedro Melendez
PBUT30.688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.18 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-04 | 2026-03-31 | No | 85% | Engineering & Asset Management | Pedro Melendez
PBUT30.688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.9 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2026-03-31 | Yes | 87% | Engineering & Asset Management | Pedro Melendez
PBUT30.688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.38 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2026-03-31 | No | 84% | Engineering & Asset Management | Pedro Melendez
PBUT30.688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.13 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-07 | 2026-03-31 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-07 | 2026-03-31 | No | 51% | Engineering & Asset Management | Pedro Melendez
PBUT30.688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.54 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2026-03-31 | No | 87% | Engineering & Asset Management | Pedro Melendez
PBUT30.689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-09 | 2026-03-31 | Yes | 90% | Engineering & Asset Management | Pedro Melendez
PBUT30.691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.25 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-28 | 2026-03-31 | No | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-01-03 | 2023-10-31 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.19 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-01-03 | 2023-10-25 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.62 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2026-03-31 | Yes | 84% | Engineering & Asset Management | Pedro Melendez
PBUT30.701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2026-03-31 | Yes | 90% | Engineering & Asset Management | Pedro Melendez
PBUT30.701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.65 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2026-03-31 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-04 | 2026-03-31 | No | 67% | Engineering & Asset Management | Pedro Melendez
PBUT30.704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.58 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 88% | Engineering & Asset Management | Pedro Melendez
PBUT30.704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.44 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 91% | Engineering & Asset Management | Pedro Melendez
PBUT30.704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.52 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 84% | Engineering & Asset Management | Pedro Melendez
PBUT30.704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 86% | Engineering & Asset Management | Pedro Melendez
PBUT30.704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-03 | 2026-03-31 | Yes | 80% | Engineering & Asset Management | Pedro Melendez
PBUT30.704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.43 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-03 | 2026-03-16 | No | 50% | Engineering & Asset Management | Pedro Melendez
PBUT30.705527 | FAASt [Distribution Pole and Conductor Repair – San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-08 | 46112 | No | 68% | Engineering & Asset Management | Pedro Melendez
PBUT30.705584 | FAASt [Pole and Conductor Repair - Ponce Groups 14 & 15] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.84 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-09 | 2026-03-31 | No | 80% | Engineering & Asset Management | Pedro Melendez
PBUT30.708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 2.15 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-03 | 2026-03-31 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 7.2 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-20 | 2026-03-31 | No | 71% | Engineering & Asset Management | Pedro Melendez
PBUT30.710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 6.9 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-20 | 2026-03-31 | No | 93% | Engineering & Asset Management | Pedro Melendez
PBUT30.710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-03-20 | 2024-11-25 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT30.711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 11.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-03 | 2026-01-30 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT30.711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 5.5 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-03 | 2026-03-31 | No | 92% | Engineering & Asset Management | Pedro Melendez
PBUT30.712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 5.8 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-04 | 2025-10-31 | No | 84% | Engineering & Asset Management | Pedro Melendez
PBUT30.738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 5.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-11-15 | 2025-12-31 | No | 93% | Engineering & Asset Management | Pedro Melendez
PBUT30.738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 10.6 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-11-15 | 2025-12-31 | No | 69% | Engineering & Asset Management | Pedro Melendez
PBUT30.738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 14.2 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-11-17 | 46022 | No | 64% | Engineering & Asset Management | Pedro Melendez
PBUT30.742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 1.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2024-01-04 | 46052 | No | 85% | Engineering & Asset Management | Pedro Melendez
PBUT30.742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 5.6 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2024-01-05 | 2026-03-31 | No | 85% | Engineering & Asset Management | Pedro Melendez
PBUT30.749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Plan | 2024-06-05 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT30.749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | Pending Obligation | Program Cost Included in PBUT13.681672 | 2021-09-22 | Plan | 2024-06-05 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT30.750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 12.9 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2024-07-02 | 46232 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT30.752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 7.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2024-08-01 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT30.790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.186 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2025-04-02 | 46232 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.01 | Line40600 Baymn-Monac(UG Loop) | Transmission | Transmission Line Rebuild | NFC | 0 | 0.16 | 2025-07-31 | Plan | 2022-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.02 | 36100 Fast Track-NFC Structure | Transmission | Transmission Line Rebuild | NFC | 0 | 0.4 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.03 | Restorat.of UG TL Segment 2200 | Transmission | Transmission Line Rebuild | NFC | 0 | 2.18 | 2025-07-31 | Plan | 2026-03-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.04 | Restorat.of UG TL Segment16800 | Transmission | Transmission Line Rebuild | NFC | 0 | 0.18 | 2025-07-31 | Plan | 2026-03-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.05 | DOE TL 2100 | Transmission | Transmission Line Rebuild | NFC | 0 | 2 | 2025-07-31 | Close Out | 2025-07-01 | 2025-12-31 | N/A | 99% | Engineering & Asset Management | Pedro Melendez
PBUT33.06 | DOE TL 9100 | Transmission | Transmission Line Rebuild | NFC | 0 | 1.5 | 2025-07-31 | Close Out | 2025-07-01 | 2025-12-31 | N/A | 99% | Engineering & Asset Management | Pedro Melendez
PBUT33.07 | Line 100/200 out of service segment | Transmission | Transmission Line Rebuild | NFC | 0 | 0.25 | 2025-07-31 | Design | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.08 | Line 16800 | Transmission | Transmission Line Rebuild | NFC | 0 | 4 | 2025-07-31 | Initiation | N/A | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 73.06 | 2021-06-08 | Plan | 2020-12-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.167446 | FAASt - Line 36100 (115kV) - Dos Bocas HP to Monacillos TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 109.97 | 2021-06-08 | Plan | 2021-01-13 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.168226 | FAASt San Juan 115kV Underground Transmission Loop (Transmission) | Transmission | Transmission Line Rebuild | FF | 14.75 | 11.6 | 2021-06-08 | Design | 2021-01-20 | 2030-08-27 17:00 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 83.26 | 2021-06-08 | Plan | 2021-01-22 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Transmission | Transmission Line Rebuild | FF | 33.5 | 6.71 | 2021-06-08 | Design | 2021-03-23 | 2028-08-02 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Transmission | Transmission Line Rebuild | FF | 21.6 | 8.07 | 2021-06-08 | Design | 2021-03-23 | 2027-06-28 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.180052 | FAASt Ponce TC to Jobos TC - 38kV 100 & 200 (Transmission) | Transmission | Transmission Line Rebuild | FF | 74.5 | 87.28 | 2021-06-08 | Design | 2021-04-14 | 2029-08-24 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.334470 | FAASt [Line 3100 Monacillos TC to Daguao TC] (Transmission) | Transmission | Transmission Line Rebuild | FF | 47.1 | 113.33 | 2021-08-20 | Design | 2021-09-10 | 2028-08-04 | no | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 21.47 | 2021-10-18 | Plan | 2021-11-16 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.750729 | FAASt [Transmission Line 3700 GOAB 3797 to Arroyo Substation 4101] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 2 | 2024-05-07 | Plan | 2024-07-02 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 40.1 | 2024-08-22 | Plan | 2024-09-25 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT33.756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 36.5 | 2024-08-22 | Plan | 2024-09-25 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT36.714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Customer Experience | AMI Implementation Program | FF | 873.85 | 780 | 2023-04-05 | Execution | 2023-04-20 | 2028-12-31 | No | 2% | Engineering & Asset Management | Pedro Melendez
PBUT37.01 | BESS Land Purchase | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | NFC | 0 | 4 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT38.02 | 17-1-243 WR6351877MCasasFulReh | Customer Experience | New Business Connections | NFC | 0 | 1.62 | 2025-08-02 | Close Out | 2024-11-22 | 2025-09-22 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT38.03 | 15-5-0293 Los Tubos Beach | Customer Experience | New Business Connections | NFC | 0 | 0.05 | 2025-08-03 | Close Out | 2025-04-30 | 2025-09-19 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT38.04 | WR6325133-6385841 Terrumo LLC | Customer Experience | New Business Connections | NFC | 0 | 0 | 2025-08-04 | Close Out | 2025-02-01 | 2025-10-20 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT38.05 | ANTENA LIBERTY CRAN 09-165 NPC | Customer Experience | New Business Connections | NFC | 0 | 0.02 | 2025-08-05 | Close Out | 2025-03-01 | 2025-10-29 | Yes | 99% | Engineering & Asset Management | Pedro Melendez
PBUT38.06 | Hacienda Peñonales 20-5-0076 | Customer Experience | New Business Connections | NFC | 0 | 0.03 | 2025-08-06 | Close Out | 2025-09-30 | 2025-10-29 | Yes | 99% | Engineering & Asset Management | Pedro Melendez
PBUT38.07 | HYDROPHONIC LLC | Customer Experience | New Business Connections | NFC | 0 | 0.02 | 2025-08-07 | Close Out | 2025-03-13 | 2025-09-26 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT38.08 | La Maquina SG 22-4-0558 | Customer Experience | New Business Connections | NFC | 0 | 0.01 | 2025-08-08 | Close Out | 2025-09-30 | 2025-10-29 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT38.09 | UG Repairs Sanchez Osorio Ave | Customer Experience | New Business Connections | NFC | 0 | 0.31 | 2025-08-09 | Close Out | 2025-06-30 | 2025-09-19 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT38.10 | Virgen M. Ayala 25-4-0007-EE | Customer Experience | New Business Connections | NFC | 0 | 0.01 | 2025-08-10 | Close Out | 2025-09-30 | 2025-10-29 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT4.745856 | FAASt [Automation Program Group 14 DAR ARECIBO 8404- FY24] (Distribution) | Distribution | Grid Automation | FF | 1.6 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-03-22 | 2025-09-30 | No | 92% | Engineering & Asset Management | Pedro Melendez
PBUT4.745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Distribution | Grid Automation | FF | 0.46 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-03-22 | 2025-09-30 | No | 72% | Engineering & Asset Management | Pedro Melendez
PBUT4.745861 | FAASt [Automation Program Group 12: DAR – ARECIBO 7402, 7403, 7702 FY24] (Distribution) | Distribution | Grid Automation | FF | 3.6 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-03-22 | 2025-09-30 | No | 75% | Engineering & Asset Management | Pedro Melendez
PBUT4.746309 | FAASt [Automation Program Group 30- DAR – Bayamon 9203 - FY24] (TL/Distribution) | Distribution | Grid Automation | FF | Pending Obligation | Program Cost Included in PBUT4.688623 | 2022-08-25 | Plan | 2024-04-02 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.752808 | FAASt [Automation Program Group 19: Arecibo] (Distribution) | Distribution | Grid Automation | FF | 2.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-08-07 | 2025-09-30 | No | 85% | Engineering & Asset Management | Pedro Melendez
PBUT4.752810 | FAASt [Automation Program Group 20: Caguas] (Distribution) | Distribution | Grid Automation | FF | 2.6 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-08-07 | 2025-09-30 | No | 76% | Engineering & Asset Management | Pedro Melendez
PBUT4.755211 | FAASt [Automation Program Group 15] (Distribution) | Distribution | Grid Automation | FF | 0.643 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-05 | 2025-09-30 | No | 72% | Engineering & Asset Management | Pedro Melendez
PBUT4.757662 | FAASt [Automation Program Group 21] (Distribution) | Distribution | Grid Automation | FF | 1.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 2026-06-30 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757687 | FAASt [Automation Program Group 22] (Distribution) | Distribution | Grid Automation | FF | 2.3 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757689 | FAASt [Automation Program Group 24] (Distribution) | Distribution | Grid Automation | FF | 1.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757692 | FAASt [Automation Program Group 26] (Distribution) | Distribution | Grid Automation | FF | 0.938 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 46112 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757694 | FAASt [Automation Program Group 27] (Distribution) | Distribution | Grid Automation | FF | 2.3 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757696 | FAASt [Automation Program Group 31] (Distribution) | Distribution | Grid Automation | FF | 1.1 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757697 | FAASt [Automation Program Group 32] (Distribution) | Distribution | Grid Automation | FF | 1.9 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757698 | FAASt [Automation Program Group 33] (Distribution) | Distribution | Grid Automation | FF | 1.8 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46182 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757699 | FAASt [Automation Program Group 34] (Distribution) | Distribution | Grid Automation | FF | 2.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46085 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.757700 | FAASt [Automation Program Group 35] (Distribution) | Distribution | Grid Automation | FF | 1.3 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-09-27 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.800286 | FAASt [Automation Program Group 36] (Distribution) | Distribution | Grid Automation | FF | 1.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-12-30 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT4.800361 | FAASt [Automation Program Group 37] (Distribution) | Distribution | Grid Automation | FF | 1.5 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Design | 2024-12-31 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT5.542517 | FAASt [Luquillo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.81 | 1220 | 2021-09-22 | Execution | 2021-10-25 | 2026-06-11 | No | 87% | Engineering & Asset Management | Pedro Melendez
PBUT5.542687 | FAASt [Lajas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2026-01-20 | No | 92% | Engineering & Asset Management | Pedro Melendez
PBUT5.542688 | FAASt [Aguada Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 18.57 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2026-01-27 | No | 90% | Engineering & Asset Management | Pedro Melendez
PBUT5.542690 | FAASt [Maunabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 6.44 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2025-10-28 | No | 94.98% | Engineering & Asset Management | Pedro Melendez
PBUT5.542756 | FAASt [Guánica Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.06 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2026-02-13 | No | 89.37% | Engineering & Asset Management | Pedro Melendez
PBUT5.659623 | FAASt [Cataño Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 17.56 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-20 | 2025-11-07 | No | 77% | Engineering & Asset Management | Pedro Melendez
PBUT5.659625 | FAASt [Dorado Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 24.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-20 | 2026-02-26 | No | 77% | Engineering & Asset Management | Pedro Melendez
PBUT5.659715 | FAASt [Aibonito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 7.25 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-21 | 2026-01-14 | No | 88.29% | Engineering & Asset Management | Pedro Melendez
PBUT5.659968 | FAASt [San Germán Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 34.88 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-24 | 2027-09-08 | No | 70.73% | Engineering & Asset Management | Pedro Melendez
PBUT5.660227 | FAASt [Hatillo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 20.33 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-26 | 2026-09-04 | No | 76.73% | Engineering & Asset Management | Pedro Melendez
PBUT5.660239 | FAASt [Villalba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.87 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-26 | 2026-05-15 | No | 86.44% | Engineering & Asset Management | Pedro Melendez
PBUT5.660437 | FAASt [Manati Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 28.64 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-27 | 2026-05-16 | No | 65.12% | Engineering & Asset Management | Pedro Melendez
PBUT5.671502 | FAASt [Yabucoa Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.88 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-04-26 | 2026-03-06 | No | 67% | Engineering & Asset Management | Pedro Melendez
PBUT5.673504 | FAASt [Gurabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 20.74 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-05-19 | 2027-07-27 | No | 68% | Engineering & Asset Management | Pedro Melendez
PBUT5.678789 | FAASt [Carolina Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.02 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-22 | 2025-09-08 | No | 65.54% | Engineering & Asset Management | Pedro Melendez
PBUT5.678793 | FAASt [Mayagüez Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 12.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-22 | 2025-10-31 | No | 53.79% | Engineering & Asset Management | Pedro Melendez
PBUT5.679039 | FAASt [Caguas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 75.59 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-27 | 2026-01-31 | No | 45.69% | Engineering & Asset Management | Pedro Melendez
PBUT5.679780 | FAASt [Bayamón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 21.89 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-08-08 | 2026-05-15 | No | 78.01% | Engineering & Asset Management | Pedro Melendez
PBUT5.690545 | FAASt [Aguadilla Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 21.09 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-11-21 | 2026-02-06 | No | 47.19% | Engineering & Asset Management | Pedro Melendez
PBUT5.691702 | FAASt [Trujillo Alto Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 26.29 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-11-30 | 2026-02-04 | No | 45% | Engineering & Asset Management | Pedro Melendez
PBUT5.698424 | FAASt [Florida Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.31 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2028-01-17 | No | 74% | Engineering & Asset Management | Pedro Melendez
PBUT5.698439 | FAASt [Las Marias Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.36 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2028-10-26 | No | 52.98% | Engineering & Asset Management | Pedro Melendez
PBUT5.698458 | FAASt [Guaynabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.62 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-05-13 | No | 74.53% | Engineering & Asset Management | Pedro Melendez
PBUT5.698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 1.3 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-01-30 | No | 83% | Engineering & Asset Management | Pedro Melendez
PBUT5.698570 | FAASt [Corozal Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.95 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2027-08-25 | No | 81.62% | Engineering & Asset Management | Pedro Melendez
PBUT5.698579 | FAASt [Orocovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 9.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2027-06-15 | No | 55% | Engineering & Asset Management | Pedro Melendez
PBUT5.701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 7.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-01-03 | 46327 | No | 81.97% | Engineering & Asset Management | Pedro Melendez
PBUT5.703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.1 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-01-23 | 2026-02-13 | No | 54.36% | Engineering & Asset Management | Pedro Melendez
PBUT5.704679 | FAASt [Coamo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-01 | 2027-02-07 | No | 68.23% | Engineering & Asset Management | Pedro Melendez
PBUT5.704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.2 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-02 | 2027-10-12 | No | 65.74% | Engineering & Asset Management | Pedro Melendez
PBUT5.704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 5.8 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-02 | 2027-04-07 | No | 67.81% | Engineering & Asset Management | Pedro Melendez
PBUT5.704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 11 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-07-01 | No | 63.78% | Engineering & Asset Management | Pedro Melendez
PBUT5.704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.9 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 46484 | No | 89% | Engineering & Asset Management | Pedro Melendez
PBUT5.704938 | FAASt [Las Piedras Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-07-16 | No | 69.31% | Engineering & Asset Management | Pedro Melendez
PBUT5.704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2028-06-08 | No | 63% | Engineering & Asset Management | Pedro Melendez
PBUT5.709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.2 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-03-15 | 2027-05-20 | No | 80% | Engineering & Asset Management | Pedro Melendez
PBUT5.714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | Pending Obligation | Program Cost Included in PBUT5.542517 | 2021-09-22 | Plan | 2023-04-20 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT5.724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-03 | 2026-12-12 | No | 72.15% | Engineering & Asset Management | Pedro Melendez
PBUT5.724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-03 | 2027-05-28 | No | 78.95% | Engineering & Asset Management | Pedro Melendez
PBUT5.724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 12.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-05 | 2027-06-18 | No | 77% | Engineering & Asset Management | Pedro Melendez
PBUT5.724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-05 | 2026-08-16 | No | 58.6% | Engineering & Asset Management | Pedro Melendez
PBUT5.724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 14.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-06 | 2027-07-19 | No | 65% | Engineering & Asset Management | Pedro Melendez
PBUT5.724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-07 | 2027-10-07 | No | 58% | Engineering & Asset Management | Pedro Melendez
PBUT5.735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2023-10-20 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT5.738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | Pending Obligation | Program Cost Included in PBUT30.334323 | 2021-09-22 | Plan | 2023-11-09 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.01 | Feeder 1657-01 UG Repair | Distribution | Distribution Line Rebuild | NFC | 0 | 0 | 2025-07-31 | Initiation | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.02 | Feeder 1658-13 UG Repair | Distribution | Distribution Line Rebuild | NFC | 0 | 0 | 2025-07-31 | Initiation | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.03 | Martin Peña GIS - 1111-01 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.04 | Grana - 1907-05 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.05 | Canovanas TC - 2404-06 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.06 | Candelero - 2604-01 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.07 | Villa del Carmen - 5016-01 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.08 | System Improv. for Subst. 7301 | Distribution | Distribution Line Rebuild | NFC | 0 | 0.5 | 2025-07-31 | Execution | 2025-05-01 | 2026-03-31 | N/A | 80% | Engineering & Asset Management | Pedro Melendez
PBUT6.165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 31.13 | 2021-06-08 | Plan | 2020-12-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole & Conductor Repair | FF | 0.15 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-10 | 2026-03-31 | Yes | 88% | Engineering & Asset Management | Pedro Melendez
PBUT6.797148 | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | 2.3 | Program Cost Included in PBUT6.797148 | 2021-08-20 | Design | 2024-12-06 | 46272 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.798275 | FAASt [Distribution Feeder Rebuild # 1620-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | 6.7 | Program Cost Included in PBUT6.798275 | 2021-09-22 | Design | 2024-12-11 | 46399 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.801166 | FAASt [Distribution Feeder Rebuild # 6601-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | 19.8 | Program Cost Included in PBUT6.801166 | 2021-09-22 | Design | 2025-01-08 | 46650 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.801172 | FAASt [Distribution Feeder Rebuild # 1529-15] (Distribution) | Distribution | Distribution Line Rebuild | FF | 2.2 | Program Cost Included in PBUT6.801172 | 2021-09-22 | Design | 2025-01-08 | 46241 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.812569 | FAASt [Distribution Feeder Rebuild 3502-02] | Distribution | Distribution Line Rebuild | FF | 10.2 | Program Cost Included in PBUT6.812569 | 2021-09-22 | Design | 2025-02-20 | 46337 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT6.817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | 2 | Program Cost Included in PBUT6.817956 | 2021-09-22 | Design | 2025-03-26 | 46407 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.01 | GuanicaTC H.Vol.Eq.Repl.MinRep | Substation | Substation Reliability | NFC | 0 | 5.46 | 2025-07-31 | Execution | 2021-09-01 | 2026-02-28 | N/A | 25% | Engineering & Asset Management | Pedro Melendez
PBUT7.02 | Maunabo TC | Substation | Substation Reliability | NFC | 0 | 0.97 | 2025-07-31 | Execution | 2021-10-01 | 2026-01-31 | N/A | 35% | Engineering & Asset Management | Pedro Melendez
PBUT7.03 | Monacillo TCBreak&TransforRep | Substation | Substation Reliability | NFC | 0 | 4.33 | 2025-07-31 | Close Out | 2022-07-01 | 2025-09-25 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.04 | Reliability AltRioGrande | Substation | Substation Reliability | NFC | 0 | 0 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.05 | Reliability AreciboHospDist | Substation | Substation Reliability | NFC | 0 | 0 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.06 | Reliability HatoReyTC | Substation | Substation Reliability | NFC | 0 | 0 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.07 | Reliability CeibaBaja | Substation | Substation Reliability | NFC | 0 | 0 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.08 | Reliability CharcoHondo | Substation | Substation Reliability | NFC | 0 | 0 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.09 | Reliability Ciales | Substation | Substation Reliability | NFC | 0 | 0 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.10 | Reliability FortAllen | Substation | Substation Reliability | NFC | 0 | 0 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.11 | Reliability HumacaoTC | Substation | Substation Reliability | NFC | 0 | 0.15 | 2025-07-31 | Close Out | 2023-07-01 | 2025-06-15 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.12 | Reliability ManatiTC | Substation | Substation Reliability | NFC | 0 | 0.15 | 2025-07-31 | Close Out | 2023-07-01 | 2025-06-06 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.13 | Reliability VegaAlta9105 | Substation | Substation Reliability | NFC | 0 | 0.03 | 2025-07-31 | Close Out | 2023-07-01 | 2025-02-14 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.14 | Reliability Verdemar | Substation | Substation Reliability | NFC | 0 | 0.01 | 2025-07-31 | Close Out | 2023-07-01 | 2025-01-28 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.15 | Reliability YaucoPueb1 | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2023-07-01 | 2025-01-29 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.16 | L 51100 prot EcoElec to C Sur | Substation | Substation Reliability | NFC | 0 | 0.03 | 2025-07-31 | Execution | 2023-07-01 | 2026-06-30 | N/A | 60% | Engineering & Asset Management | Pedro Melendez
PBUT7.17 | Reliability CanovanasTC | Substation | Substation Reliability | NFC | 0 | 0.08 | 2025-07-31 | Design | 2023-07-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.18 | Reliability BerwindTC | Substation | Substation Reliability | NFC | 0 | 0.19 | 2025-07-31 | Design | 2023-07-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.19 | Reliability Aguada | Substation | Substation Reliability | NFC | 0 | 0.34 | 2025-07-31 | Close Out | 2023-07-01 | 2025-03-06 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.20 | Emer.MonacTC115/38kVTransfRepl | Substation | Substation Reliability | NFC | 0 | 0.01 | 2025-07-31 | Execution | 2023-07-01 | 2025-11-24 | Yes | 80% | Engineering & Asset Management | Pedro Melendez
PBUT7.21 | Maunabo Pueblo 4301-02 CB | Substation | Substation Reliability | NFC | 0 | 0.07 | 2025-07-31 | Close Out | 2024-08-01 | 2024-09-13 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.22 | Arecibo Rural 8003 Transf.Repl | Substation | Substation Reliability | NFC | 0 | 0.13 | 2025-07-31 | Design | 2024-07-01 | 2026-11-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.23 | Monacillos CB 37810 | Substation | Substation Reliability | NFC | 0 | 0.32 | 2025-07-31 | Close Out | 2024-07-01 | 2025-01-13 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.24 | Yabucoa TC RTU Replacement | Substation | Substation Reliability | NFC | 0 | 0.15 | 2025-07-31 | Close Out | 2024-07-01 | 2024-12-31 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.25 | San Juan SP RTU Replacement | Substation | Substation Reliability | NFC | 0 | 0.23 | 2025-07-31 | Design | 2024-07-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.26 | Lloren Torres 1118-08 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-05 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.27 | Minillas 1114 DA Relay Repl | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2024-07-01 | 2025-01-31 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.28 | BTC-Bayamon 1716-02 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-12 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.29 | Naguabo 2701-03 DA Relay Repl | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-13 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.30 | Once De Agosto 6014-01 CB | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Design | 2024-07-01 | 2025-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.31 | Verde Mar 2605-02 DA RelayRepl | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-06 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.32 | PlantaSanturce1117-11 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-31 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.33 | Villamar 1657 - 02 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.02 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-21 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.34 | Monacillo Bank#1 & #3 Trf.Repl | Substation | Substation Reliability | NFC | 0 | 5.14 | 2025-07-31 | Execution | 2024-07-01 | 2025-12-14 | Yes | 80% | Engineering & Asset Management | Pedro Melendez
PBUT7.35 | Yabucoa 230Kv CB Replcmnt-0040 | Substation | Substation Reliability | NFC | 0 | 0.85 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-24 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.36 | 11190 Canóvanas Sect. 38kV | Substation | Substation Reliability | NFC | 0 | 0.4 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-12 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.37 | AguadillaHosp.Distr.7003-02 CB | Substation | Substation Reliability | NFC | 0 | 0.16 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-18 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.38 | Dos Bocas 8005-2 CB | Substation | Substation Reliability | NFC | 0 | 0.16 | 2025-07-31 | Close Out | 2024-07-01 | 2024-12-23 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.39 | Manatí 8401-02 CB | Substation | Substation Reliability | NFC | 0 | 0.16 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-18 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.40 | Ojo de Agua 7002-2 CB | Substation | Substation Reliability | NFC | 0 | 0.16 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-24 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.41 | Ojo de Agua 7002-3 CB | Substation | Substation Reliability | NFC | 0 | 0.19 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-23 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.42 | Pajuil 7702-03 CB | Substation | Substation Reliability | NFC | 0 | 0.16 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-04 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.43 | Peñuelas 5401-01 CB | Substation | Substation Reliability | NFC | 0 | 0.16 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-29 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.44 | Dorado 9207 TC - CB 7810 | Substation | Substation Reliability | NFC | 0 | 0.3 | 2025-07-31 | Close Out | 2024-07-01 | 2024-12-23 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.45 | AES 50270 230kV-CB Replacement | Substation | Substation Reliability | NFC | 0 | 0.5 | 2025-07-31 | Close Out | 2024-07-01 | 2025-11-15 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.46 | Substation Relay Aeropuerto | Substation | Substation Reliability | NFC | 0 | 0.2 | 2025-07-31 | Close Out | 2024-07-01 | 2025-01-27 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.47 | A.BuenasTranRelayRplcFeed39014 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2024-12-06 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.48 | Cana-InterTranRelayRplFeed0020 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-14 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.49 | HatilloTCTranRelayRplcFeed2120 | Substation | Substation Reliability | NFC | 0 | 0.04 | 2025-07-31 | Design | 2024-07-01 | 2026-11-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.50 | IslaGrandeTranRelFeeder 0010 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Design | 2024-07-01 | 2025-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.51 | JobosTCTranRelFeeder 3750 | Substation | Substation Reliability | NFC | 0 | 0.08 | 2025-07-31 | Design | 2024-07-01 | 2025-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.52 | LosAngelesTranRelFeeder 3642 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-27 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.53 | PaloSecoTranRelFeeder 9520 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2025-04-01 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.54 | Fajardo 6T01 Replacement | Substation | Substation Reliability | NFC | 0 | 1.02 | 2025-07-31 | Execution | 2024-07-01 | 2026-03-31 | N/A | 45% | Engineering & Asset Management | Pedro Melendez
PBUT7.55 | Bayamon TC - Phase 1 Trnsformr | Substation | Substation Reliability | NFC | 0 | 2.42 | 2025-07-31 | Execution | 2024-07-01 | 2026-03-06 | N/A | 45% | Engineering & Asset Management | Pedro Melendez
PBUT7.56 | Caguas TC - Phase 1 Transfrmer | Substation | Substation Reliability | NFC | 0 | 1.88 | 2025-07-31 | Execution | 2024-07-01 | 2025-11-30 | Yes | 90% | Engineering & Asset Management | Pedro Melendez
PBUT7.57 | Centro Medico - Phase 1 Trnsfo | Substation | Substation Reliability | NFC | 0 | 0.01 | 2025-07-31 | Design | 2024-07-01 | 2027-01-07 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.58 | Costa Sur - Phase 1 Transfrmer | Substation | Substation Reliability | NFC | 0 | 1.48 | 2025-07-31 | Design | 2024-07-01 | 2026-05-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.59 | Factor - Phase 1 Transformer | Substation | Substation Reliability | NFC | 0 | 0.47 | 2025-07-31 | Design | 2024-07-01 | 2026-01-31 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.60 | Mora - Phase 1 Transformer | Substation | Substation Reliability | NFC | 0 | 0.91 | 2025-07-31 | Execution | 2024-07-01 | 2026-03-02 | N/A | 45% | Engineering & Asset Management | Pedro Melendez
PBUT7.61 | DOE LlorensT13kVMetalcladReplc | Substation | Substation Reliability | NFC | 0 | 5.7 | 2025-07-31 | Design | 2025-08-01 | 2026-04-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.62 | DOE Mayaguez TC 115kv cable | Substation | Substation Reliability | NFC | 0 | 0.5 | 2025-07-31 | Design | 2025-08-01 | 2026-06-30 | N/A | 0% | Engineering & Asset Management | Pedro Melendez
PBUT7.63 | DOE-OOS Relays | Substation | Substation Reliability | NFC | 0 | 0.43 | 2025-07-31 | Execution | 2025-08-01 | 2025-12-31 | Yes | 87% | Engineering & Asset Management | Pedro Melendez
PBUT7.64 | Monacillo 1346 | Substation | Substation Reliability | NFC | 0 | 0.5 | 2025-07-31 | Close Out |  | 2025-09-25 | N/A | 100% | Engineering & Asset Management | Pedro Melendez
PBUT7.65 | Sabana Llana – 544MVA | Substation | Substation Reliability | NFC | 0 | 9.1 | 2025-07-31 | Execution | 2024-07-01 | 2026-02-26 | N/A | 40% | Engineering & Asset Management | Pedro Melendez
PBUT7.746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation Reliability | FF | Pending Obligation | Program Cost Included in PBUT7.746660 | 2021-09-22 | Plan | 2024-04-08 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.01 | 12444 Anasco 115/13.2 kV (L) | Substation | Substation Rebuilds | NFC | 0 | 0.07 | 2025-07-31 | Close Out | 2021-07-01 | 2025-03-01 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT8.02 | HatoReyTC-Transf1420 Emer.Repl | Substation | Substation Rebuilds | NFC | 0 | 3.77 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-01 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT8.165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Substation Rebuilds | FF | 1.46 | 39.1 | 2021-06-08 | Execution | 2020-12-18 | 2029-01-01 | No | 44% | Engineering & Asset Management | Pedro Melendez
PBUT8.165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Substation Rebuilds | FF | 1.39 | 37.91 | 2021-06-08 | Execution | 2020-12-18 | 2029-01-01 | No | 2% | Engineering & Asset Management | Pedro Melendez
PBUT8.165268 | FAASt Rio Grande Estate Substation CH-2306 (Substation) | Substation | Substation Rebuilds | FF | 11.68 | 3.97 | 2021-06-08 | Execution | 2020-12-18 | 2025-08-30 | No | 93% | Engineering & Asset Management | Pedro Melendez
PBUT8.169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Plan | 2021-01-27 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.169266 | FAASt Centro Medico 1327/1359 Equipment Repair & Replacement (Substation) | Substation | Substation Rebuilds | FF | 21.33 | 11.7 | 2021-06-08 | Execution | 2021-01-28 | 2027-01-14 | No | 2% | Engineering & Asset Management | Pedro Melendez
PBUT8.169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement [Substation] | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Plan | 2021-01-28 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | Substation | Substation Rebuilds | FF | 15.34 | 23 | 2021-06-08 | Execution | 2021-01-29 | 2027-09-30 | No | 8% | Engineering & Asset Management | Pedro Melendez
PBUT8.169500 | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | FF | 6.37 | 5.7 | 2021-06-08 | Execution | 2021-01-29 | 2027-05-13 | No | 42% | Engineering & Asset Management | Pedro Melendez
PBUT8.169896 | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | Substation | Substation Rebuilds | FF | 23.25 | 3.6 | 2021-06-08 | Execution | 2021-02-02 | 2026-09-25 | No | 43% | Engineering & Asset Management | Pedro Melendez
PBUT8.174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation Rebuilds | FF | 23.26 | 11.3 | 2021-06-08 | Execution | 2021-03-04 | 2026-08-27 | No | 65% | Engineering & Asset Management | Pedro Melendez
PBUT8.178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation Rebuilds | FF | 13.4 | 4.1 | 2021-06-08 | Design | 2021-03-31 | 2028-03-03 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.178503 | FAASt [Aguirre TC - BKRS] (Substations) | Substation | Substation Rebuilds | FF | 39.03 | 12.2 | 2021-06-08 | Execution | 2021-04-01 | 2029-07-03 | No | 33% | Engineering & Asset Management | Pedro Melendez
PBUT8.178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Plan | 2021-04-01 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | FF | 1.59 | 1.8 | 2021-06-08 | Close Out | 2021-04-09 | 2022-12-12 | Yes | 100% | Engineering & Asset Management | Pedro Melendez
PBUT8.542758 | FAASt [Minor Repairs -Group B] (Substation) | Substation | Substation Rebuilds | FF | 3.41 | 400 | 2021-09-22 | Execution | 2021-10-26 | 2026-12-30 | No | 76% | Engineering & Asset Management | Pedro Melendez
PBUT8.546370 | FAASt - Substation Minor Repairs Group A (Substation) | Substation | Substation Rebuilds | FF | 4.9 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-11-09 | 2026-09-13 | No | 70% | Engineering & Asset Management | Pedro Melendez
PBUT8.546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | FF | 3.03 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-11-09 | 2025-12-14 | No | 76% | Engineering & Asset Management | Pedro Melendez
PBUT8.547187 | FAASt - [Substation Component Replacement Program] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 17.1 | 2021-10-18 | Plan | 2021-11-15 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | FF | 2.8 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-12-03 | 2026-05-08 | No | 33% | Engineering & Asset Management | Pedro Melendez
PBUT8.549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation Rebuilds | FF | 4.5 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-12-03 | 2026-07-10 | No | 54% | Engineering & Asset Management | Pedro Melendez
PBUT8.550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 5.1 | 2021-10-18 | Plan | 2021-12-07 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.550950 | FAASt - EPC - [Monacillo TC] (Substations) | Substation | Substation Rebuilds | FF | 88.1 | 105.23 | 2024-01-18 | Execution | 2021-12-14 | 2028-09-13 | No | 11% | Engineering & Asset Management | Pedro Melendez
PBUT8.551914 | FAASt [Caparra 1911 & 1924] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 6.6 | 2021-10-18 | Plan | 2021-12-21 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | FF | 90.5 | 192.27 | 2022-08-25 | Execution | 2022-09-07 | 2029-05-04 | No | 4% | Engineering & Asset Management | Pedro Melendez
PBUT8.682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 124.5 | 2024-06-28 | Plan | 2022-09-12 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation Rebuilds | FF | 8.2 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2022-09-15 | 2028-08-23 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Substation | Substation Rebuilds | FF | 61.4 | 161.98 | 2022-08-25 | Execution | 2022-09-16 | 2029-12-30 | No | 1% | Engineering & Asset Management | Pedro Melendez
PBUT8.684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | FF | 6.93 | 75.7 | 2022-08-25 | Execution | 2022-10-06 | 2026-02-07 | Yes | 95% | Engineering & Asset Management | Pedro Melendez
PBUT8.723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 42.9 | 2022-12-10 | Plan | 2023-06-15 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | FF | 100.69 | 125.5 | 2022-12-10 | Execution | 2023-06-16 | 2028-11-22 | No | 10% | Engineering & Asset Management | Pedro Melendez
PBUT8.723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | FF | 61.56 | 89.7 | 2022-12-10 | Execution | 2023-06-16 | 2028-09-13 | No | 2% | Engineering & Asset Management | Pedro Melendez
PBUT8.729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation Rebuilds | FF | 15.4 | Program Cost Included in PBUT8.542758 | 2022-08-25 | Execution | 2023-08-23 | 2028-05-14 | No | 46% | Engineering & Asset Management | Pedro Melendez
PBUT8.743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation Rebuilds | FF | 17.3 | Program Cost Included in PBUT8.542758 | 2022-08-25 | Execution | 2024-01-29 | 2028-04-23 | No | 10% | Engineering & Asset Management | Pedro Melendez
PBUT8.825843 | FAAST [Guanica Transformer Replacement] (Substation) | Substation | Substation Rebuilds | FF | 2.3 | Program Cost Included in PBUT8.825843 | 2025-03-24 | Execution | 2025-06-23 | 46076 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Substation Rebuilds | FF | 3.7 | Program Cost Included in PBUT8.956593 | 2025-03-24 | Execution | 2025-06-23 | 46172 | No | 0% | Engineering & Asset Management | Pedro Melendez
PBUT8.957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Substation Rebuilds | FF | 1.1 | Program Cost Included in PBUT8.957578 | 2025-02-06 | Design | 2025-06-18 | 46203 | No | 0% | Engineering & Asset Management | Pedro Melendez
PUBT37.751655 | FAASt [Vieques Microgrid] (Transmission) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2024-02-15 | Plan | 2024-07-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
PUBT37.751656 | FAASt [Culebra Microgrid] (Transmission) | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2024-02-15 | Plan | 2024-07-18 | Pending Obligation | Pending Obligation | 0% | Engineering & Asset Management | Pedro Melendez
Annex A