## Summary
Summary for Q1 - FY2026 Report:
| FY2026 Q1 Miles |  |  | FY2026 YTD Miles |  |  | FY2026 Q1 Acres* |  |  | FY2026 YTD Acres*
Voltage | Federally Funded Clearing** | OpEx Maintenance | Total Miles | Federally Funded Clearing** | OpEx Maintenance | Total Miles | Federally Funded Clearing** | OpEx Maintenance | Total Acres | Federally Funded Clearing** | OpEx Maintenance | Total Acres
Distribution | 141 | 318.4 | 459.4 | 141 | 318.4 | 459.4 | 170.9091 | 385.9394 | 556.8485 | 170.9091 | 385.9394 | 556.8485
38 kV | 0 | 36 | 36 | 0 | 36 | 36 | 0 | 109.0909 | 109.0909 | 0 | 109.0909 | 109.0909
115 kV | 0 | 132.6 | 132.6 | 0 | 132.6 | 132.6 | 0 | 1607.2727 | 1607.2727 | 0 | 1607.2727 | 1607.2727
230 kV | 0 | 78.4 | 78.4 | 0 | 78.4 | 78.4 | 0 | 950.303 | 950.303 | 0 | 950.303 | 950.303
Total | 141 | 565.4 | 706.4 | 141 | 565.4 | 706.4 | 170.9091 | 3052.6061 | 3223.5152 | 170.9091 | 3052.6061 | 3223.5152
*To calculate acres from miles, the miles are converted to feet by multiplying by 5,280. Then the width of the right of way is assumed for each voltage level (distribution = 10’, 38 kV = 25’, and 115 & 230 kV = 100’). The miles (in feet) are multiplied by the ROW width (in feet) to determine the square feet completed. Finally, the square feet are converted to acres by dividing by 43,560 sq feet per acre. Note: Figures may not add up due to rounding. **For federally funded miles and acres, the reported figures include both completed work and, in certain circuits, miles assessed as clear spans. All circuits reported have undergone physical vegetation clearing activities.
Vegetation Management Progress Report

## Primary Transmission Lines
etro
Primary Transmission Lines
Line Voltage (kV) | Transmission Lines ID # | Impacted Zone1 | Circuit Miles Maintained / Cleared | # of Towers / Poles Impacted | Urban or Rural Site | Right of Way (ROWs) Width | ROW Acres Maintained / Cleared | Name of Contractor | Resources Assigned & Their Clasifications (Luma Employees and Contractors) | Type of Response2 | Type of VM Implemented 3 | Type of VM Disposal Clasification4 | Recommendations for Future VM5 | VM Activity Point of Contact (POC) | Funding Source
38 | 3000 | Wire/Border/Strike | 0.71 | 24 | Urban | 25 | 2.15 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9100 | Wire/Border/Strike | 1.85 | 62 | Urban | 25 | 5.61 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.06 | 2 | Urban | 25 | 0.18 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15300 | Wire/Border/Strike | 0.17 | 6 | Urban | 25 | 0.52 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.09 | 3 | Urban | 25 | 0.27 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900, 15500 | Wire/Border/Strike | 0.28 | 9 | Urban | 25 | 0.85 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100, 38500, 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800, 40400, 38500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800, 40400, 38501 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100, 38500, 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400, 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700, 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700, 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700, 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700, 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 51000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 51000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 51000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 51000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 51000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 51000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800, 38500, 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800, 38500, 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38100, 38800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.36 | 2 | Urban | 100 | 4.36 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 12600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5300 | Wire/Border/Strike | 0.34 | 11 | Rural | 25 | 1.03 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8500 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10600 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3700 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 800 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Wright Tree |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300, 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300, 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300, 7900 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.03 | 1 | Urban | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2100 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire/Border/Strike | 0.18 | 1 | Rural | 100 | 2.18 | Site |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | PIS |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2200 | Wire/Border/Strike | 0.03 | 1 | Rural | 25 | 0.09 | Xperts |  | Corrective | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 1.5 | 50 | Rural | 25 | 4.55 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 1.3 | 43 | Rural | 25 | 3.94 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 1 | 33 | Rural | 25 | 3.03 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 1 | 33 | Rural | 25 | 3.03 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.65 | 22 | Rural | 25 | 1.97 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 1.1 | 37 | Rural | 25 | 3.33 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.7 | 23 | Rural | 25 | 2.12 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.9 | 30 | Rural | 25 | 2.73 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.4 | 13 | Rural | 25 | 1.21 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire/Border/Strike | 0.7 | 23 | Rural | 25 | 2.12 | Wright Tree |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 0.14 | 1 | Urban | 100 | 1.7 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.12 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.12 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.35 | 2 | Urban | 100 | 4.24 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.14 | 1 | Urban | 100 | 1.7 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.49 | 3 | Urban | 100 | 5.94 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.49 | 3 | Urban | 100 | 5.94 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.26 | 1 | Urban | 100 | 3.15 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.26 | 1 | Urban | 100 | 3.15 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 0.2 | 1 | Urban | 100 | 2.42 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.12 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 0.18 | 1 | Urban | 100 | 2.12 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.14 | 1 | Urban | 100 | 1.7 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.6 | 3 | Rural | 100 | 7.27 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.36 | 2 | Rural | 100 | 4.36 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 1.58 | 9 | Rural | 100 | 19.15 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 0.07 | 0 | Urban | 100 | 0.85 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 0.07 | 0 | Urban | 100 | 0.85 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 2.62 | 15 | Rural | 100 | 31.76 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire/Border/Strike | 9.78 | 54 | Urban | 100 | 118.55 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 2 | 11 | Urban | 100 | 24.24 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire/Border/Strike | 7.2 | 40 | Urban | 100 | 87.27 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37700 | Wire/Border/Strike | 4.25 | 24 | Urban | 100 | 51.52 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire/Border/Strike | 4.38 | 24 | Urban | 100 | 53.09 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700 | Wire/Border/Strike | 6.04 | 34 | Urban | 100 | 73.21 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38600 | Wire/Border/Strike | 4.76 | 26 | Urban | 100 | 57.7 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 2 | 11 | Urban | 100 | 24.24 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire/Border/Strike | 1.3 | 7 | Urban | 100 | 15.76 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire/Border/Strike | 0.48 | 3 | Rural | 100 | 5.82 | Xperts |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.8 | 4 | Rural | 100 | 9.7 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.21 | 1 | Rural | 100 | 2.55 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.27 | 2 | Rural | 100 | 3.27 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.05 | 6 | Rural | 100 | 12.73 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.01 | 6 | Rural | 100 | 12.24 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.34 | 7 | Rural | 100 | 16.24 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.09 | 1 | Rural | 100 | 1.09 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.92 | 5 | Rural | 100 | 11.15 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.61 | 3 | Rural | 100 | 7.39 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.35 | 8 | Rural | 100 | 16.36 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.13 | 1 | Rural | 100 | 1.58 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.98 | 5 | Rural | 100 | 11.88 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.6 | 3 | Rural | 100 | 7.27 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.73 | 4 | Rural | 100 | 8.85 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.42 | 2 | Rural | 100 | 5.09 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.13 | 1 | Rural | 100 | 1.58 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.44 | 2 | Rural | 100 | 5.33 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.17 | 1 | Rural | 100 | 2.06 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.71 | 4 | Rural | 100 | 8.61 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.26 | 7 | Rural | 100 | 15.27 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1 | 6 | Rural | 100 | 12.12 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.13 | 6 | Rural | 100 | 13.7 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.03 | 6 | Rural | 100 | 12.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.25 | 1 | Rural | 100 | 3.03 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.81 | 5 | Rural | 100 | 9.82 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.2 | 1 | Rural | 100 | 2.42 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.14 | 1 | Rural | 100 | 1.7 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.38 | 2 | Rural | 100 | 4.61 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.2 | 1 | Rural | 100 | 2.42 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.8 | 4 | Rural | 100 | 9.7 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.51 | 3 | Rural | 100 | 6.18 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.51 | 3 | Rural | 100 | 6.18 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.51 | 3 | Rural | 100 | 6.18 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.51 | 3 | Rural | 100 | 6.18 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.51 | 3 | Rural | 100 | 6.18 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.51 | 3 | Rural | 100 | 6.18 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 1.36 | 8 | Rural | 100 | 16.48 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire/Border/Strike | 0.26 | 1 | Rural | 100 | 3.15 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire/Border/Strike | 0.26 | 1 | Rural | 100 | 3.15 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire/Border/Strike | 0.76 | 4 | Rural | 100 | 9.21 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire/Border/Strike | 0.76 | 4 | Rural | 100 | 9.21 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire/Border/Strike | 0.83 | 5 | Rural | 100 | 10.06 | Site |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.65 | 22 | Rural | 25 | 1.97 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.65 | 22 | Rural | 25 | 1.97 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.5 | 17 | Rural | 25 | 1.52 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.5 | 17 | Rural | 25 | 1.52 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.4 | 13 | Rural | 25 | 1.21 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.4 | 13 | Rural | 25 | 1.21 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 1 | 6 | Rural | 100 | 12.12 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.5 | 3 | Rural | 100 | 6.06 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.7 | 23 | Rural | 25 | 2.12 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.7 | 23 | Rural | 25 | 2.12 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 1.1 | 6 | Rural | 100 | 13.33 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 1.1 | 6 | Rural | 100 | 13.33 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.3 | 10 | Rural | 25 | 0.91 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.3 | 10 | Rural | 25 | 0.91 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 1.2 | 7 | Rural | 100 | 14.55 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 1.2 | 7 | Rural | 100 | 14.55 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 1.1 | 6 | Rural | 100 | 13.33 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 1.1 | 6 | Rural | 100 | 13.33 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 2.7 | 15 | Rural | 100 | 32.73 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 2.7 | 15 | Rural | 100 | 32.73 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.9 | 5 | Rural | 100 | 10.91 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 0.9 | 5 | Rural | 100 | 10.91 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.9 | 30 | Rural | 25 | 2.73 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.9 | 30 | Rural | 25 | 2.73 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.8 | 27 | Rural | 25 | 2.42 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.8 | 27 | Rural | 25 | 2.42 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 1.5 | 50 | Rural | 25 | 4.55 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 1.5 | 50 | Rural | 25 | 4.55 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 0.5 | 3 | Rural | 100 | 6.06 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire/Border/Strike | 0.5 | 3 | Rural | 100 | 6.06 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire/Border/Strike | 0.6 | 20 | Rural | 25 | 1.82 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire/Border/Strike | 0.6 | 20 | Rural | 25 | 1.82 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire/Border/Strike | 1.1 | 6 | Rural | 100 | 13.33 | PIS |  | Preventative | Physical / Chemical | Chip/Haul |  | Daniel Perry | Operation Exp
|  | Total | 247.02 |  |  |  | 2665.13
1 IMPACTED ZONE - WIRE ZONE, BORDER ZONE, STRIKE ZONE
2 TYPE OF RESPONSE - REACTIVE, CORRECTIVE, PREVENTIVE
3 TYPE OF VM IMPLEMENTED - BIOLOGICAL, PHYSICAL OR CHEMICAL CONTROL
4 TYPE OF VM DISPOSAL CLASIFICATION - CHIP & HAUL, CHIP & BLOW, PILE / WINDROW, LOP & SCATTER, MULCHIN
5 RECOMMENDATIONS FOR FUTURE Describe recommended species, cadence of any herbicide application
Vegetation Management Progress Report Q1 FY2026

## Substations
Substations
Substations ID | Primary Voltages | Secondary Voltages | KVA | Maintained Area | Urban or Rural Site | Municipalities Impacted | Name of Contractor | Resources Assigned & Their Classifications (LUMA Employees and Contractors) | Type of Response1 | Type of VM Implemented2 | Type of VM Disposal Clasification3 | Recomendations for Future VM4 | VM Activity Point of Contact (POC) | Funding Source | Photos Before/After
1206 | 38000 | 4160 | 7500/11300 | 0.4 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1109 | 38000 | 4160 | 7500/11300 | 0.14 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1110 | 38000 | 4160 | 7500/11300 | 0.06 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1105 | 38000 | 4160 | 7500/11300 | 0.08 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1133 | 38000 | 4160 | 7500/11300 | 0.15 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1422/1424 | 115000 | 38000 | 60/80/100/112 MVA | 0.49 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1201 | 38000 | 4160 | 3000/3750 | 0.09 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
INTERMEDIA T.O. VILLA DE CANEY | 115000 | 38000 | 30/40/50/56 MVA | 0.06 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1205 | 115000 | 4160 | 7500/11300 | 0.29 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1203 | 38000 | 4160 | 5000/7500 | 0.32 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2402/2404 | 230000 | 13200 | 75/100/125 MVA | 1.2 | Urban | Canovanas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1419/1420 | 115000 | 38000 | 60/80/100/112 MVA | 2.62 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1107 | 38000 | 4160 | 7500/11300 | 0.18 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8504 | 38000 | 4160 | 7.5/10/11.2 | 0.27 | Urban | Barceloneta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1002 | 38000 | 4160 | 7500/10500 | 0.15 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8602 | 38000 | 4160 | 7500/10500 | 0.18 | Urban | Florida | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1102 | 38000 | 4160 | 7500/11300 | 0.25 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1104 | 38000 | 4160 | 7500/11300 | 0.16 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1101 | 38000 | 4160 | 3072/4000 | 0.34 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1119/1120 | 115000 | 13200 | 18/24/30/33.6 MVA | 0.14 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1001 | 38000 | 4160 | 7500/10500 | 0.25 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8801 | 38000 | 4160 | 7500/11300 | 0.34 | Urban | Morovis | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8701 | 38000 | 4160 | 7500/11300 | 0.42 | Urban | Ciales | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7801/7802/7805 | 230000 | 13200 | 75/100/125 MVA | 0.67 | Urban | San Sebastian | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1401/1421 | 115000 | 38000 | 60/80/100/112 MVA | 0.39 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
BARCELONETA TC | 115000 | 38000 | 30/40/50/56 MVA | 0.91 | Urban | Barceloneta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9501 | 38000 | 4160 | 7500/11300 | 0.74 | Urban | Corozal | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1416 | 38000 | 4160 | 7500/11300 | 0.17 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9502/9503 | 230000 | 13200 | 75/100/125 MVA | 0.29 | Urban | Corozal | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8007 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.28 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8103 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Utuado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1327/1359 | 115000 | 38000 | 60/80/100/112 MVA | 0.27 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1310 | 38000 | 4160 | 7500/11300 | 0.27 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1529 | 38000 | 4160 | 7500/11300 | 0.16 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1526/1530 | 115000 | 38000 | 60/80/100/112 MVA | 0.27 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1531 | 38000 | 4160 | 7500/11300 | 0.21 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1418 | 38000 | 4160 | 7500/11300 | 0.24 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1519/1521 | 115000 | 38000 | 60/80/100/112 MVA | 0.21 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8002 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.09 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8011/8014 | 230000 | 13200 | 75/100/125 MVA | 0.38 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8001/8003/8012/8015 | 230000 | 13200 | 75/100/125 MVA | 0.38 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
PORTATIL AEE CHARCO HONDO | 13000 | 480 | 2.5KVA | 0.04 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1512 | 38000 | 4160 | 7500/11300 | 0.18 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1329 | 38000 | 4160 | 7500/11300 | 0.21 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1338 | 38000 | 4160 | 7500/11300 | 0.19 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1345 | 38000 | 4160 | 7500/11300 | 0.12 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1342 | 38000 | 4160 | 7500/11300 | 0.21 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1910 | 38000 | 4800 | 5000/6250 | 0.08 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1414 | 38000 | 4160 | 7500/11300 | 0.17 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8004 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.35 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8010 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.12 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8005 | 115000 | 13200 | 24/32/40/44.8 MVA | 2.27 | Urban | Utuado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2702 | 38000 | 4800 | 5000/6250 | 0.2 | Urban | Naguabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2602/2603 | 230000 | 13200 | 75/100/125 MVA | 2.42 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
CAMBALACHE GP TC | 115000 | 38000 | 30/40/50/56 MVA | 2.98 | Urban | Arecibo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2906 | 38000 | 4800 | 5000/6250 | 0.58 | Urban | Yabucoa | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8104 | 38000 | 4160 | 7500/10500 | 0.33 | Urban | Utuado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1520 | 38000 | 4160 | 7500/11300 | 0.25 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
HATILLO TC | 115000 | 38000 | 30/40/50/56 MVA | 1.39 | Urban | Hatillo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6001/6014 | 230000 | 13200 | 75/100/125 MVA | 0.47 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8101 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.07 | Urban | Utuado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1116/1117 | 38000 | 13200 | 18/24/30/33.6 MVA | 0.25 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1423 | 38000 | 4160 | 7500/11300 | 0.1 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1437 | 38000 | 4160 | 7500/11300 | 0.12 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7701 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.23 | Urban | Hatillo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7702 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.07 | Urban | Hatillo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8013 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.38 | Urban | Hatillo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1616 | 38000 | 4160 | 7500/10500 | 0.17 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7403 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.05 | Urban | Quebradillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7525 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.19 | Urban | Quebradillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7402/7404 | 230000 | 13200 | 75/100/125 MVA | 0.23 | Urban | Quebradillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7601/7602 | 230000 | 13200 | 75/100/125 MVA | 0.35 | Urban | Camuy | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3009 | 38000 | 4800 | 5000/6250 | 0.33 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3016 | 38000 | 4800 | 5000/6250 | 0.74 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3005 | 38000 | 4800 | 5000/6250 | 0.12 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3010 | 38000 | 4800 | 5000/6250 | 0.73 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3013 | 38000 | 4800 | 5000/6250 | 0.55 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7504 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.02 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7506 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.36 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7502 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.29 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7012 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7503 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.15 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
ISABELA T.O. | 115000 | 38000 | 30/40/50/56 MVA | 0.28 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
MOCA GIS | 115000 | 38000 | 30/40/50/56 MVA | 0.48 | Urban | Moca | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2604 | 38000 | 4800 | 5000/6250 | 2.48 | Urban | Yabucoa | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3007/3015 | 230000 | 13200 | 75/100/125 MVA | 0.37 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3014 | 38000 | 4800 | 5000/6250 | 0.5 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7103 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.32 | Urban | Moca | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7101 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.13 | Urban | Moca | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1111/1112/1113 | 115000 | 13200 | 18/24/30/33.6 MVA | 1.14 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7302 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.11 | Urban | Rincon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9201 | 38000 | 4160 | 7500/11300 | 0.15 | Urban | Dorado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9202/9206 | 230000 | 13200 | 75/100/125 MVA | 0.43 | Urban | Dorado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9203/9207 | 230000 | 13200 | 75/100/125 MVA | 1.25 | Urban | Dorado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9001/9003/9004 | 230000 | 13200 | 75/100/125 MVA | 1.15 | Urban | Vega Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
DUPONT SWITCH YARD | 115000 | 38000 | 30/40/50/56 MVA | 0.05 | Urban | Manati | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8405 | 38000 | 4160 | 7500/11300 | 0.33 | Urban | Manati | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3725 | 38000 | 8320 | 7500 | 3.6 | Urban | Aguas Buenas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9002 | 38000 | 4160 | 7500/11300 | 0.27 | Urban | Vega Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9103 | 38000 | 4160 | 7500/11300 | 0.37 | Urban | Vega Alta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9101/9105 | 230000 | 13200 | 75/100/125 MVA | 0.38 | Urban | Vega Alta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3301 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | San Lorenzo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8401 | 38000 | 4160 | 7500/11300 | 0.23 | Urban | Manati | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3101 | 38000 | 4800 | 5000/6250 | 0.13 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3102 | 38000 | 4800 | 5000/6250 | 0.18 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3701 | 38000 | 8320 | 7500 | 0.19 | Urban | Aguas Buenas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8404 | 38000 | 4160 | 7500/11300 | 3.68 | Urban | Manati | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3202 | 38000 | 4800 | 5000/6250 | 0.14 | Urban | Juncos | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3103 | 38000 | 4800 | 5000/6250 | 0.49 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7303 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.42 | Urban | Rincon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3601 | 38000 | 4800 | 5000/6250 | 0.24 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7301 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Rincon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8501 | 38000 | 4160 | 7500/11300 | 0.24 | Urban | Barceloneta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3302 | 38000 | 4800 | 5000/6250 | 0.38 | Urban | San Lorenzo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8301/8302 | 230000 | 13200 | 75/100/125 MVA | 0.6 | Urban | Jayuya | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3602 | 38000 | 8320 | 7500 | 0.6 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3603/3604 | 230000 | 13200 | 75/100/125 MVA | 0.33 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7201 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.21 | Urban | Aguada | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6101 | 38000 | 13200 | 24/32/40/44.8 MVA | 0.67 | Urban | Anasco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6012 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.42 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6305 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.17 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6201 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.18 | Urban | Las Marias | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6306 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.06 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8202 | 38000 | 4160 | 7500/11300 | 0.11 | Urban | Adjuntas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8203 | 38000 | 4160 | 7500/11300 | 0.15 | Urban | Adjuntas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6301 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.16 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1303 | 38000 | 4160 | 7500/11300 | 0.63 | Urban | Cupey Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9404 | 38000 | 4160 | 7500/11300 | 0.23 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6303 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.03 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6010 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.12 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6003 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6002 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.11 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1706 | 38000 | 4160 | 7500/10500 | 0.21 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7902 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.07 | Urban | Lares | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7901/7903 | 230000 | 13200 | 75/100/125 MVA | 0.36 | Urban | Lares | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1704 | 38000 | 4160 | 7500/10500 | 0.15 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1705 | 38000 | 4160 | 7500/10500 | 0.15 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1734 | 38000 | 4800 | 5000/6250 | 0.08 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1707 | 38000 | 4160 | 7500/10500 | 0.24 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3403 | 38000 | 4800 | 5000/6250 | 0.02 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7003 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.53 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3405 | 38000 | 4800 | 5000/6250 | 0.15 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1708 | 38000 | 4160 | 7500/10500 | 0.24 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1652 | 38000 | 4160 | 7500/10500 | 0.2 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2302 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2306 | 38000 | 4800 | 5000/6250 | 0.2 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2301 | 38000 | 4800 | 5000/6250 | 0.17 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7011 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.17 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1602 | 38000 | 4160 | 7500/11300 | 0.37 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1618/1619 | 115000 | 38000 | 60/80/100/112 MVA | 0.22 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7004 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7005 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7006 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.17 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7008 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.25 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1802 | 38000 | 4800 | 5000/6250 | 0.16 | Urban | Catano | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7002 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.07 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1803 | 38000 | 4800 | 5000/6250 | 0.44 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1907/1909 | 115000 | 38000 | 60/80/100/112 MVA | 0.58 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1901/1904 | 115000 | 38000 | 60/80/100/112 MVA | 0.26 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1903 | 38000 | 4800 | 5000/6250 | 0.22 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6801/6802 | 230000 | 13200 | 75/100/125 MVA | 1.95 | Urban | Hormigueros | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1709/1720 | 115000 | 38000 | 60/80/100/112 MVA | 0.78 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1911/1912/1924 | 115000 | 38000 | 60/80/100/112 MVA | 0.46 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6404 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.59 | Urban | San German | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4601 | 38000 | 8320 | 7500 | 0.21 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4602 | 38000 | 8320 | 7500 | 0.25 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1334 | 38000 | 4160 | 7500/11300 | 0.02 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4402 | 38000 | 8320 | 7500 | 1.34 | Urban | Santa Isabel | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1615 | 38000 | 4160 | 8.5/11.33/12.67 MVA | 0.18 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1607 | 38000 | 4160 | 7500/11300 | 0.31 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1106/1118 | 38000 | 4160 | 7500/11300 | 0.27 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1617 | 38000 | 4160 | 7500/10500 | 0.26 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1114 | 38000 | 13200 | 12/16/20/22.4 MVA | 0.24 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1620 | 38000 | 4160 | 7500/10500 | 0.66 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1335 | 38000 | 4160 | 7500/11300 | 0.22 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1403/1404 | 115000 | 38000 | 60/80/100/112 MVA | 0.33 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1336/1301 | 115000 | 38000 | 60/80/100/112 MVA | 0.89 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2401 | 38000 | 4800 | 5000/6250 | 0.23 | Urban | Canovanas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1011/1012/1013/1014 | 38000 | 4160 | 12/16 MVA | 0.23 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1525 | 38000 | 4160 | 7500/11300 | 0.3 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2403 | 38000 | 4800 | 5000/6250 | 0.32 | Urban | Loiza | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4001 | 38000 | 8320 | 7500 | 0.5 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1204 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.74 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1328/1348 | 115000 | 38000 | 60/80/100/112 MVA | 0.34 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5801 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.29 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
SAN JUAN SP TC/PUERTO NUEVO | 13000 | 480 | 2.5KVA | 1.61 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9601/9602 | 230000 | 13200 | 75/100/125 MVA | 1.67 | Urban | Barranquitas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9605 | 38000 | 4160 | 7500/11300 | 0.11 | Urban | Barranquitas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1657 | 38000 | 4160 | 7500/10500 | 0.22 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1658 | 38000 | 4160 | 7500/10500 | 0.49 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
MAUNABO TC | 115000 | 38000 | 30/40/50/56 MVA | 0.82 | Urban | Maunabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4301 | 38000 | 8320 | 7500 | 0.15 | Urban | Maunabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2305 | 38000 | 4800 | 5000/6250 | 0.89 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2901 | 38000 | 4800 | 5000/6250 | 0.17 | Urban | Yabucoa | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4006 | 38000 | 8320 | 7500 | 0.74 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4101 | 38000 | 4160 | 7500/11300 | 0.22 | Urban | Arroyo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3008 | 38000 | 8320 | 7500/11300 | 0.62 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1806 | 115000 | 13200 | 24/32/40/44.8 MVA | 2.81 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4201 | 38000 | 4160 | 7500/11300 | 0.21 | Urban | Patillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5021 | 38000 | 8320 | 7500 | 0.09 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1908 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.65 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
Zona Libre | N/A | N/A | N/A | 0.35 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6004 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.2 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6705 | 38000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6015 | 38000 | 13200 | 9/12/13.4 MVA | 0.41 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6008 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.49 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6702 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.28 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6704 | 38000 | 13200 | 12/16/20/22.4 MVA | 0.24 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6005 | 38000 | 4160 | 5000/5600/7500 | 1.03 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2701 | 38000 | 4160 | 7500/10500 | 0.18 | Urban | Naguabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6102 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.19 | Urban | Anasco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2801 | 38000 | 4160 | 7.5/10/11.2 | 0.24 | Urban | Las Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2201 | 38000 | 8320 | 7500/11300 | 0.24 | Urban | Luquillo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2605 | 38000 | 13200 | 7500/9375/10500 KVA | 0.23 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2006 | 38000 | 13200 | 12/16/20/22.4 MVA | 0.54 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3401 | 38000 | 8320 | 8.5/11.33/12.67 MVA | 1.89 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3406/3402 | 230000 | 13200 | 75/100/125 MVA | 0.44 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4504 | 38000 | 8320 | 7500 | 0.17 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
Horizon SY | 115000 | 38000 | 30/40/50/56 MVA | 0.38 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3501 | 38000 | 4800 | 5000/6250 | 0.09 | Urban | Aibonito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3502 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Aibonito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9703 | 38000 | 4160 | 7500/11300 | 0.18 | Urban | Comerio | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
COMERIO TC | 115000 | 38000 | 30/40/50/56 MVA | 1.82 | Urban | Comerio | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4002 | 38000 | 8320 | 7500 | 0.18 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2003 | 38000 | 4800 | 5000/6250 | 0.13 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2002 | 38000 | 4800 | 5000/6250 | 0.08 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2001/2005 | 115000 | 38000 | 60/80/100/112 MVA | 0.92 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4003 | 38000 | 8320 | 7500 | 3.84 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3870 | 38000 | 8320 | 7500 | 0.05 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2601 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4503 | 38000 | 8320 | 7500 | 0.09 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2101 | 38000 | 4800 | 5000/6250 | 2.02 | Urban | Ceiba | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4502 | 38000 | 8320 | 7500 | 0.23 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4501 | 38000 | 8320 | 7500 | 0.22 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1711/1714/1716 | 115000 | 38000 | 60/80/100/112 MVA | 7.5 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1330/1346 | 115000 | 38000 | 60/80/100/112 MVA | 2.48 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1100/1115 | 38000 | 4160 | 7500/11300 | 1.16 | Urban | Santurce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1343 | 38000 | 4160 | 7500/11300 | 0.28 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1710/1712/1719 | 115000 | 38000 | 60/80/100/112 MVA | 1.14 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6006 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.15 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
|  |  | Total | 121.56
1 TYPE OF RESPONSE - REACTIVE, CORRECTIVE, PREVENTIVE
2 TYPE OF VM IMPLEMENTED - BIOLOGICAL, PHYSICAL OR CHEMICAL CONTROL
3 TYPE OF VM DISPOSAL CLASIFICATION - CHIP & HAUL, CHIP & BLOW, PILE / WINDROW, LOP & SCATTER, MULCHIN
4 RECOMMENDATIONS FOR FUTURE VM - Describe recommended species, cadence of any herbicide application
Vegetation Management Progress Report Q1 FY2026

## Distribution Lines
Distribution Lines
Line Voltage (kV) | Primary Distribution Line ID # | Impacted Zone1 | Circuit Miles Maintained / Cleared | # of Poles Impacted | Urban or Rural Site | Municipalities Impacted | Right of Way (Rows) Width | Name of Contractor | Resources Assigned & Their Clasifications (Luma Employees and Contractors) | Type of Response2 | Type of VM Implemented 3 | Type of VM Disposal Clasification4 | Recommendations for Future VM5 | Luma Labor Required | VM Activity Point of Contact (POC) | Funding Source | Photos Before/After
8 | 9501-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Vega Alta | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp |  | Federal PA Obligated Funds
240 | 8001-01 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Arecibo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp |  | Nonfederal Funds
13.2 | 8405-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Barceloneta | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp |  | Operation Exp
240 | 8104-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 8011-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8501-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Barceloneta | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9001-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Vega Baja | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8203-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8015-09 / 8003-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 7402-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Camuy | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8101-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 7702-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7702-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hatillo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8101-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 7701-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8203-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 8701-04 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Ciales | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8203-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8010-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8203-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8008-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7402-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Camuy | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7402-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Quebradillas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8203-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8302-05 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8001-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7702-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8101-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9003-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Vega Baja | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8101-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8302-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8203-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8602-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7403-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Quebradillas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-05 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8010-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hatillo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8005-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8602-03 | Wire Zone / Border Zone | 0.2 | 7 | Urban | Florida | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8101-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7402-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Quebradillas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Ciales | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7404-06 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Quebradillas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9001-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Vega Baja | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8202-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-02 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8504-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Barceloneta | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7402-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Quebradillas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7402-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Quebradillas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8103-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8202-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13 | 8405-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Manati | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8101-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8302-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8005-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8602-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Florida | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8101-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8302-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8014-08 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 9103-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Vega Alta | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8801-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Morovis | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 8504-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Barceloneta | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8104-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8602-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Arecibo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1707-04 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1707-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1718-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Toa Baja | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 1801-03 | Wire Zone / Border Zone | 0.51 | 17 | Urban | Catano | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1901-03 | Wire Zone / Border Zone | 0.23 | 8 | Urban | Guaynabo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1734-02 | Wire Zone / Border Zone | 0.85 | 28 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9801-01 | Wire Zone / Border Zone | 0.71 | 24 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1806-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Toa Baja | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1343-05 | Wire Zone / Border Zone | 0.23 | 8 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 9103-01 | Wire Zone / Border Zone | 0.28 | 9 | Urban | Dorado | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1710-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1704-1 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1908-03 | Wire Zone / Border Zone | 0.34 | 11 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1734-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1716-03 | Wire Zone / Border Zone | 0.71 | 24 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1343-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1924-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1734-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1707-03 | Wire Zone / Border Zone | 0.2 | 7 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1703-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 1801-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Catano | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1710-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9401-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1705-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9301-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Dorado | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9502-03 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Naranjito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9503-06 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Corozal | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9801-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Naranjito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1343-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9801-03 | Wire Zone / Border Zone | 0.28 | 9 | Urban | Naranjito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1706-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9801-03 | Wire Zone / Border Zone | 0.2 | 7 | Urban | Naranjito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1734-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9801-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Naranjito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9202-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Dorado | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9403-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1719-19 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 9401-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1801-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1706-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1706-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9801-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1908-03 | Wire Zone / Border Zone | 0.88 | 29 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1708-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1703-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1924-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1705-03 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1908-04 | Wire Zone / Border Zone | 0.43 | 14 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9801-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1806-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Catano | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1716-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1710-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2701-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Humacao | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 3009-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2701-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Naguabo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3701-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguas Buneas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3201-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9902-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Orocovis | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3007-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3202-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3604-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3007-03 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3013-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3201-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3301-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3205-07 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 3014-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3701-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Aguas Buneas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-04 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9703-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3103-02 | Wire Zone / Border Zone | 0.4 | 13 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3604-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguas Buneas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3102-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9703-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3301-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3005-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3201-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3102-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3302-04 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2601-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Piedras | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3201-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juncos | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3302-01 | Wire Zone / Border Zone | 0.37 | 12 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2701-01 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Naguabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguas Buneas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3701-03 | Wire Zone / Border Zone | 0.45 | 15 | Urban | Aguas Buneas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3101-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2801-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Piedras | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2901-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yabucoa | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3501-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aibonito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9901-01 | Wire Zone / Border Zone | 0.2 | 7 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9601-01 | Wire Zone / Border Zone | 0.2 | 7 | Urban | Barranquitas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3604-06 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3302-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-02 | Wire Zone / Border Zone | 0.31 | 10 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3302-04 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3405-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cayey | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2601-04 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Humacao | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguas Buneas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9601-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Barranquitas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9902-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9605-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9901-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3405-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3102-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3007-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9605-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Barranquitas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9601-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9703-03 | Wire Zone / Border Zone | 0.34 | 11 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3302-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3007-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3009-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3301-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3602-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cidra | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3013-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9902-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9703-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-04 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Aguas Buneas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 9703-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2901-03 | Wire Zone / Border Zone | 0.2 | 7 | Urban | Yabucoa | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3014-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3604-06 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2601-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Humacao | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3202-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2801-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Humacao | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2606-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yabucoa | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3101-01 | Wire Zone / Border Zone | 0.54 | 18 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3202-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3405-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3501-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Aibonito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3302-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3302-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3103-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3601-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cidra | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3301-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3201-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3402-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 3403-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3501-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Aibonito | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3202-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 3010-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 8010-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6010-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 6702-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7103-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6801-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cabo Rojo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7003-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7805-13 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6014-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6012-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6201-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7902-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6004-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7103-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6101-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6704-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7104-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 7008-08 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguadilla | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6015-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Mayaguez | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7201-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6101-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7004-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6010-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7805-11 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6406-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6201-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7104-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7802-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7802-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6801-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Hormigueros | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6010-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6201-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Las Marias | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7301-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Rincon | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7301-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Rincon | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7101-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Moca | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6301-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Maricao | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6404-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6101-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Añasco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6401-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7903-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7003-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7012-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7006-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6306-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7901-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6702-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7011-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7201-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7201-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6704-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cabo Rojo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7301-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Rincon | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7104-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6404-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7802-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6801-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hormigueros | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7502-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6802-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6404-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6305-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maricao | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6010-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7801-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Las Marias | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6404-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6705-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6010-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7104-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7104-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7801-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6802-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6801-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Hormigueros | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6305-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maricao | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7502-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6101-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6010-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6404-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6404-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7403-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7801-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7004-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6014-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7502-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6102-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7901-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7505-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7103-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7103-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6406-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 7801-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6010-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6014-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6801-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6010-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6010-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6014-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7902-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6201-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Las Marias | 10 | PIS |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6404-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6201-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Las Marias | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7805-11 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7805-13 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6802-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Hormigueros | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6305-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maricao | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6702-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cabo Rojo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6004-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6005-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6004-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6010-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 7301-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Rincon | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5012-04 | Wire Zone / Border Zone | 0.31 | 10 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 4201-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Patillas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5013-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 4201-04 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Patillas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5304-03 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Yauco | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6305-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5013-02 | Wire Zone / Border Zone | 0.31 | 10 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5817-02 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Juana Diaz | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 4301-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Maunabo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 4602-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Coamo | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4003-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guayama | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5018-05 | Wire Zone / Border Zone | 0.4 | 13 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5303-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5401-04 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Penuelas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 5302-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 4101-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Arroyo | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5303-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Yauco | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5901-02 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Villalba | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5501-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Guayanilla | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5305-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Yauco | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5501-04 | Wire Zone / Border Zone | 0.4 | 13 | Urban | Guayanilla | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5012-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5303-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 4001-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guayama | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5004-06 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5302-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 6501-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Sabana Grande | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 6702-02 | Wire Zone / Border Zone | 0.2 | 7 | Urban | Lajas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5902-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Villalba | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6601-03 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Lajas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 6601-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Lajas | 10 | Xperts |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5501-04 | Wire Zone / Border Zone | 0.26 | 9 | Urban | Guayanilla | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 6601-04 | Wire Zone / Border Zone | 0.63 | 21 | Urban | Lajas | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5804-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5501-04 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Guayanilla | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5401-01 | Wire Zone / Border Zone | 0.26 | 9 | Urban | Penuelas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5013-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Juana Diaz | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5501-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guayanilla | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 4503-01 | Wire Zone / Border Zone | 0.23 | 8 | Urban | Salinas | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
240 | 5013-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Juana Diaz | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5802-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juana Diaz | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5305-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5401-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Penuelas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5301-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5303-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5303-01 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Yauco | 10 | Site |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 5301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1113-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1342-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2301-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Rio Grande | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1531-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1908-03 | Wire Zone / Border Zone | 0.14 | 5 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1204-03/1201-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Trujillo Alto | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1204-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1908-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 3014-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1328-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2404-08 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Canovanas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1424-05/1338-02 | Wire Zone / Border Zone | 0.28 | 9 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1301-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2002-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Luquillo | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1607-04 | Wire Zone / Border Zone | 0.26 | 9 | Urban | Carolina | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1203-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1359-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1348-08 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2401-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 1607-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Carolina | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2702-01 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Rio Grande | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1205-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1203-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Trujillo Alto | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1301-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1652-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1345-02 | Wire Zone / Border Zone | 0.14 | 5 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-03 | Wire Zone / Border Zone | 0.28 | 9 | Urban | Trujillo Alto | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2101-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | Fajardo | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1602-04 | Wire Zone / Border Zone | 0.17 | 6 | Urban | Carolina | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1525-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1342-02 | Wire Zone / Border Zone | 2 | 67 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1205-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 2302-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Rio Grande | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1619-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Carolina | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1421-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1619-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Carolina | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2302-03 | Wire Zone / Border Zone | 0.28 | 9 | Urban | Rio Grande | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1203-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1401-07 | Wire Zone / Border Zone | 0.28 | 9 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-05 | Wire Zone / Border Zone | 0.23 | 8 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1113-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1334-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1205-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1646-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Carolina | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1652-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9 | Urban | Canovanas | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1205-03 | Wire Zone / Border Zone | 0.11 | 4 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2404-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Carolina | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1525-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2201-01 | Wire Zone / Border Zone | 0.28 | 9 | Urban | Ceiba | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2401-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Canovanas | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1602-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Canovanas | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1530-07 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1908-03 | Wire Zone / Border Zone | 1.14 | 38 | Urban | San Juan | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1345-04 | Wire Zone / Border Zone | 0.17 | 6 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1303-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1345-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9 | Urban | Canovanas | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4 | 1359-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4402-4 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Santaisabel | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4301-1 /4301-2 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maunabo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4301-1 /4301-2 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maunabo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4301-1 /4301-2 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maunabo | 10 | Site |  | Corrective | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.05 | 35 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 1 | 33 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 1.3 | 43 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.39 | 13 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.21 | 40 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.49 | 16 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.5 | 17 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 1.32 | 44 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.45 | 15 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.196 | 7 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.47 | 16 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.66 | 22 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.019 | 34 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 1.14 | 38 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.5 | 17 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.406 | 14 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.6 | 20 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.002 | 33 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0.74 | 25 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.64 | 21 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.855 | 29 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.227 | 8 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.757 | 25 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0.57 | 19 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.6 | 20 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.4 | 13 | Urban | QUEBRADILLAS | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.6 | 20 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.3 | 10 | Urban | QUEBRADILLAS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.446 | 15 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.538 | 18 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.086 | 36 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0.82 | 27 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.74 | 25 | Urban | ARECIBO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.6692 | 22 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.4616 | 15 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9101-01 | Wire Zone / Border Zone | 1.3 | 43 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8801-01 | Wire Zone / Border Zone | 0.9 | 30 | Urban | MANATI | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8302-04 | Wire Zone / Border Zone | 0.52 | 17 | Urban | ARECIBO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.8 | 27 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0 | 0 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 1.14 | 38 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0 | 0 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.25 | 8 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.72 | 24 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.28 | 9 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.413 | 14 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9001-02 | Wire Zone / Border Zone | 0.648 | 22 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 1.2 | 40 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.62 | 21 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.523 | 17 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.497 | 17 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.243 | 8 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9001-02 | Wire Zone / Border Zone | 0.826 | 28 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0.39 | 13 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.36 | 12 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.659 | 22 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.43 | 14 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9001-02 | Wire Zone / Border Zone | 1.198 | 40 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 1.09 | 36 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.9 | 30 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.18 | 6 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-02 | Wire Zone / Border Zone | 0.594 | 20 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-03 | Wire Zone / Border Zone | 0.154 | 5 | Urban | ARECIBO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9101-01 | Wire Zone / Border Zone | 0.237 | 8 | Urban | VEGA ALTA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9001-02 | Wire Zone / Border Zone | 0.973 | 32 | Urban | VEGA BAJA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-03 | Wire Zone / Border Zone | 0.75 | 25 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0.42 | 14 | Urban | MOROVIS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 1.22 | 41 | Urban | JAYUYA | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-01 | Wire Zone / Border Zone | 0.479 | 16 | Urban | QUEBRADILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-03 | Wire Zone / Border Zone | 0.384 | 13 | Urban | ARECIBO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9001-02 | Wire Zone / Border Zone | 1.056 | 35 | Urban | MANATI | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8801-01 | Wire Zone / Border Zone | 0.13 | 4 | Urban | MOROVIS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-03 | Wire Zone / Border Zone | 1.23 | 41 | Urban | SAN SEBASTIAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-03 | Wire Zone / Border Zone | 0.8 | 27 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.65 | 22 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.45 | 15 | Urban | TOA BAJA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.5 | 17 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.5 | 17 | Urban | TOA BAJA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 0.4 | 13 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 0.4 | 13 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 1.2 | 40 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 1 | 33 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 0.75 | 25 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 0.6 | 20 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 1.3 | 43 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 0.8 | 27 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 1.2 | 40 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 1.1 | 37 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9401-01 | Wire Zone / Border Zone | 0.75 | 25 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.8 | 27 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1720-07 | Wire Zone / Border Zone | 0.5 | 17 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1720-07 | Wire Zone / Border Zone | 0.3 | 10 | Urban | DORADO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9401-01 | Wire Zone / Border Zone | 0.6 | 20 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 9401-01 | Wire Zone / Border Zone | 0.25 | 8 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.5 | 17 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.6 | 20 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9401-01 | Wire Zone / Border Zone | 0.2 | 7 | Urban | COROZAL | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1720-07 | Wire Zone / Border Zone | 0.6 | 20 | Urban | #N/A | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1908-03 | Wire Zone / Border Zone | 0.88 | 29 | Urban | HUMACAO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9401-01 | Wire Zone / Border Zone | 0.3 | 10 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9801-03 | Wire Zone / Border Zone | 0.35 | 12 | Urban | FAJARDO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1908-03 | Wire Zone / Border Zone | 0.22 | 7 | Urban | YABUCOA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1720-07 | Wire Zone / Border Zone | 0.65 | 22 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9801-03 | Wire Zone / Border Zone | 0.35 | 12 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9801-01 | Wire Zone / Border Zone | 0.2 | 7 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9801-01 | Wire Zone / Border Zone | 0.15 | 5 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 0.17 | 6 | Urban | TOA BAJA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 0.01 | 0 | Urban | HUMACAO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.8 | 27 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.26 | 9 | Urban | TOA BAJA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 0.99 | 33 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 0.34 | 11 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.65 | 22 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 1.51 | 50 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 0.57 | 19 | Urban | TOA BAJA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 1.25 | 42 | Urban | TOA BAJA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 1.11 | 37 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 0.43 | 14 | Urban | YABUCOA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 2.44 | 81 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 1.05 | 35 | Urban | CAGUAS | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3010-01 | Wire Zone / Border Zone | 0.88 | 29 | Urban | NAGUABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3010-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 1.11 | 37 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 2.19 | 73 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 0.4 | 13 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 1.45 | 48 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 0.45 | 15 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 1.76 | 59 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 1.25 | 42 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 0.71 | 24 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 1.59 | 53 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 1.05 | 35 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 1.16 | 39 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 3.16 | 105 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3501-01 | Wire Zone / Border Zone | 1.08 | 36 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2702-01 | Wire Zone / Border Zone | 5.23 | 174 | Urban | YABUCOA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-01 | Wire Zone / Border Zone | 3.15 | 105 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 3501-01 | Wire Zone / Border Zone | 5.09 | 170 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 2702-01 | Wire Zone / Border Zone | 3.92 | 131 | Urban | SAN SEBASTIAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3010-01 | Wire Zone / Border Zone | 3.01 | 100 | Urban | MAYAGÜEZ | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3501-01 | Wire Zone / Border Zone | 5.85 | 195 | Urban | MAYAGÜEZ | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 3010-01 | Wire Zone / Border Zone | 0.63 | 21 | Urban | CABO ROJO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3501-01 | Wire Zone / Border Zone | 5.63 | 188 | Urban | SAN SEBASTIAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2702-01 | Wire Zone / Border Zone | 5.31 | 177 | Urban | MAYAGÜEZ | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 2906-02 | Wire Zone / Border Zone | 2.9 | 97 | Urban | MAYAGÜEZ | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 3007-03 | Wire Zone / Border Zone | 2.24 | 75 | Urban | JUANA DIAZ | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3701-03 | Wire Zone / Border Zone | 2.02 | 67 | Urban | GUAYAMA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6703-01 | Wire Zone / Border Zone | 1.69 | 56 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.1 | 37 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-03 | Wire Zone / Border Zone | 0.88 | 29 | Urban | RIO GRANDE | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6010-02 | Wire Zone / Border Zone | 0.37 | 12 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6703-01 | Wire Zone / Border Zone | 0.96 | 32 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.1 | 37 | Urban | MAYAGÜEZ | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 2.29 | 76 | Urban | SAN JUAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6010-02 | Wire Zone / Border Zone | 0.38 | 13 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6703-01 | Wire Zone / Border Zone | 1.67 | 56 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 1.3 | 43 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.01 | 0 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1 | 33 | Urban | SAN SEBASTIAN | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 1.04 | 35 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6703-01 | Wire Zone / Border Zone | 0.61 | 20 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 1.69 | 56 | Urban | JUNCOS | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.49 | 16 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 7901-01 | Wire Zone / Border Zone | 1 | 33 | Urban | CABO ROJO | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-03 | Wire Zone / Border Zone | 1.66 | 55 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6703-01 | Wire Zone / Border Zone | 0.35 | 12 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 1.02 | 34 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.04 | 1 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7901-01 | Wire Zone / Border Zone | 1 | 33 | Urban | MAYAGÜEZ | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.86 | 29 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 1.19 | 40 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 1.43 | 48 | Urban | SAN SEBASTIAN | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1 | 33 | Urban | MAYAGÜEZ | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6703-01 | Wire Zone / Border Zone | 0.27 | 9 | Urban | MAYAGÜEZ | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 0.74 | 25 | Urban | SAN SEBASTIAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.52 | 17 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7103-01 | Wire Zone / Border Zone | 1.15 | 38 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7901-01 | Wire Zone / Border Zone | 1.1 | 37 | Urban | CABO ROJO | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 0.86 | 29 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.23 | 8 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7103-01 | Wire Zone / Border Zone | 0.48 | 16 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7901-01 | Wire Zone / Border Zone | 0.91 | 30 | Urban | CABO ROJO | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 0.27 | 9 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 0.79 | 26 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 1.11 | 37 | Urban | MAYAGÜEZ | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7103-01 | Wire Zone / Border Zone | 1.59 | 53 | Urban | MAYAGÜEZ | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6012-03 | Wire Zone / Border Zone | 0.85 | 28 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-01 | Wire Zone / Border Zone | 1.28 | 43 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 0.94 | 31 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7101-03 | Wire Zone / Border Zone | 1.08 | 36 | Urban | MAYAGÜEZ | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6012-03 | Wire Zone / Border Zone | 1.62 | 54 | Urban | CABO ROJO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6802-01 | Wire Zone / Border Zone | 1.96 | 65 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 0.34 | 11 | Urban | CABO ROJO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7101-03 | Wire Zone / Border Zone | 1.26 | 42 | Urban | YAUCO | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-02 | Wire Zone / Border Zone | 3.13 | 104 | Urban | PONCE | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 1.44 | 48 | Urban | CIDRA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-01 | Wire Zone / Border Zone | 1.58 | 53 | Urban | YAUCO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 1.06 | 35 | Urban | PONCE | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7101-03 | Wire Zone / Border Zone | 1.37 | 46 | Urban | CIDRA | 10 | PIS |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-03 | Wire Zone / Border Zone | 0.68 | 23 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6702-02 | Wire Zone / Border Zone | 0.27 | 9 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-01 | Wire Zone / Border Zone | 0.36 | 12 | Urban | BAYAMON | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 0.29 | 10 | Urban | YAUCO | 10 | Xperts |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 0.152 | 5 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.128 | 4 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 0 | 0 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 1.46 | 49 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.54 | 18 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 0.16 | 5 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 1.29 | 43 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 1.522 | 51 | Urban | CAYEY | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 0.87 | 29 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 1.43 | 48 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 1.35 | 45 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 1.14 | 38 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 1.52 | 51 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 1.176 | 39 | Urban | CIDRA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 1.05 | 35 | Urban | RIO GRANDE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 1.39 | 46 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 1.845 | 62 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 1.36 | 45 | Urban | CAYEY | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 1.01 | 34 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 2.521 | 84 | Urban | YAUCO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 1.3 | 43 | Urban | PONCE | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 1.01 | 34 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.99 | 33 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 4001-03 | Wire Zone / Border Zone | 1.03 | 34 | Urban | CIDRA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5021-01 | Wire Zone / Border Zone | 1.25 | 42 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 0.2 | 7 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.22 | 7 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 1.16 | 39 | Urban | GUAYAMA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5021-01 | Wire Zone / Border Zone | 1.48 | 49 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 0.62 | 21 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.306 | 10 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 0.79 | 26 | Urban | GUAYAMA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5021-01 | Wire Zone / Border Zone | 0.276 | 9 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 0.51 | 17 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-01 | Wire Zone / Border Zone | 0.53 | 18 | Urban | YAUCO | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 0.61 | 20 | Urban | GUAYAMA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5021-01 | Wire Zone / Border Zone | 1.42 | 47 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 1.17 | 39 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6601-03 | Wire Zone / Border Zone | 0.25 | 8 | Urban | LAJAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 1.3 | 43 | Urban | GUAYAMA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.32 | 11 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5021-01 | Wire Zone / Border Zone | 0.956 | 32 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6601-03 | Wire Zone / Border Zone | 1.17 | 39 | Urban | SAN JUAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 0 | 0 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4001-03 | Wire Zone / Border Zone | 1.23 | 41 | Urban | GUAYAMA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.411 | 14 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5021-01 | Wire Zone / Border Zone | 0.615 | 21 | Urban | PONCE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
7.2 | 6601-03 | Wire Zone / Border Zone | 1.66 | 55 | Urban | SAN GERMAN | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 0 | 0 | Urban | PATILLAS | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4003-01 | Wire Zone / Border Zone | 0 | 0 | Urban | GUAYAMA | 10 | Site |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.1988 | 7 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.1988 | 7 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.1988 | 7 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.0852 | 3 | Urban | LUQUILLO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.5113 | 17 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.7102 | 24 | Urban | LUQUILLO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2302-03 | Wire Zone / Border Zone | 0.4829 | 16 | Urban | RIO GRANDE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.5966 | 20 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.4261 | 14 | Urban | LUQUILLO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2302-03 | Wire Zone / Border Zone | 1.4488 | 48 | Urban | CEIBA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.3693 | 12 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.4261 | 14 | Urban | GUAYNABO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1619-03 | Wire Zone / Border Zone | 0.625 | 21 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.4261 | 14 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.28 | 9 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.48 | 16 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1619-03 | Wire Zone / Border Zone | 0.62 | 21 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.56 | 19 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.5966 | 20 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.7102 | 24 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1619-03 | Wire Zone / Border Zone | 0.4261 | 14 | Urban | CAROLINA | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.5113 | 17 | Urban | RIO GRANDE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.53 | 18 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1336-07 | Wire Zone / Border Zone | 0.42 | 14 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.71 | 24 | Urban | RIO GRANDE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2302-03 | Wire Zone / Border Zone | 0.12 | 4 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2302-03 | Wire Zone / Border Zone | 1.02 | 34 | Urban | RIO GRANDE | 10 | Wright Tree |  | Preventative | Physical | Chip / Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.2557 | 9 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1619-03 | Wire Zone / Border Zone | 0.3125 | 10 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.3409 | 11 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.2841 | 9 | Urban | CEIBA | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.5682 | 19 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.2841 | 9 | Urban | FAJARDO | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.4261 | 14 | Urban | RIO GRANDE | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-02 | Wire Zone / Border Zone | 0.2841 | 9 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-02 | Wire Zone / Border Zone | 0.4261 | 14 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.852 | 28 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.4261 | 14 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.1136 | 4 | Urban | TRUJILLO ALTO | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-03 | Wire Zone / Border Zone | 1.4204 | 47 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-02 | Wire Zone / Border Zone | 0.7386 | 25 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.1704 | 6 | Urban | CEIBA | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.7954 | 27 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-05 | Wire Zone / Border Zone | 0.2272 | 8 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-02 | Wire Zone / Border Zone | 0.65 | 22 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.28 | 9 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2201-01 | Wire Zone / Border Zone | 0.14 | 5 | Urban | BAYAMON | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1908-03 | Wire Zone / Border Zone | 0.3977 | 13 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1908-03 | Wire Zone / Border Zone | 0.2841 | 9 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1118-09 | Wire Zone / Border Zone | 0.142 | 5 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2401-01 | Wire Zone / Border Zone | 0.5397 | 18 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1204-02 | Wire Zone / Border Zone | 0.6818 | 23 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1619-03 | Wire Zone / Border Zone | 0.2841 | 9 | Urban | SAN JUAN | 10 | Wright Tree |  | Preventative | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-04 | Wire Zone / Border Zone | 0.44 | 14.6667 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3013-02 | Wire Zone / Border Zone | 4.1 | 136.6667 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3013-03 | Wire Zone / Border Zone | 1.98 | 66 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 3102-01 | Wire Zone / Border Zone | 6.45 | 215 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 3103-01 | Wire Zone / Border Zone | 1.53 | 51 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3401-02 | Wire Zone / Border Zone | 3.13 | 104.3333 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3502-02 | Wire Zone / Border Zone | 6.38 | 212.6667 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3601-03 | Wire Zone / Border Zone | 3.47 | 115.6667 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3601-04 | Wire Zone / Border Zone | 2.05 | 68.3333 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3602-01 | Wire Zone / Border Zone | 0.77 | 25.6667 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 3602-02 | Wire Zone / Border Zone | 2.15 | 71.6667 | Urban | Caguas A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 4201-03 | Wire Zone / Border Zone | 3.08 | 102.6667 | Urban | Ponce A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 4602-02 | Wire Zone / Border Zone | 2.62 | 87.3333 | Urban | Ponce A High | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 4602-04 | Wire Zone / Border Zone | 3.51 | 117 | Urban | Ponce A High | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5003-02 | Wire Zone / Border Zone | 2.1 | 70 | Urban | Ponce A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5005-03 | Wire Zone / Border Zone | 5.07 | 169 | Urban | Ponce A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5008-01 | Wire Zone / Border Zone | 0.92 | 30.6667 | Urban | Ponce A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5019-01 | Wire Zone / Border Zone | 1.44 | 48 | Urban | Ponce A High | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5304-01 | Wire Zone / Border Zone | 1.09 | 36.3333 | Urban | Ponce A High | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5501-02 | Wire Zone / Border Zone | 2.94 | 98 | Urban | Ponce A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 5501-04 | Wire Zone / Border Zone | 3.44 | 114.6667 | Urban | Ponce A High | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 5808-02 | Wire Zone / Border Zone | 0.41 | 13.6667 | Urban | Ponce A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6001-03 | Wire Zone / Border Zone | 3.95 | 131.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6001-05 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6002-02 | Wire Zone / Border Zone | 0.08 | 2.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6002-05 | Wire Zone / Border Zone | 2.21 | 73.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6004-02 | Wire Zone / Border Zone | 3.89 | 129.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6007-05 | Wire Zone / Border Zone | 0.44 | 14.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 6404-04 | Wire Zone / Border Zone | 0.68 | 22.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 6406-04 | Wire Zone / Border Zone | 5.03 | 167.6667 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7002-02 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7103-04 | Wire Zone / Border Zone | 2.13 | 71 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7303-01 | Wire Zone / Border Zone | 0.24 | 8 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7402-01 | Wire Zone / Border Zone | 3.31 | 110.3333 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7402-03 | Wire Zone / Border Zone | 0.78 | 26 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7503-02 | Wire Zone / Border Zone | 2.55 | 85 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7504-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7601-04 | Wire Zone / Border Zone | 4.31 | 143.6667 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7701-04 | Wire Zone / Border Zone | 2.24 | 74.6667 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 7802-01 | Wire Zone / Border Zone | 0.1 | 3.3333 | Urban | Mayaguez A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 8002-01 | Wire Zone / Border Zone | 0.76 | 25.3333 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 8002-02 | Wire Zone / Border Zone | 0.89 | 29.6667 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 8011-01 | Wire Zone / Border Zone | 4.26 | 142 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8013-03 | Wire Zone / Border Zone | 0.97 | 32.3333 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 8014-06 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 8101-05 | Wire Zone / Border Zone | 1.4 | 46.6667 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 8202-03 | Wire Zone / Border Zone | 0.12 | 4 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 8301-01 | Wire Zone / Border Zone | 1.37 | 45.6667 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
4.16 | 8602-01 | Wire Zone / Border Zone | 6.63 | 221 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 8701-01 | Wire Zone / Border Zone | 3.25 | 108.3333 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 8701-03 | Wire Zone / Border Zone | 0.93 | 31 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 8801-02 | Wire Zone / Border Zone | 2.63 | 87.6667 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 9003-06 | Wire Zone / Border Zone | 9.67 | 322.3333 | Urban | Arecibo A High | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 9004-10 | Wire Zone / Border Zone | 4.9 | 163.3333 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
13.2 | 9004-11 | Wire Zone / Border Zone | 1.63 | 54.3333 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 9103-02 | Wire Zone / Border Zone | 2.34 | 78 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 9103-04 | Wire Zone / Border Zone | 2.23 | 74.3333 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
8.32 | 9201-02 | Wire Zone / Border Zone | 5.34 | 178 | Urban | Arecibo A High | 10 | Wright Tree Services |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federally Funded
| 9201-02 | Total | 459.4379
1 IMPACTED ZONE - REMOVAL/REDUCTION ZONE, EDGE ZONE, STRIKE ZONE
2 TYPE OF RESPONSE - REACTIVE, CORRECTIVE, PREVENTIVE
3 TYPE OF VM IMPLEMENTED - BIOLOGICAL, PHYSICAL OR CHEMICAL CONTROL
4 TYPE OF VM DISPOSAL CLASIFICATION - CHIP & HAUL, CHIP & BLOW, PILE / WINDROW, LOP & SCATTER, MULCHIN
5 RECOMMENDATIONS FOR FUTURE VM - Describe recommended species, cadence of any herbicide application
Vegetation Management Progress Report Q1 FY2026