## Sheet1
Attachment H
Genera Monthly Reporting Requirements - Generation Maintenance
Thermal Generation Facility Maintenance Report
Aguirre, Costa Sur, Palo Seco, San Juan Power Plants
Monthly Reporting
As of August 31, 2024
NO. | POWER PLANT | UNIT NUMBER | PROJECT ACTIVITY | CATEGORY | ACTIVITY BUDGET | START DATE | COMPLETION DATE | ACTIVITY STATUS - PERCENTAGE FOR COMPLETION | PROCUREMENT / BID (S) NUMBER | POC - MAINTENANCE ACTIVITY | CONTRACTOR/SUPPLIER | APPROVED FOR PAYMENT
1 | Aguirre | 1 & 2 | ASP Generator Spare Rotor Rewind | Federal |  |  |  | PLANNING |  | Robert Rosario
2 | Aguirre |  | ASP Rehabilitation WTP Nautilis Tank 1B | Federal | 2504728 | 2025-11-24 | 2027-05-30 | PROCUREMENT | REQ.339889 | Manuel Cortés |  | 1028051.28
3 | Aguirre CC | 1-4 | Hot Gas Inspection 1-4 (HGPI 1-4) | Federal | 2124037 | 2025-06-16 | 2026-06-30 | EXECUTION | C-106760 | José Vázquez | MD&A | 1298786.2
4 | Aguirre CC |  | Gas Turbine Rotor Refurbish MS7001B/AE | Federal | 1094955 | 2025-11-01 | 2026-04-30 | PROCUREMENT | C-105235 | José Vázquez | MD&A
5 | Mayagüez |  | Inspection and Maintenance 4 Generator Brush | NME | 1847478 | 2025-03-01 | 2026-06-30 | EXECUTION | C-104923 | José Vázquez | GESA | 646617.3
6 | Cambalache | 2 & 3 | Inspection C - Manpower and Spare Parts | Federal | 22000000 | 2025-10-15 | 2026-12-31 | PROCUREMENT | 111173 | José Vázquez | HTS
7 | Cambalache |  | Structural Rehabilitation Fuel Tank D-2 | Federal | 1598000 | 2024-06-10 | 2025-12-31 | EXECUTION | C-101295 | Manuel Cortés | All Contractors | 985834.8
8 | Aguirre CC | 1-3 | Major inspection Unit 1-3 | Federal | 3750000 | 2024-09-09 | 2026-06-30 | EXECUTION | C-104889 | José Vázquez | RG Engineering | 1251583.85
9 | Aguirre | 1-4 | Replacement of Load Center 1-4 Condenser Circulating Water Pump | Federal | 820000 | 2025-02-03 | 2026-05-30 | EXECUTION | C-101421 | Luis Ortiz | Allied Power | 62000
10 | San Juan | 5 | Replacement of the Online Condenser Cleaner Unit 5 | Federal | 3463000 | 2026-01-01 | 2026-12-31 | EXECUTION | C-106758 | José Vázquez | Malnat
11 | San Juan | 6 | Unit 6 - Major Overhaul (ST Repairs) | Federal | 13692168.2 | 2025-01-20 | 2026-03-31 | EXECUTION | C-105509 | José Vázquez | MD&A | 7641508.44
12 | San Juan | 7 | SJ7 Mayor Overhaul (Boiler & Aux) | Federal | 2567090 | 2025-04-01 | 2025-09-30 | CLOSING |  | Fernando Rivera | Various | 2478100.9
13 | San Juan | 7 | Unit 7 Rehabilitation ( Turbine) | Federal | 22380974.33 | 2025-03-21 | 2026-02-28 | EXECUTION | C-108148 | Fernando Rivera | MD&A | 15932700.87
14 | Palo Seco | 3 | Update Voltage Regulation System Unit 3, Palo Seco Power Plant | Federal | 294082 | 2026-01-12 | 2026-02-28 | EXECUTION | C-101258 | Robert Rosario | ESI | 119103.21
15 | Palo Seco |  | Upgrade OSI DCS | Federal | 2445496 | 2025-03-14 | 2026-04-30 | EXECUTION | C- 103154 | Robert Rosario | Emerson | 2078756.48
16 | Costa Sur | 5 | Replacement of Excitation System Units 5 | Federal | 1583848 | 2024-09-17 | 2026-12-31 | EXECUTION | C-102867 | Robert Rosario | ESI | 1108693.6
17 | Costa Sur | 5 | Replacement of Unit 5 Electric Load Center | Federal | 356295 | 2023-01-10 | 2025-09-30 | CLOSING | C-97578 | Robert Rosario | Allied Power | 356295
18 | Costa Sur |  | Traveling Screens Replacement | Federal | 5000000 | 2025-09-30 | 2027-03-24 | PLANNING |  | Luis Ortiz
19 | Costa Sur | 6-1 | Rehabilitation Condenser Circulating Water Pump (CCWP) 6-1 | Federal | 417657 | 2025-02-17 | 2025-12-31 | CLOSING | C-107189 | Luis Ortiz | Reliable Industrial | 296990
20 | Aguirre |  | Traveling Screen Project 316B | Federal | 13500000 |  |  | PLANNING |  | Luis Ortiz
21 | Aguirre |  | ASP Phase IV Stage 1 - Advanced Water Treatment System (Design) | NME | 784612 | 2025-01-01 | 2025-12-13 | CLOSING | C-102062 (T6-R7) | Luis Ortiz | Integra | 784612
22 | Aguirre |  | ASP Phase 4 Stage 2 - Advanced Water Treatment System (Desgin) | NME | 452894 | 2025-06-01 | 2025-12-13 | EXECUTION | C-102062 (T8-R9) | Luis Ortiz | Integra | 303484.75
23 | Costa Sur |  | Upgrade to Foxboro Simulation System | Federal | 1215173 | 2024-12-04 | 2025-11-30 | CLOSING | C-103503 | Robert Rosario | LT Automation | 1215173
24 | Costa Sur | 5 | Manufacture and Delivery of Bifurcate (Boiler) Tubes Unit 5 | Federal | 255110 | 2026-01-05 | 2026-08-31 | PROCUREMENT | MR-871412 | Fernando Rivera | GE | 255110
25 | Palo Seco |  | New Demineralized Water Tank #2 | Federal | 2450000 | 2024-09-03 | 2026-03-31 | EXECUTION | C-102570 | Manuel Cortés | Alonso & Carus | 2202125.05
26 | Aguirre CC | GT 2-3 | Major inspection of units GT 2-3. | Federal | 10000000 | 2026-02-01 | 2026-06-30 | PROCUREMENT | REQ. 354439 | José Vázquez
27 | Palo Seco | 4 | Major & Environment Maintenance PS4 | Federal | 9000000 | 2024-09-01 | 2025-08-20 | CLOSING | Varios | Fernando Rivera | Varios | 2076394.48
28 | Palo Seco | 4 | Generator Repair PS4 | Forced Outage | 15200000 | 2024-07-31 | 2025-09-30 | CLOSING | C-104814 | Robert Rosario | Ethos Energy Power | 12980597.54
29 | San Juan | 9 | Major Overhaul SJ9 | Federal | 28000000 | 2026-01-15 | 2026-06-15 | PROCUREMENT | Various | José Vázquez | Various
30 | San Juan | 7 | Condenser Rehabilitation SJ7 | Federal | 5700000 | 2025-10-10 | 2026-01-18 | EXECUTION | C-106982 | Fernando Rivera | Malnat | 1340900
31 | Costa Sur |  | Tanques Raw Water 1&2 | Federal | 4713865 | 2023-03-08 | 2025-07-30 | COMPLETED | C-98193 | Greg Hernández | Alonso & Carus | 4713865
32 | Mayagüez |  | New Waste Water Tanks 1&2 | NME | 379600 | 2025-07-23 | 2026-06-09 | EXECUTION | C-107651 | Luis Ortiz | Alonso & Carus | 99333
33 | Mayagüez | 4A | Hot Section Inspection Unit 4A | Federal | 9000000 | 2025-07-03 | 2025-12-29 | CLOSING | C-108663 | Luis Ortiz | ARG Precision | 7001396.69
34 | Aguirre |  | ASP Phase IV Demineralized Water System | EPA | 7201932 | 2026-01-01 | 2027-01-01 | PROCUREMENT | 111089 | Luis Ortiz | R&J Pram Mechanical
35 | Aguirre |  | New WTP Retention Tank #1 | Federal | 6000000 | 2026-01-01 | 2026-12-31 | PLANNING |  | Luis Ortiz
36 | Aguirre |  | New WTP Retention Tank #2 | Federal | 6000000 | 2026-01-01 | 2026-12-31 | PLANNING |  | Luis Ortiz
37 | Aguirre CC |  | Manufacture and Delivery of Power Circuit Breaker 245kV SF6 | NME | 823006 | 2025-09-01 | 2026-08-08 | EXECUTION | C-108519 | Robert Rosario | Pro-Energy | 164601.2
38 | Aguirre CC |  | New Condensate Tank #2 | Federal | 2511000 | 2025-12-01 | 2026-12-01 | EXECUTION | C-110325 | Luis Ortiz | Alonso & Carus
39 | Cambalache |  | Camba Design Flood Protection Barrier | Federal | 385000 | 2024-04-12 | 2025-12-31 | CLOSING | C-102184 (T7-R2) | Manuel Cortés | Sargent & Lundy | 359834
40 | Costa Sur | 6 | Replacement Load Center 6-2A & 6-2B | NME | 265000 | 2022-11-30 | 2025-12-31 | EXECUTION | C-97582 | Luis Ortiz | Allied Power | 159000
41 | Costa Sur | 5 & 6 | Fabrication and Delivery of Steam Coils | Federal | 1275993 | 2025-09-10 | 2026-12-01 | EXECUTION | C-109034 | Luis Ortiz | Antilles Power Depor Inc. | 612996
42 | Costa Sur |  | Structural Rehabilitation Water Discharge Channel | Federal | 5700000 | 2024-10-30 | 2025-06-30 | COMPLETED | C-89554 | Greg Hernández | Gabriel Fuentes Construction | 5309787.8
43 | Costa Sur |  | Caustic Soda and Acid Tanks Replacement Works | Federal | 550100 | 2022-10-18 | 2025-01-31 | CANCELLED | C-96561 | Greg Hernández | Alonso & Carus | 550100
44 | Costa Sur | 6 | Environmental Inspection | Federal/NME | 6000000 | 2025-11-10 | 2026-03-06 | PLANNING |  | Fernando Rivera
45 | Mayagüez | 1B | Repair & Replace Combustors Components | Federal |  |  |  | PLANNING |  | Luis Ortiz
46 | Palo Seco | 3 & 4 | Upgrade to Mark IV | Federal | 248076 | 2025-08-30 | 2026-02-28 | PROCUREMENT | C-103504 | Robert Rosario | GE
47 | Palo Seco | 4 | Economizer Water Inlet Valve | Federal | 115615 | 2025-11-01 | 2026-12-31 | EXECUTION | C-110963 | Robert Rosario | EPS
48 | Palo Seco | 3 | Environmental Maintenance | NME | 1762000 | 2026-01-05 | 2026-03-02 | PLANNING |  | Robert Rosario
49 | Palo Seco |  | New Multimedia Filters | Federal | 822020 | 2024-03-08 | 2025-06-30 | CLOSING | C-101296 | Manuel Cortés | EPS | 822020
50 | Palo Seco |  | Tank R3 Interconnection System | Federal | 12000000 |  |  | PLANNING |  | Manuel Cortés
51 | Palo Seco | 4 | Superheater Header (material and installation) | Federal | 1206123 | 2026-03-23 | 2027-03-23 | PROCUREMENT |  | Fernando Rivera | GE
52 | Palo Seco |  | Deaerator Pump | NME | 457387 | 2024-02-16 | 2025-12-31 | COMPLETED | C-101706 | Fernando Rivera | Camfer | 457387
53 | Aguirre | 1 & 2 | ASP U1&U2 Manufacture & Installation of Service Elevators | Federal | 433790 |  |  | PROCUREMENT | C-111095 | Greg Hernández | VERTECH
54 | Aguirre | 1 | ASP U1 Forced Outage and APH Basket Replacement | Federal/NME |  | 2026-01-12 | 2026-04-30 | PLANNING |  | Fernando Rivera
55 | Palo Seco | 3&4 | PSSP U3&U4 Manufacture & Installation of Service Elevators | Federal | 387894 | 2024-07-30 | 2026-06-30 | PROCUREMENT | C-111095 | Manuel Cortés | VERTECH
56 | San Juan | 5&6 | SJSP U5&U6 Purchase & Installation 2 UPS & 4 Battery Chargers | Federal | 1253000 | 2025-09-17 | 2026-06-30 | EXECUTION | C-106978 | Manuel Cortés | MALNAT | 112770
57 | San Juan | 7 | SJSP U7 Manufacture & Installation of Service Elevators | Federal | 219800 | 2025-02-01 | 2026-06-30 | PROCUREMENT | C-111095 | Fernando Rivera | VERTECH
58 | San Juan | 5 | SJSP U5 CT Turbine Inspection | NME | 159940846 | 2025-10-06 | 2025-10-26 | CLOSING | C-74903 | José Vázquez | MHI PR | 132057746.27
59 | Aguirre | 2 | ASP U2 Environmental Outage and APH Basket Replacement | NME | 1762000 | 2026-03-01 |  | PLANNING |  | Robert Rosario
60 | Aguirre | 1 | ASP U1 Generator Stator & Generator Rotor Rewind | Federal |  |  |  | PLANNING |  | Robert Rosario
61 | Mayagüez | 3A | Repair & Replace Combustors Components | Federal | 500000 | 2026-01-02 | 2026-06-30 | PROCUREMENT | C-111222 | Luis Ortiz | ARG Precision
62 | Mayagüez | 2B | Repair & Replace Combustors Components | Federal | 500000 |  |  | PROCUREMENT | C-111219 | Luis Ortiz | ARG Precision
63 | San Juan | 6 | Repaacement CT Battery Bank | Federal | 230500 | 2024-09-09 | 2025-12-31 | CLOSING | C-102668 | Manuel Cortés | RGE | 230500
64 | Costa Sur | 5&6 | Manufacture & Installation of Service Elevators | Federal | 433790 | 2025-02-01 | 2026-06-30 | PROCUREMENT | C-111095 | Luis Ortiz | VERTECH
65 | San Juan |  | SJSP Demolition WTP Retention Tank #1 | Federal | 245098.04 | 2026-07-01 | 2026-12-31 | PROCUREMENT | REQ.339839 | Manuel Cortés
66 | San Juan | 6 | SJSP U6 Condenser and Piping Surface Rehab and Coating | NME | 511500 | 2026-01-15 | 2026-06-30 | EXECUTION | C-109699 | José Vázquez | Malnat
67 | Aguirre | 2 | ASP U2 Air Preheater installation | Federal |  |  |  | PLANNING |  | Robert Rosario
68 | Cambalache |  | Camb Overhead Crane - Foundation Forensic Study | Federal | 110000 | 2026-01-27 | 2026-06-30 | EXECUTION | C-110722 (T3 R2) | Manuel Cortés | HGE
69 | Cambalache |  | Camba Overhead Crane - As Built & Civil Design | Federal | 401040 | 2026-01-27 | 2026-06-30 | EXECUTION | C-102062 (T10 R10) | Manuel Cortés | INTEGRA
70 | Cambalache |  | Camba Overhead Crane - Mechanical Design | Federal | 525028 | 2026-01-27 | 2026-06-30 | EXECUTION | C-101951 (T1 R1) | Manuel Cortés | CPM
71 | Mayagüez | 4A | Maya 4A Inspection Stage II | Federal | 900000 | 2026-02-12 | 06/30/026 | PROCUREMENT | 111121 | Luis Ortiz | ARG Precision
|  | **** | NME MAINTENANCE ACTIVITY COULD INCLUDE DIFERENT CONTRACTS