## Anejo 12312025 Vf
Nombre de Proyecto | Categoría* | Fondos | [6 empty] | Aprobación Negociado de Energía |  | Fase del proyecto
|  | Origen | Programa* | Num. | Monto Aprobado | Monto desembolso | A | Estimado de Costo ($) | Costo ($) | Fecha | Fase** | Estado Permisos | Fecha Comienzo | Fecha Terminación | % Completado
FAASt South Coast Irrigation District - Canals | H | Federal | PA, CDBG | 435769 | 0 | 1109506 | B | 144851431.5 | 32140000 | 2021-09-08 | D | N/A | 2022-07-30 | 2026-05-01 | 50%
FAASt Isabela Irrigation District - Canals & USDA Funding | H | Federal | PA, WFPO | 436467 | 0 | 208706.1 | B | 32000000 | 15000000 | 2021-09-08 | D | N/A | 2022-07-30 | TBD | TBD
FAASt Lajas Irrigation Canals | H | Federal | PA, CDBG | 436462 | 0 | 224672.9 | B | 42573271.52 | 15000000 | 2021-09-08 | D | N/A | 2022-07-31 | 2026-07-01 | 25%
FAASt Loco Reservoir Dredging | H | Federal | PA, CDBG | 334803 | 0 | 512774.2503 | B | 8080000 | 2730000 | 2021-08-20 | D | N/A | 2024-03-31 | 2026-12-01 | 60%
FAASt Guineo Reservoir – Dredging | H | Federal | PA, CDBG | 335207 | 0 | 317680.7729 | B | 3143743 | 1250000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-02-02 | 45%
FAASt Guerrero Reservoir – Dredging | H | Federal | PA, CDBG | 334798 | 0 | 341493.9752 | B | 3918132 | 19000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-02-15 | 30%
FAASt Guayo Reservoir Dredging | H | Federal | PA, CDBG | 334813 | 0 | 495715.0925 | B | 17260000 | 21010000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-08-01 | 40%
FAASt Dos Bocas Reservoir Dredging | H | Federal | PA, CDBG | 334811 | 0 | 779059.3066 | B | 117400543.58 | 58250000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-07-01 | 37%
FAASt Caonillas (Dredging) | H | Federal | PA, CDBG | 178722 | 0 | 767473.1666 | B | 81857757 | 41740000 | 2021-04-28 | D | N/A | 2024-03-31 | 2027-05-31 | 37%
FAASt Matrullas Reservoir–Dredging | H | Federal | PA, CDBG | 335206 | 0 | 322817.2563 | B | 7752364 | 3080000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-04-01 | 35%
FAASt Lucchetti Reservoir – Dredging | H | Federal | PA, CDBG | 334773 | 0 | 639474.4903 | B | 40020000 | 35810000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-06-01 | 40%
FAASt Guayabal Reservoir – Dredging | H | Federal | PA, CDBG | 334772 | 0 | 324893.9229 | B | 6452231 | 7750000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-10-01 | 35%
FAASt Guajataca Reservoir – Dredging | H | Federal | PA, CDBG | 334771 | 0 | 485993.4463 | B | 43732382 | 18990000 | 2021-08-20 | D | N/A | 2024-03-31 | 2028-06-22 | 35%
FAASt Garzas Reservoir – Dredging | H | Federal | PA, CDBG | 334769 | 0 | 402004.6813 | B | 11154286 | 1530000 | 2021-06-08 | D | N/A | 2024-03-31 | 2027-06-10 | 30%
FAASt Toro Negro Hydroelectric System Connection | H | Federal | PA, CDBG | 436468 | 0 | 382385.49 | B | 57244061.71 | 15220000 | 2021-09-08 | D | N/A | 2021-07-30 | 2026-09-30 | 35%
FAAST Caonillas Hydroelectric Power Plant I | H | Federal | PA, CDBG | 728260 | 0 | 280825.9 | B | 3611152 | 1650000 | 2021-04-28 | D | N/A | 2024-02-14 | 2027-03-31 | 30%
FAASt - Rio Blanco Hydroelectric System | H | Federal | PA, CDBG | 180723 | 0 | 357833.33 | B | 49005575.55 | 48120000 | 2021-04-28 | D | N/A | 2021-07-31 | 2026-09-30 | 30%
Retrofit projects on hydroelectric turbines (15 Projects) | H | Federal | PA, CDBG | COR3-1966 | 0 | 0 |  | 320790000 | 320790000 | 2023-09-28 | D | N/A | Pending PRDOH | TBD | N/A
FAASt Guajataca Dam – Permanent Repairs | H | Federal | PA, CDBG | 334770 | 0 | 9143848.24 | B | 1086970000 | 566000000 | 2021-08-20 | D | N/A | 2024-01-15 | 2028-12-31 | 12%
FAASt Dams Minor Repairs | H | Federal | PA, CDBG | 436621 | 0 | 0 |  | 24607290.48 | 3560000 | 2021-09-28 | D | N/A | 2024-02-12 | 2026-07-25 | 30%
FAASt - Guayabal Seismic Retrofit | H | Federal | PA, CDBG | 721184 | 0 | 0 |  | 326154895.79 | 299278101 | 2023-05-18 | D | N/A | 2024-07-01 | 2030-12-01 | 10%
Patillas Dams | H | Federal | HMGP | 4339-0011 | 558000000 | 2634999.95 |  | 567024315 | 558530000 | 2021-08-20 | D | N/A | 2024-01-01 | TBD | 80%
Early Warning System | H | Federal | HMGP | 4339-0012 | 99976487 | 31174191.08 |  | 99976487 | 100000000 | 2021-08-20 | P | N/A | 2024-03-31 | 2026-06-30 | 85%
FAASt- System Upgrade for Generation Plants (IT/OT) | IT | Federal | PA, CDBG | 725535 | 11423825 | 3116322.782 |  | 11423825 | 11423825 | 2023-06-22 | C | N/A | 2024-02-08 | 2026-12-31 | 30%
FAASt Bonus Plant | Edif. | Federal | PA, CDBG | 746897 | 1579615.4333 | 0 |  | 1579615.43 | 1670081 | 2024-04-04 | C | N/A | 2025-06-30 | 2026-12-31 | 25%
Proyectos reclamados por PREPAs y transferidos a Operadores |  |  |  |  | E | [5 empty] | C
FAASt Mobile Generation Units Purchases | G | Federal | PA, CDBG | 180692 | 59740469.9222 | 53766422.93 |  | 59740469.92 | 59740469.92 | 2021-06-08 | Transferred to Genera
FAASt Palo Seco Demin Water Tank 4 | G | Federal | PA, CDBG | 334509 | 2890937.3333 | 3232395.154 |  | 2550000 | 2550000 | 2021-09-08 | Transferred to Genera
FAASt Fire Pump for Aguirre Power Complex (AG-004) | G | Federal | PA, CDBG | 670036 | 0 | 0 |  | 280040 | 280040 | 2022-03-09 | Transferred to Genera
FAASt Cambalache Power Plant – Flood Protection Barrier (Generation) | G | Federal | PA, CDBG | 169340 | 0 | 251663.526 |  | 4000000 | 4000000 | 2021-06-08 | Transferred to Genera
FAASt New Black Start System at Costa Sur | G | Federal | PA, CDBG | 164988 | 0 | 104048.19 |  | 45200000 | 45200000 | 2021-06-08 | Transferred to Genera
Rehabilitation Fuel Tank Farm Liners | G | Federal | PA, CDBG | 669498 | 1291000 | 279931.14 |  | 1291000 | 1291000 | 2022-02-11 | Transferred to Genera
Two New Condenser Discharge Water Pumps Motors | G | Federal | PA, CDBG | 669498 | 750000 | 600300 |  | 750000 | 750000 | 2022-02-11 | Transferred to Genera
Two New BCWP Motors | G | Federal | PA, CDBG | 669498 | 640150 | 0 |  | 640150 | 640150 | 2022-02-11 | Transferred to Genera
Purchase and Installation Breakers 480 V | G | Federal | PA, CDBG | 669498 | 350115 | 288846 |  | 350115 | 350115 | 2022-03-09 | Transferred to Genera
Sea Water Intake Structural Repairs Work | G | NME | N/A | N/A | Not eligible | 0 |  | 5274222 | 5274222 | 2022-02-11 | Transferred to Genera
Unit 1 South Wall Boiler Tubing Replacement and Boilers Repairs /Air and Gas Duct Pre-heaters Repair Work | G | Federal | PA, CDBG | 669233 | 5983852.95 | 3014409.6 |  | 5983852.95 | 5983852.95 | 2022-07-22 | Transferred to Genera
Replacement of Load Center 1-4 Condenser Circulating Water Pump | G | Federal | PA, CDBG | 669233 | 630000 | 0 |  | 630000 | 630000 | 2022-02-11 | Transferred to Genera
Inner Barrel Bundle | G | Federal | PA, CDBG | 669233 | 1625954 | 229491.23 |  | 1625954 | 1625954 | 2022-02-18 | Transferred to Genera
Unit 1 - Major Inspection (Replacement Turbo-Generator) | G | Federal | PA, CDBG | 669233 | 11164417 | 10371203.45 |  | 11164417 | 11164417 | 2022-02-11 | Transferred to Genera
Unit 2 Excitation System | G | Federal | PA, CDBG | 669233 | 1501675 | 273001.5 |  | 1516675 | 1516675 | 2022-02-11 | Transferred to Genera
Procurement of Stages 1-1 & 1-2 Turbine Rotor Bucket Set | G | Federal | PA, CDBG | 669815 | 497267 | 447540.3 |  | 497267 | 497267 | 2022-03-09 | Transferred to Genera
New Water Condensate Tank | G | Federal | PA, CDBG | 669815 | 1389220 | 650726.46 |  | 1389220 | 410125 | 2022-03-09 | Transferred to Genera
Major inspection Unit 1-3 | G | Federal | PA, CDBG | 669815 | 2599971 | 602631.63 |  | 2559917 | 2599971 | 2022-03-09 | Transferred to Genera
Hot Gas Path Repairs Work Units 2-4 and stand by transformer | G | Federal | PA, CDBG | 669815 | 806507.36 | 427219.24 |  | 716267.36 | 716267.36 | 2022-02-11 | Transferred to Genera
Hot Gas Path Inspection Work Units 1-1 and 1-2 | G | Federal | PA, CDBG | 669815 | 1092000 | 953782 |  | 1092000 | 1092000 | 2022-02-11 | Transferred to Genera
Units 5 Cooling Tower Replacement | G | Federal | PA, CDBG | 662947 | 1887145 | 2098251 |  | 1887145 | 1887145 | 2022-02-11 | Transferred to Genera
Units 5 New High Pressure Pumps | G | Federal | PA, CDBG | 662947 | 1600000 | 215830.98 |  | 1600000 | 1600000 | 2022-03-09 | Transferred to Genera
Units 5 Condenser Repair and Coating Application | G | Federal | PA, CDBG | 662947 | 1031250 | 1262492.77 |  | 1031250 | 1031250 | 2022-02-11 | Transferred to Genera
Units 5 HP Bleed Valve, LP Bleed Valve and Heat Injection Steam Valve | G | Federal | PA, CDBG | 662947 | 374237 | 270635.4 |  | 374237 | 374237 | 2022-02-11 | Transferred to Genera
Units 5 and 6 Black Start Emergency Generator Upgrade | G | Federal | PA, CDBG | 662947 | 348509.53 | 308169.56 |  | 348509.53 | 348509.53 | 2022-02-11 | Transferred to Genera
Units 5 Replacement of Outlet Valves and Elbow Condenser | G | Federal | PA, CDBG | 662947 | 673667 | 337500 |  | 673667 | 673667 | 2022-02-11 | Transferred to Genera
Unit 5 SCR - Amonium Procurement | G | NME | N/A | N/A | Not eligible | 0 |  | 500000 | 500000 | 2022-02-28 | Transferred to Genera
Units 5 Heavy Equipment Rental Services | G | NME | N/A | N/A | Not eligible | 0 |  | 850000 | 850000 | 2022-03-09 | Transferred to Genera
LTSA SJ5 | G | NME | N/A | N/A | Not eligible | 0 |  | 8000000 | 8000000 | 2022-04-13 | Transferred to Genera
LTSA SJ6 | G | NME | N/A | N/A | Not eligible | 0 |  | 8000000 | 8000000 | 2022-04-13 | Transferred to Genera
Steam Rotor Replacement Unit 5 & CT Repairs | G | Federal | PA, CDBG | 662947 | 12055544.4 | 8985166.43 |  | 12055544.4 | 12055544.4 | 2022-04-13 | Transferred to Genera
Control System Upgrade units 5 & 6 | G | Federal | PA, CDBG | 662947 | 3203050 | 2882744.52 |  | 3203050 | 3203050 | 2022-02-11 | Transferred to Genera
Unit 6 - Major Overhaul (Combustion Turbine Repairs) | G | Federal | PA, CDBG | 662947 | 12768424.79 | 0 |  | 12768424.79 | 12768424.79 | 2022-03-09 | Transferred to Genera
Purchases and Installation of Modules D&E HRSG Unit 6 | G | Federal | PA, CDBG | 662947 | 12619593 | 439890.2 |  | 12619593 | 12619593 | 2023-03-20 | Transferred to Genera
Purchases and Installation of Modules D&E HRSG Unit 5 | G | Federal | PA, CDBG | 662947 | 9750263 | 7070213.69 |  | 9750263 | 9750263 | 2022-02-11 | Transferred to Genera
Replacement of the Online Condenser Cleaner Unit 5 | G | Federal | PA, CDBG | 662947 | 3600000 | 678798.22 |  | 3600000 | 3600000 | 2022-02-11 | Transferred to Genera
Unit 6 - Major Overhaul - Steam Turbine Repairs | G | Federal | PA, CDBG | 662947 | 12768424.79 | 0 |  | 12768424.79 | 12768424.79 | 2022-03-09 | Transferred to Genera
Unit 7 Air Preheater Maintenance and Replacement | G | Federal | PA, CDBG | 687480 | 600000 | 0 |  | 600000 | 600000 | 2022-03-09 | Transferred to Genera
Replacement of Two Uninterruptible Power Supply Systems for Units 7 and 8 | G | Federal | PA, CDBG | 687480 | 739092 | 50443.452 |  | 450000 | 450000 | 2022-03-09 | Transferred to Genera
Unit 7 Rehabilitation ( Turbine) | G | Federal | PA, CDBG | 687480 | 10000000 | 0 |  | 10000000 | 10000000 | 2022-10-21 | Transferred to Genera
Unit 7 Boiler Sections Replace, Repairs & Auxiliary Equipment Inspection Work | G | Federal | PA, CDBG | 687480 | 8000000 | 536627.96 |  | 8000000 | 8000000 | 2022-10-21 | Transferred to Genera
Cooling Tower Unit 10 Repair Works | G | Federal | PA, CDBG | Pending | Pending | 0 |  | 385000 | 385000 | 2022-06-04 | Transferred to Genera
Repairs to Nautilus Water Treatment System | G | Federal | PA, CDBG | 667744 | 250000 | 0 |  | 250000 | 250000 | 2022-03-09 | Transferred to Genera
Units 7-10 New Raw Water Tank | G | Federal | PA, CDBG | 667744 | 1496000 | 1300994.8 |  | 1496000 | 1000000 | 2022-03-09 | Transferred to Genera
Structural Repairs Fuel Service Tank 10 | G | Federal | PA, CDBG | 667744 | 975689 | 878120.11 |  | 975689 | 647000 | 2022-06-04 | Transferred to Genera
Water Treatment and Technical Assistance Cooling Water System | G | NME | N/A | N/A | Not eligible | 0 |  | 232727.04 | 232727.04 | 2022-03-09 | Transferred to Genera
Traveling Screens Replacement | G | Federal | PA, CDBG | 672950 | 5000000 | 0 |  | 5000000 | 5000000 | 2022-03-09 | Transferred to Genera
Replacement of Regulator Valves for Boiler Feed Water Units 5 & 6 | G | Federal | PA, CDBG | 672950 | 301664 | 270000 |  | 301664 | 301664 | 2022-03-09 | Transferred to Genera
Low Pressure Water Heater 3 Repair Work | G | Federal | PA, CDBG | 672950 | 400000 | 0 |  | 400000 | 400000 | 2022-03-09 | Transferred to Genera
Procurement of Water Heater 5 (Deaerator) Spare Pump | G | Federal | PA, CDBG | 672950 | 400000 | 95045.4 |  | 400000 | 400000 | 2022-02-28 | Transferred to Genera
Procurement & Replacement of Air-Preheaters Baskets, Unit 5 | G | Federal | PA, CDBG | 672950 | 1966083 | 1009313.1 |  | 1966083 | 1966083 | 2022-02-11 | Transferred to Genera
Replacement of Air-Preheaters Baskets, Unit 5 | G | Federal | PA, CDBG | 672950 | Consolidated 3050 | 327600 |  | 700000 | 700000 | 2022-04-13 | Transferred to Genera
CCWP and BCWP Spare Motors for Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 865670 | 0 |  | 865670 | 865670 | 2022-02-11 | Transferred to Genera
Procurement of (IDF) and (FDF) Spare Motors for Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 1160000 | 0 |  | 1160000 | 1160000 | 2022-02-28 | Transferred to Genera
Procurement of Condensate Pump (CP) Motor for Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 870000 | 0 |  | 870000 | 870000 | 2022-02-28 | Transferred to Genera
Replacement of Unit 5 Electric Load Center | G | Federal | PA, CDBG | 672950 | 285000 | 32066.55 |  | 285000 | 285000 | 2022-02-11 | Transferred to Genera
Replacement of Excitation System Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 2760934 | 351989.325 |  | 2760934 | 2760934 | 2022-02-18 | Transferred to Genera
Replacement of 4160 V Electric Cable Normal Transformer 5A, 5B | G | Federal | PA, CDBG | 672950 | 1028944.34 | 454392.612 |  | 375000 | 375000 | 2022-02-28 | Transferred to Genera
CS 5Major Inspection Unit 5 - HP/IP/LP Turbine Rotor Replacement | G | Federal | PA, CDBG | 672950 | 13782989.73 | 5668091.64 |  | 9388488 | 5902222 | 2022-04-13 | Transferred to Genera
Unit 5 Boiler Replace and Repairs & Auxiliary Equipment Repairs | G | Federal | PA, CDBG | 672950 | 9000000 | 0 |  | 9000000 | 9000000 | 2022-03-09 | Transferred to Genera
Water Heater 6 Replacement Work | G | Federal | PA, CDBG | 672950 | 2000000 | 0 |  | 2000000 | 2000000 | 2022-03-09 | Transferred to Genera
Unit 6 - HP/IP/LP Inspection (Failure) - To be combined w/ 3058 | G | Federal | PA, CDBG | 672950 | 1060530.5 | 791460.117 |  | 1060530.5 | 1060530.5 | 2022-04-13 | Transferred to Genera
BFWP Inner Barrel Bundle | G | Federal | PA, CDBG | 672950 | 1625954 | 878015.52 |  | 1625954 | 1625954 | 2022-02-11 | Transferred to Genera
Unit 6 LP-B Repair & Instalation Work (Failure) | G | Federal | PA, CDBG | 672950 | 2076415 | 1868773.5 |  | 2076415 | 2076415 | 2022-02-18 | Transferred to Genera
AGC - Replacement Project | G | Federal | PA, CDBG | 672950 | 400000 | 0 |  | 400000 | 400000 | 2022-02-28 | Transferred to Genera
Fuel Igniters Replacement Work | G | Federal | PA, CDBG | 672950 | 2364000 | 1829700 |  | 2364000 | 2364000 | 2022-02-28 | Transferred to Genera
Caustic Soda and Acid tanks replacement works | G | Federal | PA, CDBG | 673006 | 750000 | 110520 |  | 750000 | 750000 | 2022-04-13 | Transferred to Genera
Upgrade to Foxboro Simulation System | G | Federal | PA, CDBG | 673006 | 500000 | 0 |  | 500000 | 500000 | 2022-04-13 | Transferred to Genera
PS 3 Procurement and Delivery of Water Wall Boiler Tubes and Economizer | G | Federal | PA, CDBG | 662957 | 4028051.2 | 3600000 |  | 4028051.2 | 4028051.2 | 2022-07-22 | Transferred to Genera
PS 3 Low Pressure Turbine Rotor Refurbished, Unit 3 | G | Federal | PA, CDBG | 662957 | 3500000 | 0 |  | 3500000 | 3500000 | 2022-07-22 | Transferred to Genera
PS 4 Refractory, Insulation, scaffolding and Painting | G | Federal | PA, CDBG | 662957 | 700000 | 0 |  | 700000 | 700000 | 2022-06-04 | Transferred to Genera
Contract, on request, for Crane Services PS4 | G | NME | N/A | N/A | Not Eligible | 0 |  | 700000 | 700000 | 2022-02-18 | Transferred to Genera
Procurement Turning Gear System, Units 3 and 4 | G | Federal | PA, CDBG | 662957 | 295381.6 | 0 |  | 295381.6 | 295381.6 | 2022-06-04 | Transferred to Genera
Upgrade to Mark VI e | G | Federal | PA, CDBG | 662957 | 500000 | 0 |  | 500000 | 500000 | 2022-03-09 | Transferred to Genera
Unit 4, Superheater Header Num. 5 Material and Installation | G | Federal | PA, CDBG | 662957 | 2243385 | 0 |  | 2243385 | 2243385 | 2022-06-04 | Transferred to Genera
PS3 Boiler Repairs; MPT, Generatior and turbine Repair & Aux. Equipment | G | Federal | PA, CDBG | 662957 | 15000000 | 0 |  | 15000000 | 15000000 | 2022-02-28 | Transferred to Genera
Fuel Tanks Level Measurement System | G | Federal | PA, CDBG | 671481 | 550000 | 0 |  | 550000 | 550000 | 2022-02-18 | Transferred to Genera
Water Retention Tank Num. 3 | G | Federal | PA, CDBG | 671481 | 800000 | 518788 |  | 800000 | 800000 | 2022-02-18 | Transferred to Genera
New Water Condensate 1-2 Tank | G | Federal | PA, CDBG | 671481 | 1000000 | 531819.27 |  | 1000000 | 1000000 | 2022-02-28 | Transferred to Genera
Mega-Gens Environmental Comissioning | G | Federal | PA, CDBG | 334509 | Consolidated 334509 | 0 |  | 1036800 | 1036800 | 2022-02-11 | Transferred to Genera
Upgrade OSI DCS | G | Federal | PA, CDBG | 671481 | 1132578 | 0 |  | 1145548 | 1145578 | 2022-02-18 | Transferred to Genera
Spare Generator Breakers for Frame 5000 Hitachi Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | 0 |  | 650000 | 650000 | 2022-04-13 | Transferred to Genera
Procurement of Turbo-Compressors for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | 0 |  | 7800000 | 7800000 | 2022-04-13 | Transferred to Genera
Procurement of Spare Speed Reduction Gear for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | 0 |  | 1560000 | 1560000 | 2022-04-13 | Transferred to Genera
New Spare Three Exhaust Plenums for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | 0 |  | 780000 | 780000 | 2022-04-13 | Transferred to Genera
Three Exhaust Gas Diffusion Ducts for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | 0 |  | 390000 | 390000 | 2022-04-13 | Transferred to Genera
Major Outage Turbo -compressor (CT) 15 units | G | Federal | PA, CDBG | Pending | To be submitted | 0 |  | 39000000 | 39000000 | 2022-04-14 | Transferred to Genera
Control System Power Plant Maintenance -Generator and Technical Services | G | NME | N/A | N/A | Not Eligible | 0 |  | 2500000 | 2500000 | 2022-02-28 | Transferred to Genera
Automatic Voltage Regulatior & SFC Upgrade for 2 Units | G | Federal | PA, CDBG | 663383 | 1012000 | 893430 |  | 1043000 | 1043000 | 2022-02-28 | Transferred to Genera
LTSA Units Camb 1, 2, 3 | G | NME | N/A | N/A | Not Eligible | 0 |  | 12000000 | 12000000 | 2022-02-28 | Transferred to Genera
Unit 1A, 1B and 4A Rehabilitation | G | Federal | PA, CDBG | 663385 | 17995020 | 17692412.3444 |  | 17995020 | 17995020 | 2022-02-11 | Transferred to Genera
Unit 3B- Gas Generator Inspections and Repairs | G | Federal | PA, CDBG | 663385 | 4045630 | 4061993 |  | 4045630 | 4045630 | 2023-07-06 | Transferred to Genera
Power Generation (Generation) | G | Federal | PA, CDBG | 739681 | 372298490 | 275938880.823 | D | 372298490 | 372298490 | 2024-03-15 | Transferred to Genera
North Generation | G | Federal | HMGP | 4339-0008 | 1818550.74 | 1818550.74 |  | 1818550.74 | 5000000 | 2021-03-26 | Cancelled - Transferred to P3 for execution.
Simple Cycle Gas Turbines | G | Federal | HMGP | 4339-0010 | 280822500 | 1202604.98 |  | 280822500 | 280822500 | 2022-11-04 | Transferred to Genera
A - Monto aprobado refleja 100% del costo necesario para el proyecto. Reembolso refleja cantidad recibida en banco
B - Cantidades reembolsadas provienen de PW 9510 A&E para costos de Ingeniería, arquitectura y estudios técnicos ambientales.
C - Proyectos aprobados por NEPR y transferidos a Genera para ejecución. Desglose financiero captura aprobaciones realizadas a la Autoridad y reembolsos recibidos para gastos incurridos hasta 6/30/2023.
D - Compra de Generadores Temporeros. Reclamación y manejo de fondos es realizada por la AEE y operación de los activos es realizada por Genera.
E - Balances incluyen solo cuantias de proyectos obligados por la AEE.
* Categoría |  |  | *** Programa | [5 empty] | Department/Federal Agency |  |  | ** Fase
Generación | G |  | PA | FEMA Public Assistance |  |  |  |  | DHS |  |  | D | Diseño
Transmisión | T |  | HMGP | Hazard Mitigation Grant Program |  |  |  |  | DHS |  |  | P | Permisología
Distribución | D |  | WFPO | Watershed and Flood Prevention Operations |  |  |  |  | DHS |  |  | S | Subasta
Subestaciones | S |  | CDBG | Community Development Block Grant |  |  |  |  | DHS |  |  | C | Construcción
Hidroeléctricas | H
IT/Telecom | IT
Edificaciones | Edif.
Asuntos Ambientales | AA

## Anejo A Xref (hidden)
| Nombre de Proyecto | Categoría* | Fondos |  |  |  | Prior | Xref | Diff | Comment |  | Prior |  | Xref | Xref | Total Xref | Diff | Comment | A |  | Prior | Xref | Diff | Aprobación Negociado de Energía |  | Fase del proyecto
|  |  | Origen | Programa* | Num. | Monto Aprobado | Monto Aprobado |  |  |  | Monto desembolso | Monto desembolso | MT | AE | PMT |  |  |  |  | Estimado de Costo ($) | Estimado de Costo ($) |  |  | Costo ($) | Fecha | Fase** | Estado Permisos | Fecha Comienzo | Fecha Terminación | % Completado
435769 | FAASt South Coast Irrigation District - Canals | H | Federal | PA, CDBG | 435769 | 0 | 0 | 0 | 0 |  | 520604.64 | 353765.52 |  | 520604.64 |  | 520604.64 | 166839.12 |  | B | 144851431.5 | 144851431.5 | 144851431.5 | 0 | 32140000 | 2021-09-08 | D | N/A | 2022-07-30 | 2026-02-01 | 30%
436467 | FAASt Isabela Irrigation District - Canals & USDA Funding | H | Federal | PA, WFPO | 436467 | 0 | 0 | 0 | 0 |  | 172461.24 | 127009.8 |  | 172461.24 |  | 172461.24 | 45451.44 |  | B | 32000000 | 32000000 | 32000000 | 0 | 15000000 | 2021-09-08 | D | N/A | 2022-07-30 | 2025-12-01 | 20%
436462 | FAASt Lajas Irrigation Canals | H | Federal | PA, CDBG | 436462 | 0 | 0 | 0 | 0 |  | 170501.49 | 113814.45 |  | 170501.49 |  | 170501.49 | 56687.04 |  | B | 42573271.52 | 15000000 | 42573271.52 | -27573271.52 | 15000000 | 2021-09-08 | D | N/A | 2022-07-31 | 2026-03-27 | 20%
334803 | FAASt Loco Reservoir Dredging | H | Federal | PA, CDBG | 334803 | 0 | 0 | 0 | 0 |  | 281934.0699 | 281934.0699 |  | 281934.0699 |  | 281934.0699 | 0 |  | B | 8080000 | 6386107 | 8080000 | -1693893 | 2730000 | 2021-08-20 | D | N/A | 2024-03-31 | 2026-03-01 | 40%
335207 | FAASt Guineo Reservoir – Dredging | H | Federal | PA, CDBG | 335207 | 0 | 0 | 0 | 0 |  | 281934.0699 | 281934.0699 |  | 281934.0699 |  | 281934.0699 | 0 |  | B | 4271836 | 4271836 | 4271836 | 0 | 1250000 | 2021-08-20 | D | N/A | 2024-03-31 | 2026-05-01 | 10%
334798 | FAASt Guerrero Reservoir – Dredging | H | Federal | PA, CDBG | 334798 | 0 | 0 | 0 | 0 |  | 282084.8916 | 282084.8916 |  | 282084.8916 |  | 282084.8916 | 0 |  | B | 3918132 | 268862 | 3918132 | -3649270 | 19000 | 2021-08-20 | D | N/A | 2024-03-31 | TBD | 30%
334813 | FAASt Guayo Reservoir Dredging | H | Federal | PA, CDBG | 334813 | 0 | 0 | 0 | 0 |  | 282159.0699 | 282159.0699 |  | 282159.0699 |  | 282159.0699 | 0 |  | B | 17260000 | 40792788 | 17260000 | 23532788 | 21010000 | 2021-08-20 | D | N/A | 2024-03-31 | 2026-05-01 | 30%
334811 | FAASt Dos Bocas Reservoir Dredging | H | Federal | PA, CDBG | 334811 | 0 | 0 | 0 | 0 |  | 282141.1416 | 282141.1416 |  | 282141.1416 |  | 282141.1416 | 0 |  | B | 79831592 | 79831592 | 79831592 | 0 | 58250000 | 2021-08-20 | D | N/A | 2024-03-31 | 2027-01-29 | 30%
178722 | FAASt Caonillas (Dredging) | H | Federal | PA, CDBG | 178722 | 0 | 0 | 0 | 0 |  | 282253.6416 | 282253.6416 |  | 282253.6416 |  | 282253.6416 | 0 |  | B | 81857757 | 91747984 | 81857757 | 9890227 | 41740000 | 2021-04-28 | D | N/A | 2024-03-31 | 2027-08-04 | 30%
335206 | FAASt Matrullas Reservoir–Dredging | H | Federal | PA, CDBG | 335206 | 0 | 0 | 0 | 0 |  | 281934.0699 | 281934.0699 |  | 281934.0699 |  | 281934.0699 | 0 |  | B | 8055082 | 8055082 | 8055082 | 0 | 3080000 | 2021-08-20 | D | N/A | 2024-03-31 | 2026-05-01 | 10%
334773 | FAASt Lucchetti Reservoir – Dredging | H | Federal | PA, CDBG | 334773 | 0 | 0 | 0 | 0 |  | 281990.3199 | 281990.3199 |  | 281990.3199 |  | 281990.3199 | 0 |  | B | 40020000 | 66060757 | 40020000 | 26040757 | 35810000 | 2021-08-20 | D | N/A | 2024-03-31 | 2026-05-01 | 30%
334772 | FAASt Guayabal Reservoir – Dredging | H | Federal | PA, CDBG | 334772 | 0 | 0 | 0 | 0 |  | 281934.0699 | 281934.0699 |  | 281934.0699 |  | 281934.0699 | 0 |  | B | 20606934 | 20606934 | 20606934 | 0 | 7750000 | 2021-08-20 | D | N/A | 2024-03-31 | 2026-05-01 | 10%
334771 | FAASt Guajataca Reservoir – Dredging | H | Federal | PA, CDBG | 334771 | 0 | 0 | 0 | 0 |  | 282084.8916 | 282084.8916 |  | 282084.8916 |  | 282084.8916 | 0 |  | B | 40334479 | 26718925 | 40334479 | -13615554 | 18990000 | 2021-08-20 | D | N/A | 2024-03-31 | TBD | 30%
334769 | FAASt Garzas Reservoir – Dredging | H | Federal | PA, CDBG | 334769 | 0 | 0 | 0 | 0 |  | 282679.7444 | 282679.7444 |  | 282679.7444 |  | 282679.7444 | 0 |  | B | 11154286 | 4598559 | 11154286 | -6555727 | 1530000 | 2021-06-08 | D | N/A | 2024-03-31 | TBD | 30%
436468 | FAASt Toro Negro Hydroelectric System Connection | H | Federal | PA, CDBG | 436468 | 0 | 0 | 0 | 0 |  | 346546.926 | 346546.926 |  | 346546.926 |  | 346546.926 | 0 |  | B | 57244061.71 | 57244061.71 | 57244061.71 | 0 | 15220000 | 2021-09-08 | D | N/A | 2021-07-30 | 2025-09-25 | 35%
728260 | FAAST Caonillas Hydroelectric Power Plant I | H | Federal | PA, CDBG | 728260 | 0 | 0 | 0 | 0 |  | 252743.31 | 252743.31 |  | 252743.31 |  | 252743.31 | 0 |  | B | 3611152 | 3611152 | 3611152 | 0 | 1650000 | 2021-04-28 | D | N/A | 2024-02-14 | 2025-07-25 | 30%
180723 | FAASt - Rio Blanco Hydroelectric System | H | Federal | PA, CDBG | 180723 | 0 | 0 | 0 | 0 |  | 322049.997 | 322049.997 |  | 322049.997 |  | 322049.997 | 0 |  | B | 49005575.55 | 49005575.55 | 49005575.55 | 0 | 48120000 | 2021-04-28 | D | N/A | 2021-07-31 | 2025-12-25 | 30%
COR3-1966 | Retrofit projects on hydroelectric turbines (15 Projects) | H | Federal | PA, CDBG | COR3-1966 | 0 | 0 | 0 | 0 | Ok | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 320790000 | 320790000 | 320790000 | 0 | 320790000 | 2023-09-28 | D | N/A | Pending PRDOH | TBD | NA
334770 | FAASt Guajataca Dam – Permanent Repairs | H | Federal | PA, CDBG | 334770 | 0 | 0 | 0 | 0 |  | 4190573.646 | 1833808.968 |  | 4190573.646 |  | 4190573.646 | 2356764.678 |  | B | 1086970000 | 1086970000 | 1086970000 | 0 | 566000000 | 2021-08-20 | D | N/A | 2024-01-15 | Dec-28 | 10%
436621 | FAASt Dams Minor Repairs | H | Federal | PA, CDBG | 436621 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 24607290.48 | 27445939.52 | 24607290.48 | 2838649.04 | 3560000 | 2021-09-28 | D | N/A | 2024-02-12 | 2025-07-25 | 30%
721184 | FAASt - Guayabal Seismic Retrofit | H | Federal | PA, CDBG | 721184 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 326154895.79 | 326154895.79 | 326154895.79 | 0 | 299278101 | 2023-05-18 | D | N/A | 2024-07-01 | 2027-12-26 | 10%
4339-0011 | Patillas Dams | H | Federal | HMGP | 4339-0011 | 558000000 | 558000000 | 558000000 | 0 |  | 1855903.87 | 1635041.76 | 1855903.87 |  | 0 | 1855903.87 | 220862.11 |  | C | 567024315 | 568336927 | 567024315 | 1312612 | 558530000 | 2021-08-20 | D | N/A | 2024-01-01 | 2026-08-10 | 71%
4339-0012 | Early Warning System | H | Federal | HMGP | 4339-0012 | 99976487 | 99976487 | 99976487 | 0 |  | 10271778.18 | 10271778.18 | 10271778.18 |  | 0 | 10271778.18 | 0 |  | C | 99976487 | 100000000 | 99976487 | 23513 | 100000000 | 2021-08-20 | C | N/A | 2024-03-31 | 2024-08-01 | 78%
725535 | FAASt- System Upgrade for Generation Plants (IT/OT) | IT | Federal | PA, CDBG | 725535 | 11423825 | 11423825 | 11423825 | 0 |  | 1335253.5 | 0 | 1335253.5 |  | 0 | 1335253.5 | 1335253.5 |  |  | 11423825 | 11423825 | 11423825 | 0 | 11423825 | 2023-06-22 | D | N/A | 2024-02-08 | 2025-10-01 | 75%
746897 | FAASt Bonus Plant | Edif. | Federal | PA, CDBG | 746897 | 1579615.4333 | 0 | 1579615.4333 | -1579615.4333 | Ok new obligation | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 1579615.43 | 1579615.43 | 1579615.43 | 0 | 1670081 | 2024-04-04 | D | N/A | TBD | 2026-06-01 | 30%
[9 empty] | 0 | [7 empty] | 0 |  |  | 3083202018.98
| Proyectos reclamados por PREPAs y transferidos a Operadores | [5 empty] | E |  | 0 | [7 empty] | 0 | [8 empty] | C
180692 | FAASt Mobile Generation Units Purchases | G | Federal | PA, CDBG | 180692 | 59740469.9222 | 59740469.92 | 59740469.9222 | -0.0022222 |  | 53766422.93 | 53766422.93 | 53766422.93 | 0 | 0 | 53766422.93 | 0 |  |  | 59740469.92 | 59740469.92 |  |  | 59740469.92 | 2021-06-08 | Transferred to Genera
334509 | FAASt Palo Seco Demin Water Tank 4 | G | Federal | PA, CDBG | 334509 | 2890937.3333 | 2890937.33 | 2890937.3333 | -0.0033333 |  | 3232395.154 | 2944059.924 | 2883352.33 | 349042.824 | 0 | 3232395.154 | 288335.23 |  |  | 2550000 | 2550000 |  |  | 2550000 | 2021-09-08 | Transferred to Genera
670036 | FAASt Fire Pump for Aguirre Power Complex (AG-004) | G | Federal | PA, CDBG | 670036 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 280040 | 280040 |  |  | 280040 | 2022-03-09 | Transferred to Genera
663383 | FAASt Cambalache Power Plant – Flood Protection Barrier (Generation) | G | Federal | PA, CDBG | 169340 | 0 | 0 | 0 | 0 | Eliminate - Consolidated to another project | 251663.526 | 251663.526 |  | 0 | 251663.526 | 251663.526 | 0 |  |  | 4000000 | 4000000 |  |  | 4000000 | 2021-06-08 | Transferred to Genera
164988 | FAASt New Black Start System at Costa Sur | G | Federal | PA, CDBG | 164988 | 235670650 | 0 | 235670650 | -235670650 | Genera Obligation | 104048.19 | 104048.19 |  | 0 | 104048.19 | 104048.19 | 0 |  |  | 45200000 | 45200000 |  |  | 45200000 | 2021-06-08 | Transferred to Genera
2033 | Rehabilitation Fuel Tank Farm Liners | G | Federal | PA, CDBG | 669498 | 1662329.23 | 1291000 | 1662329.23 | -371329.23 | Genera Obligation | 279931.14 | 279931.14 |  | 0 | 279931.14 | 279931.14 | 0 |  |  | 1291000 | 1291000 |  |  | 1291000 | 2022-02-11 | Transferred to Genera
2034 | Two New Condenser Discharge Water Pumps Motors | G | Federal | PA, CDBG | 669498 | 750000 | 750000 | 750000 | 0 |  | 600300 | 600300 |  | 0 | 600300 | 600300 | 0 |  |  | 750000 | 750000 |  |  | 750000 | 2022-02-11 | Transferred to Genera
2035 | Two New BCWP Motors | G | Federal | PA, CDBG | 669498 | 640150 | 640150 | 640150 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 640150 | 640150 |  |  | 640150 | 2022-02-11 | Transferred to Genera
2044 | Purchase and Installation Breakers 480 V | G | Federal | PA, CDBG | 669498 | 350115 | 350115 | 350115 | 0 |  | 288846 | 288846 |  | 0 | 288846 | 288846 | 0 |  |  | 350115 | 350115 |  |  | 350115 | 2022-03-09 | Transferred to Genera
2032 | Sea Water Intake Structural Repairs Work | G | NME | N/A | N/A | Not eligible | Not eligible | Not eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 5274222 | 5274222 |  |  | 5274222 | 2022-02-11 | Transferred to Genera
2029 | Unit 1 South Wall Boiler Tubing Replacement and Boilers Repairs /Air and Gas Duct Pre-heaters Repair Work | G | Federal | PA, CDBG | 669233 | 5983852.95 | 5983852.95 | 5983852.95 | 0 |  | 3014409.6 | 3014409 |  | 0 | 3014409.6 | 3014409.6 | 0.6 |  |  | 5983852.95 | 5983852.95 |  |  | 5983852.95 | 2022-07-22 | Transferred to Genera
2031 | Replacement of Load Center 1-4 Condenser Circulating Water Pump | G | Federal | PA, CDBG | 669233 | 630000 | 630000 | 630000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 630000 | 630000 |  |  | 630000 | 2022-02-11 | Transferred to Genera
2041 | Inner Barrel Bundle | G | Federal | PA, CDBG | 669233 | 1625954 | 1625954 | 1625954 | 0 |  | 229491.23 | 229491.23 |  | 0 | 229491.23 | 229491.23 | 0 |  |  | 1625954 | 1625954 |  |  | 1625954 | 2022-02-18 | Transferred to Genera
2042 | Unit 1 - Major Inspection (Replacement Turbo-Generator) | G | Federal | PA, CDBG | 669233 | 11164417 | 11164417 | 11164417 | 0 |  | 10371203.45 | 10371203.45 |  | 0 | 10371203.45 | 10371203.45 | 0 |  |  | 11164417 | 11164417 |  |  | 11164417 | 2022-02-11 | Transferred to Genera
2043 | Unit 2 Excitation System | G | Federal | PA, CDBG | 669233 | 1501675 | 1501675 | 1501675 | 0 |  | 273001.5 | 273001.5 |  | 0 | 273001.5 | 273001.5 | 0 |  |  | 1516675 | 1516675 |  |  | 1516675 | 2022-02-11 | Transferred to Genera
2036 | Procurement of Stages 1-1 & 1-2 Turbine Rotor Bucket Set | G | Federal | PA, CDBG | 669815 | 497267 | 497267 | 497267 | 0 |  | 447540.3 | 447540.3 |  | 0 | 447540.3 | 447540.3 | 0 |  |  | 497267 | 497267 |  |  | 497267 | 2022-03-09 | Transferred to Genera
2037 | New Water Condensate Tank | G | Federal | PA, CDBG | 669815 | 1389220 | 1389220 | 1389220 | 0 |  | 650726.46 | 650726.46 |  | 0 | 650726.46 | 650726.46 | 0 |  |  | 1389220 | 1389220 |  |  | 410125 | 2022-03-09 | Transferred to Genera
2038 | Major inspection Unit 1-3 | G | Federal | PA, CDBG | 669815 | 2599971 | 2599971 | 2599971 | 0 |  | 602631.63 | 602631.63 |  | 0 | 602631.63 | 602631.63 | 0 |  |  | 2559917 | 2559917 |  |  | 2599971 | 2022-03-09 | Transferred to Genera
2039 | Hot Gas Path Repairs Work Units 2-4 and stand by transformer | G | Federal | PA, CDBG | 669815 | 806507.36 | 806507.36 | 806507.36 | 0 |  | 427219.24 | 427219.24 |  | 0 | 427219.24 | 427219.24 | 0 |  |  | 716267.36 | 716267.36 |  |  | 716267.36 | 2022-02-11 | Transferred to Genera
2040 | Hot Gas Path Inspection Work Units 1-1 and 1-2 | G | Federal | PA, CDBG | 669815 | 1092000 | 1092000 | 1092000 | 0 |  | 953782 | 953782 |  | 0 | 953782 | 953782 | 0 |  |  | 1092000 | 1092000 |  |  | 1092000 | 2022-02-11 | Transferred to Genera
1001 | Units 5 Cooling Tower Replacement | G | Federal | PA, CDBG | 662947 | 1887145 | 1887145 | 1887145 | 0 |  | 2098251 | 2098251 |  | 0 | 2098251 | 2098251 | 0 |  |  | 1887145 | 1887145 |  |  | 1887145 | 2022-02-11 | Transferred to Genera
1002 | Units 5 New High Pressure Pumps | G | Federal | PA, CDBG | 662947 | 1600000 | 1600000 | 1600000 | 0 |  | 215830.98 | 215830.98 |  | 0 | 215830.98 | 215830.98 | 0 |  |  | 1600000 | 1600000 |  |  | 1600000 | 2022-03-09 | Transferred to Genera
1003 | Units 5 Condenser Repair and Coating Application | G | Federal | PA, CDBG | 662947 | 1031250 | 1031250 | 1031250 | 0 |  | 1262492.77 | 1262492.77 |  | 0 | 1262492.77 | 1262492.77 | 0 |  |  | 1031250 | 1031250 |  |  | 1031250 | 2022-02-11 | Transferred to Genera
1004 | Units 5 HP Bleed Valve, LP Bleed Valve and Heat Injection Steam Valve | G | Federal | PA, CDBG | 662947 | 374237 | 374237 | 374237 | 0 |  | 270635.4 | 270635.4 |  | 0 | 270635.4 | 270635.4 | 0 |  |  | 374237 | 374237 |  |  | 374237 | 2022-02-11 | Transferred to Genera
1005 | Units 5 and 6 Black Start Emergency Generator Upgrade | G | Federal | PA, CDBG | 662947 | 348509.53 | 348509.53 | 348509.53 | 0 |  | 308169.56 | 308169.56 |  | 0 | 308169.56 | 308169.56 | 0 |  |  | 348509.53 | 348509.53 |  |  | 348509.53 | 2022-02-11 | Transferred to Genera
1006 | Units 5 Replacement of Outlet Valves and Elbow Condenser | G | Federal | PA, CDBG | 662947 | 673667 | 673667 | 673667 | 0 |  | 337500 | 337500 |  | 0 | 337500 | 337500 | 0 |  |  | 673667 | 673667 |  |  | 673667 | 2022-02-11 | Transferred to Genera
1013 | Unit 5 SCR - Amonium Procurement | G | NME | N/A | N/A | Not eligible | 0 | Not eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 500000 | 500000 |  |  | 500000 | 2022-02-28 | Transferred to Genera
1014 | Units 5 Heavy Equipment Rental Services | G | NME | N/A | N/A | Not eligible | 0 | Not eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 850000 | 850000 |  |  | 850000 | 2022-03-09 | Transferred to Genera
1018 | LTSA SJ5 | G | NME | N/A | N/A | Not eligible | 0 | Not eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 8000000 | 8000000 |  |  | 8000000 | 2022-04-13 | Transferred to Genera
1019 | LTSA SJ6 | G | NME | N/A | N/A | Not eligible | 0 | Not eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 8000000 | 8000000 |  |  | 8000000 | 2022-04-13 | Transferred to Genera
1017 | Steam Rotor Replacement Unit 5 & CT Repairs | G | Federal | PA, CDBG | 662947 | 12055544.4 | 12055544.4 | 12055544.4 | 0 |  | 8985166.43 | 8985166.43 |  | 0 | 8985166.43 | 8985166.43 | 0 |  |  | 12055544.4 | 12055544.4 |  |  | 12055544.4 | 2022-04-13 | Transferred to Genera
1020 | Control System Upgrade units 5 & 6 | G | Federal | PA, CDBG | 662947 | 3203050 | 3203050 | 3203050 | 0 |  | 2882744.52 | 2882744.52 |  | 0 | 2882744.52 | 2882744.52 | 0 |  |  | 3203050 | 3203050 |  |  | 3203050 | 2022-02-11 | Transferred to Genera
1023 | Unit 6 - Major Overhaul (Combustion Turbine Repairs) | G | Federal | PA, CDBG | 662947 | 12768424.79 | 12768424.79 | 12768424.79 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 12768424.79 | 12768424.79 |  |  | 12768424.79 | 2022-03-09 | Transferred to Genera
1029 | Purchases and Installation of Modules D&E HRSG Unit 6 | G | Federal | PA, CDBG | 662947 | 12619593 | 12619593 | 12619593 | 0 |  | 439890.2 | 439890.2 |  | 0 | 439890.2 | 439890.2 | 0 |  |  | 12619593 | 12619593 |  |  | 12619593 | 2023-03-20 | Transferred to Genera
1024 | Purchases and Installation of Modules D&E HRSG Unit 5 | G | Federal | PA, CDBG | 662947 | 9750263 | 9750263 | 9750263 | 0 |  | 7070213.69 | 7070213.69 |  | 0 | 7070213.69 | 7070213.69 | 0 |  |  | 9750263 | 9750263 |  |  | 9750263 | 2022-02-11 | Transferred to Genera
1025 | Replacement of the Online Condenser Cleaner Unit 5 | G | Federal | PA, CDBG | 662947 | 5994350 | 3600000 | 5994350 | -2394350 | Genera Obligation | 678798.22 | 678798.22 |  | 0 | 678798.22 | 678798.22 | 0 |  |  | 3600000 | 3600000 |  |  | 3600000 | 2022-02-11 | Transferred to Genera
1026 | Unit 6 - Major Overhaul - Steam Turbine Repairs | G | Federal | PA, CDBG | 662947 | 12768424.79 | 12768424.79 | 12768424.79 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 12768424.79 | 12768424.79 |  |  | 12768424.79 | 2022-03-09 | Transferred to Genera
1007 | Unit 7 Air Preheater Maintenance and Replacement | G | Federal | PA, CDBG | 687480 | 600000 | 600000 | 600000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 600000 | 600000 |  |  | 600000 | 2022-03-09 | Transferred to Genera
1010 | Replacement of Two Uninterruptible Power Supply Systems for Units 7 and 8 | G | Federal | PA, CDBG | 687480 | 739092 | 739092 | 739092 | 0 |  | 50443.452 | 50443.452 |  | 0 | 50443.452 | 50443.452 | 0 |  |  | 450000 | 450000 |  |  | 450000 | 2022-03-09 | Transferred to Genera
1022 | Unit 7 Rehabilitation ( Turbine) | G | Federal | PA, CDBG | 687480 | 10000000 | 10000000 | 10000000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 10000000 | 10000000 |  |  | 10000000 | 2022-10-21 | Transferred to Genera
1027 | Unit 7 Boiler Sections Replace, Repairs & Auxiliary Equipment Inspection Work | G | Federal | PA, CDBG | 687480 | 8000000 | 8000000 | 8000000 | 0 |  | 536627.96 | 536627.96 |  | 0 | 536627.96 | 536627.96 | 0 |  |  | 8000000 | 8000000 |  |  | 8000000 | 2022-10-21 | Transferred to Genera
1009 | Cooling Tower Unit 10 Repair Works | G | Federal | PA, CDBG | Pending | Pending | 0 | Pending | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 385000 | 385000 |  |  | 385000 | 2022-06-04 | Transferred to Genera
1008 | Repairs to Nautilus Water Treatment System | G | Federal | PA, CDBG | 667744 | 250000 | 250000 | 250000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 250000 | 250000 |  |  | 250000 | 2022-03-09 | Transferred to Genera
1011 | Units 7-10 New Raw Water Tank | G | Federal | PA, CDBG | 667744 | 1496000 | 1496000 | 1496000 | 0 |  | 1300994.8 | 1300994.8 |  | 0 | 1300994.8 | 1300994.8 | 0 |  |  | 1496000 | 1496000 |  |  | 1000000 | 2022-03-09 | Transferred to Genera
1012 | Structural Repairs Fuel Service Tank 10 | G | Federal | PA, CDBG | 667744 | 975689 | 975689 | 975689 | 0 |  | 878120.11 | 878120.11 |  | 0 | 878120.11 | 878120.11 | 0 |  |  | 975689 | 975689 |  |  | 647000 | 2022-06-04 | Transferred to Genera
1015 | Water Treatment and Technical Assistance Cooling Water System | G | NME | N/A | N/A | Not eligible | 0 | Not eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 232727.04 | 232727.04 |  |  | 232727.04 | 2022-03-09 | Transferred to Genera
3046 | Traveling Screens Replacement | G | Federal | PA, CDBG | 672950 | 5000000 | 5000000 | 5000000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 5000000 | 5000000 |  |  | 5000000 | 2022-03-09 | Transferred to Genera
3047 | Replacement of Regulator Valves for Boiler Feed Water Units 5 & 6 | G | Federal | PA, CDBG | 672950 | 301664 | 301664 | 301664 | 0 |  | 270000 | 270000 |  | 0 | 270000 | 270000 | 0 |  |  | 301664 | 301664 |  |  | 301664 | 2022-03-09 | Transferred to Genera
3048 | Low Pressure Water Heater 3 Repair Work | G | Federal | PA, CDBG | 672950 | 400000 | 400000 | 400000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 400000 | 400000 |  |  | 400000 | 2022-03-09 | Transferred to Genera
3049 | Procurement of Water Heater 5 (Deaerator) Spare Pump | G | Federal | PA, CDBG | 672950 | 400000 | 400000 | 400000 | 0 |  | 95045.4 | 95045.4 |  | 0 | 95045.4 | 95045.4 | 0 |  |  | 400000 | 400000 |  |  | 400000 | 2022-02-28 | Transferred to Genera
3050 | Procurement & Replacement of Air-Preheaters Baskets, Unit 5 | G | Federal | PA, CDBG | 672950 | 1966083 | 1966083 | 1966083 | 0 |  | 1009313.1 | 1009313.1 |  | 0 | 1009313.1 | 1009313.1 | 0 |  |  | 1966083 | 1966083 |  |  | 1966083 | 2022-02-11 | Transferred to Genera
3051 | Replacement of Air-Preheaters Baskets, Unit 5 | G | Federal | PA, CDBG | 672950 | Consolidated 3050 | 0 | Consolidated 3050 | 0 | ok | 327600 | 327600 |  | 0 | 327600 | 327600 | 0 |  |  | 700000 | 700000 |  |  | 700000 | 2022-04-13 | Transferred to Genera
3052 | CCWP and BCWP Spare Motors for Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 865670 | 865670 | 865670 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 865670 | 865670 |  |  | 865670 | 2022-02-11 | Transferred to Genera
3053 | Procurement of (IDF) and (FDF) Spare Motors for Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 1160000 | 1160000 | 1160000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 1160000 | 1160000 |  |  | 1160000 | 2022-02-28 | Transferred to Genera
3054 | Procurement of Condensate Pump (CP) Motor for Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 870000 | 870000 | 870000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 870000 | 870000 |  |  | 870000 | 2022-02-28 | Transferred to Genera
3055 | Replacement of Unit 5 Electric Load Center | G | Federal | PA, CDBG | 672950 | 285000 | 285000 | 285000 | 0 |  | 32066.55 | 32066.55 |  | 0 | 32066.55 | 32066.55 | 0 |  |  | 285000 | 285000 |  |  | 285000 | 2022-02-11 | Transferred to Genera
3056 | Replacement of Excitation System Units 5 and 6 | G | Federal | PA, CDBG | 672950 | 2760934 | 2760934 | 2760934 | 0 |  | 351989.325 | 351989.325 |  | 0 | 351989.325 | 351989.325 | 0 |  |  | 2760934 | 2760934 |  |  | 2760934 | 2022-02-18 | Transferred to Genera
3057 | Replacement of 4160 V Electric Cable Normal Transformer 5A, 5B | G | Federal | PA, CDBG | 672950 | 1028944.34 | 1028944.34 | 1028944.34 | 0 |  | 454392.612 | 454392.612 |  | 0 | 454392.612 | 454392.612 | 0 |  |  | 375000 | 375000 |  |  | 375000 | 2022-02-28 | Transferred to Genera
3058 | CS 5Major Inspection Unit 5 - HP/IP/LP Turbine Rotor Replacement | G | Federal | PA, CDBG | 672950 | 13782989.73 | 13782989.73 | 13782989.73 | 0 |  | 5668091.64 | 5668091.64 |  | 0 | 5668091.64 | 5668091.64 | 0 |  |  | 9388488 | 9388488 |  |  | 5902222 | 2022-04-13 | Transferred to Genera
3059 | Unit 5 Boiler Replace and Repairs & Auxiliary Equipment Repairs | G | Federal | PA, CDBG | 672950 | 9000000 | 9000000 | 9000000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 9000000 | 9000000 |  |  | 9000000 | 2022-03-09 | Transferred to Genera
3060 | Water Heater 6 Replacement Work | G | Federal | PA, CDBG | 672950 | 2000000 | 2000000 | 2000000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 2000000 | 2000000 |  |  | 2000000 | 2022-03-09 | Transferred to Genera
3062 | Unit 6 - HP/IP/LP Inspection (Failure) - To be combined w/ 3058 | G | Federal | PA, CDBG | 672950 | 1060530.5 | 1060530.5 | 1060530.5 | 0 |  | 791460.117 | 791460.117 |  | 0 | 791460.117 | 791460.117 | 0 |  |  | 1060530.5 | 1060530.5 |  |  | 1060530.5 | 2022-04-13 | Transferred to Genera
3063 | BFWP Inner Barrel Bundle | G | Federal | PA, CDBG | 672950 | 1625954 | 1625954 | 1625954 | 0 |  | 878015.52 | 878015.52 |  | 0 | 878015.52 | 878015.52 | 0 |  |  | 1625954 | 1625954 |  |  | 1625954 | 2022-02-11 | Transferred to Genera
3065 | Unit 6 LP-B Repair & Instalation Work (Failure) | G | Federal | PA, CDBG | 672950 | 2076415 | 2076415 | 2076415 | 0 |  | 1868773.5 | 1868773.5 |  | 0 | 1868773.5 | 1868773.5 | 0 |  |  | 2076415 | 2076415 |  |  | 2076415 | 2022-02-18 | Transferred to Genera
3066 | AGC - Replacement Project | G | Federal | PA, CDBG | 672950 | 400000 | 400000 | 400000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 400000 | 400000 |  |  | 400000 | 2022-02-28 | Transferred to Genera
3067 | Fuel Igniters Replacement Work | G | Federal | PA, CDBG | 672950 | 2364000 | 2364000 | 2364000 | 0 |  | 1829700 | 1829700 |  | 0 | 1829700 | 1829700 | 0 |  |  | 2364000 | 2364000 |  |  | 2364000 | 2022-02-28 | Transferred to Genera
3061 | Caustic Soda and Acid tanks replacement works | G | Federal | PA, CDBG | 673006 | 750000 | 750000 | 750000 | 0 |  | 110520 | 110520 |  | 0 | 110520 | 110520 | 0 |  |  | 750000 | 750000 |  |  | 750000 | 2022-04-13 | Transferred to Genera
3068 | Upgrade to Foxboro Simulation System | G | Federal | PA, CDBG | 673006 | 500000 | 500000 | 500000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 500000 | 500000 |  |  | 500000 | 2022-04-13 | Transferred to Genera
4069 | PS 3 Procurement and Delivery of Water Wall Boiler Tubes and Economizer | G | Federal | PA, CDBG | 662957 | 4028051.2 | 4028051.2 | 4028051.2 | 0 |  | 3600000 | 3600000 |  | 0 | 3600000 | 3600000 | 0 |  |  | 4028051.2 | 4028051.2 |  |  | 4028051.2 | 2022-07-22 | Transferred to Genera
4070 | PS 3 Low Pressure Turbine Rotor Refurbished, Unit 3 | G | Federal | PA, CDBG | 662957 | 3500000 | 3500000 | 3500000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 3500000 | 3500000 |  |  | 3500000 | 2022-07-22 | Transferred to Genera
4073 | PS 4 Refractory, Insulation, scaffolding and Painting | G | Federal | PA, CDBG | 662957 | 700000 | 700000 | 700000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 700000 | 700000 |  |  | 700000 | 2022-06-04 | Transferred to Genera
4074 | Contract, on request, for Crane Services PS4 | G | NME | N/A | N/A | Not Eligible | Not Eligible | Not Eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 700000 | 700000 |  |  | 700000 | 2022-02-18 | Transferred to Genera
4075 | Procurement Turning Gear System, Units 3 and 4 | G | Federal | PA, CDBG | 662957 | 295381.6 | 295381.6 | 295381.6 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 295381.6 | 295381.6 |  |  | 295381.6 | 2022-06-04 | Transferred to Genera
4079 | Upgrade to Mark VI e | G | Federal | PA, CDBG | 662957 | 500000 | 500000 | 500000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 500000 | 500000 |  |  | 500000 | 2022-03-09 | Transferred to Genera
4080 | Unit 4, Superheater Header Num. 5 Material and Installation | G | Federal | PA, CDBG | 662957 | 2243385 | 2243385 | 2243385 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 2243385 | 2243385 |  |  | 2243385 | 2022-06-04 | Transferred to Genera
4081 | PS3 Boiler Repairs; MPT, Generatior and turbine Repair & Aux. Equipment | G | Federal | PA, CDBG | 662957 | 15000000 | 15000000 | 15000000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 15000000 | 15000000 |  |  | 15000000 | 2022-02-28 | Transferred to Genera
4071 | Fuel Tanks Level Measurement System | G | Federal | PA, CDBG | 671481 | 550000 | 550000 | 550000 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 550000 | 550000 |  |  | 550000 | 2022-02-18 | Transferred to Genera
4072 | Water Retention Tank Num. 3 | G | Federal | PA, CDBG | 671481 | 800000 | 800000 | 800000 | 0 |  | 518788 | 518788 |  | 0 | 518788 | 518788 | 0 |  |  | 800000 | 800000 |  |  | 800000 | 2022-02-18 | Transferred to Genera
4076 | New Water Condensate 1-2 Tank | G | Federal | PA, CDBG | 671481 | 1000000 | 1000000 | 1000000 | 0 |  | 531819.27 | 531819.27 |  | 0 | 531819.27 | 531819.27 | 0 |  |  | 1000000 | 1000000 |  |  | 1000000 | 2022-02-28 | Transferred to Genera
4077 | Mega-Gens Environmental Comissioning | G | Federal | PA, CDBG | 334509 | Consolidated 334509 | Consolidated 334509 | Consolidated 334509 | 0 | ok | 0 | 0 |  | 0 | Fully reimbursed | 0 | 0 |  |  | 1036800 | 1036800 |  |  | 1036800 | 2022-02-11 | Transferred to Genera
4078 | Upgrade OSI DCS | G | Federal | PA, CDBG | 671481 | 1132578 | 1132578 | 1132578 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 1145548 | 1145548 |  |  | 1145578 | 2022-02-18 | Transferred to Genera
5082 | Spare Generator Breakers for Frame 5000 Hitachi Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | To be submitted | To be submitted | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 650000 | 650000 |  |  | 650000 | 2022-04-13 | Transferred to Genera
5083 | Procurement of Turbo-Compressors for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | To be submitted | To be submitted | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 7800000 | 7800000 |  |  | 7800000 | 2022-04-13 | Transferred to Genera
5084 | Procurement of Spare Speed Reduction Gear for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | To be submitted | To be submitted | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 1560000 | 1560000 |  |  | 1560000 | 2022-04-13 | Transferred to Genera
5085 | New Spare Three Exhaust Plenums for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | To be submitted | To be submitted | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 780000 | 780000 |  |  | 780000 | 2022-04-13 | Transferred to Genera
5086 | Three Exhaust Gas Diffusion Ducts for Frame 5000 Gas Turbines | G | Federal | PA, CDBG | Pending | To be submitted | To be submitted | To be submitted | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 390000 | 390000 |  |  | 390000 | 2022-04-13 | Transferred to Genera
5087 | Major Outage Turbo -compressor (CT) 15 units | G | Federal | PA, CDBG | Pending | To be submitted | To be submitted | To be submitted | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 39000000 | 39000000 |  |  | 39000000 | 2022-04-14 | Transferred to Genera
6089 | Control System Power Plant Maintenance -Generator and Technical Services | G | NME | N/A | N/A | Not Eligible | Not Eligible | Not Eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 2500000 | 2500000 |  |  | 2500000 | 2022-02-28 | Transferred to Genera
6090 | Automatic Voltage Regulatior & SFC Upgrade for 2 Units | G | Federal | PA, CDBG | 663383 | 1012000 | 1012000 | 1012000 | 0 |  | 893430 | 893430 |  | 0 | 893430 | 893430 | 0 |  |  | 1043000 | 1043000 |  |  | 1043000 | 2022-02-28 | Transferred to Genera
6091 | LTSA Units Camb 1, 2, 3 | G | NME | N/A | N/A | Not Eligible | Not Eligible | Not Eligible | 0 | ok | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 12000000 | 12000000 |  |  | 12000000 | 2022-02-28 | Transferred to Genera
7092 | Unit 1A, 1B and 4A Rehabilitation | G | Federal | PA, CDBG | 663385 | 17995020 | 17995020 | 17995020 | 0 |  | 17692412.3444 | 15940450.984 |  | 0 | 17692412.3444 | 17692412.3444 | 1751961.3604 |  |  | 17995020 | 17995020 |  |  | 17995020 | 2022-02-11 | Transferred to Genera
7093 | Unit 3B- Gas Generator Inspections and Repairs | G | Federal | PA, CDBG | 663385 | 4045630 | 4045630 | 4045630 | 0 |  | 4061993 | 3623787.13 |  | 0 | 4061993 | 4061993 | 438205.87 |  |  | 4045630 | 4045630 |  |  | 4045630 | 2023-07-06 | Transferred to Genera
739681 | Power Generation (Generation) | G | Federal | PA, CDBG | 739681 | 372298490 | 372298490 | 372298490 | 0 |  | 275938880.823 | 275938880.823 |  | 275938880.823 | 0 | 275938880.823 | 0 |  | D | 372298490 | 372298490 |  |  | 372298490 | 2024-03-15 | Transferred to Genera
4339-0008 | North Generation | G | Federal | HMGP | 4339-0008 | 1818550.74 | 1818550.74 | 1818550.74 | 0 |  | 1818550.74 | 1818550.74 |  | 1818550.74 | 0 | 1818550.74 | 0 |  |  | 1818550.74 | 1818550.74 |  |  | 5000000 | 2021-03-26 | Cancelled - Transferred to P3 for execution.
4339-0010 | Simple Cycle Gas Turbines | G | Federal | HMGP | 4339-0010 | 280822500 | 280822500 | 280822500 | 0 |  | 1202604.98 | 1202604.98 |  | 1202604.98 | 0 | 1202604.98 | 0 |  |  | 280822500 | 280822500 |  |  | 280822500 | 2022-11-04 | Transferred to Genera on July 2023 - Following PREB orders
[11 empty] | 445296485.1424 | 438636124.194 |  |  |  | 445296485.1424 | 6660360.9484 | Total Increase in Report
| A - Monto aprobado refleja 100% del costo necesario para el proyecto. Reembolso refleja cantidad recibida en banco, neta del pareo local (10%). | [10 empty] | 6660360.9484 |  |  |  |  | 6660303.65 | Total RFRs in Master Tracker Received in Quarter
| B - Cantidades reembolsadas provienen de PW 9510 A&E para costos de Ingeniería, arquitectura y estudios técnicos ambientales. | [15 empty] | 57.2984
C - Proyectos aprobados por NEPR y transferidos a Genera para ejecución. Desglose financiero captura aprobaciones realizadas a la Autoridad y reembolsos recibidos para gastos incurridos hasta 6/30/2023.
D - Compra de Generadores Temporeros. Reclamación y manejo de fondos es realizada por la AEE y operación de los activos es realizada por Genera.
E - Balances incluyen solo cuantias de proyectos obligados por la AEE.
| * Categoría |  |  | *** Programa | [19 empty] | Department/Federal Agency |  |  | ** Fase
| Generación | G |  | PA | FEMA Public Assistance | [18 empty] | DHS |  |  | D | Diseño
| Transmisión | T |  | HMGP | Hazard Mitigation Grant Program | [18 empty] | DHS |  |  | P | Permisología
| Distribución | D |  | WFPO | Watershed and Flood Prevention Operations | [18 empty] | USDA |  |  | S | Subasta
| Subestaciones | S |  | CDBG | Community Development Block Grant | [18 empty] | HUD |  |  | C | Construcción
| Hidroeléctricas | H
| IT/Telecom | IT
| Edificaciones | Edif.
| Asuntos Ambientales | AA