## PREB 2-11 Projects To Activate
|  | PREPA Comments | [5 empty] | Project Details-LUMA Provided
Project Number |  | Asset | Withdrawn Date | Identified by LUMA in PREB Priority Stabilization plan | LUMA Priority Group-PREB 12/23 Motion | FEMA Status as of July 31, 2025 | Comment or forecast | Total Estimate Incurred Cost | 428Cost | 406 Cost | Total Estimated Cost
727530 | FAASt [Region 6 -Ponce Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn by FEMA | Yes | 2 | Previously Withdrawn | See comment | 5115.75 |  | 70421923.26 | 70421923.26 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727540 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn by FEMA | Yes | 2 | Previously Withdrawn | See comment | 4692.54 |  | 66510486.76 | 66510486.76 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727558 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn by FEMA | Yes | 2 | Previously Withdrawn | See comment | 3251.49 |  | 16374246.76 | 16374246.76 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727562 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn by FEMA | Yes | 2 | Previously Withdrawn | See comment | 5599.08 |  | 84411128.06 | 84411128.06 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | Yes | 2 | Pending Revised DSOW |  | 38329.46 |  | 44200121.5 | 44200121.5
727694 | FAASt [Region 4 -Caguas Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn by FEMA | Yes | 2 | Previously Withdrawn | See comment | 6393.72 |  | 76781710.48 | 76781710.48 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
740406 | FAASt [Region 1-San Juan Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025 | 14548.58 |  | 5894785.29 | 5894785.29
740408 | FAASt [Region 3-Bayamon Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025 | 4225.96 |  | 11782088.78 | 11782088.78
740409 | FAASt [Region 4-Caguas Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025 | 8084.15 |  | 23846154.02 | 23846154.02
740410 | FAASt [Region 2-Arecibo Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025 | 8296.79 |  | 5425376.76 | 5425376.76
740411 | FAASt [Region 5-Mayaguez Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025 | 5962.2 |  | 3777166.88 | 3777166.88
740414 | FAASt [Region 6-Ponce Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025 | 7563.55 |  | 13788400.37 | 13788400.37
741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | 2025-08-01 | Yes | 3 | Pending Revised DSOW | Pending Since May 2025 | 8787.49 |  | 1347191.63 | 1347191.63
741098 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn by FEMA | Yes | 3 | Previously Withdrawn | See comment | 8365.17 |  | 961518.65 | 961518.65 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741100 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn by FEMA | Yes | 3 | Previously Withdrawn | See comment | 3733.86 |  | 1428325.86 | 1428325.86 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741101 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn by FEMA | Yes | 3 | Previously Withdrawn | See comment | 6352.17 |  | 1058188.92 | 1058188.92 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741102 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn by FEMA | Yes | 3 | Previously Withdrawn | See comment | 7244.12 |  | 1516985.37 | 1516985.37 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741104 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn by FEMA | Yes | 3 | Previously Withdrawn | See comment | 4492.45 |  | 1992973.53 | 1992973.53 | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | 2025-08-01 | No | 3 | Pending DSOW | Pending Since 2023 | 3238497.73 | 15889643 | 901810364 | 917700007
748180 | FAASt Transm. Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System (Telecommunication) | Transmission | 2025-08-01 | Yes | 4 | Pending Revised DSOW | No forecast | 578474.45 |  | 52804979.05 | 52804979.05
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | BESS | 2025-08-01 | Yes | 1 | Non Eligible 406 determination | No forecast | 771738.9 |  | 55941767.5 | 55941767.5 | Project ineligible under 406 Mitigation measures- A s determined by FEMA
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | BESS | 2025-08-01 | Yes | 1 | Non Eligible 406 determination | No forecast | 917517.07 |  | 52720520.35 | 52720520.35 | Project ineligible under 406 Mitigation measures- A s determined by FEMA
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | BESS | 2025-08-01 | Yes | 1 | Non Eligible 406 determination | No forecast | 933346.51 |  | 55503065.56 | 55503065.56 | Project ineligible under 406 Mitigation measures- A s determined by FEMA
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | BESS | 2025-08-01 | Yes | 1 | Non Eligible 406 determination | No forecast | 877404.95 |  | 57640005.67 | 57640005.67 | Project ineligible under 406 Mitigation measures- A s determined by FEMA
752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | 2025-08-01 | No | 3 | Pending DSOW | No forecast | 436437.47 | 359175.24 | 4177144.45 | 4536319.69
754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending Revised DSOW | Forecast is 8/8/2025 | 830833.49 |  | 15123199.33 | 15123199.33
754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending Revised DSOW | Forecast is 8/8/2025 | 722563.3 |  | 7066632.8 | 7066632.8
666894 | FAASt [San Juan Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 9279864.9 | 35282713 | 3532039 | 38814752
671396 | FAASt [Utuado Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2599723.93 | 21135871 | 2911033 | 24046904
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1880917.99 | 10053300 | 1109633 | 11162933
678794 | FAASt [Ponce Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 3450445.62 | 18852071 | 1444528 | 20296599
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2701705.05 | 17274978 | 1527389 | 18802367
686482 | FAASt [Isabela Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1088990.74 | 8712288 | 733835 | 9446123
688623 | FAASt [Automation Program Group 1A] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Forecast is 7/31/2025 | 2577701.87 | 1005286 | 1877045 | 2882331
690480 | FAASt [Humacao Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1203691.71 | 9318022 | 922000 | 10240022
690483 | FAASt [Cayey Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2980653.6 | 15993979 | 1319139 | 17313118
690721 | FAASt [Guayama Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1577001.01 | 7045719 | 542958 | 7588677
693543 | FAASt [Juncos Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | RFI sent on 10/21/24 | 2135208.44 | 13468580 | 1643590 | 15112170
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1831642.93 | 7465021 | 481369 | 7946390
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | Pending DSOW | Forecast is 11/30/2026 | 1589931.76 | 11188812 | 1117331 | 12306143
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1271901.7 | 8618625 | 968057 | 9586682
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2857852.61 | 18680447 | 1909452 | 20589899
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2151035.48 | 16995906 | 1574362 | 18570268
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2617616.95 | 9707069 | 820333 | 10527402
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2726930.5 | 13631005 | 1104923 | 14735928
704931 | FAASt [Camuy Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 2832594.37 | 18265434 | 2269186 | 20534620
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | Pending DSOW | No forecast | 2396659.73 | 11029424 | 1044683 | 12074107
Projects Added on Resolution and Order of 2/11
764705 | FAASt [Feeder Rebuild # 6014-02] (Distribution) | Distribution | Previously Withdrawn by FEMA | No | 1 | Pending DSOW | No forecast | 2798780.93 | 13387462.29 | TBD | 13387462.29 | The project was withdrawn with the comment "Comment: Project is being administratively withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided.".
764707 | FAASt [Feeder Rebuild # 6012-02] (Distribution) | Distribution | Previously Withdrawn by FEMA | No | 1 | Pending DSOW | No forecast | 2862242.58 | 5540622.64 | TBD | 5540622.64 | The project was withdrawn with the comment "Comment: Project is being administratively withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided.".
693615 | FAASt [Rio Grande Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | Pending DSOW | Forecast not met | 960976.98 | 7956012 | 700108 | 8656120
698427 | FAASt [Maricao Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 693123.6 | 6223855 | 1028907 | 7252762
698427 | FAASt [Mayagüez TC] (Substation) | Substation |  | No | 5 | Pending DSOW | Forecast is 9/25/2025 | 2917609.09 | 3200000 | TBD | 3200000
698522 | FAASt [Vieques Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1232844.63 | 5760781 | 519326 | 6280107
704741 | FAASt [Moca Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 569073.77 | 22275170.39 | 1110824.64 | 23385995.03
704744 | FAASt [San Sebastian Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | None | Costs clarifications required | 3475795.78 | 25971963 | 3663221 | 29635184
704793 | FAASt [Yauco Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 3578073.85 | 17432028 | 1639888 | 19071916
704929 | FAASt [San Lorenzo Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 1730016.45 | 17124231 | 2284857 | 19409088
705657 | FAASt [Automation Program Group 3] (TL/Distribution) | Automation TL/ Distribution | 2025-08-01 | No | 5 | RFI not Responded | Deadline not met | 18817445.98 | 4929019 | 19657460 | 24586479
713795 | FAASt [Lares Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | Pending DSOW | Forecast is 9/30/2025 | 329165.18 | 14590612.85 | 712022.01 | 15302634.86
724599 | FAASt [Sabana Grande Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | None | Costs clarifications required | 476592.07 | 13386336.57 | 725698.37 | 14112034.94
724605 | FAASt [Guayanilla Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | None | Costs clarifications required | 549460.97 | 9591958.43 | 469904.54 | 10061862.97
724669 | FAASt [Ciales Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | Pending DSOW | No forecast | 432585.69 | 14800410.24 | 773133.74 | 15573543.98
724670 | FAASt [Patillas Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | Pending DSOW | No forecast | 316938.97 | 10290796.35 | 406586.59 | 10697382.94
724716 | FAASt [Quebradillas Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | None | Costs clarifications required | 378967.21 | 13016938.52 | 628110.03 | 13645048.55
724781 | FAASt [Penuelas Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | None | Costs clarifications required | 283235.26 | 9760940.6 | 408490.41 | 10169431.01
724828 | FAASt [Loiza Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | None | Costs clarifications required | 1446142.33 | 8349850 | 816844 | 9166694
724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) | Streetlights | 2025-08-01 | No | 5 | Pending DSOW | Forecast is 9/30/2026 | 656476.53 | 13577880 | 1686477 | 15264357
730657 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | Transmission | 2025-08-01 | No | 5 | Pending DSOW | Forecast not met | 9253031.2 | 103800000 | TBD | 103800000
740662 | FAASt [Automation Program Group 2] (TL/ Distribution) | Automation TL/ Distribution | 2025-08-01 | No | 5 | Pending Revised DSOW | Forecast is 9/30/2025 | 23189802.99 | 2600293 | 7224272 | 9824565
741678 | FAASt [Automation Program Group 4] (TL/Distribution) | Automation TL/ Distribution | 2025-08-01 | No | 5 | Pending Revised DSOW | Forecast is 9/30/2025 | 22176812.88 | 3213239.22 | 10499139.71 | 13712378.93
Projects Removed and Replaced on Resolution and Order of 2/11
177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | 2025-08-01 | No | 3 | Pending DSOW | Pending Since 2023 | 2347246.55 | 19407885 | 906873 | 20314758
334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since 2023 | 9689812.09 | 44675547 | 38483744 | 83159291
334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since 2023 | 5762106.74 | 47224922 | 45582792 | 92807714
334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since 2023 | 3857112.76 | 18783750 | 5366655 | 24150405
334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since 2023 | 2350006.68 | 18285383 | 18767542 | 37052925
436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since 2023 | 3049964.36 | 27194288 | 14494388 | 41688676
546374 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since 2023 | 2563501.36 | 21058160 | 12777559 | 33835719
546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since 2023 | 1640643.01 | 6564391 | 23252037 | 29816428
547241 | FAASt Tallaboa 5402 (Substation) | Substation | 2025-08-01 | No | 3 | Pending DSOW | No forecast | 1194229.01 | 10924436 | 5628609 | 16553045
547243 | FAASt Egozcue - 1109 (Substation) | Substation | 2025-08-01 | No | 3 | Pending DSOW | No forecast | 1875010.93 | 13896445.76 | 6952342.26 | 20848788.02
547247 | FAASt Cambalache TC Relocation (Substation) | Substation | 2025-08-01 | Yes | 1 | Pending DSOW | Forecast 7/30/2025 | 4499385.99 | 5463505.9 | 84733286.06 | 90196791.96
547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | 2025-08-01 | No | 3 | Pending DSOW | Forecast is 10/31/2025 | 2943473.75 | 6846444.9 | 54844288.98 | 61690733.88
547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | Substation | 2025-08-01 | No | 1 | Pending DSOW | Forecast is 10/31/2025 | 2584284.14 | 8874442.51 | 42895135.02 | 51769577.53
550894 | FAASt [Baldrich - 1422] (Substation) | Substation | 2025-08-01 | Yes | 3 | Pending DSOW | No forecast | 945895.54 | 973098 | 28669863 | 29642961
550986 | FAASt [Condado - 1133] (Substation) | Substation | 2025-08-01 | Yes | 3 | Pending DSOW | Pending Since March 2025 | 1063570.56 | 10649911 | 5427167 | 16077078
551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | Substation | 2025-08-01 | No | 1 | Pending DSOW | No forecast | 1173137.64 | 19213188.6 | 3299617.88 | 22512806.48
668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | Transmission | Previously Withdrawn by FEMA | No | 3 | Pending DSOW | No forecast | 73993.29 | 307465 |  | 307465 | The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided.".
730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Pending Since March 2025 | 2623408 | 14523276 | 18671456 | 33194732
730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | No forecast | 2500998.26 | 18969808 | 12719346 | 31689154
730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | No forecast | 2464564.33 | 4115433 | 2840853 | 6956286
745851 | FAASt [Automation Program Group 11] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending Revised DSOW | Forecast not met | 255436.45 | 479854 | 1052298 | 1532152
745854 | FAASt [ Automation Program Group 9] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending Revised DSOW | Forecast not met | 184886.52 | 546905 | 1164604 | 1711509
757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending RFI Response | Forecast is 8/1/2025 | 60037.43 | 2892589.5 | 15039.03 | 2907628.53
790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending Revised DSOW | Forecast not met | 121427.65 | 4662521.3 | 28582.12 | 4691103.42
805519 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) | Transmission | 2025-08-01 | No | 1 | Pending Revised DSOW | Forecast is 7/31/2025 | 197629.44 | 708408.01 | 769393.29 | 1477801.3
817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | Forecast is 7/31/2025 | 189461.99 | 5100000 |  | 5100000
958367 | FAASt [Feeder Rebuild #6603-01] (Distribution) | Distribution | 2025-08-01 | No | 1 | Pending DSOW | No forecast | 1860753.24 | 14474191.76 | 1172038.62 | 15646230.38

## PREB 2-5 Projects To Activate (hidden)
|  |  |  | Project Details-LUMA Provided |  |  |  |  | PREPA Comments
Project Number |  | Asset | Withdrawn Date | Total Estimate Incurred Cost | 428Cost | 406 Cost | Total Estimated Cost | Identified by LUMA in PREB Priority Stabilization plan | LUMA Priority Group-PREB 12/23 Motion | FEMA Status as of July 31, 2025 | Comment or forecast
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | BESS | 2025-08-01 | 771738.9 |  | 55941767.5 | 55941767.5 | Yes | 1 | Non Eligible 406 determination | No forecast | Project ineligible under 406 Mitigation measures
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | BESS | 2025-08-01 | 917517.07 |  | 52720520.35 | 52720520.35 | Yes | 1 | Non Eligible 406 determination | No forecast | Project ineligible under 406 Mitigation measures
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | BESS | 2025-08-01 | 933346.51 |  | 55503065.56 | 55503065.56 | Yes | 1 | Non Eligible 406 determination | No forecast | Project ineligible under 406 Mitigation measures
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | BESS | 2025-08-01 | 877404.95 |  | 57640005.67 | 57640005.67 | Yes | 1 | Non Eligible 406 determination | No forecast | Project ineligible under 406 Mitigation measures
334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | 2025-08-01 | 9689812.09 | 44675547 | 38483744 | 83159291 | No | 1 | Pending DSOW | Pending Since 2023
334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | 2025-08-01 | 5762106.74 | 47224922 | 45582792 | 92807714 | No | 1 | Pending DSOW | Pending Since 2023
334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | 2025-08-01 | 3857112.76 | 18783750 | 5366655 | 24150405 | No | 1 | Pending DSOW | Pending Since 2023
334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | 2025-08-01 | 2350006.68 | 18285383 | 18767542 | 37052925 | No | 1 | Pending DSOW | Pending Since 2023
436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | 2025-08-01 | 3049964.36 | 27194288 | 14494388 | 41688676 | No | 1 | Pending DSOW | Pending Since 2023
546374 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | Distribution | 2025-08-01 | 2563501.36 | 21058160 | 12777559 | 33835719 | No | 1 | Pending DSOW | Pending Since 2023
546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | 2025-08-01 | 1640643.01 | 6564391 | 23252037 | 29816428 | No | 1 | Pending DSOW | Pending Since 2023
688623 | FAASt [Automation Program Group 1A] (Distribution) | Distribution | 2025-08-01 | 2577701.87 | 1005286 | 1877045 | 2882331 | No | 1 | Pending DSOW | Forecast is 7/31/2025
730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | 2025-08-01 | 2623408 | 14523276 | 18671456 | 33194732 | No | 1 | Pending DSOW | Pending Since March 2025
730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | 2025-08-01 | 2500998.26 | 18969808 | 12719346 | 31689154 | No | 1 | Pending DSOW | No forecast
730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | 2025-08-01 | 2464564.33 | 4115433 | 2840853 | 6956286 | No | 1 | Pending DSOW | No forecast
745851 | FAASt [Automation Program Group 11] (Distribution) | Distribution | 2025-08-01 | 255436.45 | 479854 | 1052298 | 1532152 | No | 1 | Pending Revised DSOW | Forecast not met
745854 | FAASt [ Automation Program Group 9] (Distribution) | Distribution | 2025-08-01 | 184886.52 | 546905 | 1164604 | 1711509 | No | 1 | Pending Revised DSOW | Forecast not met
754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | Distribution | 2025-08-01 | 830833.49 |  | 15123199.33 | 15123199.33 | No | 1 | Pending Revised DSOW | Forecast is 8/8/2025
754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | Distribution | 2025-08-01 | 722563.3 |  | 7066632.8 | 7066632.8 | No | 1 | Pending Revised DSOW | Forecast is 8/8/2025
757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | Distribution | 2025-08-01 | 60037.43 | 2892589.5 | 15039.03 | 2907628.53 | No | 1 | Pending RFI Response | Forecast is 8/1/2025
790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | Distribution | 2025-08-01 | 121427.65 | 4662521.3 | 28582.12 | 4691103.42 | No | 1 | Pending Revised DSOW | Forecast not met
817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) | Distribution | 2025-08-01 | 189461.99 | 5100000 |  | 5100000 | No | 1 | Pending DSOW | Forecast is 7/31/2025
958367 | FAASt [Feeder Rebuild #6603-01] (Distribution) | Distribution | 2025-08-01 | 1860753.24 | 14474191.76 | 1172038.62 | 15646230.38 | No | 1 | Pending DSOW | No forecast
666894 | FAASt [San Juan Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 9279864.9 | 35282713 | 3532039 | 38814752 | No | 5 | RFI not Responded | Deadline not met
671396 | FAASt [Utuado Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2599723.93 | 21135871 | 2911033 | 24046904 | No | 5 | RFI not Responded | Deadline not met
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 1880917.99 | 10053300 | 1109633 | 11162933 | No | 5 | RFI not Responded | Deadline not met
678794 | FAASt [Ponce Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 3450445.62 | 18852071 | 1444528 | 20296599 | No | 5 | RFI not Responded | Deadline not met
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2701705.05 | 17274978 | 1527389 | 18802367 | No | 5 | RFI not Responded | Deadline not met
686482 | FAASt [Isabela Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 1088990.74 | 8712288 | 733835 | 9446123 | No | 5 | RFI not Responded | Deadline not met
690480 | FAASt [Humacao Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 1203691.71 | 9318022 | 922000 | 10240022 | No | 5 | RFI not Responded | Deadline not met
690483 | FAASt [Cayey Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2980653.6 | 15993979 | 1319139 | 17313118 | No | 5 | RFI not Responded | Deadline not met
690721 | FAASt [Guayama Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 1577001.01 | 7045719 | 542958 | 7588677 | No | 5 | RFI not Responded | Deadline not met
693543 | FAASt [Juncos Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2135208.44 | 13468580 | 1643590 | 15112170 | No | 5 | RFI not Responded | RFI sent on 10/21/24
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 1831642.93 | 7465021 | 481369 | 7946390 | No | 5 | RFI not Responded | Deadline not met
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 1589931.76 | 11188812 | 1117331 | 12306143 | No | 5 | Pending DSOW | Forecast is 11/30/2026
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 1271901.7 | 8618625 | 968057 | 9586682 | No | 5 | RFI not Responded | Deadline not met
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2857852.61 | 18680447 | 1909452 | 20589899 | No | 5 | RFI not Responded | Deadline not met
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2151035.48 | 16995906 | 1574362 | 18570268 | No | 5 | RFI not Responded | Deadline not met
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2617616.95 | 9707069 | 820333 | 10527402 | No | 5 | RFI not Responded | Deadline not met
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2726930.5 | 13631005 | 1104923 | 14735928 | No | 5 | RFI not Responded | Deadline not met
704931 | FAASt [Camuy Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2832594.37 | 18265434 | 2269186 | 20534620 | No | 5 | RFI not Responded | Deadline not met
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Streetlights | 2025-08-01 | 2396659.73 | 11029424 | 1044683 | 12074107 | No | 5 | Pending DSOW | No forecast
547241 | FAASt Tallaboa 5402 (Substation) | Substation | 2025-08-01 | 1194229.01 | 10924436 | 5628609 | 16553045 | No | 3 | Pending DSOW | No forecast
547243 | FAASt Egozcue - 1109 (Substation) | Substation | 2025-08-01 | 1875010.93 | 13896445.76 | 6952342.26 | 20848788.02 | No | 3 | Pending DSOW | No forecast
547247 | FAASt Cambalache TC Relocation (Substation) | Substation | 2025-08-01 | 4499385.99 | 5463505.9 | 84733286.06 | 90196791.96 | Yes | 1 | Pending DSOW | Forecast 7/30/2025
547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | 2025-08-01 | 2943473.75 | 6846444.9 | 54844288.98 | 61690733.88 | No | 3 | Pending DSOW | Forecast is 10/31/2025
547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | Substation | 2025-08-01 | 2584284.14 | 8874442.51 | 42895135.02 | 51769577.53 | No | 1 | Pending DSOW | Forecast is 10/31/2025
550894 | FAASt [Baldrich - 1422] (Substation) | Substation | 2025-08-01 | 945895.54 | 973098 | 28669863 | 29642961 | Yes | 3 | Pending DSOW | No forecast
550986 | FAASt [Condado - 1133] (Substation) | Substation | 2025-08-01 | 1063570.56 | 10649911 | 5427167 | 16077078 | Yes | 3 | Pending DSOW | Pending Since March 2025
551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | Substation | 2025-08-01 | 1173137.64 | 19213188.6 | 3299617.88 | 22512806.48 | No | 1 | Pending DSOW | No forecast
752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | 2025-08-01 | 436437.47 | 359175.24 | 4177144.45 | 4536319.69 | No | 3 | Pending DSOW | No forecast
177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | 2025-08-01 | 2347246.55 | 19407885 | 906873 | 20314758 | No | 3 | Pending DSOW | Pending Since 2023
668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | Transmission | Previously Withdrawn | 73993.29 | 307465 |  | 307465 | No | 3 | Pending DSOW | No forecast | The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided.".
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | 2025-08-01 | 3238497.73 | 15889643 | 901810364 | 917700007 | No | 3 | Pending DSOW | Pending Since 2023
748180 | FAASt Transm. Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System (Telecommunication) | Transmission | 2025-08-01 | 578474.45 |  | 52804979.05 | 52804979.05 | Yes | 4 | Pending Revised DSOW | No forecast
805519 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) | Transmission | 2025-08-01 | 197629.44 | 708408.01 | 769393.29 | 1477801.3 | No | 1 | Pending Revised DSOW | Forecast is 7/31/2025
741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | 2025-08-01 | 8787.49 |  | 1347191.63 | 1347191.63 | Yes | 3 | Pending Revised DSOW | Pending Since May 2025
741098 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn | 8365.17 |  | 961518.65 | 961518.65 | Yes | 3 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741100 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn | 3733.86 |  | 1428325.86 | 1428325.86 | Yes | 3 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741101 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn | 6352.17 |  | 1058188.92 | 1058188.92 | Yes | 3 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741102 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn | 7244.12 |  | 1516985.37 | 1516985.37 | Yes | 3 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
741104 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | Vegetation- Subs-Telecom | Previously Withdrawn | 4492.45 |  | 1992973.53 | 1992973.53 | Yes | 3 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727530 | FAASt [Region 6 -Ponce Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn | 5115.75 |  | 70421923.26 | 70421923.26 | Yes | 2 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727540 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn | 4692.54 |  | 66510486.76 | 66510486.76 | Yes | 2 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727558 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn | 3251.49 |  | 16374246.76 | 16374246.76 | Yes | 2 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
740408 | FAASt [Region 3-Bayamon Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | 4225.96 |  | 11782088.78 | 11782088.78 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025
727562 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn | 5599.08 |  | 84411128.06 | 84411128.06 | Yes | 2 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | 38329.46 |  | 44200121.5 | 44200121.5 | Yes | 2 | Pending Revised DSOW
727694 | FAASt [Region 4 -Caguas Group C] (Vegetation) | Vegetation-38kv trans | Previously Withdrawn | 6393.72 |  | 76781710.48 | 76781710.48 | Yes | 2 | Previously Withdrawn |  | The project was withdrawn with the comment "Project is being administratively withdrawn since the vegetation works will be capture in the individual sub-FAASt projects.". Single line Project created
740406 | FAASt [Region 1-San Juan Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | 14548.58 |  | 5894785.29 | 5894785.29 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025
740409 | FAASt [Region 4-Caguas Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | 8084.15 |  | 23846154.02 | 23846154.02 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025
740410 | FAASt [Region 2-Arecibo Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | 8296.79 |  | 5425376.76 | 5425376.76 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025
740411 | FAASt [Region 5-Mayaguez Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | 5962.2 |  | 3777166.88 | 3777166.88 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025
740414 | FAASt [Region 6-Ponce Group B] (Vegetation) | Vegetation-38kv trans | 2025-08-01 | 7563.55 |  | 13788400.37 | 13788400.37 | Yes | 2 | Pending DSOW | Forecast is 7/31/2025
|  |  |  | 119281901.01 | 636789618.48 | 2093674845.85 | 2730464464.33
|  |  |  | 272 | 19