## STATUS LIST (hidden)
DSOW – Pending Design Package for Development | DSOW – Pending Design Package for Development
DSOW – Scope and Cost Update in Progress | DSOW – Scope and Cost Update in Progress
DSOW – Scope and Cost development in progress | DSOW – Scope and Cost development in progress
DSOW – Submitted to COR3/PREPA | DSOW- Ready to Submit /Pending Reactivation
DSOW – Submitted to FEMA -Currently under FEMA evaluation
Amendment – Pending Design Package for Development
Amendment – Amendment Needed/Pending Development
Amendment – Scope and Cost development in progress
Amendment – Submitted to COR3/PREPA
Amendment – Submitted to FEMA
Obligated -No expected changes

## Summary
LUMA Consolidated List | Amount ($M)
428 Allocation (Without the A&E and E&M) | 3035704041.1365
406 Allocation (Without the A&E and E&M) | 1701407212.3368
428 A&E-PW 9510 | 349129466.0157
406 A&E-PW 9510 | 90824442.8178
428 E&M-PW 10710 | 293981332.0697
406 E&M-PW 10710 | 200575645.3054
Expected Total Project Cost | 5662215825.4988
Total 428 Expected cost | 3678814839.2219
Total 406 Expected Cost | 1992807300.4599
Attachment A | Amount ($M)
428 Allocation (Without the A&E and E&M) | 595423815.646
406 Allocation (Without the A&E and E&M) | 317047219.3924
428 A&E-PW 9510 | 101270058.7045
406 A&E-PW 9510 | 29159565.4211
428 E&M-PW 10710 | 56366956.4058
406 E&M-PW 10710 | 170203524.1003
Expected Total Project Cost | 1269471139.6701
Total 428 Expected Cost | 753060830.7563
Total 406 Expected Cost | 516410308.9138
Summary Expected Project Costs Allocation

## LUMA Consolidated List
Expected Project Costs Allocation
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Process Step | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected cost | Total 406 Expected Cost | Project Reconciliation Status | Expected Reconciliation date | Comments
701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 211260.32 | 1161.51 | 23475.13 | 868.52 | 24568.7 | 7563.4 | 268897.58 | 259304.15 | 9593.43 | Amendment – Submitted to COR3/PREPA | Submitted | Amendment submitted Feb 12, 2026
334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 13767291.01 | 5248.03 | 1304890.11 | 3414.73 | 1450714.05 | 34575.55 | 16566133.48 | 16522895.17 | 43238.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
169896 | FAASt - Costa Sur SP TC  Equipment Repair and | Substation | Substation Rebuilds | Yes | Obligated | 28250123.84 | 498874.07 | 3402149.85 | 53563.53 | 0 | 0 | 32204711.29 | 31652273.69 | 552437.6 | Amendment – Submitted to COR3/PREPA | Submitted
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 1538953.94 | 1267232.34 | 603858.08 | 681493.25 | 16046.1 | 488163.85 | 4595747.56 | 2158858.12 | 2436889.44 | Amendment – Submitted to COR3/PREPA | Submitted | Only existing substation is obligated
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 1479929.82 | 1291181.43 | 731583.82 | 878415.74 | 16046.1 | 505613.85 | 4902770.76 | 2227559.74 | 2675211.02 | Amendment – Submitted to COR3/PREPA | Submitted | Only existing substation is obligated
179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 1564453.0618 | 238313.587 | 159091.5333 | 54214.3022 | 192536.3467 | 357851.909 | 2566460.74 | 1916080.9418 | 650379.7982 | Amendment – Submitted to COR3/PREPA | Submitted
743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation | Yes | Obligated | 3917912.12 | 0 | 463572.76 | 0 | 1196146.39 | 0 | 5577631.27 | 5577631.27 | 0 | Amendment – Submitted to COR3/PREPA | Submitted | Scope does not include hazard mitigation. No reconciliation needed. Project is in execution; Amendment due to scope/cost changes submitted.
729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation | Yes | Obligated | 7320658.38 | 0 | 866190.39 | 0 | 2235011.61 | 0 | 10421860.38 | 10421860.38 | 0 | Amendment – Submitted to COR3/PREPA | Submitted | Scope does not include hazard mitigation. No reconciliation needed. Project is in execution; Amendment due to scope/cost changes submitted.
178503 | FAASt Aguirre TC - BKRS (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 38926711.43 | 257069.07 | 4062989.94 | 24113.89 | 0 | 0 | 43270884.33 | 42989701.37 | 281182.96 | Amendment – Submitted to COR3/PREPA | Submitted
551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 7266305.24 | 1694442.12 | 1060764.2767 | 273088.36 | 264479.04 | 191012.64 | 10750091.6767 | 8591548.5567 | 2158543.12 | Amendment – Submitted to COR3/PREPA | Submitted | 428/206 split revised, 1 additional site was included in the submitted amendment.
657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Telecom) | Telecommunication | IT/OT | Yes | Obligated | 36457328.36 | 28655579.63 | 2477105.02 | 1951041.22 | 443546.56 | 414080 | 70398680.79 | 39377979.94 | 31020700.85 | Amendment – Submitted to COR3/PREPA | Submitted | Amendment submitted Feb 12, 2026
668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 665239.4 | 2703.16 | 58708.55 | 918.24 | 51007.18 | 8541.82 | 787118.35 | 774955.13 | 12163.22 | Amendment – Submitted to COR3/PREPA | Submitted
334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1528829.9 | 33717.27 | 129281.25 | 2827.08 | 9793.65 | 0 | 1704449.15 | 1667904.8 | 36544.35 | Amendment – Submitted to COR3/PREPA | Submitted
668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 359543.38 | 5405.05 | 34734.97 | 698.02 | 39893.71 | 2641.29 | 442916.42 | 434172.06 | 8744.36 | Amendment – Submitted to COR3/PREPA | Submitted
551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Security | Yes | Obligated | 3696956.6 | 303177.29 | 844836.71 | 133205.94 | 0 | 0 | 4978176.54 | 4541793.31 | 436383.23 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation
550910 | FAASt Physical Security - Group 1 (Substatio | Substation | Substation Security | Yes | Obligated | 6025270.22 | 463212.07 | 1278327.96 | 202746.89 | 0 | 0 | 7969557.14 | 7303598.18 | 665958.96 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation
542758 | FAASt Substation Minor Repairs -Group B (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2973035 | 302946 | 723315 | 136595 | 0 | 0 | 4135891 | 3696350 | 439541 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation
167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 18657617.56 | 10503244.02 | 1398471.71 | 1349494.84 | 2069637.1 | 5306300.43 | 39284765.66 | 22125726.37 | 17159039.29 | Amendment – Scope and Cost development in progress | Submitted
550950 | FAASt - EPC - [Monacillo TC] (Substations) | Priority Substation | Substation | Yes | Obligated | 93729896.23 | 13188476.41 | 18252835.9 | 1706525.37 | 28961853.03 | 3326240.35 | 159165827.29 | 140944585.16 | 18221242.13 | Amendment – Submitted to FEMA | Submitted
723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 63916173.58 | 8155710.69 | 5214828.56 | 730706.2 | 24860010.19 | 6746067.42 | 109623496.64 | 93991012.33 | 15632484.31 | Amendment – Pending Design Package for Development | Q4 FY2026
180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 189214147.25 | 38650198.93 | 18683215.39 | 6899520.54 | 21880052.02 | 41872865.87 | 317200000 | 229777414.66 | 87422585.34 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Currently undergoing redesign with updated scope
334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 35438292.75 | 7238872.38 | 3499216.45 | 1292224.88 | 4097958.32 | 7842452.06 | 59409016.84 | 43035467.52 | 16373549.32 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Obligated for $47.1M, the expected total project cost is $54M
176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 29688455.53 | 656415.25 | 4164273.96 | 93674.84 | 96089.14 | 15401.72 | 34714310.44 | 33948818.63 | 765491.81 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Obligated for $33.5M. The expected total project cost is $40.8M
176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 18028195.83 | 3833616.78 | 1664551.02 | 342899.38 | 118276.26 | 2127.1 | 23989666.37 | 19811023.11 | 4178643.26 | Amendment – Scope and Cost development in progress | Q4 FY2026
165268 | FAASt Rio Grande Estate Substation CH-2306 (Su | Substation | Substation Rebuilds | Yes | Obligated | 10575737.82 | 5646415.07 | 1670755.76 | 1105969.75 | 15043028.3 | 11317055.94 | 45358962.64 | 27289521.88 | 18069440.76 | Amendment – Submitted to COR3/PREPA | Q4 FY2026 | Submit to COR3 on 02/27/2026
542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4984296 | 531658.24 | 332286.4 | 132914.56 | 332286.4 | 332286.4 | 6645728 | 5648868.8 | 996859.2 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 41692705.96 | 18968379.24 | 4167397.2 | 2030397.52 | 19295213.53 | 10753215.44 | 96907308.89 | 65155316.69 | 31751992.2 | Amendment – Scope and Cost development in progress | Q4 FY2026
682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 76051918.2725 | 3432327.8875 | 7365108.11 | 326910.77 | 33047353.6975 | 1412947.2125 | 121636565.95 | 116464380.08 | 5172185.87 | Amendment – Scope and Cost development in progress | Q4 FY2026 | scope to be revised
682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Priority Substation | Substation | Yes | Obligated | 36917509.58 | 0 | 6435349.91 | 0 | 35509832.36 | 0 | 78862691.85 | 78862691.85 | 0 | Amendment – Scope and Cost development in progress | Q4 FY2026
757687 | FAASt [Automation Program Group 22] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1488484.9 | 1318276.22 | 169367.15 | 153103.22 | 44894.57 | 52753.12 | 3226879.18 | 1702746.62 | 1524132.56 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406HM Revision to be submitted May 2026/ Estimated date Cfci strategy to be defined
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1427638.4262 | 995016.61 | 137043.707 | 78366.543 | 175789.83 | 397237.57 | 3211092.6862 | 1740471.9632 | 1470620.723 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
745861 | FAASt [Automation Program Group 12] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2181157.9 | 1341922.17 | 200395.78 | 97562.89 | 228547.36 | 557560.64 | 4607146.74 | 2610101.04 | 1997045.7 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
745856 | FAASt [Automation Program Group 14] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1410445.2 | 1001406.99 | 112272.97 | 65062.72 | 148295.58 | 442571.92 | 3180055.38 | 1671013.75 | 1509041.63 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7579644.48 | 2302.03 | 706904.78 | 1475.8 | 768737.4 | 15126.8 | 9074191.29 | 9055286.66 | 18904.63 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 6828692.0723 | 1040216.6366 | 694419.7424 | 236640.3857 | 840403.2415 | 1561990.2915 | 11202362.37 | 8363515.0562 | 2838847.3138 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | estimate under review
755211 | FAASt [Automation Program Group 15] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 276277.7686 | 249580.66 | 29684.97 | 18557.49 | 53139.71 | 103164.29 | 730404.8886 | 359102.4486 | 371302.44 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 469650.95 | 75853 | 90260 | 20101.05 | 0 | 0 | 655865 | 559910.95 | 95954.05 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 186321 | 40981 | 36670 | 10860 | 0 | 0 | 240482.16 | 222991 | 51841 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 8687329.99 | 35434.35 | 773151.6 | 23427.4 | 622940.21 | 246677.69 | 10388961.24 | 10083421.8 | 305539.44 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5461200.05 | 170555 | 491327 | 35032.38 | 0 | 0 | 6158114.43 | 5952527.05 | 205587.38 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3882564.66 | 6767.3 | 361458.25 | 1409.37 | 388789.38 | 9887.36 | 4650876.32 | 4632812.29 | 18064.03 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 254972.22 | 50008 | 49774 | 13252 | 0 | 0 | 368006.22 | 304746.22 | 63260 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 872891 | 188303 | 171585 | 49900.3 | 0 | 0 | 1282679 | 1044476 | 238203.3 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 621804 | 135633 | 121044 | 35951 | 0 | 0 | 914462 | 742848 | 171584 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 10940320.91 | 328412 | 891094 | 67251.43 | 0 | 0 | 12227078.34 | 11831414.91 | 395663.43 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 510067.96 | 80878 | 98276 | 21432.67 | 0 | 0 | 710654.63 | 608343.96 | 102310.67 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1764568.92 | 307856 | 343118 | 81581.84 | 0 | 0 | 2497124.76 | 2107686.92 | 389437.84 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 68823 | 11847 | 13127 | 3139 | 0 | 0 | 96936 | 81950 | 14986 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation | Yes | Obligated | 9014992.3462 | 1373256.3891 | 916747.8334 | 312404.0802 | 1109469.9702 | 2062083.1008 | 14788953.72 | 11041210.1499 | 3747743.5701 | DSOW – Scope and Cost development in progress | Q1 FY2027
169266 | FAASt Centro Medico 1327/1359 (Substattion) Rebuilt | Substation | Substation Rebuilds | Yes | Obligated | 12202124 | 7130202 | 3317753 | 1306032 | 2593199.4 | 2593199.4 | 29142509.8 | 18113076.4 | 11029433.4 | Amendment – Amendment Needed/Pending Development | Q4 FY2026
674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5641956.19 | 3297.53 | 528429.47 | 2122.11 | 560196.28 | 21609.72 | 6757611.3 | 6730581.94 | 27029.36 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
546370 | FAASt - Substation Minor Repairs Group A (Subs | Substation | Substation Rebuilds | Yes | Obligated | 4482972.51 | 333712.07 | 996359.11 | 154490.51 | 0 | 0 | 5967534.2 | 5479331.62 | 488202.58 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation
549764 | FAASt Physical Security - Group 2 (Substation) | Substation | Substation Security | Yes | Obligated | 2159012.31 | 150511.17 | 529771.49 | 74169.51 | 0 | 0 | 2913464.48 | 2688783.8 | 224680.68 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation
546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2648259.06 | 262056.28 | 646473.16 | 122575.86 | 0 | 0 | 3679364.36 | 3294732.22 | 384632.14 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation
738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 11041271 | 234531 | 1159111 | 175368.81 | 0 | 0 | 12610281.81 | 12200382 | 409899.81 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1408531 | 283336 | 273831 | 75084 | 0 | 0 | 2040782 | 1682362 | 358420 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 211622.76 | 26654 | 41364 | 7063.31 | 0 | 0 | 286704.07 | 252986.76 | 33717.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 64425.44 | 12827 | 12535 | 3399.16 | 0 | 0 | 93186.6 | 76960.44 | 16226.16 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 243073 | 43919 | 46884 | 11639 | 0 | 0 | 345515 | 289957 | 55558 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 483786 | 84198 | 93451 | 22312 | 0 | 0 | 683747 | 577237 | 106510 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 85921.77 | 13827 | 16717 | 3664 | 0 | 0 | 120129.77 | 102638.77 | 17491 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 70683 | 16718 | 13377 | 4430 | 0 | 0 | 105208 | 84060 | 21148 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 438209.69 | 68128 | 83451 | 18053.92 | 0 | 0 | 607842.61 | 521660.69 | 86181.92 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 353628 | 42939 | 66915 | 11378.84 | 0 | 0 | 474860.84 | 420543 | 54317.84 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 59545.08 | 13827 | 11879 | 3664 | 0 | 0 | 88915.08 | 71424.08 | 17491 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5629060 | 1482809 | 503551 | 35903.97 | 0 | 0 | 6311323.97 | 6132611 | 1518712.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 250906 | 54308 | 49227 | 14392 | 0 | 0 | 395615 | 300133 | 68700 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 355178 | 46090 | 67123 | 12214 | 0 | 0 | 464097.87 | 422301 | 58304 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 43374 | 8718 | 8414 | 2310 | 0 | 0 | 62816 | 51788 | 11028 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 20584 | 3949 | 4059 | 1046 | 0 | 0 | 29638 | 24643 | 4995 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1033375.81 | 68618 | 83943 | 15418.96 | 0 | 0 | 1201354.77 | 1117318.81 | 84036.96 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 8070964.96 | 925633.77 | 1873982 | 414167.51 | 0 | 0 | 11284748.24 | 9944946.96 | 1339801.28 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 1155804 | 91406 | 476439 | 62197 | 0 | 0 | 1785846 | 1632243 | 153603 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
660239 | FAASt Streetlighting - Villalba (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10190536.0518 | 497349.58 | 2630718.608 | 84516.08 | 0 | 0 | 13503120.3189 | 12821254.6598 | 581865.66 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 13884126 | 310288 | 1643630 | 66835.67 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 17238816.15 | 68279.82 | 1579773.97 | 43968.92 | 1309700 | 447970.2 | 20688509.06 | 20128290.12 | 560218.94 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7714746.94 | 2136.3 | 719754.49 | 1369.92 | 787627.58 | 14046.32 | 9239681.55 | 9222129.01 | 17552.54 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 243833.22 | 919.39 | 21435.45 | 574.91 | 14432.64 | 6007.36 | 287202.97 | 279701.31 | 7501.66 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 904194 | 179969 | 175796 | 47692 | 0 | 0 | 1307651 | 1079990 | 227661 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 190570 | 39481 | 37242 | 10468 | 0 | 0 | 277755 | 227812 | 49949 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2046324.94 | 9000.11 | 182160.96 | 5677.18 | 145915.26 | 59322.74 | 2448401.19 | 2374401.16 | 74000.03 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 6704421.69 | 196450 | 602047 | 42926.93 | 0 | 0 | 7545845.62 | 7306468.69 | 239376.93 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7096249.5 | 165571 | 614123 | 29565.32 | 0 | 0 | 7905508.82 | 7710372.5 | 195136.32 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 208400 | 45590 | 40930 | 12081.35 | 0 | 0 | 357577 | 249330 | 57671.35 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 635326.93 | 85929 | 120284 | 22771.19 | 0 | 0 | 813282.28 | 755610.93 | 108700.19 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 517156 | 83531 | 99229 | 22135.72 | 0 | 0 | 714869 | 616385 | 105666.72 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
542690 | FAASt Maunabo Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7730315.5622 | 179642 | 1530438.4909 | 64238 | 0 | 0 | 9504634.3826 | 9260754.0531 | 243880 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Amendment pending to remove underground scope Grants portal total project cost is $7.9M
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 493168.61 | 1670722.97 | 4283.23 | 14502.82 | 0 | 0 | 2182677.63 | 497451.84 | 1685225.79 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $17,938,929.50, however only 10.54/30.97 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution.
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 952531.08 | 3226919.92 | 8275.53 | 28020.6 | 0 | 0 | 4215747.13 | 960806.61 | 3254940.52 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $21,304,288.88, however only 11.48/36.78 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution.
334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2083897.82 | 821.8 | 197576.9 | 535.27 | 213549.07 | 5402.43 | 2501783.29 | 2495023.79 | 6759.5 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
825843 | FAASt [Guanica TC] (Substation) | Priority Substation | Substation | Yes | Obligated | 2320373.96 | 0 | 826981.13 | 0 | 4200723.52 | 0 | 7348078.61 | 7348078.61 | 0 | Amendment – Amendment Needed/Pending Development | Q4 FY2026
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Substation | Yes | Obligated | 1031094.1802 | 157066.8744 | 104853.484 | 35731.3702 | 126896.1731 | 235851.7681 | 1691493.85 | 1262843.8373 | 428650.0127 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | scope and estimate to be revised
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Substation | Yes | Obligated | 3600960.6953 | 548535.3833 | 366186.9904 | 124787.1069 | 443168.1805 | 823681.2536 | 5907319.61 | 4410315.8663 | 1497003.7437 | Obligated -No expected changes | N/A
682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation | Yes | Obligated | 58589915.3537 | 8925018.7361 | 5958094.6826 | 2030365.4081 | 7210627.4912 | 13401816.6283 | 96115838.3 | 71758637.5275 | 24357200.7725 | Amendment – Pending Design Package for Development | FY2027 | The Amount Obligated by FEMA was $8.2M
682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 1770998.9781 | 269776.7861 | 180095.4914 | 61371.9109 | 217955.8349 | 405097.0787 | 2905296.08 | 2169050.3043 | 736245.7757 | Amendment – Submitted to COR3/PREPA | Submitted
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Building | Building | No | Pending PDMG Scope & Cost Routing | 78491693.5616 | 36937267.5584 | 10703412.7584 | 5036900.1216 | 0 | 0 | 131169274 | 89195106.32 | 41974167.68 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project under NEPA review process. An amendment will be developed after obligation to add 406 split.
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 71272552.67 | 5820746.94 | 4233792.76 | 345260.6 | 28635.6 | 0 | 81700988.57 | 75534981.03 | 6166007.54 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Project contains multiple segments and distribution scope. The estimates are still under review and the current estimates are over $120M all together.
701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 19848.36 | 4609 | 3959.6 | 1221.39 | 0 | 0 | 29638.35 | 23807.96 | 5830.39 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 223935.37 | 198410.11 | 21856.33 | 15504.92 | 33515.73 | 77702.27 | 570924.73 | 279307.43 | 291617.3 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 85296.74 | 2000 | 14756 | 478.06 | 0 | 0 | 102530.8 | 100052.74 | 2478.06 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 20468 | 4609 | 10153 | 1221 | 0 | 0 | 36451 | 30621 | 5830 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 21408.25 | 4609 | 4169 | 1221 | 0 | 0 | 31407.25 | 25577.25 | 5830 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4099047 | 437231.68 | 273269.8 | 109307.92 | 273269.8 | 273269.8 | 5465396 | 4645586.6 | 819809.4 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | Yes | Obligated | 36790729.34 | 2900981.23 | 3092708.78 | 618690.18 | 1982784.48 | 4857192.36 | 50243086.37 | 41866222.6 | 8376863.77 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Pending obligation, latest estimate is $54.5M
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 1290814.82 | 3837707.16 | 107228.43 | 294225.77 | 0 | 0 | 5529976.18 | 1398043.25 | 4131932.93 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $13,419,649.03, however based on conversations with FEMA, only 9.21/22.35 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1624663.76 | 4830269.73 | 134961.38 | 370322.63 | 0 | 0 | 6960217.5 | 1759625.14 | 5200592.36 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 24080 | 71591.83 | 2000.35 | 5488.7 | 0 | 0 | 103160.88 | 26080.35 | 77080.53 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | Distribution | Feeders | Yes | Obligated | 5339236.4 | 338774.39 | 1228581.96 | 98180.39 | 490913.44 | 127633.81 | 7623320.39 | 7058731.8 | 564588.59 | Amendment – Submitted to COR3/PREPA | Q4 FY2026
705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1464496 | 299196 | 284698 | 79287 | 0 | 0 | 2127677 | 1749194 | 378483 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 642721 | 98919 | 125147 | 26214 | 0 | 0 | 893001 | 767868 | 125133 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 448719.06 | 90680 | 87444 | 24030.2 | 0 | 0 | 541993.45 | 536163.06 | 114710.2 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1201420 | 177653 | 231255 | 47078 | 0 | 0 | 1657406 | 1432675 | 224731 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 516951 | 85571 | 94044 | 22676 | 0 | 0 | 719242 | 610995 | 108247 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 911136.76 | 163360 | 175441 | 43290.4 | 0 | 0 | 1293228.16 | 1086577.76 | 206650.4 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 577000.79 | 92316 | 109859 | 24463.74 | 0 | 0 | 823042.1 | 686859.79 | 116779.74 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 60838.48 | 12667 | 12053 | 3356.76 | 0 | 0 | 88915.24 | 72891.48 | 16023.76 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 273996 | 23695 | 49755 | 6279 | 0 | 0 | 353725 | 323751 | 29974 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 208544.25 | 42487 | 40949 | 11259.06 | 0 | 0 | 303239.31 | 249493.25 | 53746.06 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5425810.57 | 132877 | 434785 | 33026 | 0 | 0 | 6026498.87 | 5860595.57 | 165903 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 164908.86 | 11847 | 29922 | 3139.46 | 0 | 0 | 209816.86 | 194830.86 | 14986.46 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 42728.41 | 7898 | 8327 | 2092.97 | 0 | 0 | 61046.38 | 51055.41 | 9990.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 106941.99 | 22045 | 20834 | 5841.93 | 0 | 0 | 155662.92 | 127775.99 | 27886.93 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 198050.74 | 33041 | 38248 | 8755.87 | 0 | 0 | 278095.61 | 236298.74 | 41796.87 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 710014.69 | 151206 | 139358 | 40069.59 | 0 | 0 | 1040648.28 | 849372.69 | 191275.59 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 487190 | 102007 | 95198 | 27032 | 0 | 0 | 711427 | 582388 | 129039 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 547010 | 80962 | 104535 | 21455 | 0 | 0 | 753962 | 651545 | 102417 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 523404 | 85891 | 101359 | 22761 | 0 | 0 | 639749 | 624763 | 108652 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 775779 | 139828 | 150784 | 37054.42 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 30099566.86 | 127486673.75 | 279159.4 | 1171019.3 | 0 | 0 | 159036419.31 | 30378726.26 | 128657693.05 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $159,036,419.31, however based on conversations with FEMA, only 38.21/402.54 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 431381.68 | 83591 | 83822 | 22151.62 | 0 | 0 | 526864.68 | 515203.68 | 105742.62 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution | Feeders | Yes | Obligated | 2102127.04 | 7555.38 | 513368.91 | 6761.68 | 78644.98 | 21278.54 | 2729736.53 | 2694140.93 | 35595.6 | Amendment – Submitted to COR3/PREPA | Q4 FY2026
812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Distribution | Feeders | Yes | Obligated | 9913132.84 | 597420.75 | 1301050.25 | 86144.8 | 547637.41 | 95316.25 | 12540702.3 | 11761820.5 | 778881.8 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | IEM is working on versioning, to be submitted to FEMA on Mar 2026
801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | Distribution | Feeders | Yes | Obligated | 18342600.15 | 1465349.66 | 1564501.94 | 153975.57 | 1578988.43 | 497075.32 | 23602491.07 | 21486090.52 | 2116400.55 | Amendment – Pending Design Package for Development | Q1 FY2027 | IFA versioning in-progress. Survey aligment of 477 structures, 7.2 miles on rural area. Next step is IFC development and submission to FEMA on Jul 2026
165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Vieques and Culebra Projects (6) | No | Pending PDMG Scope & Cost Routing | 53571610.15 | 8023162.98 | 6288308.87 | 1016034.08 | 3512487.97 | 1200342.27 | 73611946.32 | 63372406.99 | 10239539.33 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | DSOW was sent 2/16/2026
704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 486385 | 72920 | 92511 | 19324 | 0 | 0 | 671140 | 578896 | 92244 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 338491 | 76424 | 66168 | 20252 | 0 | 0 | 501335 | 404659 | 96676 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 129744 | 21694 | 25191 | 5749 | 0 | 0 | 182378 | 154935 | 27443 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 163846.51 | 40583 | 31068 | 10754.5 | 0 | 0 | 352067.51 | 194914.51 | 51337.5 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 537688 | 106478 | 103281 | 28217 | 0 | 0 | 775664 | 640969 | 134695 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 443331 | 77853 | 86719 | 20631 | 0 | 0 | 628534 | 530050 | 98484 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13648195 | 1608383.29 | 2640715 | 617490.33 | 0 | 0 | 18534652 | 16288910 | 2225873.62 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9762754.59 | 605024.35 | 1979750 | 248032.07 | 0 | 0 | 12595561.01 | 11742504.59 | 853056.42 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13807923.4 | 1285354.42 | 2760454 | 522246.69 | 0 | 0 | 18375978.51 | 16568377.4 | 1807601.11 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7277670.2 | 931433.8 | 1704126 | 419107.52 | 0 | 0 | 10332337.52 | 8981796.2 | 1350541.32 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13486398.85 | 1257031.57 | 2499521 | 487450.7 | 0 | 0 | 17730402.12 | 15985919.85 | 1744482.27 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7240724 | 1182070.57 | 1925642 | 487666.4 | 0 | 0 | 10872694 | 9166366 | 1669736.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11644048.42 | 1501948.72 | 2348210 | 613589.66 | 0 | 0 | 16107796.8 | 13992258.42 | 2115538.38 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12097203.53 | 1141690.52 | 2463886 | 469330.38 | 0 | 0 | 16172110.43 | 14561089.53 | 1611020.9 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9529190.37 | 444807.71 | 1814022 | 175326.98 | 0 | 0 | 11963347.06 | 11343212.37 | 620134.69 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
690545 | FAASt Aguadilla Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 19796809 | 962442 | 3021242 | 333333 | 0 | 0 | 24113826 | 22818051 | 1295775 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Amendment pending to remove underground scope
704679 | FAASt Coamo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14311922.45 | 1481726 | 2687464 | 579175.35 | 0 | 0 | 19060287.8 | 16999386.45 | 2060901.35 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12199399 | 763112 | 2277871 | 246446 | 0 | 0 | 14825251 | 14477270 | 1009558 | Amendment – Amendment Needed/Pending Development | FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $29.7M
724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10742462 | 1338877 | 2199844 | 552275 | 0 | 0 | 14833458 | 12942306 | 1891152 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12087876.17 | 1294052.66 | 2420466 | 526309.26 | 0 | 0 | 16328704.09 | 14508342.17 | 1820361.92 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5314332 | 489465.16 | 1504203 | 250928.85 | 0 | 0 | 7558929.01 | 6818535 | 740394.01 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9430329.22 | 1104151.73 | 2048083 | 472894.36 | 0 | 0 | 13055458.31 | 11478412.22 | 1577046.09 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5152111.14 | 472131.79 | 1481546.84 | 244786.81 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12812478.84 | 1311297.11 | 2516456 | 526932.49 | 0 | 0 | 17167164.44 | 15328934.84 | 1838229.6 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 6538769.44 | 862125.75 | 1640383 | 0 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 20710527 | 1176376 | 3212958 | 0 | 0 | 0 | 25099861 | 23923485 | 1176376 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 71310194 | 1422693 | 8324691 | 426651.06 | 0 | 0 | 81478724 | 79634885 | 1849344.06 | Amendment – Amendment Needed/Pending Development | Q1 FY2028 | Amendment pending to remove underground scope Grants portal total project cost is $84.1M
678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14865613.02 | 1158946.56 | 2559493 | 0 | 0 | 0 | 18584052.58 | 17425106.02 | 1158946.56 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673504 | FAASt [Distribution Streetlighting - Gurabo] | Distribution | Distribution Streetlighting | Yes | Obligated | 19208993.6756 | 1132656 | 3043675.3411 | 400644 | 0 | 0 | 23785969.008 | 22252669.0167 | 1533300 | Amendment – Amendment Needed/Pending Development | Q2 FY2028 | Amendment pending to remove underground scope
671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14931289.0239 | 1987567.5115 | 2927309.7471 | 0 | 0 | 0 | 19846166.2825 | 17858598.771 | 1987567.5115 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
659968 | FAASt [San Germán Streetlighting] (Distributio | Distribution | Distribution Streetlighting | Yes | Obligated | 30849348.4835 | 3004065 | 4619206.9342 | 1029513 | 0 | 0 | 39502133.2497 | 35468555.4178 | 4033578 | Amendment – Amendment Needed/Pending Development | Q1 FY2028 | Amendment pending to remove underground scope
678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11019180.1 | 1352204.36 | 2291581 | 0 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12445015 | 1331811.11 | 2459743 | 537278.89 | 0 | 0 | 16773847 | 14904758 | 1869090 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
542688 | FAASt Aguada Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 21869280.099 | 807222.0429 | 4104785.7618 | 0 | 0 | 0 | 26781287.9037 | 25974065.8608 | 807222.0429 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $4.1M
659715 | FAASt Distribution Streetlighting - Aibonito | Distribution | Distribution Streetlighting | Yes | Obligated | 7074498.4202 | 129540 | 1880872.5823 | 49247 | 0 | 0 | 9134157.9756 | 8955371.0025 | 178787 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
659623 | FAASt Distribution Streetlighting - Cataño ( | Distribution | Distribution Streetlighting | Yes | Obligated | 16996757.9573 | 516042 | 3574762.8595 | 49247 | 0 | 0 | 21136810.1562 | 20571520.8168 | 565289 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
659625 | FAASt Distribution Streetlighting - Dorado | Distribution | Distribution Streetlighting | Yes | Obligated | 22864971.8931 | 1149672 | 4716594.2453 | 355973 | 0 | 0 | 29087211.5954 | 27581566.1384 | 1505645 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
660227 | FAASt Hatillo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 18570095.2497 | 1316105.06 | 4317860.4264 | 448282.64 | 0 | 0 | 24652343.3772 | 22887955.6761 | 1764387.7 | Amendment – Amendment Needed/Pending Development | Q3 FY2027 | Amendment pending to remove underground scope
542687 | FAASt Lajas Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12791189.8219 | 426332.4825 | 2512853.7311 | 0 | 0 | 0 | 15730376.0356 | 15304043.553 | 426332.4825 | Amendment – Amendment Needed/Pending Development | Q3 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2.5
542517 | FAASt -Luquillo Distribution Streetlighting | Distribution | Distribution Streetlighting | Yes | Obligated | 10632900.5227 | 181658.0813 | 2004233.2331 | 0 | 0 | 0 | 12818791.8371 | 12637133.7558 | 181658.0813 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2M
660437 | FAASt Manati Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 27067865.4688 | 1188605 | 5821635.5034 | 380359 | 0 | 0 | 34458464.7468 | 32889500.9722 | 1568964 | Amendment – Amendment Needed/Pending Development | Q4 FY2027 | Amendment pending to remove underground scope
698439 | FAASt Streetlight - Las Marías (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7073217 | 1287705 | 1653390 | 0 | 0 | 0 | 10014312 | 8726607 | 1287705 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698424 | FAASt Streetlight Florida Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 9311841.53 | 720017 | 1705096 | 277173 | 0 | 0 | 12014127.53 | 11016937.53 | 997190 | Amendment – Amendment Needed/Pending Development | FY2027 | Amendment pending to remove underground scope
542756 | FAASt Streetlighting - Guánica (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 11924623.8365 | 370808.2187 | 2237386.3309 | 0 | 0 | 0 | 14532818.386 | 14162010.1673 | 370808.2187 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2.237M
714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10915553.24 | 588048.55 | 1928249.61 | 106422.03 | 753614 | 0 | 14809005.76 | 13597416.85 | 694470.58 | DSOW – Submitted to FEMA | Q4 FY2027 | Pending Homeland Security for final signature and start construction Grants portal total project cost is $14.2M
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 560135.46 | 1665332.49 | 46530.65 | 127676.16 | 0 | 0 | 2399674.76 | 606666.11 | 1793008.65 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $7,736,264.86, however based on conversations with FEMA, only 4.02/12.96 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 79935.82 | 237656.27 | 6640.3 | 18220.4 | 0 | 0 | 342452.79 | 86576.12 | 255876.67 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $1,260,848.93, however based on conversations with FEMA, only 0.66/2.43 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Vegetation | Vegetation-DT | No | Pending QA Review | 1968823.15 | 5853486.17 | 163550.83 | 448769.62 | 0 | 0 | 8434629.77 | 2132373.98 | 6302255.79 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending Insurance Completion | 2959532.24 | 8798952.37 | 245849.34 | 674589.93 | 0 | 0 | 12678923.88 | 3205381.58 | 9473542.3 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1800712.05 | 5353676.97 | 149585.76 | 410450.73 | 0 | 0 | 7714425.51 | 1950297.81 | 5764127.7 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1977622.66 | 5879647.9 | 164281.79 | 450775.37 | 0 | 0 | 8472327.72 | 2141904.45 | 6330423.27 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 1837079.03 | 5461799.24 | 152606.78 | 418740.16 | 0 | 0 | 7870225.21 | 1989685.81 | 5880539.4 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $22,582,890.08, however based on conversations with FEMA, only 13.86/39.77 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Large Project Review | 1174137.29 | 4014718.94 | 10939.54 | 37040.89 | 0 | 0 | 5236836.66 | 1185076.83 | 4051759.83 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $27,603,651.36, however based on conversations with FEMA, only 14.13/74.48 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 1109346.43 | 3793180 | 10335.88 | 34996.91 | 0 | 0 | 4947859.22 | 1119682.31 | 3828176.91 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $ $19,687,816.76, however based on conversations with FEMA, only 13.37/53.2 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 906918.96 | 3101021.26 | 8449.84 | 28610.86 | 0 | 0 | 4045000.92 | 915368.8 | 3129632.12 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $19,606,400.98 however based on conversations with FEMA, only 10.92/52.93 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 1047946.55 | 3583235.86 | 9763.81 | 33059.91 | 0 | 0 | 4674006.13 | 1057710.36 | 3616295.77 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $32,248,051.77, however based on conversations with FEMA, only 12.63/87.14 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 672079.74 | 2298037.25 | 6261.82 | 21202.32 | 0 | 0 | 2997581.13 | 678341.56 | 2319239.57 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $23,077,673.93, however based on conversations with FEMA, only 8.1/62.36 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 1894465.49 | 6477731.82 | 17650.9 | 59765.31 | 0 | 0 | 8449613.52 | 1912116.39 | 6537497.13 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $57,838,512.87, however based on conversations with FEMA, only 22.79/156 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1849955.27 | 5500081.4 | 153676.43 | 421675.11 | 0 | 0 | 7925388.21 | 2003631.7 | 5921756.51 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 2787055.9 | 8286164.87 | 231521.7 | 635275.99 | 0 | 0 | 11940018.46 | 3018577.6 | 8921440.86 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 4807675.47 | 13386633.34 | 0 | 259813.59 | 0 | 0 | 18194308.81 | 4807675.47 | 13646446.93 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 17267191.18 | 48049971.59 | 273636.92 | 931916.64 | 0 | 0 | 65590799.69 | 17540828.1 | 48981888.23 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 21333819.52 | 59366309.82 | 338081.66 | 1151514.49 | 0 | 0 | 81038211 | 21671901.18 | 60517824.31 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 7414164.75 | 20637925.62 | 0 | 328143.02 | 0 | 0 | 28052090.37 | 7414164.75 | 20966068.64 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 32703357.23 | 90995446.51 | 514882.72 | 2059216.24 | 0 | 0 | 124213686.46 | 33218239.95 | 93054662.75 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 3767690.42 | 10493001.48 | 0 | 203638.57 | 0 | 0 | 14260691.9 | 3767690.42 | 10696640.05 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 15900537.4 | 44246939.88 | 251979.26 | 858465.45 | 0 | 0 | 60399456.54 | 16152516.66 | 45105405.33 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 18254467.11 | 50797296.22 | 289282.49 | 985459.15 | 0 | 0 | 69341045.82 | 18543749.6 | 51782755.37 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 12945985.39 | 36028872.38 | 0 | 698724.72 | 0 | 0 | 48974857.77 | 12945985.39 | 36727597.1 | Obligated -No expected changes | N/A | Project is pending FEMA obligation
727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 6849050.26 | 19064883.85 | 0 | 369745.52 | 0 | 0 | 25913934.11 | 6849050.26 | 19434629.37 | Obligated -No expected changes | N/A | Project is currently in execution
738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 10313627 | 243128.63 | 834793 | 63002.37 | 0 | 0 | 11454551.37 | 11148420 | 306131 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4926640.11 | 116500.1 | 439975 | 31370.9 | 0 | 0 | 5514486.01 | 5366615.11 | 147871 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2569486.15 | 1816.46 | 240897.11 | 1170.09 | 251407.95 | 11885.35 | 3076663.11 | 3061791.21 | 14871.9 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1747929 | 286587 | 335721.9 | 75946 | 0 | 0 | 2446183.9 | 2083650.9 | 362533 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7474369.54 | 3899.16 | 696566.78 | 2495.46 | 751912.5 | 25571.51 | 8954814.95 | 8922848.82 | 31966.13 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 284349 | 57917 | 55024 | 15348 | 0 | 0 | 412638 | 339373 | 73265 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4686914.68 | 1064121.8 | 900015 | 0 | 0 | 0 | 6651051.48 | 5586929.68 | 1064121.8 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
752808 | FAASt [Automation Program Group 19] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1352947.241 | 723597.72 | 119711.919 | 52375.13 | 134857.23 | 320428.9 | 2703918.14 | 1607516.39 | 1096401.75 | Amendment – Submitted to FEMA | Submitted | 406HM Revision on FEMA CRC / Estimated date Cfci strategy to be defined
673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1894033.53 | 373539 | 370850 | 98988 | 0 | 0 | 2737410.53 | 2264883.53 | 472527 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 303774 | 72188.49 | 58918 | 0 | 0 | 0 | 434880.49 | 362692 | 72188.49 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 452956.93 | 87431 | 86724 | 23169.22 | 0 | 0 | 650281.15 | 539680.93 | 110600.22 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 545661.24 | 89627 | 104353 | 23751.16 | 0 | 0 | 763392.24 | 650014.24 | 113378.16 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 573047.24 | 107654 | 110616.4 | 28528.31 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 65944 | 9218 | 12740 | 2443 | 0 | 0 | 90345 | 78684 | 11661 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 320740 | 70006 | 62490 | 18552 | 0 | 0 | 471788 | 383230 | 88558 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 729040 | 142215 | 140628 | 37687 | 0 | 0 | 1049570 | 869668 | 179902 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 589335 | 123232 | 115386 | 33921 | 0 | 0 | 861874 | 704721 | 157153 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 498436 | 75480 | 95421 | 20002 | 0 | 0 | 689339 | 593857 | 95482 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
547187 | FAASt [Substation Component Replacement Program] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 8100488.35 | 247967.31 | 2674863.91 | 80958.71 | 2426520.07 | 20166.62 | 13550964.97 | 13201872.33 | 349092.64 | DSOW – Submitted to COR3/PREPA | Submitted | Submitted to COR3 in Feb. 2026
723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 46386613.5309 | 7066086.2431 | 4717122.9683 | 1607474.1693 | 5708774.0907 | 10610441.8276 | 76096512.83 | 56812510.5899 | 19284002.2401 | DSOW – Pending Design Package for Development | FY2027 | Planning and Engineering is working on the scope for the project.
169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 19057031.49 | 9240046.5742 | 1213803.7 | 655599.77 | 4285314.68 | 3369687 | 37821483.2142 | 24556149.87 | 13265333.3442 | Amendment – Amendment Needed/Pending Development | Q4 FY2026
551914 | FAASt [Caparra 1912 & 1924] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 5432996.3672 | 827609.9065 | 552489.3929 | 188274.1735 | 668635.7665 | 1242739.8233 | 8912745.43 | 6654121.5267 | 2258623.9033 | DSOW – Submitted to COR3/PREPA | Q1 FY2027 | We resubmit DSOW on January 2026.
550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 6785925.6525 | 1619262.5575 | 668387.83 | 277399.36 | 1675808.9975 | 1892815.1025 | 12919599.5 | 9130122.48 | 3789477.02 | DSOW – Scope and Cost development in progress | Q4 FY2026 | Pending recieve assesment to iclude repairs to the fiber between Monacillos and El Conquistador
169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 6681615.89 | 1589026.4125 | 944927.79 | 429312.71 | 5815884.59 | 4089397.02 | 19550164.4125 | 13442428.27 | 6107736.1425 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Pending IFC to complete Estimate review
174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation | Yes | Obligated | 16677900.7662 | 2540549.443 | 3127217.3734 | 1291524.2237 | 2052539.7423 | 3814891.4615 | 29504623.01 | 21857657.8819 | 7646965.1281 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Pending IFC package to include all the changes in scope as part of the DSOW ammendment.
178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 23590868.47 | 6947025.75 | 2694924.72 | 918361.02 | 3261461.81 | 6061818.23 | 43474460 | 29547255 | 13927205 | DSOW – Scope and Cost development in progress | Q2 FY2027 | Currently under Scope revision by Planning
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 10188475.3228 | 1552013.39 | 1036081.0436 | 353069.7686 | 1253889.8514 | 2330504.7835 | 16714034.16 | 12478446.2178 | 4235587.9422 | DSOW – Submitted to COR3/PREPA | Submitted | Submitted to COR3 in Jan. 2026
660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Security | Yes | Obligated | 3478518 | 226650 | 766618 | 111627 | 0 | 0 | 4583413 | 4245136 | 338277 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation
549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation | Yes | Obligated | 3924015.69 | 377039.3 | 818227.24 | 202728.22 | 0 | 0 | 5322010.45 | 4742242.93 | 579767.52 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation
169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 44329891.87 | 20397885.95 | 3422296.52 | 1244683.56 | 11765689.6 | 6188 | 81166635.5 | 59517877.99 | 21648757.51 | DSOW – Pending Design Package for Development | FY2027
549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2583133.54 | 182993.64 | 580188.69 | 105129.94 | 0 | 0 | 3451445.81 | 3163322.23 | 288123.58 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Telecommunication | IT/OT | No | Pending CRC Review | 28822774.33 | 5421191.94 | 2708151.69 | 509326.83 | 0 | 0 | 37461444.79 | 31530926.02 | 5930518.77 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Proyect under CRC review by Feb 16th. Pending Obligation to determine Amendment submission date.
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 5267467.9889 | 939009.17 | 800287.4104 | 134453.4396 | 396718.56 | 0 | 7537936.5689 | 6464473.9594 | 1073462.6096 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Q1 FY2027 | Pending FEMA Obligation, currently in Phase 5.
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 13148929.44 | 45408.4 | 2828793.1 | 10487.44 | 0 | 0 | 16033618.38 | 15977722.54 | 55895.84 | Amendment – Pending Design Package for Development | Q1 FY2027 | Design Package expected Jun 2026.
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 8124106.79 | 44186.4888 | 1075319.59 | 4963.76 | 4917.0688 | 427.5712 | 9253921.2688 | 9204343.4488 | 49577.82 | Amendment – Pending Design Package for Development | Q1 FY2027 | Design Package expected Jun 2026.
714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Telecommunication | AMI Implementation Program | Yes | Obligated | 332062581 | 541786319 | 16450923 | 2421276 | 0 | 0 | 892721099 | 348513504 | 544207595 | Obligated -No expected changes | Submitted | Already Submitted
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 90286761.91 | 12425361.64 | 7450643.73 | 918661.08 | 14930827.72 | 619919.91 | 126632175.99 | 112668233.36 | 13963942.63 | DSOW – Scope and Cost development in progress | Q1 FY2026 | Issue for Approval was received meeting ongoing to discuss the design and agree in the final scope to be submitted to FEMA.
750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 428428.21 | 31613.73 | 45787.13 | 3335.39 | 40011.28 | 2523.72 | 551699.46 | 514226.62 | 37472.84 | Obligated -No expected changes | N/A | Already Submitted
751655 | FAASt [Culebra Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 287219.87 | 55806508.56 | 15173.21 | 5897280.98 | 0 | 8788889.34 | 70795071.96 | 302393.08 | 70492678.88 | DSOW – Pending Design Package for Development | Q2 FY2027 | The DSOW Revision 2 for the Vieques and Culebra Microgrid was submitted in July 2025. After receiving various Requests for Information (RFIs) from FEMA related to the design, an internal decision was made to re-submit the DSOW once the 30% design is completed, providing more robust information to adequately address the agency’s requests. As of today, the DSOW is estimated to be re-submitted in October 2026 following the completion of the 60% design.
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 30997111.49 | 4687634.65 | 2356500.58 | 611010.51 | 1066728.72 | 3628503.17 | 43347489.12 | 34420340.79 | 8927148.33 | DSOW – Submitted to COR3/PREPA | Submitted | Already Submitted
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 25335445.6 | 4067258.81 | 2040875.23 | 429319.88 | 2446381.79 | 1777436.92 | 36096718.23 | 29822702.62 | 6274015.61 | DSOW – Submitted to COR3/PREPA | Submitted | Already Submitted
711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 2619583.06 | 20527.74 | 292186.72 | 3160.19 | 140718.36 | 9363.36 | 3085539.43 | 3052488.14 | 33051.29 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 763811.92 | 51189.5 | 68678.99 | 4322.92 | 69251.52 | 4576.48 | 961831.33 | 901742.43 | 60088.9 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 32064811.63 | 4437681.65 | 3286608.94 | 1116082.17 | 4091238.32 | 7842452.06 | 52838874.77 | 39442658.89 | 13396215.88 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 125923.56 | 5675.78 | 19852.4 | 1075.68 | 5971.66 | 1473.34 | 159972.42 | 151747.62 | 8224.8 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 425379.95 | 829239.3 | 40970.81 | 86903.02 | 19608.94 | 114799.06 | 1516901.08 | 485959.7 | 1030941.38 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1508927.85 | 9181.75 | 131787.84 | 648.92 | 107681.05 | 17151.55 | 1775378.96 | 1748396.74 | 26982.22 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
751656 | FAASt [Vieques Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 520290.54 | 99551019.1 | 27002.9 | 8445174.73 | 0 | 16900821.81 | 125444309.08 | 547293.44 | 124897015.64 | DSOW – Pending Design Package for Development | Q2 FY2027 | The DSOW Revision 2 for the Vieques and Culebra Microgrid was submitted in July 2025. After receiving various Requests for Information (RFIs) from FEMA related to the design, an internal decision was made to re-submit the DSOW once the 30% design is completed, providing more robust information to adequately address the agency’s requests. As of today, the DSOW is estimated to be re-submitted in October 2026 following the completion of the 60% design.
168226 | FAASt San Juan 115kV Underground Transmission | Transmission | Transmission Line Rebuild | Yes | Obligated | 12496039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 14754379.24 | 14754379.24 | 0 | Obligated -No expected changes | N/A | Scope confirmation under discussion to create amendment Insurance deduction of $2,250,000
684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 3874950.13 | 0 | 458489.44 | 0 | 1183030.01 | 0 | 5516469.58 | 5516469.58 | 0 | Obligated -No expected changes | N/A | No Amendment Needed
708637 | FAASt T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 255862.85 | 38293.66 | 30158.85 | 4783.59 | 20073.47 | 5479.68 | 354652.1 | 306095.17 | 48556.93 | Obligated -No expected changes | N/A | No Amendment Needed
681672 | FAASt Transmission Priority Pole Replacements | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 271850.8 | 4298.39 | 27464.76 | 560.49 | 41708.61 | 2113.04 | 347996.09 | 341024.17 | 6971.92 | Obligated -No expected changes | N/A | No Amendment Needed
711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 102171.23 | 13243.54 | 16958.53 | 1285.62 | 662.57 | 950.36 | 135271.85 | 119792.33 | 15479.52 | Obligated -No expected changes | N/A | No Amendment Needed
712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 232028.81 | 37424.09 | 28581 | 4483.52 | 23456.66 | 2666.22 | 328640.3 | 284066.47 | 44573.83 | Obligated -No expected changes | N/A | No Amendment Needed
801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | Distribution | Feeders | Yes | Obligated | 1862738.37 | 50953.86 | 568090.34 | 22194.71 | 160515.06 | 28092.46 | 2692584.8 | 2591343.77 | 101241.03 | Amendment – Submitted to FEMA | Submitted | Working on re-versioning (PA-428 & HM-406 already submitted to FEMA), to be submitted to FEMA on Feb 2026
735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 17211915.22 | 71311.91 | 1524520.51 | 44806.65 | 1144636.03 | 468198.97 | 20465389.29 | 19881071.76 | 584317.53 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 8687329.99 | 35434.35 | 773151.6 | 23427.4 | 622940.21 | 246677.69 | 10388961.24 | 10083421.8 | 305539.44 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
752810 | FAASt [Automation Program Group 20] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1645985.22 | 847714.06 | 176266.8 | 72284.36 | 202809.71 | 358776.21 | 3303836.36 | 2025061.73 | 1278774.63 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
757662 | FAASt [Automation Program Group 21] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1284891.5683 | 425656.3717 | 205400.7597 | 75115.8303 | 162255.9386 | 350540.5414 | 2503861.01 | 1652548.2666 | 851312.7434 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | 406HM Revision to be submitted June 2026 / Estimated date Cfci strategy to be defined
757689 | FAASt [Automation Program Group 24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1598412.2339 | 442039.2361 | 142037.0968 | 67265.4432 | 168735.76 | 400852.24 | 2819342.01 | 1909185.0907 | 910156.9193 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
757692 | FAASt [Automation Program Group 26] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 805588.09 | 597770.7 | 71140.9 | 41960.7 | 89982.74 | 251069 | 1857512.13 | 966711.73 | 890800.4 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | Vegetation | Yes | Obligated, Amendment Pending Award | 102333.57 | 346668.94 | 3287.5 | 11131.3 | 0 | 0 | 463421.31 | 105621.07 | 357800.24 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $474,552.61, however only .913/2.82 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution, project version pending obligation.
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 244155.63 | 919.99 | 25573.49 | 679.94 | 16392.64 | 6007.36 | 293729.05 | 286121.76 | 7607.29 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
757694 | FAASt [Automation Program Group 27] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1683592.9921 | 631140.7879 | 308544.3439 | 111377.7861 | 458173.9582 | 519763.0018 | 3712592.87 | 2450311.2942 | 1262281.5758 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted May 2026 / Estimated date Cfci strategy to be defined
550896 | FAASt Line 6700 Martin Peña TC to Villamar Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1923721.17 | 13772.66 | 166749.56 | 1956.97 | 173673.6 | 10982.34 | 2290856.3 | 2264144.33 | 26711.97 | Amendment – Submitted to FEMA | Submitted
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | Vegetation | Yes | Obligated, Amendment Pending FEMA 406 HMP Completion | 573361.58 | 1942395.21 | 5324.16 | 18027.38 | 0 | 0 | 2539108.33 | 578685.74 | 1960422.59 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $4,685,447.53, however only 3.83/11.13 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution, project version pending obligation.
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Vegetation | Yes | Obligated, Amendment Pending Large Project Review | 6584889.61 | 18404524.67 | 82677.83 | 23074.58 | 0 | 0 | 25072092.11 | 6667567.44 | 18427599.25 | Amendment – Submitted to FEMA | Submitted | Obligated portion of project is currently in execution, project version pending obligation
746309 | FAASt [Automation Program Group 30] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 327791.49 | 236273.14 | 53695.19 | 28394.95 | 65212.75 | 98251.25 | 809618.77 | 446699.43 | 362919.34 | DSOW – Submitted to FEMA | N/A | No Amendment Needed
757696 | FAASt [Automation Program Group 31] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 942101.34 | 583449.9 | 87474.903 | 43702.3571 | 122168.23 | 240541.77 | 2019438.5 | 1151744.473 | 867694.0271 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20/ Estimated date Cfci strategy to be defined
757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2115845.46 | 475340.55 | 196682.43 | 74220.68 | 209878.53 | 481486.47 | 3553454.12 | 2522406.42 | 1031047.7 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted April 2026/ Estimated date Cfci strategy to be defined
757698 | FAASt [Automation Program Group 33] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1124448.32 | 1149434.09 | 141667.93 | 165158.11 | 30777.97 | 144660.32 | 2756146.74 | 1296894.22 | 1459252.52 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted April 2026/ Estimated date Cfci strategy to be defined
797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | Distribution | Feeders | Yes | Obligated | 2174764.98 | 235072.1 | 641910.96 | 66287.34 | 431054.74 | 34079.01 | 3583169.13 | 3247730.68 | 335438.45 | Amendment – Submitted to FEMA | Submitted | Working on re-versioning (PA-428 & HM-406 already submitted to FEMA), attending soft RFI received from FEMA, to be submitted to FEMA on Mar 2026
757699 | FAASt [Automation Program Group 34] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2600700.95 | 561457.08 | 233404.43 | 74776.72 | 147275.17 | 403036.03 | 4020650.38 | 2981380.55 | 1039269.83 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406HM Revision to be submitted June 2026 / Estimated date Cfci strategy to be defined
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1133466.58 | 869967.07 | 148303.89 | 84426.9677 | 118838.82 | 298749.59 | 2653752.9177 | 1400609.29 | 1253143.6277 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
800361 | FAASt [Automation Program Group 37] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1539270.03 | 341311.78 | 182365.82 | 60877.03 | 158441.28 | 302864.72 | 2585130.66 | 1880077.13 | 705053.53 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 4489030.64 | 3693295.57 | 671253.14 | 539034.63 | 0 | 0 | 9392613.98 | 5160283.78 | 4232330.2 | Amendment – Submitted to FEMA | Submitted | Amedment submitted to FEMA on Jan 26,2026. Cost estimate revised and splited 428 55% & 406 45% Aprox.
[6 empty] | 3035704041.1365 | 1701407212.3368 | 349129466.0157 | 90824442.8178 | 293981332.0697 | 200575645.3054 | 5662215825.4988 | 3678814839.2219 | 1992807300.4599

## Sheet1 (hidden)
FAASt %23 | P/W %23 | FEMA Best Available Cost | 406 Cost Estimate | A&E Cost Estimate | E&M Cost Estimate | 428 Cost Estimate | 406 A&E | 406 CE - 406 A&E | Luma Expected Cost (428+406) | Total LUMA Expected Cost (406+428+A&E) | Earliest Expected Obligation Date | Latest Expected Obligation Date | Initial Date Obligated | Last Date Obligated | Obligated Amount - V0 CRC Net Cost | Obligated Amount - V0 CRC Gross Cost | Obligated Amount - V1 CRC Net Cost | Obligated Amount - V1 CRC Gross Cost | Obligated Amount - V2 CRC Net Cost | E&M Obligated Cost | Obligated Amount - V2 CRC Gross Cost | Approved Obligated Amount - CRC Net Cost Cal | Approved Obligated Amount - CRC Gross Cost Cal | PoP Expiration Date | Document Path | Notes | Modified | Created | Created By | For Jeremy | Modified By | ObligationEstimatingFormulaResult | ObligationEstimatingFormulaResultLookUp | 428 A&E Obligated Cost | 406 A&E Obligated Cost | Attachments | Scope Change | Scope Change Score | Date Inactivated | RFIFAASt | Title | E&M 428 | E&M 406 | E&M 428 + 406 Total Calc | Multiple Financial Numbers
68753 | 1165 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 2019-09-06 |  | 0 | 0 | [5 empty] | 0 | 0 |  |  |  | 2026-02-17 12:44 | 2023-08-14 11:10 | Jahdiel Franqui |  | Marlina Crespo |  |  |  |  | 0 | #DIV/0! | #DIV/0! | 2025-05-23 | 68753RFI394 | 68753 |  |  | 0
83182 | 1294 | 620193956.54 |  |  |  | 620193956.5 | 0 | 0 | 620193956.5 | 620193956.5 |  |  | 2020-02-05 | 2023-04-14 | 52465131.5 | 52465131.5 | 620193956.54 | 620193956.54 |  |  |  | 620193956.54 | 620193956.54 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/393/PRJ_Report_83182_20240219.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  | 0 |  | 1 | 1 | 1 |  | 83182RFI393 | 83182 |  |  | 0
136271 | 6099 | 4132895287.7 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 2020-09-24 | 2024-09-18 | 6129706543.59 | 6323452979.59 | 5955252831.92 | 6148999267.92 | 4106613749.59 |  | 4300360185.59 | 4106613749.59 | 4300360185.59 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/392/136271-DR4339PR-Detailed%20SOW-T-Pole%20TL9600%20Bayamon%20TC%20%E2%80%93%20Catano%20Sect_Rev.0_2-17-2025.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  |  |  | 1 | #DIV/0! | #DIV/0! |  | 136271RFI392 | 136271 |  |  | 0
165208 | 107205 | 15186702.6 | [5 empty] | 0 | 15186702.6 | 15186702.6 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/391/165208-DR4339PR-Transmission%20Access%20Roads-11.24.2020.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Manager Joanna Dlugopolski. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission Access Roads | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 165208RFI391 | 165208 |  |  | 0
165209 | 10626 | 14048046 | 0 | 1493591 |  | 12765829 | 0 | 0 | 12765829 | 14259420 |  |  | 2022-06-10 |  | 1387420 | 1282218 | 1459609 | 1282218 |  |  |  | 1387420 | 1282218 | 2027-09-20 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/390/165209-DR-4339PR-Culebra%20Substation%203801%20and%20New%20Culebra%20Substation%203802%20FEMA%20Detailed%20Scope%20of%20Work%20Rev.%208%20(7.12.2024)%20-%20signed.pdf?web=1 | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Culebra 3801 & New Culebra Substation 3802 | Jason Fournier |  |  | 522360 |  | 1 | 1.1004 | 1 |  | 165209RFI390 | 165209 |  |  | 0
165213 | 11244 | 0 | 19118456.86 | 4617946.01 |  | 67974026.1 | 1883144.1 | 17235312.76 | 87092482.96 | 91710428.97 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 | 2027-09-20 |  | Use this link: https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/389/165213-DR4339PR%20DSOW%20TL%205400%20Rio%20Blanco%20HP%20to%20DaguaoTC%20to%20Vieques%20To%20Culebra%20Vieques%20and%20Culebra%20Microgrid%20Rev-4_Sep.22.2025_signed.pdf?web=1 | 2025-11-20 13:53 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Marlina Crespo | 0 Months |  |  |  | 1 | 0 | 5 |  | 165213RFI389 | 165213 | 0 | 12125.03 | 12125.03
165225 | 10624 | 14704637.25 | 0 | 1491087 |  | 13495526 | 0 | 0 | 13495526 | 14986613 |  |  | 2022-06-10 | 2022-06-10 | 1313648.1 | 1209111 | 1387420 | 1209111 |  |  |  | 1387420 | 1209111 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/388/165225-%20DR-%204339%20-%20DSOW-Vieques%20New%20Substation(Isla%20Nena)%20Rev.8%20(1.27.2024)%20signed.pdf?web=1 |  | 2026-02-03 09:48 | 2023-08-14 11:10 | Jahdiel Franqui | Vieques 2501 & New Vieques Substation 2502 | Marlina Crespo |  |  | 531763 |  | 1 | 1.0896 | 1 |  | 165225RFI388 | 165225 |  |  | 0
165226 | 107206 | 57351920 | 12438987.09 | 5588218.14 |  | 66623350 | 962266.1 | 11476720.99 | 79062337.09 | 84650555.23 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/387/PN165226-DR4339PR-Feeders%20VC-DSOW%20Rev.4%20Signed(HM_ARR_11.21.25).docx?web=1 |  | 2025-12-04 11:50 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution – Vieques Feeders 2501-01, 2501-02, 2501-03 and Culebra Feeders 3801-01, 3801-02 | Marlina Crespo | 0 Months |  |  |  | 1 | 0.7254 | 2 |  | 165226RFI387 | 165226 | 3880212.29 | 1009930.36 | 4890142.65
165268 | 11045 | 11683614.71 | 4585370.95 | 1391013 |  | 7098243 | 1768433.49 | 2816937.46 | 11683613.95 | 13074626.95 |  |  | 2022-12-21 |  | 11683614.71 | 7098243.76 | [5 empty] | 11683614.71 | 7098243.76 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/386/165268-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20Rio%20Grande%20Estates%20CH%202306%20(10055-CP-SOW-0003Rev4%202022-11-10)%20(1).pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Rio Grande Estates - CH - 2306 | Jason Fournier |  |  | 1391012.61 |  | 1 | 1 | 1 |  | 165268RFI386 | 165268 |  |  | 0
166707 | 11431 | 0 | 16781976 | 3528829 |  | 28280524 | 1774233 | 15007743 | 45062500 | 48591329 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/385/166707-DR4339PR-DSOW-TL-51300-Rev%204_TGH_02-01-24%20-%20signed%20(1).pdf?web=1 |  | 2025-08-18 14:49 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission Line 51300 - Ponce TC to Costa Sur SP TC | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 166707RFI385 | 166707 |  |  | 0
166834 | 107214 | 15980000 | [5 empty] | 0 | 15980000 | 15980000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/384/166834-DR4339PR-Transmission%20%20Line%2040100%20&%2040200%20-%20Aguirre%20SP%20TC%20to%20Jobos%20TC%20(1).pdf?web=1 | 9/12/2024 - GP Notes6/18/2024 - The project is not included in the 90-Day Plan submitted in June 2024. Forecast have been requested to the applicant.6/25/2024- The project was withdrawn | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 166834RFI384 | 166834 |  |  | 0
166860 | 11255 | 0 | 19709323 | 7900833 |  | 74111756 | 1889975 | 17819348 | 93821079 | 101721912 | 2024-09-30 | 2025-02-28 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/383/166860-DR4339PR-%20Detailed%20SOW%20Line%2037800%20Rev.4.pdf?web=1 |  | 2025-08-18 14:42 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 166860RFI383 | 166860 |  |  | 0
166904 | 11451 |  | 9229435 | 4855883 |  | 45544705 | 881999 | 8347436 | 54774140 | 59630023 | 2024-07-31 | 2024-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/382/166904-DR4339PR-%20Detailed%20SOW%20Line%2037800%20Rev.2%20(1).pdf?web=1 |  | 2025-08-18 14:41 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 166904RFI382 | 166904 |  |  | 0
167168 | 11246 |  | 24646695 | 10274876 |  | 96370356 | 2374619 | 22272076 | 121017051 | 131291927 | 2025-08-31 | 2025-01-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/381/167168-DR4339PR-%20Detailed%20SOW%20Line%2037100%20(10062-CP-SOW-0002_Rev1)%2028JUNE2023.pdf?web=1 | 13SEPTEMBER2024 DSOW Rev. 2 was removed from GP. It was originally submitted on January 12, 2024 | 2025-08-18 14:39 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt_TRANSMISSION-LINE-37100_COSTA SUR-ST_ACACIAS-TC | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 167168RFI381 | 167168 |  |  | 0
167443 | 11251 | 0 | 15967020 | 6485111 |  | 62522200 | 1461125 | 14505895 | 78489220 | 84974331 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/380/167443-DR4339PR-Detailed%20SOW-TL36200%20Monacillos%20TC%20to%20Juncos%20TC%20rev%205-1-11-24%20TGH-sign%5B25722%5D.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 36200 | 2025-08-18 13:33 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt - Line 36200 - Monacillos TC to Juncos TC (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 167443RFI380 | 167443 |  |  | 0
167446 | 11307 |  | 0 | 3371255.12 |  | 32863940.58 | 0 | 0 | 32863940.58 | 36235195.7 | 2024-11-30 | 2025-04-30 | 2025-11-05 |  | 33956314.58 | 33956314.58 |  |  |  | 85008 |  | 33956314.58 | 33956314.58 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/379/PW%2011307%20PRJ_MultiVersionReport_167446_20251105.pdf?web=1 | 8/8/2025 - Field EHP: RFI response received on 08/08/2025, under EHP specialist revision. Expected Completion Date (ECD) 08/22/2025. 8/11/2025 -This project is under the DOE Emergency declaration 202C, pending R2 guidance. 8/12/2025 8:24 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-01-29 09:25 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt - Line 36100 - Dos Bocas HP to Monacillos TC (Transmission) | Ashleah Dingle |  |  | 3408229.98 | 0 | 1 | 0 | 5 |  | 167446RFI379 | 167446 | 85008 |  | 85008
167508 | 11250 |  | 4609955 | 7023284 |  | 71765405 | 200381 | 4409574 | 76375360 | 83398644 | 2024-07-31 | 2024-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/378/167508-DR4339PR-DSOW-TL-50100-Cambalache%20GP%20to%20Manati%20TC-Rev5_05-10-2024-TGH-IEM_Updated%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 50100 | 2025-08-18 13:27 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission - Line 50100 - Cambalache GP TC to Manati TC (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 167508RFI378 | 167508 |  |  | 0
168226 | 10978 | 14746039.57 | 0 | 584325 |  | 16420054 | 0 | 0 | 16420054 | 17004379 |  |  | 2022-12-21 | 2025-09-10 | 14746039.57 | 14746039.57 | 14746039.57 | 14746039.57 |  |  |  | 14746039.57 | 14746039.57 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/377/168226%20-Detailed%20SOW-115kV-%20TL%2038000%20%20San%20Juan-Isla%20Grande%20Underground%20Loop.pdf?web=1 |  | 2026-01-29 09:36 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission - San Juan 115-kV Underground Transmission Loop | Ashleah Dingle |  |  | 2258339.67 |  | 1 | 0.89805 | 1 |  | 168226RFI377 | 168226 |  |  | 0
168483 | 11241 | 0 | 8111071 | 10145828 |  | 96749488 | 339692 | 7771379 | 104860559 | 115006387 | 2024-06-30 | 2024-09-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/376/168483-DR4339PR-%20TL36400%20Dos%20Bocas%20to%20Ponce%20-Detailed%20SOW%20-Rev4_05-09-2024%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 36400 7/30/ | 2025-08-11 09:54 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission - Line 36400 - Dos Bocas HP to Ponce TC | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 |  | 168483RFI376 | 168483 |  |  | 0
169058 | 107220 | 18279001 | 13265333.34 | 1213803.7 |  | 23342346.17 | 655599.77 | 12609733.57 | 36607679.51 | 37821483.21 | 2024-12-31 | 2025-06-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/375/169058-DR4339PR-DSOW%20Llorens%20Torres%20Substation%20-%20Rev.15%20(5.5.2025)%20signed.pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Llorens Torres MC 1106 - Equipment Repair & Replacement | Jason Fournier |  |  |  |  | 1 | 0.49932 | 3 |  | 169058RFI375 | 169058 | 4078410.44 | 3369687 | 7448097.44
169266 | 11489 | 21332361 | 6537037 | 1810918 |  | 14795324 | 0 | 6537037 | 21332361 | 23143279 |  |  | 2023-11-03 | 2024-08-30 | 21332361 | 14795324 | 21332361 | 14795324 |  |  |  | 21332361 | 14795324 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/374/PW%2011489%20PRJ_Report_169266_20231103.pdf?web=1 |  | 2026-02-17 11:29 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Centro Medico 1327/1359 Equipment Repair and Replacement | Marlina Crespo |  |  | 1810918 |  | 1 | 1 | 1 |  | 169266RFI374 | 169266 |  |  | 0
169276 | 107222 | 20425907 | 3661876.82 | 5917803.36 |  | 75107786 | 267449.67 | 3394427.15 | 78769662.82 | 84687466.18 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/373/169276-DR4339PR-Detailed%20Scope%20of%20Work-%20Viaducto%20TC-MC-1100%20Rev6.%20040224%20-%20signed.pdf?web=1 | 3/27/2024: QC Review Complete | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substations) | Jason Fournier |  |  |  |  | 1 | 0.25931 | 4 |  | 169276RFI373 | 169276 |  |  | 0
169495 | 11479 | 15339932.33 | 7159883.3 | 1397860 |  | 8180049 | 1044957.8 | 6114925.5 | 15339932.3 | 16737792.3 |  |  | 2023-08-22 |  | 15339932.33 | 8180049.03 | [5 empty] | 15339932.33 | 8180049.03 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/372/169495-DR4339PR-%2000%20Detailed%20SOW%20Tapia%20Substation%20-%20(10059-CP-SOW-0002Rev6)(rev%202023-06-14)%20-%20signed.pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Tapia GIS Rebuilt - Equipment Repair and Replacement | Jason Fournier |  |  | 1397859.52 |  | 1 | 1 | 1 |  | 169495RFI372 | 169495 |  |  | 0
169500 | 11347 | 6372063 | 3575881 | 634045 |  | 2796182 | 1496809 | 2079072 | 6372063 | 7006108 |  |  | 2023-06-16 |  | 6372063 | 2796182 | [5 empty] | 6372063 | 2796182 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/371/169500-DR4339PR%20-%20FEMA%20DSOW%20-%20Bayamon%20TC%20(10100-CP-SOW-0002_Rev.4)%202023-04-2700-CP-SOW-0002_Rev.4.pdf |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Bayamon TC – MC-BKRS-Y1 | Jason Fournier |  |  | 634046 |  | 1 | 1 | 1 |  | 169500RFI371 | 169500 |  |  | 0
169503 | 107224 | 2700000 | [5 empty] | 0 | 2700000 | 2700000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/370/DI433943-DR4339PR-Substations%20-%20Ceiba%20Baja%20TRF%207012%20%20Intial%20SOW%20&%20CE%201-11-21%20(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 169503RFI370 | 169503 |  |  | 0
169576 | 107225 | 1800000 | [5 empty] | 0 | 1800000 | 1800000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/369/%5B169576%5D-DR4339PR-Arecibo%20Regional%20Office%20Building.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Buildings - Arecibo Regional Office Building | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | 169576RFI369 | 169576 |  |  | 0
169798 | 107226 | 2320000 | [5 empty] | 0 | 2320000 | 2320000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/368/%5B169798%5D-DR4339PR-Arecibo%20Electric%20Service%20Center.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Buildings - Arecibo Electric Service Center | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | 169798RFI368 | 169798 |  |  | 0
169804 | 107227 | 3500000 | [5 empty] | 0 | 3500000 | 3500000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/367/%5B169804%5D-DR4339PR-Aguadilla%20Electric%20Service%20Center.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Buildings - Aguadilla Electric Service Center | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 169804RFI367 | 169804 |  |  | 0
169896 | 10788 | 23251835 | 0 | 4734912 |  | 23251835 | 0 | 0 | 23251835 | 27986747 |  |  | 2022-08-02 |  | 23251835 | 23251835 | [5 empty] | 23251835 | 23251835 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/366/169896%20-%20DR-4339-PR%20-%20Detailed%20Scope%20of%20Work%20-%20Costs%20Sur%20230kV%2010101%20(2).pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Costa Sur SP TC – Equipment Repair and Replacement | Jason Fournier |  |  | 4734912 |  | 1 | 1 | 1 |  | 169896RFI366 | 169896 |  |  | 0
174422 | 10496 | 23255048.94 | 807222.04 | 4104786 |  | 18571716 | 0 | 807222.04 | 19378938.04 | 23483724.04 |  |  | 2022-05-18 |  | 23255048.94 | 16359899.17 | [5 empty] | 23255048.94 | 16359899.17 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/365/542688%20DR4339PR%20Aguada%20Streetlight%2050000-EN-SOW-0018_Rev1%20(1).pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Cataño – Rebuilt 1801 | Jason Fournier |  |  | 1211174.91 |  | 1 | 1.2 | 1 |  | 174422RFI365 | 174422 |  |  | 0
176913 | 11432 | 11649409 | 0 | 297862.88 |  | 40504745.14 | 0 | 0 | 40504745.14 | 40802608.02 | 2025-07-31 | 2025-12-31 | 2025-11-05 |  | 33526671.86 | 33526671.86 |  |  |  | 297862.88 |  | 33526671.86 | 33526671.86 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/364/PW%2011432%20PRJ_MultiVersionReport_176913_20251105.pdf?web=1 | 8/12/2025 8:24 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-01-29 09:25 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Palo Seco SP to Catano SectLine-9500 (Transmission) | Ashleah Dingle |  |  | 4657292.73 | 0 | 1 | 0.28761 | 4 |  | 176913RFI364 | 176913 | 297862.88 | 0 | 297862.88
176954 | 11439 | 0 | 4127356 | 571113 |  | 2791523 | 700994 | 3426362 | 6918879 | 7489992 | 2024-07-31 | 2024-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/363/176954%20Detail%20Scope%20of%20Work%2010069-CP-SOW-0003%20-%20signed.pdf?web=1 |  | 2025-08-18 13:27 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Garzas 1 HP to Garzas 2 HP - Line 1100 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 176954RFI363 | 176954 |  |  | 0
176971 | 11373 | 15567361 | 0 | 3250894.37 |  | 23193643.55 | 0 | 0 | 23193643.55 | 26444537.92 | 2024-07-31 | 2024-12-31 | 2025-11-05 |  | 21670623.78 | 21670623.78 |  |  |  | 120403.36 |  | 21670623.78 | 21670623.78 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/362/PW%2011373%20PRJ_MultiVersionReport_176971_20251105.pdf?web=1 | 8/8/2025 - Field EHP: RFI response received on 07/31/2025, under EHP specialist revision. The expected completion date (ECD) for the response revision is 08/15/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-01-29 09:25 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt San Juan SP to Catano SectLine-8200 (Transmission) | Ashleah Dingle |  |  | 3124951.32 | 0 | 1 | 0.67119 | 2 |  | 176971RFI362 | 176971 | 120403.36 |  | 120403.36
177134 | 11440 | 0 | 7821691 | 5401272 |  | 54274064 | 471725 | 7349966 | 62095755 | 67497027 | 2024-11-30 | 2025-01-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/361/177134-DR4339PR-Detailed%20SOW%20-%20TL4100%20Guaraguao%20TC%20-Comerio%20TC%20Rev.5%20-%20signed.pdf?web=1 |  | 2025-08-18 12:54 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Guaraguao TC to Comerio TCLine-4100 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 177134RFI361 | 177134 |  |  | 0
177191 | 11433 | 0 | 906873 | 2036324 |  | 17371561 | 93989 | 812884 | 18278434 | 20314758 | 2024-10-31 | 2025-01-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/360/177191-DR4339PR-Detailed%20SOW%20-%20TL39000%20Aguas%20Buenas%20TC%20to%20Caguas%20TC%20-Rev4_05-09-2024%20-%20signed.pdf?web=1 |  | 2026-02-24 13:54 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Aguas Buenas TC to Caguas TC - 39000 (Transmission) | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 | 2025-08-20 | 177191RFI360 | 177191 |  |  | 0
178258 | 11721 | 13486572.33 | 4123842.4 | 1302381.39 |  | 9362729.93 | 961993.54 | 3161848.86 | 13486572.33 | 14788953.72 | 2024-10-31 | 2025-01-31 | 2025-02-06 |  | 13486572.33 | 9362729.93 | [5 empty] | 13486572.33 | 9362729.93 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/359/PW%2011721%20PRJ_Report_178258_20250207.pdf?web=1 |  | 2026-01-29 09:26 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Taft – MC 1105 | Ashleah Dingle |  |  | 1302381.39 | 503587.39 | 1 | 1 | 1 |  | 178258RFI359 | 178258 |  |  | 0
178503 | 11100 | 39034592 | 0 | 5171019 |  | 39034592 | 0 | 0 | 39034592 | 44205611 |  |  | 2022-12-27 | 2023-04-14 | 39034592 | 39034592 | 39034592 | 39034592 |  |  |  | 39034592 | 39034592 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/358/178503-DR4339PR-%20Detail%20SOW-Aguirre%20TC%20-%20BKRS%20-%20(10104-CP-SOW-0002_Rev%201)%20(3).pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Aguirre TC - BRKS | Jason Fournier |  |  | 5171019 |  | 1 | 1 | 1 |  | 178503RFI358 | 178503 |  |  | 0
178577 | 11507 | 0 | 16340158.71 | 3196266.58 |  | 24361713.92 | 1892257.29 | 14447901.42 | 40701872.63 | 43898139.21 | 2025-02-28 | 2025-04-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/357/178577-4339%20DR-PR-FEMA%20DSOW%20for%20Cachete%20Substation%202.16.24%20-%20signed.pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Cachete – MC 1526 | Jason Fournier |  |  |  |  | 1 | 0 | 5 |  | 178577RFI357 | 178577 |  |  | 0
179558 | 10632 | 1593443 | 0 | 688917 |  | 1593443 | 0 | 0 | 1593443 | 2282360 |  |  | 2022-05-26 |  | 1593443 | 1593443 | [5 empty] | 1593443 | 1593443 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/356/179558-DR4339PR%20-%20Detailed%20SOW%20-%20Manati%20TC%20-%20BRKS%20230kV%20(10106-CP-SOW-0002%20Rev1)%20(2).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Manati TC - BRKS 230 kv (Substation) | Rey Roldan Rodríguez |  |  | 688917 |  | 1 | 1 | 1 |  | 179558RFI356 | 179558 |  |  | 0
179988 | 107305 | 2400000 | [5 empty] | 0 | 2400000 | 2400000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/355/179988-DR4339PR-Las%20Lomas%20-%20XFMER%201525%20-%20FEMA%20SOW%20CE%201-27-21.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 179988RFI355 | 179988 |  |  | 0
180052 | 11453 | 0 | 0 | 1776747.63 |  | 17796351.55 | 0 | 0 | 17796351.55 | 19573099.18 | 2024-06-30 | 2024-08-31 | 2025-11-05 |  | 74520098.48 | 74520098.48 |  |  |  | 9413216.96 |  | 74520098.48 | 74520098.48 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/354/PW%2011453%20PRJ_MultiVersionReport_180052_20251105.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 100/200 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 8/4/2025 - EHP RFI-PRJ-121350 has been sent to the applicant on July 22, 2025, for their action. The deadline is set for 8/15/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2025-12-01 16:32 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Ponce TC to Jobos TC - 100 (Transmission) FASSt Ponce TC to Jobos TC - 200 (Transmission) | Marlina Crespo | 0 Months |  | 8369786.38 | 0 | 1 | 0 | 5 |  | 180052RFI354 | 180052 | 9413216.96 |  | 9413216.96
180326 | 11441 | 0 | 32488767 | 6478150 |  | 60760627 | 3117231 | 29371536 | 93249394 | 99727544 | 2024-07-31 | 2024-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/353/180326-DR4339PR-%20Detailed%20SOW%20Line%2036800%20Rev.2%20-%20signed.pdf?web=1 |  | 2025-08-19 11:14 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-18 | 180326RFI353 | 180326 |  |  | 0
334191 | 107513 | 98525716 | 38483744 | 7245123 |  | 37430424 | 6091551 | 32392193 | 75914168 | 83159291 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/352/DR4339-PR_334191_DSOW_10140%20-%20Mayag%C3%BCez%20STG3_R1.pdf?web=1 |  | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 3 | Ashleah Dingle |  |  |  |  | 1 | 1.2979 | 1 | 2025-08-15 | 334191RFI352 | 334191 |  |  | 0
334285 | 107514 | 81195988 | 35887745 | 6284173 |  | 42366398 | 4489868 | 31397877 | 78254143 | 84538316 | 2025-05-31 | 2025-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/351/DR4339-PR-334285_DSOW_10139%20-%20Mayag%C3%BCez%20STG2_R1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List 8/13/2024 Removed from Priority Projects, broken down further with pending faast number | 2025-08-18 14:53 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 2 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1.0376 | 1 | 2025-08-15 | 334285RFI351 | 334285 |  |  | 0
334293 | 107516 | 86877699 | 45582792 | 5930015 |  | 41294907 | 5327428 | 40255364 | 86877699 | 92807714 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/350/Revised%20FEMA%20SOW%20-%20334293-DR4339PR-DSOW-%20Mayag%C3%BCez%20STG4%20-%20signed%20(1).pdf?web=1 | <div class="ExternalClass87E8A90E10984BD18A0558075A015B3F"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);">7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List<br></div></div> | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 4 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 334293RFI350 | 334293 |  |  | 0
334308 | 107517 | 72626419 | 32030114 | 7650658 |  | 37671047 | 5407189 | 26622925 | 69701161 | 77351819 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/349/DR4339-PR_334308_DSOW_10011%20-%20Mayag%C3%BCez%20STG1_R1.pdf?web=1 |  | 2025-08-18 14:50 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1.042 | 1 | 2025-08-15 | 334308RFI349 | 334308 |  |  | 0
334323 | 10630 | 392822 | 69130 | 26179 |  | 323152 | 0 | 69130 | 392282 | 418461 |  |  | 2022-05-26 | 2024-08-30 | 392822 | 323692 | 392822 | 323692 |  |  |  | 392822 | 323692 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/348/334323-DR4339PR-Detailed%20SOW-Distribution%20Pole%20and%20Conductor%20Repair%20%E2%80%93%20Ponce%20Group%201-Rev3%20(3).pdf?web=1 |  | 2026-02-17 11:30 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 26179 |  | 1 | 1.0014 | 1 |  | 334323RFI348 | 334323 |  |  | 0
334329 | 10629 | 380253 | 64134 | 25530 |  | 316119 | 0 | 64134 | 380253 | 405783 |  |  | 2022-05-20 | 2024-08-30 | 380253 | 316119 | 380253 | 316119 |  |  |  | 380253 | 316119 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/347/DSOW%205.4.22.pdf?web=1 |  | 2026-02-17 11:31 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 25530 |  | 1 | 1 | 1 |  | 334329RFI347 | 334329 |  |  | 0
334331 | 11528 | 0 |  | 2009300.52 |  | 31788090.96 |  | 0 | 31788090.96 | 33797391.48 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/346/334331-DR4339PR-Detailed%20SOW-TL%201900%20%20Dos%20Bocas%20to%20Caguanas-(Rev%202)_7.1.2025.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 1900 | 2025-11-19 15:53 | 2023-08-14 11:10 | Jahdiel Franqui | Line 1900 Dos Bocas HP to San Sebastian TC | Marlina Crespo | 0 Months |  |  |  | 1 | 0 | 5 | 2025-08-18 | 334331RFI346 | 334331 | 681967 | 0 | 681967
334334 | 107518 | 36590000 | [5 empty] | 0 | 36590000 | 36590000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/345/DI%20661562%20-%20DR%204339%20-10079-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%20500%20Ponce%20TC%20to%20Costa%20Sur%20SP%20Signed.pdf?web=1 | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn. The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Line 500 Ponce TC to Costa Sur SP | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 334334RFI345 | 334334 |  |  | 0
334420 | 107519 | 70560944 | 25596317 | 8617160 |  | 44964627 | 3805840 | 21790477 | 70560944 | 79178104 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/344/334420%20-%20DR4339PR%20-%20FEMA%20SOW%20%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%201.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-08-18 14:10 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 1 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 334420RFI344 | 334420 |  |  | 0
334443 | 107520 | 104883530 | 51954249 | 8863340 |  | 52929281 | 7448718 | 44505531 | 104883530 | 113746870 | 2025-01-31 | 2025-07-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/343/334443-DR4339PR-DSOW-CAGUAS%202.pdf?web=1 |  | 2025-08-19 12:57 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 2 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | 334443RFI343 | 334443 |  |  | 0
334452 | 107521 | 79565087 | 20046792 | 6235944 |  | 39516463 | 2749314 | 17297478 | 59563255 | 65799199 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/342/DR4339PR-334452-%2010147%20Caguas%20ST%20Group%203%20DSOW%20R1.pdf?web=1 |  | 2025-08-18 13:46 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 3 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1.3358 | 1 | 2025-08-15 | 334452RFI342 | 334452 |  |  | 0
334468 | 10679 | 1217429 | 0 | 242850 |  | 1217429 | 0 | 0 | 1217429 | 1460279 |  |  | 2022-07-13 | 2024-08-30 | 1217429 | 1217429 | 1217429 | 1217429 |  |  |  | 1217429 | 1217429 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/341/334468-DR4339PR-DSOW%20-TL%202200-Transmission%20Priority%20Pole%20Replacement-%20V0%20(4).pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2200 | 2026-01-29 09:16 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  | 242850 |  | 1 | 1 | 1 |  | 334468RFI341 | 334468 |  |  | 0
334469 | 107522 | 11510000 | [5 empty] | 0 | 11510000 | 11510000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/340/334469-DR4339PR-10075-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%208900%20Monacillos%20TC%20to%20Adm%20Signed%20-%20Copy.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 6/26/2024. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Line 8900 Monacillos TC to Adm. Tribunal Apelaciones | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 334469RFI340 | 334469 |  |  | 0
334470 | 11708 | 113330000 |  | 2848650.5 |  | 51867865.42 | 0 | 0 | 51867865.42 | 54716515.92 |  |  | 2025-11-05 |  | 47112099.92 | 47112099.92 |  |  |  | 965924.9 |  | 47112099.92 | 47112099.92 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/339/PW%2011708%20PRJ_MultiVersionReport_334470_20251105.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 3100 . 8/7/2025 - RFI response received on 08/06/2025, under EHP specialist revision. The expected completion date (ECD) for the response revision is 08/13/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2025-12-01 16:32 | 2023-08-14 11:10 | Jahdiel Franqui | Line 3100 Monacillos TC to Daguao TC | Marlina Crespo | 0 Months |  | 2747003.78 | 0 | 1 | 2.185 | 1 |  | 334470RFI339 | 334470 | 965924.9 |  | 965924.9
334471 | 107523 | 62894812 | 26997816 | 7053158 |  | 35896996 | 4433509 | 22564307 | 62894812 | 69947970 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/338/334471-DR4339PR-%20DSOW-San%20Juan%20STG%201.pdf?web=1 |  | 2025-08-18 13:33 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ San Juan Short Term Group 1 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 334471RFI338 | 334471 |  |  | 0
334472 | 107524 | 27652844 | 5366655 | 3690321 |  | 15093429 | 1052352 | 4314303 | 20460084 | 24150405 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/337/DR4339PR-334472-10142%20San%20Juan%20ST%20Group%202%20DSOW%20R1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ San Juan Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1 | 1.3516 | 1 | 2025-08-15 | 334472RFI337 | 334472 |  |  | 0
334473 | 107525 | 61103928 | 1173247.16 | 1298493.93 |  | 16234566.74 | 135257.91 | 1037989.25 | 17407813.9 | 18706307.83 | 2025-04-30 | 2025-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/336/334473-DR4339PR-Feeders%20Rebuild%201806-02%20Detailed%20Scope%20of%20Work%20Rev.%200.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-11-20 13:01 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 1 | Marlina Crespo |  |  |  |  | 1 | 3.5101 | 1 | 2025-08-15 | 334473RFI336 | 334473 | 1060714.92 | 202401.99 | 1263116.91
334474 | 107526 | 4337037 | 659178 | 384975 |  | 804315 | 213377 | 445801 | 1463493 | 1848468 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/335/DR4339-PR-334474-DSOW_10136%20-%20BAYAMON%20STG2_R1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-08-20 11:17 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 2 | Maria Mujica Gonzalez |  |  |  |  | 1 | 2.9635 | 1 | 2025-08-19 | 334474RFI335 | 334474 |  |  | 0
334475 | 107527 | 67962252 | 17884283 | 4579075 |  | 45856819 | 1623714 | 16260569 | 63741102 | 68320177 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/334/DR4339PR-334475-Detail%20SOW%20-%20Bayamon%20Short%20Term%20Group%203_FINAL%20(11-28-23)_Rev%201-1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-08-20 11:22 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 3 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1.0662 | 1 | 2025-08-19 | 334475RFI334 | 334475 |  |  | 0
334476 | 107528 | 40500000 | 18767542 | 4031089 |  | 14254294 | 3637670 | 15129872 | 33021836 | 37052925 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/333/DR4339PR-334476%20-%20FEMA%20Detailed%20Scope%20of%20Work%20-%20Carolina%20Short%20Term%20Group%202%20-%20signed.pdf?web=1 |  | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Carolina Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1 | 1.2265 | 1 | 2025-08-19 | 334476RFI333 | 334476 |  |  | 0
334477 | 107529 | 39416251 | 23907802 | 2623895 |  | 20298233 | 2736726 | 21171076 | 44206035 | 46829930 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/332/DR4339PR-334477-10137-Carolina%20Short%20Term%20Group%203%20DSOW%20R1%20(1).pdf?web=1 |  | 2025-08-20 11:40 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Carolina Short Term Group 3 | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 0.89165 | 1 | 2025-08-19 | 334477RFI332 | 334477 |  |  | 0
334482 | 11450 | 0 | [5 empty] | 0 | 90440000 | 90440000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/331/334482-DR4339PR-10083-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%203000%20Monacillos%20TC%20to%20Juncos%20TC%20Signed%20-%20Copy.pdf?web=1 | 9/12/2024 - GP notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Line 3000 Monacillos TC to Juncos TC | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 |  | 334482RFI331 | 334482 |  |  | 0
334488 | 10635 | 153743 | 10826 | 19965 |  | 134417 | 0 | 10826 | 145243 | 165208 |  |  | 2022-05-26 | 2024-08-30 | 153743 | 142917 | 153743 | 142917 |  |  |  | 153743 | 142917 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/330/PRJ_Report_334488_20250213.pdf?web=1 |  | 2026-02-17 11:32 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 11465 |  | 1 | 1.0585 | 1 |  | 334488RFI330 | 334488 |  |  | 0
334491 | 107530 | 38058553 | 13582684 | 3119148 |  | 16427785 | 2165073 | 11417611 | 30010469 | 33129617 | 2025-01-31 | 2025-07-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/329/DR4339PR-334491-10149-Caguas%20Short%20Term%20Group%205%20DSOW%20R1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-08-20 11:45 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 5 | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 1.2682 | 1 | 2025-08-19 | 334491RFI329 | 334491 |  |  | 0
334497 | 107531 | 83151265 | 22180767 | 6980220 |  | 60970498 | 2278513 | 19902254 | 83151265 | 90131485 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/328/334497-DR4339PR-%20DSWOR-%20Caguas%20Short%20Term%20Group%206-Signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-08-18 15:13 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 6 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 334497RFI328 | 334497 |  |  | 0
334518 | 107532 | 36582202 | 7784267 | 1942279 |  | 10283602 | 1224114 | 6560153 | 18067869 | 20010148 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/327/DR4339PR-334518-10151-Caguas%20Short%20Term%20Group%207%20DSOW.pdf?web=1 |  | 2025-08-18 15:13 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 7 | Ashleah Dingle |  |  |  |  | 1 | 2.0247 | 1 | 2025-08-15 | 334518RFI327 | 334518 |  |  | 0
334527 | 10701 | 123721 | 14874 |  |  | 102513 | 0 | 14874 | 117387 | 117387 |  |  | 2022-06-10 | 2024-08-30 | 123721 | 108847 | 123721 | 108847 |  |  |  | 123721 | 108847 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/326/PRJ_Report_334527_20250213.pdf?web=1 |  | 2026-02-17 11:32 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 8540 |  | 1 | 1.054 | 1 |  | 334527RFI326 | 334527 |  |  | 0
335168 | 9510 | 1086406842.43 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 2021-10-07 | 2023-06-21 | 1086406842.43 |  | 486406842.43 | 486406842.43 | 1058513052.43 |  | 1058513052.43 | 1058513052.43 | 1058513052.43 | 2027-09-20 |  |  | 2025-09-19 11:58 | 2023-08-14 11:10 | Jahdiel Franqui |  | Gabriel Licha |  |  | 0 |  | 1 | #DIV/0! | #DIV/0! |  | 335168RFI325 | 335168 |  |  | 0
435257 | 107545 | 924000 | [5 empty] | 0 | 924000 | 924000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/324/FEMA%20Scope%20of%20Work%20Line%203000%20Monacillos%20TC%20-%20Bairoa%20TO.DOC%20(1).pdf?web=1 | 9/12/2024 - GP Notes "The project was withdrawn with the comment "8/15/2024 - Applicant requested to withdraw the reference project. Please see document with the naming convention "435257-DR4339PR-Withdrawn Confirmation.msg"". | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 435257RFI324 | 435257 |  |  | 0
436616 | 107551 | 51555365 | 14494388 | 2468970 |  | 24725318 | 1315945 | 13178443 | 39219706 | 41688676 | 2025-05-31 | 2025-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/323/436616-DR4339PR-Detail%20SOW%20-%20Arecibo%20Short%20Term%20Group%201_FINAL%20(11-28-2023)%20Rev%201%20(2).pdf?web=1 |  | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Arecibo Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1.3145 | 1 | 2025-08-15 | 436616RFI323 | 436616 |  |  | 0
542517 | 10515 | 8810325.37 | 181658.08 | 2004233 |  | 8628668 | 0 | 181658.08 | 8810326.08 | 10814559.08 |  |  | 2022-05-20 | 2024-08-30 | 8810325.37 | 8628667.29 | 8810325.37 | 8628667.29 |  |  |  | 8810325.37 | 8628667.29 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/322/542517-10515%20Luquillo%20Streetlights%20Detailed%20SOW%20Rev.3.pdf?web=1 |  | 2026-02-17 11:33 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2004233.23 |  | 1 | 1 | 1 |  | 542517RFI322 | 542517 |  |  | 0
542687 | 10521 | 10704668.57 | 426332 | 2512854 |  | 10278336 | 0 | 426332 | 10704668 | 13217522 |  |  | 2022-05-20 | 2024-08-30 | 10704668.57 | 10278336.09 | 10704668.57 | 10278336.09 |  |  |  | 10704668.57 | 10278336.09 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/321/PRJ_Report_542687_20240918.pdf?web=1 |  | 2026-02-17 11:34 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2512853.73 |  | 1 | 1 | 1 |  | 542687RFI321 | 542687 |  |  | 0
542688 | 10539 | 18571716.38 | 807222 | 4104786 |  | 17764494 | 0 | 807222 | 18571716 | 22676502 |  |  | 2022-05-05 | 2024-08-30 | 18571716.38 | 17764494.34 | 18571716.38 | 17764494.34 |  |  |  | 18571716.38 | 17764494.34 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/320/PRJ_Report_542688_20240918.pdf?web=1 |  | 2026-02-17 11:35 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 4104785.76 |  | 1 | 1 | 1 |  | 542688RFI320 | 542688 |  |  | 0
542690 | 10499 | 6443757.4 | 243880.33 | 1530438 |  | 6199878 | 243880.33 | 0 | 6443758.33 | 7974196.33 |  |  | 2022-05-05 |  | 6443757.4 | 6199877.07 | [5 empty] | 6443757.4 | 6199877.07 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/319/Revised%20FEMA%20SOW%20-%20542690-DR4339PR-Detailed%20SOW%20Maunabo%20Rev0%20-%20signed%20-%20DSOW.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1530438.49 |  | 1 | 1 | 1 |  | 542690RFI319 | 542690 |  |  | 0
542756 | 10538 | 10058046 | 370808 | 2237386 |  | 9687238 | 0 | 370808 | 10058046 | 12295432 |  |  | 2022-05-26 |  | 10058046 | 9687238 | [5 empty] | 10058046 | 9687238 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/318/PRJ_Report_542756_20240918.pdf?web=1 |  | 2025-07-24 14:56 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 2237386 |  | 1 | 1 | 1 |  | 542756RFI318 | 542756 |  |  | 0
542758 | 11385 | 3412576 | 439541 | 723314 |  | 2973035 | 27113 | 412428 | 3412576 | 4135890 |  |  | 2023-07-07 |  | 3412576 | 2973035 | [5 empty] | 3412576 | 2973035 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/317/Revised%20FEMA%20SOW%20-%20542758-DR4339PR-%200%20FEMA%20DSOW%20Group%20B%20Minor%20Repairs%20(43001-CP-SOW-0012_Rev5)%20(2023-05-03)%20-%20signed.pdf?web=1 |  | 2025-09-08 13:23 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  | 152806 | 14467 | 1 | 1 | 1 |  | 542758RFI317 | 542758 |  |  | 0
542762 | 10690 | 767868 | 157420 |  |  | 661242 | 0 | 157420 | 818662 | 818662 |  |  | 2022-06-03 | 2024-08-30 | 767868 | 610448 | 767868 | 610448 |  |  |  | 767868 | 610448 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/316/PRJ_Report_542762_20250213.pdf?web=1 |  | 2026-02-17 11:41 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 50794 |  | 1 | 0.93795 | 1 |  | 542762RFI316 | 542762 |  |  | 0
546370 | 10858 | 4971175.09 | 488203 | 996359 |  | 4482973 | 0 | 488203 | 4971176 | 5967535 |  |  | 2024-02-13 | 2024-08-30 | 4971175.09 | 4482972.51 | 4971175.09 | 4482972.51 |  |  |  | 4971175.09 | 4482972.51 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/315/PRJ_Report_546370_20240213.pdf?web=1 |  | 2026-02-17 12:12 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Marlina Crespo |  |  | 996359.11 |  | 1 | 1 | 1 |  | 546370RFI315 | 546370 |  |  | 0
546371 | 11478 | 3032891.2 | 384632.14 | 646473 |  | 2648259 | 25197.64 | 359434.5 | 3032891.14 | 3679364.14 |  |  | 2023-08-22 |  | 3032891.2 | 2648259.06 | [5 empty] | 3032891.2 | 2648259.06 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/314/546371-DR4339PR-00%20FEMA%20DSOW%20for%20Sub.%20Minor%20Repairs%20-Group%20C%20(43001-CP-SOW-0009_Rev7)%20(2023-06-26)%20-%20signed.pdf |  | 2025-07-24 14:47 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Jose J Ramos Figueroa |  |  | 173985.91 |  | 1 | 1 | 1 |  | 546371RFI314 | 546371 |  |  | 0
546374 | 107556 | 38107125 | 12777559 | 2091400 |  | 18966760 | 1260325 | 11517234 | 31744319 | 33835719 | 2025-05-31 | 2025-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/313/DR4339PR-546374-San%20Juan%20Short%20Term%20Group%203%20DSOW.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders - San Juan Short Term Group 3 | Ashleah Dingle | 0 Months |  |  |  | 1 | 1.2004 | 1 | 2025-08-15 | 546374RFI313 | 546374 |  |  | 0
546386 | 107558 | 28991235 | 23252037 | 825193 |  | 5739198 | 2922954 | 20329083 | 28991235 | 29816428 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/312/546386-DR4339PR-DSOW%20EL%20YUNQUE%20SUPPLY%20-%20signed.pdf?web=1 |  | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | El Yunque 2305-01 Supply | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 546386RFI312 | 546386 |  |  | 0
547160 | 107689 | 55370000 | [5 empty] | 0 | 55370000 | 55370000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/311/921046-DR4339PR-10076-EN-SOW-0001_Rev0%20-%20Line%201200%20Mayaguez%20GP%20to%20Yauco%202%20HP.pdf?web=1 |  | 2025-08-19 11:27 | 2023-08-14 11:10 | Jahdiel Franqui | Line 1200 Mayaguez GP to Yauco 2 HP | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | 547160RFI311 | 547160 |  |  | 0
547187 | 107690 | 330300000 | 308929.24 | 2069220.14 |  | 6551618.4 | 66626.67 | 242302.57 | 6860547.64 | 8929767.78 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/310/547187-DR4339PR%20-%20%20Substation%20Component%20Replacement%20Program%20Group%201%20Detail%20Scope%20of%20Work%20signed%20(3.7.2025).pdf?web=1 |  | 2026-02-25 14:34 | 2023-08-14 11:10 | Jahdiel Franqui | Arecibo Pueblo 8002 Relocation | Ashleah Dingle |  |  |  |  | 1 | 48.1448 | 1 |  | 547187RFI310 | 547187 | 2233992.76 | 99234.74 | 2333227.5
547221 | 107692 | 39980000 | [5 empty] | 0 | 39980000 | 39980000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/309/547221%20-%20DR4339PR%20%20Line%203600%20Monacillos%20TC%20to%20Martin%20Pe%C3%B1a%20TC%20(Transmission).pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 9/9/2024. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Line 3600 Monacillos TC to Martin Peña TC | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 547221RFI309 | 547221 |  |  | 0
547226 | 11689 | 13810000 | [5 empty] | 0 | 13810000 | 13810000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/308/547226%20DR4339PR%20Line%2011400%20Barceloneta%20TC%20to%20Florida%20TO.pdf?web=1 |  | 2025-08-19 11:35 | 2023-08-14 11:10 | Jahdiel Franqui | Line 11400 Barceloneta TC to Florida TO | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | 547226RFI308 | 547226 |  |  | 0
547241 | 11448 | 0 | 5628609 | 1268607 |  | 9655829 | 653626 | 4974983 | 15284438 | 16553045 | 2024-12-31 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/307/547241-DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Tallaboa%205402%20Substation%20-%20signed%20(1).pdf?web=1 |  | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Tallaboa 5402 | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 | 2025-08-18 | 547241RFI307 | 547241 |  |  | 0
547243 | 107693 | 21850323 | 6952342.26 | 1400260.82 |  | 12496184.94 | 700164.05 | 6252178.21 | 19448527.2 | 20848788.02 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/306/547243-DR43339PR-00%20FEMA%20DSOW%20Egozcue%20MC%201109%20020924%20F.pdf?web=1 |  | 2026-02-24 13:45 | 2023-08-14 11:10 | Jahdiel Franqui | Egozcue - 1109 | Ashleah Dingle |  |  |  |  | 1 | 1.1235 | 1 | 2025-08-15 | 547243RFI306 | 547243 |  |  | 0
547247 | 107694 | 30700000 | 84733286.06 | 319703.09 |  | 5143802.81 | 2090449.36 | 82642836.7 | 89877088.87 | 90196791.96 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/305/547247%20-%20DR4339PR%20-%20DSOW%20Cambalache%20TC%20Rev%200.pdf?web=1 |  | 2026-02-24 13:46 | 2023-08-14 11:10 | Jahdiel Franqui | Cambalache TC Relocation | Ashleah Dingle | 0 Months |  |  |  | 1 | 0.34158 | 4 | 2025-08-15 | 547247RFI305 | 547247 |  |  | 0
547248 | 107695 | 1700000 | [5 empty] | 0 | 1700000 | 1700000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/304/921822-DR4339PR-10109-EN-SOW-0001_Rev0%20-%20Canas%20TC.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Canas TC | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 547248RFI304 | 547248 |  |  | 0
547251 | 11807 | 21470000 |  | 433482.47 |  | 6482242.86 |  | 0 | 6482242.86 | 6915725.33 |  |  | 2026-02-20 |  | 50289473.68 | 50289473.68 |  |  |  | 975659.88 |  | 50289473.68 | 50289473.68 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/303/PW%2011807%20PRJ_MultiVersionReport_547251_20260220.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2400 8/8/2025 - Field EHP: In review. Expected Completion Date (ECD) 8/22/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-23 09:58 | 2023-08-14 11:10 | Jahdiel Franqui | Line 2400 Dos Bocas HP to America Apparel | Ashleah Dingle | 0 Months |  | 3753435.29 |  | 1 | 3.3121 | 1 |  | 547251RFI303 | 547251 | 8180.36 | 0 | 8180.36
547259 | 11480 | 0 | 55843908 | 6838079 |  | 64136647 | 5366230 | 50477678 | 119980555 | 126818634 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/302/547259-DR4339PR-TL-2700%20DSOW-38kV-Victoria%20TC%20to%20Quebradillas%20Sect%2001122024.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2700 | 2025-08-19 11:37 | 2023-08-14 11:10 | Jahdiel Franqui | Line 2700 Victoria TC to Quebradillas Sect. | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-18 | 547259RFI302 | 547259 |  |  | 0
547269 | 11481 | 0 | 11466633 | 3954335 |  | 32159582 | 1250116 | 10216517 | 43626215 | 47580550 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/301/547269-DR4339PR-TL-2800%20Aguadilla%20Hosp%20to%20T-BONE%2016APR2024t%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2800 | 2025-08-20 11:58 | 2023-08-14 11:10 | Jahdiel Franqui | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Marlina Crespo |  |  |  |  | 1 | 0 | 5 | 2025-08-18 | 547269RFI301 | 547269 |  |  | 0
547271 | 107698 | 17000000 | [5 empty] | 0 | 17000000 | 17000000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/300/921686%20DR4339PR-%20San%20Jose%20Relocation%20SOW%20and%20Cost%20Estimate.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Pending Task Order signature to complete Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | San Jose Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 547271RFI300 | 547271 |  |  | 0
547273 | 107699 | 16300000 | [5 empty] | 0 | 16300000 | 16300000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/299/547273%20DR4339PR%20Charco%20Hondo%208008%20Relocation%20SOW%20and%20Cost%20Estimate%20(1).pdf?web=1 |  | 2025-08-18 14:34 | 2023-08-14 11:10 | Jahdiel Franqui | Charco Hondo 8008 Relocation | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 547273RFI299 | 547273 |  |  | 0
547342 | 107700 | 58610000 | [5 empty] | 0 | 58610000 | 58610000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/298/921980-DR4339PR-10088-EN-SOW-0001_Rev0%20Line%201500%20Mayaguez%20GP%20to%20GOAB%201515.pdf?web=1 | 9/12/2024 - GP Notes "The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Line 1500 Mayaguez GP to GOAB 1515 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 547342RFI298 | 547342 |  |  | 0
547343 | 107701 | 5500000 | 54844288.98 | 606808.32 |  | 6239636.58 | 4859932.94 | 49984356.04 | 61083925.56 | 61690733.88 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/297/547343%20-%20DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20VIctoria%20TC%20Rev00%20-%20signed.pdf?web=1 |  | 2026-02-24 13:46 | 2023-08-14 11:10 | Jahdiel Franqui | Victoria TC 7008 | Ashleah Dingle |  |  |  |  | 1 | 0.09004 | 5 | 2025-08-15 | 547343RFI297 | 547343 |  |  | 0
547344 | 107702 | 29100000 | 42895135.02 | 677999.83 |  | 8196442.68 | 3277151.71 | 39617983.31 | 51091577.7 | 51769577.53 | 2025-10-31 | 2026-03-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/296/547344-FEMA%20Detailed%20Scope%20of%20Work%20for%20Acacias%20TC%20rev%201%20-%20signed.pdf?web=1 | 2/28/2024: QC Review Complete | 2026-02-24 13:46 | 2023-08-14 11:10 | Jahdiel Franqui | Acacias 6801 TC Relocation | Ashleah Dingle |  |  |  |  | 1 | 0.56957 | 3 | 2025-08-15 | 547344RFI296 | 547344 |  |  | 0
547350 | 11854 | 5390000 | [5 empty] | 0 | 5390000 | 5390000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/295/547350%20-%20DR4339PR%20-%20%20FAASt%20-%20Line%2013300%20Bayam%C3%B3n%20TC%20to%20Plaza%20del%20Sol%20(Transmission)%20FEMA%20SOW%20CE.pdf?web=1 |  | 2025-08-20 11:58 | 2023-08-14 11:10 | Jahdiel Franqui | Line 13300 Bayamon TC to Plaza del Sol | Marlina Crespo |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | 547350RFI295 | 547350 |  |  | 0
548393 | 107705 | 9226902 | [5 empty] | 0 | 9226902 | 9226902 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/294/548393%20DR4339PR%20Arecibo%20Region%20Repairs%20(Building).pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Arecibo Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 548393RFI294 | 548393 |  |  | 0
548440 | 107707 | 13346360 | [5 empty] | 0 | 13346360 | 13346360 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/293/548440-DR4339PR--FA-SOW-0001_Rev0-%20Mayaguez%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Mayaguez Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 548440RFI293 | 548440 |  |  | 0
548596 | 107708 | 2478182 | [5 empty] | 0 | 2478182 | 2478182 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/292/548596-DR4339PR-10033-FA-SOW-0001_Rev0-San%20German%20ESC.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | San German Electrical Service Center | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 548596RFI292 | 548596 |  |  | 0
548598 | 11494 | 0 | 15963429 | 4765220 |  | 37425267 | 1717803 | 14245626 | 53388696 | 58153916 | 2024-10-31 | 2024-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/291/548598-DR4339PR-FEMA-115kV-DSOW%20TL-36200%20Fajardo%20TC%20to%20Rio%20Blanco%20HP%20%2018APR2024%20-%20signed.pdf?web=1 |  | 2025-08-19 11:42 | 2023-08-14 11:10 | Jahdiel Franqui | Line 36200 Fajardo to Rio Blanco | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-18 | 548598RFI291 | 548598 |  |  | 0
549715 | 11682 | 2871257.17 | 288124 | 580189 |  | 2583134 | 0 | 288124 | 2871258 | 3451447 | 2024-06-30 | 2024-07-31 | 2024-04-12 | 2024-08-30 | 2871257.17 | 2583133.54 | 2871257.17 | 2583133.54 |  |  |  | 2871257.17 | 2583133.54 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/290/PW%2011682%20PRJ_Report_549715_20240412.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-17 12:13 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Marlina Crespo |  |  | 580188.69 |  | 1 | 1 | 1 |  | 549715RFI290 | 549715 |  |  | 0
549725 | 11707 | 4503783.21 | 579768 | 818227 |  | 3924016 | 22126.13 | 557641.87 | 4503784 | 5322011 | 2024-06-30 | 2024-07-31 | 2024-05-10 |  | 4503783.21 | 3924015.69 | [5 empty] | 4503783.21 | 3924015.69 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/289/PRJ_Report_549725_20240510.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-24 14:43 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Jose J Ramos Figueroa |  |  | 98349.5 | 11328.47 | 1 | 1 | 1 |  | 549725RFI289 | 549725 |  |  | 0
549764 | 11350 | 2383692.99 | 224680.68 | 529771 |  | 2159012 | 0 | 224680.68 | 2383692.68 | 2913463.68 |  |  | 2023-06-16 | 2024-08-30 | 2383692.99 | 2159012.31 | 2383692.99 | 2159012.31 |  |  |  | 2383692.99 | 2159012.31 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/288/549764-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20Physical%20Security%20Group%202%20(40000-CP-SOW-0012Rev2%20)(2023-03-23)%20-%20signed%20(1).pdf?web=1 |  | 2026-02-17 12:14 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Marlina Crespo |  |  | 529771.49 |  | 1 | 1 | 1 |  | 549764RFI288 | 549764 |  |  | 0
549768 | 107709 | 1200000 | [5 empty] | 0 | 1200000 | 1200000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/287/549768-DR4339PR-Physical%20Security%2040000-EN-SOW-0007_Rev0.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 549768RFI287 | 549768 |  |  | 0
550019 | 107710 | 21404169 | 4035264 | 2943392 |  | 19190123 | 488834 | 3546430 | 23225387 | 26168779 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/286/550019-DR4339PR%20DSOW-TL600%20Caguas%20TC%20to%20Gautier%20Ben%C3%ADtez%20Sect%203-15-24%20(1)%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 600 | 2025-08-19 11:48 | 2023-08-14 11:10 | Jahdiel Franqui | Line 600 Caguas TC to Gautier Benitez Sect. | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.92159 | 1 | 2025-08-18 | 550019RFI286 | 550019 |  |  | 0
550060 | 107711 | 14472109 | [5 empty] | 0 | 14472109 | 14472109 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/285/550060%20-DR4339PR%20-%20Caguas%20Region%20Repairs%20Initial%20SOW%20CE.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Caguas Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 550060RFI285 | 550060 |  |  | 0
550070 | 107712 | 22330000 | [5 empty] | 0 | 22330000 | 22330000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/284/550070%20-%20DR4339PR%20-%20Line%204000%20Comerio%20HP%20to%20Escuela%20Francisco%20Morales%20Initial%20SOW%20CE.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 7/18/2024. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Line 4000 Comerio HP to Escuela Francisco Morales | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 550070RFI284 | 550070 |  |  | 0
550099 | 107713 | 14335434 | 6851320.87 | 1112050.13 |  | 8804423.21 | 762291.03 | 6089029.84 | 15655744.08 | 16767794.21 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/283/550099-4339%20DR-PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Esc%20Industrial%20Miguel%20Such%201423_Rev3_03262024%20-%20signed%20(1).pdf?web=1 |  | 2026-02-06 13:25 | 2023-08-14 11:10 | Jahdiel Franqui | Esc. Industrial M. Such - 1423 | Jason Fournier |  |  |  |  | 1 | 0.91567 | 1 | 2025-08-15 | 550099RFI283 | 550099 |  |  | 0
550106 | 107714 | 11639958 | 1101071.22 | 1478605.83 |  | 9827316 | 143115.56 | 957955.66 | 10928387.22 | 12406993.05 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/282/55016-DR43339PR-00%20FEMA%20DSOW%20for%20Conquistador%20CH%20Rev%200.1%2004.01.2024%20-%20signed.pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Conquistador - CH | Jason Fournier |  |  |  |  | 1 | 1.0651 | 1 |  | 550106RFI282 | 550106 |  |  | 0
550162 | 11813 | 51763597 | 6718315 | 4182974 |  | 40767573 | 625188 | 6093127 | 47485888 | 51668862 | 2024-12-31 | 2025-03-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/281/550162%204339%20DR-PR%20DETAILED%20SCOPE%20OF%20WORKS%2011-27-2023%20-%20Copy%20-%20signed.pdf?web=1 |  | 2025-08-18 14:24 | 2023-08-14 11:10 | Jahdiel Franqui | Berwind TC - 1336 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1.0901 | 1 | 2025-08-15 | 550162RFI281 | 550162 |  |  | 0
550498 | 107717 | 5844709 | [5 empty] | 0 | 16300000 | 16300000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/280/921048-DR4339PR-10026-EN-SOW-0001_Rev0%20-%20Pampanos%20Sect%20Relocation.pdf?web=1 |  | 2025-08-18 14:23 | 2023-08-14 11:10 | Jahdiel Franqui | Pampanos Relocation | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.35857 | 4 | 2025-08-15 | 550498RFI280 | 550498 |  |  | 0
550500 | 107718 | 20294279 | [5 empty] | 0 | 20294279 | 20294279 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/279/550500-DR4339PR-10040-FA-SOW-0001_Rev0-Ponce%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Ponce Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 550500RFI279 | 550500 |  |  | 0
550771 | 107719 | 2500000 | [5 empty] | 0 | 2500000 | 2500000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/278/550771%20-%20DR4339%20-%20Caguas%20TC%20(Substation)%20Initial%20SOW.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Caguas TC | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 550771RFI278 | 550771 |  |  | 0
550894 | 107720 | 26709229 | 28669863 | 88908 |  | 884190 | 2619452 | 26050411 | 29554053 | 29642961 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/277/550894-DR4339PR%20-%20Baldrich%201422%20%20FEMA%20DSOW%20Rev3.pdf?web=1 |  | 2026-02-24 13:46 | 2023-08-14 11:10 | Jahdiel Franqui | Baldrich - 1422 | Ashleah Dingle |  |  |  |  | 1 | 0.90374 | 1 | 2025-08-15 | 550894RFI277 | 550894 |  |  | 0
550896 | 10837 | 690703 | 17395.24 | 86095.96 | 93552 | 1163826.56 | 1139.54 | 16255.7 | 1181221.8 | 1267317.76 |  |  | 2022-08-08 | 2025-12-18 | 690703 | 690703 | 1070274.56 | 1070274.56 |  |  |  | 1070274.56 | 1070274.56 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/276/550896-DR4339PR-Detailed%20SOW%20-%20Line%206700%20Martin%20Pe%C3%B1a%20TC%20%E2%80%93%20Seboruco%20TO%20Rev.1_20251218_signed.pdf?web=1 |  | 2026-02-17 12:14 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Marlina Crespo |  |  | 133416 |  | 1 | 0.58474 | 3 |  | 550896RFI276 | 550896 |  |  | 0
550902 | 11688 | 2320000 | [5 empty] | 0 | 2320000 | 2320000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/275/550902-DR4339PR-10092-EN-SOW-0001_Rev0%20-%20Line%209700%20Palo%20Seco%20SP%20to%20Bay%20View%20Sect(1).pdf?web=1 |  | 2025-08-19 11:56 | 2023-08-14 11:10 | Jahdiel Franqui | Line 9700 Palo Seco SP to Bay View Sect. | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | 550902RFI275 | 550902 |  |  | 0
550910 | 10841 | 6691229.18 | 665958.96 | 1278328 |  | 6025270 | 0 | 665958.96 | 6691228.96 | 7969556.96 |  |  | 2023-05-04 | 2024-08-30 | 6691229.18 | 6025270.22 | 6691229.18 | 6025270.22 |  |  |  | 6691229.18 | 6025270.22 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/274/550910-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Physical%20Security%20-%20Group%201%20(2023-03-17)%20-%20signed.pdf?web=1 |  | 2026-02-17 12:15 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Marlina Crespo |  |  | 1278327.97 |  | 1 | 1 | 1 |  | 550910RFI274 | 550910 |  |  | 0
550950 | 11557 | 88096455.73 | 0 | 2179830 |  | 13072870.61 | 0 | 0 | 13072870.61 | 15252700.61 |  |  | 2023-12-19 | 2025-09-17 | 88096455.73 | 88096455.73 | 58195134.17 | 88096455.73 | 58195134 | 42974192.2 | 58195134 | 58195134 | 58195134 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/273/PW%2011557%20PRJ_MultiVersionReport_550950_20250917.pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Monacillo TC | Jason Fournier |  |  | 6623439.52 | 0 | 1 | 6.7389 | 1 |  | 550950RFI273 | 550950 | 42974192.2 |  | 42974192.2
550972 | 107721 | 31400000 | [5 empty] | 0 | 31400000 | 31400000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/272/550972-DR4339PR-10019-EN-SOW-0001_Rev0%20-%20Fonalledas%20GIS%20Rebuilt%201401%201421(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Fonalledas GIS Rebuilt 1401 1421 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 550972RFI272 | 550972 |  |  | 0
550980 | 107722 | 20916860 | 8962734.08 | 1608592.37 |  | 10128904.68 | 1227475.29 | 7735258.79 | 19091638.76 | 20700231.13 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/271/550980-DR4339PR-FEMA%20DSOW%20for%20Parques%20y%20Recreos%20(Final)%202.16.2024%20-%20signed.pdf?web=1 |  | 2026-02-06 13:25 | 2023-08-14 11:10 | Jahdiel Franqui | Parques y Recreos - 1002 | Jason Fournier |  |  |  |  | 1 | 1.0956 | 1 | 2025-08-15 | 550980RFI271 | 550980 |  |  | 0
550986 | 107723 | 14709154 | 5427167 | 1367924 |  | 9281987 | 697091 | 4730076 | 14709154 | 16077078 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/270/550986-4339%20DR-PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Condado%201133-6-30-2023%20signed%20(1).pdf?web=1 |  | 2026-02-24 13:46 | 2023-08-14 11:10 | Jahdiel Franqui | Condado - 1133 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 550986RFI270 | 550986 |  |  | 0
550998 | 107724 | 9900000 | [5 empty] | 0 | 9900000 | 9900000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/269/550998-DR4339PR-10022-EN-SOW-0001_Rev0%20-%20Santurce%20Planta%20(Sect)%201116(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Santurce Planta (Sect) 1116 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 550998RFI269 | 550998 |  |  | 0
551067 | 11687 | 3790000 | [5 empty] | 0 | 3790000 | 3790000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/268/551067-DR4339PR-10093-EN-SOW-0001_Rev0%20-%20Line%2011100%20Canovanas%20Sect.%20to%20GOAB%2011115.pdf?web=1 |  | 2025-08-19 12:08 | 2023-08-14 11:10 | Jahdiel Franqui | Line 11100 Canovanas Sect. to GOAB 11115 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | 551067RFI268 | 551067 |  |  | 0
551100 | 107725 | 16700000 | [5 empty] | 0 | 16700000 | 16700000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/267/551100-DR4339PR-10024-EN-SOW-0001_Rev0%20-%20Bayview%20Sectionalizer%201802%20Relocation.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Bayview Sectionalizer 1802 Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 551100RFI267 | 551100 |  |  | 0
551242 | 107726 | 15451305 | [5 empty] | 0 | 15451305 | 15451305 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/266/551242-DR4339PR-10036-FA-SOW-0001_Rev0-Bayamon%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Bayamon Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 551242RFI266 | 551242 |  |  | 0
551247 | 11570 | 0 | [5 empty] | 0 | 11170493 | 11170493 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/265/551247-DR4339PR-10035-FA-SOW-0001_Rev0-%20Palo%20Seco%20South%20Building%20Repairs.pdf?web=1 |  | 2025-08-12 10:29 | 2023-08-14 11:10 | Jahdiel Franqui | Palo Seco South Building Repairs | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-11 | 551247RFI265 | 551247 |  |  | 0
551260 | 107727 | 22373983 | 10941966.54 | 2334521.27 |  | 20046985.57 | 1141020.24 | 9800946.3 | 30988952.11 | 33323473.38 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/264/551260-DR43339PR-FEMA%20DSOW%20for%20Guaynabo%20Pueblo%20Rev.%207%20signed%20(6.5.2025).2025)?web=1 | 3/27/2024: QC Review Complete | 2025-11-20 12:52 | 2023-08-14 11:10 | Jahdiel Franqui | Guaynabo Pueblo Substation | Marlina Crespo |  |  |  |  | 1 | 0.722 | 2 | 2025-08-15 | 551260RFI264 | 551260 | 10219258.33 | 6990448.48 | 17209706.81
551827 | 107732 | 31028730 | [5 empty] | 0 | 31028730 | 31028730 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/263/551827-DR4339PR-10038-FA-SOW-0001_Rev0-%20San%20Juan%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | San Juan Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 551827RFI263 | 551827 |  |  | 0
551861 | 11372 | 4133339.83 | 436383.23 | 844837 |  | 3696956 | 73108.14 | 363275.09 | 4133339.23 | 4978176.23 |  |  | 2023-06-16 |  | 4133339.83 | 3696956.6 | [5 empty] | 4133339.83 | 3696956.6 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/262/551861-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Physical%20Security%20-%20Group%203%20(40000-CP-SOW-0009Rev5)(2023-04-27)%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Rey Roldan Rodríguez |  |  | 844836.71 |  | 1 | 1 | 1 |  | 551861RFI262 | 551861 |  |  | 0
551911 | 11434 | 0 | [5 empty] | 0 | 5050000 | 5050000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/261/551911%20-%20DR4339PR%20-%20Line%209100%20Guaraguao%20TC%20to%20Bayamon%20Pueblo%20Sect.%20SOW%20-%20CE.pdf?web=1 |  | 2025-08-18 15:15 | 2023-08-14 11:10 | Jahdiel Franqui | Line 9100 Guaraguao TC to Bayamon Pueblo Sect. | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 | 2025-08-18 | 551911RFI261 | 551911 |  |  | 0
551912 | 107733 | 16844776 | 6035307 | 1382809 |  | 10809469 | 684505 | 5350802 | 16844776 | 18227585 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/260/551912-DR4339PR%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Puerto%20Nuevo%201520_Rev1_20230927%20(1).pdf?web=1 |  | 2026-02-06 13:25 | 2023-08-14 11:10 | Jahdiel Franqui | Puerto Nuevo - 1520 | Jason Fournier |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 551912RFI260 | 551912 |  |  | 0
551914 | 11470 | 0 | 5838512.8 | 1069270.88 |  | 8228185.09 | 671468.81 | 5167043.99 | 14066697.89 | 15135968.77 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/259/551914%20-%20DR4339PR%20-%20Caparra%201912%20and%201924%20DSOW%20Rev2%20(signed%203.10.2025).pdf?web=1 |  | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | Caparra 1911 & 1924 | Jason Fournier |  |  |  |  | 1 | 0 | 5 |  | 551914RFI259 | 551914 |  |  | 0
551916 | 107734 | 40100000 | [5 empty] | 0 | 40100000 | 40100000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/258/551916%20-%20DR4339PR%20-%20Dorado%20TC%20Relocation%20(Substation)%20SOW%20CE.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:52 | 2023-08-14 11:10 | Jahdiel Franqui | Dorado TC Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 551916RFI258 | 551916 |  |  | 0
551918 | 11409 | 0 | 6048401 | 1241556 |  | 11476729 | 590443 | 5457958 | 17525130 | 18766686 | 2025-12-31 | 2025-02-28 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/257/551918-DR4339-PR%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Crematorio%201512%20Substation%20(1).pdf?web=1 |  | 2025-08-18 14:12 | 2023-08-14 11:10 | Jahdiel Franqui | Crematorio - 1512 | Maria Mujica Gonzalez |  |  |  |  | 1 | 0 | 5 | 2025-08-15 | 551918RFI257 | 551918 |  |  | 0
551925 | 11537 | 7664336.14 | 2119378.2 | 1043403.42 | 0 | 7566499.86 | 266016.14 | 1853362.06 | 9685878.06 | 10729281.48 | 2024-06-30 | 2024-11-30 | 2024-11-01 |  | 7664336.14 | 5962412.52 | [5 empty] | 7664336.14 | 5962412.52 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/256/551925%20-%20DR4339PR%20-%20DSOW%20SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group%201-%20Rev%208%20-%20Version%201%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short & Long List | 2026-02-25 16:23 | 2023-08-14 11:10 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Marlina Crespo |  |  | 1248409.19 | 294727.35 | 1 | 0.79129 | 2 |  | 551925RFI256 | 551925 |  |  | 0
551926 | 107735 | 8456184.1 | 1073462.61 | 800287.41 |  | 5664186.55 | 134453.44 | 939009.17 | 6737649.16 | 7537936.57 | 2024-11-30 | 2025-02-28 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/255/551926%20-%20DR4339PR%20-%20DSOW%20SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group%202%20Rev%206%20signed.pdf?web=1 | 8/14/2025 - Field EHP: In review. Expected Completion Date (ECD) 08/21/2025. | 2026-02-06 12:55 | 2023-08-14 11:10 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Jason Fournier |  |  |  |  | 1 | 1.2551 | 1 |  | 551926RFI255 | 551926 |  |  | 0
551927 | 107736 | 26178032.7 | 3299617.88 | 2431898.51 |  | 16781290.09 | 409517.03 | 2890100.85 | 20080907.97 | 22512806.48 | 2025-04-30 | 2024-10-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/254/551927%20-%20DR4339PR%20-%20DSOW%20SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group%203%20Rev%206%20-%20Signed.pdf?web=1 | 4/17/2024: QC Review Complete | 2026-02-24 13:46 | 2023-08-14 11:09 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Ashleah Dingle |  |  |  |  | 1 | 1.3036 | 1 | 2025-08-11 | 551927RFI254 | 551927 | 1825681.47 | 155359.48 | 1981040.95
551963 | 11859 | 84287009 | 4232330.2 | 671253.14 |  | 4489030.64 | 539034.63 | 3693295.57 | 8721360.84 | 9392613.98 | 2024-11-30 | 2025-05-31 | 2025-09-17 |  | 5490297 | 5490297 |  |  |  | 1143166.33 |  | 5490297 | 5490297 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/253/551963%20DR4339PR%20-%20DSOW%20Transport%20Network%20Amendment%20Rev%207%20Version%201%20signed.pdf?web=1 | 3/27/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Transport Network | Jason Fournier | 0 Months |  | 836416.02 | 0 | 1 | 9.6644 | 1 |  | 551963RFI253 | 551963 | 1143166.33 | 0 | 1143166.33
657300 | 10957 | 48941484 | 0 | 2041312 |  | 48941484 | 0 | 0 | 48941484 | 50982796 |  |  | 2022-10-17 | 2024-10-17 | 48941484 | 48941484 | 164579862 | 164579862 |  |  |  | 164579862 | 164579862 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/252/657300-DR4339PR-00%20Detailed%20SOW%20EMS-10128-EN-SOW-0002Rev3.pdf?web=1 | 5/16/2024 - Previously, 657300 included the EMS (software / servers) and the PCC / SCC (2 buildings) projects. The PCC / SCC projects have been moved to 746545. This means 657300 includes only the EMS (software / servers) scope. Therefore, 657300 is a Telecommunications project, not a Building project. [Update provided by Andrew Buresh, PM for 746545. Phil Vallejo is the PM for 65730] | 2026-01-29 09:32 | 2023-08-14 11:09 | Jahdiel Franqui | Primary Control Center Secondary Data Center & Control Room | Ashleah Dingle | 0 Months |  | 2041312 |  | 1 | 1 | 1 |  | 657300RFI252 | 657300 |  |  | 0
659623 | 10884 | 17562047 | 565289 | 3574763 |  | 16996758 | 49247 | 516042 | 17562047 | 21136810 |  |  | 2022-12-27 |  | 17562047 | 16996758 | [5 empty] | 17562047 | 16996758 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/251/659623-DSOW-Distribution%20Streetlighting%20-%20Cata%C3%B1o-Rev0.pdf?web=1 |  | 2025-11-26 11:35 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  | 3574763 |  | 1 | 1 | 1 |  | 659623RFI251 | 659623 |  |  | 0
659625 | 11099 | 24370617 | 1505645 | 4716594 |  | 22864972 | 355973 | 1149672 | 24370617 | 29087211 |  |  | 2023-01-24 |  | 24370617 | 22864972 | [5 empty] | 24370617 | 22864972 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/250/659625-DR4339PR-SOW-Distribution%20Streetlighting%20-%20Dorado_Rev2.pdf?web=1 |  | 2025-07-21 16:23 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 3031749 | 165500 | 1 | 1 | 1 |  | 659625RFI250 | 659625 |  |  | 0
659715 | 10876 | 7253285 | 178787 | 1880873 |  | 7074498 | 49247 | 129540 | 7253285 | 9134158 |  |  | 2022-12-27 |  | 7253285 | 7074498 | [5 empty] | 7253285 | 7074498 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/249/659715-DR4339PR-Distribution%20Streetlighting%20-%20DSOW-Aibonito_Rev2.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1880873 |  | 1 | 1 | 1 |  | 659715RFI249 | 659715 |  |  | 0
659968 | 11318 | 34882926 | 4033578 | 4619207 |  | 30849348 | 1029513 | 3004065 | 34882926 | 39502133 |  |  | 2023-05-04 |  | 34882926 | 30849348 | [5 empty] | 34882926 | 30849348 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/248/FEMA%20Detailed%20Scope%20of%20Work%20San%20Germ%C3%A1n%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 4619207 |  | 1 | 1 | 1 |  | 659968RFI248 | 659968 |  |  | 0
660227 | 11095 | 20334482.95 | 1764387.7 | 4317860 |  | 18570180 | 448282.64 | 1316105.06 | 20334567.7 | 24652427.7 |  |  | 2023-01-24 |  | 20334482.95 | 18570095.25 | [5 empty] | 20334482.95 | 18570095.25 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/247/660227-DR4339PR-Distribution%20Streetlighting%20-%20DSOW-Aibonito_Rev2.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 4317860.43 |  | 1 | 1 | 1 |  | 660227RFI247 | 660227 |  |  | 0
660239 | 10857 | 10872401.71 | 681865.66 | 2630719 |  | 10190536 | 84516.08 | 597349.58 | 10872401.66 | 13503120.66 |  |  | 2022-08-24 |  | 10872401.71 | 10190536.05 | [5 empty] | 10872401.71 | 10190536.05 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/246/660239-DSOW-Distribution%20Streetlighting%20-%20Villalba_Rev3.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2630718.61 |  | 1 | 1 | 1 |  | 660239RFI246 | 660239 |  |  | 0
660422 | 11566 | 3816798 | 338280 | 766618 |  | 3478518 | 0 | 338280 | 3816798 | 4583416 |  |  | 2023-12-29 | 2024-08-30 | 3816798 | 3478518 | 3816798 | 3478518 |  |  |  | 3816798 | 3478518 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/245/PW%2011566%20PRJ_Report_660422_20240102.pdf?web=1 |  | 2026-02-17 12:16 | 2023-08-14 11:09 | Jahdiel Franqui | Physical Security | Marlina Crespo |  |  | 460523 |  | 1 | 1 | 1 |  | 660422RFI245 | 660422 |  |  | 0
660437 | 11097 | 28636829 | 1568964 | 5821636 |  | 27067865 | 380359 | 1188605 | 28636829 | 34458465 |  |  | 2023-01-24 |  | 28636829 | 27067865 | [5 empty] | 28636829 | 27067865 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/244/660437-Streetlight-Manati%20DSOW_Rev1%20(2).pdf?web=1 |  | 2025-07-21 15:23 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 5821635 |  | 1 | 1 | 1 |  | 660437RFI244 | 660437 |  |  | 0
662238 | 107742 | 16046926.54 | 5926449.37 | 2708469.23 | 0 | 28826526.19 | 509009.29 | 5417440.08 | 34752975.56 | 37461444.79 | 2024-07-31 | 2024-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/243/662238%20DR4339PR%20FEMA%20DSOW%20Microwave%20PTP%20Backbone%20Rev%2011%20signed.pdf?web=1 | Originally withdrawn on 12/4/2025. This project was reactivated on 12/10/2025 | 2026-02-18 12:40 | 2023-08-14 11:09 | Jahdiel Franqui | Microwave Point-to-Point | Marlina Crespo | 0 Months |  |  |  | 1 | 0.46174 | 3 |  | 662238RFI243 | 662238 | 0 | 0 | 0
666894 | 11519 | 30550204.86 | 3532039 | 4738922 |  | 30543791 | 474312 | 3057727 | 34075830 | 38814752 | 2024-08-31 | 2024-11-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/242/DR4339PR-666894-Detailed%20SOW%20San%20Juan%20Phase%201%20High%20Priority%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:46 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.89654 | 1 | 2025-08-04 | 666894RFI242 | 666894 |  |  | 0
668583 | 10800 | 453597 | 0 | 81996 |  | 453597 | 0 | 0 | 453597 | 535593 |  |  | 2022-08-02 | 2024-08-30 | 453597 | 453597 | 453597 | 453597 |  |  |  | 453597 | 453597 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/241/668583-DR4339PR-Detailed%20SOW%20-%20Line%2013300%20Rev1.pdf?web=1 |  | 2026-02-17 12:18 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Marlina Crespo |  |  | 81996 |  | 1 | 1 | 1 |  | 668583RFI241 | 668583 |  |  | 0
668592 | 10891 | 420866 | 0 | 43984 |  | 420867 | 0 | 0 | 420867 | 464851 |  |  | 2022-09-16 |  | 420866 | 420866 | [5 empty] | 420866 | 420866 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/240/668592-DR4339PR-Detailed%20SOW%20-%20Line%209800%20Rev.0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 43984 |  | 1 | 1 | 1 |  | 668592RFI240 | 668592 |  |  | 0
668665 | 107753 | 24500000 | 0 | 2150367.26 |  | 22436888.87 | 0 | 0 | 22436888.87 | 24587256.13 | 2024-08-31 | 2024-12-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/239/668665-DR4339PR%20Detailed%20Scope%20of%20Work%20IT%20OT%20Cybersecurity%20Program%20Rev%204%20signed.pdf?web=1 |  | 2025-11-20 12:50 | 2023-08-14 11:09 | Jahdiel Franqui | Cybersecurity Implementation Program | Marlina Crespo | 0 Months |  |  |  | 1 | 1.092 | 1 | 2025-08-11 | 668665RFI239 | 668665 | 0 | 0 | 0
668669 | 107754 | 307465 | 0 |  |  | 307465 | 0 | 0 | 307465 | 307465 | 2025-08-31 | 2026-01-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/238/668669-DR4339PR-Detailed%20SOW%20-Transmission%20Priority%20Pole%20Replacement-%20Mora%2050500%20Rev0.pdf?web=1 | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2026-02-24 13:55 | 2023-08-14 11:09 | Jahdiel Franqui | 230 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 668669RFI238 | 668669 |  |  | 0
671396 | 11530 | 17961216.53 | 2911033 | 3174654 |  | 17961217 | 437244 | 2473789 | 20872250 | 24046904 | 2024-11-30 | 2025-04-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/237/671396-DR4339PR-Detailed%20SOW%20Utuado%20Rev2%20-%20DSOW%20-%20signed%20(1).pdf?web=1 |  | 2026-02-06 14:46 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.86053 | 1 | 2025-08-04 | 671396RFI237 | 671396 |  |  | 0
671400 | 11529 | 8163052.71 | 1109633 | 1890247 |  | 8163053 | 198246 | 911387 | 9272686 | 11162933 | 2024-11-30 | 2025-04-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/236/671400-DR4339PR-Detailed%20SOW%20Barceloneta%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:47 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.88033 | 1 | 2025-08-05 | 671400RFI236 | 671400 |  |  | 0
671502 | 11522 | 16883989.33 | 1986076 | 2741367 |  | 14918273 | 0 | 1986076 | 16904349 | 19645716 |  |  | 2023-12-29 | 2024-08-30 | 16883989.33 | 14918381.07 | 16883989.33 | 14918381.07 |  |  |  | 16883989.33 | 14918381.07 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/235/PW11522%20PRJ_Report_671502_20240102.pdf?web=1 |  | 2026-02-17 12:19 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2742910.41 |  | 1 | 0.9988 | 1 |  | 671502RFI235 | 671502 |  |  | 0
673292 | 11452 | 6767654.15 | 49577.82 | 1075319.59 |  | 8129023.86 | 49577.82 | 0 | 8178601.68 | 9253921.27 | 2025-06-30 | 2025-11-30 | 2025-10-30 |  | 8173684.61 | 8124106.79 |  |  |  | 4917.07 |  | 8173684.61 | 8124106.79 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/234/PW%2011452%20PRJ_MultiVersionReport_673292_20251031.pdf?web=1 | 8/15/2025 - Field EHP: ESA Consultation letter submitted to USFWS on 5/28/2025. Waiting for response. ECD Updated to 9/15/2025 | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier |  |  | 1075319.59 | 4963.76 | 1 | 0.82748 | 1 |  | 673292RFI234 | 673292 | 4917.07 | 427.57 | 5344.64
673504 | 11317 | 20742294 | 1533300 | 3043675 |  | 19208994 | 400644 | 1132656 | 20742294 | 23785969 |  |  | 2023-05-17 |  | 20742294 | 19208994 | [5 empty] | 20742294 | 19208994 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/233/673504-FEMA%20Detailed%20SOW-Streetlight-%20Gurabo.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3043676 |  | 1 | 1 | 1 |  | 673504RFI233 | 673504 |  |  | 0
673691 | 10710 | 3075694700.2 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 2022-06-10 | 2023-12-29 | 1506189735.2 |  | 797183125.2 | 797183125.2 | 1733204375 |  | 1733204375 | 1733204375 | 1733204375 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/232/PRJ_Report_673691_20241106.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  | 0 |  | 1 | #DIV/0! | #DIV/0! |  | 673691RFI232 | 673691 |  |  | 0
673771 | 10909 | 2366560.53 | 472527 | 370850 |  | 1894034 | 98988 | 373539 | 2366561 | 2737411 |  |  | 2022-10-17 |  | 2366560.53 | 1894033.53 | [5 empty] | 2366560.53 | 1894033.53 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/231/PRJ_Report_673771_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 370850.25 |  | 1 | 1 | 1 |  | 673771RFI231 | 673771 |  |  | 0
673772 | 10919 | 4122520 | 835984 | 636837 |  | 3286536 | 175127 | 660857 | 4122520 | 4759357 |  |  | 2022-10-24 |  | 4122520 | 3286536 | [5 empty] | 4122520 | 3286536 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/230/PRJ_Report_673772_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 636837 |  | 1 | 1 | 1 |  | 673772RFI230 | 673772 |  |  | 0
673774 | 10773 | 1766951 | 358420 | 273831 |  | 1408531 | 75084 | 283336 | 1766951 | 2040782 |  |  | 2022-08-02 |  | 1766951 | 1408531 | [5 empty] | 1766951 | 1408531 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/229/PRJ_Report_673774_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 273831 |  | 1 | 1 | 1 |  | 673774RFI229 | 673774 |  |  | 0
673775 | 10962 | 4432647.91 | 859175 | 689888 |  | 3575455 | 79570.1 | 779604.9 | 4434630 | 5124518 |  |  | 2022-12-27 |  | 4432647.91 | 3575454.81 | [5 empty] | 4432647.91 | 3575454.81 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/228/PRJ_Report_673775_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 689888.45 |  | 1 | 0.99955 | 1 |  | 673775RFI228 | 673775 |  |  | 0
673795 | 10777 | 1794117 | 368954 | 278117 |  | 1425163 | 77291 | 291663 | 1794117 | 2072234 |  |  | 2022-08-02 |  | 1794117 | 1425163 | [5 empty] | 1794117 | 1425163 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/227/PRJ_Report_673795_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 278116 |  | 1 | 1 | 1 |  | 673795RFI227 | 673795 |  |  | 0
673818 | 10821 | 793418 | 171614 | 121044 |  | 621804 | 0 | 171614 | 793418 | 914462 |  |  | 2022-08-08 |  | 793418 | 621804 | [5 empty] | 793418 | 621804 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/226/PRJ_Report_673818_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 121044 |  | 1 | 1 | 1 |  | 673818RFI226 | 673818 |  |  | 0
673836 | 11041 | 5751036.48 | 1064121.8 | 900015 |  | 4686915 | 0 | 1064121.8 | 5751036.8 | 6651051.8 |  |  | 2022-12-21 | 2024-08-30 | 5751036.48 | 4686914.68 | 5751036.48 | 4686914.68 |  |  |  | 5751036.48 | 4686914.68 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/225/PRJ_Report_673836_20250213.pdf?web=1 |  | 2026-02-17 12:20 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 900014.8 |  | 1 | 1 | 1 |  | 673836RFI225 | 673836 |  |  | 0
673838 | 10764 | 357614 | 73265 | 55024 |  | 284348 | 15348 | 57917 | 357613 | 412637 |  |  | 2022-07-12 |  | 357614 | 284349 | [5 empty] | 357614 | 284349 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/224/673838-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%202%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 55025 |  | 1 | 1 | 1 |  | 673838RFI224 | 673838 |  |  | 0
673839 | 10742 | 26298 | 5830 | 10153 |  | 20468 | 1221 | 4609 | 26298 | 36451 |  |  | 2022-07-12 |  | 26298 | 20468 | [5 empty] | 26298 | 20468 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/223/673839-DR4339PR-Detailed%20SOW%20Bayamon%20Group%202%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 10152 |  | 1 | 1 | 1 |  | 673839RFI223 | 673839 |  |  | 0
673843 | 10922 | 1131855 | 227661 | 175796 |  | 904194 | 47692 | 179969 | 1131855 | 1307651 |  |  | 2022-10-17 |  | 1131855 | 904194 | [5 empty] | 1131855 | 904194 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/222/PRJ_Report_673843_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 175796 |  | 1 | 1 | 1 |  | 673843RFI222 | 673843 |  |  | 0
673844 | 10864 | 1392064.88 | 319213.9 | 208800.6 |  | 1072851 | 0 | 319213.9 | 1392064.9 | 1600865.5 |  |  | 2022-08-24 | 2024-08-30 | 1392064.88 | 1072850.98 | 1392064.88 | 1072850.98 |  |  |  | 1392064.88 | 1072850.98 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/221/PRJ_Report_673844_20250213.pdf?web=1 |  | 2026-02-17 12:20 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 208800.58 |  | 1 | 1 | 1 |  | 673844RFI221 | 673844 |  |  | 0
673847 | 10812 | 240513 | 49943 | 37242 |  | 190570 | 10462 | 39481 | 240513 | 277755 |  |  | 2022-08-08 |  | 240513 | 190570 | [5 empty] | 240513 | 190570 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/220/673847-DR4339PR-Detalied%20SOW%20Carolina%20Group%202%20Rev2.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 37242 |  | 1 | 1 | 1 |  | 673847RFI220 | 673847 |  |  | 0
673848 | 10751 | 49345 | 5620 | 13281 |  | 43725 | 1177 | 4443 | 49345 | 62626 |  |  | 2022-07-12 |  | 49345 | 43725 | [5 empty] | 49345 | 43725 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/219/PRJ_Report_673848_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13281 |  | 1 | 1 | 1 |  | 673848RFI219 | 673848 |  |  | 0
673920 | 107764 | 600000 | [5 empty] | 0 | 600000 | 600000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/218/673920-DR4339PR-ISOW-Isla%20Grande%201101-Substation.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Isla Grande 1101 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 673920RFI218 | 673920 |  |  | 0
674072 | 10906 | 1111094 | 238203 | 171585 |  | 872891 | 49900.3 | 188302.7 | 1111094 | 1282679 |  |  | 2022-09-16 |  | 1111094 | 872891 | [5 empty] | 1111094 | 872891 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/217/PRJ_Report_674072_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 171585 |  | 1 | 1 | 1 |  | 674072RFI217 | 674072 |  |  | 0
674083 | 10827 | 2110462 | 362533 | 335721.9 |  | 1747928.9 | 75946 | 286587 | 2110461.9 | 2446183.8 |  |  | 2022-08-08 |  | 2110462 | 1747929 | [5 empty] | 2110462 | 1747929 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/216/PRJ_Report_674083_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 335722 |  | 1 | 1 | 1 |  | 674083RFI216 | 674083 |  |  | 0
674088 | 10933 | 1702021 | 289653 | 267370 |  | 1412368 | 60678 | 228975 | 1702021 | 1969391 |  |  | 2022-10-17 |  | 1702021 | 1412368 | [5 empty] | 1702021 | 1412368 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/215/PRJ_Report_674088_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 267370 |  | 1 | 1 | 1 |  | 674088RFI215 | 674088 |  |  | 0
674092 | 10893 | 531730 | 90422 | 82578 |  | 441308 | 18942 | 71480 | 531730 | 614308 |  |  | 2022-09-16 |  | 531730 | 441308 | [5 empty] | 531730 | 441308 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/214/PRJ_Report_674092_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 82578 |  | 1 | 1 | 1 |  | 674092RFI214 | 674092 |  |  | 0
674096 | 10935 | 2092280 | 318852 | 332705 |  | 1773428 | 66795 | 252057 | 2092280 | 2424985 |  |  | 2022-10-17 |  | 2092280 | 1773428 | [5 empty] | 2092280 | 1773428 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/213/PRJ_Report_674096_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 332705 |  | 1 | 1 | 1 |  | 674096RFI213 | 674096 |  |  | 0
674098 | 10824 | 107755 | 23322 | 16516 |  | 84433 | 0 | 23322 | 107755 | 124271 |  |  | 2022-08-08 |  | 107755 | 84433 | [5 empty] | 107755 | 84433 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/212/PRJ_Report_674098_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 16517 |  | 1 | 1 | 1 |  | 674098RFI212 | 674098 |  |  | 0
674506 | 107765 | 330000000 | [5 empty] | 0 | 330000000 | 330000000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/211/921840-DR4339PR-SOW%20(1).pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch.This project is being developed and internal strategy needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 8/26/2024. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Field Area Network(FAN) | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 674506RFI211 | 674506 |  |  | 0
675345 | 107766 | 21640536 | 0 | 798980.71 |  | 8378200.51 | 0 | 0 | 8378200.51 | 9177181.22 | 2025-01-31 | 2025-06-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/210/675345-DR4339PR-Mass%20Storage-SOW-01172024%20(1).pdf?web=1 |  | 2025-08-12 11:27 | 2023-08-14 11:09 | Jahdiel Franqui | IT OT Technology Systems Reparations | Maria Mujica Gonzalez |  |  |  |  | 1 | 2.583 | 1 | 2025-08-11 | 675345RFI210 | 675345 |  |  | 0
675406 | 107767 | 46200000 | [5 empty] | 0 | 46200000 | 46200000 | [11 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/209/675406-DR4339PR-Two-Way%20Land%20Mobile%20Radio%20Network.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Two Way Land Mobile Radio Network | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | 675406RFI209 | 675406 |  |  | 0
678789 | 11533 | 16024559.58 | 1158946.56 | 2559493 |  | 14865613 | 0 | 1158946.56 | 16024559.56 | 18584052.56 |  |  | 2023-11-03 | 2024-08-30 | 16024559.58 | 14865613.02 | 16024559.58 | 14865613.02 |  |  |  | 16024559.58 | 14865613.02 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/208/678789-DR4339PR-Detailed%20SOW%20Carolina%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(1).pdf |  | 2026-02-17 12:21 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2559492.85 |  | 1 | 1 | 1 |  | 678789RFI208 | 678789 |  |  | 0
678793 | 11532 | 12371384.46 | 1352204.36 | 2291581 |  | 11019180 | 0 | 1352204.36 | 12371384.36 | 14662965.36 |  |  | 2023-11-03 | 2024-08-30 | 12371384.46 | 11019180.1 | 12371384.46 | 11019180.1 |  |  |  | 12371384.46 | 11019180.1 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/207/678793-DR4339PR-Detailed%20SOW%20Mayaguez%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 2026-02-17 12:25 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2291581 |  | 1 | 1 | 1 |  | 678793RFI207 | 678793 |  |  | 0
678794 | 11527 | 16043135.52 | 1444528 | 2808935 |  | 16043136 | 215232 | 1229296 | 17487664 | 20296599 | 2024-12-31 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/206/678794-DR4339PR-Detailed%20SOW%20Ponce%20Phase%201%20High%20Priority%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:47 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.9174 | 1 | 2025-08-05 | 678794RFI206 | 678794 |  |  | 0
678795 | 11535 | 14607500.56 | 1527389 | 2673960 |  | 14601018 | 222962 | 1304427 | 16128407 | 18802367 | 2024-11-30 | 2025-04-30 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/205/678795-DR4339PR-Detailed%20SOW%20Arecibo%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 2026-02-06 14:47 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.9057 | 1 | 2025-08-05 | 678795RFI205 | 678795 |  |  | 0
678800 | 11425 |  | 55895.84 | 2828793.1 |  | 13148929.44 | 10487.44 | 45408.4 | 13204825.28 | 16033618.38 |  |  | 2025-11-05 |  | 13204825.28 | 13148929.44 |  |  |  | 0 |  | 13204825.28 | 13148929.44 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/204/PW%2011425%20PRJ_MultiVersionReport_678800_20251105.pdf?web=1 | 4/04/2024: QC Review Complete 8/5/2025 - Field EHP – Environmental: Initial review. Expected Completion Date (ECD) 08/27/2025 | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier | 7-12 months |  | 2828793.1 | 10487.44 | 1 | 0 | 5 |  | 678800RFI204 | 678800 |  |  | 0
678985 | 11103 | 407945.84 | 54317.84 | 66915 |  | 353628 | 11378.84 | 42939 | 407945.84 | 474860.84 |  |  | 2022-12-27 |  | 407945.84 | 353628 | [5 empty] | 407945.84 | 353628 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/203/678985-DR4339PR-Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%204.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 66915 |  | 1 | 1 | 1 |  | 678985RFI203 | 678985 |  |  | 0
678988 | 11113 | 1117787.16 | 206650.4 | 175441 |  | 911137 | 0 | 206650.4 | 1117787.4 | 1293228.4 |  |  | 2022-12-27 | 2024-08-30 | 1117787.16 | 911136.76 | 1117787.16 | 911136.76 |  |  |  | 1117787.16 | 911136.76 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/202/PRJ_Report_678988_20250213.pdf?web=1 |  | 2026-02-17 12:24 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 175440.55 |  | 1 | 1 | 1 |  | 678988RFI202 | 678988 |  |  | 0
679006 | 11862 | 25192128 | 8186857 | 386408 |  | 12739422 | 500959 | 7685898 | 20926279 | 21312687 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/201/679006%20DR-4339PR_FAASt%20Test%20and%20Technology%20Laboratory%20Phase%201%20DSOW_V05_05.16.2024%20-%20signed.pdf?web=1 |  | 2025-08-12 11:10 | 2023-08-14 11:09 | Jahdiel Franqui | Test and Technology Laboratory | Maria Mujica Gonzalez |  |  |  |  | 1 | 1.2039 | 1 | 2025-08-11 | 679006RFI201 | 679006 |  |  | 0
679025 | 11101 | 298631 | 55558 | 46884 |  | 243073 | 11639 | 43919 | 298631 | 345515 |  |  | 2022-12-27 |  | 298631 | 243073 | [5 empty] | 298631 | 243073 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/200/679025-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%204%20Rev2%20New%20Template.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 46884 | 6588 | 1 | 1 | 1 |  | 679025RFI200 | 679025 |  |  | 0
679026 | 11107 | 590296 | 106510 | 93451 |  | 483786 | 22312 | 84198 | 590296 | 683747 |  |  | 2022-12-27 |  | 590296 | 483786 | [5 empty] | 590296 | 483786 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/199/679026-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%205%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 93451 | 12630 | 1 | 1 | 1 |  | 679026RFI199 | 679026 |  |  | 0
679033 | 11098 | 908942 | 179902 | 140628 |  | 729040 | 37687 | 142215 | 908942 | 1049570 |  |  | 2022-12-27 |  | 908942 | 729040 | [5 empty] | 908942 | 729040 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/198/PRJ_Report_679033_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 140628 |  | 1 | 1 | 1 |  | 679033RFI198 | 679033 |  |  | 0
679035 | 11861 | 5900000 | [5 empty] | 0 | 5900000 | 5900000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/197/PR679035%20-%20DR4339PR%20-%20Telecom%20Infraestructure%20-%20Group%20A%20SOW.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-06 13:25 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | 679035RFI197 | 679035 |  |  | 0
679039 | 11351 | 75586568.64 | 1849344.06 | 8534897 |  | 73737225 | 426651.06 | 1422693 | 75586569.06 | 84121466.06 |  |  | 2023-07-05 |  | 75586568.64 | 73737224.58 | [5 empty] | 75586568.64 | 73737224.58 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/196/679039-DR4339PR-Detailed%20SOW%20Caguas%20Phase%201%20High%20Priority%20Rev0%20-%20signed%20-%20DSOW.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 8534896.89 |  | 1 | 1 | 1 |  | 679039RFI196 | 679039 |  |  | 0
679127 | 11096 | 217162.81 | 46010.58 | 33340 |  | 46010.58 | 9638.58 | 36372 | 92021.16 | 125361.16 |  |  | 2022-12-27 |  | 217162.81 | 171152.23 | [5 empty] | 217162.81 | 171152.23 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/195/PRJ_Report_679127_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 33340.3 |  | 1 | 2.3599 | 1 |  | 679127RFI195 | 679127 |  |  | 0
679133 | 11090 | 21362 | 633 | 4078 |  | 20729 | 133 | 500 | 21362 | 25440 |  |  | 2022-12-27 | 2025-09-12 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/194/679133-DR4339PR-Detailed%20SOW%20Arecibo%20Group%204%20Rev1.pdf?web=1 | 15SEPTEMBER2025 - Version 2 was created to withdraw funds of Project 679133. In version 01, the funds for work to be completed were de-obligated. The replacement of the pole is no longer feasible because is a private pole and does not belong to PREPA/LUMA. Please refer to document "679133 4339-DR Withdrawal form - Arecibo Group 4 - Phase 1 signed.pdf”. | 2026-02-17 12:26 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 0 | 0 | 1 | 1 | 1 | 2025-09-19 | 679133RFI194 | 679133 |  |  | 0
679134 | 11109 | 563557.15 | 110600.22 | 86724 |  | 452957 | 23169.22 | 87431 | 563557.22 | 650281.22 |  |  | 2023-01-10 |  | 563557.15 | 452956.93 | [5 empty] | 563557.15 | 452956.93 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/193/PRJ_Report_679134_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 86724.25 | 13114.65 | 1 | 1 | 1 |  | 679134RFI193 | 679134 |  |  | 0
679149 | 11089 | 157187 | 27443 | 25191 |  | 129744 | 5749 | 21694 | 157187 | 182378 |  |  | 2022-12-27 |  | 157187 | 129744 | [5 empty] | 157187 | 129744 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/192/679149-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%205%20Rev2%20New%20Template.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 25191 |  | 1 | 1 | 1 |  | 679149RFI192 | 679149 |  |  | 0
679153 | 11106 | 215184.01 | 51337.5 | 31068 |  | 163847 | 10754.5 | 40583 | 215184.5 | 246252.5 |  |  | 2022-12-27 |  | 215184.01 | 163846.51 | [5 empty] | 215184.01 | 163846.51 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/191/679153-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%206%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 31068.05 |  | 1 | 1 | 1 |  | 679153RFI191 | 679153 |  |  | 0
679457 | 11105 | 746488 | 157153 | 115386 |  | 589335 | 33921 | 123232 | 746488 | 861874 |  |  | 2022-12-27 |  | 746488 | 589335 | [5 empty] | 746488 | 589335 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/190/PRJ_Report_679457_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 115386 |  | 1 | 1 | 1 |  | 679457RFI190 | 679457 |  |  | 0
679458 | 11114 | 593918 | 95482 | 95421 |  | 498436 | 20002 | 75480 | 593918 | 689339 |  |  | 2023-01-10 |  | 593918 | 498436 | [5 empty] | 593918 | 498436 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/189/PRJ_Report_679458_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 95421 | 11322 | 1 | 1 | 1 |  | 679458RFI189 | 679458 |  |  | 0
679780 | 11540 | 21886903 | 1176376 | 3212958 |  | 20710527 | 0 | 1176376 | 21886903 | 25099861 |  |  | 2023-11-03 | 2024-08-30 | 21886903 | 20710527 | 21886903 | 20710527 |  |  |  | 21886903 | 20710527 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/188/679780-DR4339PR-Detailed%20SOW%20Bayam%c3%b3n%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(1).pdf |  | 2026-02-17 12:26 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 3212958 |  | 1 | 1 | 1 |  | 679780RFI188 | 679780 |  |  | 0
681672 | 11184 | 216367 | 2243 | 26175 |  | 214124 | 699 | 1544 | 216367 | 242542 |  |  | 2023-01-31 | 2024-04-18 | 216367 | 214124 | 216367 | 214124 |  |  |  | 216367 | 214124 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/187/681672-DR4339PR-Detailed%20SOW%20-%20Line%202300%20Rev.2.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 26175 |  | 1 | 1 | 1 |  | 681672RFI187 | 681672 |  |  | 0
682028 | 11166 | 537125.3 | 105743.62 | 83822 |  | 431382 | 22151.62 | 83592 | 537125.62 | 620947.62 |  |  | 2023-01-10 |  | 537125.3 | 431381.68 | [5 empty] | 537125.3 | 431381.68 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/186/682028-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 83822 | 12539 | 1 | 1 | 1 |  | 682028RFI186 | 682028 |  |  | 0
682031 | 11181 | 625198 | 108247 | 94044 |  | 516951 | 22676 | 85571 | 625198 | 719242 |  |  | 2023-01-31 |  | 625198 | 516951 | [5 empty] | 625198 | 516951 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/185/682031-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%209%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 94044 | 12836 | 1 | 1 | 1 |  | 682031RFI185 | 682031 |  |  | 0
682121 | 11652 | 82726096.38 |  | 11520000 |  | 180750000 | 0 | 0 | 180750000 | 192270000 | 2024-06-01 | 2025-08-31 | 2024-03-22 | 2024-08-30 | 82726096.38 | 82726096.38 | 82726096.38 | 82726096.38 |  |  |  | 82726096.38 | 82726096.38 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/184/PW%2011652%20PRJ_Report_682121_20240322.pdf?web=1 |  | 2026-02-17 12:27 | 2023-08-14 11:09 | Jahdiel Franqui | Aguirre TC (El Coqui) - Phase II and Phase III | Marlina Crespo |  |  | 7789677 |  | 1 | 0.45768 | 3 |  | 682121RFI184 | 682121 |  |  | 0
682135 | 11149 | 693780.53 | 116779.74 | 109859 |  | 577001 | 24463.74 | 92316 | 693780.74 | 803639.74 |  |  | 2023-01-10 |  | 693780.53 | 577000.79 | [5 empty] | 693780.53 | 577000.79 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/183/PRJ_Report_682135_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 109858.85 | 13847.4 | 1 | 1 | 1 |  | 682135RFI183 | 682135 |  |  | 0
682136 | 11203 | 565605 | 95954.05 | 90260 |  | 469651 | 20101.05 | 75853 | 565605.05 | 655865.05 |  |  | 2023-01-31 |  | 565605 | 469650.95 | [5 empty] | 565605 | 469650.95 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/182/682136-DR4339PR-Detailed%20SOW%20Bayamon%20Group%209%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 90259.5 | 11377.95 | 1 | 1 | 1 |  | 682136RFI182 | 682136 |  |  | 0
682172 | 11182 | 266071.35 | 57671.35 | 40930 |  | 208400 | 12081.35 | 45590 | 266071.35 | 307001.35 |  |  | 2023-01-24 |  | 266071.35 | 208400 | [5 empty] | 266071.35 | 208400 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/181/682172-DR4339PR-Detailed%20SOW%20Arecibo%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 40930 | 6838 | 1 | 1 | 1 |  | 682172RFI181 | 682172 |  |  | 0
682178 | 11201 | 262290.31 | 53746.06 | 40949 |  | 208544 | 11259.06 | 42487 | 262290.06 | 303239.06 |  |  | 2023-01-31 | 2024-04-17 | 262290.31 | 208544.25 | 262290.31 | 208544.25 |  |  |  | 262290.31 | 208544.25 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/180/682178-DR4339PR-Detailed%20SOW%20Arecibo%20Group%207%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 40949.45 |  | 1 | 1 | 1 |  | 682178RFI180 | 682178 |  |  | 0
682180 | 11168 | 54402 | 11028 | 8414 |  | 43374 | 2310 | 8718 | 54402 | 62816 |  |  | 2023-01-10 |  | 54402 | 43374 | [5 empty] | 54402 | 43374 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/179/PRJ_Report_682180_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 8414 | 1308 | 1 | 1 | 1 |  | 682180RFI179 | 682180 |  |  | 0
682210 | 11169 | 239847.61 | 41796.87 | 38248 |  | 198051 | 8755.87 | 33041 | 239847.87 | 278095.87 |  |  | 2023-01-24 |  | 239847.61 | 198050.74 | [5 empty] | 239847.61 | 198050.74 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/178/682210-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%209%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 38248.35 | 4956.15 | 1 | 1 | 1 |  | 682210RFI178 | 682210 |  |  | 0
682228 | 11196 | 952661.42 | 176882.42 | 150784 |  | 775779 | 37054.42 | 139828 | 952661.42 | 1103445.42 |  |  | 2023-01-31 |  | 952661.42 | 775779 | [5 empty] | 952661.42 | 775779 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/177/PRJ_Report_682228_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 150784 | 20974 | 1 | 1 | 1 |  | 682228RFI177 | 682228 |  |  | 0
682324 | 11145 | 709229.55 | 136182.31 | 110616 |  | 573047 | 28528.31 | 107654 | 709229.31 | 819845.31 |  |  | 2023-01-10 |  | 709229.55 | 573047.24 | [5 empty] | 709229.55 | 573047.24 | 2027-09-20 | /:b:/r/sites/Test4552/Shared%20Documents/General/ISOW%20DSOW%20Information%20(Attachments)/682324-DR4339PR-Detailed%20SOW%20Caguas%20Group%2013%20Rev0.pdf?csf=1&web=1&e=dG2f7P |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 110616.4 | 16148.1 | 1 | 1 | 1 |  | 682324RFI176 | 682324 |  |  | 0
682328 | 11876 | 2637502.74 | 0 | 1136049.98 |  | 9126057.99 | 0 | 0 | 9126057.99 | 10262107.97 | 2025-01-31 | 2025-04-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/175/682328-DR-4339-PR-DSOW%20Transformer%20Replacement%20115-40kV%20112MVA%20Bayamon%20TC%207.24.2025%20signed.pdf?web=1 |  | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Bayamon TC - Phase II | Jason Fournier |  |  |  |  | 1 | 0.28901 | 4 |  | 682328RFI175 | 682328 | 4748384.44 | 0 | 4748384.44
682331 | 107777 | 4360000 | [5 empty] | 0 | 4360000 | 4360000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/174/1241927-DR4339PR-SOW.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | 682331RFI174 | 682331 |  |  | 0
682373 | 11165 | 77605 | 11661 | 12740 |  | 65944 | 2443 | 9218 | 77605 | 90345 |  |  | 2023-01-10 |  | 77605 | 65944 | [5 empty] | 77605 | 65944 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/173/PRJ_Report_682373_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12740 | 1383 | 1 | 1 | 1 |  | 682373RFI173 | 682373 |  |  | 0
682645 | 107779 | 96115838 | 0 | 1605121.68 |  | 13016336.93 | 0 | 0 | 13016336.93 | 14621458.61 |  |  | 2025-09-17 |  | 8292125 | 8292125 |  |  |  | 4724211.98 |  | 8292125 | 8292125 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/172/PW%20107779%20PRJ_MultiVersionReport_682645_20250917.pdf?web=1 |  | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Jason Fournier |  |  | 1605121.68 | 0 | 1 | 7.3842 | 1 |  | 682645RFI172 | 682645 | 4724211.98 |  | 4724211.98
682834 | 11402 | 61444255.52 | 0 | 1345002.69 |  | 10983086.42 | 0 | 0 | 10983086.42 | 12328089.11 |  |  | 2024-02-13 | 2025-09-17 | 61444255.52 | 61444255.52 | 36917509.58 | 61444255.52 | 36917510 | 30357996.36 | 36917510 | 36917510 | 36917510 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/171/PW%2011402%20PRJ_MultiVersionReport_682834_20250917.pdf?web=1 |  | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Costa Sur TC (Guaypao TC) - Phase II & III | Jason Fournier | 0 Months |  | 5090347.22 | 0 | 1 | 5.5944 | 1 |  | 682834RFI171 | 682834 | 30357996.36 | 5151836 | 35509832.36
682865 | 11123 | 91831 | 21148 | 13377 |  | 70683 | 4430 | 16718 | 91831 | 105208 |  |  | 2022-12-27 |  | 91831 | 70683 | [5 empty] | 91831 | 70683 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/170/PRJ_Report_682865_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13377 | 2508 | 1 | 1 | 1 |  | 682865RFI170 | 682865 |  |  | 0
682870 | 11137 | 103412.77 | 17491 | 16717 |  | 85922 | 0 | 17491 | 103413 | 120130 |  |  | 2022-12-27 | 2024-08-30 | 103412.77 | 85921.77 | 103412.77 | 85921.77 |  |  |  | 103412.77 | 85921.77 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/169/PRJ_Report_682870_20250213.pdf?web=1 |  | 2026-02-17 12:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 16716.65 |  | 1 | 1 | 1 |  | 682870RFI169 | 682870 |  |  | 0
682882 | 11130 | 659039.4 | 113378.16 | 104353 |  | 545661 | 23751.16 | 89627 | 659039.16 | 763392.16 |  |  | 2023-01-10 |  | 659039.4 | 545661.24 | [5 empty] | 659039.4 | 545661.24 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/168/682882-DR4339PR-Detailed%20SOW%20Caguas%20Group%2011%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 104353.35 |  | 1 | 1 | 1 |  | 682882RFI168 | 682882 |  |  | 0
682890 | 11136 | 612378.63 | 102310.67 | 98276 |  | 510068 | 21432.67 | 80878 | 612378.67 | 710654.67 |  |  | 2022-12-27 |  | 612378.63 | 510067.96 | [5 empty] | 612378.63 | 510067.96 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/167/PRJ_Report_682890_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 98275.6 | 12131.7 | 1 | 1 | 1 |  | 682890RFI167 | 682890 |  |  | 0
682898 | 11183 | 744027.12 | 108700.19 | 120284 |  | 635327 | 22771.19 | 85929 | 744027.19 | 864311.19 |  |  | 2023-01-24 |  | 744027.12 | 635326.93 | [5 empty] | 744027.12 | 635326.93 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/166/PRJ_Report_682898_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 120284.25 | 12889.35 | 1 | 1 | 1 |  | 682898RFI166 | 682898 |  |  | 0
682910 | 11212 | 622823 | 105667 | 99229 |  | 517156 | 22135.72 | 83531.28 | 622823 | 722052 |  |  | 2023-01-31 |  | 622823 | 517156 | [5 empty] | 622823 | 517156 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/165/PRJ_Report_682910_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 99229 | 12530 | 1 | 1 | 1 |  | 682910RFI165 | 682910 |  |  | 0
684920 | 11573 | 6929384 | 0 | 958084 |  | 6929383 | 0 | 0 | 6929383 | 7887467 |  |  | 2023-12-29 | 2024-08-30 | 6929384 | 6929384 | 6929384 | 6929384 |  |  |  | 6929384 | 6929384 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/164/PW%2011573%20PRJ_Report_684920_20240102.pdf?web=1 |  | 2026-02-17 12:28 | 2023-08-14 11:09 | Jahdiel Franqui | Substation High Voltage Equipment Replacement | Marlina Crespo |  |  | 958084 |  | 1 | 1 | 1 |  | 684920RFI164 | 684920 |  |  | 0
685263 | 11143 | 672383 | 134695 | 103281 |  | 537688 | 28217 | 106478 | 672383 | 775664 |  |  | 2022-12-27 |  | 672383 | 537688 | [5 empty] | 672383 | 537688 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/163/PRJ_Report_685263_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 103281 | 15972 | 1 | 1 | 1 |  | 685263RFI163 | 685263 |  |  | 0
685370 | 11150 | 83809 | 14986 | 13127 |  | 68823 | 3139 | 11847 | 83809 | 96936 |  |  | 2023-01-10 |  | 83809 | 68823 | [5 empty] | 83809 | 68823 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/162/685370-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13127 | 1777 | 1 | 1 | 1 |  | 685370RFI162 | 685370 |  |  | 0
685477 | 11171 | 413482 | 58304 | 67123 |  | 355178 | 12214 | 46090 | 413482 | 480605 |  |  | 2023-01-24 |  | 413482 | 355178 | [5 empty] | 413482 | 355178 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/161/685477-DR4339PR-Detailed%20SOW%20Arecibo%20Group%206%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 67123 | 6914 | 1 | 1 | 1 |  | 685477RFI161 | 685477 |  |  | 0
685869 | 107780 | 14464362 | [5 empty] | 0 | 3200000 | 3200000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/160/685869-DR4339PR0ISOW-Substation%20Minor%20Repairs%20Group%20G.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 4.5201 | 1 | 2025-08-19 | 685869RFI160 | 685869 |  |  | 0
685943 | 11138 | 318232.22 | 63260 | 49774 |  | 254972 | 13252 | 50008 | 318232 | 368006 |  |  | 2023-01-10 |  | 318232.22 | 254972.22 | [5 empty] | 318232.22 | 254972.22 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/159/685943-DR4339PR-Detailed%20SOW%20Ponce%20Group%205%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49774.2 | 7501.2 | 1 | 1 | 1 |  | 685943RFI159 | 685943 |  |  | 0
686453 | 11152 | 25579 | 4995 | 4059 |  | 20584 | 1046 | 3949 | 25579 | 29638 |  |  | 2022-12-27 |  | 25579 | 20584 | [5 empty] | 25579 | 20584 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/158/686453-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%207%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 4059 |  | 1 | 1 | 1 |  | 686453RFI158 | 686453 |  |  | 0
686471 | 11116 | 319606 | 68700 | 49227 |  | 250906 | 14392 | 54308 | 319606 | 368833 |  |  | 2022-12-27 | 2024-04-17 | 319606 | 250906 | 319606 | 250906 |  |  |  | 319606 | 250906 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/157/PRJ_Report_686471_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49227 |  | 1 | 1 | 1 |  | 686471RFI157 | 686471 |  |  | 0
686480 | 11229 | 632056 | 108652 | 101359 |  | 523404 | 22761 | 85891 | 632056 | 733415 |  |  | 2023-02-16 |  | 632056 | 523404 | [5 empty] | 632056 | 523404 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/156/PRJ_Report_686480_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 101359 |  | 1 | 1 | 1 |  | 686480RFI156 | 686480 |  |  | 0
686482 | 11572 | 7013624.27 | 733835 | 1698664 |  | 7013624 | 143078 | 590757 | 7747459 | 9446123 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/155/686482-DR4339PR-Detailed%20SOW%20Isabela%20Phase%201%20High%20Priority%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:49 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.90528 | 1 | 2025-08-06 | 686482RFI155 | 686482 |  |  | 0
688096 | 11214 | 27238.64 | 5830.39 | 4169 |  | 21408 | 1221.39 | 4609 | 27238.39 | 31407.39 |  |  | 2023-01-31 |  | 27238.64 | 21408.25 | [5 empty] | 27238.64 | 21408.25 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/154/688096-DR4339PR-Detailed%20SOW%20Caguas%20Group%2015%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 4169.45 | 691.35 | 1 | 1 | 1 |  | 688096RFI154 | 688096 |  |  | 0
688109 | 11264 | 563429.26 | 114710.2 | 87444 |  | 448719 | 0 | 114710.2 | 563429.2 | 650873.2 |  |  | 2023-03-08 | 2024-08-30 | 563429.26 | 448719.06 | 563429.26 | 448719.06 |  |  |  | 563429.26 | 448719.06 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/153/688109%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2011%20Rev0%20-%20signed.pdf?web=1 |  | 2026-02-17 12:28 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 87443.55 |  | 1 | 1 | 1 |  | 688109RFI153 | 688109 |  |  | 0
688198 | 11276 | 76862.24 | 16023.76 | 12053 |  | 60838 | 3356.76 | 12667 | 76861.76 | 88914.76 |  |  | 2023-03-20 |  | 76862.24 | 60838.48 | [5 empty] | 76862.24 | 60838.48 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/152/PRJ_Report_688198_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12052.8 |  | 1 | 1 | 1 |  | 688198RFI152 | 688198 |  |  | 0
688472 | 11217 | 179894.86 | 14986 | 29922 |  | 164909 | 0 | 14986 | 179895 | 209817 |  |  | 2023-02-16 | 2024-08-30 | 179894.86 | 164908.86 | 179894.86 | 164908.86 |  |  |  | 179894.86 | 164908.86 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/151/688472-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2011%20Rev0%20(1).pdf |  | 2026-02-17 12:29 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 29921.55 |  | 1 | 1 | 1 |  | 688472RFI151 | 688472 |  |  | 0
688623 | 107781 | 5145417.32 | 1877045 | 130382 |  | 874904 | 243445 | 1633600 | 2751949 | 2882331 | 2025-08-31 | 2026-01-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/150/688623-DR4339PR-DSOW%20Automation%20Group%201%20RV%20001%2012-26-2023%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2026-02-06 14:49 | 2023-08-14 11:09 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Jason Fournier |  |  |  |  | 1 | 1.8697 | 1 | 2025-08-18 | 688623RFI150 | 688623 |  |  | 0
688625 | 11279 | 901290.28 | 191275.59 | 139358 |  | 710015 | 0 | 191275.59 | 901290.59 | 1040648.59 |  |  | 2023-03-20 | 2024-08-30 | 901290.28 | 710014.69 | 901290.28 | 710014.69 |  |  |  | 901290.28 | 710014.69 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/149/PRJ_Report_688625_20250213.pdf?web=1 |  | 2026-02-17 12:31 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 139357.85 |  | 1 | 1 | 1 |  | 688625RFI149 | 688625 |  |  | 0
688627 | 11193 | 375962.49 | 72188.49 | 58918 |  | 303774 | 0 | 72188.49 | 375962.49 | 434880.49 |  |  | 2023-01-31 | 2024-08-30 | 375962.49 | 303774 | 375962.49 | 303774 |  |  |  | 375962.49 | 303774 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/148/688627-DR4339PR-Detailed%20SOW%20Arecibo%20Group%209%20Rev0.pdf?web=1 |  | 2026-02-17 12:32 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 58918 |  | 1 | 1 | 1 |  | 688627RFI148 | 688627 |  |  | 0
688629 | 11277 | 134828.92 | 27886.93 | 20834 |  | 106942 | 5841.93 | 22045 | 134828.93 | 155662.93 |  |  | 2023-03-08 |  | 134828.92 | 106941.99 | [5 empty] | 134828.92 | 106941.99 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/147/688629-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2013%20Rev0%20-%20signed%20(2).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 20833.9 |  | 1 | 1 | 1 |  | 688629RFI147 | 688629 |  |  | 0
688630 | 11273 | 52719.38 | 9990.97 | 8327 |  | 42728 | 0 | 9990.97 | 52718.97 | 61045.97 |  |  | 2023-03-08 | 2024-08-30 | 52719.38 | 42728.41 | 52719.38 | 42728.41 |  |  |  | 52719.38 | 42728.41 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/146/PRJ_Report_688630_20250213.pdf?web=1 |  | 2026-02-17 12:32 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 8327.05 |  | 1 | 1 | 1 |  | 688630RFI146 | 688630 |  |  | 0
688774 | 11207 | 541815 | 98484 | 86719 |  | 443331 | 20631 | 77853 | 541815 | 628534 |  |  | 2023-01-31 |  | 541815 | 443331 | [5 empty] | 541815 | 443331 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/145/688774-DR4339PR-Detailed%20SOW%20Ponce%20Group%209%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 86719 | 11678 | 1 | 1 | 1 |  | 688774RFI145 | 688774 |  |  | 0
689071 | 11256 | 77036.24 | 17491.16 | 11879 |  | 59545 | 3664.16 | 13827 | 77036.16 | 88915.16 |  |  | 2023-03-02 |  | 77036.24 | 59545.08 | [5 empty] | 77036.24 | 59545.08 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/144/689071-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2011%20Rev%201.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 11878.8 |  | 1 | 1 | 1 |  | 689071RFI144 | 689071 |  |  | 0
690480 | 11683 | 7598892 | 922000 | 1719130 |  | 7598892 | 170104 | 751896 | 8520892 | 10240022 | 2024-09-30 | 2025-02-28 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/143/690480-DR4339PR-Detailed%20SOW%20Humacao%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:49 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.8918 | 1 | 2025-08-06 | 690480RFI143 | 690480 |  |  | 0
690483 | 11552 | 13343261.38 | 1319139 | 2650718 |  | 13343261 | 218624 | 1100515 | 14662400 | 17313118 | 2024-11-30 | 2025-04-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/142/690483-DR4339PR-Detailed%20SOW%20Cayey%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:49 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.91003 | 1 | 2025-08-06 | 690483RFI142 | 690483 |  |  | 0
690545 | 11319 | 21092584 | 1295775 | 3021242 |  | 19796808 | 333333 | 962442 | 21092583 | 24113825 |  |  | 2023-05-17 | 2024-05-15 | 21092584 | 19796809 | 21092584 | 19796809 |  |  |  | 21092584 | 19796809 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/141/FEMA%20Detailed%20Scope%20of%20Work%20Aguadilla%20Municipality%20Phase%201%20High%20Priority%20-%20Signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3021242 |  | 1 | 1 | 1 |  | 690545RFI141 | 690545 |  |  | 0
690721 | 11531 | 5525916.66 | 542958 | 1519802 |  | 5525917 | 117119 | 425839 | 6068875 | 7588677 | 2025-01-31 | 2025-06-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/140/DR4339PR-690721--Detailed%20SOW%20Guayama%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:50 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.91053 | 1 | 2025-08-06 | 690721RFI140 | 690721 |  |  | 0
691246 | 11231 | 245340.07 | 33717.31 | 41364 |  | 211623 | 0 | 33717.31 | 245340.31 | 286704.31 |  |  | 2023-02-16 | 2024-08-30 | 245340.07 | 211622.76 | 245340.07 | 211622.76 |  |  |  | 245340.07 | 211622.76 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/139/691246%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2010%20Rev1.pdf?web=1 |  | 2026-02-17 12:33 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 41363.6 |  | 1 | 1 | 1 |  | 691246RFI139 | 691246 |  |  | 0
691702 | 11326 | 26286925 | 1009578 | 3389490 |  | 25277347 | 246446 | 763132 | 26286925 | 29676415 |  |  | 2023-05-17 |  | 26286925 | 25277347 | [5 empty] | 26286925 | 25277347 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/138/FEMA%20Detailed%20Scope%20of%20Work%20Trujillo%20Alto%20Phase%201%20High%20Priority%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3389490 |  | 1 | 1 | 1 |  | 691702RFI138 | 691702 |  |  | 0
693543 | 11634 | 12854140.62 | 1643590 | 1899782 |  | 11568798 | 260418 | 1383172 | 13212388 | 15112170 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/137/693543%20FAASt%20Juncos%20Streetlighting%20(Distribution)-Detailed%20Scope%20of%20Work-Rev.%204.pdf?web=1 |  | 2026-02-06 14:50 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 1 | 0.97289 | 1 | 2025-08-06 | 693543RFI137 | 693543 |  |  | 0
693615 | 11685 | 6376770.32 | 700108 | 1579242 |  | 6376770 | 138969 | 561139 | 7076878 | 8656120 | 2024-07-31 | 2024-12-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/136/693615-DR4339PR-Detailed%20SOW%20R%C3%ADo%20Grande%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.90107 | 1 | 2025-08-06 | 693615RFI136 | 693615 |  |  | 0
693788 | 11547 | 5847563.41 | 481369 | 1617458 |  | 5847563 | 104298 | 377071 | 6328932 | 7946390 | 2024-11-30 | 2025-04-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/135/693788-DR4339PR-Detailed%20SOW%20Toa%20Alta%20Phase%201%20High%20Priority%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.92394 | 1 | 2025-08-06 | 693788RFI135 | 693788 |  |  | 0
697183 | 11668 | 9248657.11 | 1117331 | 1940155 |  | 9248657 | 193746 | 923585 | 10365988 | 12306143 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/134/697183-DR4339PR-Detailed%20SOW%20Vega%20Baja%20Phase%201%20-%20High%20Priority%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.89221 | 1 | 2025-08-06 | 697183RFI134 | 697183 |  |  | 0
698424 | 11344 | 10309031.53 | 997190 | 1705096 |  | 9311842 | 277173 | 720017 | 10309032 | 12014128 |  |  | 2023-10-23 |  | 10309031.53 | 9311841.53 | [5 empty] | 10309031.53 | 9311841.53 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/133/698424-DR4339PR-Detailed%20SOW%20Florida%20Rev0%20-%20signed%20-%20DSOW%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1705096.48 |  | 1 | 1 | 1 |  | 698424RFI133 | 698424 |  |  | 0
698427 | 11525 | 4846034.89 | 1028907 | 1377820 |  | 4846035 | 227776 | 801131 | 5874942 | 7252762 | 2024-11-30 | 2025-04-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/132/698427-DR4339PR-Detailed%20SOW%20Maricao%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.82487 | 1 | 2025-08-06 | 698427RFI132 | 698427 |  |  | 0
698432 | 11523 | 6920157.56 | 968057 | 1698467 |  | 6920158 | 190774 | 777283 | 7888215 | 9586682 | 2024-12-31 | 2025-05-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/131/698432-DR4339PR-Detailed%20SOW%20Hormigueros%20Rev2%20-%20DSOW%20-%20signed%2012-23.pdf?web=1 |  | 2026-02-06 14:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.87728 | 1 | 2025-08-06 | 698432RFI131 | 698432 |  |  | 0
698439 | 11526 | 8360922 | 1287705 | 1653390 |  | 7073217 | 0 | 1287705 | 8360922 | 10014312 |  |  | 2023-11-03 | 2024-08-30 | 8360922 | 7073217 | 8360922 | 7073217 |  |  |  | 8360922 | 7073217 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/130/698439-DR4339PR-Detailed%20SOW%20Las%20Mar%C3%ADas%20Rev1%20-%20DSOW%20-%20signed%20(2).pdf?web=1 |  | 2026-02-17 12:34 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1653390 |  | 1 | 1 | 1 |  | 698439RFI130 | 698439 |  |  | 0
698458 | 11518 | 10615811.01 | 853056.42 | 1979750 |  | 9762755 | 0 | 853056.42 | 10615811.42 | 12595561.42 |  |  | 2023-11-03 | 2024-08-30 | 10615811.01 | 9762754.59 | 10615811.01 | 9762754.59 |  |  |  | 10615811.01 | 9762754.59 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/129/698458-DR4339PR-Detailed%20SOW%20Guaynabo%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(2).pdf |  | 2026-02-17 12:34 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1979750.26 |  | 1 | 1 | 1 |  | 698458RFI129 | 698458 |  |  | 0
698511 | 11680 | 1309407 | 153603 | 476439 |  | 1155804 | 62197 | 91406 | 1309407 | 1785846 | 2024-06-30 | 2024-07-31 | 2024-04-12 |  | 1309407 | 1155804 | [5 empty] | 1309407 | 1155804 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/128/PW%2011680%20PRJ_Report_698511_20240412.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 476440 |  | 1 | 1 | 1 |  | 698511RFI128 | 698511 |  |  | 0
698522 | 11582 | 4386770.2 | 519326 | 1374011 |  | 4386770 | 123865 | 395461 | 4906096 | 6280107 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/127/698522-DR4339PR-Detailed%20SOW%20Vieques%20Rev2%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.89415 | 1 | 2025-08-06 | 698522RFI127 | 698522 |  |  | 0
698570 | 11560 | 15946081.93 | 2225874 | 2501126 |  | 13720208 | 0 | 2225874 | 15946082 | 18447208 |  |  | 2023-12-29 | 2024-08-30 | 15946081.93 | 13720208.31 | 15946081.93 | 13720208.31 |  |  |  | 15946081.93 | 13720208.31 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/126/PW11560%20PRJ_Report_698570_20240102.pdf?web=1 |  | 2026-02-17 12:35 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2501126 |  | 1 | 1 | 1 |  | 698570RFI126 | 698570 |  |  | 0
698579 | 11629 | 9410766.24 | 1339801 | 1873982 |  | 8070965 | 414167.51 | 925633.49 | 9410766 | 11284748 | 2024-06-30 | 2024-08-31 | 2024-03-22 |  | 9410766.24 | 8070964.96 | [5 empty] | 9410766.24 | 8070964.96 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/125/PW%2011629%20PRJ_Report_698579_20240322.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1873982.08 |  | 1 | 1 | 1 |  | 698579RFI125 | 698579 |  |  | 0
699814 | 11576 | 15781505 | 1909452 | 2898942 |  | 15781505 | 296320 | 1613132 | 17690957 | 20589899 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/124/699814-DR4339PR-Detailed%20SOW%20Juana%20D%C3%ADaz%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:52 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.89207 | 1 | 2025-08-06 | 699814RFI124 | 699814 |  |  | 0
701472 | 11727 | 7400895.19 | 862126 | 1640383 |  | 6538769 | 0 | 862126 | 7400895 | 9041278 | 2024-06-30 | 2024-08-31 | 2024-05-10 | 2024-08-30 | 7400895.19 | 6538769.44 | 7400895.19 | 6538769.44 |  |  |  | 7400895.19 | 6538769.44 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/123/PRJ_Report_701472_20240510.pdf?web=1 | 2/28/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-17 12:35 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1640383 |  | 1 | 1 | 1 |  | 701472RFI123 | 701472 |  |  | 0
701473 | 11693 | 14314798.95 | 1574362 | 14314799 |  | 2681107 | 1574362 | 0 | 4255469 | 18570268 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/122/1280261-DR4339PR-Detailed%20SOW%20Can%C3%B3vanas%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:52 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 3.3639 | 1 | 2025-08-06 | 701473RFI122 | 701473 |  |  | 0
701495 | 11263 | 25678.75 | 5830.39 | 3960 |  | 19848 | 1221.39 | 4609 | 25678.39 | 29638.39 |  |  | 2023-03-02 |  | 25678.75 | 19848.36 | [5 empty] | 25678.75 | 19848.36 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/121/701495-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2014%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 3959.6 |  | 1 | 1 | 1 |  | 701495RFI121 | 701495 |  |  | 0
701504 | 11268 | 188223 | 37878 | 29252 |  | 150345 | 7935 | 29943 | 188223 | 217475 |  |  | 2023-03-08 |  | 188223 | 150345 | [5 empty] | 188223 | 150345 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/120/701504-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 29252 | 4491 | 1 | 1 | 1 |  | 701504RFI120 | 701504 |  |  | 0
701545 | 11269 | 616229 | 129039 | 95198 |  | 487190 | 27032 | 102007 | 616229 | 711427 |  |  | 2023-03-08 |  | 616229 | 487190 | [5 empty] | 616229 | 487190 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/119/PRJ_Report_701545_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 95198 |  | 1 | 1 | 1 |  | 701545RFI119 | 701545 |  |  | 0
701552 | 11257 | 238162 | 51841 | 36670 |  | 186321 | 10860 | 40981 | 238162 | 274832 |  |  | 2023-03-08 |  | 238162 | 186321 | [5 empty] | 238162 | 186321 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/118/701552-DR4339PR-Detailed%20SOW%20Ponce%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 36670 |  | 1 | 1 | 1 |  | 701552RFI118 | 701552 |  |  | 0
701555 | 11275 | 649427 | 102417 | 104535 |  | 547010 | 21455 | 80962 | 649427 | 753962 |  |  | 2023-03-08 |  | 649427 | 547010 | [5 empty] | 649427 | 547010 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/117/PRJ_Report_701555_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 104535 |  | 1 | 1 | 1 |  | 701555RFI117 | 701555 |  |  | 0
701679 | 11267 | 80651.6 | 16226.16 | 12535 |  | 64425 | 3399.16 | 12827 | 80651.16 | 93186.16 |  |  | 2023-03-02 |  | 80651.6 | 64425.44 | [5 empty] | 80651.6 | 64425.44 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/116/PRJ_Report_701679_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12535.35 |  | 1 | 1 | 1 |  | 701679RFI116 | 701679 |  |  | 0
703222 | 107824 | 4500000 | [5 empty] | 0 | 4500000 | 4500000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/115/703222-DR4339PR-T%20ad%20D%20intelligent%20Re0closers,%20Single%20Phase%20Reclosers%20and%20Fault%20Current%20Indicators%20Group%202.pdf | 4/3/2024 - Received withdrawal status data/info from Project Manager Oscar Fuentes Garcia. FEMA Canceled this FAASt because it wasn’t included in 90 Plan, new FAASt was assigned to this group on December 2023 - 740662 (initial DSOW submission - 12/13/2024) | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 703222RFI115 | 703222 |  |  | 0
703535 | 11636 | 10149325.06 | 620135 | 1814022 |  | 9529190 | 0 | 620135 | 10149325 | 11963347 | 2024-06-30 | 2024-08-31 | 2024-06-18 | 2024-08-30 | 10149325.06 | 9529190.37 | 10149325.06 | 9529190.37 |  |  |  | 10149325.06 | 9529190.37 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/114/PW%2011636%20PRJ_Report_703535_20240618.pdf?web=1 |  | 2026-02-17 12:37 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1814022 |  | 1 | 1 | 1 |  | 703535RFI114 | 703535 |  |  | 0
704679 | 11524 | 16372823.8 | 2060901.35 | 2687464 |  | 14311922 | 0 | 2060901.35 | 16372823.35 | 19060287.35 |  |  | 2023-11-03 | 2024-08-30 | 16372823.8 | 14311922.45 | 16372823.8 | 14311922.45 |  |  |  | 16372823.8 | 14311922.45 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/113/704679-DR4339PR-Detailed%20SOW%20Coamo%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-17 12:37 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2687463.9 |  | 1 | 1 | 1 |  | 704679RFI113 | 704679 |  |  | 0
704741 | 11737 | 17686091.97 | 1110824.64 | 3152500.55 |  | 19122669.84 | 167188.56 | 943636.08 | 20233494.48 | 23385995.03 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/112/704741-DR4339PR-FAASt%20%5BMoca%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work-Rev.%205.pdf?web=1 | 2/28/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 0.8741 | 1 | 2025-08-06 | 704741RFI112 | 704741 | 1190151 | 802329 | 1992480
704744 | 11626 | 22246737.73 | 3663221 | 3725225 |  | 22246738 | 525425 | 3137796 | 25909959 | 29635184 | 2024-08-31 | 2025-01-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/111/DR4339PR-704744-Detailed%20SOW%20San%20Sebasti%C3%A1n%20Rev0%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.85862 | 1 | 2025-08-06 | 704744RFI111 | 704744 |  |  | 0
704750 | 11314 | 578629 | 92244 | 92511 |  | 486385 | 19324 | 72920 | 578629 | 671140 |  |  | 2023-04-06 |  | 578629 | 486385 | [5 empty] | 578629 | 486385 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/110/704750-DR4339PR-Detailed%20SOW%20Bayamon%20Group%2010%20Rev1%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 92511 |  | 1 | 1 | 1 |  | 704750RFI110 | 704750 |  |  | 0
704751 | 11311 | 435167 | 96676 | 66168 |  | 338491 | 20252 | 76424 | 435167 | 501335 |  |  | 2023-04-06 |  | 435167 | 338491 | [5 empty] | 435167 | 338491 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/109/704751-DR4339PR-Detailed%20SOW%20Bayamon%20Group%2011%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 66168 |  | 1 | 1 | 1 |  | 704751RFI109 | 704751 |  |  | 0
704755 | 11352 | 524391.61 | 86181.92 | 83451 |  | 438210 | 0 | 86181.92 | 524391.92 | 607842.92 |  |  | 2023-05-17 |  | 524391.61 | 438209.69 | [5 empty] | 524391.61 | 438209.69 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/108/PRJ_Report_704755_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 83450.9 |  | 1 | 1 | 1 |  | 704755RFI108 | 704755 |  |  | 0
704757 | 11638 | 7956662 | 820333 | 1750406 |  | 7956663 | 147924 | 672409 | 8776996 | 10527402 | 2024-08-31 | 2025-01-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/107/DR4339PR-704757-Detailed%20SOW%20Santa%20Isabel%20Rev0%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:52 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.90654 | 1 | 2025-08-06 | 704757RFI107 | 704757 |  |  | 0
704763 | 107825 | 2800000 | [5 empty] | 0 | 2800000 | 2800000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/106/704763-DR4339PR-Telecom%20Infrastructure%20%E2%80%93%20Group%20C-Rev.%201.pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project will need low level support as we work to procure land needed for the project5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 12/20/2025. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 704763RFI106 | 704763 |  |  | 0
704793 | 11691 | 14713958.38 | 1639888 | 2718070 |  | 14713958 | 255698 | 1384190 | 16353846 | 19071916 | 2024-08-31 | 2025-01-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/105/704793-DR4339PR-Detailed%20SOW%20Yauco%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.89972 | 1 | 2025-08-06 | 704793RFI105 | 704793 |  |  | 0
704805 | 11863 | 6905000 | [5 empty] | 0 | 6905000 | 6905000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/104/704805-DR4339PR-Telecom%20Infrastructure%20%E2%80%93%20Group%20D-Rev.%201.pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 9/30/2024.9/12/2024 - "6/25/2024 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1122383" Grants Portal6/12/2025 - Project withdrawn in Grants Portal | 2026-02-06 13:25 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | 704805RFI104 | 704805 |  |  | 0
704844 | 11340 | 409298 | 88558 | 62490 |  | 320740 | 18552 | 70006 | 409298 | 471788 |  |  | 2023-05-17 |  | 409298 | 320740 | [5 empty] | 409298 | 320740 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/103/704844-DR4339PR-Detailed%20SOW%20Caguas%20Group%2016-17-18-19-20%20Rev0.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 62490 |  | 1 | 1 | 1 |  | 704844RFI103 | 704844 |  |  | 0
704849 | 11658 | 13290413.39 | 1669737 | 2380243 |  | 11620676 | 0 | 1669737 | 13290413 | 15670656 | 2024-06-30 | 2024-08-31 | 2024-05-10 | 2024-08-30 | 13290413.39 | 11620676.42 | 13290413.39 | 11620676.42 |  |  |  | 13290413.39 | 11620676.42 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/102/PRJ_Report_704849_20240510.pdf?web=1 |  | 2026-02-17 12:38 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2380242.99 |  | 1 | 1 | 1 |  | 704849RFI102 | 704849 |  |  | 0
704862 | 11728 | 11333806.13 | 1104923 | 2297199 |  | 11333806 | 1104923 | 0 | 12438729 | 14735928 | 2024-07-31 | 2024-12-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/101/704862-DR4339PR-Detailed%20SOW%20Fajardo%20-%20DSOW-Work%20To%20Be%20Completed%20Rev4%20-%20signed.pdf?web=1 | QC Review Complete: 2/28/2024 | 2026-02-06 14:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.91117 | 1 | 2025-08-06 | 704862RFI101 | 704862 |  |  | 0
704868 | 11650 | 5869029.74 | 716919 | 1481547 |  | 5152111 | 244786.81 | 472132.19 | 5869030 | 7350577 | 2024-06-30 | 2024-08-31 | 2024-07-08 |  | 5869029.74 | 5152111.14 | [5 empty] | 5869029.74 | 5152111.14 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/100/PW%2011650%20PRJ_Report_704868_20240708.pdf?web=1 |  | 2026-01-29 10:45 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  | 1481546.84 |  | 1 | 1 | 1 |  | 704868RFI100 | 704868 |  |  | 0
704916 | 11312 | 303970 | 29974 | 49755 |  | 273996 | 6279 | 23695 | 303970 | 353725 |  |  | 2023-04-06 |  | 303970 | 273996 | [5 empty] | 303970 | 273996 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/99/704916-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2013-14-15-16%20Rev1%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49755 |  | 1 | 1 | 1 |  | 704916RFI99 | 704916 |  |  | 0
704921 | 11675 | 11007375.31 | 1577046 | 2048083 |  | 9430329 | 472894.36 | 1104151.64 | 11007375 | 13055458 | 2024-06-30 | 2024-08-31 | 2024-05-31 |  | 11007375.31 | 9430329.22 | [5 empty] | 11007375.31 | 9430329.22 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/98/PW%2011675%20PRJ_Report_704921_20240531.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2048083.31 |  | 1 | 1 | 1 |  | 704921RFI98 | 704921 |  |  | 0
704927 | 11711 | 13908238.09 | 1820362 | 2420466 |  | 12087876 | 0 | 1820362 | 13908238 | 16328704 | 2024-06-30 | 2024-08-31 | 2024-07-08 | 2024-08-30 | 13908238.09 | 12087876.17 | 13908238.09 | 12087876.17 |  |  |  | 13908238.09 | 12087876.17 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/97/PW%2011711%20PRJ_Report_704927_20240708.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2026-02-17 12:38 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2420466.41 |  | 1 | 1 | 1 |  | 704927RFI97 | 704927 |  |  | 0
704929 | 11635 | 14343817.06 | 2284857 | 2780414 |  | 14343817 | 2284857 | 0 | 16628674 | 19409088 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/95/704929-DR4339PR-Detailed%20SOW%20San%20Lorenzo%20Rev0%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.8626 | 1 | 2025-08-05 | 704929RFI95 | 704929 |  |  | 0
704931 | 11651 | 15436783.23 | 2269186 | 2828651 |  | 15436783 | 351414 | 1917772 | 17705969 | 20534620 | 2024-08-31 | 2025-01-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/94/704931-DR4339PR-Detailed%20SOW%20Camuy%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:54 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.87184 | 1 | 2025-08-05 | 704931RFI94 | 704931 |  |  | 0
704933 | 11465 | 1426151 | 224731 | 231255 |  | 1201420 | 47078 | 177653 | 1426151 | 1657406 |  |  | 2023-08-04 |  | 1426151 | 1201420 | [5 empty] | 1426151 | 1201420 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/93/704933%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2013-14-15-16%20Rev1%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 231255 |  | 1 | 1 | 1 |  | 704933RFI93 | 704933 |  |  | 0
704938 | 11633 | 15615524.51 | 1807601 | 2760454 |  | 13807923 | 522246.69 | 1285354.31 | 15615524 | 18375978 | 2024-06-30 | 2024-08-31 | 2024-04-12 |  | 15615524.51 | 13807923.4 | [5 empty] | 15615524.51 | 13807923.4 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/96/PW%2011633%20PRJ_Report_704938_20240412.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2760454.04 |  | 1 | 1 | 1 |  | 704938RFI96 | 704938 |  |  | 0
704943 | 11664 | 13759586.8 | 2115538 | 2348210 |  | 11644048 | 613589.66 | 1501948.34 | 13759586 | 16107796 | 2024-06-30 | 2024-08-31 | 2024-04-12 |  | 13759586.8 | 11644048.42 | [5 empty] | 13759586.8 | 11644048.42 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/92/PW%2011664%20PRJ_Report_704943_20240412.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2348209.91 |  | 1 | 1 | 1 |  | 704943RFI92 | 704943 |  |  | 0
705503 | 11476 | 1176665.69 | 192105 | 221088 |  | 1396854 | 21294 | 170811 | 1588959 | 1810047 | 2025-01-31 | 2025-06-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/91/705503-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2015-16-17-18-19%20Rev0.pdf?web=1 |  | 2025-08-11 09:11 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 0.74053 | 2 | 2025-08-08 | 705503RFI91 | 705503 |  |  | 0
705527 | 11449 | 767854 | 125133 | 125147 |  | 642721 | 0 | 125133 | 767854 | 893001 |  |  | 2023-07-28 |  | 767854 | 642721 | [5 empty] | 767854 | 642721 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/90/PRJ_Report_705527_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 125147 |  | 1 | 1 | 1 |  | 705527RFI90 | 705527 |  |  | 0
705584 | 11365 | 1842979 | 378483 | 284698 |  | 1464496 | 0 | 378483 | 1842979 | 2127677 |  |  | 2023-06-16 |  | 1842979 | 1464496 | [5 empty] | 1842979 | 1464496 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/89/PRJ_Report_705584_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 284698 |  | 1 | 1 | 1 |  | 705584RFI89 | 705584 |  |  | 0
705657 | 107826 | 6300000 | 19657460 | 466338 |  | 4462681 | 1859214 | 17798246 | 24120141 | 24586479 | 2024-12-31 | 2025-06-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/88/705657-DR4339PR-DSOW%20DA%20MAYAGUEZ%20GROUP%2003-%20REV%20001%20%2012-26-2023%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 0.26119 | 4 | 2025-08-18 | 705657RFI88 | 705657 |  |  | 0
706498 | 107832 | 5800000 | [5 empty] | 0 | 5800000 | 5800000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/87/1302760-DR4339PR-Applicant SOW Transmission and Distribution Group 4 Feb072022.pdf | 4/3/2024 - Received withdrawal status data/info from Project Manager Oscar Fuentes Garcia. FEMA Canceled this FAASt because it wasn’t included in 90 Plan, new FAASt was assigned to this group on December 2023 - 740662 (initial DSOW submission - 12/13/2024) | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 706498RFI87 | 706498 |  |  | 0
708575 | 107839 | 380992 | [5 empty] | 0 | 380992 | 380992 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/86/708575-DR4339PR- ISOW Transmission Line 37400 Cambalache TC - Dos Bocas Hydro Plant.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 115 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708575RFI86 | 708575 |  |  | 0
708577 | 107840 | 190496 | [5 empty] | 0 | 190496 | 190496 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/85/708577-DR4339PR- ISOW Transmission Line 4800 Santa Isabel TC - Santa Isabel Sect.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708577RFI85 | 708577 |  |  | 0
708579 | 11508 | 2154006.76 | 389437.84 | 343118 |  | 1764569 | 0 | 389437.84 | 2154006.84 | 2497124.84 |  |  | 2023-10-23 | 2024-08-30 | 2154006.76 | 1764568.92 | 2154006.76 | 1764568.92 |  |  |  | 2154006.76 | 1764568.92 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/84/708579-DR4339PR-Detailed%20SOW%20Ponce%20Group%2016-17-18-19%20Rev1%20(1).pdf?web=1 |  | 2026-02-17 12:39 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 343118.15 |  | 1 | 1 | 1 |  | 708579RFI84 | 708579 |  |  | 0
708599 | 107841 | 380992 | [5 empty] | 0 | 380992 | 380992 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/83/ISOW-EN-SOW-0001_Rev1 - Line 700 Costa Sur SP - Yauco 2 HP.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708599RFI83 | 708599 |  |  | 0
708630 | 107842 | 285744 | [5 empty] | 0 | 285744 | 285744 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/82/708630-DR4339PR-Line 37400 Dorado TC - Vega Baja TC.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 115 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708630RFI82 | 708630 |  |  | 0
708637 | 11723 | 377354.58 | 73394 | 39574 |  | 303960 | 14229.08 | 59164.92 | 377354 | 416928 | 2024-11-30 | 2025-02-28 | 2024-08-26 | 2024-12-16 | 377354.58 | 303960.92 | 377354.58 | 303960.92 |  |  |  | 377354.58 | 303960.92 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/81/PRJ_Report_708637_20241217.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 39573.63 | 8454.62 | 1 | 1 | 1 |  | 708637RFI81 | 708637 |  |  | 0
708734 | 107843 | 349243 | [5 empty] | 0 | 349243 | 349243 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/80/1305869-DR4339PR- Line 800 Comsat Sect - Cidra Sect (1).pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708734RFI80 | 708734 |  |  | 0
708819 | 107844 | 761985 | [5 empty] | 0 | 761985 | 761985 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/79/708819-DR4339PR-ISOW-EN-SOW-0001_Rev1 - Line 2000 Once de Agosto Sect - San Sebastian TC.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Duplicate FAASt. Project under 712978. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708819RFI79 | 708819 |  |  | 0
708909 | 107845 | 600000 | [5 empty] | 0 | 600000 | 600000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/78/[708909] DR4339PR FAASt [Line 3000 Juncos TC - Rio Blanco HP] (Transimission) ISOW CE.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 712980. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708909RFI78 | 708909 |  |  | 0
708951 | 107846 | 510000 | [5 empty] | 0 | 510000 | 510000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/77/[708951] DR4339PR FAASt [Line 6500 Toro Negro 1 HP - Barranquitas TC] (Transmission) Initial SOW and CE (2).docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 708951RFI77 | 708951 |  |  | 0
709631 | 11627 | 15230881.12 | 1744482 | 2499521 |  | 13486399 | 487450.7 | 1257031.3 | 15230881 | 17730402 | 2024-06-30 | 2024-08-31 | 2024-03-22 |  | 15230881.12 | 13486398.85 | [5 empty] | 15230881.12 | 13486398.85 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/76/PW%2011627%20PRJ_Report_709631_20240322.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2499521.06 |  | 1 | 1 | 1 |  | 709631RFI76 | 709631 |  |  | 0
710026 | 107849 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/75/710026-DR4339PR-FEMA Project Scope of Work Distribution Pole and Conductor Repair - Arecibo Group 17.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 710026RFI75 | 710026 |  |  | 0
710045 | 107849 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/74/710045-DR4339PR- FEMA Project Scope of Work Distribution Pole and Conductor Repair - Mayaguez Group 20 (1).pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 710045RFI74 | 710045 |  |  | 0
710094 | 11639 | 7291385.82 | 195136 | 614123 |  | 7096250 | 29565.32 | 165570.68 | 7291386 | 7905509 | 2024-06-30 | 2024-11-30 | 2024-11-01 |  | 7291385.82 | 7096249.5 | [5 empty] | 7291385.82 | 7096249.5 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/73/PW%2011639%20PRJ_Report_710094_20241104.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 614123.07 |  | 1 | 1 | 1 |  | 710094RFI73 | 710094 |  |  | 0
710099 | 11667 | 6943798.62 | 239377 | 602047 |  | 6704422 | 42926.93 | 196450.07 | 6943799 | 7545846 | 2024-06-30 | 2024-11-30 | 2025-01-07 |  | 6943798.62 | 6704421.69 | [5 empty] | 6943798.62 | 6704421.69 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/72/PRJ_Report_710099_20250114.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 602047.2 | 620667.23 | 1 | 1 | 1 |  | 710099RFI72 | 710099 |  |  | 0
710110 | 11534 | 87774.8 | 2478.06 | 14756 |  | 85297 | 478.06 | 2000 | 87775.06 | 102531.06 |  |  | 2023-10-23 |  | 87774.8 | 85296.74 | [5 empty] | 87774.8 | 85296.74 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/71/PRJ_Report_710110_20250213.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 14756.12 |  | 1 | 1 | 1 |  | 710110RFI71 | 710110 |  |  | 0
710363 | 107850 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/70/1310158-DR4339PR-FEMA Project Scope of Work Distribution Pole and Conductor Repair - Bayamon Group 15 (1).pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 710363RFI70 | 710363 |  |  | 0
710498 | 107851 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/69/[710498] DR4339 FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) ISOW CE.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 710498RFI69 | 710498 |  |  | 0
711172 | 107854 | 539739 | [5 empty] | 0 | 539739 | 539739 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/68/711172-DR4339PR-ISOW- Line 3700 Jobos TC - Maunabo TC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 708637. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 711172RFI68 | 711172 |  |  | 0
711291 | 107855 | 5600000 | [5 empty] | 0 | 5600000 | 5600000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/67/711291-DR4339PR_ISOW_Telecomm Antennas_Moca_Quebradillas_San Sebastian.pdf | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 10/30/2024. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 711291RFI67 | 711291 |  |  | 0
711670 | 11719 | 118160.28 | 23372 | 12341 |  | 94787 | 0 | 23372 | 118159 | 130500 | 2024-06-30 | 2024-08-31 | 2024-06-18 | 2024-08-30 | 118160.28 | 94787.57 | 118160.28 | 94787.57 |  |  |  | 118160.28 | 94787.57 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/66/PW%2011719%20PRJ_Report_711670_20240618.pdf?web=1 |  | 2026-02-17 12:39 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Marlina Crespo |  |  | 12340.69 |  | 1 | 1 | 1 |  | 711670RFI66 | 711670 |  |  | 0
711819 | 11840 | 1804189 | 197625.13 | 201035.14 |  | 2349734.4 | 15575.52 | 182049.61 | 2547359.53 | 2748394.67 | 2025-04-30 | 2025-07-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/65/711819-DR4339PR-Detailed%20SOW%20-%20Line%2013400%20Acacias%20TC-%20San%20German%20Sect.%20Rev.9_signed.pdf?web=1 |  | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  |  |  | 1 | 0.70826 | 2 |  | 711819RFI65 | 711819 | 147447.87 | 21069.57 | 168517.44
711829 | 107856 | 1309000 | [5 empty] | 0 | 1309000 | 1309000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/64/711829-DR4339PR-Project Scope of Work L100 Santa Isabel Sect. - Salinas Sect..DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 711829RFI64 | 711829 |  |  | 0
711856 | 11746 | 11335984.34 | 395663 | 891094 |  | 10940321 | 67251.43 | 328411.57 | 11335984 | 12227078 | 2024-06-30 | 2024-11-30 | 2024-08-26 | 2024-12-16 | 11335984.34 | 10940320.91 | 11335984.34 | 10940320.91 |  |  |  | 11335984.34 | 10940320.91 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/63/PRJ_Report_711856_20241217.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 891093.89 |  | 1 | 1 | 1 |  | 711856RFI63 | 711856 |  |  | 0
711862 | 107857 | 1232000 | [5 empty] | 0 | 1232000 | 1232000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/62/711862 DR4339PR- FAASt FEMA Scope of Work TL100 Ponce TC to Santa Isabel Sect.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 711862RFI62 | 711862 |  |  | 0
711888 | 11640 | 5591713.87 | 165903 | 434785 |  | 5425810 | 0 | 165903 | 5591713 | 6026498 | 2024-06-30 | 2024-08-31 | 2024-03-22 | 2024-08-30 | 5591713.87 | 5425810.57 | 5591713.87 | 5425810.57 |  |  |  | 5591713.87 | 5425810.57 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/61/PRJ_Report_711888_20250213.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-17 12:40 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 434784.65 |  | 1 | 1 | 1 |  | 711888RFI61 | 711888 |  |  | 0
711909 | 107858 | 231000 | [5 empty] | 0 | 231000 | 231000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/60/711909-DR4339PR-FEMA Scope of Work TL100 Jobos TC to Guayama TO.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 711670. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 711909RFI60 | 711909 |  |  | 0
711962 | 107859 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/59/711962-DR4339PR-Project Scope of Work Distribution Pole and Conductor Repair -Mayaguez Group 21.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 711962RFI59 | 711962 |  |  | 0
712963 | 107860 | 231000 | [5 empty] | 0 | 231000 | 231000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/58/712963-DR4339PR-Project Scope of Work L1600 Mayaguez GP - Leon Sect.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 712963RFI58 | 712963 |  |  | 0
712968 | 11666 | 5807772.97 | 178713 | 503551 |  | 5629060 | 35903.97 | 142809.03 | 5807773 | 6311324 | 2024-06-30 | 2024-11-30 | 2024-11-01 |  | 5807772.97 | 5629060 | [5 empty] | 5807772.97 | 5629060 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/57/PW%2011666%20PRJ_Report_712968_20241104.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 503550 |  | 1 | 1 | 1 |  | 712968RFI57 | 712968 |  |  | 0
712977 | 107861 | 154000 | [5 empty] | 0 | 154000 | 154000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/56/[712977] DR4339PR FAASt [L3000 Caguas TC - Caguax Sect] Initial SOW CE.pdf | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided.". | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 712977RFI56 | 712977 |  |  | 0
712978 | 107862 | 1848000 | [5 empty] | 0 | 1848000 | 1848000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/55/712978-DR4339PR-Scope of Work L2000 Once de Agosto Sect. - San Sebastian TC.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2026-02-25 13:35 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 712978RFI55 | 712978 |  |  | 0
712979 | 107863 | 539000 | [5 empty] | 0 | 539000 | 539000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/54/[712979] DR4339 FAASt [TL 12600 Humacao TC to Verde Mar] (Transmission) Initial SOW and Cost Estimate.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 712979RFI54 | 712979 |  |  | 0
712980 | 11754 | 631194.26 | 72118 | 72788 |  | 559077 | 13981.67 | 58136.33 | 631195 | 703983 | 2024-08-31 | 2024-11-30 | 2024-11-01 |  | 631194.26 | 559076.77 | [5 empty] | 631194.26 | 559076.77 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/53/PW%2011754%20PRJ_Report_712980_20241104.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 72787.96 |  | 1 | 1 | 1 |  | 712980RFI53 | 712980 |  |  | 0
712981 | 107864 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/52/FEMA Project Scope of Work Distribution Pole and Conductor Repair - Ponce Group 24.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 712981RFI52 | 712981 |  |  | 0
712982 | 107865 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/51/FEMA Project Scope of Work Distribution Pole and Conductor Repair -Mayaguez Group 23.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-08-08 13:51 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 712982RFI51 | 712982 |  |  | 0
712988 | 107866 | 70500000 | [5 empty] | 0 | 70500000 | 70500000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/50/712988-DR4339PR-Minor Protection, Automation, and Control (PAC) Replacement (1).pdf | 4/8/2024 - Email notification received from Kevin Smeltzer for this FAASt #, placed under a new FAASt # 7466604/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. DSOW for Group 1 we tried to submitted in March 28, but project is withdrawn from GP. DSOW Group 1 is ready to be submitted, as soon the project are active in GP. 3/27/2024: QC Review Complete | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Reliability | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 712988RFI50 | 712988 |  |  | 0
713149 | 107867 | 2000000 | [5 empty] | 0 | 2000000 | 2000000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/49/FEMA Initial Scope of Work - Substation Minor Repairs - Group E-1 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713149RFI49 | 713149 |  |  | 0
713179 | 107868 | 1800000 | [5 empty] | 0 | 1800000 | 1800000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/48/FEMA Project Scope of Work - Substation Minor Repairs - Group D-1 Rev0.pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713179RFI48 | 713179 |  |  | 0
713181 | 107869 | 2600000 | [5 empty] | 0 | 2600000 | 2600000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/47/713181-FEMA Initial Scope of Work - Substation Minor Repairs - Group E-2 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713181RFI47 | 713181 |  |  | 0
713459 | 107870 | 3450000 | [5 empty] | 0 | 3450000 | 3450000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/46/713459-DR4339PR-Substation Minor Repairs - Group A-2 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713459RFI46 | 713459 |  |  | 0
713491 | 107871 | 3800000 | [5 empty] | 0 | 3800000 | 3800000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/45/713491-DR4339PR-FEMA Initial Scope of Work - Substation Minor Repairs - Group A-1 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713491RFI45 | 713491 |  |  | 0
713496 | 107872 | 3500000 | [5 empty] | 0 | 3500000 | 3500000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/44/[713496] DR4339PR FAASt [Substation Minor Repairs - Group H] (Substations) Initial SOW CE (2).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713496RFI44 | 713496 |  |  | 0
713497 | 107873 | 2800000 | [5 empty] | 0 | 2800000 | 2800000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/43/1313998-DR4339PR-FEMA Initial Scope of Work - Substation Minor Repairs - Group C-1 Rev0 (2) (2).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713497RFI43 | 713497 |  |  | 0
713592 | 107874 | 4600000 | [5 empty] | 0 | 4600000 | 4600000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/42/713592-DR4339PR-Telecom Infrastructure.pdf | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 11/15/2024. | 2025-08-08 13:50 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 713592RFI42 | 713592 |  |  | 0
713795 | 11624 | 11909808.29 | 712022.01 | 1974624.75 |  | 12615988.1 | 101922.08 | 610099.93 | 13328010.11 | 15302634.86 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/41/713795-DR4339PR-FAASt%20%5BLares%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work-Rev.%201.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.89359 | 1 | 2025-08-05 | 713795RFI41 | 713795 | 733893 | 494747 | 1228640
714641 | 11630 | 10689504.94 | 694470.58 | 1946225.97 |  | 11592957.26 | 106422.03 | 588048.55 | 12287427.84 | 14233653.81 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/40/714641-DR4339PR-Rinc%C3%B3n%20Streetlight-Detailed%20Scope%20of%20Work%20Rev.%2010.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List 8/12/2025 - Field EHP: In final review. ECD Updated: 8/15/2025. 8/15/2025 10:03 AM AST - EHP Compliance review was completed, project is in Pending PDMG Project Review. | 2025-11-20 12:44 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo | 0 Months |  |  |  | 1 | 0.86995 | 1 |  | 714641RFI40 | 714641 | 750618 | 506022 | 1256640
714654 | 11583 | 876270176 | 544207595 | 16450923 |  | 317095666 | 2421276 | 541786319 | 861303261 | 877754184 |  |  | 2023-12-08 | 2024-05-01 | 873848901 | 873848901 | 332062581 | 332062581 | 876270176 |  | 332062581 | 876270176 | 332062581 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/39/714654-DR4339PR-DSOW%20AMI%2012-8-2023_Amendment_w_Mitigation.pdf?web=1 |  | 2025-09-18 15:09 | 2023-08-14 11:09 | Jahdiel Franqui | Advanced Metering Infrastructure (AMI) | Marlina Crespo |  |  | 1484008 | 2421276 | 1 | 1.0174 | 1 |  | 714654RFI39 | 714654 |  |  | 0
715610 | 107877 | 118409122.46 | 0 | 26336371 |  | 118409122 | 0 | 0 | 118409122 | 144745493 | 2024-07-31 | 2024-10-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/38/715610-DR-4339-PR-%20Detailed%20Scope%20of%20Work%20for%20Network%20Upgrades_11-17-2023%20j%20-%20signed.pdf?web=1 |  | 2025-08-18 15:14 | 2023-08-14 11:09 | Jahdiel Franqui | PREB Mandate | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | 715610RFI38 | 715610 |  |  | 0
718951 | 107882 | 143758497 | 64652304 | 4748151 |  | 91592573 | 3186387 | 61465917 | 156244877 | 160993028 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/37/718951-DR4339PR-%20TLine%2051200%20DSOW10-31-2023%20(002)%20-%20signed.pdf?web=1 |  | 2025-08-18 15:14 | 2023-08-14 11:09 | Jahdiel Franqui | Line 51200 from Costa Sur Steam Plant to Cambalache Gas Plant | Ashleah Dingle |  |  |  |  | 1 | 0.92008 | 1 | 2025-08-18 | 718951RFI37 | 718951 |  |  | 0
718955 | 107883 | 219184721 | 88423396 | 6123395 |  | 146779642 | 4590570 | 83832826 | 235203038 | 241326433 | 2025-05-31 | 2025-10-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/36/718955-DR4339PR-T%20Line%2050200%20DSOW%20Costa%20Sur%20SP%20to%20Bayamon%20TC%2010-31-2023%20-%20signed.pdf?web=1 |  | 2025-08-18 15:14 | 2023-08-14 11:09 | Jahdiel Franqui | Line 50200 from Costa Sur SP to Bayamon TC | Ashleah Dingle |  |  |  |  | 1 | 0.9319 | 1 | 2025-08-18 | 718955RFI36 | 718955 |  |  | 0
718971 | 107884 | 917523716 | 901810364 | 176291 |  | 15713352 | 10005336 | 891805028 | 917523716 | 917700007 | 2025-05-31 | 2025-10-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/35/718971-DR4339-PR%20DSOW-0001_Rev1%20-%20T%20Line%2050300%20from%20Costa%20Sur%20SP%20to%20Aguirre%20SP%20-%20signed%20(2).pdf |  | 2026-02-06 14:54 | 2023-08-14 11:09 | Jahdiel Franqui | Line 50300 from Costa Sur Steam Plant to Aguirre Steam Plant | Jason Fournier |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 718971RFI35 | 718971 |  |  | 0
723002 | 107888 | 70090705.72 | 0 | 6191932.29 |  | 69904580.54 | 0 | 0 | 69904580.54 | 76096512.83 | 2025-02-28 | 2025-05-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/34/723002%20-%20DR%20-%204339PR%20-%20Jobos%20TC%20-%20FEMA%20Project%20Detailed%20Scope%20of%20Work%20Rev.%208%20(11.26.2024).pdf?web=1 | 8/12/2025 11:16AM AST - Field EHP: SHPO consultation process initiated; drafting ongoing. Expected Completion Date (ECD) 8/22/2025. | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Jobos TC | Jason Fournier | 0 Months |  |  |  | 1 | 1.0027 | 1 |  | 723002RFI34 | 723002 |  |  | 0
723077 | 11556 | 100686731.41 | 0 | 583002.82 |  | 3281329.98 | 0 | 0 | 3281329.98 | 3864332.8 |  |  | 2023-12-19 | 2025-04-28 | 100686731.41 | 100686731.41 | 46643078.39 | 46643078.39 |  | 57324983 |  | 46643078.39 | 46643078.39 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/33/PRJ_MultiVersionReport_723077_20250502.pdf?web=1 | 4/24/2024: QC Review Complete | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Sabana Llana TC | Jason Fournier |  |  | 4850983.03 |  | 1 | 30.6847 | 1 |  | 723077RFI33 | 723077 | 57324983 |  | 57324983
723078 | 11555 | 61558468.95 |  | 3713097 |  | 61558469 | 0 | 0 | 61558469 | 65271566 |  |  | 2023-12-19 |  | 61558468.95 | 61558468.95 | [5 empty] | 61558468.95 | 61558468.95 | 2027-09-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/32/PW%2011555%20PRJ_Report_723078_20231219.pdf?web=1 |  | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | San Juan SP TC | Jason Fournier |  |  | 3713096.54 |  | 1 | 1 | 1 |  | 723078RFI32 | 723078 |  |  | 0
723883 | 11696 | 18151116.72 | 145069437.94 |  |  |  | 23074.58 | 145046363.36 | 145069437.94 | 145069437.94 | 2024-06-30 | 2024-08-31 | 2024-06-05 | 2024-07-30 | 18151116.72 | 0 | 18151116.72 | 0 | 24989414.28 |  | 0 | 24989414.28 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/31/Region%201%20San%20Juan%20Group%20A%20-%20PW%20723883%20V2%20DSOW%2011_13_2025.pdf.pdf | Project advancing in the project process flow. Refer to Process Status History for more details. | 2026-02-06 13:00 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier | 0 Months |  | 0 |  | 1 | 0.12512 | 5 |  | 723883RFI31 | 723883 |  |  | 0
724599 | 11738 | 10744021.82 | 725698.37 | 1906868.06 |  | 11479468.51 | 110216.6 | 615481.77 | 12205166.88 | 14112034.94 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/30/724599-DR4339PR-FAASt%20%5BSabana%20Grande%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work%20Rev.%205.pdf?web=1 | 2/28/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.88028 | 1 | 2025-08-05 | 724599RFI30 | 724599 | 725196 | 488884 | 1214080
724600 | 11735 | 8628211.52 | 1350541 | 1704126 |  | 7277670 | 419107.52 | 931433.48 | 8628211 | 10332337 | 2024-06-30 | 2024-08-31 | 2024-05-31 |  | 8628211.52 | 7277670.2 | [5 empty] | 8628211.52 | 7277670.2 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/29/PW%2011735%20PRJ_Report_724600_20240531.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1704125.72 |  | 1 | 1 | 1 |  | 724600RFI29 | 724600 |  |  | 0
724601 | 11739 | 13708224.43 | 1611021 | 2463886 |  | 12097204 | 469330.38 | 1141690.62 | 13708225 | 16172111 | 2024-06-30 | 2024-08-31 | 2024-07-08 |  | 13708224.43 | 12097203.53 | [5 empty] | 13708224.43 | 12097203.53 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/28/PW%2011739%20PRJ_Report_724601_20240708.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2463885.54 |  | 1 | 1 | 1 |  | 724601RFI28 | 724601 |  |  | 0
724603 | 11684 | 9017148.04 | 1044683 | 2012276 |  | 9017148 | 190599 | 854084 | 10061831 | 12074107 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/27/724603-DR4339PR-Detailed%20SOW%20Cabo%20Rojo%20P1%20-%20High%20Priority%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-06 14:54 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.89617 | 1 | 2025-08-05 | 724603RFI27 | 724603 |  |  | 0
724605 | 11732 | 7949936.1 | 469904.54 | 1372729.11 |  | 8219229.32 | 71428.54 | 398476 | 8689133.86 | 10061862.97 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/26/724605-DR4339PR-FAASt%20%5BGuayanilla%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work-%20Rev.%205.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.91493 | 1 | 2025-08-05 | 724605RFI26 | 724605 | 424146 | 285934 | 710080
724669 | 11730 | 10780496.72 | 773133.74 | 2044738.82 |  | 12755671.42 | 113108.63 | 660025.11 | 13528805.16 | 15573543.98 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/25/724669-DR4339PR-FAASt%20%5BCiales%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work-Rev.%205.pdf?web=1 | <div class="ExternalClassDB9581A60FAA41448D386AD98828A1B2"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);">7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List<br></div></div> | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.79686 | 2 | 2025-08-04 | 724669RFI25 | 724669 | 741921 | 500159 | 1242080
724670 | 11731 | 8375887.52 | 406586.59 | 1456883.53 |  | 8833912.82 | 60595.15 | 345991.44 | 9240499.41 | 10697382.94 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/24/724670-DR4339PR-FAASt%20%5BPatillas%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work-Rev.%206.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.90643 | 1 | 2025-08-04 | 724670RFI24 | 724670 | 425484 | 286836 | 712320
724698 | 11734 | 12633614 | 1891152 | 2199844 |  | 10742462 | 552275 | 1338877 | 12633614 | 14833458 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 12633614 | 10742462 | [5 empty] | 12633614 | 10742462 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/23/PW%2011734%20PRJ_Report_724698_20240618.pdf?web=1 | QC Review Complete: 2/28/2024 | 2025-07-18 18:26 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2199843.63 |  | 1 | 1 | 1 |  | 724698RFI23 | 724698 |  |  | 0
724703 | 11671 | 6054726.01 | 740394 | 1504203 |  | 5314332 | 250928.85 | 489465.15 | 6054726 | 7558929 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 6054726.01 | 5314332 | [5 empty] | 6054726.01 | 5314332 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/22/PW%2011671%20PRJ_Report_724703_20240618.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:26 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1504203.15 |  | 1 | 1 | 1 |  | 724703RFI22 | 724703 |  |  | 0
724716 | 11729 | 10455022.32 | 628110.03 | 1872541.02 |  | 11144397.5 | 95914.82 | 532195.21 | 11772507.53 | 13645048.55 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/21/724716-DR4339PR-FAASt%20%5BQuebradillas%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work-Rev.%205.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.88809 | 1 | 2025-08-04 | 724716RFI21 | 724716 | 642240 | 432960 | 1075200
724781 | 11736 | 7948618.17 | 408490.41 | 1433020.87 |  | 8327919.73 | 63060.64 | 345429.77 | 8736410.14 | 10169431.01 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/20/724781-DR4339PR-%20FAASt%20%5BPenuelas%20Streetlighting%5D%20(Distribution)-Detailed%20Scope%20of%20Work-Rev.%205.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.90983 | 1 | 2025-08-04 | 724781RFI20 | 724781 | 398055 | 268345 | 666400
724825 | 11725 | 14650708.44 | 1838230 | 2516456 |  | 12812479 | 526932.49 | 1311297.51 | 14650709 | 17167165 | 2024-06-30 | 2024-08-31 | 2024-05-10 |  | 14650708.44 | 12812478.84 | [5 empty] | 14650708.44 | 12812478.84 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/19/PRJ_Report_724825_20240510.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:26 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2516455.74 |  | 1 | 1 | 1 |  | 724825RFI19 | 724825 |  |  | 0
724828 | 11692 | 6696269.82 | 816844 | 1653580 |  | 6696270 | 161766 | 655078 | 7513114 | 9166694 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/18/724828-DR4339PR-Detailed%20SOW%20Lo%C3%ADza%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.89128 | 1 | 2025-08-04 | 724828RFI18 | 724828 |  |  | 0
724938 | 11673 | 14314104.85 | 1869090 | 2459743 |  | 12445015 | 537278.89 | 1331811.11 | 14314105 | 16773848 | 2024-06-30 | 2024-07-31 | 2024-05-10 |  | 14314104.85 | 12445015.33 | [5 empty] | 14314104.85 | 12445015.33 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/17/PRJ_Report_724938_20240510.pdf?web=1 |  | 2025-07-18 18:26 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2459742.66 |  | 1 | 1 | 1 |  | 724938RFI17 | 724938 |  |  | 0
724941 | 11733 | 11260820.47 | 1686477 | 2317060 |  | 11260820 | 287979 | 1398498 | 12947297 | 15264357 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/16/724941-DR4339PR-Detailed%20SOW%20Aguas%20Buenas-DSOW-Work%20To%20Be%20Completed%20Rev4%20-%20signed.pdf?web=1 |  | 2026-02-24 13:53 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.86974 | 1 | 2025-08-04 | 724941RFI16 | 724941 |  |  | 0
727522 | 107892 | 102855378 | 3098128.05 | 8437.83 |  | 897595.83 | 28586.43 | 3069541.62 | 3995723.88 | 4004161.71 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/15/727522%20FAASt%20Region%203%20Bayamon%20TL%20-%20115kV%20(Vegetation)%20DSOW.V2.pdf?web=1 | 08/07/2025 04:40 PM AST - Project unwithdrawn by System Admin per FEMA Request INC1748838 | 2026-02-06 12:59 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 25.7414 | 1 | 2025-07-07 | 727522RFI15 | 727522 |  |  | 0
727529 | 107893 | 20674478.43 | 44340770.67 | 120822.29 |  | 12967819.92 | 68979.15 | 44271791.52 | 57308590.59 | 57429412.88 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/14/727529%20FAASt%20%5BRegion%206%20Ponce%20TL%20-%20115kV%5D%20(Vegetation)%20DSOW.v3.pdf?web=1 | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 2026-02-06 13:12 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.36076 | 4 | 2025-07-07 | 727529RFI14 | 727529 |  |  | 0
727530 | 107894 | 32605348.76 | 70421923.26 |  |  |  |  | 70421923.26 | 70421923.26 | 70421923.26 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/13/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Ponce%20Group%20A%20%20(4).xlsx?web=1 |  | 2026-02-06 14:54 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.463 | 3 | 2025-07-07 | 727530RFI13 | 727530 |  |  | 0
727531 | 11715 | 4324993.22 | 42520736.92 |  |  |  | 369745.52 | 42150991.4 | 42520736.92 | 42520736.92 | 2024-09-30 | 2024-12-31 | 2025-04-28 |  | 25913934.11 | 6849050.26 | [5 empty] | 25913934.11 | 6849050.26 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/12/PW%2011715%20PRJ_MultiVersionReport_727531_20250429.pdf?web=1 | 7/25/2025 - Work continues to be performed and completed by field crews | 2026-02-06 13:12 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  | 0 |  | 1 | 0.10171 | 5 |  | 727531RFI12 | 727531 |  |  | 0
727540 | 107895 | 42848782.64 | 66510486.76 |  |  |  |  | 66510486.76 | 66510486.76 | 66510486.76 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/11/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20C%20Arecibo%20(2).xlsx?web=1 |  | 2026-02-06 14:55 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.64424 | 2 | 2025-07-07 | 727540RFI11 | 727540 |  |  | 0
727558 | 107896 | 16458603.47 | 16374246.76 |  |  |  |  | 16374246.76 | 16374246.76 | 16374246.76 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/10/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20C%20Bayamon%20(2).xlsx?web=1 |  | 2026-02-06 14:55 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 1.0052 | 1 | 2025-07-07 | 727558RFI10 | 727558 |  |  | 0
727562 | 107897 | 34961938.79 | 84411128.06 |  |  |  |  | 84411128.06 | 84411128.06 | 84411128.06 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/9/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20C%20Mayaguez%20(1).xlsx?web=1 |  | 2026-02-06 14:55 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.41419 | 3 | 2025-07-07 | 727562RFI9 | 727562 |  |  | 0
727572 | 11720 | 8173601.57 | 80353343.34 |  |  |  | 698724.72 | 79654618.62 | 80353343.34 | 80353343.34 | 2024-08-31 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/8/Region%203%20Bayamon%20Group%20A%20-%20PW%20727572%20DSOW%2010_16_2025.pdf?web=1 |  | 2026-02-06 13:12 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.10172 | 5 |  | 727572RFI8 | 727572 |  |  | 0
727606 | 107898 | 16306957.02 | 24722341.5 | 67364.86 |  | 7230250.37 | 33062.87 | 24689278.63 | 31952591.87 | 32019956.73 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/7/727606%20FAASt%20Region%204%20Caguas%20TL%20-%20115kV%20(Vegetation)%20DSOW.V2.pdf?web=1 | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 2026-02-06 13:12 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.51035 | 3 | 2025-07-07 | 727606RFI7 | 727606 |  |  | 0
727608 | 107899 | 18605239.31 | 4008841.52 | 10918.18 |  | 1161449.55 | 36989.58 | 3971851.94 | 5170291.07 | 5181209.25 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/6/727608%20FAASt%20Region%201%20San%20Juan%20TL%20-%20115kV%20(Vegetation)%20DSOW.V2.pdf?web=1 |  | 2026-02-06 13:12 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 3.5985 | 1 |  | 727608RFI6 | 727608 |  |  | 0
727657 | 107900 | 16212759.99 | 2298062.02 | 6258.83 |  | 665799.1 | 21204.22 | 2276857.8 | 2963861.12 | 2970119.95 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/5/727657%20FAASt%20Region%205%20Mayaguez%20TL%20-%20115kV%20(Vegetation)%20DSOW.V2.pdf | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 2026-02-06 13:12 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 5.4701 | 1 | 2025-07-07 | 727657RFI5 | 727657 |  |  | 0
727659 | 107901 | 18075945.32 | 3793220.88 | 10330.93 |  | 1098979.51 | 35000.05 | 3758220.83 | 4892200.39 | 4902531.32 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/4/727659%20FAASt%20Region%202%20Arecibo%20TL%20-%20115kV%20(Vegetation)%20DSOW.V2.pdf?web=1 | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 2026-02-06 13:12 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 3.6948 | 1 | 2025-07-07 | 727659RFI4 | 727659 |  |  | 0
727691 | 107902 | 18245048.09 | 44200121.5 |  |  |  |  | 44200121.5 | 44200121.5 | 44200121.5 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/3/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20C%20San%20Juan%20(1).xlsx?web=1 |  | 2026-02-06 14:55 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.41278 | 3 | 2025-08-11 | 727691RFI3 | 727691 |  |  | 0
727692 | 11724 | 4681848.01 | 46038244.43 |  |  |  | 328143.02 | 45710101.41 | 46038244.43 | 46038244.43 | 2024-09-30 | 2024-12-31 | 2025-04-28 |  | 28052090.37 | 7414164.75 | [5 empty] | 28052090.37 | 7414164.75 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/2/PW%2011724%20PRJ_MultiVersionReport_727692_20250429.pdf?web=1 | 18JULY2024 Project was split into High and Low Density which reduced the total miles in the previous submittal for this project. So if the High and Low Density project values are added together, it will equate to the original submission total.7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List7/25/2025 - Work continues to be performed and completed by field crews | 2026-02-06 13:11 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.10169 | 5 |  | 727692RFI2 | 727692 |  |  | 0
727694 | 107903 | 41689596.63 | 76781710.48 |  |  |  |  | 76781710.48 | 76781710.48 | 76781710.48 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20C%20Caguas%20(1).xlsx?web=1 |  | 2026-02-06 14:55 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.54296 | 3 | 2025-07-07 | 727694RFI1 | 727694 |  |  | 0
728827 | 11714 | 3036845.07 | 29878565.39 |  |  |  | 259813.59 | 29618751.8 | 29878565.39 | 29878565.39 | 2024-09-30 | 2024-12-31 | 2025-04-28 |  | 18194308.81 | 4807675.47 | [5 empty] | 18194308.81 | 4807675.47 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/396/PW%2011714%20PRJ_MultiVersionReport_728827_20250429.pdf?web=1 | 7/25/2025 - Work continues to be performed and completed by field crews. | 2026-02-06 13:12 | 2023-08-14 13:38 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  | 79166.85 |  | 1 | 0.10164 | 5 |  | 728827RFI396 | 728827 |  |  | 0
728832 | 11718 | 2380535.97 | 23418437.42 |  |  |  | 203638.57 | 23214798.85 | 23418437.42 | 23418437.42 | 2024-08-31 | 2024-11-30 | 2025-04-28 |  | 14260691.9 | 3767690.42 | [5 empty] | 14260691.9 | 3767690.42 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/395/PW%2011718%20PRJ_MultiVersionReport_728832_20250429.pdf?web=1 | <div class="ExternalClass117FD3EDD6014C58A48DC9570AAC4B93"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);">7/25/2025 - Thomas Miller - Work continues to be performed and completed by field crews</div></div> | 2026-02-06 13:12 | 2023-08-14 13:37 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  | 62820.38 |  | 1 | 0.10165 | 5 |  | 728832RFI395 | 728832 |  |  | 0
729286 | 11726 | 15413889.89 | 0 | 2006783 |  | 15413890 | 0 | 0 | 15413890 | 17420673 | 2024-06-30 | 2024-08-31 | 2024-07-08 | 2024-08-30 | 15413889.89 | 15413889.89 | 15413889.89 | 15413889.89 |  |  |  | 15413889.89 | 15413889.89 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/400/PW%2011726%20PRJ_Report_729286_20240708.pdf?web=1 |  | 2026-02-17 11:27 | 2023-08-24 08:11 | Gabriel Licha | Substation High Voltage Equipment Replacement | Marlina Crespo |  |  | 2006783 |  | 1 | 1 | 1 |  | 729286RFI398 | 729286 |  |  | 0
729522 | 107905 | 700000000 | [5 empty] | 0 | 700000000 | 700000000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/398/729522-DR4339PR-ISOW%20FAASt%20Transmission%20&%20Distribution%20Automation%20Program%20.PDF?web=1 | 9/12/2024 - GP Notes "9/5/2024 The project was withdrawn with the comment "Applicant requested project withdrawal, for reference see: 729522-DR4339PR-Applicant requested project withdrawal.pdf". | 2025-07-18 18:27 | 2023-08-22 10:37 | Gabriel Licha | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 | 1 |  | 729522RFI397 | 729522 |  |  | 0
730513 | 107907 | 38886020 | 10929872 | 3184390 |  | 24634172 | 1251143 | 9678729 | 35564044 | 38748434 | 2024-11-30 | 2025-05-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/404/DR4339PR-730513-%2010148%20Caguas%20ST%20Group%204%20DSOW%20-R1.docx?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-08-18 15:16 | 2023-09-01 14:32 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 4 | Ashleah Dingle |  |  |  |  | 1 | 1.0934 | 1 | 2025-08-15 | 730513RFI401 | 730513 |  |  | 0
730541 | 107908 | 31124653 | 18671456 | 2070079 |  | 12453197 | 2618347 | 16053109 | 31124653 | 33194732 | 2024-10-31 | 2025-04-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/405/730541-DR4339-DSOW%20CAGUAS%208.pdf?web=1 |  | 2026-02-24 13:47 | 2023-09-01 14:34 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 8 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 730541RFI402 | 730541 |  |  | 0
730586 | 107909 | 26972761 | 12719346 | 4716393 |  | 14253415 | 3101803 | 9617543 | 26972761 | 31689154 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/406/730586-DR4339PR-DSOW-%20Ponce%20STG%201.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-24 13:47 | 2023-09-01 14:35 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 730586RFI403 | 730586 |  |  | 0
730657 | 11559 | 0 | [5 empty] | 0 | 103800000 | 103800000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/409/334468-DR4339PR-Initial%20SOW%20(2).pdf?web=1 |  | 2026-02-24 13:53 | 2023-09-11 14:47 | Marlina Crespo | Line 2200 Dos Bocas HP to Dorado TC | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 | 2025-08-18 | 730657RFI406 | 730657 |  |  | 0
730784 | 107910 | 6010000 | [5 empty] | 0 | 6010000 | 6010000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/410/73784-DR4339PR-Line%206700%20Martin%20Pe%C3%B1a%20TC%20to%20Villamar%20Sect.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 5/24/2024. | 2025-07-18 18:27 | 2023-09-12 08:42 | Marlina Crespo | Line 6700 Martin Peña TC to Villamar Sect. | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 |  | 730784RFI407 | 730784 |  |  | 0
730821 | 107911 | 80513487 | 27363279 | 6380697 |  | 53150208 | 2513389 | 24849890 | 80513487 | 86894184 | 2025-04-30 | 2025-10-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/402/10134-EN-SOW-0001_Rev%20ARECIBO%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-08-18 15:28 | 2023-09-01 14:28 | Marlina Crespo | Distribution Feeders - Arecibo Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-15 | 730821RFI399 | 730821 |  |  | 0
730824 | 107912 | 42380000 | 2840853 | 1157768 |  | 2957665 | 799199 | 2041654 | 5798518 | 6956286 | 2025-06-30 | 2025-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/403/DR4339PR-730824-FEMA%20Detailed%20Scope%20of%20Work%20-%20Ponce%20Short%20Term%20Group%202%20-%20signed.pdf?web=1 |  | 2026-02-24 13:47 | 2023-09-01 14:30 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1 | 7.3088 | 1 | 2025-08-15 | 730824RFI400 | 730824 |  |  | 0
734393 | 11805 | 7838709 | 1016421 | 1851275 |  | 7838709 | 194188 | 822233 | 8855130 | 10706405 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/444/734393-DR4339PR-Detailed%20SOW%20Cabo%20Rojo%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 10:34 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.88522 | 1 | 2025-08-06 | 734393RFI416 | 734393 |  |  | 0
734396 | 107915 | 6205493 | 1169678 | 1692815 |  | 6988631 | 228078 | 941600 | 8158309 | 9851124 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/446/734396-DR4339PR-Detailed%20SOW%20Cabo%20Rojo%20P3%20Low%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 10:37 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 0.76063 | 2 | 2025-08-06 | 734396RFI418 | 734396 |  |  | 0
734728 | 11774 | 12998720.23 | 1402396 | 2475101 |  | 12998720 | 224318 | 1178078 | 14401116 | 16876217 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/450/734728-DR4339PR-Detailed%20SOW%20Ponce%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-07 15:04 | 2023-10-11 10:44 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.90262 | 1 | 2025-08-06 | 734728RFI422 | 734728 |  |  | 0
734760 | 11830 | 13799462 | 1946734 | 2696696 |  | 13799462 | 318240 | 1628494 | 15746196 | 18442892 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/448/734760-DR4339PR-Detailed%20SOW%20Ponce%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-11-19 16:25 | 2023-10-11 10:39 | Marlina Crespo | Distribution Streetlighting | Marlina Crespo |  |  |  |  | 1 | 0.87637 | 1 | 2025-08-06 | 734760RFI420 | 734760 |  |  | 0
734789 | 107916 | 5424696 | 635977 | 1444780 |  | 6296106 | 145939 | 490038 | 6932083 | 8376863 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/457/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guayama%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 10:57 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.78255 | 2 | 2025-08-06 | 734789RFI429 | 734789 |  |  | 0
734791 | 11808 | 5650820 | 757008 | 1536868 |  | 5650820 | 161863 | 595145 | 6407828 | 7944696 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/455/734791-DR4339PR-Detailed%20SOW%20Guayama%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-07 15:04 | 2023-10-11 10:55 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.88186 | 1 | 2025-08-06 | 734791RFI427 | 734791 |  |  | 0
734853 | 11837 | 15679863.58 | 2684586 | 2921897 |  | 15679863 | 421685 | 2262901 | 18364449 | 21286346 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/475/734853-DR4339PR-Detailed%20SOW%20Arecibo%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-12 08:54 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.85382 | 1 | 2025-08-06 | 734853RFI447 | 734853 |  |  | 0
734859 | 11780 | 8885681.25 | 1346103 | 1987953 |  | 8885681 | 246099 | 1100004 | 10231784 | 12219737 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/476/734859-DR4339PR-Detailed%20SOW%20Aguadilla%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | QC Review Complete: 3/25/20247/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-07 15:04 | 2023-10-12 08:55 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.86844 | 1 | 2025-08-06 | 734859RFI448 | 734859 |  |  | 0
734927 | 11773 | 8007445.57 | 1301829 | 1834728 |  | 8007445 | 242681 | 1059148 | 9309274 | 11144002 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/453/734927-DR4339PR-Detailed%20SOW%20Isabela%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | 3/25/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-11 09:13 | 2023-10-11 10:48 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.86016 | 1 | 2025-08-05 | 734927RFI425 | 734927 |  |  | 0
734928 | 107917 | 5293882 | [5 empty] | 0 | 5293882 | 5293882 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/452/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Isabela%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-11 09:14 | 2023-10-11 10:45 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 1 | 2025-08-05 | 734928RFI424 | 734928 |  |  | 0
735131 | 11775 | 11247096.52 | 1546160 | 2337125 |  | 11247096 | 266012 | 1280148 | 12793256 | 15130381 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/474/735131-DR4339PR-Detailed%20SOW%20Arecibo%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | QC Review Complete: Mar 25 20247/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-11 09:14 | 2023-10-12 08:53 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.87914 | 1 | 2025-08-05 | 735131RFI446 | 735131 |  |  | 0
735338 | 11834 | 8195391 | 1423703 | 1856753 |  | 8195391 | 262975 | 1160728 | 9619094 | 11475847 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/479/735338-DR4339PR-Detailed%20SOW%20Aguadilla%20P3%20Low%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-11-19 16:29 | 2023-10-20 13:30 | Marlina Crespo | Distribution Streetlighting | Marlina Crespo | 0 Months |  |  |  | 1 | 0.85199 | 1 | 2025-08-05 | 735338RFI451 | 735338 |  |  | 0
735357 | 11777 | 7368131.58 | 1097078 | 1731118 |  | 7368132 | 208717 | 888361 | 8465210 | 10196328 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/451/735357-DR4339PR-Detailed%20SOW%20Mayag%C3%BCez%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-11 09:15 | 2023-10-11 10:44 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.8704 | 1 | 2025-08-05 | 735357RFI423 | 735357 |  |  | 0
735360 | 11832 | 13951292 | 2189842 | 2675465 |  | 13951292 | 352374 | 1837468 | 16141134 | 18816599 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/449/735360-DR4339PR-Detailed%20SOW%20Mayaguez%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-11 09:16 | 2023-10-11 10:40 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 0.86433 | 1 | 2025-08-05 | 735360RFI421 | 735360 |  |  | 0
735470 | 11804 | 17963819 | 1727642 | 3031817 |  | 17963819 | 249476 | 1478166 | 19691461 | 22723278 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/478/735470-DR4339PR-Detailed%20SOW%20Bayam%C3%B3n%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero.11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-06 09:21 | 2023-10-12 08:56 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.91226 | 1 | 2025-08-05 | 735470RFI450 | 735470 |  |  | 0
735472 | 11833 | 18291400 | 2632407 | 3249865 |  | 18291400 | 397144 | 2235263 | 20923807 | 24173672 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/477/735472-DR4339PR-Detailed%20SOW%20Bayam%C3%B3n%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero.11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-06 09:21 | 2023-10-12 08:56 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 0.87419 | 1 | 2025-08-05 | 735472RFI449 | 735472 |  |  | 0
735474 | 107918 | 3500000 | 584317.53 | 1524520.51 | 1144636.03 | 18356551.25 | 44806.65 | 539510.88 | 18940868.78 | 20465389.29 | 2026-05-31 | 2026-09-30 | 2025-09-17 |  | 14075641 | 14075641 |  |  |  | 2709364 |  | 14075641 | 14075641 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/445/735474-DR4339PR-Detailed%20SOW%20Caguas%20Group%203%20-%20Phase%202%20-V1-REV3%20.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. DSOW was submitted 3.27.2024 on project 136271 for FEMA revision and project formulation.3/25/2024: QC Review Complete11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 | 2026-02-25 16:18 | 2023-10-11 10:35 | Marlina Crespo | Distribution Streetlighting | Marlina Crespo |  |  | 1962096.73 | 0 | 1 | 0.18479 | 5 |  | 735474RFI417 | 735474 | 1317347.93 | 295487.07 | 1612835
735483 | 107919 | 5377685 | [5 empty] | 0 | 5377685 | 5377685 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/447/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Vega%20Baja%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-06 09:18 | 2023-10-11 10:38 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 1 | 2025-08-05 | 735483RFI419 | 735483 |  |  | 0
735487 | 107920 | 5817139 | 916292 | 1627090 |  | 7901161 | 188693 | 727599 | 8817453 | 10444543 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/454/735487-DR4339PR-FAASt%20%5BHumacao%20Streetlighting%20-Part%203%20(Distribution)-Detailed%20Scope%20of%20Work%20Rev.%200.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-06 09:17 | 2023-10-11 10:49 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 0.65973 | 2 | 2025-08-05 | 735487RFI426 | 735487 |  |  | 0
735493 | 11799 | 6274071 | 916292 | 1627090 |  | 6274071 | 188693 | 727599 | 7190363 | 8817453 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/456/735493-DR4339PR-Detailed%20SOW%20Humacao%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-06 09:19 | 2023-10-11 10:56 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 1 | 0.87257 | 1 | 2025-08-05 | 735493RFI428 | 735493 |  |  | 0
735496 | 11835 | 14764763 | 2019124 | 2756137 |  | 14764763 | 317620 | 1701504 | 16783887 | 19540024 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/458/735496-DR4339PR-Detailed%20SOW%20Carolina%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-06 09:20 | 2023-10-11 11:04 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 0.8797 | 1 | 2025-08-05 | 735496RFI430 | 735496 |  |  | 0
735499 | 107921 | 7033301 | [5 empty] | 0 | 7033301 | 7033301 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/459/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guaynabo%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 11:06 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 1 | 1 | 2025-08-06 | 735499RFI431 | 735499 |  |  | 0
735665 | 11783 | 12296300.92 | 557536 | 2334972 |  | 12296301 | 88976 | 468560 | 12853837 | 15188809 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/460/735665-DR4339PR-Detailed%20SOW%20Carolina%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | 3/25/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-07 15:04 | 2023-10-11 11:07 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.95662 | 1 | 2025-08-06 | 735665RFI432 | 735665 |  |  | 0
735672 | 11838 | 11986815 | 1624355 | 2432645 |  | 11986815 | 274039 | 1350316 | 13611170 | 16043815 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/461/735672-DR4339PR-Detailed%20SOW%20Caguas%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 11:08 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 0.88066 | 1 | 2025-08-06 | 735672RFI433 | 735672 |  |  | 0
735677 | 11801 | 7566377 | 1014066 | 1759349 |  | 7566377 | 191308 | 822758 | 8580443 | 10339792 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/462/735677-DR4339PR-Detailed%20SOW%20Guaynabo%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 11:09 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.88182 | 1 | 2025-08-06 | 735677RFI434 | 735677 |  |  | 0
735940 | 11806 | 7551926.09 | 1067250 | 1758054 |  | 7551927 | 201535 | 865715 | 8619177 | 10377231 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/463/735940-DR4339PR-Detailed%20SOW%20Vega%20Baja%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 11:09 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.87618 | 1 | 2025-08-06 | 735940RFI435 | 735940 |  |  | 0
735952 | 11831 | 7111974 | 1149506 | 1726148 |  | 7111974 | 224507 | 924999 | 8261480 | 9987628 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/464/735952-DR4339PR-Detailed%20SOW%20Trujillo%20Alto%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 11:12 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 0.86086 | 1 | 2025-08-06 | 735952RFI436 | 735952 |  |  | 0
735954 | 11772 | 6426439.39 | 884864 | 1636132 |  | 6426439 | 179565 | 705299 | 7311303 | 8947435 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/465/735954-DR4339PR-Detailed%20SOW%20Trujillo%20Alto%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-07 15:04 | 2023-10-11 11:16 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.87897 | 1 | 2025-08-06 | 735954RFI437 | 735954 |  |  | 0
735959 | 107922 | 5878458 | [5 empty] | 0 | 5878458 | 5878458 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/466/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Baja%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:04 | 2023-10-11 11:16 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 1 | 1 | 2025-08-06 | 735959RFI438 | 735959 |  |  | 0
735960 | 11803 | 7964179 | 1238774 | 1818344 |  | 7964179 | 230260 | 1008514 | 9202953 | 11021297 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/467/735960-DR4339PR-Detailed%20SOW%20Toa%20Baja%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 14:52 | 2023-10-11 11:17 | Marlina Crespo | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.86539 | 1 | 2025-08-06 | 735960RFI439 | 735960 |  |  | 0
737699 | 107923 | 5526895 | [5 empty] | 0 | 5526895 | 5526895 | [11 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/468/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Alta%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:08 | 2023-10-11 11:18 | Marlina Crespo | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 1 | 1 | 1 | 2025-08-07 | 737699RFI440 | 737699 |  |  | 0
737707 | 11797 | 7066938 | 979674 | 1741115 |  | 7066938 | 193656 | 786018 | 8046612 | 9787727 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/469/737707-DR4339PR-Detailed%20SOW%20Toa%20Alta%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:10 | 2023-10-11 11:19 | Marlina Crespo | Distribution Streetlighting | Jason Fournier |  |  |  |  | 1 | 0.87825 | 1 | 2025-08-07 | 737707RFI441 | 737707 |  |  | 0
737712 | 11836 | 27223280 | 3250259 | 4358459 |  | 27223280 | 448553 | 2801706 | 30473539 | 34831998 | [11 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/470/737712-DR4339PR-Detailed%20SOW%20San%20Juan%20P3%20Low%20Priority-DSOW-WtbC%20R1%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:11 | 2023-10-11 11:23 | Marlina Crespo | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 1 | 0.89334 | 1 | 2025-08-07 | 737712RFI442 | 737712 |  |  | 0
737798 | 107924 | 4962759 | 877731 | 1513312 |  | 7059041 | 188168 | 689563 | 7936772 | 9450084 | [11 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/472/%5B737798%5DFAASt%20%5BRio%20Grande%20Streetlighting%20%E2%80%93%20Part%203%5D%20(Distribution)-Detailed%20Scope%20of%20Work%20Rev.%200.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-08-07 15:12 | 2023-10-11 11:25 | Marlina Crespo | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 1 | 0.62529 | 2 | 2025-08-07 | 737798RFI444 | 737798 |  |  | 0
737804 | 11809 | 6104606.88 | 838135 | 1588337 |  | 6104607 | 173048 | 665087 | 6942742 | 8531079 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/473/737804-DR4339PR-Detailed%20SOW%20R%C3%ADo%20Grande%20P2%20Medium%20Priority-DSOW-WtbC%20-%20signed.pdf?web=1 | <div class="ExternalClass8A3DEC4383DF43B983FFB9D352A22D75"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);"><span style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero.&#160;</span><br></div></div><div style="margin-top&#58;0px;margin-bottom&#58;0px;"><span style="color&#58;rgb(0, 0, 0);font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;14.6667px;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">11/29 The project was withdrawn.</span><br style="color&#58;rgb(0, 0, 0);font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;14.6667px;background-color&#58;rgb(255, 255, 255);"><span style="color&#58;rgb(0, 0, 0);font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;14.6667px;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831<p><span style="font-size&#58;14px;color&#58;rgb(50, 49, 48);">7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List</span><br></p></span></div> | 2025-08-08 11:45 | 2023-10-11 11:26 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.87928 | 1 | 2025-08-07 | 737804RFI445 | 737804 |  |  | 0
737825 | 107925 | 7140000 | [5 empty] | 0 | 7140000 | 7140000 | [11 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/437/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20San%20Juan%20Group%201%20-%20Phase%202.pdf?web=1 | Project was resubmitted into Grants Portal under a new FAAst #. Old number was 737825. New number is 742070. Edited on 01/10/2024 by J Fournier. 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-10-09 09:00 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 |  | 737825RFI409 | 737825 |  |  | 0
738120 | 11850 | 11451170.81 | 286036 | 1159111 |  | 11041271 | 175368.81 | 110667.19 | 11327307 | 12486418 | 2024-06-30 | 2024-11-30 | 2024-11-25 |  | 11451170.81 | 11041271 | [5 empty] | 11451170.81 | 11041271 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/471/PW%2011850%20PRJ_Report_738120_20241126.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. DSOW was submitted 3.27.2024 on project 136271 for FEMA revision and project formulation.11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:24 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 1159111 |  | 1 | 1.0109 | 1 |  | 738120RFI443 | 738120 |  |  | 0
738143 | Project Not In GP | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/439/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20San%20Juan%20Group%202%20-%20Phase%202.pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. Project was resubmitted into Grants Portal under a new FAAst #7420269/13/2024 - GP Notes "11/29/2023 The project was deleted" - GP Query pulls as old status "Pending Formulation Completion" ensure to filter out project | 2025-08-11 09:21 | 2023-10-09 09:03 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2023-11-29 | 738143RFI411 | 738143 |  |  | 0
738667 | 107927 | 6120000 | 33268.04 | 1724241.14 |  | 14893960.55 | 17535.19 | 15732.85 | 14927228.59 | 16651469.73 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/438/738667-DR4339PR-Detailed%20SOW%20Ponce%20Group%202%20-%20Phase%202%20Rev3%20-%20signed.pdf?web=1 |  | 2025-11-19 16:04 | 2023-10-09 09:02 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  |  |  | 1 | 0.40999 | 3 | 2025-08-08 | 738667RFI410 | 738667 | 1436520 | 138772.32 | 1575292.32
738670 | 11712 | 5074511.01 | 147871 | 439975 |  | 4926640 | 31370.9 | 116500.1 | 5074511 | 5514486 | 2024-06-30 | 2024-11-30 | 2024-11-25 |  | 5074511.01 | 4926640 | [5 empty] | 5074511.01 | 4926640 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/436/PW%2011712%20PRJ_Report_738670_20241126.pdf?web=1 |  | 2025-07-18 18:27 | 2023-10-09 08:57 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 439974.62 |  | 1 | 1 | 1 |  | 738670RFI408 | 738670 |  |  | 0
738671 | 11819 | 216800000 | 55941767.5 | 0 |  | 0 | 5211394.35 | 50730373.15 | 55941767.5 | 55941767.5 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/480/738671%20-%20FEMA%20DSOW%2025%20MW%20BESS%20Installation%20&%20Integration%20-%20Barceloneta%20signed.pdf?web=1 |  | 2026-02-06 14:57 | 2023-10-25 16:59 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Jason Fournier |  |  |  |  | 1 | 3.8755 | 1 | 2025-08-07 | 738671RFI452 | 738671 | 0 | 30411453.8 | 30411453.8
738672 | 11686 | 10619758.37 | 306131 | 834793 |  | 10313627 | 63002.37 | 243128.63 | 10619758 | 11454551 | 2024-06-30 | 2024-11-30 | 2024-11-25 |  | 10619758.37 | 10313627 | [5 empty] | 10619758.37 | 10313627 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/440/PW%2011686%20PRJ_Report_738672_20241126.pdf?web=1 |  | 2025-07-18 18:27 | 2023-10-09 09:05 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 834793 |  | 1 | 1 | 1 |  | 738672RFI412 | 738672 |  |  | 0
738674 | 107928 | 9180000 | 28130.53 | 922352.8 |  | 8013484.69 | 14786.8 | 13343.73 | 8041615.22 | 8963968.02 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/441/738674-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%202%20-%20Phase%202%20Rev3%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-11-19 16:06 | 2023-10-09 09:07 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo | 0 months |  |  |  | 1 | 1.1416 | 1 | 2025-08-08 | 738674RFI413 | 738674 | 727458.75 | 84241.09 | 811699.84
738692 | 107929 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/443/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Carolina%20Group%201%20-%20Phase%202.pdf?web=1 |  | 2025-08-12 11:15 | 2023-10-09 09:10 | Marlina Crespo | Distribution Pole & Conductor Replacement | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-11 | 738692RFI415 | 738692 |  |  | 0
738696 | 107930 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/442/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Carolina%20Group%202%20-%20Phase%202.pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-10-09 09:08 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 |  | 738696RFI414 | 738696 |  |  | 0
738971 | 11812 | 14261249.67 | 377124 | 1643630 |  | 13884126 | 66835.67 | 310288.33 | 14261250 | 15904880 | 2024-07-31 | 2024-10-31 | 2025-02-06 |  | 14261249.67 | 13884126 | [5 empty] | 14261249.67 | 13884126 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/408/PW%2011812%20PRJ_Report_738971_20250207.pdf?web=1 |  | 2025-07-18 18:27 | 2023-09-07 15:54 | Gabriel Licha | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 1643630 | 33543 | 1 | 1 | 1 |  | 738971RFI405 | 738971 |  |  | 0
738972 | 107931 | 3500000 | [5 empty] | 0 | 3500000 | 3500000 | [11 empty] | 0 | 0 | 2019-03-20 | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/407/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Caguas%20Group%203%20-%20Phase%202%20(2).pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-09-07 15:51 | Gabriel Licha | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 |  | 738972RFI404 | 738972 |  |  | 0
740406 | 107933 | 691016.47 | 5894785.29 |  |  |  | 1682447.99 | 4212337.3 | 5894785.29 | 5894785.29 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/483/Region%201_San%20Juan%20Group%20B%20-%20PW%20740406%20DSOW%202_19_25.pdf?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:36 PM AST Project Updated Title: FAASt [Region 1-San Juan Group B] High Density (Vegetation) - FAASt [Region 1-San Juan Group B] (Vegetation) FAASt #756472 merged under project | 2026-02-06 14:57 | 2023-12-11 09:28 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.11723 | 5 | 2025-08-15 | 740406RFI455 | 740406 |  |  | 0
740408 | 107934 | 1049080.08 | 11782088.78 | 0 |  | 0 | 1838308.82 | 9943779.96 | 11782088.78 | 11782088.78 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/484/Region%203_Bayamon%20Group%20B%20-%20PW%20740408%20DSOW%202_19_25.pdf?web=1 | 10/22/2024 - Grants Portal 10/17/2024 02:39 PM AST Project UpdatedTitle: FAASt [Region 3-Bayamon Group B] High Density (Vegetation) - FAASt [Region 3-Bayamon Group B] (Vegetation) FAASt #756474 merged under project | 2026-02-06 15:26 | 2023-12-11 09:28 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.08904 | 5 | 2025-08-15 | 740408RFI456 | 740408 |  |  | 0
740409 | 107935 | 3068261.01 | 23846154.02 |  |  |  | 2150317.53 | 21695836.49 | 23846154.02 | 23846154.02 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/485/Region%204_Caguas%20Group%20B%20-%20PW%20740409%20DSOW%2012_19_25.pdf?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:39 PM AST Project UpdatedTitle: FAASt [Region 4-Caguas Group B] High Density (Vegetation) - FAASt [Region 4-Caguas Group B] (Vegetation) FAASt 756476 MERGED UNDER PROJECT | 2026-02-06 15:26 | 2023-12-11 09:29 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.12867 | 5 | 2025-08-15 | 740409RFI457 | 740409 |  |  | 0
740410 | 107936 | 30966.29 | 5425376.76 | 0 |  | 0 | 1658267.85 | 3767108.91 | 5425376.76 | 5425376.76 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/486/Region%202_Arecibo%20Group%20B%20-%20PW%20740410%20DSOW%202_19_25.pdf | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:40 PM AST Project UpdatedTitle: FAASt [Region 2-Arecibo Group B] High Density (Vegetation) - FAASt [Region 2-Arecibo Group B] (Vegetation) FAASt 756475 MERGED UNDER PROJECT | 2026-02-06 15:26 | 2023-12-11 09:29 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.0057077 | 5 | 2025-08-15 | 740410RFI458 | 740410 |  |  | 0
740411 | 107937 | 720951.73 | 3777166.88 | 0 |  | 0 | 1618073.62 | 2159093.26 | 3777166.88 | 3777166.88 | 2024-09-30 | 2025-02-28 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/487/Region%205_Mayaguez%20Group%20B%20-%20PW%20740411%20DSOW%202_19_25.pdf?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:47 PM AST Project UpdatedTitle: FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) - FAASt [Region 5-Mayaguez Group B] (Vegetation) FAASt 756477 MERGED UNDER PROJECT | 2026-02-06 15:26 | 2023-12-11 09:30 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.19087 | 5 | 2025-08-15 | 740411RFI459 | 740411 |  |  | 0
740414 | 107938 | 1316423.25 | 13788400.37 | 0 |  | 0 | 1887413.02 | 11900987.35 | 13788400.37 | 13788400.37 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/488/Region%206_Ponce%20Group%20B%20-%20PW%20740414%20DSOW%202_19_25.pdf?web=1 |  | 2026-02-06 15:27 | 2023-12-11 09:31 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.095473 | 5 | 2025-08-15 | 740414RFI460 | 740414 |  |  | 0
740662 | 107939 | 4500000 | 7224272 | 314567 |  | 2285726 | 873947 | 6350325 | 9509998 | 9824565 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/489/740662-DR4339PR-DSOW%20T&D%20AUTOMATION%20GROUP%202.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2026-02-24 13:53 | 2023-12-11 10:18 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 0.47319 | 3 | 2025-08-18 | 740662RFI461 | 740662 |  |  | 0
741097 | 107940 | 1267726 | 1347191.63 |  |  |  |  | 1347191.63 | 1347191.63 | 1347191.63 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/491/Appendix%20C%20_Region%201%20San%20Juan%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 2026-02-06 15:27 | 2023-12-18 14:58 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.94101 | 1 | 2025-08-11 | 741097RFI462 | 741097 |  |  | 0
741098 | 107941 | 961519 | 961518.65 |  |  |  |  | 961518.65 | 961518.65 | 961518.65 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/492/Appendix%20C%20_Region%203%20Bayamon%20Substation%20and%20Telecom%20location.xlsx?web=1 | 07JULY2025 - The project was withdrawn | 2026-02-06 15:28 | 2023-12-18 14:59 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 1 | 1 | 2025-07-07 | 741098RFI463 | 741098 |  |  | 0
741100 | 107942 | 1428326.03 | 1428325.86 |  |  |  |  | 1428325.86 | 1428325.86 | 1428325.86 | 2024-10-31 | 2025-03-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/493/Appendix%20C%20_Region%204%20Caguas%20Substation%20and%20Telecom%20location%20(1).xlsx?web=1 |  | 2026-02-06 15:29 | 2023-12-18 15:00 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 1 | 1 | 2025-07-07 | 741100RFI464 | 741100 |  |  | 0
741101 | 107943 | 956850.56 | 1058188.92 |  |  |  |  | 1058188.92 | 1058188.92 | 1058188.92 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/494/Appendix%20C%20_Region%202%20Arecibo%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 2026-02-06 15:29 | 2023-12-18 15:02 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.90423 | 1 | 2025-07-07 | 741101RFI465 | 741101 |  |  | 0
741102 | 107944 | 956850.56 | 1516985.37 |  |  |  |  | 1516985.37 | 1516985.37 | 1516985.37 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/495/Appendix%20C%20_Region%205%20Mayaguez%20Substation%20and%20Telecom%20location%20(1).xlsx?web=1 |  | 2026-02-06 15:29 | 2023-12-18 15:03 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.63076 | 2 | 2025-07-07 | 741102RFI466 | 741102 |  |  | 0
741104 | 107945 | 1538820 | 1992973.53 |  |  |  |  | 1992973.53 | 1992973.53 | 1992973.53 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/496/Appendix%20C%20_Region%206%20Ponce%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 2026-02-06 15:29 | 2023-12-18 15:04 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.77212 | 2 | 2025-07-07 | 741104RFI467 | 741104 |  |  | 0
741105 | 107946 | 27012545.63 | 157385518.05 |  |  |  | 2593672.87 | 154791845.18 | 157385518.05 | 157385518.05 | 2025-02-28 | 2025-08-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/497/741105-DR4339PR-PA%20DSOW%20FAASt%20%5BAll%20Regions%20TL%20-%20230kV%5D.V1.pdf?web=1 |  | 2026-02-06 13:12 | 2023-12-18 15:05 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.17163 | 5 |  | 741105RFI468 | 741105 |  |  | 0
741678 | 107947 | 13712378.94 | 10499139.71 | 360048.57 |  | 2853190.65 | 1176445.32 | 9322694.39 | 13352330.36 | 13712378.93 | 2025-07-31 | 2025-12-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/561/741678%20DR4339PR%20DSOW%20Automation%20Group%204-%20SAN%20JUAN%20BAYAMON%20REGION%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2026-02-24 13:53 | 2023-12-22 16:07 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1.027 | 1 | 2025-08-18 | 741678RFI489 | 741678 |  |  | 0
742026 | 11716 | 1117411.77 | 84036 | 83943 |  | 1033376 | 0 | 84036 | 1117412 | 1201355 | 2024-06-30 | 2024-08-31 | 2024-05-31 | 2024-08-30 | 1117411.77 | 1033375.81 | 1117411.77 | 1033375.81 |  |  |  | 1117411.77 | 1033375.81 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/584/PRJ_Report_742026_20250213.pdf?web=1 | Project created with the following damages initially assigned: 661700.7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-17 11:09 | 2024-01-04 11:31 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 83942.74 |  | 1 | 1 | 1 |  | qwer3 | 742026 |  |  | 0
742070 | 11753 | 5666787.43 | 205587 | 491327 |  | 5461200 | 35032.38 | 170554.62 | 5666787 | 6158114 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 5666787.43 | 5461200.05 | [5 empty] | 5666787.43 | 5461200.05 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/585/PW%2011753%20PRJ_Report_742070_20240618.pdf?web=1 | Project was resubmitted into Grants Portal under a new FAAst #. Old number was 737825. New number is 742070. Edited on 01/10/2024 by J Fournier.7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2024-01-12 16:33 | Jason Fournier | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 491326.68 |  | 1 | 1 | 1 |  | qwer4 | 742070 |  |  | 0
743399 | 11764 | 17307539.01 | 0 | 2253323.31 |  | 17307538.97 | 0 | 0 | 17307538.97 | 19560862.28 | 2024-06-30 | 2024-11-30 | 2024-08-26 |  | 17307539.01 | 17307539.01 | [5 empty] | 17307539.01 | 17307539.01 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/587/743399-DR4339PR-DSOW%20HV%20Equipment%20Replacement_Group%203%20DSOW%20for%20submittal%203%2028%2024%20-%20signed.pdf?web=1 |  | 2025-07-24 15:41 | 2024-01-24 17:17 | Marlina Crespo | Substation High Voltage Equipment Replacement | Jose J Ramos Figueroa |  |  | 2253322.97 |  | 1 | 1 | 1 |  | qwer6 | 743399 |  |  | 0
744072 | 107948 | 42700000 | 490438.07 | 181440.64 |  | 1893141.74 | 42892.47 | 447545.6 | 2383579.81 | 2565020.45 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/588/744072%20DR4339PR%20DSOW%20Network%20Communication%20Infrastructure%20Group%202%20Rev%200%20Signed.pdf?web=1 | ISOW was never submitted to the Island Wide FAASt Project | 2026-02-06 13:25 | 2024-02-12 09:14 | Marlina Crespo | IT OT Technology Systems Reparations | Jason Fournier |  |  |  |  | 1 | 17.9142 | 1 | 2025-08-11 | qwer7 | 744072 | 225680 | 292320 | 518000
745851 | 107953 | 1532152 | 1052298 | 46322 |  | 433532 | 101582 | 950716 | 1485830 | 1532152 | 2024-07-31 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/528/729522-DR4339PR-DSOW%20Automation%20Group-%20Group%2011%20DAR%20Bayamon%201901,%201907-FY24%20-%20signed.pdf?web=1 |  | 2026-02-24 13:47 | 2023-12-21 12:23 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1.0312 | 1 | 2025-08-18 | 745851RFI483 | 745851 |  |  | 0
745852 | 107954 | 2854430 | 1966004 | 85763 |  | 802663 | 189786 | 1776218 | 2768667 | 2854430 | 2025-01-31 | 2025-07-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/555/745852-DR4339PR-DSOW%20Group%2013%20-%20DAR%20-%20ARECIBO%208010,%208013,%208015%20-%20FY24%20-%20signed%20(1).pdf?web=1 |  | 2025-08-18 15:29 | 2023-12-21 12:46 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1.031 | 1 | 2025-08-18 | 745852RFI487 | 745852 |  |  | 0
745854 | 107955 | 1711509 | 1164604 | 52795 |  | 494110 | 112423 | 1052181 | 1658714 | 1711509 | 2025-01-31 | 2025-07-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/526/745854-DR4339PR-DSOW-Group%209%20DAR%20-%20BAYAMON%201703,%201704%20-FY24%20-%20signed.pdf?web=1 |  | 2026-02-24 13:48 | 2023-12-21 12:21 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1.0318 | 1 | 2025-08-18 | 745854RFI481 | 745854 |  |  | 0
745856 | 107956 | 1237309 | 1001406.99 | 112272.97 | 148295.58 | 1558740.78 | 65062.72 | 936344.27 | 2560147.77 | 2672420.74 | 2025-01-31 | 2025-07-31 | 2025-02-06 |  | 1640186.96 | 1640186.96 | [5 empty] | 1640186.96 | 1640186.96 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/557/745856-DR4339PR-%20DSOW%20Group%2014%20%20Revision%20005-%20V1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2026-02-18 12:31 | 2023-12-21 12:47 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo | 0 Months |  | 208604.89 |  | 1 | 0.4833 | 3 |  | 745856RFI488 | 745856 | 148295.58 | 442571.92 | 590867.5
745859 | 11839 | 467287.59 | 197005.11 | 22140.69 |  | 258571.74 | 15220.56 | 181784.55 | 455576.85 | 477717.54 | 2024-10-31 | 2025-01-31 | 2024-09-18 | 2025-10-15 | 467287.59 | 467287.59 | 422345.48 | 223935.37 |  | 33515.73 |  | 422345.48 | 223935.37 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/550/745859-DR4339PR-%20DSOW%20Group%2018%20428-406%20HM%20Revision%2010%20V1..pdf?web=1 | 4/01/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2026-02-17 11:24 | 2023-12-21 12:44 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo | 0 Months |  | 21856.33 |  | 1 | 1.0257 | 1 |  | 745859RFI484 | 745859 | 33515.73 | 76444.91 | 109960.64
745861 | 107957 | 2360527 | 1341922.17 | 200395.78 | 297958.67 | 2409705.25 | 97562.89 | 1244359.28 | 3751627.42 | 3952023.2 | 2025-01-31 | 2025-07-31 | 2025-02-06 |  | 3664210.1 | 3664210.1 | [5 empty] | 3664210.1 | 3664210.1 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/553/745861-%20DR4339PR-%20DSOW%20Group%2012-%20Revision%2005%20-%20V1%20.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2026-01-29 16:16 | 2023-12-21 12:45 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 477953.55 |  | 1 | 0.6292 | 2 |  | 745861RFI486 | 745861 | 228785.14 | 557322.86 | 786108
745871 | 107958 | 861045 | 582637 | 26876 |  | 251532 | 56244 | 526393 | 834169 | 861045 | 2025-08-31 | 2026-01-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/527/729522-DR4339PR-DSOW-%2010%20-%20DAR%20-%20BAYAMON%201717%209503%20-FY24%20-%20signed.pdf?web=1 |  | 2025-08-18 15:29 | 2023-12-21 12:22 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1.0322 | 1 | 2025-08-18 | 745871RFI482 | 745871 |  |  | 0
746108 | 11779 | 26445766.74 | 3331645 | 4224718 |  | 26445767 | 458919 | 2872726 | 29777412 | 34002130 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/783/746108-DR4339PR-Detailed%20SOW%20San%20Juan%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev1%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-08 11:54 | 2024-03-28 10:07 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.88812 | 1 | 2025-08-07 | qwer134 | 746108 |  |  | 0
746111 | 11778 | 10160311.88 | 1317294 | 2151320 |  | 10160312 | 230183 | 1087111 | 11477606 | 13628926 | 2024-06-30 | 2024-11-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/784/746111-DR4339PR-Detailed%20SOW%20Caguas%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20Rev2%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-08-08 11:48 | 2024-03-28 10:11 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 1 | 0.88523 | 1 | 2025-08-07 | qwer135 | 746111 |  |  | 0
746309 | 107959 | 425975.74 | 251311.27 | 51889.2 |  | 379772.1 | 30200.94 | 221110.33 | 631083.37 | 682972.57 | 2024-11-30 | 2025-04-30 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/632/746309-DR4339PR-DSOW-%20Group%2030-%20Revision%20015%20.pdf?web=1 | 8/1/2025 - Field EHP - Environmental: Initial review. Expected Completion Date (ECD) 08/20/2025. 8/12/2025 7:43 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2025-11-19 16:42 | 2024-03-18 14:57 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  |  |  | 1 | 0.67499 | 2 |  | qwer37 | 746309 | 65212.75 | 98251.25 | 163464
746545 | 11824 | 115638378 | 0 | 15530896 |  | 115638378 | 0 | 0 | 115638378 | 131169274 | 2024-10-31 | 2025-01-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/830/746545%20DR-4339PR%20FAASt%20DSOW_PCC%20-%20SDCCR%20Version%200_FEMA%20Project%20Detailed%20Scope%20of%20Work%20rev.%2001-%2005.13.2024%20-%20signed.pdf?web=1 | 4/17/2024: QC Review Complete | 2025-07-18 18:30 | 2024-04-08 09:59 | Marlina Crespo | IT OT Telecom Systems & Network | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 |  | qwer174 | 746545 |  |  | 0
746660 | 107960 | 70500000 | 564455.36 | 1887258.58 |  | 14828645.93 | 63677.66 | 500777.7 | 15393101.29 | 17280359.87 | 2025-04-30 | 2025-10-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/832/746660-DR4339PR-FEMA%20DSOW%20PAC%20Upgrades%20-%20Group%201%20Rev%203%20(8.15.2025)%20signed.pdf?web=1 | Originally withdrawn on 12/4/2025. This project was reactivated on 12/10/2025 | 2026-02-06 13:12 | 2024-04-09 08:54 | Marlina Crespo | Minor PAC Replacement and Hazard Mitigation | Jason Fournier |  |  |  |  | 1 | 4.58 | 1 |  | qwer176 | 746660 |  |  | 0
748180 | 107961 | 49755331 | 52804979.05 | 0 |  | 0 | 5250645.64 | 47554333.41 | 52804979.05 | 52804979.05 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/788/748180%20-%20DR4339PR%20-%20DSOW%20PMU%20Transmission%20Advance%20Sensors%20Project%20Rev0%20Signed.pdf?web=1 |  | 2026-02-06 15:30 | 2024-04-01 09:36 | Marlina Crespo | Deployment of Advanced Sensors, Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC) | Jason Fournier | 0 Months |  |  |  | 1 | 0.94225 | 1 | 2025-08-11 | qwer139 | 748180 | 0 | 423360 | 423360
749060 | 11874 | 717817.65 | 140677.54 | 120608.99 |  | 1316781.32 | 11800 | 128877.54 | 1457458.86 | 1578067.85 | 2024-08-31 | 2024-12-31 | [9 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/481/749060-DR4339PR-Detailed%20SOW-T-Pole%20TL5600%20Victoria%20TC%20-%20A%C3%B1asco%20TC%20Rev%208%20-%20signed.pdf?web=1 |  | 2025-11-19 16:24 | 2023-11-14 09:14 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo | 0 Months |  |  |  | 1 | 0.49251 | 3 |  | 749060RFI453 | 749060 | 141345.83 | 17467.93 | 158813.76
749072 | 11877 | 158495.32 | 59629.8 | 73616.34 |  | 823313.44 | 4890.99 | 54738.81 | 882943.24 | 956559.58 | 2024-08-31 | 2024-12-31 | 2025-11-05 |  | 827007.6 | 767377.79 |  |  |  | 55935.65 |  | 827007.6 | 767377.79 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/482/PW%2011877%20PRJ_MultiVersionReport_749072_20251105.pdf?web=1 |  | 2026-02-06 13:12 | 2023-11-27 12:32 | Marlina Crespo | Distribution Pole & Conductor Replacement | Jason Fournier | 0 Months |  | 73616.34 | 4890.99 | 1 | 0.17951 | 5 |  | 749072RFI454 | 749072 | 55935.65 |  | 55935.65
749124 | 107963 | 3342857 | [5 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/517/729522-DR4339PR-DSOW%20Automation%20Group%207-%20DAR%20-%20BAYAMON%201709,%201719%20-%20FY24%20-%20signed%20(1).pdf?web=1 |  | 2025-09-12 15:58 | 2023-12-21 12:15 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  |  |  | 1 | #DIV/0! | #DIV/0! | 2025-09-18 | 749124RFI479 | 749124 |  |  | 0
750063 | 107965 | 11000000 | 113327804.46 |  |  |  | 985459.15 | 112342345.31 | 113327804.46 | 113327804.46 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/913/Region%206%20Ponce%20Group%20A%20Low%20Density%20-%20PW%20750063%20DSOW%2011_20_2025.pdf?web=1 | 8/12/2025 9:12 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-06 13:11 | 2024-06-20 09:41 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.097064 | 5 |  | qwer231 | 750063 |  |  | 0
750065 | 107966 | 15000000 | 132424167.91 |  |  |  | 1151514.49 | 131272653.42 | 132424167.91 | 132424167.91 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/912/Region%203%20Bayamon%20Group%20A%20Low%20Density%20-%20PW%20750065%20DSOW%2012_22_2025.pdf | 10/2/2024 FEMA comment via GP: 10/01/2024 11:52 AM AST, GARCIA DIAZ, CHRISTIAN D. - Commented: "10/1/2024 - LUMA provided respond for email of duplicity. Still pending to confirm if LUMA used the rural ROW for their review." 10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language 8/7/2025 - EHP final review. ECD 8/14/2025. | 2026-02-06 13:12 | 2024-06-20 09:40 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.11327 | 5 |  | qwer230 | 750065 |  |  | 0
750066 | 107967 | 16000000 | 3142832.19 |  |  |  | 2059216.24 | 1083615.95 | 3142832.19 | 3142832.19 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/911/Region%204%20caguas%20Group%20A%20Low%20Density%20-%20PW%20750066%20DSOW%2012_22_2025.pdf?web=1 | 10/2/2024 FEMA comment via GP: 10/01/2024 01:04 PM AST, GARCIA DIAZ, CHRISTIAN D. Commented: "10/1/2024 - LUMA sent the documents on 9/20/2024. FEMA performed a pre-review and email with feedback was sent to LUMA on 10/1/2024 for their action to remove duplicity found between Distribution and Transmission. Deadline stablished is 10/3/2024 for LUMA submit documents corrected." 10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language | 2026-02-06 13:12 | 2024-06-20 09:39 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 5.0909 | 1 |  | qwer229 | 750066 |  |  | 0
750067 | 107968 | 9000000 | 107170415.13 |  |  |  | 931916.64 | 106238498.49 | 107170415.13 | 107170415.13 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/910/Region%202%20Arecibo%20Group%20A%20Low%20Density%20-%20PW%20750067%20DSOW%2012_22_2025.pdf | 10/2/2024 FEMA comment via GP: 10/01/2024 01:08 PM AST, GARCIA DIAZ, CHRISTIAN D. Commented: "10/1/2024 - LUMA sent the documents on 9/20/2024. FEMA performed a pre-review and email with feedback was sent to LUMA on 10/1/2024 for their action to remove duplicity found between Distribution and Transmission. Deadline stablished is 10/3/2024 for LUMA submit documents corrected."10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language | 2026-02-06 13:12 | 2024-06-20 09:38 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.083978 | 5 |  | qwer228 | 750067 |  |  | 0
750068 | 107969 | 7000000 | 98723529.73 |  |  |  | 858465.45 | 97865064.28 | 98723529.73 | 98723529.73 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/909/Region%205%20Mayaguez%20Group%20A%20Low%20Density%20-%20PW%20750068%20DSOW%2012.19.2025.pdf?web=1 | 8/12/2025 9:13 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-06 13:34 | 2024-06-20 09:31 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 0.070905 | 5 |  | qwer227 | 750068 |  |  | 0
750150 | 107970 | 58488 | 8224.8 | 19852.4 |  | 131895.22 | 1075.68 | 7149.12 | 140120.02 | 159972.42 |  |  | 2025-11-05 |  | 134148.36 | 125923.56 |  |  |  | 5971.66 |  | 134148.36 | 125923.56 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/914/PW%20107970%20PRJ_MultiVersionReport_750150_20251105.pdf?web=1 |  | 2026-02-06 13:11 | 2024-06-20 12:17 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  | 19852.4 | 1075.68 | 1 | 0.41741 | 3 |  | qwer232 | 750150 | 5971.66 |  | 5971.66
750151 | 107971 | 123160.67 | 12563.87 | 23495.18 |  | 260054.1 | 1041.06 | 11522.81 | 272617.97 | 296113.15 |  |  | 2026-01-16 |  | 255832.03 | 243268.16 |  |  |  | 19127 |  | 255832.03 | 243268.16 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/915/PRJ_MultiVersionReport_750151_20260116.pdf |  | 2026-02-06 13:11 | 2024-06-20 12:18 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  | 23495.18 | 1041.06 | 1 | 0.45177 | 3 |  | qwer233 | 750151 | 16785.94 | 2341.06 | 19127
750168 | 107972 | 375810.42 | 37472.84 | 45787.13 |  | 468439.49 | 3335.39 | 34137.45 | 505912.33 | 551699.46 |  |  | 2025-11-25 |  | 469229.99 | 431757.15 |  |  |  | 36682.34 |  | 469229.99 | 431757.15 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/916/PW%20107972%20PRJ_MultiVersionReport_750168_20251126.pdf?web=1 |  | 2026-02-06 13:17 | 2024-06-21 09:25 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  | 45787.13 | 3335.39 | 1 | 0.74284 | 2 |  | qwer234 | 750168 | 36682.34 | 5852.66 | 42535
750502 | 107977 | 3370000 | 52720520.35 | 0 |  | 0 | 3340630.47 | 49379889.88 | 52720520.35 | 52720520.35 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/918/750502%20-%20DR4339PR-%20FEMA%20DSOW%20for%2025%20MW%20BESS%20Installation%20and%20Integration%20-%20Aguadilla%20(Substation)%20signed.pdf?web=1 | Still pending SOW documentation | 2026-02-06 15:30 | 2024-06-28 11:04 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Jason Fournier |  |  |  |  | 1 | 0.063922 | 5 | 2025-08-07 | qwer235 | 750502 | 0 | 28261718.24 | 28261718.24
750503 | 107978 | 0 | 55503065.56 | 0 |  | 0 | 3187811.29 | 52315254.27 | 55503065.56 | 55503065.56 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/919/750503%20-%20DR4339PR%20-%20FEMA%20DSOW%20for%2025%20MW%20BESS%20Installation%20and%20Integration%20-%20San%20Juan%20(6.6.2025)%20signed.pdf?web=1 | Still pending SOW documentation | 2026-02-06 15:31 | 2024-06-28 11:05 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Jason Fournier |  |  |  |  | 1 | 0 | 5 | 2025-08-07 | qwer236 | 750503 | 0 | 28261718.24 | 28261718.24
750692 | 107979 | 8160000 | 539706.65 | 1378411.71 | 1059507.72 | 16594079.1 | 37871.84 | 501834.81 | 17133785.75 | 18512197.46 |  |  | 2025-09-25 |  | 12921047 | 12921047 |  |  |  | 2509617 |  | 12921047 | 12921047 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/922/750692-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%203%20-%20Phase%202%20V1-REV3%20.pdf?web=1 |  | 2026-02-25 16:16 | 2024-07-02 11:22 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo | 0 Months |  | 1799743 | 0 | 1 | 0.47625 | 3 |  | qwer237 | 750692 | 1096303.06 | 395734.94 | 1492038
750729 | 107980 | 2083232.55 | [5 empty] | 0 | 2083232.55 | 2083232.55 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/923/750729-DR4339PR-Transmission%20Line%203700%20GOAB%203797%20to%20Arroyo%20Substation%204101.pdf?web=1 | 02JULY2025 Project is being administratively use as a placeholder since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project for the 33 DI's included in this project at the request of the Applicant and COR3 if a SOW submittal date is provided. | 2025-07-18 18:30 | 2024-07-03 10:35 | Marlina Crespo | Transmission Line 3700 GOAB 3797 to Arroyo Substation 4101 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 |  | qwer238 | 750729 |  |  | 0
750730 | 107981 | 36590000 | [5 empty] | 0 | 36590000 | 36590000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/924/750730-DR4339PR-Line%20500%20Ponce%20TC%20to%20Costa%20Sur%20SP.pdf?web=1 |  | 2025-08-18 15:30 | 2024-07-03 10:38 | Marlina Crespo | Line 500 Ponce TC to Costa Sur SP | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | qwer239 | 750730 |  |  | 0
751655 | 107982 | 81410371 | 124703389.13 | 63813.14 |  | 605646.11 | 11753427.33 | 112949961.8 | 125309035.24 | 125372848.38 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/927/751655-DR4339-PR%20DSOW%20rev%201%20Signed%20-%202025-08-14%2012_52-1.pdf?web=1 |  | 2025-11-19 16:03 | 2024-07-19 10:12 | Marlina Crespo | Vieques and Culebra Microgrid | Marlina Crespo |  |  |  |  | 1 | 0.64968 | 2 |  | qwer240 | 751655 | 0 | 14497546.99 | 14497546.99
751656 | 107983 | 40846080 | 73445001.67 | 366170.82 |  | 46260.79 | 73445001.67 | 0 | 73491262.46 | 73857433.28 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/836/751656-DR4339%20DSOW%20rev1%20Culebra%20Microgrid%20Signed%20-%202025-08-14%2012_54.pdf?web=1 |  | 2025-11-19 16:02 | 2024-04-25 16:03 | Marlina Crespo | Vieques and Culebra Microgrid | Marlina Crespo |  |  |  |  | 1 | 0.5558 | 3 |  | qwer178 | 751656 | 0 | 8788889.34 | 8788889.34
752039 | 107984 | 7032180.12 | [5 empty] | 0 | 7032180.12 | 7032180.12 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/929/752039-DR4339PR-Transmission%20Line%2010000%20Sierra%20Linda%20TO%20to%20Magnolia%20TO.pdf | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:38 | Marlina Crespo | Transmission Line 10000 Sierra Linda TO to Magnolia TO | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer241 | 752039 |  |  | 0
752041 | 107985 | 4060000 | [5 empty] | 0 | 4060000 | 4060000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/930/752041-DR4339PR-Transmission%20Line%201000%20Venezuela%20Sect%20to%20Capuchinos%20Sect.pdf | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:52 | Marlina Crespo | Transmission Line 1000 Venezuela Sect to Capuchinos Sect | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer242 | 752041 |  |  | 0
752047 | 107986 | 6540000 | [5 empty] | 0 | 6540000 | 6540000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/931/752047-DR4339PR-Transmission%20Line%203300%20Chardon%20Sect%20to%20Egozcue%20Sect.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:55 | Marlina Crespo | Transmission Line 3300 Chardon Sect to Egozcue Sect | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer243 | 752047 |  |  | 0
752048 | 107987 | 8120000 | [5 empty] | 0 | 8120000 | 8120000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/932/752048-DR4339PR-Transmission%20Line%203500%20Las%20Lomas%20Sect%20to%20Monacillos%20TC.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:57 | Marlina Crespo | Transmission Line 3500 Las Lomas Sect to Monacillos TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer244 | 752048 |  |  | 0
752049 | 107988 | 5200000 | [5 empty] | 0 | 5200000 | 5200000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/933/752049-DR4339PR-Transmission%20Line%205600%20Hotel%20Rincon%20to%20Rincon%20Substation7301.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:59 | Marlina Crespo | Transmission Line 5600 Hotel Rincon to Rincon Substation7301 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer245 | 752049 |  |  | 0
752050 | 107989 | 20320000 | [5 empty] | 0 | 20320000 | 20320000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/934/752050-DR4339PR-Transmission%20Line%209300%20Gautier%20Benitez%20Sect%20to%20ACB%209323.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 11:02 | Marlina Crespo | Transmission Line 9300 Gautier Benitez Sect to ACB 9323 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer246 | 752050 |  |  | 0
752051 | 107990 | 16250000 | [5 empty] | 0 | 16250000 | 16250000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/935/752051-DR4339PR-Transmission%20Line%209300%20Juncos%20TC%20to%20ACB%209301.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 11:04 | Marlina Crespo | Transmission Line 9300 Juncos TC to ACB 9301 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer247 | 752051 |  |  | 0
752052 | 107991 | 32110000 | [5 empty] | 0 | 32110000 | 32110000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/936/752052-DR4339PRE-Transmission%20Line%209900%20TAP9905A%20to%20Rio%20Blanco%20HP.pdf?web=1 |  | 2025-08-18 15:30 | 2024-07-24 11:08 | Marlina Crespo | Transmission Line 9900 TAP9905A to Rio Blanco HP | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | qwer248 | 752052 |  |  | 0
752053 | 107992 | 33330000 | [5 empty] | 0 | 33330000 | 33330000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/937/752053-DR4339PR-Transmission%20Line%2013400%20Boqueron%20TO%20to%20Acacias%20TC.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 11:10 | Marlina Crespo | Transmission Line 13400 Boqueron TO to Acacias TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer249 | 752053 |  |  | 0
752275 | 107993 | 9157533 | [5 empty] | 0 | 9157533 | 9157533 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/946/DR4339PR-FEMA%20ISOW%20Unib%C3%B3n%209501%20Rev%207%20-%20signed.pdf?web=1 |  | 2026-02-25 14:36 | 2024-07-29 12:56 | Marlina Crespo | Substation Unibón 9501 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-19 | qwer254 | 752275 |  |  | 0
752276 | 107994 | 39664220 | [5 empty] | 0 | 39664220 | 39664220 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/945/DR4339PR-FEMA%20ISOW%20Monterrey%209502-9503%20Rev%205%20-%20signed.pdf?web=1 |  | 2026-02-25 13:51 | 2024-07-29 12:55 | Marlina Crespo | Substation Monterey 9502 & 9503 | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-19 | qwer253 | 752276 |  |  | 0
752277 | 107995 | 5825951 | 4177144.45 | 35108.3 |  | 324066.94 | 554759.8 | 3622384.65 | 4501211.39 | 4536319.69 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/944/752277%20-%20DR4339PR%20-%20Ciales%208701%20-%20FEMA%20Detail%20Scope%20of%20Work%20Rev.%200%20(11.26.2024)%20-%20signed.pdf?web=1 |  | 2026-02-25 13:51 | 2024-07-29 12:54 | Marlina Crespo | Substation Ciales 8701 | Ashleah Dingle |  |  |  |  | 1 | 1.2943 | 1 | 2025-08-19 | qwer252 | 752277 |  |  | 0
752500 | 107996 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2026-02-25 13:52 | 2024-08-01 12:11 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-18 | qwer255 | 752500 |  |  | 0
752502 | 107997 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2026-02-25 13:52 | 2024-08-01 12:12 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-18 | qwer256 | 752502 |  |  | 0
752503 | 107998 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2026-02-25 13:53 | 2024-08-01 12:13 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-18 | qwer257 | 752503 |  |  | 0
752540 | 107999 | 9107127 | 305539.44 | 773151.6 | 622940.21 | 9310270.2 | 23427.4 | 282112.04 | 9615809.64 | 10388961.24 |  |  | 2025-09-25 |  | 7111613.91 | 7111613.91 |  |  |  | 1376029 |  | 7111613.91 | 7111613.91 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/950/752540-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%204%20-%20Phase%202%20VER1-REV4%20.pdf?web=1 | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2026-02-25 16:14 | 2024-08-01 12:15 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 991211.9 | 0 | 1 | 0.9471 | 1 |  | qwer258 | 752540 | 628196.69 | 241421.21 | 869617.9
752808 | 108000 | 1482000 | 723597.72 | 119711.92 | 134857.23 | 1487804.47 | 52375.13 | 671222.59 | 2211402.19 | 2331114.11 |  |  | 2025-02-06 |  | 2753627.24 | 2753627.24 | [5 empty] | 2753627.24 | 2753627.24 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/952/752808-%20DR4339PR%20-%20DSOW%20Group%2019-%20Revision%20004-%20V1.pdf?web=1 |  | 2026-02-25 13:54 | 2024-08-08 09:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 348510.65 |  | 1 | 0.67016 | 2 |  | qwer259 | 752808 | 143163.5 | 312122.7 | 455286.2
752810 | 108001 | 1740000 | 869464.69 | 176266.8 | 202809.71 | 1848791.93 | 72284.36 | 797180.33 | 2718256.62 | 2894523.42 |  |  | 2025-02-06 |  | 2623262.08 | 2623262.08 | [5 empty] | 2623262.08 | 2623262.08 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/953/752810-DR4339PR-%20DSOW%20Group%2020%20Revision%20005%20-%20v1.pdf?web=1 | Pending ISOW documentation 8/8/24 - MC | 2026-02-25 16:09 | 2024-08-08 09:19 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo | 0 Months |  | 333695.7 |  | 1 | 0.64012 | 2 |  | qwer260 | 752810 | 209802.68 | 349543.04 | 559345.72
752972 | 108002 | 54200000 | 57640005.67 | 0 |  | 0 | 3414922.97 | 54225082.7 | 57640005.67 | 57640005.67 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/954/752972%20-%20FEMA%20DSOW%2025%20MW%20BESS%20Installation%20%26%20Integration%20-%20Manat%C3%AD%20sigend.pdf?web=1 | no ISOW was provided at the moment | 2026-02-25 13:55 | 2024-08-12 11:00 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle |  |  |  |  | 1 | 0.94032 | 1 | 2025-08-07 | qwer261 | 752972 | 0 | 30416253.08 | 30416253.08
753301 | 108003 | 7256000 | [5 empty] | 0 | 7256000 | 7256000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/964/-DR4339PR-ISOW%20Telecom%20Infrastructure%20Group%20H%20Signed%208-7-2024.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-08-16 16:50 | Marlina Crespo | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 1 | 2025-06-12 | qwer269 | 753301 |  |  | 0
753302 | 108004 | 8381000 | [5 empty] | 0 | 8381000 | 8381000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/963/753302-DR4339PR-ISOW%20Telecom%20Infrastructure%20Group%20G%20signed%208-7-2024.pdf?web=1 |  | 2026-02-25 13:57 | 2024-08-16 16:47 | Marlina Crespo | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-04 | qwer268 | 753302 |  |  | 0
753777 | 108008 | 0 | [5 empty] | 0 | 58661000 | 58661000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 13:57 | 2024-08-23 10:56 | Jason Fournier | Transmission Line Rebuild | Ashleah Dingle |  |  |  |  | 0 | 0 | 5 | 2025-08-18 | qwer278 | 753777 |  |  | 0
753781 | 108009 | 1569945.94 | 33695.78 | 85434.18 |  | 640758.24 | 6440.37 | 27255.41 | 674454.02 | 759888.2 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/973/753781-DR4339PR-Detailed%20SOW-TPole%20Line%20800%20Comsat%20Sect%20%E2%80%93%20Cidra%20Sect_8.13.2025.pdf?web=1 | 7/25/2025 - We have received your Request for Information regarding Align DSOW poles to be replaced vs. the Structures List amount, Structures list, DSOW structures alignment, clarify fence removal, installation, restoration, and KMZ alignment. Our team is currently reviewing the details, and we will respond promptly. (Note: This project conatins both Construction and Vegetation scope and cost and is submitted as "428 only" 8/13/2025 – The 4th Hazard mitigation RFI response, revised DSOW and cost estimates were submitted today in the project document section for HM review. | 2026-02-06 13:26 | 2024-08-23 10:53 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  |  |  | 1 | 2.3277 | 1 | 2025-08-18 | qwer277 | 753781 | 44078.65 | 15908.55 | 59987.2
753782 | 108010 | 199697.38 | 2218.84 | 20500.96 |  | 135332.58 | 291.07 | 1927.77 | 137551.42 | 158052.38 |  |  | 2025-10-30 |  | 131580.76 | 129361.92 |  |  |  | 5970.66 |  | 131580.76 | 129361.92 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/972/PW%20108010%20PRJ_MultiVersionReport_753782_20251031.pdf?web=1 |  | 2026-02-25 14:00 | 2024-08-23 10:51 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  | 20500.96 | 291.07 | 1 | 1.4518 | 1 |  | qwer276 | 753782 | 5970.66 |  | 5970.66
753785 | 108011 | 298678.49 | 0 | 38000.29 |  | 298678.49 | 0 | 0 | 298678.49 | 336678.78 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/971/753785-DR4339PR-Detailed%20SOW-TPole%20TL3300%20San%20Gerardo%20Sect%20-%20Venezuela%20Sect.pdf?web=1 |  | 2026-02-25 14:00 | 2024-08-23 10:49 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | qwer275 | 753785 |  |  | 0
753786 | 108012 | 599861.6 | 24170.88 | 70136.4 |  | 436928.46 | 5360.23 | 18810.65 | 461099.34 | 531235.74 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/970/753786-DR4339-PR%20DSOW%20rev%202%20T%20Pole%205900%202025-08-15%2009_02.pdf?web=1 |  | 2026-02-25 14:00 | 2024-08-23 10:45 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1.3009 | 1 | 2025-08-18 | qwer274 | 753786 | 36524.75 | 11050.25 | 47575
753787 | 108013 | 553203.43 | 0 | 70371.06 |  | 553203.43 | 0 | 0 | 553203.43 | 623574.49 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/969/753787-DR4339PR-Detailed%20SOW-T-Pole%20TL13700%20Mora%20TC-Isabela%20TO%20(1).pdf?web=1 |  | 2026-02-25 14:00 | 2024-08-23 10:38 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | qwer273 | 753787 |  |  | 0
753788 | 108014 | 840422.28 | 0 | 217503.32 |  | 840422.28 | 0 | 0 | 840422.28 | 1057925.6 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/968/753788-DR4339PR-Detailed%20SOW-TPole%20TL1900%20Dos%20Bocas%20HP%20-%20San%20Sebastian%20TC.pdf?web=1 |  | 2025-08-19 11:28 | 2024-08-23 10:23 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 1 | 2025-08-18 | qwer272 | 753788 |  |  | 0
754350 | 108015 | 15123199.33 | 15123199.33 | 0 |  | 0 | 1419257.38 | 13703941.95 | 15123199.33 | 15123199.33 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/976/754350-DR4339PR-Underground%20%20Circuit%20Feeders-San%20Juan%20Group%201-Detailed%20Scope%20of%20Work.pdf?web=1 |  | 2026-02-25 14:02 | 2024-08-26 08:36 | Jason Fournier | Distribution Underground Circuit Rebuilds - Phase 1 | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 1 | 2025-08-15 | qwer280 | 754350 |  |  | 0
754351 | 108016 | 7066632.8 | 7066632.8 | 0 |  | 0 | 931013.36 | 6135619.44 | 7066632.8 | 7066632.8 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/975/75435-DR4339PR-Distribution%20Underground%20Circuit%20Feeders%20-%20San%20Juan%20Group%202_Detailed%20Scope%20of%20Work%20Rev.1v4%20-%20Signed.pdf?web=1 |  | 2026-02-25 14:02 | 2024-08-26 08:31 | Jason Fournier | Distribution Underground Circuit Rebuilds - Phase 1 | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 1 | 2025-08-15 | qwer279 | 754351 |  |  | 0
755211 | 108022 | 324000 | 250899.06 | 28366.57 |  | 329417.48 | 19875.89 | 231023.17 | 580316.54 | 608683.11 |  |  | 2025-02-06 | 2025-10-15 | 643560.85 | 643560.85 | 527176.83 | 276277.77 |  | 53139.71 |  | 527176.83 | 276277.77 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/985/755211-DR4339PR-DSOW%20Group%2015%20Automation-%20Revision%20006-%20V4%20(1).pdf?web=1 | 13MAY2025 Version 1 was created to address fund code correction from FC6E to FC06 for FAASt projects. This administrative amendment does not change the previously approved scope of work or costs, however, to be able to process the correction a version is being submitted for de-obligating the available balance in this PW, and a next version will be submitted to reconcile available funding in the correct code. Per the Financial Management Section, the amount to be de-obligated in this version is -$643,560.85 (100%) / -$579,204.77 (90%). 06SEPTEMBER2024 No ISOW provided in Grants Portal at this time - MC | 2026-02-25 14:03 | 2024-09-06 09:13 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 19875.89 |  | 1 | 0.55832 | 3 |  | qwer281 | 755211 | 53139.71 | 103164.29 | 156304
756472 | 108024 | 691016.47 | [5 empty] | 0 | 691016.47 | 691016.47 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - Merged w/ 740406 10/17/2024 02:36 PM AST Project Updated Title: FAASt [Region 1-San Juan Group B] High Density (Vegetation) - FAASt [Region 1-San Juan Group B] (Vegetation) FAASt #756472 added | 2025-07-18 18:31 | 2024-09-20 12:35 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 1 | 1 |  | qwer418 | 756472 |  |  | 0
756474 | 108025 | 1049080.08 | [5 empty] | 0 | 1049080.08 | 1049080.08 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740408 10/17/2024 02:39 PM AST 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 3-Bayamon Group B] High Density (Vegetation) - FAASt [Region 3-Bayamon Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:36 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 1 | 1 |  | qwer419 | 756474 |  |  | 0
756475 | 108026 | 30966.29 | [5 empty] | 0 | 30966.29 | 30966.29 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740410 10/17/2024 02:40 PM AST Project Updated Title: FAASt [Region 2-Arecibo Group B] High Density (Vegetation) - FAASt [Region 2-Arecibo Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:36 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 1 | 1 |  | qwer420 | 756475 |  |  | 0
756476 | 108027 | 3068261.01 | [5 empty] | 0 | 3068261.01 | 3068261.01 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740409 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 4-Caguas Group B] High Density (Vegetation) - FAASt [Region 4-Caguas Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:37 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 1 | 1 |  | qwer421 | 756476 |  |  | 0
756477 | 108028 | 720951.73 | [5 empty] | 0 | 720951.73 | 720951.73 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - MERGED W/ 740411 10/17/2024 02:47 PM AST Project UpdatedTitle: FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) - FAASt [Region 5-Mayaguez Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:38 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 1 | 1 |  | qwer422 | 756477 |  |  | 0
756479 | 108029 | 1316423.25 | [5 empty] | 0 | 1316423.25 | 1316423.25 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT2024 & The project was withdrawn with the comment "LUMA requests the elimination of this project. The information of this project will be part of the one that is kept in the system as group B. For more details, please see attached document DR4339PR-Email confirmation to remove Group B Low Density 10.17.24.". | 2025-07-18 18:31 | 2024-09-20 12:38 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 1 | 1 |  | qwer423 | 756479 |  |  | 0
756997 | 108030 | 51200000 | 11624435.67 | 2584537.17 |  | 35688297.3 | 770659.35 | 10853776.32 | 47312732.97 | 49897270.14 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1168/756997-DR4339PR-Detailed%20SOW-TL1900%20Caguanas%20to%20Lares-02.04.2026.pdf?web=1 | 25SEPTEMBER2024 No ISOW submitted at this time 8/1/2025 - Environmental: review ongoing. ECD 8/15/2025. | 2026-02-25 14:04 | 2024-09-25 09:25 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Ashleah Dingle |  |  |  |  | 1 | 1.0822 | 1 |  | qwer424 | 756997 | 510654.48 | 0 | 510654.48
756999 | 108031 | 51200000 | 8558819.19 | 2251104.25 | 2446381.79 | 31467109.13 | 2720179.87 | 5838639.32 | 40025928.32 | 42277032.57 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1169/756999-DR4339PR-Detailed%20SOW-TL1900%20Lares%20to%20San%20Sebastian-02.04.2026.pdf?web=1 | 25SEPTEMBER2024 No ISOW submitted at this time | 2026-02-25 14:04 | 2024-09-25 09:29 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Ashleah Dingle |  |  |  |  | 1 | 1.2792 | 1 |  | qwer425 | 756999 | 1449761.7 | 0 | 1449761.7
757662 | 108032 | 1488000 | 0 | 280516.59 |  | 2223344.42 | 0 | 0 | 2223344.42 | 2503861.01 |  |  | 2025-10-30 |  | 2356733.87 | 2356733.87 | 1710547.94 | 1710547.94 |  | 512796.48 |  | 2356733.87 | 2356733.87 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1170/757662-DR4339PR-%20DSOW%20Group%2021Rev%204.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List27SEPTEMBER2024 No ISOW in GP at this time | 2026-02-25 14:05 | 2024-09-27 10:08 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 280516.59 | 0 | 1 | 0.66926 | 2 |  | qwer426 | 757662 | 512796.48 |  | 512796.48
757687 | 108033 | 1671000 | 0 | 359230.44 |  | 2768746.03 | 0 | 0 | 2768746.03 | 3127976.47 |  |  | 2025-10-30 |  | 2356733.87 | 2356733.87 |  |  |  | 412012.16 |  | 2356733.87 | 2356733.87 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1179/PW%20108033%20PRJ_MultiVersionReport_757687_20251031.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 2026-02-25 14:05 | 2024-09-30 12:35 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 359230.44 | 0 | 1 | 0.60352 | 2 |  | qwer435 | 757687 | 412012.16 |  | 412012.16
757689 | 108034 | 1836000 | 914277.86 | 141012.25 | 169799.83 | 1764051.9 | 68290.29 | 845987.57 | 2678329.76 | 2819342.01 |  |  | 2025-09-17 |  | 1774822 | 1774822 |  |  |  | 562828 |  | 1774822 | 1774822 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1178/757689%20-DR4339PR%20-%20Detailed%20Scope%20of%20Work%20Group%2024%20-%20Rev%2005%20-%20V1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 2026-02-25 16:12 | 2024-09-30 12:34 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 299299.32 | 0 | 1 | 0.6855 | 2 |  | qwer434 | 757689 | 562828 |  | 562828
757692 | 108035 | 1194000 | 585424.28 | 69852.89 |  | 945770.46 | 43248.71 | 542175.57 | 1531194.74 | 1601047.63 |  |  | 2025-09-03 |  | 938783.63 | 938783.63 |  |  |  | 430336.48 |  | 938783.63 | 938783.63 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1177/757692-DR4339PR-%20DSOW%20Group%2026%20Revision%20003%20-%20V1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 2026-02-25 14:06 | 2024-09-30 12:33 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 175325.33 | 0 | 1 | 0.77978 | 2 |  | qwer433 | 757692 | 169539 | 256947 | 426486
757694 | 108036 | 2364000 | 0 | 419922.13 |  | 3292670.74 | 0 | 0 | 3292670.74 | 3712592.87 |  |  | 2025-09-25 |  | 2314733.78 | 2314733.78 |  |  |  | 977936.96 |  | 2314733.78 | 2314733.78 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1176/757694-%20DR4339-PR-%20DSOW-%20Group%2027%20-%20Revision%2003.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 2026-02-25 14:06 | 2024-09-30 12:32 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 419922.13 | 0 | 1 | 0.71796 | 2 |  | qwer432 | 757694 | 977936.96 |  | 977936.96
757696 | 108037 | 2085000 | 584984.03 | 87081.37 | 122168.23 | 1063128.97 | 44095.89 | 540888.14 | 1648113 | 1735194.37 |  |  | 2025-09-17 |  | 1145458 | 1145458 |  |  |  | 369544 |  | 1145458 | 1145458 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1175/757696-DR4339PR-%20DSOW%20Group%2031%20Revision%208-%20V1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 2026-02-25 16:19 | 2024-09-30 12:31 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 195175.66 | 0 | 1 | 1.2651 | 1 |  | qwer431 | 757696 | 119259.88 | 241210.12 | 360470
757697 | 108038 | 798000 | 0 | 339647.19 |  | 2663099.41 | 0 | 0 | 2663099.41 | 3002746.6 |  |  | 2025-09-25 |  | 1996678.58 | 1996678.58 |  |  |  | 666420.83 |  | 1996678.58 | 1996678.58 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1174/757697-DR4339PR-%20DSOW%20Group%2032%20REv%203-.pdf?web=1 | <div class="ExternalClass88C5F8DA8A014162A6AA0901E67F47D7"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);"><span style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List</span><br><p><br></p>30SEPTEMBER2024 - No ISOWs in GP</div></div> | 2026-02-25 14:07 | 2024-09-30 12:30 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 339647.19 | 0 | 1 | 0.29965 | 4 |  | qwer430 | 757697 | 666420.83 |  | 666420.83
757698 | 108039 | 2226000 | 0 | 311582.64 |  | 2483045.65 | 0 | 0 | 2483045.65 | 2794628.29 |  |  | 2025-09-25 |  | 1888928.21 | 1888928.21 |  |  |  | 594117.44 |  | 1888928.21 | 1888928.21 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1173/757698-DR4339PR-%20DSOW%20Group%2033%20-%20rev%203.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 2026-02-25 14:07 | 2024-09-30 12:29 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 311582.64 | 0 | 1 | 0.89648 | 1 |  | qwer429 | 757698 | 594117.44 |  | 594117.44
757699 | 108040 | 561000 | 0 | 462362.68 |  | 3439728.11 | 0 | 0 | 3439728.11 | 3902090.79 |  |  | 2025-11-05 |  | 2755938.99 | 2755938.99 |  |  |  | 683789.12 |  | 2755938.99 | 2755938.99 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1172/PW%20108040%20PRJ_MultiVersionReport_757699_20251105.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP 8/7/2025 - Field EHP: In initial review. Expected Completion Date (ECD) 8/28/2025. 8/12/2025 7:47 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:07 | 2024-09-30 12:27 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 462362.68 | 0 | 1 | 0.16309 | 5 |  | qwer428 | 757699 | 683789.12 |  | 683789.12
757700 | 108041 | 1023000 | 874476.72 | 147185.05 | 118838.8 | 1248914.59 | 85545.81 | 788930.91 | 2123391.31 | 2270576.36 |  |  | 2025-09-17 |  | 1318516 | 1318516 |  |  |  | 424560.64 |  | 1318516 | 1318516 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1171/757700-DR4339PR-DSOW-%20Group%2035-%20Revision%2005-%20V1.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 2026-02-25 16:02 | 2024-09-30 12:26 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 245359.86 | 0 | 1 | 0.48178 | 3 |  | qwer427 | 757700 | 121387.44 | 293400.96 | 414788.4
757945 | 108042 | 8540000 | 15039.03 | 259116.51 |  | 2633472.99 | 1347.18 | 13691.85 | 2648512.02 | 2907628.53 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1180/757945-DR4339PR-Detailed%20SOW%20Arecibo%20Group%203%20-%20Phase%202%20Rev1%20-%20signed.pdf?web=1 |  | 2026-02-25 14:08 | 2024-10-01 08:59 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 3.2245 | 1 | 2025-08-11 | qwer436 | 757945 | 251407.95 | 11885.35 | 263293.3
759004 | 108045 | 9280000 | [5 empty] | 0 | 9280000 | 9280000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1182/ISOW%20Pole%20and%20Conductor%20-%20Arecibo%20Group%204%20-%20Phase%202.pdf?web=1 |  | 2026-02-25 14:08 | 2024-10-10 15:23 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-11 | qwer438 | 759004 |  |  | 0
759051 | 108046 | 3999999 | [5 empty] | 0 | 3990000 | 3990000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1181/ISOW%20Pole%20and%20Conductor%20-%20Bayamon%20Group%204%20-%20Phase%202.pdf?web=1 |  | 2026-02-25 14:08 | 2024-10-10 15:21 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1.0025 | 1 | 2025-08-11 | qwer437 | 759051 |  |  | 0
760568 | 108048 | 10467848 | [5 empty] | 0 | 10467848 | 10467848 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:09 | 2024-10-28 13:13 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer439 | 760568 |  |  | 0
760571 | 108049 | 18005134 | [5 empty] | 0 | 18005134 | 18005134 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:09 | 2024-10-28 13:16 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer440 | 760571 |  |  | 0
760575 | 108050 | 18102407 | [5 empty] | 0 | 18102407 | 18102407 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:09 | 2024-10-28 13:17 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer441 | 760575 |  |  | 0
760577 | 108051 | 8421396 | [5 empty] | 0 | 8421396 | 8421396 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:09 | 2024-10-28 13:19 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer442 | 760577 |  |  | 0
760579 | 108052 | 14143466 | [5 empty] | 0 | 14143466 | 14143466 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:09 | 2024-10-28 13:21 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer443 | 760579 |  |  | 0
761563 | 108055 | 17000000 | [5 empty] | 0 | 17000000 | 17000000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1195/761563-DR4339PR-EN-SOW-0001_Rev0%20-%20San%20Jose%20Relocation.pdf?web=1 |  | 2026-02-25 14:10 | 2024-11-04 10:16 | Marlina Crespo | San Jose Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 | 2025-08-19 | qwer449 | 761563 |  |  | 0
764705 | 108056 | 13387462.29 | [5 empty] | 0 | 13387462.29 | 13387462.29 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-11-04 10:15 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer448 | 764705 |  |  | 0
764706 | 108057 | 9329781.4 | [5 empty] | 0 | 9329781.4 | 9329781.4 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-11-04 10:14 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer447 | 764706 |  |  | 0
764707 | 108058 | 5540622.64 | [5 empty] | 0 | 5540622.64 | 5540622.64 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-11-04 10:14 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer446 | 764707 |  |  | 0
764708 | 108059 | 5190387.52 | [5 empty] | 0 | 5190387.52 | 5190387.52 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-11-04 10:13 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer445 | 764708 |  |  | 0
764709 | 108060 | 8740820.93 | [5 empty] | 0 | 8740820.93 | 8740820.93 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-11-04 10:12 | Marlina Crespo | Distribution Feeders ‐ San Juan Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer444 | 764709 |  |  | 0
767005 | 108062 | 12631766 | [5 empty] | 0 | 12631766 | 12631766 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-09-11 13:38 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer301 | 767005 |  |  | 0
767139 | 108064 | 3205041 | [5 empty] | 0 | 3205041 | 3205041 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-11-22 15:03 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer450 | 767139 |  |  | 0
767381 | 108067 | 9998489 | [5 empty] | 0 | 9998489 | 9998489 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-09-11 13:35 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 1 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer296 | 767381 |  |  | 0
767387 | 108068 | 4798378.99 | [5 empty] | 0 | 4798378.99 | 4798378.99 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:11 | 2024-09-11 13:35 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 2 | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer295 | 767387 |  |  | 0
790427 | 108069 | 5100000 | 71738.97 | 1002538.6 |  | 8239298.14 | 7782.12 | 63956.85 | 8311037.11 | 9313575.71 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1305/790427-DR4339PR-Detailed%20SOW%20Caguas%20Group%205%20-%20Phase%202%20Rev0%20428%20&%20406-1.pdf?web=1 |  | 2026-02-25 14:12 | 2025-02-05 20:37 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 0.61364 | 2 | 2025-08-11 | 790427RFI1042 | 790427 | 781861.25 | 57239.39 | 839100.64
790443 | 108070 | 5100000 | 7501.66 | 21435.45 | 14432.64 | 258265.86 | 574.91 | 6926.75 | 265767.52 | 287202.97 |  |  | 2025-09-03 |  | 186697 | 186697 |  |  |  | 35624 |  | 186697 | 186697 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1306/790443-DR4439PR%20-Detailed%20SOW%20San%20Juan%20Group%203%20-%20Phase%202%20Rev1%20V1%20.pdf?web=1 |  | 2026-02-25 14:12 | 2025-02-05 20:39 | Marlina Crespo |  | Ashleah Dingle |  |  | 25985 | 0 | 1 | 19.1897 | 1 |  | 790443RFI1043 | 790443 | 14432.64 | 6007.36 | 20440
790446 | 108071 | 5100000 | 28582.12 | 523611.41 |  | 4138909.89 | 3209.84 | 25372.28 | 4167492.01 | 4691103.42 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1307/790446-DR4339PR-Detailed%20SOW%20Caguas%20Group%204%20-%20Phase%202%20Rev0-.pdf?web=1 |  | 2026-02-25 14:12 | 2025-02-05 20:43 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.2238 | 1 | 2025-08-11 | 790446RFI1044 | 790446 | 382663.75 | 15948.73 | 398612.48
797148 | 108074 | 4700455 | 334489.47 | 642859.94 | 431054.74 | 2605819.72 | 65338.36 | 269151.11 | 2940309.19 | 3583169.13 |  |  | 2025-09-17 |  | 2359896 | 2359896 |  |  |  | 245423.36 |  | 2359896 | 2359896 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1002/797148-DR4339PR-Feeders%208101-03-DSOW-Rev.5(HM_Rev_2.10.26_ARR).pdf | 09DECEMBER2024 No ISOW in Grants Portal - MC | 2026-02-25 14:13 | 2024-09-11 13:35 | Rey Roldan Rodríguez | Distribution Feeders - Arecibo Short Term Group 2 | Ashleah Dingle |  |  | 777847.24 | 0 | 1 | 1.5986 | 1 |  | qwer289 | 797148 | 245423.36 |  | 245423.36
798275 | 108075 | 6925970.19 | 0 | 954420.68 |  | 7464273.83 | 0 | 0 | 7464273.83 | 8418694.51 |  |  | 2025-09-17 |  | 6711421 | 6711421 |  |  |  | 752852.93 |  | 6711421 | 6711421 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1277/PW%20108075%20PRJ_MultiVersionReport_798275_20250917.pdf?web=1 | 12DECEMBER2024 No ISOWs in GP at this time MC | 2026-02-25 14:13 | 2024-12-11 16:31 | Marlina Crespo | Distribution Feeders - San Juan Short Term Group 3 | Ashleah Dingle |  |  | 954420.68 | 0 | 1 | 0.92788 | 1 |  | 798275RFI1025 | 798275 | 752852.93 |  | 752852.93
800286 | 108077 | 2175000 | 995016.61 | 137043.71 | 175789.83 | 1603428.25 | 78366.54 | 916650.07 | 2598444.86 | 2735488.57 |  |  | 2025-09-17 |  | 1703713 | 1703713 |  |  |  | 597390.08 |  | 1703713 | 1703713 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1142/800286-DR4339PR-DSOW-%20Group%2036-%20Rev%20004-V1.pdf?web=1 | 30DECEMBER2024 No ISOWs in GP at this time MC | 2026-02-25 14:14 | 2024-09-11 14:07 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 300364.95 | 0 | 1 | 0.83704 | 1 |  | qwer407 | 800286 | 230628.16 | 342399.24 | 573027.4
800361 | 108078 | 2148000 |  | 297988.09 |  | 2069863.13 |  | 0 | 2069863.13 | 2367851.22 |  |  | 2025-09-17 |  | 1596193 | 1596193 |  |  |  | 473670.4 |  | 1596193 | 1596193 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/993/PW%20108078%20PRJ_MultiVersionReport_800361_20250917.pdf?web=1 |  | 2026-02-25 14:14 | 2024-09-11 13:35 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 297988.09 | 0 | 1 | 1.0377 | 1 |  | qwer282 | 800361 | 473670.4 |  | 473670.4
800369 | 108079 | 1335000 | [5 empty] | 0 | 1335000 | 1335000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:14 | 2024-09-11 13:35 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | qwer283 | 800369 |  |  | 0
800394 | 108080 | 3084000 | [5 empty] | 0 | 3084000 | 3084000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:14 | 2024-09-11 13:35 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | qwer284 | 800394 |  |  | 0
800399 | 108081 | 2577000 | [5 empty] | 0 | 2577000 | 2577000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:14 | 2024-09-11 13:35 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | qwer285 | 800399 |  |  | 0
801166 | 108082 | 9010977 | 0 | 1724565.72 |  | 21962621.6 | 0 | 0 | 21962621.6 | 23687187.32 |  |  | 2026-01-08 |  | 19826783.47 | 19826783.47 |  |  |  | 2135838.13 |  | 19826783.47 | 19826783.47 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1280/801166-DR4339PR-Feeders%206601-03-DSOW.%20Rev.%205.pdf?web=1 | 14JANUARY2025 No ISOW in Grants Portal - MC 8/13/2025 - Field EHP: EHP Formal Request for Information Initiated on 08/13/2025. EHP is requesting additional information for the subject project. This RFI is needed for Completeness and Compliance. To determine compliance, the following information should be provided no later than 15 days from the date of this request. | 2026-02-25 14:15 | 2024-12-11 16:33 | Marlina Crespo |  | Ashleah Dingle |  |  | 1724565.72 | 0 | 1 | 0.41029 | 3 |  | 801166RFI1028 | 801166 | 2135838.13 | 0 | 2135838.13
801172 | 108083 | 7155677 | 101241.03 | 568090.34 | 160515.06 | 2023253.43 | 22194.71 | 79046.32 | 2124494.46 | 2692584.8 |  |  | 2025-09-17 |  | 2285961 | 2285961 |  |  |  | 243286.39 |  | 2285961 | 2285961 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1279/801172-DR4339PR-Feeders%201529-15-Detailed%20Scope%20of%20Work-Rev.%201%20Amendment%20RFI.pdf?web=1 | 14JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 16:06 | 2024-12-11 16:33 | Marlina Crespo |  | Marlina Crespo |  |  | 508777.01 | 0 | 1 | 3.3682 | 1 |  | 801172RFI1027 | 801172 | 243286.39 |  | 243286.39
801197 | 108084 | 3863358 | [5 empty] | 0 | 3863358 | 3863358 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC6/12/2025 - Project withdrawn in Grants Portal | 2026-02-25 14:16 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | qwer300 | 801197 |  |  | 0
801432 | 108085 | 2391000 | [5 empty] | 0 | 2391000 | 2391000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:16 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | 801432RFI1005 | 801432 |  |  | 0
801437 | 108086 | 2883000 | [5 empty] | 0 | 2883000 | 2883000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:16 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | 801437RFI1006 | 801437 |  |  | 0
801438 | 108087 | 2490000 | [5 empty] | 0 | 2490000 | 2490000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:16 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | 801438RFI1007 | 801438 |  |  | 0
801440 | 108088 | 3902000 | [5 empty] | 0 | 3902000 | 3902000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:16 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | 801440RFI1008 | 801440 |  |  | 0
801441 | 108089 | 2400000 | [5 empty] | 0 | 2400000 | 2400000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:16 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-19 | 801441RFI1009 | 801441 |  |  | 0
805513 | 108090 | 3250000 | [5 empty] | 0 | 3250000 | 3250000 | [11 empty] | 0 | 0 |  |  | Deleted from Grants Portal on 23JUN2025 - AND 22JANUARY2025 No ISOW in Grants Portal - MC | 2025-08-11 09:20 | 2025-01-22 11:45 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-06-12 | 805513RFI1040 | 805513 |  |  | 0
805517 | 108091 | 2990000 | 733123.39 | 47826.67 |  | 414584.72 | 75820.29 | 657303.1 | 1147708.11 | 1195534.78 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1300/805517%20-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%202100_Rev1_8..2025_signed.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:18 | 2025-01-22 11:44 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 2.6052 | 1 | 2025-08-18 | 805517RFI1039 | 805517 | 4111.54 | 68433.46 | 72545
805519 | 108092 | 3180000 | 769393.29 | 69012.67 |  | 639395.34 | 74943.63 | 694449.66 | 1408788.63 | 1477801.3 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1299/805519%20-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%201900_Rev1_8.4.2025_signed.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:18 | 2025-01-22 11:42 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Ashleah Dingle |  |  |  |  | 1 | 2.2573 | 1 | 2025-08-18 | 805519RFI1038 | 805519 | 31058.62 | 70900.38 | 101959
805521 | 108093 | 2980000 | 725071.07 | 32294 |  | 252749.08 | 82142.46 | 642928.61 | 977820.15 | 1010114.15 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1221/805521-DR4339PR-38kV%20Reclosers%20Transmission%20Line%207800_Rev.1_7.11.2025.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 2026-02-25 14:18 | 2024-12-11 15:19 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 3.0476 | 1 | 2025-08-18 | qwer473 | 969 | 9182.3 | 97016.62 | 106198.92
806935 | 108097 | 6120000 | [5 empty] | 0 | 6120000 | 6120000 | [11 empty] | 0 | 0 |  |  | 28JANUARY2025 No ISOW docs in Grants Portal - MC | 2026-02-25 14:19 | 2024-12-12 14:29 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-11 | 806935RFI1036 | 806935 |  |  | 0
806936 | 108098 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  |  | 28JANUARY2025 No ISOW docs in Grants Portal - MC | 2026-02-25 14:19 | 2024-12-12 14:29 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-11 | 806936RFI1037 | 806936 |  |  | 0
811913 | 108099 | 335555.06 | 43773.6 | 64330 |  | 355873.89 | 6697.9 | 37075.7 | 399647.49 | 463977.49 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1213/811913-DR4339PR-Detailed%20SOW-T-Pole%20TL9600%20Bayamon%20TC%20%E2%80%93%20Catano%20Sect%20Rev1_signed.pdf?web=1 |  | 2026-02-25 14:20 | 2024-12-11 15:13 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 0.83963 | 1 | 2025-08-18 | qwer465 | 811913961 | 83732.55 | 5802.45 | 89535
811923 | 108100 | 28863.82 | 22761.43 | 53616.55 |  | 206622.43 | 4687.63 | 18073.8 | 229383.86 | 283000.41 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1212/811923-DR4339PR-Detailed%20SOW-T-Pole%20TL16500%20Fajardo%20TC-Dos%20Marinas%20Rev1_signed.pdf?web=1 |  | 2026-02-25 14:20 | 2024-12-11 15:11 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 0.12583 | 5 | 2025-08-18 | qwer464 | 811923960 | 11021.7 | 3868.3 | 14890
812041 | 108101 | 13725835 | 0 | 3314820.98 |  | 25929254.07 | 0 | 0 | 25929254.07 | 29244075.05 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1310/812041-%20DR4339PR-%20-Feeder%209501-02-DETAILED%20SCOPE%20OF%20WORK%20Rev.%205.pdf?web=1 | 20FEBRUARY2025 No ISOW in GP at this time - MC 7/30/2025 - As confirmed by PDMG, project sent back to Phase II because project is not included in PREPA Consolidated Plan of 7/7/2025. | 2026-02-25 14:20 | 2025-02-21 12:31 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 0.52936 | 3 | 2025-08-15 | 812041RFI1046 | 812041 | 3693316.44 | 0 | 3693316.44
812569 | 108102 | 15430988 | 0 | 1403642.18 |  | 10978061.1 | 0 | 0 | 10978061.1 | 12381703.28 |  |  | 2025-09-25 |  | 10217566.54 | 10217566.54 |  |  |  | 760494.56 |  | 10217566.54 | 10217566.54 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1282/812569-DR4339PR-Feeder%203502-02%20DSOW-Detailed%20Scope%20of%20Work%20Rev.%205%20-%20signed.pdf?web=1 | 21FEBRUARY2025 No ISOWs in GP at this time - MC | 2026-02-25 14:20 | 2024-12-11 16:34 | Marlina Crespo |  | Ashleah Dingle |  |  | 1403642.18 | 0 | 1 | 1.4056 | 1 |  | 812569RFI1030 | 812569 | 760494.56 |  | 760494.56
814792 | 108105 | 5600000 | [5 empty] | 0 | 5600000 | 5600000 | [11 empty] | 0 | 0 |  |  | 07MARCH2025 No ISOW in GP - MC | 2026-02-25 14:21 | 2025-03-07 12:13 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-04 | 814792RFI1048 | 814792 |  |  | 0
814793 | 108106 | 4600000 | [5 empty] | 0 | 4600000 | 4600000 | [11 empty] | 0 | 0 |  |  | 07MARCH2025 No ISOW in GP - MC | 2026-02-25 14:21 | 2025-03-07 12:17 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-11 | 814793RFI1049 | 814793 |  |  | 0
817242 | 108113 | 2040000 | [5 empty] | 0 | 2040000 | 2040000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:22 | 2025-03-13 16:49 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-11 | 817242RFI1097 | 817242 |  |  | 0
817247 | 108114 | 11650000 | [5 empty] | 0 | 11650000 | 11650000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:22 | 2025-03-13 16:49 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-11 | 817247RFI1100 | 817247 |  |  | 0
817249 | 108116 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:22 | 2025-03-13 16:48 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-04 | 817249RFI1095 | 817249 |  |  | 0
817250 | 108117 | 7610000 | [5 empty] | 0 | 7610000 | 7610000 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:22 | 2025-03-13 16:50 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-11 | 817250RFI1103 | 817250 |  |  | 0
817956 | 108119 | 6132436 | 0 | 1376522.26 |  | 2184086.98 | 0 | 0 | 2184086.98 | 3560609.24 |  |  | 2025-09-25 |  | 2054461.78 | 2054461.78 |  |  |  | 129625.2 |  | 2054461.78 | 2054461.78 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1316/817956-%20DR4339PR-%20DETAILED%20SCOPE%20OF%20WORK%20San%20Juan%20Short%20Term%20Group%201%20FEEDER%201303-02%20-%20signed.pdf?web=1 | 8/1/2025 - Field EHP: Initial review. Expected Completion Date ECD 8/15/2025. 8/13/2025 1:37 PM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:23 | 2025-03-13 16:37 | Marlina Crespo |  | Ashleah Dingle |  |  | 1376522.26 | 0 | 1 | 2.8078 | 1 |  | 817956RFI1052 | 817956 | 129625.2 |  | 129625.2
817961 | 108120 | 23882838 | 399260.06 | 1826739.4 |  | 19517674.31 | 50231.61 | 349028.45 | 19916934.37 | 21743673.77 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:23 | 2025-03-13 16:39 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.1991 | 1 | 2025-08-15 | 817961RFI1059 | 817961 | 692201.89 | 82130.27 | 774332.16
817962 | 108121 | 5548949 | [5 empty] | 0 | 5548949 | 5548949 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:23 | 2025-03-13 16:42 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-15 | 817962RFI1070 | 817962 |  |  | 0
817993 | 108122 | 6131846 | [5 empty] | 0 | 6131846 | 6131846 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:23 | 2025-03-13 16:40 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-15 | 817993RFI1063 | 817993 |  |  | 0
818006 | 108123 | 34516477 | [5 empty] | 0 | 34516477 | 34516477 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:23 | 2025-03-13 16:39 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-15 | 818006RFI1061 | 818006 |  |  | 0
818041 | 108124 | 24349603.89 | [5 empty] | 0 | 24349603.89 | 24349603.89 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:24 | 2025-03-13 16:41 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-15 | 818041RFI1069 | 818041 |  |  | 0
818055 | 108125 | 8829008 | [5 empty] | 0 | 8829008 | 8829008 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:24 | 2025-03-13 16:41 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-15 | 818055RFI1067 | 818055 |  |  | 0
818056 | 108126 | 22352214 | [5 empty] | 0 | 22352214 | 22352214 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 14:24 | 2025-03-13 16:40 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 1 | 1 | 2025-08-15 | 818056RFI1065 | 818056 |  |  | 0
825753 | 108133 | [6 empty] | 0 | 5750000 | 5750000 | [11 empty] | 0 | 0 |  |  | 04/10/2025 02:01 PM AST The project was withdrawn with the comment "Project already created under: 825843 FASSt Guanica TC". 04/10/2025 02:01 PM AST Projected 100% Amount set to $0.00 because Project was made inactive for Public Assistance. Reason: Project already created under: 825843 FASSt Guanica TC | 2025-08-01 11:20 | 2025-04-10 13:00 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 0 | 5 |  | 825753RFI1152 | 825753 |  |  | 0
825843 | 108134 |  |  | 826981.13 |  | 6521097.48 | 0 | 0 | 6521097.48 | 7348078.61 |  |  | 2025-09-22 |  | 2320373.96 | 2320373.96 |  |  |  | 4200723.52 |  | 2320373.96 | 2320373.96 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1355/PW%20108134%20PRJ_MultiVersionReport_825843_20250923.pdf?web=1 | 8/13/2025 9:48 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:26 | 2025-03-13 16:46 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  | 826981.13 | 0 | 1 | 0 | 5 |  | 825843RFI1091 | 825843 | 4200723.52 |  | 4200723.52
950482 | 108138 | 4375640 | [5 empty] | 0 | 4375640 | 4375640 | [11 empty] | 0 | 0 |  |  |  | 2025-09-12 15:58 | 2025-05-08 09:34 | Marlina Crespo |  | Marlina Crespo |  |  |  |  | 0 | 1 | 1 | 2025-08-15 | 950482RFI1316 | 950482 |  |  | 0
954184 | 108144 | 2747126.23 | 0 | 293002.71 |  | 2454123.52 | 0 | 0 | 2454123.52 | 2747126.23 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1681/954184-DR%204339PR%20Carolina%20ESC%20Building%20Repairs%20-Detail%20Scope%20of%20Work%20signed.pdf?web=1 |  | 2025-11-19 14:11 | 2025-06-18 15:05 | Marlina Crespo |  | Marlina Crespo |  |  |  |  | 1 | 1.1194 | 1 | 2025-08-11 | 954184RFI1410 | 954184 | 0 | 0 | 0
956330 | 108145 | 7985860.15 | 5853486.17 | 163550.83 |  | 1968823.15 | 448769.62 | 5404716.55 | 7822309.32 | 7985860.15 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1689/956330%20-%20FAASt%20%5BCaguas%20Region%204%20-%20Feeder%203007-03%5D%20(Vegetation)%20DSOW%20Rev%202.pdf?web=1 | 7/25/2025- Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:13 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:28 | 2025-06-18 16:33 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956330RFI1418 | 956330 |  |  | 0
956331 | 108146 | 8021552.35 | 5879647.9 | 1977622.66 |  | 164281.79 | 5879647.9 | 0 | 6043929.69 | 8021552.35 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1688/956331%20-%20FAASt%20Mayaguez%20Region%205%20Feeder%206014-02%20(Vegetation)%20DSOW%20(1).pdf?web=1 | 7/25/2025- Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:28 | 2025-06-18 16:31 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1 | 1.3272 | 1 |  | 956331RFI1417 | 956331 |  |  | 0
956332 | 108147 | 11073220.77 | 8286164.87 | 231521.7 |  | 2787055.9 | 635275.99 | 7650888.88 | 11073220.77 | 11304742.47 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1687/956332%20FAASt%20Single%20Line%20DSOW%20Feeder%202401-01%20San%20Juan%20Region%201%206-27-25.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:28 | 2025-06-18 16:30 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 1 |  | 956332RFI1416 | 956332 |  |  | 0
956335 | 108148 | 7503713.1 | 5500081.4 | 153676.43 |  | 1849955.27 | 421675.11 | 5078406.29 | 7350036.67 | 7503713.1 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1686/956335%20-%20FAASt%20%5BSan%20Juan%20Region%201%20-%20Feeder%202301-02%5D%20(Vegetation)%20DSOW.pdf?web=1 | 7/25/2025- Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:27 | 2025-06-18 16:29 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956335RFI1415 | 956335 |  |  | 0
956337 | 108149 | 7303974.78 | 5353676.97 | 149585.76 |  | 1800712.05 | 410450.73 | 4943226.24 | 7154389.02 | 7303974.78 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1685/956337%20-%20FAASt%20%5BMayaguez%20Region%205%20Feeder%206012-02%5D%20(Vegetation)%20DSOW%20.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:28 | 2025-06-18 16:28 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956337RFI1414 | 956337 |  |  | 0
956339 | 108150 | 12004333.95 | 8798952.37 | 2959532.24 |  | 245849.34 | 8798952.37 | 0 | 9044801.71 | 12004333.95 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1684/956339%20-%20FAASt%20%5BCaguas%20Region%204%20-%20Feeder%203301-01%5D%20(Vegetation)%20DSOW.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:28 | 2025-06-18 16:25 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1 | 1.3272 | 1 |  | 956339RFI1413 | 956339 |  |  | 0
956340 | 108151 | 6589894.87 | 4830269.73 | 1624663.76 |  | 134961.38 | 4830269.73 | 0 | 4965231.11 | 6589894.87 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1683/956340%20-%20FAASt%20%5BPonce%20Region%206%20Feeder%205602-02%5D%20(Vegetation)%20DSOW%20Rev%201%20(1).pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:28 | 2025-06-18 16:24 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1 | 1.3272 | 1 |  | 956340RFI1412 | 956340 |  |  | 0
956341 | 108152 | 97672.18 | 71591.83 | 2000.35 |  | 24080 | 5488.7 | 66103.13 | 95671.83 | 97672.18 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1682/956341%20-%20FAASt%20%5BPonce%20Region%206%20Feeder%205803-02%5D%20(Vegetation)%20DSOW.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 2026-02-25 14:28 | 2025-06-18 16:02 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956341RFI1411 | 956341 |  |  | 0
956342 | 108153 | 44397505.59 | 32542541.69 | 909263.06 |  | 10945700.85 | 2494941.49 | 30047600.2 | 43488242.54 | 44397505.6 |  |  | 2025-09-17 |  | 4093248 | 4093248 | [5 empty] | 4093248 | 4093248 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1673/PW%20108153%20PRJ_MultiVersionReport_956342_20250917.pdf?web=1 | 07/25/2025 01:06 PM AST - Project submitted as 428/406 on 06.26.2025 for FEMA review. Projects will be amended to "428 only" and resubmitted to FEMA with revised costs factoring in additional miles of assessments from Vendors. 8/15/2025 9:15 AM- The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. 8/15/2025 11:02 AM EDT - Field EHP: Previous EHP Status applies. ECD 08/22/2025. 8/22/2025 8:55 AM AST - Field EHP - Historic: This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. EDC To be determined. | 2026-02-25 14:28 | 2025-06-12 16:08 | Marlina Crespo |  | Ashleah Dingle |  |  | 126595.31 | 0 | 1 | 1.0209 | 1 |  | 956342RFI1403 | 956342 |  |  | 0
956343 | 108154 | 21381353.56 | 15672132.45 | 437891.18 |  | 5271329.93 | 1201536.52 | 14470595.93 | 20943462.38 | 21381353.56 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1678/956343-FAASt%20[Ponce%20Region%206%20Line%204800%20(38kV)%20%e2%80%93%20Toro%20Negro%20to%20Aibonito,%20Santa%20Isabel]%20(Vegetation)%20Rev3.pdf | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1678/956343%20-FAASt%20%5BPonce%20Region%206%20Line%204800%20(38kV)%20%E2%80%93%20Toro%20Negro%20to%20Aibonito,%20Santa%20Isabel%5D%20(Vegetation)%20DSOW%20REV%202.pdf?web=1 | 2026-02-25 14:28 | 2025-06-12 16:09 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956343RFI1408 | 956343 |  |  | 0
956345 | 108155 | 7324652.18 | 5368833.09 | 150009.25 |  | 1805809.83 | 411612.69 | 4957220.4 | 7174642.92 | 7324652.17 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1676/956345%20-%20FAASt%20[Arecibo%20Region%202%20Line%202400%20(38kV)%20%e2%80%93%20Dos%20Bocas%20HP%20to%20Caonillas%202]%20(Vegetation)%20DSOW%20Rev3.pdf |  | 2026-02-25 14:29 | 2025-06-12 16:09 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956345RFI1406 | 956345 |  |  | 0
956348 | 108156 | 1193764.74 | 875007.19 | 24448.38 |  | 294309.16 | 67084.2 | 807922.99 | 1169316.35 | 1193764.73 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1674/956348-FAASt%20%5BBayamon%20Region%203%20Line%2010000%20(38kV)%20%E2%80%93Bayamon%20Pueblo%20to%20Magnolia%20TO%5D%20(Vegetation)%20DSOW%20Rev%203.pdf?web=1 |  | 2026-02-25 14:29 | 2025-06-12 16:08 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956348RFI1404 | 956348 |  |  | 0
956349 | 108157 | 13853576.49 | 10154412.56 | 283721.94 |  | 3415441.98 | 778509.08 | 9375903.48 | 13569854.54 | 13853576.48 |  |  | 2025-09-17 |  | 1364416 | 1364416 | [5 empty] | 1364416 | 1364416 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1675/956349%20FAASt%20%5BSan%20Juan%20Region%201%20Line%2036800%20(115kV)%20%E2%80%93%20Canovanas%20TC%20to%20Palmer%20TC%5D%20(Vegetation)%20DSOW%20V1.pdf?web=1 | 07/25/2025 01:07 PM AST - Project submitted as 428/406 on 06.26.2025 for FEMA review. Projects will be amended to "428 only" and resubmitted to FEMA with revised costs factoring in additional miles of assessments from Vendors. 8/15/2025 11:03 AM EDT - Field EHP: Previous EHP Status applies. ECD 08/22/2025. 8/22/2025 11:33 AM AST -Field EHP - Historic: This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. EDC To be determined. | 2026-02-25 14:29 | 2025-06-12 16:09 | Marlina Crespo |  | Ashleah Dingle |  |  | 42198.44 | 0 | 1 | 1.0209 | 1 |  | 956349RFI1405 | 956349 |  |  | 0
956353 | 108158 | 37008593.33 | 27126607.1 | 757937.79 |  | 9124048.44 | 2079717.62 | 25046889.48 | 36250655.54 | 37008593.33 |  |  | 2025-09-17 |  | 3756065 | 3756065 | [5 empty] | 3756065 | 3756065 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1672/PW%20108158%20PRJ_MultiVersionReport_956353_20250917.pdf?web=1 | 07/25/2025 01:08 PM AST - Project submitted as 428/406 on 06.26.2025 for FEMA review. Projects will be amended to "428 only" and resubmitted to FEMA with revised costs factoring in additional miles of assessments from Vendors. 8/22/2025 9:02 AM EDT - Field EHP: This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. Once more information is available on the progress of these discussions. ECD: to be determine. | 2026-02-25 14:29 | 2025-06-12 16:08 | Marlina Crespo |  | Ashleah Dingle |  |  | 116166.96 | 0 | 1 | 1.0209 | 1 |  | 956353RFI1402 | 956353 |  |  | 0
956356 | 108159 | 3583135.14 | 0 | 30566.17 |  | 988951.38 | 0 | 0 | 988951.38 | 1019517.55 |  |  | 2025-09-17 |  | 325421.1 | 325421.1 | [5 empty] | 325421.1 | 325421.1 |  |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1679/956356%20FAASt%20%5BPonce%20Region%206%20Line%2039000%20(115kV)%20%E2%80%93%20Aguas%20Buenas%20Substation%20to%20Hacienda%20San%20Jose%5D%20(Vegetation)%20DSOW%20V1%20rev.1.pdf?web=1 07/25/2025 01:09 PM AST - Project submitted as "428 only" on 07.24.2025 as per FEMA guidance for expedited obligation. Project is under FEMA review. 07/25/2025 10:48 AM AST - LUMA uploaded on 07.24.2025 a revised DSOW and LPCE as a "428 only" oriented project in alignment to a request by COR3 and FEMA to do so in support of the DOE directive and a commitment from FEMA to expedite obligations of vegetation related projects. 8/12/2025 9:17 AM - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. 8/15/2025 10:47 AM EDT - Field EHP - Historic: Previous Status Applies. This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. Once more information is available on the progress of these discussions, an ECD will be provided. | 2026-02-25 14:29 | 2025-06-12 16:09 | Marlina Crespo |  | Ashleah Dingle |  |  | 10064.57 | 0 | 1 | 3.6232 | 1 |  | 956356RFI1409 | 956356 |  |  | 0
956357 | 108160 | 12705648.38 | 9313002.71 | 260212.32 |  | 3132433.36 | 714000.65 | 8599002.06 | 12445436.07 | 12705648.39 | [11 empty] | 0 | 0 |  |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1677/956357%20-%20FAASt%20%5BMayaguez%20Region%205%20Line%201900%20(38kV)%20%E2%80%93Dos%20Bocas%20HP%20to%20San%20Sebastian%20TC%5D%20(Vegetation)%20DSOW%20Rev%203.pdf?web=1 | 2026-02-25 14:30 | 2025-06-12 16:09 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.0209 | 1 |  | 956357RFI1407 | 956357 |  |  | 0
956593 | 108161 | 5907319.61 | 0 | 414861.11 |  | 5492458.5 | 0 | 0 | 5492458.5 | 5907319.61 |  |  | 2025-09-22 |  | 3751193.63 | 3751193.63 |  |  |  | 1741264.87 |  | 3751193.63 | 3751193.63 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1690/PW%20108161%20PRJ_MultiVersionReport_956593_20250923.pdf?web=1 |  | 2026-02-25 14:31 | 2025-06-24 09:46 | Marlina Crespo |  | Ashleah Dingle |  |  | 414861.11 | 0 | 1 | 1.0755 | 1 |  | 956593RFI1419 | 956593 | 1741264.87 |  | 1741264.87
956782 | 108162 | 21957625.63 | 2769954.18 | 2489006.38 |  | 19468619.25 | 313928.68 | 2456025.5 | 22238573.43 | 24727579.81 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1691/956782-DR4339PR-6802-04%20DSOW%20Full%20428-406_06212025%20Rev%200.pdf?web=1 |  | 2026-02-25 14:31 | 2025-06-26 09:35 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 0.98737 | 1 | 2025-08-15 | 956782RFI1420 | 956782 | 2239396.69 | 615641.23 | 2855037.92
957578 | 108163 | 1250845.17 | 0 | 141856.25 |  | 1108989.51 | 0 | 0 | 1108989.51 | 1250845.76 |  |  | 2025-09-17 |  | 1108990 | 1108990 | [5 empty] | 1108990 | 1108990 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1692/PW%20108163%20PRJ_MultiVersionReport_957578_20250917.pdf?web=1 | 7/31/2025 - EHP final review. ECD: 8/07/2025. 8/13/2025 9:47 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly | 2026-02-25 14:32 | 2025-07-09 09:23 | Marlina Crespo |  | Ashleah Dingle |  |  | 141856.25 | 0 | 1 | 1.1279 | 1 |  | 957578RFI1421 | 957578 |  |  | 0
958367 | 108164 | 14474191.76 | 1172038.62 | 2885305.81 |  | 11588885.95 | 233606.49 | 938432.13 | 12760924.57 | 15646230.38 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1694/958367-DR4339PR-6603-01%20Detail%20Scope%20of%20Work%20Full%20428%20-%20406%20Rev_0.pdf?web=1 |  | 2026-02-25 14:32 | 2025-07-16 09:42 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1.1343 | 1 | 2025-08-15 | qwer506 | 958367 | 1224980.72 | 253175.12 | 1478155.84
1064452 | 108242 | 1569945.94 | 33695.78 | 85434.18 | 44078.65 | 640758.24 | 6440.37 | 27255.41 | 674454.02 | 759888.2 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1696/753781-DR4339PR-Detailed%20SOW-TPole%20Line%20800%20Comsat%20Sect%20%e2%80%93%20Cidra%20Sect_8.13.2025.pdf |  | 2026-02-25 13:31 | 2026-01-29 16:38 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 2.3277 | 1 |  |  | 1064452 |  |  | 0
36600 115kV San Sabastian - Dos Bocas (Batch 5) | [7 empty] | 0 | 107109345 | 107109345 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-26 11:04 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer183 | 36600 115kV San Sabastian - Dos Bocas (Batch 5) |  |  | 0
36600 115kV San Sebastian – Dos Bocas (Batch 6) | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:56 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | 36600 115kV San Sebastian – Dos Bocas (Batch 6)RFI492 | 36600 115kV San Sebastian – Dos Bocas (Batch 6) |  |  | 0
3700 - Striker to Arroyo | [7 empty] | 0 | 2083233 | 2083233 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (6 - no PLRC) | 2025-07-18 18:28 | 2023-12-27 09:55 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | 3700 - Striker to ArroyoRFI491 | 3700 - Striker to Arroyo |  |  | 0
41200 - Sabana Llana to Canóvanas | [7 empty] | 0 | 48460000 | 48460000 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (18 - PLRC Approval Required)3/19/2024 LUMA Regulatory ISOW to PREB Notes - TBD for PREB Submittal Target Date On Hold. Daniel Haughton is working with PM to update initial SOW. Once they complete that they will send it back to us for submittal. | 2025-07-18 18:30 | 2024-03-20 16:16 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer111 | 41200 - Sabana Llana to Canóvanas |  |  | 0
700 - Costa Sur to Yauco Plaza | [7 empty] | 0 | 24998791 | 24998791 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (18 - PLRC Approval Required) | 2025-07-18 18:30 | 2024-03-20 16:05 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer110 | 700 - Costa Sur to Yauco Plaza |  |  | 0
738671-1 | 11819 | [6 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 13:47 | 2024-03-19 14:59 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer104 | 738671-1 |  |  | 0
738671-2 | 11819 | [6 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 13:47 | 2024-03-19 15:00 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer105 | 738671-2 |  |  | 0
738671-3 | 11819 | [6 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 13:47 | 2024-03-19 15:01 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer106 | 738671-3 |  |  | 0
738671-4 | 11819 | [6 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2026-02-25 13:47 | 2024-06-13 13:05 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer225 | 738671-4 |  |  | 0
Adjuntas Pueblo 8.32kV 8202-01 | [7 empty] | 0 | 4500000 | 4500000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:01 | Jeremy Malone | Distribution Feeder Adjuntas Pueblo 8.32 kV 8202-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer140 | Adjuntas Pueblo 8.32kV 8202-01 |  |  | 0
Aguada 7205-01 4.16kV | [7 empty] | 0 | 13500000 | 13500000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:01 | Jeremy Malone | Distribution Feeder Aguada 7205-01 4.16 kV | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer141 | Aguada 7205-01 4.16kV |  |  | 0
Aguas Buenas 3701-02 | [7 empty] | 0 | 5200000 | 5200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:01 | Jeremy Malone | Distribution Feeder Aguas Buenas 3701-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer142 | Aguas Buenas 3701-02 |  |  | 0
Añasco 6101-04 | [7 empty] | 0 | 12600000 | 12600000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:01 | Jeremy Malone | Distribution Feeder Añasco 6101-04 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer143 | Añasco 6101-04 |  |  | 0
Añasco 6101-05 | [7 empty] | 0 | 10500000 | 10500000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:02 | Jeremy Malone | Distribution Feeder Añasco 6101-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer144 | Añasco 6101-05 |  |  | 0
Area Planning Bayamón A | [7 empty] | 0 | 89400000 | 89400000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:56 | Jeremy Malone | Area Planning ‐ Bayamón A | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer131 | Area Planning Bayamón A |  |  | 0
Area Planning Bayamón C | [7 empty] | 0 | 64800000 | 64800000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:56 | Jeremy Malone | Area Planning ‐ Bayamón C | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer132 | Area Planning Bayamón C |  |  | 0
Area Planning Bayamón F | [7 empty] | 0 | 119100000 | 119100000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:42 | Jeremy Malone | Area Planning - Bayamón F | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer123 | Area Planning Bayamón F |  |  | 0
Area Planning Bayamón G | [7 empty] | 0 | 42200000 | 42200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:43 | Jeremy Malone | Area Planning - Bayamón G | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer124 | Area Planning Bayamón G |  |  | 0
Area Planning San Juan A | [7 empty] | 0 | 120100000 | 120100000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-05 17:11 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer173 | Area Planning San Juan A |  |  | 0
Area Planning San Juan B | [7 empty] | 0 | 58200000 | 58200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:54 | Jeremy Malone | Area Planning - San Juan B | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer125 | Area Planning San Juan B |  |  | 0
Area Planning San Juan C | [7 empty] | 0 | 1507000 | 1507000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:54 | Jeremy Malone | Area Planning - San Juan C | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer126 | Area Planning San Juan C |  |  | 0
Area Planning San Juan D | [7 empty] | 0 | 71800000 | 71800000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:55 | Jeremy Malone | Area Planning - San Juan D | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer127 | Area Planning San Juan D |  |  | 0
Area Planning San Juan F | [7 empty] | 0 | 30300000 | 30300000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:55 | Jeremy Malone | Area Planning - San Juan F | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer128 | Area Planning San Juan F |  |  | 0
Area Planning San Juan G | [7 empty] | 0 | 39500000 | 39500000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:55 | Jeremy Malone | Area Planning - San Juan G | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer129 | Area Planning San Juan G |  |  | 0
Area Planning San Juan K | [7 empty] | 0 | 45400000 | 45400000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:56 | Jeremy Malone | Area Planning - San Juan K | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer130 | Area Planning San Juan K |  |  | 0
Arecibo Sectionalizer | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-07-26 10:19 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer251 | Arecibo Sectionalizer |  |  | 0
Asset Management System Implementation | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-05-30 16:35 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer184 | Asset Management System Implementation |  |  | 0
Bayamon TC 4kV 1714-02 | [7 empty] | 0 | 3750000 | 3750000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-05 17:05 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer171 | Bayamon TC 4kV 1714-02 |  |  | 0
Berwind 13KV 1336-07 | [7 empty] | 0 | 11200000 | 11200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:23 | Jeremy Malone | Distribution Feeder Berwin 13 kV 1336-07 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer120 | Berwind 13KV 1336-07 |  |  | 0
Buen Pastor 1908-03 | [7 empty] | 0 | 20700000 | 20700000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:26 | Jeremy Malone | Distribution Feeder Buen Pastor 1908-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer122 | Buen Pastor 1908-03618 |  |  | 0
Buen Pastor 1908-03 | [7 empty] | 0 | 20700000 | 20700000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:03 | Jeremy Malone | Distribution Feeder Buen Pastor 1908-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer145 | Buen Pastor 1908-03641 |  |  | 0
Buildings Island-Wide Program | [7 empty] | 0 | 97477246.69 | 97477246.69 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-05 16:22 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer169 | Buildings Island-Wide Program |  |  | 0
Cachete 13KV 1529-11 | [7 empty] | 0 | 8100000 | 8100000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 12:49 | Jeremy Malone | Distribution Feeder Cachete 13 kV 1529-11 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer118 | Cachete 13KV 1529-11 |  |  | 0
Cana (Interamericana) 1719-15 | [7 empty] | 0 | 7500000 | 7500000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:04 | Jeremy Malone | Distribution Feeder Cana (Interamericana) 1719-15 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer146 | Cana (Interamericana) 1719-15 |  |  | 0
Cana (Interamericana) 1719-18 | [7 empty] | 0 | 11200000 | 11200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:04 | Jeremy Malone | Distribution Feeder Cana (Interamericana) 1719-18 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer147 | Cana (Interamericana) 1719-18 |  |  | 0
Candelero 2604-01 | [7 empty] | 0 | 12700000 | 12700000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:04 | Jeremy Malone | Distribution Feeder Candelero 2604-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer148 | Candelero 2604-01 |  |  | 0
Caparra Sectionalizer | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-08-22 16:05 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer271 | Caparra Sectionalizer |  |  | 0
Cerro las Mesas 6010-02 | [7 empty] | 0 | 15000000 | 15000000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-05 17:05 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer170 | Cerro las Mesas 6010-02 |  |  | 0
Coamo PDS 4603-02 | [7 empty] | 0 | 12000000 | 12000000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:08 | Jeremy Malone | Distribution Feeder Coamo PDS 4603-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer149 | Coamo PDS 4603-02 |  |  | 0
Crea 1717-01 | [7 empty] | 0 | 7500000 | 7500000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:08 | Jeremy Malone | Distribution Feeders Crea 1717-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer150 | Crea 1717-01 |  |  | 0
Cuatro Hermanos 6004-02 | [7 empty] | 0 | 13900000 | 13900000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:08 | Jeremy Malone | Distribution Feeder Cuatro Hermanos 6004-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer151 | Cuatro Hermanos 6004-02 |  |  | 0
Dorado Pueblo 9202-04 | [7 empty] | 0 | 9800000 | 9800000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 12:40 | Jeremy Malone | Distribution Feeder Dorado Pueblo 8.32 kV 9202-04 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer114 | Dorado Pueblo 9202-04 |  |  | 0
El Abanico PDS 9605-02 | [7 empty] | 0 | 20400000 | 20400000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 12:42 | Jeremy Malone | Distribution Feeder El Abanico PDS 9605-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer116 | El Abanico PDS 9605-02 |  |  | 0
Encantada 1206-03 | [7 empty] | 0 | 12700000 | 12700000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:24 | Jeremy Malone | Distribution Feeder Encantada 1206-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer121 | Encantada 1206-03 |  |  | 0
FAASt number pending | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:38 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pendingRFI1058 | FAASt number pending |  |  | 0
FAASt Number Pending 1 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-20 15:25 | Marlina Crespo | Substation High Voltage Equipment Replacement | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 1RFI469 | FAASt Number Pending 1 |  |  | 0
FAASt Number Pending 10 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:09 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 10RFI476 | FAASt Number Pending 10 |  |  | 0
FAASt number pending 100 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer39 | FAASt number pending 100 |  |  | 0
FAASt number pending 101 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer40 | FAASt number pending 101 |  |  | 0
FAASt number pending 102 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:10 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer41 | FAASt number pending 102 |  |  | 0
FAASt number pending 103 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:11 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer42 | FAASt number pending 103 |  |  | 0
FAASt number pending 104 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:11 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer43 | FAASt number pending 104 |  |  | 0
FAASt number pending 105 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer44 | FAASt number pending 105 |  |  | 0
FAASt number pending 106 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer45 | FAASt number pending 106 |  |  | 0
FAASt number pending 107 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:13 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer46 | FAASt number pending 107 |  |  | 0
FAASt number pending 108 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:14 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer47 | FAASt number pending 108 |  |  | 0
FAASt number pending 109 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:14 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer48 | FAASt number pending 109 |  |  | 0
FAASt Number Pending 11 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:10 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 11RFI477 | FAASt Number Pending 11 |  |  | 0
FAASt number pending 110 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:15 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer49 | FAASt number pending 110 |  |  | 0
FAASt number pending 111 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:16 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer50 | FAASt number pending 111 |  |  | 0
FAASt number pending 112 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:16 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer51 | FAASt number pending 112 |  |  | 0
FAASt number pending 113 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer52 | FAASt number pending 113 |  |  | 0
FAASt number pending 114 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:18 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer53 | FAASt number pending 114 |  |  | 0
FAASt number pending 115 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:18 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer54 | FAASt number pending 115 |  |  | 0
FAASt number pending 116 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer55 | FAASt number pending 116 |  |  | 0
FAASt number pending 117 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer56 | FAASt number pending 117 |  |  | 0
FAASt number pending 118 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:22 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer57 | FAASt number pending 118 |  |  | 0
FAASt Number Pending 12 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:11 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 12RFI478 | FAASt Number Pending 12 |  |  | 0
FAASt number pending 120 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer58 | FAASt number pending 120 |  |  | 0
FAASt number pending 121 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer59 | FAASt number pending 121 |  |  | 0
FAASt number pending 122 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer60 | FAASt number pending 122 |  |  | 0
FAASt number pending 123 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer61 | FAASt number pending 123 |  |  | 0
FAASt number pending 124 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:27 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer62 | FAASt number pending 124 |  |  | 0
FAASt number pending 125 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:27 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer63 | FAASt number pending 125 |  |  | 0
FAASt number pending 126 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:28 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer64 | FAASt number pending 126560 |  |  | 0
FAASt number pending 126 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:28 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer65 | FAASt number pending 126561 |  |  | 0
FAASt number pending 127 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:29 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer66 | FAASt number pending 127 |  |  | 0
FAASt number pending 128 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:30 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer67 | FAASt number pending 128 |  |  | 0
FAASt number pending 129 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:31 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer68 | FAASt number pending 129 |  |  | 0
FAASt number pending 130 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:32 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer69 | FAASt number pending 130 |  |  | 0
FAASt number pending 131 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer70 | FAASt number pending 131 |  |  | 0
FAASt number pending 132 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer71 | FAASt number pending 132 |  |  | 0
FAASt number pending 133 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:34 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer72 | FAASt number pending 133 |  |  | 0
FAASt number pending 134 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:35 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer73 | FAASt number pending 134 |  |  | 0
FAASt number pending 135 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:35 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer74 | FAASt number pending 135 |  |  | 0
FAASt number pending 136 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer75 | FAASt number pending 136 |  |  | 0
FAASt number pending 137 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer76 | FAASt number pending 137 |  |  | 0
FAASt number pending 138 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer77 | FAASt number pending 138 |  |  | 0
FAASt number pending 139 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer78 | FAASt number pending 139 |  |  | 0
FAASt number pending 140 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer79 | FAASt number pending 140 |  |  | 0
FAASt number pending 141 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:14 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer80 | FAASt number pending 141 |  |  | 0
FAASt number pending 142 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:14 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer81 | FAASt number pending 142 |  |  | 0
FAASt number pending 143 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:15 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer82 | FAASt number pending 143 |  |  | 0
FAASt number pending 144 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:15 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer83 | FAASt number pending 144 |  |  | 0
FAASt number pending 145 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:16 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer84 | FAASt number pending 145 |  |  | 0
FAASt number pending 146 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer85 | FAASt number pending 146 |  |  | 0
FAASt number pending 147 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer86 | FAASt number pending 147 |  |  | 0
FAASt number pending 148 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer87 | FAASt number pending 148 |  |  | 0
FAASt number pending 149 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:18 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer88 | FAASt number pending 149 |  |  | 0
FAASt number pending 150 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:18 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer89 | FAASt number pending 150 |  |  | 0
FAASt number pending 151 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer90 | FAASt number pending 151 |  |  | 0
FAASt number pending 152 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer91 | FAASt number pending 152 |  |  | 0
FAASt number pending 153 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer92 | FAASt number pending 153 |  |  | 0
FAASt number pending 154 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer93 | FAASt number pending 154 |  |  | 0
FAASt number pending 155 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer94 | FAASt number pending 155 |  |  | 0
FAASt number pending 156 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer95 | FAASt number pending 156 |  |  | 0
FAASt number pending 157 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer96 | FAASt number pending 157 |  |  | 0
FAASt number pending 158 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:22 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer97 | FAASt number pending 158 |  |  | 0
FAASt number pending 159 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:22 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer98 | FAASt number pending 159 |  |  | 0
FAASt number pending 160 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer99 | FAASt number pending 160 |  |  | 0
FAASt number pending 161 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer100 | FAASt number pending 161 |  |  | 0
FAASt number pending 162 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:24 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer101 | FAASt number pending 162 |  |  | 0
FAASt number pending 163 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 16:24 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer102 | FAASt number pending 163 |  |  | 0
FAASt Number Pending 164 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-19 12:46 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer103 | FAASt Number Pending 164 |  |  | 0
FAASt number pending 165 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-19 15:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer107 | FAASt number pending 165 |  |  | 0
FAASt Number Pending 166 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-19 17:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer108 | FAASt Number Pending 166 |  |  | 0
FAASt Number Pending 167 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-19 17:39 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer109 | FAASt Number Pending 167 |  |  | 0
FAASt Number Pending 168 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-21 14:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer113 | FAASt Number Pending 168 |  |  | 0
FAASt number pending 171 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:26 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer186 | FAASt number pending 171 |  |  | 0
FAASt number pending 172 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:27 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer187 | FAASt number pending 172 |  |  | 0
FAASt number pending 173 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:27 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer188 | FAASt number pending 173 |  |  | 0
FAASt number pending 176 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:29 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer189 | FAASt number pending 176 |  |  | 0
FAASt number pending 178 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:31 | Marlina Crespo | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer190 | FAASt number pending 178 |  |  | 0
FAASt number pending 179 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:31 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer191 | FAASt number pending 179 |  |  | 0
FAASt number pending 180 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:33 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer192 | FAASt number pending 180 |  |  | 0
FAASt number pending 181 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-12 16:34 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer193 | FAASt number pending 181 |  |  | 0
FAASt number pending 184 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:20 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer194 | FAASt number pending 184 |  |  | 0
FAASt number pending 185 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer195 | FAASt number pending 185 |  |  | 0
FAASt number pending 186 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer196 | FAASt number pending 186 |  |  | 0
FAASt number pending 187 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:22 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer197 | FAASt number pending 187 |  |  | 0
FAASt number pending 188 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer198 | FAASt number pending 188 |  |  | 0
FAASt number pending 189 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:24 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer199 | FAASt number pending 189 |  |  | 0
FAASt number pending 190 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer200 | FAASt number pending 190 |  |  | 0
FAASt number pending 191 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:26 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer201 | FAASt number pending 191 |  |  | 0
FAASt number pending 192 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:27 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer202 | FAASt number pending 192 |  |  | 0
FAASt number pending 193 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:28 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer203 | FAASt number pending 193 |  |  | 0
FAASt number pending 194 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:29 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer204 | FAASt number pending 194 |  |  | 0
FAASt number pending 195 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:30 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer205 | FAASt number pending 195 |  |  | 0
FAASt number pending 196 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:30 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer206 | FAASt number pending 196 |  |  | 0
FAASt number pending 197 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:32 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer207 | FAASt number pending 197 |  |  | 0
FAASt number pending 198 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:32 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer208 | FAASt number pending 198 |  |  | 0
FAASt number pending 199 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:33 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer209 | FAASt number pending 199 |  |  | 0
FAASt number pending 200 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer210 | FAASt number pending 200 |  |  | 0
FAASt number pending 201 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer211 | FAASt number pending 201 |  |  | 0
FAASt number pending 202 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer212 | FAASt number pending 202 |  |  | 0
FAASt number pending 203 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:38 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer213 | FAASt number pending 203 |  |  | 0
FAASt number pending 204 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:39 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer214 | FAASt number pending 204 |  |  | 0
FAASt number pending 205 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:39 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer215 | FAASt number pending 205 |  |  | 0
FAASt number pending 206 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer216 | FAASt number pending 206 |  |  | 0
FAASt number pending 207 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 12:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer217 | FAASt number pending 207 |  |  | 0
FAASt number pending 208 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:42 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer218 | FAASt number pending 208 |  |  | 0
FAASt number pending 209 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:43 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer219 | FAASt number pending 209 |  |  | 0
FAASt number pending 210 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer220 | FAASt number pending 210 |  |  | 0
FAASt number pending 211 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer221 | FAASt number pending 211 |  |  | 0
FAASt number pending 212 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer222 | FAASt number pending 212 |  |  | 0
FAASt number pending 214 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:47 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer223 | FAASt number pending 214 |  |  | 0
FAASt number pending 215 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-06-13 12:47 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer224 | FAASt number pending 215 |  |  | 0
FAASt number pending 216 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:30 | 2024-06-13 13:09 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer226 | FAASt number pending 216 |  |  | 0
FAASt Number Pending 217 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:00 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer262 | FAASt Number Pending 217 |  |  | 0
FAASt Number Pending 218 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:02 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer263 | FAASt Number Pending 218 |  |  | 0
FAASt Number Pending 219 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:04 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer264 | FAASt Number Pending 219 |  |  | 0
FAASt Number Pending 220 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:06 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer265 | FAASt Number Pending 220 |  |  | 0
FAASt Number Pending 221 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:14 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer266 | FAASt Number Pending 221 |  |  | 0
FAASt Number Pending 223 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:29 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer267 | FAASt Number Pending 223 |  |  | 0
FAASt Number Pending 25 |  |  | 1776856 | 124341 |  | 725740 | 182964 | 1593892 | 2502596 | 2626937 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/522/729522-DR4339PR-%20DSOW-%20Group%208-%20DAR%20-%20BAYAMON%209401%209801%209802%20-%20FY24%20-%20signed.pdf?web=1 | 7AUGUST2024 ISOW / DSOW submitted on 1/31/24 - this project was replaced with another project - MC22JANUARY2025 - Removing the DSOW date - MC | 2025-07-18 18:28 | 2023-12-21 12:18 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 0 | 5 |  | FAASt Number Pending 25RFI480 | FAASt Number Pending 25 |  |  | 0
FAASt number pending 250 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:58 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer318 | FAASt number pending 250 |  |  | 0
FAASt number pending 251 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:36 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer408 | FAASt number pending 251 |  |  | 0
FAASt number pending 252 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer409 | FAASt number pending 252 |  |  | 0
FAASt number pending 253 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer410 | FAASt number pending 253 |  |  | 0
FAASt number pending 254 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer411 | FAASt number pending 254 |  |  | 0
FAASt number pending 255 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer412 | FAASt number pending 255 |  |  | 0
FAASt number pending 258 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer319 | FAASt number pending 258 |  |  | 0
FAASt number pending 259 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer320 | FAASt number pending 259 |  |  | 0
FAASt number pending 260 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer321 | FAASt number pending 260 |  |  | 0
FAASt number pending 261 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer322 | FAASt number pending 261 |  |  | 0
FAASt number pending 262 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer323 | FAASt number pending 262 |  |  | 0
FAASt number pending 263 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer324 | FAASt number pending 263 |  |  | 0
FAASt number pending 264 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer325 | FAASt number pending 264 |  |  | 0
FAASt number pending 265 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer326 | FAASt number pending 265 |  |  | 0
FAASt number pending 266 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer327 | FAASt number pending 266 |  |  | 0
FAASt number pending 267 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer328 | FAASt number pending 267 |  |  | 0
FAASt number pending 268 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer329 | FAASt number pending 268 |  |  | 0
FAASt number pending 269 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer330 | FAASt number pending 269 |  |  | 0
FAASt number pending 270 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer331 | FAASt number pending 270 |  |  | 0
FAASt number pending 271 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer332 | FAASt number pending 271 |  |  | 0
FAASt number pending 272 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer333 | FAASt number pending 272 |  |  | 0
FAASt number pending 273 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer334 | FAASt number pending 273 |  |  | 0
FAASt number pending 274 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer335 | FAASt number pending 274 |  |  | 0
FAASt number pending 275 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer336 | FAASt number pending 275 |  |  | 0
FAASt number pending 276 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer337 | FAASt number pending 276 |  |  | 0
FAASt number pending 277 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer338 | FAASt number pending 277 |  |  | 0
FAASt number pending 278 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer339 | FAASt number pending 278 |  |  | 0
FAASt number pending 279 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer340 | FAASt number pending 279 |  |  | 0
FAASt number pending 280 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer341 | FAASt number pending 280 |  |  | 0
FAASt number pending 281 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer342 | FAASt number pending 281 |  |  | 0
FAASt number pending 282 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer343 | FAASt number pending 282 |  |  | 0
FAASt number pending 283 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer344 | FAASt number pending 283 |  |  | 0
FAASt number pending 284 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer345 | FAASt number pending 284 |  |  | 0
FAASt number pending 285 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer346 | FAASt number pending 285 |  |  | 0
FAASt number pending 286 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer347 | FAASt number pending 286 |  |  | 0
FAASt number pending 287 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer348 | FAASt number pending 287 |  |  | 0
FAASt number pending 288 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer349 | FAASt number pending 288 |  |  | 0
FAASt number pending 289 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer350 | FAASt number pending 289 |  |  | 0
FAASt number pending 290 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer351 | FAASt number pending 290 |  |  | 0
FAASt number pending 291 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer352 | FAASt number pending 291 |  |  | 0
FAASt number pending 292 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer353 | FAASt number pending 292 |  |  | 0
FAASt number pending 293 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer354 | FAASt number pending 293 |  |  | 0
FAASt number pending 294 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer355 | FAASt number pending 294 |  |  | 0
FAASt number pending 295 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer356 | FAASt number pending 295 |  |  | 0
FAASt number pending 296 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer357 | FAASt number pending 296 |  |  | 0
FAASt number pending 297 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer358 | FAASt number pending 297 |  |  | 0
FAASt number pending 298 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer413 | FAASt number pending 298 |  |  | 0
FAASt number pending 299 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer414 | FAASt number pending 299 |  |  | 0
FAASt number pending 300 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer415 | FAASt number pending 300 |  |  | 0
FAASt number pending 301 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer416 | FAASt number pending 301 |  |  | 0
FAASt number pending 302 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer417 | FAASt number pending 302 |  |  | 0
FAASt number pending 303 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer359 | FAASt number pending 303 |  |  | 0
FAASt number pending 304 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer360 | FAASt number pending 304 |  |  | 0
FAASt number pending 305 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer361 | FAASt number pending 305 |  |  | 0
FAASt number pending 306 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer362 | FAASt number pending 306 |  |  | 0
FAASt number pending 307 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer363 | FAASt number pending 307 |  |  | 0
FAASt number pending 308 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer364 | FAASt number pending 308 |  |  | 0
FAASt number pending 309 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer365 | FAASt number pending 309 |  |  | 0
FAASt number pending 310 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer366 | FAASt number pending 310 |  |  | 0
FAASt number pending 311 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer367 | FAASt number pending 311 |  |  | 0
FAASt number pending 312 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer368 | FAASt number pending 312 |  |  | 0
FAASt number pending 313 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer369 | FAASt number pending 313 |  |  | 0
FAASt number pending 314 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer370 | FAASt number pending 314 |  |  | 0
FAASt number pending 315 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer371 | FAASt number pending 315 |  |  | 0
FAASt number pending 316 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer372 | FAASt number pending 316 |  |  | 0
FAASt number pending 317 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer373 | FAASt number pending 317 |  |  | 0
FAASt number pending 318 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer374 | FAASt number pending 318 |  |  | 0
FAASt number pending 319 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer375 | FAASt number pending 319 |  |  | 0
FAASt number pending 320 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer376 | FAASt number pending 320 |  |  | 0
FAASt number pending 321 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer377 | FAASt number pending 321 |  |  | 0
FAASt number pending 322 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer378 | FAASt number pending 322 |  |  | 0
FAASt number pending 323 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer379 | FAASt number pending 323 |  |  | 0
FAASt number pending 324 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer380 | FAASt number pending 324 |  |  | 0
FAASt number pending 325 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer381 | FAASt number pending 325 |  |  | 0
FAASt number pending 326 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer382 | FAASt number pending 326 |  |  | 0
FAASt number pending 327 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer383 | FAASt number pending 327 |  |  | 0
FAASt number pending 328 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer384 | FAASt number pending 328 |  |  | 0
FAASt number pending 329 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer385 | FAASt number pending 329 |  |  | 0
FAASt number pending 330 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | Transmission – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer386 | FAASt number pending 330 |  |  | 0
FAASt number pending 331 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Palo Seco SP to Catano SectLine-9500 (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer387 | FAASt number pending 331 |  |  | 0
FAASt number pending 332 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | Line 500 Ponce TC to Costa Sur SP | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer388 | FAASt number pending 332 |  |  | 0
FAASt number pending 333 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer389 | FAASt number pending 333 |  |  | 0
FAASt number pending 334 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer390 | FAASt number pending 334 |  |  | 0
FAASt number pending 335 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer391 | FAASt number pending 335 |  |  | 0
FAASt number pending 336 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer392 | FAASt number pending 336 |  |  | 0
FAASt number pending 337 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer393 | FAASt number pending 337 |  |  | 0
FAASt number pending 338 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer394 | FAASt number pending 338 |  |  | 0
FAASt number pending 339 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer395 | FAASt number pending 339 |  |  | 0
FAASt number pending 340 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer396 | FAASt number pending 340 |  |  | 0
FAASt number pending 341 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer397 | FAASt number pending 341 |  |  | 0
FAASt number pending 343 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer398 | FAASt number pending 343 |  |  | 0
FAASt number pending 344 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer399 | FAASt number pending 344 |  |  | 0
FAASt number pending 345 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer400 | FAASt number pending 345 |  |  | 0
FAASt number pending 346 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer401 | FAASt number pending 346 |  |  | 0
FAASt number pending 347 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer402 | FAASt number pending 347 |  |  | 0
FAASt number pending 348 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer403 | FAASt number pending 348 |  |  | 0
FAASt number pending 349 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer404 | FAASt number pending 349 |  |  | 0
FAASt number pending 350 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer405 | FAASt number pending 350 |  |  | 0
FAASt number pending 351 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer406 | FAASt number pending 351 |  |  | 0
FAASt number pending 357 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer286 | FAASt number pending 357 |  |  | 0
FAASt number pending 358 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer287 | FAASt number pending 358 |  |  | 0
FAASt number pending 361 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer288 | FAASt number pending 361 |  |  | 0
FAASt number pending 363 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer290 | FAASt number pending 363 |  |  | 0
FAASt number pending 364 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer291 | FAASt number pending 364 |  |  | 0
FAASt number pending 365 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer292 | FAASt number pending 365 |  |  | 0
FAASt number pending 366 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer293 | FAASt number pending 366 |  |  | 0
FAASt number pending 367 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer294 | FAASt number pending 367 |  |  | 0
FAASt number pending 371 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:35 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer297 | FAASt number pending 371 |  |  | 0
FAASt number pending 372 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer298 | FAASt number pending 372 |  |  | 0
FAASt number pending 373 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer299 | FAASt number pending 373 |  |  | 0
FAASt number pending 376 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer302 | FAASt number pending 376 |  |  | 0
FAASt number pending 377 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer303 | FAASt number pending 377 |  |  | 0
FAASt number pending 378 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer304 | FAASt number pending 378 |  |  | 0
FAASt number pending 379 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer305 | FAASt number pending 379 |  |  | 0
FAASt number pending 384 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer306 | FAASt number pending 384 |  |  | 0
FAASt number pending 385 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer307 | FAASt number pending 385 |  |  | 0
FAASt number pending 386 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer308 | FAASt number pending 386 |  |  | 0
FAASt number pending 389 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer309 | FAASt number pending 389 |  |  | 0
FAASt number pending 390 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer310 | FAASt number pending 390 |  |  | 0
FAASt number pending 391 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer311 | FAASt number pending 391 |  |  | 0
FAASt number pending 392 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer312 | FAASt number pending 392 |  |  | 0
FAASt number pending 393 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer313 | FAASt number pending 393 |  |  | 0
FAASt number pending 395 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer314 | FAASt number pending 395 |  |  | 0
FAASt number pending 396 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:38 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer315 | FAASt number pending 396 |  |  | 0
FAASt number pending 397 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer316 | FAASt number pending 397 |  |  | 0
FAASt number pending 398 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer317 | FAASt number pending 398 |  |  | 0
FAASt Number Pending 4 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:04 | Marlina Crespo | Vieques and Culebra Microgrid | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 4RFI470 | FAASt Number Pending 4 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 14:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer451 | FAASt Number Pending 400947 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer452 | FAASt Number Pending 400948 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer453 | FAASt Number Pending 400949 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:05 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer454 | FAASt Number Pending 400950 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:05 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer455 | FAASt Number Pending 400951 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:06 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer456 | FAASt Number Pending 400952 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:07 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer457 | FAASt Number Pending 400953 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:07 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer458 | FAASt Number Pending 400954 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:07 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer459 | FAASt Number Pending 400955 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer460 | FAASt Number Pending 400956 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer461 | FAASt Number Pending 400957 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer462 | FAASt Number Pending 400958 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:09 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer463 | FAASt Number Pending 400959 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:14 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer466 | FAASt Number Pending 400962 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:16 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer467 | FAASt Number Pending 400963 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer468 | FAASt Number Pending 400964 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer469 | FAASt Number Pending 400965 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer470 | FAASt Number Pending 400966 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer471 | FAASt Number Pending 400967 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:18 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer472 | FAASt Number Pending 400968 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer474 | FAASt Number Pending 400970 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer475 | FAASt Number Pending 400971 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer476 | FAASt Number Pending 400972 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer477 | FAASt Number Pending 400973 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer478 | FAASt Number Pending 400974 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer479 | FAASt Number Pending 400975 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer480 | FAASt Number Pending 400976 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer481 | FAASt Number Pending 400977 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer482 | FAASt Number Pending 400978 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:22 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer483 | FAASt Number Pending 400979 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:22 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer484 | FAASt Number Pending 400980 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer485 | FAASt Number Pending 400981 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer486 | FAASt Number Pending 400982 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer487 | FAASt Number Pending 400983 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer488 | FAASt Number Pending 400984 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:25 | Marlina Crespo | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer489 | FAASt Number Pending 400985 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer490 | FAASt Number Pending 400986 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer491 | FAASt Number Pending 400987 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer492 | FAASt Number Pending 400988 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:26 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer493 | FAASt Number Pending 400989 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:26 | Marlina Crespo | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer494 | FAASt Number Pending 400990 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 15:28 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer495 | FAASt Number Pending 400991 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:10 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer496 | FAASt Number Pending 400992 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:10 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer497 | FAASt Number Pending 400993 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:11 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer498 | FAASt Number Pending 400994 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer499 | FAASt Number Pending 400995 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer500 | FAASt Number Pending 400996 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer501 | FAASt Number Pending 400997 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer502 | FAASt Number Pending 400998 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer503 | FAASt Number Pending 400999 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-12-11 16:14 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer504 | FAASt Number Pending 4001000 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:14 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1001 | FAASt Number Pending 4001001 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:14 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1002 | FAASt Number Pending 4001002 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:14 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1003 | FAASt Number Pending 4001003 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:14 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1004 | FAASt Number Pending 4001004 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1010 | FAASt Number Pending 4001010 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1011 | FAASt Number Pending 4001011 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1012 | FAASt Number Pending 4001012 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1013 | FAASt Number Pending 4001013 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1014 | FAASt Number Pending 4001014 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1015 | FAASt Number Pending 4001015 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1016 | FAASt Number Pending 4001016 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1017 | FAASt Number Pending 4001017 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1018 | FAASt Number Pending 4001018 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1019 | FAASt Number Pending 4001019 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1020 | FAASt Number Pending 4001020 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1021 | FAASt Number Pending 4001021 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1022 | FAASt Number Pending 4001022 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1023 | FAASt Number Pending 4001023 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:25 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1024 | FAASt Number Pending 4001024 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:31 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1026 | FAASt Number Pending 4001026 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:34 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1029 | FAASt Number Pending 4001029 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:34 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1031 | FAASt Number Pending 4001031 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:35 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1032 | FAASt Number Pending 4001032 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:35 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1033 | FAASt Number Pending 4001033 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-12 14:27 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1034 | FAASt Number Pending 4001034 |  |  | 0
FAASt Number Pending 400 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-12 14:27 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 400RFI1035 | FAASt Number Pending 4001035 |  |  | 0
FAASt Number Pending 401 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-01-23 13:42 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 401RFI1041 | FAASt Number Pending 401 |  |  | 0
FAASt Number Pending 5 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:05 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 5RFI471 | FAASt Number Pending 5 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:34 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1050 | FAASt number pending 5001050 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:36 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1051 | FAASt number pending 5001051 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:37 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1053 | FAASt number pending 5001053 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1054 | FAASt number pending 5001054 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:37 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1055 | FAASt number pending 5001055 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:38 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1056 | FAASt number pending 5001056 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:38 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1057 | FAASt number pending 5001057 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:39 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1060 | FAASt number pending 5001060 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:40 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1062 | FAASt number pending 5001062 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:40 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1064 | FAASt number pending 5001064 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:40 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1066 | FAASt number pending 5001066 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:41 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1068 | FAASt number pending 5001068 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:42 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1071 | FAASt number pending 5001071 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1072 | FAASt number pending 5001072 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:42 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1073 | FAASt number pending 5001073 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1074 | FAASt number pending 5001074 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:43 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1075 | FAASt number pending 5001075 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:43 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1076 | FAASt number pending 5001076 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1077 | FAASt number pending 5001077 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1078 | FAASt number pending 5001078 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1079 | FAASt number pending 5001079 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1080 | FAASt number pending 5001080 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1081 | FAASt number pending 5001081 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1082 | FAASt number pending 5001082 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1083 | FAASt number pending 5001083 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1084 | FAASt number pending 5001084 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1085 | FAASt number pending 5001085 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1086 | FAASt number pending 5001086 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1087 | FAASt number pending 5001087 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1088 | FAASt number pending 5001088 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1089 | FAASt number pending 5001089 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1090 | FAASt number pending 5001090 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:47 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1092 | FAASt number pending 5001092 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:47 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1093 | FAASt number pending 5001093 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:48 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1094 | FAASt number pending 5001094 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:48 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1096 | FAASt number pending 5001096 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:49 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1098 | FAASt number pending 5001098 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:49 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1099 | FAASt number pending 5001099 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:50 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1101 | FAASt number pending 5001101 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:50 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1102 | FAASt number pending 5001102 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:50 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1104 | FAASt number pending 5001104 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1105 | FAASt number pending 5001105 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1106 | FAASt number pending 5001106 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1107 | FAASt number pending 5001107 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1108 | FAASt number pending 5001108 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1109 | FAASt number pending 5001109 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:52 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1110 | FAASt number pending 5001110 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:52 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1111 | FAASt number pending 5001111 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:53 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1112 | FAASt number pending 5001112 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:53 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1113 | FAASt number pending 5001113 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:53 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1114 | FAASt number pending 5001114 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:53 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1115 | FAASt number pending 5001115 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1116 | FAASt number pending 5001116 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1117 | FAASt number pending 5001117 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1118 | FAASt number pending 5001118 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1119 | FAASt number pending 5001119 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:56 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1120 | FAASt number pending 5001120 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:56 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1121 | FAASt number pending 5001121 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1122 | FAASt number pending 5001122 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1123 | FAASt number pending 5001123 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1124 | FAASt number pending 5001124 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1125 | FAASt number pending 5001125 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1126 | FAASt number pending 5001126 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1127 | FAASt number pending 5001127 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1128 | FAASt number pending 5001128 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1129 | FAASt number pending 5001129 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1130 | FAASt number pending 5001130 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1131 | FAASt number pending 5001131 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:00 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1132 | FAASt number pending 5001132 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:00 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1133 | FAASt number pending 5001133 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:00 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1134 | FAASt number pending 5001134 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1135 | FAASt number pending 5001135 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1136 | FAASt number pending 5001136 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1137 | FAASt number pending 5001137 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1138 | FAASt number pending 5001138 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1139 | FAASt number pending 5001139 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1140 | FAASt number pending 5001140 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1141 | FAASt number pending 5001141 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1142 | FAASt number pending 5001142 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1143 | FAASt number pending 5001143 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1144 | FAASt number pending 5001144 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1145 | FAASt number pending 5001145 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1146 | FAASt number pending 5001146 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1147 | FAASt number pending 5001147 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1148 | FAASt number pending 5001148 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1149 | FAASt number pending 5001149 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1150 | FAASt number pending 5001150 |  |  | 0
FAASt number pending 500 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt number pending 500RFI1151 | FAASt number pending 5001151 |  |  | 0
FAASt Number Pending 56 |  |  | 570640 | 41953 |  | 322238 | 65735 | 504905 | 892878 | 934831 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/552/729522-DR4339PR-DSOW%20Group%2017-%20DAR%20-%20SAN%20JUAN%202403,2404%20-%20FY24%20-%20signed.pdf?web=1 | 7AUGUST2024 ISOW / DSOW submitted on 1/31/24 - this project was replaced with another project - MC22JANUARY2025 - Removing the DSOW date - MC | 2025-07-18 18:28 | 2023-12-21 12:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 0 | 5 |  | FAASt Number Pending 56RFI485 | FAASt Number Pending 56 |  |  | 0
FAASt Number Pending 6 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:06 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 6RFI472 | FAASt Number Pending 6 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:26 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1317 | FAASt Number Pending 6001317 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:28 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1318 | FAASt Number Pending 6001318 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:29 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1319 | FAASt Number Pending 6001319 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:30 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1320 | FAASt Number Pending 6001320 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:31 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1321 | FAASt Number Pending 6001321 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:31 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1322 | FAASt Number Pending 6001322 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:32 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1323 | FAASt Number Pending 6001323 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1324 | FAASt Number Pending 6001324 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1325 | FAASt Number Pending 6001325 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:34 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1326 | FAASt Number Pending 6001326 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:34 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1327 | FAASt Number Pending 6001327 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:35 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1328 | FAASt Number Pending 6001328 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1329 | FAASt Number Pending 6001329 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1330 | FAASt Number Pending 6001330 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1331 | FAASt Number Pending 6001331 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1332 | FAASt Number Pending 6001332 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1333 | FAASt Number Pending 6001333 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1334 | FAASt Number Pending 6001334 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1335 | FAASt Number Pending 6001335 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1336 | FAASt Number Pending 6001336 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1337 | FAASt Number Pending 6001337 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:38 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1338 | FAASt Number Pending 6001338 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1339 | FAASt Number Pending 6001339 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1340 | FAASt Number Pending 6001340 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1341 | FAASt Number Pending 6001341 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1342 | FAASt Number Pending 6001342 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:41 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1343 | FAASt Number Pending 6001343 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:41 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1344 | FAASt Number Pending 6001344 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:41 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1345 | FAASt Number Pending 6001345 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:41 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1346 | FAASt Number Pending 6001346 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1347 | FAASt Number Pending 6001347 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1348 | FAASt Number Pending 6001348 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1349 | FAASt Number Pending 6001349 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1350 | FAASt Number Pending 6001350 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1351 | FAASt Number Pending 6001351 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1352 | FAASt Number Pending 6001352 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1353 | FAASt Number Pending 6001353 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1354 | FAASt Number Pending 6001354 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1355 | FAASt Number Pending 6001355 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1356 | FAASt Number Pending 6001356 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1357 | FAASt Number Pending 6001357 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1358 | FAASt Number Pending 6001358 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1359 | FAASt Number Pending 6001359 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1360 | FAASt Number Pending 6001360 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1361 | FAASt Number Pending 6001361 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:46 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1362 | FAASt Number Pending 6001362 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:46 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1363 | FAASt Number Pending 6001363 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1364 | FAASt Number Pending 6001364 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1365 | FAASt Number Pending 6001365 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1366 | FAASt Number Pending 6001366 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:48 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1367 | FAASt Number Pending 6001367 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:49 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1368 | FAASt Number Pending 6001368 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:49 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1369 | FAASt Number Pending 6001369 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:50 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1370 | FAASt Number Pending 6001370 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:50 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1371 | FAASt Number Pending 6001371 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:50 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1372 | FAASt Number Pending 6001372 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-09-04 14:15 | 2025-06-12 15:51 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1373 | FAASt Number Pending 6001373 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-09-04 14:15 | 2025-06-12 15:52 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1374 | FAASt Number Pending 6001374 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:53 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1375 | FAASt Number Pending 6001375 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:53 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1376 | FAASt Number Pending 6001376 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:53 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1377 | FAASt Number Pending 6001377 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1378 | FAASt Number Pending 6001378 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1379 | FAASt Number Pending 6001379 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1380 | FAASt Number Pending 6001380 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1381 | FAASt Number Pending 6001381 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1382 | FAASt Number Pending 6001382 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1383 | FAASt Number Pending 6001383 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1384 | FAASt Number Pending 6001384 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1385 | FAASt Number Pending 6001385 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1386 | FAASt Number Pending 6001386 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 15:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1387 | FAASt Number Pending 6001387 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:03 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1388 | FAASt Number Pending 6001388 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1389 | FAASt Number Pending 6001389 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1390 | FAASt Number Pending 6001390 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1391 | FAASt Number Pending 6001391 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1392 | FAASt Number Pending 6001392 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1393 | FAASt Number Pending 6001393 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1394 | FAASt Number Pending 6001394 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:04 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1395 | FAASt Number Pending 6001395 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1396 | FAASt Number Pending 6001396 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:06 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1397 | FAASt Number Pending 6001397 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-06-12 16:06 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1398 | FAASt Number Pending 6001398 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:06 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1399 | FAASt Number Pending 6001399 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:06 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1400 | FAASt Number Pending 6001400 |  |  | 0
FAASt Number Pending 600 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:07 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 600RFI1401 | FAASt Number Pending 6001401 |  |  | 0
FAASt Number Pending 65 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-15 12:39 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer8 | FAASt Number Pending 65 |  |  | 0
FAASt Number Pending 66 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-15 12:39 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer9 | FAASt Number Pending 66 |  |  | 0
FAASt Number Pending 7 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:07 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 7RFI473 | FAASt Number Pending 7 |  |  | 0
FAASt number pending 72 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 11:00 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer10 | FAASt number pending 72 |  |  | 0
FAASt number pending 73 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 12:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer11 | FAASt number pending 73 |  |  | 0
FAASt number pending 74 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 12:59 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer12 | FAASt number pending 74508 |  |  | 0
FAASt number pending 74 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer13 | FAASt number pending 74509 |  |  | 0
FAASt number pending 75 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:02 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer14 | FAASt number pending 75 |  |  | 0
FAASt number pending 76 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:05 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer15 | FAASt number pending 76 |  |  | 0
FAASt number pending 77 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:07 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer16 | FAASt number pending 77 |  |  | 0
FAASt number pending 78 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:07 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer17 | FAASt number pending 78 |  |  | 0
FAASt Number Pending 8 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:08 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 8RFI474 | FAASt Number Pending 8 |  |  | 0
FAASt number pending 80 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:50 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer18 | FAASt number pending 80 |  |  | 0
FAASt number pending 81 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:52 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer19 | FAASt number pending 81 |  |  | 0
FAASt number pending 82 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:53 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer20 | FAASt number pending 82 |  |  | 0
FAASt number pending 83 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:54 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer21 | FAASt number pending 83 |  |  | 0
FAASt number pending 84 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:55 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer22 | FAASt number pending 84 |  |  | 0
FAASt number pending 85 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:56 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer23 | FAASt number pending 85 |  |  | 0
FAASt number pending 86 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer24 | FAASt number pending 86 |  |  | 0
FAASt number pending 87 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:41 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer25 | FAASt number pending 87 |  |  | 0
FAASt number pending 88 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer26 | FAASt number pending 88 |  |  | 0
FAASt number pending 89 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer27 | FAASt number pending 89 |  |  | 0
FAASt Number Pending 9 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:08 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt Number Pending 9RFI475 | FAASt Number Pending 9 |  |  | 0
FAASt number pending 90 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer28 | FAASt number pending 90 |  |  | 0
FAASt number pending 91 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer29 | FAASt number pending 91 |  |  | 0
FAASt number pending 92 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer30 | FAASt number pending 92 |  |  | 0
FAASt number pending 93 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer31 | FAASt number pending 93 |  |  | 0
FAASt number pending 94 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer32 | FAASt number pending 94 |  |  | 0
FAASt number pending 95 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:49 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer33 | FAASt number pending 95 |  |  | 0
FAASt number pending 96 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:50 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer34 | FAASt number pending 96530 |  |  | 0
FAASt number pending 96 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:51 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer35 | FAASt number pending 96531 |  |  | 0
FAASt number pending 97 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:57 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer36 | FAASt number pending 97 |  |  | 0
FAASt number pending 99 | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:58 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer38 | FAASt number pending 99 |  |  | 0
FAASt Pending | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-02-21 09:25 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt PendingRFI1045 | FAASt Pending1045 |  |  | 0
FAASt Pending | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-07 11:20 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | FAASt PendingRFI1047 | FAASt Pending1047 |  |  | 0
Fort Allen 13KV 5803-02 | [7 empty] | 0 | 18000000 | 18000000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 13:17 | Jeremy Malone | Distribution Feeder Fort Allen 5803-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer119 | Fort Allen 13KV 5803-02 |  |  | 0
Grana PDS 1907-05 | [7 empty] | 0 | 3000000 | 3000000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:08 | Jeremy Malone | Distribution Feeder Grana PDS 1907-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer152 | Grana PDS 1907-05 |  |  | 0
Hato Tejas TC 1713-05 | [7 empty] | 0 | 12300000 | 12300000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 12:41 | Jeremy Malone | Distribution Feeder Hato Tejas 1713-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer115 | Hato Tejas TC 1713-05 |  |  | 0
Humacao Pueblo 2601-01 | [7 empty] | 0 | 11200000 | 11200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-22 12:43 | Jeremy Malone | Distribution Feeder Humacao Pueblo 2601-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer117 | Humacao Pueblo 2601-01 |  |  | 0
Humacao TC 13 kV 2603-09 | [7 empty] | 0 | 17600000 | 17600000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:11 | Jeremy Malone | Distribution Feeder Humacao TC 13 kV 2603-09 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer153 | Humacao TC 13 kV 2603-09 |  |  | 0
Isabela Planta 3 7504-01 4.16kV | [7 empty] | 0 | 6900000 | 6900000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:12 | Jeremy Malone | Distribution Feeder Isabela Planta 3 7504-01 4.16 kV | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer154 | Isabela Planta 3 7504-01 4.16kV |  |  | 0
Juncos 3201-02 | [7 empty] | 0 | 15000000 | 15000000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:18 | Jeremy Malone | Distribution Feeder Juncos 3201-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer155 | Juncos 3201-02 |  |  | 0
Llorens Torres 13 kV 1118-08 | [7 empty] | 0 | 4200000 | 4200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:18 | Jeremy Malone | Distribution Feeder Llorens Torres 13 kV 1118-08 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer156 | Llorens Torres 13 kV 1118-08 |  |  | 0
Llorens Torres 13 kV 1118-09 | [7 empty] | 0 | 4500000 | 4500000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:18 | Jeremy Malone | Distribution Feeder Llorens Torres 13 kV 1118-09 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer157 | Llorens Torres 13 kV 1118-09 |  |  | 0
Maunabo TC Rev 2 | [7 empty] | 0 | 96115838 | 96115838 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/786/DR4339PR%20-%20FEMA%20ISOW%20Maunabo%20TC%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 4/1/2024 but has since been removed | 2025-07-18 18:30 | 2024-04-01 09:35 | Marlina Crespo | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 0 | 5 |  | qwer137 | Maunabo TC Rev 2 |  |  | 0
Mayaguez TC Rev 2 | [7 empty] | 0 | 14464362 | 14464362 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/787/DR4339PR-FEMA%20ISOW%20Mayaguez%20TC%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 4/1/2024 but has since been removed | 2025-07-18 18:30 | 2024-04-01 09:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 0 | 5 |  | qwer138 | Mayaguez TC Rev 2 |  |  | 0
Monacillos 13 kV 1346-03 | [7 empty] | 0 | 8200000 | 8200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:19 | Jeremy Malone | Distribution Feeder Monacillos 13 kV 1346-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer158 | Monacillos 13 kV 1346-03 |  |  | 0
Monterrey PDS 13 kV 9503-06 | [7 empty] | 0 | 11700000 | 11700000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:27 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer159 | Monterrey PDS 13 kV 9503-06 |  |  | 0
Morovis 8801 Rev 2 | [7 empty] | 0 | 5844709 | 5844709 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/831/DR4339PR-FEMA%20ISOW%20Morovis%208801%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 4/8/2024 but has since been removed | 2025-07-18 18:30 | 2024-04-08 10:43 | Marlina Crespo | Pampanos Relocation | Rey Roldan Rodríguez |  |  |  |  | 1 | 0 | 5 |  | qwer175 | Morovis 8801 Rev 2 |  |  | 0
Pending | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:57 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | PendingRFI494 | Pending494 |  |  | 0
Pending | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:59 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | PendingRFI495 | Pending495 |  |  | 0
Pending | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:59 | Gabriel Licha | Santurce Planta (Sect) 1116 | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | PendingRFI496 | Pending496 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:41 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1153 | Pending PREB Approval1153 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1154 | Pending PREB Approval1154 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1155 | Pending PREB Approval1155 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:48 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1156 | Pending PREB Approval1156 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:51 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1157 | Pending PREB Approval1157 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:51 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1158 | Pending PREB Approval1158 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:53 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1159 | Pending PREB Approval1159 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1160 | Pending PREB Approval1160 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1161 | Pending PREB Approval1161 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:35 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1162 | Pending PREB Approval1162 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:36 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1163 | Pending PREB Approval1163 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:36 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1164 | Pending PREB Approval1164 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1165 | Pending PREB Approval1165 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1166 | Pending PREB Approval1166 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1167 | Pending PREB Approval1167 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1168 | Pending PREB Approval1168 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1169 | Pending PREB Approval1169 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1170 | Pending PREB Approval1170 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:42 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1171 | Pending PREB Approval1171 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:43 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1172 | Pending PREB Approval1172 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:44 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1173 | Pending PREB Approval1173 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:44 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1174 | Pending PREB Approval1174 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:45 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1175 | Pending PREB Approval1175 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:45 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1176 | Pending PREB Approval1176 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1177 | Pending PREB Approval1177 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:47 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1178 | Pending PREB Approval1178 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:51 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1179 | Pending PREB Approval1179 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1180 | Pending PREB Approval1180 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1181 | Pending PREB Approval1181 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:03 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1182 | Pending PREB Approval1182 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:04 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1183 | Pending PREB Approval1183 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:04 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1184 | Pending PREB Approval1184 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:06 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1185 | Pending PREB Approval1185 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:12 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1186 | Pending PREB Approval1186 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:12 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1187 | Pending PREB Approval1187 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:15 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1188 | Pending PREB Approval1188 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:16 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1189 | Pending PREB Approval1189 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1190 | Pending PREB Approval1190 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:19 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1191 | Pending PREB Approval1191 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:20 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1192 | Pending PREB Approval1192 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1193 | Pending PREB Approval1193 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1194 | Pending PREB Approval1194 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:23 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1195 | Pending PREB Approval1195 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:26 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1196 | Pending PREB Approval1196 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:26 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1197 | Pending PREB Approval1197 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:27 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1198 | Pending PREB Approval1198 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:28 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1199 | Pending PREB Approval1199 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:28 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1200 | Pending PREB Approval1200 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:29 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1201 | Pending PREB Approval1201 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1202 | Pending PREB Approval1202 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1203 | Pending PREB Approval1203 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:32 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1204 | Pending PREB Approval1204 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:33 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1205 | Pending PREB Approval1205 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:33 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1206 | Pending PREB Approval1206 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:34 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1207 | Pending PREB Approval1207 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:35 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1208 | Pending PREB Approval1208 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:36 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1209 | Pending PREB Approval1209 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1210 | Pending PREB Approval1210 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1211 | Pending PREB Approval1211 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1212 | Pending PREB Approval1212 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1213 | Pending PREB Approval1213 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1214 | Pending PREB Approval1214 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:41 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1215 | Pending PREB Approval1215 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:43 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1216 | Pending PREB Approval1216 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:43 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1217 | Pending PREB Approval1217 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:44 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1218 | Pending PREB Approval1218 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:44 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1219 | Pending PREB Approval1219 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1220 | Pending PREB Approval1220 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1221 | Pending PREB Approval1221 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:47 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1222 | Pending PREB Approval1222 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:48 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1223 | Pending PREB Approval1223 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:48 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1224 | Pending PREB Approval1224 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:49 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1225 | Pending PREB Approval1225 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:50 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1226 | Pending PREB Approval1226 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:51 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1227 | Pending PREB Approval1227 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:53 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1228 | Pending PREB Approval1228 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:53 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1229 | Pending PREB Approval1229 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:54 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1230 | Pending PREB Approval1230 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:57 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1231 | Pending PREB Approval1231 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:58 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1232 | Pending PREB Approval1232 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:58 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1233 | Pending PREB Approval1233 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:59 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1234 | Pending PREB Approval1234 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1235 | Pending PREB Approval1235 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1236 | Pending PREB Approval1236 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1237 | Pending PREB Approval1237 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:05 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1238 | Pending PREB Approval1238 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:06 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1239 | Pending PREB Approval1239 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:07 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1240 | Pending PREB Approval1240 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:09 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1241 | Pending PREB Approval1241 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:10 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1242 | Pending PREB Approval1242 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:16 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1243 | Pending PREB Approval1243 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:16 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1244 | Pending PREB Approval1244 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:17 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1245 | Pending PREB Approval1245 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1246 | Pending PREB Approval1246 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1247 | Pending PREB Approval1247 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 15:19 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1248 | Pending PREB Approval1248 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:35 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1249 | Pending PREB Approval1249 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1250 | Pending PREB Approval1250 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1251 | Pending PREB Approval1251 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:55 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1252 | Pending PREB Approval1252 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:56 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1253 | Pending PREB Approval1253 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:56 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1254 | Pending PREB Approval1254 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:57 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1255 | Pending PREB Approval1255 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:58 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1256 | Pending PREB Approval1256 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:58 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1257 | Pending PREB Approval1257 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:59 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1258 | Pending PREB Approval1258 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 08:59 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1259 | Pending PREB Approval1259 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1260 | Pending PREB Approval1260 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1261 | Pending PREB Approval1261 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1262 | Pending PREB Approval1262 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:02 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1263 | Pending PREB Approval1263 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:03 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1264 | Pending PREB Approval1264 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:03 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1265 | Pending PREB Approval1265 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:04 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1266 | Pending PREB Approval1266 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:05 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1267 | Pending PREB Approval1267 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:06 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1268 | Pending PREB Approval1268 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:07 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1269 | Pending PREB Approval1269 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:07 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1270 | Pending PREB Approval1270 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:08 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1271 | Pending PREB Approval1271 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:09 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1272 | Pending PREB Approval1272 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:09 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1273 | Pending PREB Approval1273 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:10 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1274 | Pending PREB Approval1274 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:10 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1275 | Pending PREB Approval1275 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:11 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1276 | Pending PREB Approval1276 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:11 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1277 | Pending PREB Approval1277 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:12 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1278 | Pending PREB Approval1278 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:13 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1279 | Pending PREB Approval1279 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:13 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1280 | Pending PREB Approval1280 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:14 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1281 | Pending PREB Approval1281 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:14 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1282 | Pending PREB Approval1282 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:15 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1283 | Pending PREB Approval1283 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:15 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1284 | Pending PREB Approval1284 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:17 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1285 | Pending PREB Approval1285 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:19 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1286 | Pending PREB Approval1286 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:21 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1287 | Pending PREB Approval1287 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1288 | Pending PREB Approval1288 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1289 | Pending PREB Approval1289 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1290 | Pending PREB Approval1290 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1291 | Pending PREB Approval1291 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1292 | Pending PREB Approval1292 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:45 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1293 | Pending PREB Approval1293 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1294 | Pending PREB Approval1294 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 09:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1295 | Pending PREB Approval1295 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1296 | Pending PREB Approval1296 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1297 | Pending PREB Approval1297 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:23 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1298 | Pending PREB Approval1298 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:24 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1299 | Pending PREB Approval1299 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:27 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1300 | Pending PREB Approval1300 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:29 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1301 | Pending PREB Approval1301 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1302 | Pending PREB Approval1302 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:32 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1303 | Pending PREB Approval1303 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:33 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1304 | Pending PREB Approval1304 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:33 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1305 | Pending PREB Approval1305 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:34 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1306 | Pending PREB Approval1306 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:36 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1307 | Pending PREB Approval1307 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1308 | Pending PREB Approval1308 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1309 | Pending PREB Approval1309 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1310 | Pending PREB Approval1310 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1311 | Pending PREB Approval1311 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1312 | Pending PREB Approval1312 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1313 | Pending PREB Approval1313 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-16 10:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1314 | Pending PREB Approval1314 |  |  | 0
Pending PREB Approval | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-17 12:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | Pending PREB ApprovalRFI1315 | Pending PREB Approval1315 |  |  | 0
Peñuelas Pueblo 5401-02 | [7 empty] | 0 | 8300000 | 8300000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:27 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer160 | Peñuelas Pueblo 5401-02 |  |  | 0
Rio Bayamon 1709-02 | [7 empty] | 0 | 8200000 | 8200000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:29 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer162 | Rio Bayamon 1709-02 |  |  | 0
Rio Bayamon 1709-05 | [7 empty] | 0 | 11100000 | 11100000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:27 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer161 | Rio Bayamon 1709-05 |  |  | 0
Sabana Grande 4.16 kV 6501-04 | [7 empty] | 0 | 9700000 | 9700000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:35 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer167 | Sabana Grande 4.16 kV 6501-04 |  |  | 0
San Jose 8104-02 4.16 kV | [7 empty] | 0 | 12000000 | 12000000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:29 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer163 | San Jose 8104-02 4.16 kV |  |  | 0
San Juan UG 115 KV Rebuild | [7 empty] | 0 | 195373742 | 195373742 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:56 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | San Juan UG 115 KV RebuildRFI493 | San Juan UG 115 KV Rebuild |  |  | 0
Sub - Rebuild Canas TC | [7 empty] | 0 | 71817966 | 71817966 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-26 11:02 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer181 | Sub - Rebuild Canas TC |  |  | 0
Sub Rebuild - Fajardo Sect | [7 empty] | 0 | 101312645.45 | 101312645.45 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Regulatory Notes on ISOW to PREB - PREB Submittal Target Date: On Hold, Notes: On hold. Awaiting guidance | 2025-07-18 18:28 | 2023-12-27 09:59 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer1 | Sub Rebuild - Fajardo Sect |  |  | 0
Sub Rebuild - Fajardo TC | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Regulatory Notes on ISOW to PREB - PREB Submittal Target Date: TBD, Notes: need the ISOW | 2025-07-18 18:30 | 2024-03-20 17:00 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer112 | Sub Rebuild - Fajardo TC |  |  | 0
Sub Rebuild - Santurce Planta | [7 empty] | 0 | 40362715 | 40362715 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-26 11:02 | Jeremy Malone | Santurce Planta (Sect) 1116 | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer180 | Sub Rebuild - Santurce Planta |  |  | 0
Substation Component Replacement Program | [7 empty] | 0 | 330300000 | 330300000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/782/DR4339PR-FEMA%20ISOW%20Substation%20Component%20Replacement%20Program%20Rev%200%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 3/26/2024 but has since been removed | 2025-07-18 18:30 | 2024-03-26 11:48 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 0 | 5 |  | qwer133 | Substation Component Replacement Program |  |  | 0
T&D Model Upgrades and Repair | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:59 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer2 | T&D Model Upgrades and Repair |  |  | 0
T/D Asset Model Verification | [7 empty] | 0 | 53716202 | 53716202 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-26 11:03 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer182 | T/D Asset Model Verification |  |  | 0
TBD L37400 Barceloneta TC - Cambalache TC | [7 empty] | 0 | 927000 | 927000 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/586/136271-DR4339PR-INITIAL%20SOW-Line%2037400%20Priority%20Pole%20Replacement%20Barceloneta%20TC%20-%20Cambalache%20TC%20-%20signed%5B25319%5D.pdf?web=1 | 02MAY2025 37400 is not a priority, and we dont know when it will be requested as a fasst - MC | 2025-08-11 09:18 | 2024-01-17 15:07 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 |  | qwer5 | TBD L37400 Barceloneta TC - Cambalache TC |  |  | 0
TBD Remaining Vegetation Funds | [7 empty] | 0 | -63127338.59 | -63127338.59 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-25 16:12 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer179 | TBD Remaining Vegetation Funds |  |  | 0
TBD UG Feeder Rebuilds - Phase 1 | [7 empty] | 0 | 249921003 | 249921003 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/785/DR-4339%20ISOW-UG%20Feeder%20Rebuilds%20-%20Phase%201_Rev.0%20-%20signed.pdf?web=1 | 02MAY2025 Taking the funds off the tracker. This is an island wide project and we already have 2 projects under this project umbrella - MC | 2025-08-11 09:18 | 2024-03-28 14:20 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 0 | 5 |  | qwer136 | TBD UG Feeder Rebuilds - Phase 1 |  |  | 0
TBD Venezuela Substation Transformer Replacement | [7 empty] | 0 | 3156254 | 3156254 | [11 empty] | 0 | 0 |  | /sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/844/DR4339PR-FEMA%20ISOW%20Venezuela%20Substation%20Transformer%20Replacement%20Rev.3%20-%20signed.pdf?web=1 |  | 2025-07-18 18:30 | 2024-06-03 13:35 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 0 | 5 |  | qwer185 | TBD Venezuela Substation Transformer Replacement |  |  | 0
Transmission Program ISOW | [7 empty] | 0 | 501947756 | 501947756 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-19 10:44 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer177 | Transmission Program ISOW |  |  | 0
Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana Llana | [7 empty] | 0 | 3000000000 | 3000000000 | [11 empty] | 0 | 0 |  |  | 3/20/2024 LUMA Regulatory notes on ISOW submission to PREB - On hold. Awaiting guidance | 2025-07-18 18:28 | 2023-12-27 09:55 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana LlanaRFI490 | Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana Llana |  |  | 0
Unibon 9.32 kV 9501-01 | [7 empty] | 0 | 11300000 | 11300000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:30 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer164 | Unibon 9.32 kV 9501-01 |  |  | 0
Vega Baja TC 13 kV 9004-08 | [7 empty] | 0 | 22800000 | 22800000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:34 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer165 | Vega Baja TC 13 kV 9004-08 |  |  | 0
Vega Baja TC 13 kV 9004-10 | [7 empty] | 0 | 21400000 | 21400000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:34 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer166 | Vega Baja TC 13 kV 9004-10 |  |  | 0
Venezuela Sectionalizer | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-08-22 15:21 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer270 | Venezuela Sectionalizer |  |  | 0
Victoria TC | [7 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-07-26 09:45 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | #DIV/0! | #DIV/0! |  | qwer250 | Victoria TC |  |  | 0
Villa del Carmen 5016-01 | [7 empty] | 0 | 11100000 | 11100000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-05 17:05 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer172 | Villa del Carmen 5016-01 |  |  | 0
Yabucoa Pueblo 2901-04 | [7 empty] | 0 | 12770000 | 12770000 | [11 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-04-03 13:52 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 0 | 5 |  | qwer168 | Yabucoa Pueblo 2901-04 |  |  | 0

## Attachment A
Expected Project Costs Allocation
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Process Step | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected Cost | Total 406 Expected Cost | Project Status | Expected COR3 Submission Date | Comments
666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 27201946.76 | 1465463.21 | 6380570.04 | 123157.52 | 976071 | 658009 | 36805217.53 | 34558587.8 | 2246629.73 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 10629532.275 | 655524.41 | 1713141.92 | 51717 | 339183 | 228657 | 13617755.605 | 12681857.195 | 935898.41 | DSOW – Scope and Cost Update in Progress | Q2 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Line Rebuild | No | Inactive | 9936000 | 5400000 | 864000 | 864000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | DSOW – Pending Design Package for Development | Q3 FY2027 | This line is key for hardening by replacing targeted structures as well as insulators and hardware along the entire line length, with a high-level estimate at $30M. Additional future scope proposed for 406 includes adding a 230/115kV new substation at Santa Isabel TC which would significantly reduce the exposure (probability and likelihood that the facility is not available after a storm) as well as facilitate a pathway for new large-scale renewables being added in the South and Southeast regions.
690483 | FAASt [Cayey Streetlighting] | Distribution | Streetlighting | No | Inactive | 10093033.82 | 936114.24 | 2435204.39 | 95954.76 | 503757 | 339603 | 14403667.21 | 13031995.21 | 1371672 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 13267153.655 | 370784.53 | 2795912.01 | 55146.97 | 744597 | 501963 | 17735557.165 | 16807662.665 | 927894.5 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 13069359.5825 | 220906.9 | 1972441.141 | 107984.699 | 958677 | 646283 | 16975652.3225 | 16000477.7235 | 975174.599 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 10758153.95 | 839531.97 | 2150579.88 | 58676.25 | 315768 | 212872 | 14335582.05 | 13224501.83 | 1111080.22 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 11412143.0925 | 485336.36 | 1902215.74 | 59360 | 466962 | 314798 | 14640815.1925 | 13781320.8325 | 859494.36 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 8241015.33 | 190912.38 | 1562084.58 | 22536.63 | 284994 | 192126 | 10493668.92 | 10088093.91 | 405575.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 15515918.205 | 2012364.47 | 3319870.72 | 155072.6 | 1245009 | 839311 | 23087545.995 | 20080797.925 | 3006748.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | No | Inactive | 3591270 | 1130585 | 332525 | 199515 | 465535 | 931070 | 6650500 | 4389330 | 2261170 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (23) 3PH Reclosers, (104) 1ph reclosers, (48) cFCi.
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 6954788.08 | 279702.31 | 1689593.17 | 41489.51 | 353232 | 238128 | 9556933.07 | 8997613.25 | 559319.82 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 11399484.83 | 1119131.43 | 2377385.56 | 89359.81 | 595410 | 401390 | 15982161.63 | 14372280.39 | 1609881.24 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 10405292.6975 | 287804.01 | 1631297.312 | 26436.06 | 589389 | 397331 | 13337550.0795 | 12625979.0095 | 711571.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 7024652.0375 | 209975.14 | 1206563.5 | 50306 | 397386 | 267894 | 9156776.6775 | 8628601.5375 | 528175.14 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 4596792.52 | 82066.81 | 1162797.94 | 17891.57 | 170595 | 115005 | 6145148.84 | 5930185.46 | 214963.38 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 8233261.46 | 807899.66 | 1621313.74 | 17891.57 | 369288 | 248952 | 11298606.43 | 10223863.2 | 1074743.23 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 3974160.015 | 215693.59 | 1011463.98 | 25642.92 | 133131 | 89749 | 5449840.505 | 5118754.995 | 331085.51 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 5694746.915 | 284606.44 | 1362869.66 | 17724.97 | 304395 | 205205 | 7869547.985 | 7362011.575 | 507536.41 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 6175629.8825 | 299807.81 | 1006696.36 | 29209 | 279642 | 188518 | 7979503.0525 | 7461968.2425 | 517534.81 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 5745883.39 | 496924.08 | 1332970.6 | 37797.8 | 259572 | 174988 | 8048135.87 | 7338425.99 | 709709.88 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | No | Inactive |  | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA. Contingent to FEMA Hazard Mitigation Evaluation and approval.
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | No | Inactive |  | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | No | Inactive |  | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | No | Inactive | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward.
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | No | Inactive |  | 20318919.35 |  | 5211394.35 |  | 30411453.8 | 55941767.5 | 0 | 55941767.5 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA
754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | Distribution | Underground | No | Inactive | 2013990.405 | 4475298.6789 | 169599.192 | 379478.1921 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward.
748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | IT/OT | N/A | No | Inactive | 33071971.884 | 4086750.8114 | 4724567.412 | 472456.7412 | 3307197.1884 | 1417370.2236 | 47080314.2606 | 41103736.4844 | 5976577.7762 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027
752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Rebuild | No | Inactive | 3553830.9091 | 524335.7079 | 349557.1386 | 116519.0462 | 466076.1848 | 815633.3234 | 5825952.31 | 4369464.2325 | 1456488.0775 | DSOW – Pending Design Package for Development | Q1 FY2028 | New DSOW needs to be developed , Proposed approach focused on replacing critical components: metal-clad, transformers, breakers, communications.
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 1313961.65 | 14439457.84 | 11049.14 | 121275.67 | 0 | 0 | 15885744.3 | 1325010.79 | 14560733.51 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 281345.36 | 3091775.16 | 2365.85 | 25967.52 | 0 | 0 | 3401453.89 | 283711.21 | 3117742.68 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 251201.23 | 2760513.52 | 2112.36 | 23185.29 | 0 | 0 | 3037012.4 | 253313.59 | 2783698.81 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 715385.11 | 7927576.7 | 6015.7 | 66028.4 | 0 | 0 | 8715005.91 | 721400.81 | 7993605.1 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation) | Vegetation | N/A | No | Inactive | 799358.09 | 8784348.55 | 6721.82 | 73778.93 | 0 | 0 | 9664207.39 | 806079.91 | 8858127.48 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 729380.61 | 8015348.33 | 6133.39 | 67320.16 | 0 | 0 | 8818182.49 | 735514 | 8082668.49 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 141749.28 | 1557718.3 | 1191.98 | 13083.11 | 0 | 0 | 1713742.67 | 142941.26 | 1570801.41 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 2053569.7 | 22567198.56 | 17268.5 | 189539.83 | 0 | 0 | 24827576.59 | 2070838.2 | 22756738.39 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 2278394.76 | 25037858.23 | 19159.06 | 210290.68 | 0 | 0 | 27545702.73 | 2297553.82 | 25248148.91 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 1842560.72 | 20248367.13 | 15494.13 | 170064.17 | 0 | 0 | 22276486.15 | 1858054.85 | 20418431.3 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 666580.3 | 7325219.95 | 5605.29 | 61523.84 | 0 | 0 | 8058929.38 | 672185.59 | 7386743.79 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 1322933.13 | 14538047.6 | 11124.57 | 122103.73 | 0 | 0 | 15994209.03 | 1334057.7 | 14660151.33 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal
740662 | [Automation Program Group 2] (TL/ Distribution | Distribution | Automation | No | Inactive | 21843000 | 6876500 | 2022500 | 1213500 | 2831500 | 5663000 | 40450000 | 26697000 | 13753000 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi.
741678 | [Automation Program Group 4] (TL/Distribution | Distribution | Automation | No | Inactive | 16985160 | 5347180 | 1572700 | 943620 | 2201780 | 4403560 | 31454000 | 20759640 | 10694360 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi.
705657 | [Automation Program Group 3] (TL/Distribution | Distribution | Automation | No | Inactive | 13656870 | 4299385 | 1264525 | 758715 | 1770335 | 3540670 | 25290500 | 16691730 | 8598770 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi.
730657 | [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission | Transmission | Line Rebuild | No | Inactive | 57872010.7354 | 31452179.7475 | 5032348.7596 | 5032348.7596 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | DSOW – Pending Design Package for Development | Q3 FY2027 | The planned scope for this facility is first to rebuild the undersized segment from Manati to Vega Baja to achieve a capacity increase to a minimum of 1160A. The proposed second phase is to restore the out-of-service segment from Dos Bocas to Cambalache. As requested by PMs based on latest value engineering, 3 segments were selected (1, 7 & 8)
704793 | [Yauco Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 12597812.93 | 1160589.76 | 2540431.6 | 79529.34 | 634212 | 427548 | 17440123.63 | 15772456.53 | 1667667.1 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
704744 | [San Sebastian Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 19955144.585 | 486338.95 | 4057973.95 | 94811.81 | 1566129 | 1055791 | 27216189.295 | 25579247.535 | 1636941.76 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
685869 | [Mayagüez TC] (Substation | Substation | Rebuild | No | Inactive | 22073642.86 | 543426.36 | 2605555.14 | 53174.57 | 13511059.91 | 183120 | 38969978.84 | 38190257.91 | 779720.93 | DSOW – Pending Design Package for Development | Q1 FY2027 | Awaiting cable termination and subcontractor. Received quote, started micropurchase. Breakers have already been maintained and transformer fans were replaced. Estimated Submission to COR3/FEMA 6/30/2026.
764707 | [Feeder Rebuild # 6012-02] (Distribution | Distribution | Rebuild | No | Inactive | 16634520 | 482160 | 5062680 | 241080 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | DSOW – Pending Design Package for Development | FY2029 | Design is about 39% complete. This project is currently classified as withdrawn (T1) and covers 5.74 miles with 239 structures. DSOW – Waiting on the design package to be developed.
764705 | [Feeder Rebuild # 6014-02] (Distribution | Distribution | Rebuild | No | Inactive | 23763600 | 688800 | 7232400 | 344400 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | DSOW – Pending Design Package for Development | FY2029 | Design is about 52% complete. This project is currently classified as withdrawn (T1) and covers 8.20 miles with 343 structures. DSOW – Waiting on the design package to be developed.
704929 | [San Lorenzo Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 12867034.6125 | 347830.72 | 2944605.83 | 60896.29 | 920544 | 620576 | 17761487.4525 | 16732184.4425 | 1029303.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
724828 | [Loiza Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 5936181.88 | 201637.58 | 1248099.37 | 14137.5 | 276966 | 186714 | 7863736.33 | 7461247.25 | 402489.08 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
698522 | [Vieques Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 3791271.0575 | 322022.91 | 810226.05 | 32120.4 | 196686 | 132594 | 5284920.4175 | 4798183.1075 | 486737.31 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
693615 | [Rio Grande Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 5156073.42 | 268046.05 | 1156399.63 | 21533.62 | 191334 | 128986 | 6922372.72 | 6503807.05 | 418565.67 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
698427 | [Maricao Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 4466381.615 | 647106.71 | 926826.7734 | 43337.3166 | 406752 | 274208 | 6764612.415 | 5799960.3884 | 964652.0266 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer.
724941 | [Aguas Buenas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 11340397.36 | 201510.89 | 2036460.34 | 0 | 693084 | 467236 | 14738688.59 | 14069941.7 | 668746.89 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
704741 | [Moca Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 17932518.84 | 308495.64 | 3152500.55 | 0 | 1190151 | 802329 | 23385995.03 | 22275170.39 | 1110824.64 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724605 | [Guayanilla Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 7795083.32 | 183970.54 | 1372729.11 | 0 | 424146 | 285934 | 10061862.97 | 9591958.43 | 469904.54 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724599 | [Sabana Grande Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 10754272.51 | 236814.37 | 1906868.06 | 0 | 725196 | 488884 | 14112034.94 | 13386336.57 | 725698.37 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724669 | [Ciales Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 12013750.42 | 272974.74 | 2044738.82 | 0 | 741921 | 500159 | 15573543.98 | 14800410.24 | 773133.74 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724716 | [Quebradillas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 10502157.5 | 195150.03 | 1872541.02 | 0 | 642240 | 432960 | 13645048.55 | 13016938.52 | 628110.03 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
713795 | [Lares Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 11882095.1 | 217275.01 | 1974624.75 | 0 | 733893 | 494747 | 15302634.86 | 14590612.85 | 712022.01 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724670 | [Patillas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 8408428.82 | 119750.59 | 1456883.53 | 0 | 425484 | 286836 | 10697382.94 | 10290796.35 | 406586.59 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724781 | [Penuelas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 7929864.73 | 140145.41 | 1433020.87 | 0 | 398055 | 268345 | 10169431.01 | 9760940.6 | 408490.41 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
741097 | Region 1 San Juan Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA.
741098 | Region 3 Bayamon Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA.
741102 | Region 5 Mayaguez Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA.
741101 | Region 2 Arecibo Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA.
741104 | Region 6 Ponce Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA.
741100 | Region 4 Caguas Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA.
[6 empty] | 595423815.646 | 317047219.3924 | 101270058.7045 | 29159565.4211 | 56366956.4058 | 170203524.1003 | 1269471139.6701 | 753060830.7563 | 516410308.9138