## Incremental Projects List
Urgency | Project # | Title | Asset | Sub Asset | Process Step | Incurred Cost | Project costs * | 428 Allocation * | 406 Allocation * | Project Status | Additional comments
As LUMA has already procured $61M dollars of this equipment and it is on hand, there is a very high risk to ratepayers if LUMA is unable to get these FASST projects re-activated. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | Automation Program | Distribution | Automation |  | 75157137.71 | 296669500 | 178001700 | 118667800 | Inactive, a few years of engineered work order packages complete, major equipment (reclosers, poles, bypass switches) all procured and in LUMA warehouse. | This Automation Program included here is based on a grouping of projects that LUMA will split to separate groups during the formulation process as DSOW's are submitted to FEMA. $61M cost Incurred to E&M PW
Cost already incurred and project complete | Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | Component Replacement | Collaboration | 3763775.37 | 3763775.37 | 3763775.37 | 0 |  | Transformer purchased and reimbursed to E&M PW ($892,425). Installation and Comissioning paid under NFC.
Cost already incurred and project complete | Pending FAASt Number | Venezuela TC | Substation | Component Replacement | Collaboration | 2613825.35 | 2613825.35 | 2613825.35 | 0 |  | Project is work Completed, costs are per Work Completed Summary given to PREB. Transformer purchased with E&M PW ($1,037,090).
Cost already incurred and project complete | Pending FAASt Number | Substation Component Group 0 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 14145405.55 | 14145405.55 | 14145405.55 | 0 | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | Work Completed, Priority to get FEMA obligated, this is equipment purchased under the federal Equipment & Material PW but installed with NFC or DOE dollars, LUMA is requesting a FASST number to be reconciled for the Equipment purchased under E&M PW. All of this equipment cost would put rate payers at risk if it is not reconciled to child PWs. *16 Gas Circuit Breakers ($1,036,579), 5 Transformers - Sabana Llana 1646 ($968,203), Mora TC 112 MVA ($2,926,189.87), Caguas 112 MVA ($4,416,882), Isla Grande 112MVA ($2,926,189.87), Hogar Crea 112 MVA ($1,871,361.81)
Critical 230kV and 115kV Supply, Failing End Of Life Transformer Assets Require Replacement, Requires Redundancies for Reliability | Pending FAASt Number | Manati TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 90000000 | 54000000 | 36000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 8404 Manatí TC and new 13.2 kV distribution substation.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7642400 | 7260280 | 382120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 233 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 15350400 | 14582880 | 767520 | High Level Assesment (HLA) has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 468 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10463200 | 9940040 | 523160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 319 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10266400 | 9753080 | 513320 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 313 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 12792000 | 12152400 | 639600 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 390 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4723200 | 4487040 | 236160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 144 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10430400 | 9908880 | 521520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 318 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5936800 | 5639960 | 296840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 181 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1148000 | 1090600 | 57400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 35 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5346400 | 5079080 | 267320 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 163 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4428000 | 4206600 | 221400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 135 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4788800 | 4549360 | 239440 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 146 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1344800 | 1277560 | 67240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 41 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 656000 | 623200 | 32800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 20 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2591200 | 2461640 | 129560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 79 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1869600 | 1776120 | 93480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 57 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 18991200 | 18041640 | 949560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 579 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8593600 | 8163920 | 429680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 262 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 12496800 | 11871960 | 624840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 381 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8560800 | 8132760 | 428040 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 261 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7216000 | 6855200 | 360800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 220 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3378400 | 3209480 | 168920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 103 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3181600 | 3022520 | 159080 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 97 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8659200 | 8226240 | 432960 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 264 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1968000 | 1869600 | 98400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 60 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1344800 | 1277560 | 67240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 41 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1541600 | 1464520 | 77080 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 47 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 13972800 | 13274160 | 698640 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 426 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7150400 | 6792880 | 357520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 218 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 12070400 | 11466880 | 603520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 368 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8495200 | 8070440 | 424760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 259 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 9610400 | 9129880 | 480520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 293 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7642400 | 7260280 | 382120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 233 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 9249600 | 8787120 | 462480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 282 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 820000 | 779000 | 41000 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 25 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2656800 | 2523960 | 132840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 81 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2755200 | 2617440 | 137760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 84 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1902400 | 1807280 | 95120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 58 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 20 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1344800 | 1277560 | 67240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 41 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10922400 | 10376280 | 546120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 333 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 6560000 | 6232000 | 328000 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 200 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7544000 | 7166800 | 377200 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 230 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7248800 | 6886360 | 362440 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 221 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 23976800 | 22777960 | 1198840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 731 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1574400 | 1495680 | 78720 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 48 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2000800 | 1900760 | 100040 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 61 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3411200 | 3240640 | 170560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 104 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2492800 | 2368160 | 124640 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 76 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1738400 | 1651480 | 86920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 53 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5051200 | 4798640 | 252560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 154 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4559200 | 4331240 | 227960 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 139 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3509600 | 3334120 | 175480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 107 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2230400 | 2118880 | 111520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 68 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 20 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 590400 | 560880 | 29520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 18 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 21 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 524800 | 498560 | 26240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 16 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 22 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 557600 | 529720 | 27880 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 17 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 23 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 328000 | 311600 | 16400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 10 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 04 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8429600 | 8008120 | 421480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 257 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5248000 | 4985600 | 262400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 160 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4034400 | 3832680 | 201720 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 123 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 984000 | 934800 | 49200 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 30 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3509600 | 3334120 | 175480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 107 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 13743200 | 13056040 | 687160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 419 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5313600 | 5047920 | 265680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 162 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 6494400 | 6169680 | 324720 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 198 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4526400 | 4300080 | 226320 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 138 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2919200 | 2773240 | 145960 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 89 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1377600 | 1308720 | 68880 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 42 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3903200 | 3708040 | 195160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 119 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2164800 | 2056560 | 108240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 66 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1148000 | 1090600 | 57400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 35 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1312000 | 1246400 | 65600 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 40 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 918400 | 872480 | 45920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 28 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 21 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2361600 | 2243520 | 118080 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 72 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 22 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 328000 | 311600 | 16400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 10 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 23 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 295200 | 280440 | 14760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 9 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 24 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1476000 | 1402200 | 73800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 45 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4100000 | 3895000 | 205000 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 125 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 15416000 | 14645200 | 770800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 470 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7183200 | 6824040 | 359160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 219 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 07/San Juan Group 55 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 295200 | 280440 | 14760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 9 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3870400 | 3676880 | 193520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 118 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4231200 | 4019640 | 211560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 129 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2033600 | 1931920 | 101680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 62 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5018400 | 4767480 | 250920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 153 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 11/San Juan Group 55 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 623200 | 592040 | 31160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 19 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3870400 | 3676880 | 193520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 118 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 262400 | 249280 | 13120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 8 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5149600 | 4892120 | 257480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 157 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1115200 | 1059440 | 55760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 34 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 852800 | 810160 | 42640 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 26 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1738400 | 1651480 | 86920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 53 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 6658400 | 6325480 | 332920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 203 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 0 | 0 | 0 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 0 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 20 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2853600 | 2710920 | 142680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 87 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 21 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3017600 | 2866720 | 150880 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 92 poles submitted from HLAs. 428/406 split varies from pole to pole.
Historical Flooding in the Arecibo Pueblo Substation require it to be relocated to Arecibo Sectionalizer Site. Site is critical to stability of system. Due to relocation, much of the project is expected to be funded by FEMA. | Pending FAASt Number | Arecibo Sect. Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 71435277.14 | 7143527.714 | 64291749.426 | Project scope to be developed and approved by leadership | Rebuild of priority sectionalizing substation including colocated 8015 Arecibo Hospital Distrito and 8003 Arecibo Rural distribution substations and relocation to site of distribution substation 8002 Arecibo Pueblo substation (due to Historical Flooding).
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 6500 Reclosers 38 kV | Transmission | Automation |  | 203930.22 | 981405.16 | 461620.3 | 519784.86 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 8100 Reclosers 38 kV | Transmission | Automation |  | 224682.71 | 1500763.76 | 730612.8 | 770150.96 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 1500 Reclosers 38 kV | Transmission | Automation |  | 199953.32 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 13400 Reclosers 38 kV | Transmission | Automation |  | 207116.84 | 1321485.96 | 579867.07 | 741618.89 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 800 Reclosers 38 kV | Transmission | Automation |  | 181941.37 | 838354.58 | 614126.79 | 224227.79 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 12600 Reclosers 38 kV | Transmission | Automation |  | 188541.16 | 1935866.57 | 1448491.28 | 487375.29 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2000 Reclosers 38 kV | Transmission | Automation |  | 212415.97 | 1701253.27 | 1309036.7 | 392216.57 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 4800 Reclosers 38 kV | Transmission | Automation |  | 467207.73 | 2697229.44 | 2013222.35 | 684007.09 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 6 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 100 Reclosers 38 kV | Transmission | Automation |  | 214159.58 | 1213187.43 | 764308.0809 | 448879.3491 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3700 Reclosers 38 kV | Transmission | Automation |  | 267304.72 | 1340624.93 | 286655.46 | 1053969.47 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 1600 Reclosers 38 kV | Transmission | Automation |  | 210875.79 | 1453119.73 | 1063054.49 | 390065.24 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2200 Reclosers 38kV | Transmission | Automation |  | 232979.14 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3100 Reclosers 38 kV | Transmission | Automation |  | 234840.63 | 1847899.09 | 1398985.55 | 448913.54 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3000 Reclosers 38 kV | Transmission | Automation |  | 256545.43 | 1149274.52 | 724042.9476 | 425231.5724 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3600 Reclosers 38 kV | Transmission | Automation |  | 232527.63 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 8200 Reclosers 38 kV | Transmission | Automation |  | 251402.92 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3200 Reclosers 38 kV | Transmission | Automation |  | 210367.39 | 721651.14 | 537627.06 | 184024.08 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 300 Reclosers 38 kV | Transmission | Automation |  | 142345.67 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 500 Reclosers 38 kV | Transmission | Automation |  | 175562.55 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 700 Reclosers 38 kV | Transmission | Automation |  | 182303.58 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2400 Reclosers 38 kV | Transmission | Automation |  | 96272.4 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2600 Reclosers 38 kV | Transmission | Automation |  | 96098.36 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2700 Reclosers 38 kV | Transmission | Automation |  | 170382.53 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2800 Reclosers 38 kV | Transmission | Automation |  | 93434.48 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 4700 Reclosers 38 kV | Transmission | Automation |  | 98154.58 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 5200 Reclosers 38 kV | Transmission | Automation |  | 131892.52 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 5400 Reclosers 38 kV | Transmission | Automation |  | 166496.05 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 6000 Reclosers 38 kV | Transmission | Automation |  | 132659.3 | 472000 | 297360 | 174640 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 1 recloser
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 7100 Reclosers 38 kV | Transmission | Automation |  | 134356.27 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 8900 Reclosers 38 kV | Transmission | Automation |  | 242439.32 | 2832000 | 1784160 | 1047840 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 6 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 9400 Reclosers 38 kV | Transmission | Automation |  | 141431.54 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 10000 Reclosers 38 kV | Transmission | Automation |  | 167088.33 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 13700 Reclosers 38 kV | Transmission | Automation |  | 131189.64 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 5600 Reclosers 38 kV | Transmission | Automation |  | 222928.53 | 1389759.59 | 1047506.87 | 342252.72 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
Maria Damage, Worst Performing Asset, Reliability and Resilience Need, A&E Design Completed, Equipment In Stock | Pending FAASt Number | 36100-DOS BOCAS HP-BARRIO PIÑA SECT- | Transmission | Rebuild |  |  | 73601257.562 | 60353031.2008 | 13248226.3612 |  | Critical line for the 115kV system.
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1118-08 | Distribution | Line Rebuild |  | 5736.83 | 4205003.39 | 3868603.1188 | 336400.2712 | Under formulation. | Distribution Line Rebuild - 1.4 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1118-09 | Distribution | Line Rebuild |  | 2651.77 | 4505360.77 | 4144931.9084 | 360428.8616 | Under formulation. | Distribution Line Rebuild - 1.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1206-03 | Distribution | Line Rebuild |  | 1106.28 | 12765188.86 | 11743973.7512 | 1021215.1088 | Under formulation. | Distribution Line Rebuild - 4.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1336-07 | Distribution | Line Rebuild |  | 6263.82 | 11203330.46 | 10307064.0232 | 896266.4368 | Under formulation. | Distribution Line Rebuild - 3.73 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1346-03 | Distribution | Line Rebuild |  | -445.4 | 8259828.09 | 7599041.8428 | 660786.2472 | Under formulation. | Distribution Line Rebuild - 2.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1529-11 | Distribution | Line Rebuild |  | 0 | 8109649.39 | 7460877.4388 | 648771.9512 | Under formulation. | Distribution Line Rebuild - 2.7 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1709-02 | Distribution | Line Rebuild |  | 3227.53 | 8259828.09 | 7599041.8428 | 660786.2472 | Under formulation. | Distribution Line Rebuild - 2.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1709-05 | Distribution | Line Rebuild |  | 4728.14 | 11075781 | 10189718.52 | 886062.48 | Under formulation. | Distribution Line Rebuild - 2.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1711-05 | Distribution | Line Rebuild |  | 2665.69 | 6007147.7 | 5526575.884 | 480571.816 | Under formulation. | Distribution Line Rebuild - 2 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1713-05 | Distribution | Line Rebuild |  | 6189.43 | 12314652.78 | 11329480.5576 | 985172.2224 | Under formulation. | Distribution Line Rebuild - 4.1 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1714-02 | Distribution | Line Rebuild |  | 0 | 3754467.31 | 3454109.9252 | 300357.3848 | Under formulation. | Distribution Line Rebuild - 1.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1717-01 | Distribution | Line Rebuild |  | 2841.76 | 7508934.63 | 6908219.8596 | 600714.7704 | Under formulation. | Distribution Line Rebuild - 2.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1719-15 | Distribution | Line Rebuild |  | 8753.24 | 7508934.63 | 6908219.8596 | 600714.7704 | Under formulation. | Distribution Line Rebuild - 2.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1719-18 | Distribution | Line Rebuild |  | 1700.06 | 11263401.93 | 10362329.7756 | 901072.1544 | Under formulation. | Distribution Line Rebuild - 3.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1907-05 | Distribution | Line Rebuild |  | 291.25 | 3003573.85 | 2763287.942 | 240285.908 | Under formulation. | Distribution Line Rebuild - 1 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1908-03 | Distribution | Line Rebuild |  | 54.36 | 20694623.82 | 19039053.9144 | 1655569.9056 | Under formulation. | Distribution Line Rebuild - 6.89 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2601-01 | Distribution | Line Rebuild |  | 11873.35 | 11263401.93 | 10362329.7756 | 901072.1544 | Under formulation. | Distribution Line Rebuild - 3.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2603-09 | Distribution | Line Rebuild |  | 410.97 | 17661915.49 | 16248962.2508 | 1412953.2392 | Under formulation. | Distribution Line Rebuild - 4.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2604-01 | Distribution | Line Rebuild |  | 3101.36 | 12765188.86 | 11743973.7512 | 1021215.1088 | Under formulation. | Distribution Line Rebuild - 4.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2901-04 | Distribution | Line Rebuild |  | 0 | 12765188.86 | 11743973.7512 | 1021215.1088 | Under formulation. | Distribution Line Rebuild - 4.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 3201-02 | Distribution | Line Rebuild |  | 567.35 | 15017869.25 | 13816439.71 | 1201429.54 | Under formulation. | Distribution Line Rebuild - 5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 3701-02 | Distribution | Line Rebuild |  | 7659.65 | 5256254.23 | 4835753.8916 | 420500.3384 | Under formulation. | Distribution Line Rebuild - 1.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 4603-02 | Distribution | Line Rebuild |  | 5265.94 | 12014295.4 | 11053151.768 | 961143.632 | Under formulation. | Distribution Line Rebuild - 4 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 5016-01 | Distribution | Line Rebuild |  | 2015.38 | 11113223.25 | 10224165.39 | 889057.86 | Under formulation. | Distribution Line Rebuild - 3.7 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 5401-02 | Distribution | Line Rebuild |  | 454.35 | 8259828.09 | 7599041.8428 | 660786.2472 | Under formulation. | Distribution Line Rebuild - 2.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 5803-02 | Distribution | Line Rebuild |  | 1494.79 | 18021443.09 | 16579727.6428 | 1441715.4472 | Under formulation. | Distribution Line Rebuild - 6 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6004-02 | Distribution | Line Rebuild |  | 1807.96 | 13816439.71 | 12711124.5332 | 1105315.1768 | Under formulation. | Distribution Line Rebuild - 4.6 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6010-02 | Distribution | Line Rebuild |  | 285.76 | 15017869.25 | 13816439.71 | 1201429.54 | Under formulation. | Distribution Line Rebuild - 5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6101-04 | Distribution | Line Rebuild |  | 8022.88 | 12615010.17 | 11605809.3564 | 1009200.8136 | Under formulation. | Distribution Line Rebuild - 4.2 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6101-05 | Distribution | Line Rebuild |  | 805.54 | 10512508.47 | 9671507.7924 | 841000.6776 | Under formulation. | Distribution Line Rebuild - 3.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6501-04 | Distribution | Line Rebuild |  | 8026.2 | 9761615.02 | 8980685.8184 | 780929.2016 | Under formulation. | Distribution Line Rebuild - 3.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 7201-05 | Distribution | Line Rebuild |  | 13405.44 | 13516082.32 | 12434795.7344 | 1081286.5856 | Under formulation. | Distribution Line Rebuild - 4.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 7504-01 | Distribution | Line Rebuild |  | 731.18 | 6908219.86 | 6355562.2712 | 552657.5888 | Under formulation. | Distribution Line Rebuild - 2.3 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 8104-02 | Distribution | Line Rebuild |  | 8736.35 | 12014295.4 | 11053151.768 | 961143.632 | Under formulation. | Distribution Line Rebuild - 4 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 8202-01 | Distribution | Line Rebuild |  | 5594.11 | 4505360.77 | 4144931.9084 | 360428.8616 | Under formulation. | Distribution Line Rebuild - 1.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9004-08 | Distribution | Line Rebuild |  | 1297.28 | 22827161.26 | 21000988.3592 | 1826172.9008 | Under formulation. | Distribution Line Rebuild - 7.6 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9004-10 | Distribution | Line Rebuild |  | 4771.77 | 21325374.33 | 19619344.3836 | 1706029.9464 | Under formulation. | Distribution Line Rebuild - 7.1 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9202-04 | Distribution | Line Rebuild |  | 10730.73 | 9761615.02 | 8980685.8184 | 780929.2016 | Under formulation. | Distribution Line Rebuild - 3.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9501-01 | Distribution | Line Rebuild |  | 2032.72 | 11313401.93 | 10408329.7756 | 905072.1544 | Under formulation. | Distribution Line Rebuild - 3.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9503-06 | Distribution | Line Rebuild |  | 14060.58 | 11713938.01 | 10776822.9692 | 937115.0408 | Under formulation. | Distribution Line Rebuild - 3.9 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9605-02 | Distribution | Line Rebuild |  | 55749.64 | 20424302.18 | 18790358.0056 | 1633944.1744 | Under formulation. | Distribution Line Rebuild - 6.8 miles
New Line | Pending FAASt Number | 41200-SABANA LLANA TC-CANOVANAS TC- | Transmission | Rebuild |  |  | 22110644.6664 | 18130728.6264 | 3979916.04 |  | Critical line for the 115kV system.
Out of Service Line Affecting Hydro Generation | Pending FAASt Number | 8700-COSTA SUR SP-GARZAS 1 HP- | Transmission | Rebuild |  |  | 16305882.362 | 13370823.5368 | 2935058.8252 |  | Out of Service line output of a Power Plant.
Required Network Upgrade for Generation (Genera and Tranches) | Pending FAASt Number | 9300-JUNCOS TC-GAUTIER BENITEZ SECT- | Transmission | Rebuild |  |  | 27135375 | 22251007.5 | 4884367.5 |  | Critical line for the system.
Required Network Upgrade for Generation (Tranches and Genera) | Pending FAASt Number | Santa Isabel TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 60000000 | 36000000 | 24000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 4402 Santa Isabel TC.
Requires a transformer upgrade from 56 MVA to 112 MVA | Pending FAASt Number | Palmer TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 25000000 | 15000000 | 10000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 2305 Palmer
This station has numerous major issues that need to be remediated to ensure reliable service. Among these are the following: 1. Out of Service Transformer 2. Out of service underground transmission lines 3.Reliability Issues 4. Large Flood Risk 5. High Critical Loads | Pending FAASt Number | Chardon Sect. Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 25000000 | 15000000 | 10000000 | Project scope to be developed and approved by leadership | Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substations 1403 Chardon I and 1404 Chardón 2
Transformers already purchased and incoming, so if project is not included in Consolidated FASST portfolio there will be large risk to ratepayers as the transformers are incoming. | Pending FAASt Number | Substation Component Group 2 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 3133498.208 | 130000000 | 123500000 | 6500000 | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | Total of 10 substations with 9 transformers, 2 metal clad, 8 PAC Upgrade, 1 cap bank, 1 RTU, 9 Distribution and 8 transmission breakers replacements plus minor repair, grounding and security for all 10 stations. High Level budgetary estimates are around $130M
Transformers already purchased and incoming, so if project is not included in Consolidated FASST portfolio there will be large risk to ratepayers as the transformers are incoming. | Pending FAASt Number | Substation Component Group 3 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 14665406.49 | 330000000 | 313500000 | 16500000 | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 33 Transformer Replacements, Transformers already procured, manufacturing commencing with delivery dates from the middle of 2026 through 2028. Cost incurred is based on progress payments made to-date, but will increase as production of transformers continues. Additionally LUMA has committed* $71,868,237.51 for the purchase of these transformers, so there is significant risk to rate payers if this project is not enstated. These transformer replacements are targeting Out of Service, Capacity Constrained, and Transformer in bad conditions to ensure reliable service to customers and build in added reselience to the system. Due to the aforementioned reasons, this is one of LUMA's top priorities for obligation. *Commitment to purchase the transformers was already made under the federally funded Equipment and Material PW at the time due to having funds obligated and expectation of receiving child FASST obligations
Underground Out of Service | Pending FAASt Number | 16800-VEGA BAJA TC-VEGA ALTA SECT- | Transmission | Rebuild |  |  | 1033000 | 847060 | 185940 |  | Out of Service line it is is critical for the reliability of the 38 kV system.
Underground Out of Service | Pending FAASt Number | 40600-BAYAMON TC-MONACILLOS TC | Transmission | Rebuild |  |  | 65222221.57 | 53482221.6874 | 11739999.8826 |  | Out of Service line it is critical to the resiliency of the 115 kV system.
Underground Out of Service | Pending FAASt Number | 41600-PALO SECO SP-SAN JUAN SP- | Transmission | Rebuild |  |  | 45999999.54 | 37719999.6228 | 8279999.9172 |  | Out of Service line it is critical to the resiliency of the 115 kV system.
| Pending FAASt Number | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 136954530 | 36628489.0485 | 100284954.5925 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 188729100 | 50475597.795 | 138196883.475 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 33723810 | 9019432.9845 | 24694259.8725 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 165176460 | 44176444.227 | 120950462.835 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 218058975 | 58319872.8638 | 159673684.4437 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 160503255 | 42926595.5498 | 117528508.4737 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | 38kV Transmission Line 100 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5136889.56 | 428416.5893 | 4708472.9707 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 200 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 3130292.05 | 261066.357 | 2869225.693 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 800 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 3249603.27 | 271016.9127 | 2978586.3573 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5555563.43 | 463333.9901 | 5092229.4399 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 6154288.74 | 513267.6809 | 5641021.0591 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 6117410.71 | 510192.0532 | 5607218.6568 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 6141272.97 | 512182.1657 | 5629090.8043 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 16228492.86 | 1353456.3045 | 14875036.5555 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 4904775.04 | 409058.2383 | 4495716.8017 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 8256335.2 | 688578.3557 | 7567756.8443 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 9898491.21 | 825534.1669 | 9072957.0431 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 13100370.02 | 1092570.8597 | 12007799.1603 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 9475478.76 | 790254.9286 | 8685223.8314 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5113027.32 | 426426.4785 | 4686600.8415 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 2279928.56 | 190146.0419 | 2089782.5181 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 4800 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 8629453.86 | 719696.4519 | 7909757.4081 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 3345052.23 | 278977.356 | 3066074.874 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5807201.58 | 484320.6118 | 5322880.9682 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5915666.32 | 493366.5711 | 5422299.7489 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 9019926.9 | 752261.9035 | 8267664.9965 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 1500-ONCE DE AGOSTO SECT-SABANA GRANDE TO- | Transmission | Pole Replacement |  |  | 2440000 | 2171600 | 268400 |  | Pole Replacements: 13 Critical Repairs: 76
| Pending FAASt Number | 36400-PONCE TC-DOS BOCAS HP- | Transmission | Pole Replacement |  |  | 6240000 | 5553600 | 686400 |  | Pole Replacements: 51 Critical Repairs: 76
| Pending FAASt Number | 500-PONCE TC-COSTA SUR SP-CANAS TC | Transmission | Pole Replacement |  |  | 2495000 | 2220550 | 274450 |  | Pole Replacements: 23 Critical Repairs: 13
| Pending FAASt Number | 2100-HATILLO TC-QUEBRADILLAS SECT- | Transmission | Pole Replacement |  |  | 1315000 | 1170350 | 144650 |  | Pole Replacements: 7 Critical Repairs: 41
| Pending FAASt Number | 9300-JUNCOS TC-GAUTIER BENITEZ SECT- | Transmission | Pole Replacement |  |  | 1365000 | 1214850 | 150150 |  | Pole Replacements: 9 Critical Repairs: 31
| Pending FAASt Number | 2000-ONCE DE AGOSTO SECT-SAN SEBASTIAN TC- | Transmission | Pole Replacement |  |  | 3265000 | 2905850 | 359150 |  | Pole Replacements: 28 Critical Repairs: 31
| Pending FAASt Number | 50900-AGUIRRE SP-AGUAS BUENAS TC- | Transmission | Pole Replacement |  |  | 540000 | 480600 | 59400 |  | Pole Replacements: 0 Critical Repairs: 36
| Pending FAASt Number | 7300-BALDRICH SECT-SAN JOSE TO- | Transmission | Pole Replacement |  |  | 965000 | 858850 | 106150 |  | Pole Replacements: 8 Critical Repairs: 11
| Pending FAASt Number | 50700-AGUIRRE SP-AES PUERTO RICO- | Transmission | Pole Replacement |  |  | 315000 | 280350 | 34650 |  | Pole Replacements: 0 Critical Repairs: 21
| Pending FAASt Number | 1600-LEON SECT-ACACIAS TC- | Transmission | Pole Replacement |  |  | 2020000 | 1797800 | 222200 |  | Pole Replacements: 19 Critical Repairs: 8
| Pending FAASt Number | 51000-AGUAS BUENAS TC-SABANA LLANA TC- | Transmission | Pole Replacement |  |  | 405000 | 360450 | 44550 |  | Pole Replacements: 0 Critical Repairs: 27
| Pending FAASt Number | 37500-RIO BAYAMON SECT-MONACILLOS TC- | Transmission | Pole Replacement |  |  | 1450000 | 1290500 | 159500 |  | Pole Replacements: 13 Critical Repairs: 10
| Pending FAASt Number | 300-TORO NEGRO 1 HP-JUANA DIAZ TC- | Transmission | Pole Replacement |  |  | 2545000 | 2265050 | 279950 |  | Pole Replacements: 19 Critical Repairs: 43
| Pending FAASt Number | 13200-DORADO TC-HATO TEJAS TC- | Transmission | Pole Replacement |  |  | 580000 | 516200 | 63800 |  | Pole Replacements: 4 Critical Repairs: 12
| Pending FAASt Number | 7200-BALDRICH SECT-ESCUELA INDUSTRIAL TO- | Transmission | Pole Replacement |  |  | 370000 | 329300 | 40700 |  | Pole Replacements: 1 Critical Repairs: 18
| Pending FAASt Number | 8100-YAUCO 1 HP-ADJUNTAS TO- | Transmission | Pole Replacement |  |  | 4195000 | 3733550 | 461450 |  | Pole Replacements: 40 Critical Repairs: 13
| Pending FAASt Number | 10500-CHARDON SECT-LAS MONJAS TO- | Transmission | Pole Replacement |  |  | 190000 | 169100 | 20900 |  | Pole Replacements: 1 Critical Repairs: 6
| Pending FAASt Number | 36200-MONACILLOS TC-JUNCOS TC- | Transmission | Pole Replacement |  |  | 5445000 | 4846050 | 598950 |  | Pole Replacements: 51 Critical Repairs: 23
| Pending FAASt Number | 6500-TORO NEGRO 1 HP-BARRANQUITAS TC- | Transmission | Pole Replacement |  |  | 2350000 | 2091500 | 258500 |  | Pole Replacements: 22 Critical Repairs: 10
| Pending FAASt Number | 6100-MAYAGUEZ GP-RADIAL- | Transmission | Pole Replacement |  |  | 1085000 | 965650 | 119350 |  | Pole Replacements: 8 Critical Repairs: 19
| Pending FAASt Number | 1700-GUANICA TC-YAUCO 2 HP- | Transmission | Pole Replacement |  |  | 3950000 | 3515500 | 434500 |  | Pole Replacements: 38 Critical Repairs: 10
| Pending FAASt Number | 9900-RIO BLANCO HP-HUMACAO SECT- | Transmission | Pole Replacement |  |  | 1420000 | 1263800 | 156200 |  | Pole Replacements: 10 Critical Repairs: 28
| Pending FAASt Number | 10100-LAS LOMAS SECT-REPARTO METROPOLITANO TO- | Transmission | Pole Replacement |  |  | 620000 | 551800 | 68200 |  | Pole Replacements: 2 Critical Repairs: 28
| Pending FAASt Number | 2100-DOS BOCAS HP-HATILLO TC- | Transmission | Pole Replacement |  |  | 685000 | 609650 | 75350 |  | Pole Replacements: 4 Critical Repairs: 19
| Pending FAASt Number | 14100-BARCELONETA TC-MERCK- | Transmission | Pole Replacement |  |  | 165000 | 146850 | 18150 |  | Pole Replacements: 0 Critical Repairs: 11
| Pending FAASt Number | 36100-DOS BOCAS HP-BARRIO PIÑA SECT- | Transmission | Pole Replacement |  |  | 1205000 | 1072450 | 132550 |  | Pole Replacements: 8 Critical Repairs: 27
| Pending FAASt Number | 5200-CAGUAS TC-AGUAS BUENAS SECT- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 16300-CAMBALACHE TC-SUPER ACUEDUCTO- | Transmission | Pole Replacement |  |  | 205000 | 182450 | 22550 |  | Pole Replacements: 1 Critical Repairs: 7
| Pending FAASt Number | 11200-BUENA VISTA SECT-VILLA DEL CARMEN TO- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 18100-JUNCOS TC-RADIAL- | Transmission | Pole Replacement |  |  | 300000 | 267000 | 33000 |  | Pole Replacements: 0 Critical Repairs: 20
| Pending FAASt Number | 1000-VILLA PRADES SECT-CAPUCHINOS SECT- | Transmission | Pole Replacement |  |  | 210000 | 186900 | 23100 |  | Pole Replacements: 0 Critical Repairs: 14
| Pending FAASt Number | 50300-AGUIRRE SP-COSTA SUR SP- | Transmission | Pole Replacement |  |  | 150000 | 133500 | 16500 |  | Pole Replacements: 0 Critical Repairs: 10
| Pending FAASt Number | 50900-AGUAS BUENAS TC-BAYAMON TC- | Transmission | Pole Replacement |  |  | 390000 | 347100 | 42900 |  | Pole Replacements: 0 Critical Repairs: 26
| Pending FAASt Number | 3100-PALMER TC-FAJARDO TC- | Transmission | Pole Replacement |  |  | 200000 | 178000 | 22000 |  | Pole Replacements: 2 Critical Repairs: 0
| Pending FAASt Number | 3100-CANOVANAS SECT-RIO GRANDE TO- | Transmission | Pole Replacement |  |  | 45000 | 40050 | 4950 |  | Pole Replacements: 0 Critical Repairs: 3
| Pending FAASt Number | 36100-CANA SECT-BAYAMON TC- | Transmission | Pole Replacement |  |  | 150000 | 133500 | 16500 |  | Pole Replacements: 0 Critical Repairs: 10
| Pending FAASt Number | 5600-AÑASCO TC-MAYAGUEZ GP- | Transmission | Pole Replacement |  |  | 100000 | 89000 | 11000 |  | Pole Replacements: 1 Critical Repairs: 0
| Pending FAASt Number | 4700-CANAS TC-ADJUNTAS TO- | Transmission | Pole Replacement |  |  | 1670000 | 1486300 | 183700 |  | Pole Replacements: 14 Critical Repairs: 18
| Pending FAASt Number | 4100-COMERIO TC-GUARAGUAO SECT- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 38300-MONACILLOS TC-SAN JUAN SP- | Transmission | Pole Replacement |  |  | 680000 | 605200 | 74800 |  | Pole Replacements: 2 Critical Repairs: 32
| Pending FAASt Number | 9200-AÑASCO TC-AÑASCO- | Transmission | Pole Replacement |  |  | 610000 | 542900 | 67100 |  | Pole Replacements: 4 Critical Repairs: 14
| Pending FAASt Number | 5400-RIO BLANCO HP-DAGUAO TC- | Transmission | Pole Replacement |  |  | 350000 | 311500 | 38500 |  | Pole Replacements: 2 Critical Repairs: 10
| Pending FAASt Number | 3800-CIDRA SECT-CAYEY TC- | Transmission | Pole Replacement |  |  | 160000 | 142400 | 17600 |  | Pole Replacements: 1 Critical Repairs: 4
| Pending FAASt Number | 50200-MANATI TC-BAYAMON TC- | Transmission | Pole Replacement |  |  | 165000 | 146850 | 18150 |  | Pole Replacements: 0 Critical Repairs: 11
| Pending FAASt Number | 3600-MONACILLOS TC-SABANA LLANA TC- | Transmission | Pole Replacement |  |  | 175000 | 155750 | 19250 |  | Pole Replacements: 1 Critical Repairs: 5
| Pending FAASt Number | 14400-CAGUAX SECT-VEREDAS SECT- | Transmission | Pole Replacement |  |  | 2115000 | 1882350 | 232650 |  | Pole Replacements: 21 Critical Repairs: 1
| Pending FAASt Number | 14400-VEREDAS SECT-GAUTIER BENITEZ SECT- | Transmission | Pole Replacement |  |  | 300000 | 267000 | 33000 |  | Pole Replacements: 3 Critical Repairs: 0
| Pending FAASt Number | 3100-FAJARDO TC-DAGUAO TC- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 3600-SABANA LLANA TC-LOS ANGELES SECT- | Transmission | Pole Replacement |  |  | 195000 | 173550 | 21450 |  | Pole Replacements: 0 Critical Repairs: 13
| Pending FAASt Number | 36900-CANAS TC-PONCE TC- | Transmission | Pole Replacement |  |  | 45000 | 40050 | 4950 |  | Pole Replacements: 0 Critical Repairs: 3
| Pending FAASt Number | 5800-SAN FERNANDO SECT-CHARDON SECT- | Transmission | Rebuild |  |  | 11700000 | 9594000 | 2106000 |  | Out of Service underground line it is important for the reliability and resiliency of the system.
| Pending FAASt Number | 3300-CHARDON SECT-BALDRICH SECT- | Transmission | Rebuild |  |  | 6050000 | 4961000 | 1089000 |  | Out of Service underground line it is essential for maintaining system reliability and resiliency.
| Pending FAASt Number | 17100-MARTIN PEÑA TC-COLISEO SECT- | Transmission | Rebuild |  |  | 4125000 | 3382500 | 742500 |  | Out of Service underground line it is vital for reliability and resiliency and also serves as a backup for the Coliseo de Puerto Rico, which functions as an emergency shelter.
| Pending FAASt Number | 40700-BAYAMON TC-PALO SECO SP- | Transmission | Rebuild |  |  | 52222221.7 | 42822221.794 | 9399999.906 |  | Out of Service line significantly impacts the resiliency of the 115 kV system.
| Pending FAASt Number | 7500-TRES MONJITAS SECT-PUERTO NUEVO TO- | Transmission | Rebuild |  |  | 7444575 | 6104551.5 | 1340023.5 |  | Out of Service line it is is critical for the reliability of the 38 kV system.
| Pending FAASt Number | 1000-CAPUCHINOS SECT-VENEZUELA SECT- | Transmission | Rebuild |  |  | 1856100 | 1522002 | 334098 |  | Critical line for the system.
| Pending FAASt Number | 3500-MONACILLOS TC-LAS LOMAS SECT- | Transmission | Rebuild |  |  | 3813075 | 3126721.5 | 686353.5 |  | Critical line for the system.
| Pending FAASt Number | 3300-EGOZCUE SECT-MARTIN PEÑA TC- 3300-MARTIN PEÑA TC-POPULAR SECT- 3300-POPULAR SECT-CHARDON SECT- | Transmission | Rebuild |  |  | 6850000 | 5617000 | 1233000 |  | Fundamental for the 38kV system in the metropolitan area.
| Pending FAASt Number | 36100-BARRIO PIÑA SECT-CANA SECT- | Transmission | Rebuild |  |  | 7108943.1 | 5829333.342 | 1279609.758 |  | Critical line for the 115kV system.
| Pending FAASt Number | 36100-CANA SECT-BAYAMON TC- | Transmission | Rebuild |  |  | 15592281.866 | 12785671.1301 | 2806610.7359 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-BARCELONETA TC-CAMBALACHE TC- | Transmission | Rebuild |  |  | 23175154.506 | 19003626.6949 | 4171527.8111 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-CAMBALACHE TC-DOS BOCAS HP- | Transmission | Rebuild |  |  | 21516401.116 | 17643448.9151 | 3872952.2009 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-DORADO TC-HATO TEJAS TC- | Transmission | Rebuild |  |  | 11611273.73 | 9521244.4586 | 2090029.2714 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-DORADO TC-VEGA BAJA TC- | Transmission | Rebuild |  |  | 21326829.3 | 17488000.026 | 3838829.274 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-HATO TEJAS TC-BAYAMON TC- | Transmission | Rebuild |  |  | 9123143.645 | 7480977.7889 | 1642165.8561 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-MANATI TC-BARCELONETA TC- | Transmission | Rebuild |  |  | 20805506.806 | 17060515.5809 | 3744991.2251 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-VEGA BAJA TC-MANATI TC- | Transmission | Rebuild |  |  | 10971468.851 | 8996604.4578 | 1974864.3932 |  | Critical line for the 115kV system.
| Pending FAASt Number | Bayamon Pueblo Sect. Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 40000000 | 24000000 | 16000000 | Project scope to be developed and approved by leadership | Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substation 1715 Bayamón Pueblo II and rebuild and conversion of distribution substation 1701 Bayamón Pueblo to 13.2 kV (only 4.8 kV substation on system).
| Pending FAASt Number | Dos Bocas HP Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 70000000 | 42000000 | 28000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 8005 Dos Bocas
| Pending FAASt Number | Falu 1334 Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 10000000 | 6000000 | 4000000 | Project scope to be developed and approved by leadership | Rebuild of Falú 1334 Distribution Substation
| Pending FAASt Number | Pastillo Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 20000000 | 3000000 | 17000000 | Project scope to be developed and approved by leadership | Rebuild of sectionalizing substation including colocated 5801 Pastillo distribution substations and rebuild in site distribution substation 5803 Fort Allen (destroyed in fire in early 2021 with loads being supplied by a mobile substation).
| Pending FAASt Number | Ponce TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 60000000 | 36000000 | 24000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substations 5001 Ponce Pueblo, 5010 Hostos 4 kV and 5011 Hostos 13 kV.
| Pending FAASt Number | Aguilita 5817 Substation Relocation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 12000000 | 1200000 | 10800000 | Project scope to be developed and approved by leadership | Relocation of substation 5817 due to flooding risk as it is located in area identified by FEMA as floodway.
| Pending FAASt Number | San Lorenzo 3301 Substation Relocation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 20000000 | 2000000 | 18000000 | Project scope to be developed and approved by leadership | Relocation of substation 3301due to flooding risk as it is located in area identified by FEMA as floodway and co-location of new 13.2 kV substation to provide support and redundancy to substations 3205 Juncos TC 13 kV and 2603 Humacao TC 13 kV.
| Pending FAASt Number | New Breñas 13.2 kV Substation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 9000000 | 4500000 | 4500000 | Project scope to be developed and approved by leadership | New 13.2 kV substation in Breñas Sectionalizer to provide support and redundancy to substations 9206 Dorado PDS, 9207 Dorado TC and 9004 Vega Baja TC. Additional land adjacent to Breñas substation in process of being acquired from Dorado Beach Properties. Current scope considers re-using elements from the existing Cataño Substation including transformer, PDS and high side breaker.
| Pending FAASt Number | New Saint Just 13.2 kV Substation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 15000000 | 7500000 | 7500000 | Project scope to be developed and approved by leadership | New 13.2 kV substation and 38 kV sectionalizer adjacent to transmission lines 3100 and 3600 to provide support and redundancy to substations 1204 Conquistador, 1206 Encantada, 1620 Parque Escorial and 1336 Berwind TC. Land targeted for project is within/adjacent to ROW of 3100/3600 Tline adjacent to PR-199.
| Pending FAASt Number | New Yeguada (Camuy) Substation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 6000000 | 3000000 | 3000000 | Project scope to be developed and approved by leadership | New 13.2 kV substation to provide support and redundancy to substations 7601 Camuy, 7602 Camuy Provisional, 7402 Quebradillas and 7404 Quebradillas Provisional. Site already acquired by PREPA.
| Pending FAASt Number | Fiber Optic Replacement Group 1 | IT/OT | N/A | LUMA PM Collaboration Development |  | 13696712.24 | 13420380.74 | 276331.5 | Project in formulation phase, DSOW and cost estimate pending review. | 30% of the design not finish, not approved yet. Original ISOW approved by FEMA for island wide fiber project 200 million
| Pending FAASt Number | Transport Network Group 2, 57 sites | IT/OT | N/A | LUMA PM Collaboration Development |  | $70,021,267.04 | $38,511,696.87 | $31,509,570.17 | Project in formulation stage, pending completion of DSOW and LUMA Project Cost Estimate | 30% design for make ready and telecom equipment have been completed by internal Telecom Engineering. 428 PA and 406 HM split are based on percentages from Group 1 Ver 1, submitted to FEMA.
| Pending FAASt Number | Transport Network Group 3, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 4, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 5, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 6, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 7, 68 sites | IT/OT | N/A | Planning Phase | 0 | $83,534,143.14 | $45,943,778.72 | $37,590,364.41 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Infrastructure Group I | IT/OT | N/A | Initiation Phase | 0 | 0 | 0 | 0 | Under formulation. | Project under development by engineering.
| Pending FAASt Number | FAASt [Pole and Conductor Repair - Mayaguez Group 5 - Phase 2 | Distribution | Pole and Conductors |  | TBD | 7610000 | TBD | TBD | Under formulation. | WTBC
| Pending FAASt Number | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20-21 - Phase 3 | Distribution | Pole and Conductors |  | TBD | 7610000 | TBD | TBD | Under formulation. | WTBC
| Pending FAASt Number | Aguadilla Custumer Experince | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| 169576 | Arecibo Bulding Repair | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| 169798 | Arecibo Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Barranquitas Electric Service Center | Buildings | N/A | LUMA Environmental Review | TBD | TBD | TBD | TBD | Under formulation in the Collabroation process (Appian) | WTBC
| Pending FAASt Number | Bayamon Electric Service Center (Minillas) | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Guayama Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Sabana Llana Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Toa Alta Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Vega Baja Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC