## Thors List of Priority Projects (hidden)
Thor Code | Work Completed | Priority Group | Notes | Project # | Title | Asset | SUB ASSET | Process Step | Project costs - Submitted to FEMA * | 428 Allocation * | 406 Allocation * | Project Status | Additional comments | Color Code | Thor Code
1 |  | 6 |  | Pending FAASt Number | Fajardo 2002 Transformer Replacement | Substation | N/A | Collaboration
1 | Yes | 6 |  | Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | N/A | Collaboration
1 |  | 6 |  | 741097 | Region 1 San Juan Substation/Telecom | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
1 |  | 6 |  | 741101 | Region 2 Arecibo Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
1 |  | 6 |  | 741098 | Region 3 Bayamon Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
1 |  | 6 |  | 741100 | Region 4 Caguas Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
1 |  | 6 |  | 741102 | Region 5 Mayaguez Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
1 |  | 6 |  | 741104 | Region 6 Ponce Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
1 |  | 7 |  | 551927 | 551927 SCADA Remote Access and RTU Replacements Group 3 | IT/OT | N/A | Pending PREPA approval to re-submit to CRC | 22512806.48 | 19213188.59 | 3299617.88 | Project was in CRC on "EHP Review" but sent back to phase 2 | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 |  | 7 |  | 668665 | Cybersecurity Program Implementation | IT/OT | N/A | Pending FEMA review | 24587256.15 | 24587256.15 |  | Pending FEMA review
1 |  | 7 |  | FAASt number pending | Fiber Optic Replacement Group 1 | IT/OT | N/A | LUMA PM Collaboration Develpment |  |  |  | Project in formulation phase, DSOW and cost estimate pending review. | 30% of the design not finish, not approved yet. This must be changing because the
1 |  | 7 |  | 675345 | IT OT Technology Systems Reparations Group 1 | IT/OT | N/A | Pending FEMA review | 22834185.5 | 21970036.67 | 864148.83 | Pending FEMA review
1 | Yes | 7 |  | Pending FAASt Number | Santa Isabel TC | Substation | N/A | Collaboration
1 |  | 7 |  | 679035 | Telecom Infrastructure – Group A | IT/OT | N/A | COR3: Pending review to submit to FEMA. | 8199354.01 | 6440145.54 | 20102.34 | Project in COR3 pending review | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 |  | 7 |  | 704805 | Telecom Infrastructure – Group D | IT/OT | N/A | COR3: Pending review to submit to FEMA. | 5981241.79 | 5297451.62 | 21457.23 | Project in COR3 pending review | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 |  | 7 |  | not assigned | TL 36100 Dos Bocas to Ciales | Transmission | Transmission | Pending initial submission | 49044355.45 | 49044355.45 | 0 | Pending COR3 review. Forecasted submission 7/30/25.
1 |  | 7 |  | FAASt number pending | Transport Network Group 2 | IT/OT | N/A | LUMA PM Collaboration Develpment | 3619477 | 1866181.88 | 1753295.12 | Project in formulation phase, DSOW and cost estimate pending review. | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 |  | 8 |  | Pending FAASt Number | 38 kV Reclosers TL 5600 | Transmission | Pole Replacement | Collaboration | 1389759.59 | 1047506.87 | 342252.72 | With QAQC revision
1 |  | 8 |  | 805521 | 38 kv Reclosers TL7800 | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 1010114.15 | 558926.82 | 451187.33 | 7/15/25 Submitted to FEMA
1 |  | 8 |  | 805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 1437246.64 | 700725.29 | 736521.35 | With Reviewers
1 |  | 8 |  | 805517 | 38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect. | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 1154980.07 | 689918.67 | 465061.4 | With Reviewers
1 |  | 8 |  | 745851 | FAASt [Automation Program Group 11] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1532152 | TBD | TBD | Under formulation | WTBC
1 | Yes | 8 |  | 688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | Pending QA/QC Revisions | TBD | TBD | TBD
1 | Yes | 8 |  | 752500 | FAASt [Automation Program Group 1B] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1250000 | TBD | TBD | Under formulation | WC
1 | Yes | 8 |  | 752502 | FAASt [Automation Program Group 1C] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1250000 | TBD | TBD | Under formulation | WC
1 |  | 8 |  | 800369 | FAASt [Automation Program Group 38] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1335000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 |  | 8 |  | 800394 | FAASt [Automation Program Group 39] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 3084000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 |  | 8 |  | 800399 | FAASt [Automation Program Group 40] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2577000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 |  | 8 |  | 801432 | FAASt [Automation Program Group 41] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2391000 | TBD | TBD | Under formulation. | WTBC
1 |  | 8 |  | 801437 | FAASt [Automation Program Group 42] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2883000 | TBD | TBD | Under formulation. | WTBC
1 |  | 8 |  | 801438 | FAASt [Automation Program Group 43] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2490000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 |  | 8 |  | 801440 | FAASt [Automation Program Group 44] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 3902000 | TBD | TBD | Under formulation. | WTBC
1 |  | 8 |  | 801441 | FAASt [Automation Program Group 45] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2400000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 |  | 8 |  | Pending FAASt Number | T Pole 9900 Rio Blanco HP to Humacao Sect | Transmission | Pole Replacement | Collaboration | 624448.65 | 583771.63 | 40677.02 | With QAQC revision
1 |  | 8 |  | Pending FAASt Number | T Pole Arecibo Group 1 | Transmission | Pole Replacement | Collaboration | 11866225 | 11218418.12 | 647806.88 | With QAQC revision
1 |  | 8 |  | Pending FAASt Number | T Pole line 4800 Santa Isabel TC to Santa Isabel Sect | Transmission | Pole Replacement | Collaboration | 184562.3 | 173722.67 | 10839.63 | With QAQC revision
1 |  | 8 |  | Pending FAASt Number | TPole Line 1600 Leon SECT – Acacias TC | Transmission | Pole Replacement | Collaboration | 541768.76 | 493105.46 | 48663.3 | With QAQC revision
1 |  | 8 |  | Pending FAASt Number | TPole Line 2000 Once de Agosto – San Sebastian TC | Transmission | Pole Replacement | Collaboration | 4995539.34 | 4853521.52 | 142017.82 | With QAQC revision
1 |  | 8 |  | 753787 | T-Pole TL 13700 Mora TC to Isabela TO | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 494608.13 | 473553.01 | 21055.12 | 7/16/25 Pending COR3 review
1 |  | 8 |  | 753785 | T-Pole TL 3300 San Gerardo Sect to Venezuela Sect | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 277452.41 | 249329.88 | 28122.53 | With Reviewers
1 |  | 8 |  | 753786 | T-Pole TL 5900 San Juan SP to Crematorio TO | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 501203.01 | 474530.5 | 26672.51 | With Reviewers
1 |  | 8 |  | 811923 | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | Transmission | Pole Replacement | Collaboration | 247198.31 | 231001.34 | 16196.97 | With QAQC revision
1 |  | 8 |  | 753781 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect | Transmission | Poles | Pending Scope & Cost Completion by Applicant | 730217.42 | 691296 | 38921.42 | 7/9/25 Submitted to FEMA
1 |  | 8 |  | 811913 | Transmission Priority Pole Replacement Program Line 9600 Bayamon TC–Catano Sect | Transmission | Pole Replacement | Collaboration | 431750.19 | 396643.71 | 35106.48 | With QAQC revision
1 |  | 9 |  | 818006 | FAASt [Feeder Rebuild #2402-02] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 34516477 | TBD | TBD | Under COR3 review. Awaiting recomendations. | WTBC
1 |  | 9 |  | 754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | Distribution | Underground | Pending Scope & Cost Completion by Applicant | 7066632.8 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | Pending Scope & Cost Completion by Applicant | 15123199.33 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 764709 | FAASt [Feeder Rebuild # 1204-05] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 8740820.93 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 |  | 9 |  | 767005 | FAASt [Feeder Rebuild # 1303-05] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 12631766 | TBD | TBD | Under COR3 review. Awaiting recomendations. Since is not in the PREPA priority listCOR3 will not perform their review. Project withdrawn by FEMA | WTBC
1 |  | 9 |  | 760577 | FAASt [Feeder Rebuild # 1718-02] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 8421396 | TBD | TBD | Under formulation. Awaiting cost estimate.Project withdrawn by FEMA. | WTBC
1 |  | 9 |  | FAASt number pending | FAASt [Feeder Rebuild # 2906-02] (Distribution) | Distribution | Feeders Rebuild | N/A | 3205041 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | FAASt number pending | FAASt # [Distribution Feeder Rebuild #6406 02] (Distribution) | Distribution | Feeders Rebuild | N/A | 13546527 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 767387 | FAASt # [Distribution Feeder Rebuild # 1303-01] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 4798378.99 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 |  | 9 |  | 817993 | FAASt # [Distribution Feeder Rebuild # 1801-03] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 6131846 | TBD | TBD | In the internal QA/QC process. | WTBC
1 |  | 9 |  | FAASt number pending | FAASt # [Distribution Feeder Rebuild # 1909-09] (Distribution) | Distribution | Feeders Rebuild | N/A | 10169668 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 818055 | FAASt # [Distribution Feeder Rebuild # 3006-05] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 8829008 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | FAASt number pending | FAASt # [Distribution Feeder Rebuild # 3007-03] (Distribution) | Distribution | Feeders Rebuild |  | 17207307 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 818041 | FAASt # [Distribution Feeder Rebuild # 3701-03] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 24349603.89 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 818056 | FAASt # [Distribution Feeder Rebuild # 6305-03] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 22352214 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 817962 | FAASt # [Distribution Feeder Rebuild # 9403-03] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 5548949 | TBD | TBD | Under formulation. | WTBC
1 |  | 9 |  | 760568 | FAASt [Distribution Feeder Rebuild # 1710-01] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 10467848 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 |  | 9 |  | 760575 | FAASt [Distribution Feeder Rebuild # 1716-03] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 18102407 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 |  | 9 |  | 760579 | FAASt [Distribution Feeder Rebuild # 1717-03] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 14143466 | TBD | TBD | In the internal QA/QC process. Project withdrawn by FEMA | WTBC
1 |  | 9 |  | 956782 | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 21957625.63 | TBD | TBD | In the internal QA/QC process. | WTBC
1 |  | 9 |  | 764705 | FAASt [Distribution Feeder Rebuild #6014-02] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 13387462.29 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 |  | 9 |  | 958367 | FAASt [Distribution Feeder Rebuild #6603-01] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 14474191.76 | TBD | TBD | In the internal QA/QC process. | WTBC
1 |  | 9 |  | 760571 | FAASt [Feeder Rebuild # 1720-07] (Distribution) | Distribution | Feeders Rebuild | Pending Scope & Cost Completion by Applicant | 18005134 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 |  | 11 |  | 759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 9280000 | TBD | TBD | Under formulation. | WTBC
1 |  | 11 |  | 759051 | FAASt [Pole and Conductor Repair - Bayamon Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 3999999 | TBD | TBD | Under formulation. | WTBC
1 |  | 11 |  | 806935 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 9151689.8 | TBD | TBD | Ready for COR3 review | WTBC
1 |  | 11 |  | 738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 5100000 | TBD | TBD | Under formulation. | WTBC
1 |  | 11 |  | 806936 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 2533802.04 | TBD | TBD | Ready for COR3 review | WTBC
1 |  | 11 |  | FAASt number pending | FAASt [Pole and Conductor Repair - Mayaguez Group 5 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 7610000 | TBD | TBD | Under formulation. | WTBC
1 |  | 11 |  | 738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending PDMG Scope & Cost Routing | 9004523.02 | TBD | TBD | Under formulation for FEMA RFI response | WTBC
1 |  | 11 |  | 738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending PDMG Scope & Cost Routing | 16694702.83 | TBD | TBD | Under formulation for FEMA RFI response | WTBC
1 |  | 11 |  | FAASt number pending | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20-21 - Phase 3 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 7610000 | TBD | TBD | Under formulation. | WTBC
1 |  | 11 |  | 817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 6856735.82 | TBD | TBD | Ready for COR3 review | WTBC
1 |  | 11 |  | 817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 2540210.59 | TBD | TBD | Ready for COR3 review | WTBC
1 |  | 11 |  | 817247 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 11650000 | TBD | TBD | Under formulation. | WTBC
1 |  | 11 |  | 817250 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 7610000 | TBD | TBD | Under formulation. | WTBC
1 |  | 99 |  | 550986 | FAASt Condado - 1133 | Substation | N/A | Pending Scope & Cost Completion by Applicant | 14709154 | 13238238.6 | 1470915.4 | 12/10/2024 - The project SOW is currently being evaluated by LUMA Engineering with a possible change in scope of work. Forecast TBD | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 |  | 99 |  | 551912 | FAASt Puerto Nuevo - 1520 | Substation | N/A | Pending Scope & Cost Completion by Applicant | 16844776 | 15160298.4 | 1684477.6 | 12/10/2024 - The project SOW is currently being evaluated by LUMA Engineering with a possible change in scope of work. Forecast TBD | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 |  | 99 |  | 550894 | FAASt [Baldrich - 1422] (Substation) | Substation | N/A | Pending Scope & Cost Completion by Applicant | 26709229 | 24038306.1 | 2670922.9 | 2/25/2025 - HM RFI Subs Matrix response received on 1/27/2025, HM forecast: pending | Project scope being evaluated, priority under evaluation, submission TBD
1 |  | 99 |  | 550099 | FAASt [Esc. Industrial M. Such - 1423] (Substation) | Substation | N/A | Pending Scope & Cost Completion by Applicant | 14335434 | 12901890.6 | 1433543.4 | 2/25/2025 - HM RFI Subs Matrix response received on 1/27/2025, HM forecast: pending | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 |  | 99 |  | 550980 | FAASt [Parques y Recreos - 1002] (Substation) | Substation | N/A | Pending Scope & Cost Completion by Applicant | 20916860 | $18,825,174.00 | 2091686 | 2/25/2025 - HM RFI Subs Matrix response received on 1/27/2025, HM forecast: pending | Project scope being evaluated, priority under evaluation, submission TBD
1 |  |  |  | 551260 | Guaynabo Pueblo Substation | Substation | N/A | Process Discontinued | 20970646.43 | 16713135.72 | 4257510.71 | Withdrawn | On 8/15, FEMA withdrew the project. As per PM, engineering is 90% complete, and the project should be on the priority list.
1 |  |  |  | 750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 52720520.35 | 0 | 52720520.35 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 |  |  |  | 738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 55941767.5 | 0 | 55941767.5 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 |  |  |  | 750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 55503065.56 | 0 | 55503065.56 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 |  |  |  | 752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 57640005.67 | 0 | 57640005.67 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 |  |  |  | 177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | Transmission | T-Line Rebuild | Process Discontinued | 35000000 |  |  |  | 9/2/2025 - Requested to be added to Tier 2 list (Withdrawn in GP on 8/15/2025). DSOW can be submitted in Jan
1 |  | 2 |  | N/A | Substation Component Group 2 | Substation | N/A | Currently working to prepare functional specifications and have been discussing with FEMA | 130000000 |  |  |  | Total of 10 substations with 8 transformers, 2 metal clad, 8 PAC Upgrade, 1 cap bank, 1 RTU, 9 Distribution and 8 transmission breakers replacements plus minor repair, grounding and security for all 10 stations. High Level budgetary estimates are around $130M
1 |  | 2 |  | N/A | Substation Component Group 3 | Substation | N/A | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 80000000 |  |  |  | Total of 7 substations with 2 transformers, 2 metal clad, 6 PAC Upgrade, 1 cap bank, 2 Distribution and 13 transmission breakers replacements plus minor repair, grounding and security for all 7 stations. High Level budgetary estimates are around $80M
Notes:
93 |  |  |  | Project costs - Submitted to FEMA = Cost presented herein are based on scope of works presented by LUMA and available in Grants Portal
Current PW Version Gross Cost & 428 allocation = Amount is the estimated amount allocated to 428 as per scope of work presented
406 Allocation = Amount is the estimated amount allocated to 428 as per SOW available on Grants Portal
A&E-PW 9510 & E&M-PW 10710 = Amount as per cost allocation on SOW available on Grants Portal
A&E Costs Incurred-Luma Provided & E&M Cost - Luma Provided = Amounts provided on LUMA P3A Prority Project list
Vegetation Projects- Cost presented are LUMA estimates. Amounts are subject to change due to FEMA Validation Analysis and HMP Approach- Distribution and Transmission

## List for Dorel Ask 11.26 (hidden)
Prioritization Code | Withdrawin/Additional Project | Work Completed | Project # | Title | Asset | SUB ASSET | Process Step | Project costs - Submitted to FEMA * | 428 Allocation * | 406 Allocation * | Project Status | Additional comments
1 | Additional Project |  | Pending FAASt Number | Fajardo 2002 Transformer Replacement | Substation | Component Replacement | Collaboration
1 | Additional Project | Yes | Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | Component Replacement | Collaboration | 3763775.37
1 | Additional Project |  | FAASt number pending | Fiber Optic Replacement Group 1 | IT/OT | N/A | LUMA PM Collaboration Develpment |  |  |  | Project in formulation phase, DSOW and cost estimate pending review. | 30% of the design not finish, not approved yet. This must be changing because the
1 | Additional Project | Yes | Pending FAASt Number | Venezuela TC | Substation | Component Replacement | Collaboration | 2613825.35 |  |  |  | Project is work Completed, costs are per Work Completed Summary given to PREB. Transformer purchased with E&M PW.
1 | Additional Project | Yes | Pending FAASt Number | Santa Isabel TC | Substation | Component Replacement | Collaboration | 18236804.57
1 | Additional Project |  | not assigned | TL 36100 Dos Bocas to Ciales | Transmission | Line Rebuild | Pending initial submission | 49044355.45 | 49044355.45 | 0 | Pending COR3 review. Forecasted submission 7/30/25.
1 | Additional Project |  | FAASt number pending | Transport Network Group 2 | IT/OT | N/A | LUMA PM Collaboration Develpment | 3619477 | 1866181.88 | 1753295.12 | Project in formulation phase, DSOW and cost estimate pending review. | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 | Additional Project |  | Pending FAASt Number | 38 kV Reclosers TL 5600 | Transmission | Automation | Collaboration | 1389759.59 | 1047506.87 | 342252.72 | With QAQC revision
1 | Additional Project |  | Pending FAASt Number | 38kV Recloser TL 1500-Yauco HP to San German TC | Transmission | Automation | Collaboration
1 | Additional Project |  | 805513 | 38kV Recloser TL 3000 Monacillos TC to Bairoa TO | Transmission | Automation | Collaboration | 1149274.52 | 1149274.52 | 0 | With QAQC revision
1 | Additional Project |  | 729124 | Automation Program Group 07 | Distribution | Automation | Pending QA/QC Revisions | TBD | TBD | TBD
1 | Additional Project |  | Pending FAASt Number | T Pole 9900 Rio Blanco HP to Humacao Sect | Transmission | Pole Replacement | Collaboration | 624448.65 | 583771.63 | 40677.02 | With QAQC revision
1 | Additional Project |  | Pending FAASt Number | T Pole Arecibo Group 1 | Transmission | Pole Replacement | Collaboration | 11866225 | 11218418.12 | 647806.88 | With QAQC revision
1 | Additional Project |  | Pending FAASt Number | T Pole line 4800 Santa Isabel TC to Santa Isabel Sect | Transmission | Pole Replacement | Collaboration | 184562.3 | 173722.67 | 10839.63 | With QAQC revision
1 | Additional Project |  | Pending FAASt Number | TPole Line 1600 Leon SECT – Acacias TC | Transmission | Pole Replacement | Collaboration | 541768.76 | 493105.46 | 48663.3 | With QAQC revision
1 | Additional Project |  | Pending FAASt Number | TPole Line 2000 Once de Agosto – San Sebastian TC | Transmission | Pole Replacement | Collaboration | 4995539.34 | 4853521.52 | 142017.82 | With QAQC revision
1 | Additional Project |  | FAASt number pending | FAASt [Feeder Rebuild # 2906-02] (Distribution) | Distribution | Line Rebuild | N/A | 3205041 | TBD | TBD | Under formulation. | WTBC
1 | Additional Project |  | FAASt number pending | FAASt # [Distribution Feeder Rebuild #6406 02] (Distribution) | Distribution | Line Rebuild | N/A | 13546527 | TBD | TBD | Under formulation. | WTBC
1 | Additional Project |  | FAASt number pending | FAASt # [Distribution Feeder Rebuild # 1909-09] (Distribution) | Distribution | Line Rebuild | N/A | 10169668 | TBD | TBD | Under formulation. | WTBC
1 | Additional Project |  | FAASt number pending | FAASt # [Distribution Feeder Rebuild # 3007-03] (Distribution) | Distribution | Line Rebuild |  | 17207307 | TBD | TBD | Under formulation. | WTBC
1 | Additional Project |  | FAASt number pending | FAASt [Pole and Conductor Repair - Mayaguez Group 5 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 7610000 | TBD | TBD | Under formulation. | WTBC
1 | Additional Project |  | FAASt number pending | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20-21 - Phase 3 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 7610000 | TBD | TBD | Under formulation. | WTBC
1 | Additional Project |  | Pending | 38kV Reclosers TL 100 | Transmission | Automation |  |  | 1213187.43 |  | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 12600 | Transmission | Automation |  |  | 1448491.28 | 487375.29 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 13400 | Transmission | Automation |  |  | 579867.07 | 741618.89 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 1600 | Transmission | Automation |  |  | 1063054.49 | 390065.24 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 2000 | Transmission | Automation |  |  | 1309036.7 | 392216.57 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 3100 | Transmission | Automation |  |  | 1398985.55 | 448913.54 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 3200 | Transmission | Automation |  |  | 537627.06 | 184024.08 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 3600 | Transmission | Automation |  |  | 753575.65 |  | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 3700 | Transmission | Automation |  |  | 286655.46 | 1053969.47 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 4800 | Transmission | Automation |  |  | 2013222.35 | 684007.09 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 6500 | Transmission | Automation |  |  | 461620.3 | 519784.86 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 800 | Transmission | Automation |  |  | 614126.79 | 224227.79 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL 8100 | Transmission | Automation |  |  | 730612.8 | 770150.96 | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL5200 | Transmission | Automation |  |  | TBD | TBD | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL6000 | Transmission | Automation |  |  | TBD | TBD | DSOW under development
1 | Additional Project |  | Pending | 38kV Reclosers TL9400 | Transmission | Automation |  |  | TBD | TBD | DSOW under development
1 | Additional Project |  | Pending | 38kV ReclosersTL 2200 | Transmission | Automation |  |  | 1,121.878.44 |  | DSOW under development
1 | Additional Project |  | Not Assigned | Line 700 Costa Sur to Yauco | Transmission | Line Rebuild | DSOW Never Submitted | 25000000 |  |  |  | At 20% Design, DSOW submittal in Q4 FY26
1 | Additional Project |  | Not Assigned | Line 36100 Dos Bocas to Barrio Pina | Transmission | Line Rebuild | DSOW Never Submitted | 150000000 |  |  |  | DSOW can be submitted Q3 FY26
1 | Additional Project |  | N/A | Substation Component Group 2 | Substation | Component Replacement | Currently working to prepare functional specifications and have been discussing with FEMA | 130000000 |  |  |  | Total of 10 substations with 8 transformers, 2 metal clad, 8 PAC Upgrade, 1 cap bank, 1 RTU, 9 Distribution and 8 transmission breakers replacements plus minor repair, grounding and security for all 10 stations. High Level budgetary estimates are around $130M
1 | Additional Project |  | N/A | Substation Component Group 3 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 80000000 |  |  |  | Total of 7 substations with 2 transformers, 2 metal clad, 6 PAC Upgrade, 1 cap bank, 2 Distribution and 13 transmission breakers replacements plus minor repair, grounding and security for all 7 stations. High Level budgetary estimates are around $80M
1 | Additional Project |  | N/A | Substation Component Group 4 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 100000000 |  |  |  | To be Scoped, Transformer & Breakers Purchased Incoming
1 | Additional Project |  | N/A | Substation Component Group 5 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 100000000 |  |  |  | To be Scoped, Transformer & Breakers Purchased Incoming
1 | Additional Project | Yes | N/A | Substation Component Group 0 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 9347853.87 |  |  |  | Work Completed, Priority to get FEMA obligated, this is equipment purchased under E&M PW but installed with NFC dollars, we would just request the DSOW for the Equipment Cost not the Construction Cost as they may be uneligible. *16 Breakers ($1,036,579), 3 Transformers - Sabana Llana 1646 ($968,203), Mora TC 112 MVA ($2,926,189.87), Caguas 112 MVA ($4,416,882)
1 | Withdrawn by FEMA |  | 551927 | 551927 SCADA Remote Access and RTU Replacements Group 3 | IT/OT | N/A | Pending PREPA approval to re-submit to CRC | 22512806.48 | 19213188.59 | 3299617.88 | Project was in CRC on "EHP Review" but sent back to phase 2 | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 | Withdrawn by FEMA |  | 547247 | Cambalache TC | Substation | Rebuild | Collaboration
1 | Withdrawn by FEMA |  | 668665 | Cybersecurity Program Implementation | IT/OT | N/A | Pending FEMA review | 24587256.15 | 24587256.15 |  | Pending FEMA review
1 | Withdrawn by FEMA |  | 675345 | IT OT Technology Systems Reparations Group 1 | IT/OT | N/A | Pending FEMA review | 22834185.5 | 21970036.67 | 864148.83 | Pending FEMA review
1 | Withdrawn by FEMA |  | 679035 | Telecom Infrastructure – Group A | IT/OT | N/A | COR3: Pending review to submit to FEMA. | 8199354.01 | 6440145.54 | 20102.34 | Project in COR3 pending review | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 | Withdrawn by FEMA |  | 704805 | Telecom Infrastructure – Group D | IT/OT | N/A | COR3: Pending review to submit to FEMA. | 5981241.79 | 5297451.62 | 21457.23 | Project in COR3 pending review | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
1 | Withdrawn by FEMA |  | 805521 | 38 kv Reclosers TL7800 | Transmission | Automation | Pending Scope & Cost Completion by Applicant | 1010114.15 | 558926.82 | 451187.33 | 7/15/25 Submitted to FEMA
1 | Withdrawn by FEMA |  | 805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Transmission | Automation | Pending Scope & Cost Completion by Applicant | 1437246.64 | 700725.29 | 736521.35 | With Reviewers
1 | Withdrawn by FEMA |  | 805517 | 38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect. | Transmission | Automation | Pending Scope & Cost Completion by Applicant | 1154980.07 | 689918.67 | 465061.4 | With Reviewers
1 | Withdrawn by FEMA |  | 745854 | Automation Program Group 9 | Distribution | Automation | Pending QA/QC Revisions | TBD | TBD | TBD
1 | Withdrawn by FEMA |  | 745851 | FAASt [Automation Program Group 11] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1532152 | TBD | TBD | Under formulation | WTBC
1 | Withdrawn by FEMA | Yes | 688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | Pending QA/QC Revisions | TBD | TBD | TBD
1 | Withdrawn by FEMA | Yes | 752500 | FAASt [Automation Program Group 1B] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1250000 | TBD | TBD | Under formulation | WC
1 | Withdrawn by FEMA | Yes | 752502 | FAASt [Automation Program Group 1C] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1250000 | TBD | TBD | Under formulation | WC
1 | Withdrawn by FEMA |  | 800369 | FAASt [Automation Program Group 38] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 1335000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 | Withdrawn by FEMA |  | 800394 | FAASt [Automation Program Group 39] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 3084000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 | Withdrawn by FEMA |  | 800399 | FAASt [Automation Program Group 40] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2577000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 | Withdrawn by FEMA |  | 801432 | FAASt [Automation Program Group 41] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2391000 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 801437 | FAASt [Automation Program Group 42] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2883000 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 801438 | FAASt [Automation Program Group 43] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2490000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 | Withdrawn by FEMA |  | 801440 | FAASt [Automation Program Group 44] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 3902000 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 801441 | FAASt [Automation Program Group 45] (Distribution) | Distribution | Automation | Pending Scope & Cost Completion by Applicant | 2400000 | TBD | TBD | Under formulation. Awaiting Cost estimate to be sent to COR3 for their review | WTBC
1 | Withdrawn by FEMA |  | 753787 | T-Pole TL 13700 Mora TC to Isabela TO | Transmission | Pole Replacement | Pending Scope & Cost Completion by Applicant | 494608.13 | 473553.01 | 21055.12 | 7/16/25 Pending COR3 review
1 | Withdrawn by FEMA |  | 753785 | T-Pole TL 3300 San Gerardo Sect to Venezuela Sect | Transmission | Pole Replacement | Pending Scope & Cost Completion by Applicant | 277452.41 | 249329.88 | 28122.53 | With Reviewers
1 | Withdrawn by FEMA |  | 753786 | T-Pole TL 5900 San Juan SP to Crematorio TO | Transmission | Pole Replacement | Pending Scope & Cost Completion by Applicant | 501203.01 | 474530.5 | 26672.51 | With Reviewers
1 | Withdrawn by FEMA |  | 811923 | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | Transmission | Pole Replacement | Collaboration | 247198.31 | 231001.34 | 16196.97 | With QAQC revision
1 | Withdrawn by FEMA |  | 753788 | Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastián TC | Transmission | Pole Replacement | Collaboration
1 | Withdrawn by FEMA |  | 753781 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect | Transmission | Pole Replacement | Pending Scope & Cost Completion by Applicant | 730217.42 | 691296 | 38921.42 | 7/9/25 Submitted to FEMA
1 | Withdrawn by FEMA |  | 811913 | Transmission Priority Pole Replacement Program Line 9600 Bayamon TC–Catano Sect | Transmission | Pole Replacement | Collaboration | 431750.19 | 396643.71 | 35106.48 | With QAQC revision
1 | Withdrawn by FEMA |  | 818006 | FAASt [Feeder Rebuild #2402-02] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 34516477 | TBD | TBD | Under COR3 review. Awaiting recomendations. | WTBC
1 | Withdrawn by FEMA |  | 754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | Distribution | Underground | Pending Scope & Cost Completion by Applicant | 7066632.8 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | Pending Scope & Cost Completion by Applicant | 15123199.33 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 764709 | FAASt [Feeder Rebuild # 1204-05] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 8740820.93 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 | Withdrawn by FEMA |  | 767005 | FAASt [Feeder Rebuild # 1303-05] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 12631766 | TBD | TBD | Under COR3 review. Awaiting recomendations. Since is not in the PREPA priority listCOR3 will not perform their review. Project withdrawn by FEMA | WTBC
1 | Withdrawn by FEMA |  | 760577 | FAASt [Feeder Rebuild # 1718-02] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 8421396 | TBD | TBD | Under formulation. Awaiting cost estimate.Project withdrawn by FEMA. | WTBC
1 | Withdrawn by FEMA |  | 767387 | FAASt # [Distribution Feeder Rebuild # 1303-01] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 4798378.99 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 | Withdrawn by FEMA |  | 817993 | FAASt # [Distribution Feeder Rebuild # 1801-03] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 6131846 | TBD | TBD | In the internal QA/QC process. | WTBC
1 | Withdrawn by FEMA |  | 818055 | FAASt # [Distribution Feeder Rebuild # 3006-05] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 8829008 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 818041 | FAASt # [Distribution Feeder Rebuild # 3701-03] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 24349603.89 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 818056 | FAASt # [Distribution Feeder Rebuild # 6305-03] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 22352214 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 817962 | FAASt # [Distribution Feeder Rebuild # 9403-03] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 5548949 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 760568 | FAASt [Distribution Feeder Rebuild # 1710-01] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 10467848 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 | Withdrawn by FEMA |  | 760575 | FAASt [Distribution Feeder Rebuild # 1716-03] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 18102407 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 | Withdrawn by FEMA |  | 760579 | FAASt [Distribution Feeder Rebuild # 1717-03] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 14143466 | TBD | TBD | In the internal QA/QC process. Project withdrawn by FEMA | WTBC
1 | Withdrawn by FEMA |  | 956782 | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 21957625.63 | TBD | TBD | In the internal QA/QC process. | WTBC
1 | Withdrawn by FEMA |  | 764705 | FAASt [Distribution Feeder Rebuild #6014-02] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 13387462.29 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 | Withdrawn by FEMA |  | 958367 | FAASt [Distribution Feeder Rebuild #6603-01] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 14474191.76 | TBD | TBD | In the internal QA/QC process. | WTBC
1 | Withdrawn by FEMA |  | 760571 | FAASt [Feeder Rebuild # 1720-07] (Distribution) | Distribution | Line Rebuild | Pending Scope & Cost Completion by Applicant | 18005134 | TBD | TBD | Under formulation. Project withdrawn by FEMA. | WTBC
1 | Withdrawn by FEMA |  | 759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 9280000 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 759051 | FAASt [Pole and Conductor Repair - Bayamon Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 3999999 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 806935 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 9151689.8 | TBD | TBD | Ready for COR3 review | WTBC
1 | Withdrawn by FEMA |  | 738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 5100000 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 806936 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 2533802.04 | TBD | TBD | Ready for COR3 review | WTBC
1 | Withdrawn by FEMA |  | 738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending PDMG Scope & Cost Routing | 9004523.02 | TBD | TBD | Under formulation for FEMA RFI response | WTBC
1 | Withdrawn by FEMA |  | 738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Pending PDMG Scope & Cost Routing | 16694702.83 | TBD | TBD | Under formulation for FEMA RFI response | WTBC
1 | Withdrawn by FEMA |  | 817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 6856735.82 | TBD | TBD | Ready for COR3 review | WTBC
1 | Withdrawn by FEMA |  | 817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 2540210.59 | TBD | TBD | Ready for COR3 review | WTBC
1 | Withdrawn by FEMA |  | 817247 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 11650000 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 817250 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2 | Distribution | Pole and Conductors | Pending Scope & Cost Completion by Applicant | 7610000 | TBD | TBD | Under formulation. | WTBC
1 | Withdrawn by FEMA |  | 550099 | FAASt [Esc. Industrial M. Such - 1423] (Substation) | Substation | Rebuild | Pending Scope & Cost Completion by Applicant | 14335434 | 12901890.6 | 1433543.4 | 2/25/2025 - HM RFI Subs Matrix response received on 1/27/2025, HM forecast: pending | 30% of the design not finished
1 | Withdrawn by FEMA |  | 551260 | Guaynabo Pueblo Substation | Substation | Rebuild | Process Discontinued | 20970646.43 | 16713135.72 | 4257510.71 | Withdrawn | On 8/15, FEMA withdrew the project. As per PM, engineering is 90% complete, and the project should be on the priority list.
1 | Withdrawn by FEMA |  | 750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 52720520.35 | 0 | 52720520.35 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 | Withdrawn by FEMA |  | 738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 55941767.5 | 0 | 55941767.5 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 | Withdrawn by FEMA |  | 750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 55503065.56 | 0 | 55503065.56 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 | Withdrawn by FEMA |  | 752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | Pending Scope & Cost Completion by Applicant | 57640005.67 | 0 | 57640005.67 | HM RFI received, pending response from FEMA | FEMA hasn't responded to the clarification provided regarding the use of outdated data from SANDIA project
1 | Withdrawn by FEMA |  | 177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | Transmission | Line Rebuild | Process Discontinued | 35000000 |  |  |  | 9/2/2025 - Requested to be added to Tier 2 list (Withdrawn in GP on 8/15/2025). DSOW can be submitted in Jan
1 | Withdrawn by FEMA |  | 551911 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) | Transmission | Line Rebuild | Process Discontinued |  |  |  |  | 9/2/2025 - Requested to be added to Tier 2 list (Withdrawn in GP on 8/18/2025)
1 | Withdrawn by FEMA |  | 167443 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | Transmission | Line Rebuild | Process Discontinued | 110000000 |  |  |  | 30% Design, DSOW submittal Q1 FY27
1 | Withdrawn by FEMA |  | 753777 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | Transmission | Line Rebuild | Process Discontinued | 120000000 |  |  |  | 45% Design, DSOW submittal Q3 FY26
1 | Withdrawn by FEMA |  | 730657 | FAASt [Line 2200 Manati TC to Vega Baja] (Transmission) | Transmission | Line Rebuild | Process Discontinued | 70000000 |  |  |  | DSOW can be submitted in Q4 FY26
1 | Withdrawn by FEMA |  | 715610 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) | Transmission | N/A | Inactive
1 | Withdrawn by FEMA | Yes | 705657 | FAASt [Automation Program Group 3] (TL/Distribution) | Distribution | Automation | Inactive
1 | Withdrawn by FEMA |  | 705503 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 685869 | FAASt [Mayagüez TC] (Substation) | Substation | Rebuild | Inactive
1 | Withdrawn by FEMA |  | 547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | Substation | Rebuild | Inactive
1 | Withdrawn by FEMA |  | 546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334518 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334497 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334491 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334477 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334475 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334474 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334473 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334471 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334452 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334443 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334420 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334308 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334285 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 730821 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 730513 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA | Yes | 740662 | FAASt [Automation Program Group 2] (TL/ Distribution) | Distribution | Automation | Inactive
1 | Withdrawn by FEMA |  | 745871 | FAASt [Automation Program Group 10] (Distribution) | Distribution | Automation | Inactive
1 | Withdrawn by FEMA |  | 745852 | FAASt [Automation Program Group 13] (Distribution) | Distribution | Automation | Inactive
1 | Withdrawn by FEMA | Yes | 741678 | FAASt [Automation Program Group 4] (TL/Distribution) | Distribution | Automation | Inactive
1 | Withdrawn by FEMA | Yes | 752503 | FAASt [Automation Program Group 1D-7 Feeders] (Distribution) | Distribution | Automation | Inactive
1 | Withdrawn by FEMA |  | 757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 790427 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 812041 | FAASt [Distribution Feeder Rebuild 9501-02] | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 817961 | FAASt [Feeder Rebuild # 2404-06] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 801197 | FAASt [Feeder Rebuild # 1204-02] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 767381 | FAASt [Feeder Rebuild # 1204-04] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 767139 | FAASt [Feeder Rebuild # 2906-02] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 764708 | FAASt [Feeder Rebuild # 5602-02] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 764707 | FAASt [Feeder Rebuild # 6012-02] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 764706 | FAASt [Feeder Rebuild # 7011-03] (Distribution) | Distribution | Line Rebuild | Inactive
1 | Withdrawn by FEMA |  | 712982 | FAASt [Distribution Pole and Conductor Repair “ Mayaguez Group 23] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 712981 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 711962 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 710498 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 710363 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 710045 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 710026 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) | Distribution | Pole and Conductors | Inactive
1 | Withdrawn by FEMA |  | 682331 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) | Telecommunication | N/A | Inactive
1 | Withdrawn by FEMA |  | 673920 | FAASt [Isla Grande 1101] (Substation) | Substation | Rebuild | Inactive
1 | Withdrawn by FEMA |  | 551916 | FAASt [Dorado TC Relocation] (Substation) | Substation | Rebuild | Inactive
2 | Additional Project |  | FAASt number pending | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | Vegetation | N/A | N/A | 157132231.6 | None | 157132231.6 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | WtbC
2 | Additional Project |  | FAASt number pending | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Vegetation | N/A | N/A | 191751441.55 | None | 191751441.55 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | WtbC
2 | Additional Project |  | FAASt number pending | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Vegetation | N/A | N/A | 34263869.06 | None | 34263869.06 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | WtbC
2 | Additional Project |  | FAASt number pending | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | Vegetation | N/A | N/A | 184318454.56 | None | 184318454.56 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | WtbC
2 | Additional Project |  | FAASt number pending | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Vegetation | N/A | N/A | 235239586.56 | None | 235239586.56 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | WtbC
2 | Additional Project |  | FAASt number pending | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | Vegetation | N/A | N/A | 168560150.82 | None | 168560150.82 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | WtbC
2 | Additional Project |  | 728832 | Mayaguez Group A High Density (vegetation) | Vegetation | N/A | Approval
2 | Additional Project |  | 727531 | Ponce Group A High Density DSOW (Vegetation) | Vegetation | N/A | Approval
2 | Additional Project |  | 460406 | San Juan Group B High Density (vegetation) | Vegetation | N/A | Approval
2 | Additional Project |  | Pending FAASt Number | Vegetation clearing Distribution Line 2401-01 - San Juan_Region 1 | Vegetation | N/A | Approval
2 | Additional Project |  | Pending FAASt Number | Vegetation clearing Distribution Line 3007-03 - Caguas_Region 4 | Vegetation | N/A | Approval
2 | Additional Project |  | Pending FAASt Number | Vegetation clearing Distribution Line 5602-02 - Ponce_Region 6 | Vegetation | N/A | Approval
2 | Additional Project |  | Pending FAASt Number | Vegetation clearing Distribution Line 5803-02 - Ponce_Region 5 | Vegetation | N/A | Approval
2 | Additional Project |  | Pending FAASt Number | Vegetation clearing Distribution Line 6012-02- Mayaguez_Region 5 | Vegetation | N/A | Approval
2 | Additional Project |  | Pending FAASt Number | Vegetation clearing for San Juan Region 1 Feeder 2301-02 | Vegetation | N/A | Approval
2 | Withdrawn by FEMA |  | 727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | 68402550.1 | None | 68402550.1 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Process Discontinued (Withdrawn project) | 47503082.49 | None | 47503082.49 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Process Discontinued (Withdrawn project) | 47503082.49 | None | 47503082.49 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Process Discontinued (Withdrawn project) | 83778525.19 | None | 83778525.19 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | 2931899.99 | None | 2931899.99 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Process Discontinued (Withdrawn project) | 96311850.23 | None | 96311850.23 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation) | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | 20445450.03 | None | 20445450.03 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Process Discontinued (Withdrawn project) | 90055650.19 | None | 90055650.19 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | 5717099.95 | None | 5717099.95 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | 410549.94 | None | 410549.94 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | 14536350 | None | 14536350 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
2 | Withdrawn by FEMA |  | 740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | 46142775.12 | None | 46142775.12 | In COR3 review, on hold until FEMA reinstates Withdrawn projects. | WtbC
3 | Withdrawn by FEMA |  | 741097 | Region 1 San Juan Substation/Telecom | Vegetation | N/A | Pending Scope & Cost Completion by Applicant | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
3 | Withdrawn by FEMA |  | 741101 | Region 2 Arecibo Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
3 | Withdrawn by FEMA |  | 741098 | Region 3 Bayamon Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
3 | Withdrawn by FEMA |  | 741100 | Region 4 Caguas Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
3 | Withdrawn by FEMA |  | 741102 | Region 5 Mayaguez Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
3 | Withdrawn by FEMA |  | 741104 | Region 6 Ponce Substation/Telecom | Vegetation | N/A | Process Discontinued (Withdrawn project) | TBD | TBD | TBD | In Formulation by LUMA PM and IEM AL | WtbC
3 | Withdrawn by FEMA |  | 550986 | FAASt Condado - 1133 | Substation | Rebuild | Pending Scope & Cost Completion by Applicant | 14709154 | 13238238.6 | 1470915.4 | 12/10/2024 - The project SOW is currently being evaluated by LUMA Engineering with a possible change in scope of work. Forecast TBD | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
3 | Withdrawn by FEMA |  | 551912 | FAASt Puerto Nuevo - 1520 | Substation | Rebuild | Pending Scope & Cost Completion by Applicant | 16844776 | 15160298.4 | 1684477.6 | 12/10/2024 - The project SOW is currently being evaluated by LUMA Engineering with a possible change in scope of work. Forecast TBD | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
3 | Withdrawn by FEMA |  | 547241 | FAASt Tallaboa 5402 | Substation | Rebuild | Pending Scope & Cost Completion by Applicant | TBD | - | - | 1/27/2025 - According with the Applicant representative, the project will require change in scope of work. Forecast TBD. | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
3 | Withdrawn by FEMA |  | 550894 | FAASt [Baldrich - 1422] (Substation) | Substation | Rebuild | Pending Scope & Cost Completion by Applicant | 26709229 | 24038306.1 | 2670922.9 | 2/25/2025 - HM RFI Subs Matrix response received on 1/27/2025, HM forecast: pending | Project scope being evaluated, priority under evaluation, submission TBD
3 | Withdrawn by FEMA |  | 550980 | FAASt [Parques y Recreos - 1002] (Substation) | Substation | Rebuild | Pending Scope & Cost Completion by Applicant | 20916860 | $18,825,174.00 | 2091686 | 2/25/2025 - HM RFI Subs Matrix response received on 1/27/2025, HM forecast: pending | Project scope being evaluated, priority under evaluation, submission TBD
3 | Withdrawn by FEMA |  | 551918 | FAASt Crematorio - 1512 | Substation | Rebuild | Pending Scope & Cost Completion by Applicant | TBD | 0 | 0 | 12/10/2024 - According with the Applicant representative, the project will require change in scope of work. Forecast TBD | 30% of the design not finish, not approved yet. This must be changing because the new priority list.
3 | Withdrawn by FEMA |  | 718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 718955 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 718951 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 551067 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550902 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550498 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550162 | FAASt [Berwind TC - 1336] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550019 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 548598 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547350 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547273 | FAASt Charco Hondo Substation 8008 Relocation (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547269 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547259 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547243 | FAASt Egozcue - 1109 (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547226 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547160 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 334331 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 180326 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 167508 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 167168 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 166904 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 166860 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 166707 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 750730 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 752052 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 752276 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 752275 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 753302 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | Telecommunication | N/A | Inactive
3 | Withdrawn by FEMA |  | 761563 | FAASt [San Jose Relocation] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 814792 | FAASt [Telecom Infrastructure – Group E] | Telecommunication | N/A | Inactive
3 | Withdrawn by FEMA |  | 814793 | FAASt [Telecom Infrastructure – Group F] | Telecommunication | N/A | Inactive
3 | Withdrawn by FEMA |  | 730784 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 712978 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 711862 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 711829 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 704763 | FAASt [Telecom Infrastructure Group C] (Telecommunication) | Telecommunication | N/A | Inactive
3 | Withdrawn by FEMA |  | 668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 551100 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550998 | FAASt [Santurce Planta (Sect) 1116] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550972 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550771 | FAASt [Caguas TC] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 550070 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547248 | FAASt Canas TC 5002 5018 (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 547221 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 334482 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 334469 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) | Transmission | Line Rebuild | Inactive
3 | Withdrawn by FEMA |  | 179988 | FAASt [Las Lomas XFMR 1525] (Substation) | Substation | Rebuild | Inactive
3 | Withdrawn by FEMA |  | 169503 | FAASt [Ceiba Baja TRF 7012] (Substation) | Substation | Rebuild | Inactive
4 | Withdrawn by FEMA |  | 744072 | Network and Communication Infrastructure Group 2 | IT/OT | N/A | Pending FEMA review | 73183161.82 | 36152750.37 | 37030411.45 | Pending FEMA review
4 | Withdrawn by FEMA |  | 748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | IT/OT | N/A | LUMA PM Collaboration review |  |  | 52804979.05 | Pending FEMA review
4 | Withdrawn by FEMA |  | 675406 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) | Telecommunication | N/A | Inactive
4 | Withdrawn by FEMA |  | 674506 | FAASt [Field Area Network (FAN)] (Telecommunication) | Telecommunication | N/A | Inactive
4 | Withdrawn by FEMA |  | 549768 | FAASt Physical Security - Group 5 (Substation) | Substation | Physical Security | Inactive
5 | Additional Project |  | FAASt number pending | FAASt [Juncos Streetlighting] (Distribution) Work Completed | Distribution | Streetlighting | N/A | TBD | TBD | TBD | Under formulation. No cost estimated for wotk completed portion. | WC
5 | Withdrawn by FEMA |  | 678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 14607500.56 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 8163052.71 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 9017148.04 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 14314798.95 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 690483 | FAASt [Cayey Streetlighting] | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 13343261.38 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 5525916.66 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 7598892 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 7013624.27 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 15781505 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 12854140.62 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 16043135.52 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 693615 | FAASt [Rio Grande Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 6376770.32 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 30550204.86 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 5847563.41 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 17961216.53 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 9248657.11 | TBD | TBD | Under formulation. The project will be split into Work Completed and Work to Be Completed (WTBC). The estimated cost includes both portions. | WTBC
5 | Withdrawn by FEMA |  | 704741 | FAASt [Moca Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 2850000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 724599 | FAASt [Sabana Grande Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 2550000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 724669 | FAASt [Ciales Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 1590000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 724781 | FAASt [Penuelas Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 1400000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 2390000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 724605 | FAASt [Guayanilla Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 2130000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 724716 | FAASt [Quebradillas Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 2560000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 713795 | FAASt [Lares Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 1340000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA |  | 724670 | FAASt [Patillas Streetlighting] (Distribution) | Distribution | Streetlighting | Pending Scope & Cost Completion by Applicant | 2080000 | TBD | TBD | Needs to be Migrates to the new DSOW template | Clean DSOW
5 | Withdrawn by FEMA | Yes | 724828 | FAASt [Loiza Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 704929 | FAASt [San Lorenzo Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 704793 | FAASt [Yauco Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 704744 | FAASt [San Sebastian Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 698522 | FAASt [Vieques Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA | Yes | 698427 | FAASt [Maricao Streetlighting] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
5 | Withdrawn by FEMA |  | 746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | Inactive
6 | Additional Project |  | FAASt number pending | Aguadilla Custumer Experince | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Additional Project |  | 169576 | Arecibo Bulding Repair | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Additional Project |  | 169798 | Arecibo Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Additional Project |  | FAASt number pending | Barranquitas Electric Service Center | Buildings | N/A | LUMA Environmental Review | TBD | TBD | TBD | Under formulation in the Collabroation process (Appian) | WtbC
6 | Additional Project |  | FAASt number pending | Bayamon Electric Service Center (Minillas) | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Additional Project |  | FAASt number pending | Guayama Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Additional Project |  | FAASt number pending | Sabana Llana Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Additional Project |  | FAASt number pending | Toa Alta Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Additional Project |  | FAASt number pending | Vega Baja Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | Under formulation by IEM team | WtbC
6 | Withdrawn by FEMA |  | 954184 | Carolina Electric Service Center | Buildings | N/A | CRC Evaluation | 2747126.23 | 2747126.23 | TBD | In FEMA CRC evaluation. | WtbC
6 | Withdrawn by FEMA |  | 679006 | FAASt [Test and Technology Laboratory] (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 551247 | FAASt [Palo Seco South Building Repairs] (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 551827 | FAASt [San Juan Region Repair] (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 551242 | FAASt [Bayamon Region Repairs] (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 550500 | FAASt - Ponce Region Repairs (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 550060 | FAASt [Caguas Region Repairs] (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 548596 | FAASt [San German Electrical Service Center] (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 548440 | FAASt [Mayaguez Region Repairs] (Building) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 548393 | FAASt Arecibo Region Repairs (Buildings) | Buildings | N/A | Inactive
6 | Withdrawn by FEMA |  | 169804 | FAASt Aguadilla Electric Service Center (Building) | Buildings | N/A | Inactive

## Urgent Incremental Projects
Prioritization Code | High Urgency | Work Completed | Project # | Title | Asset | Sub Asset | Incurred Cost | Project costs * | 428 Allocation * | 406 Allocation * | Additional comments
1 | LUMA has already procured the materials necessary and engineered work order packages for this project utilizing the global FAASt Project Wroksheets (PW's) for equipment & materials (E&M) and arechitecture and engineering (A&E) with expectation to submit Detailed Scopes of Work (DSOWs) to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete for a number of units. If LUMA is unable to get these FAASt projects activated there is a large risk of incurred cost to rate payers these projects carry high reliability impacts. |  | Pending FAASt Number | Distribution Automation Program | Distribution | Automation | 75157137.71 | 296669500 | 178001700 | 118667800 | The Automation Program included here is based on a grouping of projects that LUMA will split to separate groups during the formulation process as DSOWs are submitted to FEMA. This program has Approximately $61 million of cost Incurred to the E&M PW. To be clear, this line does not include "Work Completed" Distribution Automation, as construction has not commenced for the units included herein as we are pending FASST numbers.
1 | Cost already incurred and project complete. | Yes | Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | Component Replacement | 3763775.37 | 3763775.37 | 3763775.37 | 0 | Transformer purchased and reimbursed to E&M PW ($892,425). Remainder of Installation and Comissioning completed under NFC.
1 | Cost already incurred and project complete. | Yes | Pending FAASt Number | Venezuela TC | Substation | Component Replacement | 2613825.35 | 2613825.35 | 2613825.35 | 0 | Transformer purchased and reimbursed to E&M PW ($1,037,090). Remainder of Installation and Commissioning completed under NFC.
1 | Transformers already purchased with manufacturing and incoming. Project needs to be included in Consolidated Project List to mitigate ratepayer exposure. |  | Pending FAASt Number | Substation Component Group 2 | Substation | Component Replacement | 3133498.208 | 130000000 | 117000000 | 13000000 | Total of 10 substations with 9 transformers, 2 metal clad, 8 PAC Upgrade, 1 cap bank, 1 RTU, 9 Distribution and 8 transmission breakers replacements plus minor repair, grounding and security for all 10 stations. High Level budgetary estimates are around $130 million.
1 | Transformers already procured with manufacturing in various stages and delivery dates from the middle of 2026 through 2028. Commitment to purchase the transformers was made under the FEMA obligated E&M PW due to having funds obligated and expectation of receiving child FASST obligations. Due to changes in COR3 policy around Global PW's, If project is not included in Consolidated Project List there will be large risk to ratepayers as the transformers are incoming. Additionally, these transformer replacements are critical to grid stability. |  | Pending FAASt Number | Substation Component Group 3 | Substation | Component Replacement | 14665406.49 | 310000000 | 279000000 | 31000000 | Scope includes among other things, 31 transformer replacements. Transformers already procured with manufacturing commencing and delivery dates from the middle of 2026 through 2028. Cost incurred is based on progress payments made for transformers to manufacturers to-date, but will increase as production of transformers continues. Additionally, LUMA has committed* $71,868,237.51 for the purchase of these transformers under the Global E&M PW, so there is significant risk to ratepayers if this project is not initiated. These transformer replacements are targeting Out of Service, Capacity Constrained, and Transformer in poor conditions to ensure reliable service to customers and build in added reselience to the system. Due to the aforementioned reasons, this is one of LUMA's top priorities for FEMA initiation and subsequent obligation. *Commitment to purchase the transformers was already made under the federally funded Equipment and Material PW at the time due to having funds obligated for transformers in the global PW and expectation of receiving child FASST obligations in a timely manner.
1 | Equipment costs incurred under Global E&M PW, with labor for installation covered under NFC and DOE. | Yes | Pending FAASt Number | Substation Component Group 0 | Substation | Component Replacement | 14145405.55 | 14145405.55 | 14145405.55 | 0 | Project is a priority to get FEMA obligated. The equipment was purchased under the federal E&M PW but installed with NFC or DOE dollars. LUMA is requesting a FAASt number to be reconciled for the Equipment purchased under E&M PW. All of this equipment cost would put rate payers at risk if it is not reconciled to child PWs. Equipment included in this cost Incurred are the following: 16 Gas Circuit Breakers ($1,036,579), 5 Transformers - Sabana Llana 1646 ($968,203), Mora TC 112 MVA ($2,926,189.87), Caguas 112 MVA ($4,416,882), Isla Grande 112MVA ($2,926,189.87), Hogar Crea 112 MVA ($1,871,361.81)
1 | LUMA has already procured material and engineered work order packages for this project utilizing the global PW's for E&M and A&E with expectation to submit DSOWs to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete for a number of units. If LUMA is unable to get these projects activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. |  | Pending FAASt Number | 38 kV Reclosers Program | Transmission | Automation | 6521828.2 | 46523875.17 | 29631317.7485 | 16892557.4215 | Cost Incurred for 38kV Recloser Program is due to Engineering and Project Management Costs ($3.1M) and Equipment Purchase Cost as the Reclosers for these projects have already been procured under the Equipment & Material PW and are in LUMA's Warehouse ($3.4M). 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review.
1 | Historical Flooding in the Arecibo Pueblo Substation requires it to be relocated to Arecibo Sectionalizer Site. The site is critical to stability of system. Due to relocation, much of the project is expected to be funded by FEMA's Section 406 Hazard Mitigation. |  | Pending FAASt Number | Arecibo Sect. Substation Rebuild | Substation | Substation Rebuild | 0 | 71435277.14 | 7143527.714 | 64291749.426 | Cost Incurred to date is based on project planning exercises and therefore not tied directly to execution of project. High-Level project scope: Rebuild of priority sectionalizing substation including colocated 8015 Arecibo Hospital Distrito and 8003 Arecibo Rural distribution substations and relocation to site of distribution substation 8002 Arecibo Pueblo substation (due to Historical Flooding).
1 | This station has numerous major issues that need to be remediated to ensure reliable service. Among these are the following: 1. GIS problems. 2. Out of service underground transmission lines 3.Reliability Issues 4. Large Flood Risk 5. High Critical Loads |  | Pending FAASt Number | Chardon Sect. Substation Rebuild | Substation | Substation Rebuild | 0 | 25000000 | 15000000 | 10000000 | Cost Incurred to date is based on project planning exercises and therfore not tied directly to execution of project. Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substations 1403 Chardon I and 1404 Chardón 2

## Vegetation Incremental Projects
Project # | Title | Asset | Sub Asset | Incurred Cost | Project costs * | 428 Allocation * | 406 Allocation * | Project Status | Additional comments
FAASt number pending | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 136954530 | 36628489.0485 | 100284954.5925 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
FAASt number pending | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 188729100 | 50475597.795 | 138196883.475 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
FAASt number pending | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 33723810 | 9019432.9845 | 24694259.8725 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
FAASt number pending | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 165176460 | 44176444.227 | 120950462.835 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
FAASt number pending | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 218058975 | 58319872.8638 | 159673684.4437 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
FAASt number pending | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 160503255 | 42926595.5498 | 117528508.4737 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
FAASt number pending | 38kV Transmission Line 100 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5136889.56 | 428416.5893 | 4708472.9707 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 200 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 3130292.05 | 261066.357 | 2869225.693 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 800 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 3249603.27 | 271016.9127 | 2978586.3573 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5555563.43 | 463333.9901 | 5092229.4399 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 6154288.74 | 513267.6809 | 5641021.0591 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 6117410.71 | 510192.0532 | 5607218.6568 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 6141272.97 | 512182.1657 | 5629090.8043 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 16228492.86 | 1353456.3045 | 14875036.5555 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 4904775.04 | 409058.2383 | 4495716.8017 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 8256335.2 | 688578.3557 | 7567756.8443 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 9898491.21 | 825534.1669 | 9072957.0431 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 13100370.02 | 1092570.8597 | 12007799.1603 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 9475478.76 | 790254.9286 | 8685223.8314 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5113027.32 | 426426.4785 | 4686600.8415 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 2279928.56 | 190146.0419 | 2089782.5181 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 4800 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 8629453.86 | 719696.4519 | 7909757.4081 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 3345052.23 | 278977.356 | 3066074.874 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5807201.58 | 484320.6118 | 5322880.9682 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5915666.32 | 493366.5711 | 5422299.7489 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
FAASt number pending | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 9019926.9 | 752261.9035 | 8267664.9965 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).

## LUMA_Tier2_Projects in QAQC+ (hidden)
Project# | Title | Asset | SUB ASSET | Process Step | Project Status | Evaluation Type | APPIAN Approval ID | APPIAN# | Additional comments | 406 Cost Estimate | 428 Cost Estimate | A&E Cost Estimate | Total (406+428+A&E)
751656 | Culebra Microgrid | Grid Modernization | N/A | Collaboration | Policy & Cost QA/QC Review | RFI + DSOW | 576 | APR-576 |  | 38954081 | $ - | $ - | 38954081
751655 | Vieques Microgrid | Grid Modernization | N/A | Collaboration | Policy & Cost QA/QC Review | RFI + DSOW | 577 | APR-577 |  | 105481956 | $ - | $ - | 105481956
744072 | Network & Communication Infrastructure Group 2 | IT/OT | N/A | Collaboration | Initial QA/QC Review | RFI | 742 | APR-742 |  | 490438.07 | 1893141.74 | 181440.64 | 2565020.45
675345 | IT OT Technology Systems Reparations Group 1 | IT/OT | N/A | Collaboration | Pending QA/QC Revisions | RFI | 94 | 34425 |  | $ - | 8378200.51 | 798980.71 | 9177181.22
679035 | Telecom Infrastructure – Group A | IT/OT | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 560 | APR-560 |  | $ - | $ - | $ - | 5900000
662238 | Microwave PTP Backbone Group A | IT/OT | N/A | Collaboration | Policy & Cost QA/QC Review | RFI + DSOW | 331 | APR-331 |  | 1247527.04 | 14800399.5 | 1081553.96 | 17129480.5
704805 | Telecom Infrastructure – Group D | IT/OT | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 561 | APR-561 |  | $ - | $ - | $ - | 6905000
550910 | Physical Security Group 1 | Substation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 390 | APR-390 |  | 665958.96 | 6025270 | 1278328 | 7969556.96
547247 | Cambalache TC | Substation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 437 | APR-437 |  | 84733286.06 | 5143802.81 | 319703.09 | 90196791.96
169266 | Centro Medico 1327/1359 Equipment Repair & Replacement | Substation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 481 | APR-481 |  | 6537037 | 14795324 | 1810918 | 23143279
165209 | EPC - Culebra Substation 3801 and New Culebra Substation 3802 | Substation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 564 | APR-564 |  | $ - | 12765829 | 1493591 | 14259420
682328 | Bayamón TC - Rebuild | Substation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 688 | APR-688 |  | $ - | 2637502.74 | 267793.34 | 2905296.08
Pending FAASt Number | Santa Isabel TC | Substation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 697 | APR-697 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | Fajardo 2002 Transformer Replacement | Substation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 728 | APR-728 |  | #N/A | #N/A | #N/A | #N/A
547187 | [547187] FAASt - [Substation Component Replacement Program] | Substation | N/A | Collaboration | Policy & Cost QA/QC Review | ISOW | 691 | APR-691 |  | 308929.24 | 6551618.4 | 2069220.14 | 8929767.78
Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 714 | APR-714 |  | #N/A | #N/A | #N/A | #N/A
750151 | TPole TL 700 Costa Sur SP - Yauco 2 HP | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 318 | APR-318 | In LUMA - Projects List | 11027.93 | 123160.67 | 16034.68 | 150223.28
753782 | TPole TL 3100 Monacillos TC - Sabana Llana TC | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 319 | APR-319 | In LUMA - Projects List | 5236.77 | 128962.93 | 16491.53 | 150691.23
753785 | TPole TL 3300 San Gerardo Sect – Venezuela Sect | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 320 | APR-320 |  | $ - | 298678.49 | 38000.29 | 336678.78
753781 | TPole 800 Comsat Sect – Cidra Sect | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 330 | APR-330 |  | 38921.42 | 612950.66 | 78345.34 | 730217.42
805513 | 38kV Recloser TL 3000 Monacillos TC to Bairoa TO | Transmission |  | Collaboration | Pending QA/QC Revisions | DSOW | 425 | APR-425 | Added to Non-Priority Projects List | $ - | $ - | $ - | 3250000
811923 | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI | 486 | APR-486 | Added to Non-Priority Projects List | 35673.37 | 190142.13 | 28863.82 | 254679.32
811913 | Transmission Priority Pole Replacement Program Line 9600 Bayamon TC–Catano Sect | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI | 487 | APR-487 | Added to Non-Priority Projects List | 64492.51 | 271062.55 | 42887.43 | 378442.49
Pending FAASt Number | 38kV Recloser TL 1500-Yauco HP to San German TC | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | DSOW | 518 | APR-518 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | 38 kV Reclosers TL 5600 | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | DSOW | 519 | APR-519 | Added to Non-Priority Projects List | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | TPole Line 1600 Leon SECT – Acacias TC | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | DSOW | 541 | APR-541 | Added to Non-Priority Projects List | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | TPole Line 2000 Once de Agosto – San Sebastian TC | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | DSOW | 542 | APR-542 | Added to Non-Priority Projects List | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | T Pole 9900 Rio Blanco HP to Humacao Sect | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | DSOW | 543 | APR-543 | Added to Non-Priority Projects List | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | T Pole line 4800 Santa Isabel TC to Santa Isabel Sect | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | DSOW | 544 | APR-544 | Added to Non-Priority Projects List | #N/A | #N/A | #N/A | #N/A
805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Transmission | Line Rebuild | Collaboration | Pending QA/QC Revisions | DSOW | 562 | APR-562 |  | $ - | 1097125.99 | 140183.46 | 1237309.45
805517 | 38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect. | Transmission | Line Rebuild | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 563 | APR-563 |  | $ - | 918908.76 | 117407.32 | 1036316.08
547251 | Line 2400 Dos Bocas HP to America Apparel | Transmission | Line Rebuild | Collaboration | Pending QA/QC Revisions | DSOW | 575 | APR-575 |  | $ - | 6482242.86 | 433482.47 | 6915725.33
334331 | Line 1900 Dos Bocas HP to San Sebastian (38kV) TC | Transmission | Line Rebuild | Collaboration | Pending QA/QC Revisions | DSOW | 586 | APR-586 |  | $ - | 31788090.96 | 2009300.52 | 33797391.48
756997 | TL 1900 Caguanas to Lares TO | Transmission | Line Rebuild | Collaboration | Pending QA/QC Revisions | DSOW | 587 | APR-587 |  | $ - | 41068188.09 | 2671511.79 | 43739699.88
756999 | TL1900 Lares to San Sebastian | Transmission | Line Rebuild | Collaboration | Pending QA/QC Revisions | DSOW | 590 | APR-590 |  | $ - | 30407203.69 | 2088488.51 | 32495692.2
Pending FAASt Number | T Pole Arecibo Group 1 | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | DSOW | 592 | APR-592 | Added to Non-Priority Projects List | #N/A | #N/A | #N/A | #N/A
753787 | Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 618 | APR-618 |  | $ - | 553203.43 | 70371.06 | 623574.49
753788 | Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastián TC | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 619 | APR-619 |  | $ - | 840422.28 | 217503.32 | 1057925.6
753786 | Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO | Transmission | Pole Replacement | Collaboration | Pending QA/QC Revisions | RFI + DSOW | 620 | APR-620 | In LUMA - Projects List | $ - | 599861.6 | 79596.2 | 679457.8
711819 | TL 13400 TC-San German Sect-La Parguera Sect | Transmission | Line Rebuild | Collaboration | Pending QA/QC Revisions | RFI | 621 | APR-621 | In LUMA - Projects List | 332405.64 | 2124155.13 | 271489.55 | 2728050.32
165213 | TL 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Transmission | Line Rebuild | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | RFI + DSOW | 346 | APR-346 |  | 39446157.65 | 80817479.56 | 6015993.93 | 126279631.14
749072 | Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC | Transmission | Pole Replacement | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | RFI | 433 | APR-433 | In LUMA - Projects List | 30755.87 | 158495.32 | 20635.01 | 209886.2
753781 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect | Transmission | Pole Replacement | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | RFI | 434 | APR-434 |  | 38921.42 | 612950.66 | 78345.34 | 730217.42
750150 | Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP | Transmission | Pole Replacement | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | RFI | 484 | APR-484 | In LUMA - Projects List | 20679.11 | 129733.64 | 16583.7 | 166996.45
753782 | Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC | Transmission | Pole Replacement | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | RFI | 488 | APR-488 | In LUMA - Projects List | 5236.77 | 128962.93 | 16491.53 | 150691.23
Pending FAASt Number | Transmission Line 36100 Cana to Bayamon TC | Transmission | Line Rebuild | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 663 | APR-663 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | TL 36100 Dos Bocas to Ciales | Transmission | Line Rebuild | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 687 | APR-687 |  | #N/A | #N/A | #N/A | #N/A
749072 | Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC | Transmission | Pole Replacement | Approval | With Reviewers | RFI + DSOW | 740 | APR-740 | In LUMA - Projects List | 30755.87 | 158495.32 | 20635.01 | 209886.2
176913 | Palo Seco SP to Catano Sect 38kV Line- 9500 | Transmission | Line Rebuild | Approval | With Signers | DSOW | 653 | APR-653 | In LUMA - Projects List | $ - | 35985053.2 | 4817554.82 | 40802608.02
176971 | 38kV Line 8200 - San Juan SP to Catano Sect Line | Transmission | Line Rebuild | Approval | With Signers | DSOW | 655 | APR-655 | In LUMA - Projects List | $ - | 23193643.55 | 3250894.37 | 26444537.92
678795 | Arecibo Streetlighting | Distribution | Streetlights | Collaboration | Initial QA/QC Review | DSOW | 633 | APR-633 |  | 1527389 | 14601018 | 2673960 | 18802367
690480 | Humacao Streetlighting | Distribution | Streetlights | Collaboration | Initial QA/QC Review | DSOW | 634 | APR-634 |  | 922000 | 7598892 | 1719130 | 10240022
704931 | Camuy Streetlighting-Work to be Completed Portion | Distribution | Streetlights | Collaboration | Initial QA/QC Review | DSOW | 638 | APR-638 |  | 2269186 | 15436783 | 2828651 | 20534620
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 150 | APR-150 | Added to Non-Priority Projects List | 1877045 | 874904 | 130382 | 2882331
693543 | FAASt [Juncos Streetlighting] (Distribution)- Work to be Completed | Distribution | Streetlights | Collaboration | Pending QA/QC Revisions | DSOW | 432 | APR-432 |  | 1643590 | 11568798 | 1899782 | 15112170
729124 | Automation Program Group 07 | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 499 | APR-499 | Added to Non-Priority Projects List | #N/A | #N/A | #N/A | #N/A
745851 | Automation Program Group 11] (Distribution) | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 500 | APR-500 |  | 1052298 | 433532 | 46322 | 1532152
800369 | Automation Program Group 38 (Distribution) | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 501 | APR-501 |  | $ - | $ - | $ - | 1335000
800399 | Automation Program Group 40 (Transmission/Distribution) | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 502 | APR-502 |  | $ - | $ - | $ - | 2577000
745854 | Automation Program Group 9 | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 503 | APR-503 | Added to Non-Priority Projects List | 1164604 | 494110 | 52795 | 1711509
806935 | Pole and Conductor Repair – Caguas Group 6 – Phase 2 | Distribution | Poles and Conductors | Collaboration | Pending QA/QC Revisions | DSOW | 507 | APR-507 |  | $ - | $ - | $ - | 6120000
800394 | Automation Program Group 39 | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 508 | APR-508 |  | $ - | $ - | $ - | 3084000
801437 | Automation Program Group 42 | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 509 | APR-509 |  | $ - | $ - | $ - | 2883000
801438 | Automation Program Group 43 | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 510 | APR-510 |  | $ - | $ - | $ - | 2490000
801440 | Automation Program Group 44 | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 511 | APR-511 |  | $ - | $ - | $ - | 3902000
801441 | Automation Program Group 45 | Distribution | Automation | Collaboration | Pending QA/QC Revisions | DSOW | 512 | APR-512 |  | $ - | $ - | $ - | 2400000
817249 | Pole and Conductor Caguas Group 7 Phase 2 | Distribution | Poles and Conductors | Collaboration | Pending QA/QC Revisions | DSOW | 528 | APR-528 |  | $ - | $ - | $ - | 5100000
817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution | Distribution | Poles and Conductors | Collaboration | Pending QA/QC Revisions | DSOW | 535 | APR-535 |  | $ - | $ - | $ - | 2040000
165226 | Feeders Vieques & Culebra | Distribution | Feeders Rebuild | Collaboration | Pending QA/QC Revisions | RFI | 615 | APR-615 | In LUMA - Projects List | 27689656.16 | 59069587.62 | 7514394.03 | 94273637.81
958367 | Distribution Feeder Rebuild #6603-01 | Distribution | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 694 | APR-694 |  | 1172038.62 | 11588885.95 | 2885305.81 | 15646230.38
956782 | Distribution Feeder Rebuild #6802-04 | Distribution | Feeders | Collaboration | Pending QA/QC Revisions | DSOW | 695 | APR-695 |  | 2769954.18 | 19468619.25 | 2489006.38 | 24727579.81
817993 | Distribution Feeder Rebuild #1801-03 | Distribution | Feeders | Collaboration | Pending QA/QC Revisions | DSOW | 696 | APR-696 |  | $ - | $ - | $ - | 6131846
738667 | Pole and Conductor Repair - Ponce Group 2 - Phase 2 | Distribution | Poles and Conductors | Collaboration | Pending QA/QC Revisions | RFI | 730 | APR-730 |  | 33268.04 | 14893960.55 | 1724241.14 | 16651469.73
738674 | Pole and Conductor Repair - Mayaguez Group 2 - Phase 2 | Distribution | Poles and Conductors | Collaboration | Pending QA/QC Revisions | RFI | 731 | APR-731 |  | 28130.53 | 8013484.69 | 922352.8 | 8963968.02
806936 | Pole and Conductor Repair – Carolina Group 3 – Phase 2 | Distribution | Poles and Conductors | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 515 | APR-515 |  | $ - | $ - | $ - | 5100000
818006 | Distribution Feeder Rebuild 2402-02 | Distribution | Feeders | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 692 | APR-692 |  | $ - | $ - | $ - | 34516477
767005 | Distribution Feeder Rebuild #1303-05 | Distribution | Feeders | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 693 | APR-693 |  | $ - | $ - | $ - | 12631766
757687 | Automation Program Group 22 | Distribution | Automation | Approval | With Reviewers | RFI | 632 | APR-632 | Added to Non-Priority Projects List | $ - | 2768746.03 | 359230.44 | 3127976.47
741105 | FAASt [All Regions 230kV Transmission Lines] (Vegetation) | Vegetation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 664 | APR-664 |  | 157385518.05 | $ - | $ - | 157385518.05
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Collaboration | Pending QA/QC Revisions | DSOW | 677 | APR-677 |  | 3777166.88 | $ - | $ - | 3777166.88
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 673 | APR-673 |  | 5894785.29 | $ - | $ - | 5894785.29
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 674 | APR-674 |  | 11782088.78 | $ - | $ - | 11782088.78
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 675 | APR-675 |  | 23846154.02 | $ - | $ - | 23846154.02
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 676 | APR-676 |  | 5425376.76 | $ - | $ - | 5425376.76
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation) | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 678 | APR-678 |  | 13788400.37 | $ - | $ - | 13788400.37
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 679 | APR-679 |  | 70421923.26 | $ - | $ - | 70421923.26
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 680 | APR-680 |  | 66510486.76 | $ - | $ - | 66510486.76
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 681 | APR-681 |  | 16374246.76 | $ - | $ - | 16374246.76
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 682 | APR-682 |  | 84411128.06 | $ - | $ - | 84411128.06
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 683 | APR-683 |  | 44200121.5 | $ - | $ - | 44200121.5
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 684 | APR-684 |  | 76781710.48 | $ - | $ - | 76781710.48
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Collaboration | Policy & Cost QA/QC Review (COR3 Review) | DSOW | 685 | APR-685 |  | 11782088.78 | $ - | $ - | 11782088.78
727531 | Ponce Group A High Density DSOW (Vegetation) | Vegetation | N/A | Approval | With Reviewers | DSOW | 67 | 24563 |  | 42520736.92 | $ - | $ - | 42520736.92
728832 | Mayaguez Group A High Density (vegetation) | Vegetation | N/A | Approval | With Reviewers | DSOW | 68 | 24929 |  | 23418437.42 | $ - | $ - | 23418437.42
460406 | San Juan Group B High Density (vegetation) | Vegetation | N/A | Approval | With Reviewers | DSOW | 69 | 25294 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | Vegetation clearing for San Juan Region 1 Feeder 2301-02 | Vegetation | N/A | Approval | With Reviewers | DSOW | 567 | APR-567 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | Vegetation clearing Distribution Line 2401-01 - San Juan_Region 1 | Vegetation | N/A | Approval | With Reviewers | DSOW | 568 | APR-568 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | Vegetation clearing Distribution Line 3007-03 - Caguas_Region 4 | Vegetation | N/A | Approval | With Reviewers | DSOW | 569 | APR-569 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | Vegetation clearing Distribution Line 5602-02 - Ponce_Region 6 | Vegetation | N/A | Approval | With Reviewers | DSOW | 571 | APR-571 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | Vegetation clearing Distribution Line 5803-02 - Ponce_Region 5 | Vegetation | N/A | Approval | With Reviewers | DSOW | 572 | APR-572 |  | #N/A | #N/A | #N/A | #N/A
Pending FAASt Number | Vegetation clearing Distribution Line 6012-02- Mayaguez_Region 5 | Vegetation | N/A | Approval | With Reviewers | DSOW | 573 | APR-573 |  | #N/A | #N/A | #N/A | #N/A
740406 | Region 1 - San Juan Group B | Vegetation | N/A | Approval | With Signers | DSOW | 422 | APR-422 |  | 5894785.29 | $ - | $ - | 5894785.29
727659 | FAASt [Region 2 Arecibo Transmission - 115kV] (Vegetation) | Vegetation | N/A | Approval | With Signers | DSOW | 716 | APR-716 |  | 54305563.22 | 18265704.46 | 1517338.23 | 74088605.91

## FAASt - LUMA Obligated (hidden)
PW | LUMA - Obligated | Project Name | 428 | 406 | Total Child | Asset
10496 | PA-02-PR-4339-PW-10496 | FAASt - Catano-Rebuild 1801(Substation) | 16359899.17 | 6895149.77 | 23255048.94 | Substation
10499 | PA-02-PR-4339-PW-10499 | FAASt Maunabo Streetlighting (Distribution) | 6199877.07 | 243880.33 | 6443757.4 | Distribution
10515 | PA-02-PR-4339-PW-10515 | FAASt -Luquillo Distribution Streetlighting | 8628667.29 | 181658.08 | 8810325.37 | Distribution
10521 | PA-02-PR-4339-PW-10521 | FAASt Lajas Streetlighting (Distribution) | 10278336.09 | 426332.48 | 10704668.57 | Distribution
10538 | PA-02-PR-4339-PW-10538 | FAASt Streetlighting - Guánica (Distribution | 9687238 | 370808 | 10058046 | Distribution
10539 | PA-02-PR-4339-PW-10539 | FAASt Aguada Streetlighting (Distribution) | 17764494.34 | 807222.04 | 18571716.38 | Distribution
10624 | PA-02-PR-4339-PW-10624 | FAASt-Substation 2501 Vieques (Substation) | 1209111 | 178309 | 1387420 | Substation
10626 | PA-02-PR-4339-PW-10626 | FAASt-Substation 3801 Culebra (Substation) | 1282218 | 177391 | 1459609 | Substation
10629 | PA-02-PR-4339-PW-10629 | FAASt Distribution Feeders - Ponce Short Term | 316119 | 64134 | 380253 | Distribution
10630 | PA-02-PR-4339-PW-10630 | FAASt Distribution Feeders - Ponce Short Term | 323692 | 69130 | 392822 | Distribution
10632 | PA-02-PR-4339-PW-10632 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 1593443 | 0 | 1593443 | Substation
10635 | PA-02-PR-4339-PW-10635 | FAASt Distribution Feeders - Caguas Short Ter | 142917 | 10826 | 153743 | Distribution
10679 | PA-02-PR-4339-PW-10679 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | 1217429 | 0 | 1217429 | Transmission
10690 | PA-02-PR-4339-PW-10690 | FAASt Distribution Feeders - Arecibo Short Te | 610448 | 157420 | 767868 | Distribution
10701 | PA-02-PR-4339-PW-10701 | FAASt Distribution Feeders - Caguas Short Term | 108847 | 14874 | 123721 | Distribution
10742 | PA-02-PR-4339-PW-10742 | FAASt Distribution Pole and Conductor Repair- | 20468 | 5830 | 26298 | Distribution
10751 | PA-02-PR-4339-PW-10751 | FAASt Distribution Pole and Conductor Repair- | 43725 | 5620 | 49345 | Distribution
10764 | PA-02-PR-4339-PW-10764 | FAASt Distribution Pole and Conductor Repair | 284349 | 73265 | 357614 | Distribution
10773 | PA-02-PR-4339-PW-10773 | FAASt Distribution Pole and Conductor Repair | 1408531 | 358420 | 1766951 | Distribution
10777 | PA-02-PR-4339-PW-10777 | FAASt Distribution Pole and Conductor Repair - | 1425163 | 368954 | 1794117 | Distribution
10788 | PA-02-PR-4339-PW-10788 | FAASt - Costa Sur SP TC  Equipment Repair and | 23251835 | 0 | 23251835 | Substation
10800 | PA-02-PR-4339-PW-10800 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | 453597 | 0 | 453597 | Transmission
10812 | PA-02-PR-4339-PW-10812 | FAASt Distribution Pole and Conductor Repair- | 190570 | 49943 | 240513 | Distribution
10821 | PA-02-PR-4339-PW-10821 | FAASt Distribution Pole and Conductor Repair | 621804 | 171614 | 793418 | Distribution
10824 | PA-02-PR-4339-PW-10824 | FAASt Distribution Pole and Conductor Repair | 84433 | 23322 | 107755 | Distribution
10827 | PA-02-PR-4339-PW-10827 | FAASt Distribution Pole and Conductor Repair | 1747929 | 362533 | 2110462 | Distribution
10837 | PA-02-PR-4339-PW-10837 | FAASt Line 6700 Martin Peña TC to Villamar Se | 690703 | 0 | 690703 | Transmission
10841 | PA-02-PR-4339-PW-10841 | FAASt Physical Security - Group 1 (Substatio | 6025270.22 | 665958.96 | 6691229.18 | Substation
10857 | PA-02-PR-4339-PW-10857 | FAASt Streetlighting - Villalba (Distributio | 10190536.05 | 681865.66 | 10872401.71 | Distribution
10858 | PA-02-PR-4339-PW-10858 | FAASt - Substation Minor Repairs Group A (Subs | 4482972.51 | 488202.58 | 4971175.09 | Substation
10864 | PA-02-PR-4339-PW-10864 | FAASt Distribution Pole and Conductor Repair | 1072850.98 | 319213.9 | 1392064.88 | Distribution
10876 | PA-02-PR-4339-PW-10876 | FAASt Distribution Streetlighting - Aibonito | 7074498 | 178787 | 7253285 | Distribution
10884 | PA-02-PR-4339-PW-10884 | FAASt Distribution Streetlighting - Cataño ( | 16996758 | 565289 | 17562047 | Distribution
10891 | PA-02-PR-4339-PW-10891 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | 420866 | 0 | 420866 | Transmission
10893 | PA-02-PR-4339-PW-10893 | FAASt Distribution Pole and Conductor Repair | 441308 | 90422 | 531730 | Distribution
10906 | PA-02-PR-4339-PW-10906 | FAASt Distribution Pole and Conductor Repair | 872891 | 238203 | 1111094 | Distribution
10909 | PA-02-PR-4339-PW-10909 | FAASt Distribution Pole and Conductor Repair | 1894033.53 | 472527 | 2366560.53 | Distribution
10919 | PA-02-PR-4339-PW-10919 | FAASt Distribution Pole and Conductor Repair | 3286536 | 835984 | 4122520 | Distribution
10922 | PA-02-PR-4339-PW-10922 | FAASt Distribution Pole and Conductor Repair- | 904194 | 227661 | 1131855 | Distribution
10933 | PA-02-PR-4339-PW-10933 | FAASt Distribution Pole and Conductor Repair | 1412368 | 289653 | 1702021 | Distribution
10935 | PA-02-PR-4339-PW-10935 | FAASt Distribution Pole and Conductor Repair | 1773428 | 318852 | 2092280 | Distribution
10957 | PA-02-PR-4339-PW-10957 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Teleco | 48941484 | 0 | 48941484 | Telecommunications
10962 | PA-02-PR-4339-PW-10962 | FAASt Distribution Pole and Conductor Repair | 3575454.81 | 857193.1 | 4432647.91 | Distribution
10978 | PA-02-PR-4339-PW-10978 | FAASt San Juan 115kV Underground Transmission | 14746039.57 | 0 | 14746039.57 | Transmission
11041 | PA-02-PR-4339-PW-11041 | FAASt Distribution Pole and Conductor Repair- | 4686914.68 | 1064121.8 | 5751036.48 | Distribution
11045 | PA-02-PR-4339-PW-11045 | FAASt Rio Grande Estate Substation CH-2306 (Su | 7098243.76 | 4585370.95 | 11683614.71 | Substation
11089 | PA-02-PR-4339-PW-11089 | FAASt Distribution Pole and Conductor Repair - | 129744 | 27443 | 157187 | Distribution
11090 | PA-02-PR-4339-PW-11090 | FAASt Distribution Pole and Conductor Repair | 20729 | 633 | 21362 | Distribution
11095 | PA-02-PR-4339-PW-11095 | FAASt Hatillo Streetlight (Distribution) | 18570095.25 | 1764387.7 | 20334482.95 | Distribution
11096 | PA-02-PR-4339-PW-11096 | FAASt Distribution Pole and Conductor Repair | 171152.23 | 46010.58 | 217162.81 | Distribution
11097 | PA-02-PR-4339-PW-11097 | FAASt Manati Streetlight (Distribution) | 27067865 | 1568964 | 28636829 | Distribution
11098 | PA-02-PR-4339-PW-11098 | FAASt Distribution Pole and Conductor Repair | 729040 | 179902 | 908942 | Distribution
11099 | PA-02-PR-4339-PW-11099 | FAASt Distribution Streetlighting - Dorado | 22864972 | 1505645 | 24370617 | Distribution
11100 | PA-02-PR-4339-PW-11100 | FAASt Aguirre TC - BKRS (Substations) | 39034592 | 0 | 39034592 | Substation
11101 | PA-02-PR-4339-PW-11101 | FAASt Distribution Pole and Conductor Repair | 243073 | 55558 | 298631 | Distribution
11103 | PA-02-PR-4339-PW-11103 | FAASt Distribution Pole and Conductor Repair- | 353628 | 54317.84 | 407945.84 | Distribution
11105 | PA-02-PR-4339-PW-11105 | FAASt Distribution Pole and Conductor Repair | 589335 | 157153 | 746488 | Distribution
11106 | PA-02-PR-4339-PW-11106 | FAASt Distribution Pole and Conductor Repair | 163846.51 | 51337.5 | 215184.01 | Distribution
11107 | PA-02-PR-4339-PW-11107 | FAASt Distribution Pole and | 483786 | 106510 | 590296 | Distribution
11109 | PA-02-PR-4339-PW-11109 | FAASt Distribution Pole and Conductor Repair | 452956.93 | 110600.22 | 563557.15 | Distribution
11113 | PA-02-PR-4339-PW-11113 | FAASt Distribution Pole and Conductor Repair- | 911136.76 | 206650.4 | 1117787.16 | Distribution
11114 | PA-02-PR-4339-PW-11114 | FAASt Distribution Pole and Conductor Repair | 498436 | 95482 | 593918 | Distribution
11116 | PA-02-PR-4339-PW-11116 | FAASt Distribution Pole and Conductor Repair | 250906 | 68700 | 319606 | Distribution
11123 | PA-02-PR-4339-PW-11123 | FAASt Distribution Pole and Conductor Repair | 70683 | 21148 | 91831 | Distribution
11130 | PA-02-PR-4339-PW-11130 | FAASt Distribution Pole and Conductor Repair | 545661.24 | 113378.16 | 659039.4 | Distribution
11136 | PA-02-PR-4339-PW-11136 | FAASt Distribution Pole and Conductor Repair | 510067.96 | 102310.67 | 612378.63 | Distribution
11137 | PA-02-PR-4339-PW-11137 | FAASt Distribution Pole and Conductor Repair | 85921.77 | 17491 | 103412.77 | Distribution
11138 | PA-02-PR-4339-PW-11138 | FAASt Distribution Pole and Conductor Repair P | 254972.22 | 63260 | 318232.22 | Distribution
11143 | PA-02-PR-4339-PW-11143 | FAASt Distribution Pole and Conductor Repair - | 537688 | 134695 | 672383 | Distribution
11145 | PA-02-PR-4339-PW-11145 | FAASt Distribution Pole and Conductor Repair | 573047.24 | 136182.31 | 709229.55 | Distribution
11149 | PA-02-PR-4339-PW-11149 | FAASt Distribution Pole and Conductor Repair | 577000.79 | 116779.74 | 693780.53 | Distribution
11150 | PA-02-PR-4339-PW-11150 | FAASt Distribution Pole and Conductor Repair | 68823 | 14986 | 83809 | Distribution
11152 | PA-02-PR-4339-PW-11152 | FAASt Distribution Pole and Conductor Repair | 20584 | 4995 | 25579 | Distribution
11165 | PA-02-PR-4339-PW-11165 | FAASt Distribution Pole and Conductor Repair | 65944 | 11661 | 77605 | Distribution
11166 | PA-02-PR-4339-PW-11166 | FAASt Distribution Pole and Conductor Repair | 431381.68 | 105743.62 | 537125.3 | Distribution
11168 | PA-02-PR-4339-PW-11168 | FAASt Distribution Pole and Conductor Repair | 43374 | 11028 | 54402 | Distribution
11169 | PA-02-PR-4339-PW-11169 | FAASt Distribution Pole and Conductor Repair - | 198050.74 | 41796.87 | 239847.61 | Distribution
11171 | PA-02-PR-4339-PW-11171 | FAASt Distribution Pole and Conductor Repair - | 355178 | 58304 | 413482 | Distribution
11181 | PA-02-PR-4339-PW-11181 | FAASt Distribution Pole and Conductor Repair | 516951 | 108247 | 625198 | Distribution
11182 | PA-02-PR-4339-PW-11182 | FAASt Distribution Pole and Conductor Repair | 208400 | 57671.35 | 266071.35 | Distribution
11183 | PA-02-PR-4339-PW-11183 | FAASt Distribution Pole and Conductor Repair | 635326.93 | 108700.19 | 744027.12 | Distribution
11184 | PA-02-PR-4339-PW-11184 | FAASt Transmission Priority Pole Replacements | 214124 | 2243 | 216367 | Distribution
11193 | PA-02-PR-4339-PW-11193 | FAASt Distribution Pole and Conductor Repair | 303774 | 72188.49 | 375962.49 | Distribution
11196 | PA-02-PR-4339-PW-11196 | FAASt Distribution Pole and Conductor Repair - | 775779 | 176882.42 | 952661.42 | Distribution
11201 | PA-02-PR-4339-PW-11201 | FAASt Distribution Pole and Conductor Repair | 208544.25 | 53746.06 | 262290.31 | Distribution
11203 | PA-02-PR-4339-PW-11203 | FAASt Distribution Pole and Conductor Repair- | 469650.95 | 95954.05 | 565605 | Distribution
11207 | PA-02-PR-4339-PW-11207 | FAASt Distribution Pole and Conductor Repair | 443331 | 98484 | 541815 | Distribution
11212 | PA-02-PR-4339-PW-11212 | FAASt Distribution Pole and Conductor Repair | 517156 | 105667 | 622823 | Distribution
11214 | PA-02-PR-4339-PW-11214 | FAASt Distribution Pole and Conductor Repair | 21408.25 | 5830.39 | 27238.64 | Distribution
11217 | PA-02-PR-4339-PW-11217 | FAASt Distribution Pole and Conductor Repair - | 164908.86 | 14986 | 179894.86 | Distribution
11229 | PA-02-PR-4339-PW-11229 | FAASt Distribution Pole and Conductor Repair - | 523404 | 108652 | 632056 | Distribution
11231 | PA-02-PR-4339-PW-11231 | FAASt Distribution Pole and Conductor Repair | 211622.76 | 33717.31 | 245340.07 | Distribution
11256 | PA-02-PR-4339-PW-11256 | FAASt Distribution Pole and Conductor Repair | 59545.08 | 17491.16 | 77036.24 | Distribution
11257 | PA-02-PR-4339-PW-11257 | FAASt Distribution Pole and Conductor Repair | 186321 | 51841 | 238162 | Distribution
11263 | PA-02-PR-4339-PW-11263 | FAASt Distribution Pole and Conductor Repair | 19848.36 | 5830.39 | 25678.75 | Distribution
11264 | PA-02-PR-4339-PW-11264 | FAASt Distribution Pole and Conductor Repair | 448719.06 | 114710.2 | 563429.26 | Distribution
11267 | PA-02-PR-4339-PW-11267 | FAASt Distribution Pole and Conductor Repair | 64425.44 | 16226.16 | 80651.6 | Distribution
11268 | PA-02-PR-4339-PW-11268 | FAASt Distribution Pole and Conductor Repair | 150345 | 37878 | 188223 | Distribution
11269 | PA-02-PR-4339-PW-11269 | FAASt Distribution Pole and Conductor Repair | 487190 | 129039 | 616229 | Distribution
11273 | PA-02-PR-4339-PW-11273 | FAASt Distribution Pole and Conductor | 42728.41 | 9990.97 | 52719.38 | Distribution
11275 | PA-02-PR-4339-PW-11275 | FAASt Distribution Pole and Conductor Repair | 547010 | 102417 | 649427 | Distribution
11276 | PA-02-PR-4339-PW-11276 | FAASt Distribution Pole and Conductor Repair - | 60838.48 | 16023.76 | 76862.24 | Distribution
11277 | PA-02-PR-4339-PW-11277 | FAASt Distribution Pole and Conductor Repair | 106941.99 | 27886.93 | 134828.92 | Distribution
11279 | PA-02-PR-4339-PW-11279 | FAASt Distribution Pole and Conductor Repair | 710014.69 | 191275.59 | 901290.28 | Distribution
11311 | PA-02-PR-4339-PW-11311 | FAASt Distribution Pole and Conductor Repair - | 338491 | 96676 | 435167 | Distribution
11312 | PA-02-PR-4339-PW-11312 | FAASt [Distribution Pole and Conductor Repair | 273996 | 29974 | 303970 | Distribution
11314 | PA-02-PR-4339-PW-11314 | FAASt Distribution Pole and Conductor Repair - | 486385 | 92244 | 578629 | Distribution
11317 | PA-02-PR-4339-PW-11317 | FAASt [Distribution Streetlighting - Gurabo] | 19208994 | 1533300 | 20742294 | Distribution
11318 | PA-02-PR-4339-PW-11318 | FAASt [San Germán Streetlighting] (Distributio | 30849348 | 4033578 | 34882926 | Distribution
11319 | PA-02-PR-4339-PW-11319 | FAASt Aguadilla Streetlight (Distribution) | 19796809 | 1295775 | 21092584 | Distribution
11326 | PA-02-PR-4339-PW-11326 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | 25277347 | 1009578 | 26286925 | Distribution
11340 | PA-02-PR-4339-PW-11340 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 320740 | 88558 | 409298 | Distribution
11344 | PA-02-PR-4339-PW-11344 | FAASt Streetlight Florida Distribution | 9311841.53 | 997190 | 10309031.53 | Distribution
11347 | PA-02-PR-4339-PW-11347 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | 2796182 | 3575881 | 6372063 | Substation
11350 | PA-02-PR-4339-PW-11350 | FAASt Physical Security - Group 2 (Substation) | 2159012.31 | 224680.68 | 2383692.99 | Substation
11351 | PA-02-PR-4339-PW-11351 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | 73737224.58 | 1849344.06 | 75586568.64 | Distribution
11352 | PA-02-PR-4339-PW-11352 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 438209.69 | 86181.92 | 524391.61 | Distribution
11365 | PA-02-PR-4339-PW-11365 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | 1464496 | 378483 | 1842979 | Distribution
11372 | PA-02-PR-4339-PW-11372 | FAASt [Physical Security - Group 3] (Substation) | 3696956.6 | 436383.23 | 4133339.83 | Substation
11385 | PA-02-PR-4339-PW-11385 | FAASt Substation Minor Repairs -Group B (Substation) | 2973035 | 439541 | 3412576 | Substation
11402 | PA-02-PR-4339-PW-11402 | FAASt [Costa Sur TC - Phase II &amp;amp; III ] (Substation) | 61444255.52 | 0 | 61444255.52 | Substation
11449 | PA-02-PR-4339-PW-11449 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | 642721 | 125133 | 767854 | Distribution
11465 | PA-02-PR-4339-PW-11465 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 1201420 | 224731 | 1426151 | Distribution
11478 | PA-02-PR-4339-PW-11478 | FAASt- Substation Minor Repairs Group C (Substation) | 2648259.06 | 384632.14 | 3032891.2 | Substation
11479 | PA-02-PR-4339-PW-11479 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | 8180049.03 | 7159883.3 | 15339932.33 | Substation
11489 | PA-02-PR-4339-PW-11489 | FAASt Centro Medico 1327/1359 Equipment Repair &amp;amp; Replacement (Substation) | 14795324 | 6537037 | 21332361 | Substation
11508 | PA-02-PR-4339-PW-11508 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 16, 17, 18 &amp;amp; 19] (Distribution) | 1764568.92 | 389437.84 | 2154006.76 | Distribution
11518 | PA-02-PR-4339-PW-11518 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | 9762754.59 | 853056.42 | 10615811.01 | Distribution
11522 | PA-02-PR-4339-PW-11522 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | 14918381.07 | 1965608.26 | 16883989.33 | Distribution
11524 | PA-02-PR-4339-PW-11524 | FAASt Coamo Streetlight (Distribution) | 14311922.45 | 2060901.35 | 16372823.8 | Distribution
11526 | PA-02-PR-4339-PW-11526 | FAASt Streetlight - Las Marías (Distribution) | 7073217 | 1287705 | 8360922 | Distribution
11532 | PA-02-PR-4339-PW-11532 | FAASt [Streetlighting - Mayagüez] (Distribution) | 11019180.1 | 1352204.36 | 12371384.46 | Distribution
11533 | PA-02-PR-4339-PW-11533 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | 14865613.02 | 1158946.56 | 16024559.58 | Distribution
11534 | PA-02-PR-4339-PW-11534 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 85296.74 | 2478.06 | 87774.8 | Distribution
11537 | PA-02-PR-4339-PW-11537 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 5962412.52 | 1701923.62 | 7664336.14 | Telecommunications
11540 | PA-02-PR-4339-PW-11540 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | 20710527 | 1176376 | 21886903 | Distribution
11555 | PA-02-PR-4339-PW-11555 | FAASt - EPC - [San Juan SP TC] (Substation) | 61558468.95 | 0 | 61558468.95 | Substation
11556 | PA-02-PR-4339-PW-11556 | FAASt - EPC - [Sabana Llana TC] (Substation) | 46643078.39 | 0 | 46643078.39 | Substation
11557 | PA-02-PR-4339-PW-11557 | FAASt - EPC - [Monacillo TC] (Substations) | 88096455.74 | 0 | 88096455.74 | Substation
11560 | PA-02-PR-4339-PW-11560 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | 13720208.31 | 2225873.62 | 15946081.93 | Distribution
11566 | PA-02-PR-4339-PW-11566 | FAASt [Physical Security - Group 4] (Substation) | 3478518 | 338280 | 3816798 | Substation
11573 | PA-02-PR-4339-PW-11573 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 6929384 | 0 | 6929384 | Substation
11583 | PA-02-PR-4339-PW-11583 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 332062581 | 544207595 | 876270176 | Telecommunications
11627 | PA-02-PR-4339-PW-11627 | FAASt [Morovis Streetlighting] (Distribution) | 13486398.85 | 1744482.27 | 15230881.12 | Distribution
11629 | PA-02-PR-4339-PW-11629 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | 8070964.96 | 1339801.28 | 9410766.24 | Distribution
11633 | PA-02-PR-4339-PW-11633 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | 13807923.4 | 1807601.11 | 15615524.51 | Distribution
11636 | PA-02-PR-4339-PW-11636 | FAASt [Toa Baja Streetlighting] (Distribution) | 9529190.37 | 620134.69 | 10149325.06 | Distribution
11639 | PA-02-PR-4339-PW-11639 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 7096249.5 | 195136.32 | 7291385.82 | Distribution
11640 | PA-02-PR-4339-PW-11640 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 5425810.57 | 165903.3 | 5591713.87 | Distribution
11650 | PA-02-PR-4339-PW-11650 | FAASt [Ceiba Streetlighting] (Distribution) | 5152111.14 | 716918.6 | 5869029.74 | Distribution
11652 | PA-02-PR-4339-PW-11652 | FAASt - EPC -Aguirre TC-Phase II (Substation) | 82726096.38 | 0 | 82726096.38 | Substation
11658 | PA-02-PR-4339-PW-11658 | FAASt [Naguabo Streetlighting] (Distribution) | 11620676.42 | 1669736.97 | 13290413.39 | Distribution
11664 | PA-02-PR-4339-PW-11664 | FAASt [Naranjito Streetlighting] (Distribution) | 11644048.43 | 2115538.38 | 13759586.81 | Distribution
11666 | PA-02-PR-4339-PW-11666 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 5629060 | 178712.97 | 5807772.97 | Distribution
11671 | PA-02-PR-4339-PW-11671 | FAASt [Arroyo Streetlighting] (Distribution) | 5314332 | 740394.01 | 6054726.01 | Distribution
11673 | PA-02-PR-4339-PW-11673 | FAASt [Vega Alta Streetlighting] (Distribution) | 12445015.33 | 1869089.52 | 14314104.85 | Distribution
11675 | PA-02-PR-4339-PW-11675 | FAASt [Barranquitas Streetlighting] (Distribution) | 9430329.22 | 1577046.09 | 11007375.31 | Distribution
11680 | PA-02-PR-4339-PW-11680 | FAASt [Culebra Streetlighting] (Distribution) | 1155804 | 153603 | 1309407 | Distribution
11682 | PA-02-PR-4339-PW-11682 | FAASt Substation Minor Repairs - Group D (Substation) | 2583133.54 | 288123.63 | 2871257.17 | Substation
11686 | PA-02-PR-4339-PW-11686 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 10313627 | 306131.37 | 10619758.37 | Distribution
11696 | PA-02-PR-4339-PW-11696 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 0 | 18151116.72 | 18151116.72 | Vegetation
11707 | PA-02-PR-4339-PW-11707 | FAASt [Substation Minor Repairs - Group E] (Substation) | 3924015.69 | 579767.52 | 4503783.21 | Substation
11711 | PA-02-PR-4339-PW-11711 | FAASt [Añasco Streetlighting] (Distribution) | 12087876.17 | 1820361.92 | 13908238.09 | Distribution
11712 | PA-02-PR-4339-PW-11712 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 4926640.11 | 147870.9 | 5074511.01 | Distribution
11714 | PA-02-PR-4339-PW-11714 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 4807675.47 | 13386633.34 | 18194308.81 | Vegetation
11715 | PA-02-PR-4339-PW-11715 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 6849050.26 | 19064883.85 | 25913934.11 | Vegetation
11716 | PA-02-PR-4339-PW-11716 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 1033375.81 | 84035.96 | 1117411.77 | Distribution
11718 | PA-02-PR-4339-PW-11718 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 3767690.42 | 10493001.48 | 14260691.9 | Vegetation
11719 | PA-02-PR-4339-PW-11719 | FAASt [T-Pole Program Line 100] (Transmission) | 94787.57 | 23372.71 | 118160.28 | Transmission
11723 | PA-02-PR-4339-PW-11723 | FAASt T-Pole Program Line 3700] (Transmission) | 303960.92 | 73393.66 | 377354.58 | Transmission
11724 | PA-02-PR-4339-PW-11724 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 7414164.75 | 20637925.62 | 28052090.37 | Vegetation
11725 | PA-02-PR-4339-PW-11725 | FAASt [Cidra Streetlighting] (Distribution) | 12812478.84 | 1838229.6 | 14650708.44 | Distribution
11726 | PA-02-PR-4339-PW-11726 | FAASt HV Equipment Replacement Group 2 (Substation) | 15413889.89 | 0 | 15413889.89 | Substation
11727 | PA-02-PR-4339-PW-11727 | FAASt [Comerio Streetlighting] (Distribution) | 6538769.44 | 862125.75 | 7400895.19 | Distribution
11734 | PA-02-PR-4339-PW-11734 | FAASt [Adjuntas Streetlighting] (Distribution) | 10742462 | 1891152 | 12633614 | Distribution
11735 | PA-02-PR-4339-PW-11735 | FAASt [Jayuya Streetlighting] (Distribution) | 7277670.2 | 1350541.32 | 8628211.52 | Distribution
11739 | PA-02-PR-4339-PW-11739 | FAASt [Salinas Streetlighting] (Distribution) | 12097203.53 | 1611020.9 | 13708224.43 | Distribution
11746 | PA-02-PR-4339-PW-11746 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 10940320.91 | 395663.43 | 11335984.34 | Distribution
11753 | PA-02-PR-4339-PW-11753 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 5461200.05 | 205587.38 | 5666787.43 | Distribution
11754 | PA-02-PR-4339-PW-11754 | FAASt [T-Pole Program Line 3000] (Transmission) | 559076.77 | 72117.49 | 631194.26 | Transmission
11764 | PA-02-PR-4339-PW-11764 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 17307539.01 | 0 | 17307539.01 | Substation
11839 | PA-02-PR-4339-PW-11839 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | 467287.6 | 0 | 467287.6 | Distribution
11850 | PA-02-PR-4339-PW-11850 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 11041271 | 409899.81 | 11451170.81 | Distribution
11667 | PA-02-PR-4339-PW-11667 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 6704421.6922 | 239376.93 | 6943798.6222 | Distribution
11812 | PA-02-PR-4339-PW-11812 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 13884126 | 377123.67 | 14261249.67 | Distribution
108001 | PA-02-PR-4339-PW-108001 | FAASt [Automation Program Group 20] (TL/Distribution) | 2623262.08 | 0 | 2623262.08 | Distribution
108000 | PA-02-PR-4339-PW-108000 | FAASt [Automation Program Group 19] (TL/Distribution) | 2753627.24 | 0 | 2753627.24 | Distribution
108022 | PA-02-PR-4339-PW-108022 | FAASt [Automation Program Group 15] (TL/Distribution) | 643560.85 | 0 | 643560.85 | Distribution
107956 | PA-02-PR-4339-PW-107956 | FAASt [Automation Program Group 14] (TL/Distribution) | 1640186.96 | 0 | 1640186.96 | Distribution
107957 | PA-02-PR-4339-PW-107957 | FAASt [Automation Program Group 12] (TL/Distribution) | 3664210.1 | 0 | 3664210.1 | Distribution
11721 | PA-02-PR-4339-PW-11721 | FAASt - [Taft - MC 1105] (Substations) | 9362729.93 | 4123842.4 | 13486572.33 | Substation
| TOTAL LUMA |  | 1714393436.3922 | 734259141.97 | 2448652578.3622 | 0

## ISOW_DSOW (hidden)
FAASt # | P/W # | LUMA Project Name | LUMA ID # | Program Brief | Asset | LUMA Improvement Program | Restoration / Improved / Alternate | 90 Day Plan | Latest DSOW Submission Date per 90 Day Plan | Current or Past Priority Project | Inactive | Withdrawn Category | Withdrawn Category Status | ISOW Date Submitted to Regulatory | ISOW PREB Cost Estimate | ISOW PREB Submittal Target Date | PREB ISOW Approval Date | Resubmittal Target Date for Withdrawn Projects | ISOW PREB 30 Day Auto Date | Date Revised ISOW Received from CP | Date ISOW Sent Back to CP for Revision | # ISOW Submitted | Initial DSOW Expected Date per 90 Day Plan | ISOW - Date submitted to FEMA | Date FAASt Project Created | Initial DSOW Submission | Latest DSOW Revision | FEMA Internal EHP Deadline Date (ECD) | Date FEMA Internal EHP Deadline Posted | EHP Comments | # DSOW Submitted | ISOW Cost Estimate | FEMA Best Available Cost | 406 Cost Estimate | A&E Cost Estimate | 428 Cost Estimate | 406 A&E | 406 CE - 406 A&E | Luma Expected Cost (428+406) | Total LUMA Expected Cost (406+428+A&E) | Earliest Expected Obligation Date | Latest Expected Obligation Date | Initial Date Obligated | Last Date Obligated | Obligated Amount - V0 CRC Net Cost | Obligated Amount - V0 CRC Gross Cost | Obligated Amount - V1 CRC Net Cost | Obligated Amount - V1 CRC Gross Cost | Obligated Amount - V2 CRC Net Cost | Obligated Amount - V2 CRC Gross Cost | Approved Obligated Amount - CRC Net Cost Cal | Approved Obligated Amount - CRC Gross Cost Cal | PoP Expiration Date | Document Path | Notes | Modified | Created | Created By | For Jeremy | Modified By | ObligationEstimatingFormulaResult | ObligationEstimatingFormulaResultLookUp | 428 A&E Obligated Cost | 406 A&E Obligated Cost | Scope Change | Scope Change Score | Date Inactivated | RFIFAASt | Title | Item Type | Path
727694 | 107903 | FAASt [Region 4 -Caguas Group C] (Vegetation) | 15F019480000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/4/2023 | 2023-07-31 | 2023-12-11 |  |  |  | 1 |  | 41689596.63 | 76781710.48 |  |  |  | 76781710.48 | 76781710.48 | 76781710.48 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%204_%20Caguas%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.54296 | 3 | 2025-07-07 | 727694RFI1 | 727694 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727692 | 11724 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 14F019450000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Current | [12 empty] | 2023-07-31 | 2023-07-31 | 8/4/2023 | 2023-08-04 | 2024-11-18 | 2025-03-30 | 2025-03-12 |  |  | 4681848.01 | 4681848.01 | 46038244.43 |  |  | 328143.02 | 45710101.41 | 46038244.43 | 46038244.43 | 2024-09-30 | 2024-12-31 | 2025-04-28 |  | 28052090.37 | 7414164.75 |  |  |  |  | 28052090.37 | 7414164.75 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/2/38kV%20and%20below%20DSOW-%20Region%204_%20Caguas%20(1)%20(1).pdf?web=1 | 18JULY2024 Project was split into High and Low Density which reduced the total miles in the previous submittal for this project. So if the High and Low Density project values are added together, it will equate to the original submission total. 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.10169 | 5 |  | 727692RFI2 | 727692 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727691 | 107902 | FAASt [Region 1 -San Juan Group C] (Vegetation) | 15F019330000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Past | [12 empty] | 2023-07-31 | 2023-07-31 | 8/4/2023 | 2023-07-31 | 2023-12-11 | [5 empty] | 18245048.09 | 44200121.5 |  |  |  | 44200121.5 | 44200121.5 | 44200121.5 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/3/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%201%20San%20Juan%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.41278 | 3 |  | 727691RFI3 | 727691 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727659 | 107901 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 15F019560000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/4/2023 | 2023-07-31 | 2025-06-27 | [5 empty] | 18075945.32 | 54305563.22 | 1517338.23 | 18265704.46 | 54305563.22 | 0 | 72571267.68 | 74088605.91 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/4/115kV%20DSOW%20Region%202%20-%20Arecibo%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.24908 | 4 | 2025-07-07 | 727659RFI4 | 727659 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727657 | 107900 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 15F019410000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/4/2023 | 2023-07-31 | 2025-06-27 | [5 empty] | 16212759.99 | 91765278.3 | 2563990.79 | 30865299.08 | 7035375.59 | 84729902.71 | 122630577.38 | 125194568.17 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/5/115kV%20DSOW%20Region%205%20-%20Mayaguez%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.13221 | 5 | 2025-07-07 | 727657RFI5 | 727657 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727608 | 107899 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 15F019310000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE | [14 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-07-31 | 2025-06-27 | [5 empty] | 18605239.31 | 24398735.91 | 681719.03 | 8206527.54 | 1870579.69 | 22528156.22 | 32605263.45 | 33286982.48 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/6/115kV%20DSOW%20Region%201%20-%20San%20Juan%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.57062 | 3 |  | 727608RFI6 | 727608 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727606 | 107898 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 15F019460000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-07-31 | 2025-06-27 | [5 empty] | 16306957.02 | 109548711.44 | 3060873.27 | 36846766.07 | 8398779.43 | 101149932.01 | 146395477.51 | 149456350.78 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/7/115kV%20DSOW%20Region%204%20-%20Caguas.docx?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.11139 | 5 | 2025-07-07 | 727606RFI7 | 727606 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727572 | 11720 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 15F019880000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Current | [12 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-08-03 | 2024-11-18 | 2025-03-30 | 2025-03-12 |  |  |  | 8173601.57 | 80353343.34 |  |  | 698724.72 | 79654618.62 | 80353343.34 | 80353343.34 | 2024-08-31 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/8/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%203_%20Bayamon%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.10172 | 5 |  | 727572RFI8 | 727572 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727562 | 107897 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | 15F019430000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-07-31 | 2023-12-11 | [5 empty] | 34961938.79 | 84411128.06 |  |  |  | 84411128.06 | 84411128.06 | 84411128.06 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/9/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%205_%20Mayaguez%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.41419 | 3 | 2025-07-07 | 727562RFI9 | 727562 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727558 | 107896 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | 15F019530000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-07-31 | 2023-12-11 | [5 empty] | 16458603.47 | 16374246.76 |  |  |  | 16374246.76 | 16374246.76 | 16374246.76 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/10/115kV%20DSOW%20Region%203%20%20Bayamon%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1.0052 | 1 | 2025-07-07 | 727558RFI10 | 727558 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727540 | 107895 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | 15F019580000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-07-31 | 2023-12-11 | [5 empty] | 42848782.64 | 66510486.76 |  |  |  | 66510486.76 | 66510486.76 | 66510486.76 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/11/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%202_%20Arecibo%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.64424 | 2 | 2025-07-07 | 727540RFI11 | 727540 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727531 | 11715 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 14F019350000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Current | [12 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-08-03 | 2024-11-18 | 2025-03-21 | 2025-03-14 |  |  |  | 4324993.22 | 42520736.92 |  |  | 369745.52 | 42150991.4 | 42520736.92 | 42520736.92 | 2024-09-30 | 2024-12-31 | 2025-04-28 |  | 25913934.11 | 6849050.26 |  |  |  |  | 25913934.11 | 6849050.26 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/12/38kV%20and%20below%20DSOW-%20Region%206_%20Ponce%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  | 0 |  | 0.10171 | 5 |  | 727531RFI12 | 727531 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727530 | 107894 | FAASt [Region 6 -Ponce Group C] (Vegetation) | 15F019380000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-07-31 | 2023-12-11 | [5 empty] | 32605348.76 | 70421923.26 |  |  |  | 70421923.26 | 70421923.26 | 70421923.26 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/13/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%206_%20Ponce%20(1)%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.463 | 3 | 2025-07-07 | 727530RFI13 | 727530 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727529 | 107893 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 15F019360000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-07-31 | 8/3/2023 | 2023-07-31 | 2025-06-27 | [5 empty] | 20674478.43 | 54461273.75 | 1521688.89 | 18318077.75 | 4175386.61 | 50285887.14 | 72779351.5 | 74301040.39 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/14/115kV%20DSOW%20Region%206%20%20Ponce%20(1)%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.28407 | 4 | 2025-07-07 | 727529RFI14 | 727529 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
727522 | 107892 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 15F019510000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-07-31 | 2023-08-03 | 8/3/2023 | 2023-07-31 | 2025-06-27 | [5 empty] | 102855378 | 53608045.16 | 1497849.05 | 18031093.89 | 4109972.07 | 49498073.09 | 71639139.05 | 73136988.1 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/15/38kV%20and%20below%20DSOW-%20Region%203_%20Bayamon%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1.4357 | 1 | 2025-07-07 | 727522RFI15 | 727522 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724941 | 11733 | FAASt [Aguas Buenas Streetlighting] (Distribution) | 14F018000000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-08-03 | 7/7/2023 | 2024-02-28 | 2024-04-09 |  |  |  |  | 8126825 | 11260820.47 | 1686477 | 2317060 | 11260820 | 287979 | 1398498 | 12947297 | 15264357 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/16/724941-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Aguas%20Buenas.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.86974 | 1 |  | 724941RFI16 | 724941 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724938 | 11673 | FAASt [Vega Alta Streetlighting] (Distribution) | 14F018120000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-01-31 | 2023-06-23 | 7/7/2023 | 2024-01-22 | [5 empty] | 11756915 | 14314104.85 | 1869090 | 2459743 | 12445015 | 537278.89 | 1331811.11 | 14314105 | 16773848 | 2024-06-30 | 2024-07-31 | 2024-05-10 |  | 14314104.85 | 12445015.33 |  |  |  |  | 14314104.85 | 12445015.33 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/17/724938-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Vega%20Alta%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2459742.66 |  | 1 | 1 |  | 724938RFI17 | 724938 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724828 | 11692 | FAASt [Loiza Streetlighting] (Distribution) | 14F018060000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-01-31 | 2023-07-01 | 7/6/2023 | 2024-01-19 | [5 empty] | 5620918 | 6696269.82 | 816844 | 1653580 | 6696270 | 161766 | 655078 | 7513114 | 9166694 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/18/724828-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Lo%C3%ADza%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89128 | 1 |  | 724828RFI18 | 724828 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724825 | 11725 | FAASt [Cidra Streetlighting] (Distribution) | 14F018030000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-02-29 | 2023-07-01 | 7/6/2023 | 2024-02-28 | 2024-04-09 |  |  |  |  | 11213219 | 14650708.44 | 1838230 | 2516456 | 12812479 | 526932.49 | 1311297.51 | 14650709 | 17167165 | 2024-06-30 | 2024-08-31 | 2024-05-10 |  | 14650708.44 | 12812478.84 |  |  |  |  | 14650708.44 | 12812478.84 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/19/1336051-DR4339PR-FEMA iSOW Distribution Streetlighting - Cidra (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2516455.74 |  | 1 | 1 |  | 724825RFI19 | 724825 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724781 | 11736 | FAASt [Penuelas Streetlighting] (Distribution) | 14F018080000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/6/2023 | 2024-02-28 | 2025-07-02 |  |  |  |  | 5702676 | 7948618.17 | 408490.41 | 1433020.87 | 8327919.73 | 63060.64 | 345429.77 | 8736410.14 | 10169431.01 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/20/[724781] DR4339PR FAASt Penuelas Streetlighting (Distribution) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.90983 | 1 |  | 724781RFI20 | 724781 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724716 | 11729 | FAASt [Quebradillas Streetlighting] (Distribution) | 14F018090000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/5/2023 | 2024-02-28 | 2025-07-02 |  |  |  |  | 7787526 | 10455022.32 | 628110.03 | 1872541.02 | 11144397.5 | 95914.82 | 532195.21 | 11772507.53 | 13645048.55 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/21/1335655 DR4339PR FEMA iSOW Distribution Streetlighting - Quebradillas (3) (1) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88809 | 1 |  | 724716RFI21 | 724716 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724703 | 11671 | FAASt [Arroyo Streetlighting] (Distribution) | 14F017990000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2023-12-31 | 2023-07-01 | 7/5/2023 | 2023-12-28 | [5 empty] | 6119646 | 6054726.01 | 740394 | 1504203 | 5314332 | 250928.85 | 489465.15 | 6054726 | 7558929 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 6054726.01 | 5314332 |  |  |  |  | 6054726.01 | 5314332 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/22/724709 DR4339PR iSOW Distribution Streetlighting - Arroyo (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1504203.15 |  | 1 | 1 |  | 724703RFI22 | 724703 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724698 | 11734 | FAASt [Adjuntas Streetlighting] (Distribution) | 14F017980000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/5/2023 | 2024-02-28 | 2024-04-09 |  |  |  |  | 7264269 | 12633614 | 1891152 | 2199844 | 10742462 | 552275 | 1338877 | 12633614 | 14833458 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 12633614 | 10742462 |  |  |  |  | 12633614 | 10742462 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/23/724698 DR4339PR FEMA iSOW Distribution Streetlighting - Adjuntas (1).pdf | QC Review Complete: 2/28/2024 | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2199843.63 |  | 1 | 1 |  | 724698RFI23 | 724698 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724670 | 11731 | FAASt [Patillas Streetlighting] (Distribution) | 14F018070000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/5/2023 | 2024-02-28 | 2025-07-02 |  |  |  | 5 | 7603568 | 8375887.52 | 406586.59 | 1456883.53 | 8833912.82 | 60595.15 | 345991.44 | 9240499.41 | 10697382.94 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/24/[724670] DR4339PR FAASt Patillas Streetlighting ISOW (Distribution) (1) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.90643 | 1 |  | 724670RFI24 | 724670 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724669 | 11730 | FAASt [Ciales Streetlighting] (Distribution) | 14F018020000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/5/2023 | 2024-02-28 | 2025-07-02 | 2025-08-14 | 2025-07-23 |  |  | 7227478 | 10780496.72 | 773133.74 | 2044738.82 | 12755671.42 | 113108.63 | 660025.11 | 13528805.16 | 15573543.98 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/25/1335558-DR4339PR-SOW (1) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-23 15:59 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.79686 | 2 |  | 724669RFI25 | 724669 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724605 | 11732 | FAASt [Guayanilla Streetlighting] (Distribution) | 14F018040000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/3/2023 | 2024-02-28 | 2025-07-02 |  |  |  |  | 5831446 | 7949936.1 | 469904.54 | 1372729.11 | 8219229.32 | 71428.54 | 398476 | 8689133.86 | 10061862.97 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/26/1335512-DR4339PR-SOW (4) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.91493 | 1 |  | 724605RFI26 | 724605 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724603 | 11684 | FAASt [Cabo Rojo Streetlighting] (Distribution) | 14F018010000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-01-31 | 2023-07-01 | 7/3/2023 | 2024-01-19 | [5 empty] | 20517371 | 9017148.04 | 1044683 | 2012276 | 9017148 | 190599 | 854084 | 10061831 | 12074107 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/27/1335511-DR4339PR-SOW (2) (1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89617 | 1 |  | 724603RFI27 | 724603 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724601 | 11739 | FAASt [Salinas Streetlighting] (Distribution) | 14F018110000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/3/2023 | 2024-02-28 | 2024-04-09 |  |  |  |  | 13130463 | 13708224.43 | 1611021 | 2463886 | 12097204 | 469330.38 | 1141690.62 | 13708225 | 16172111 | 2024-06-30 | 2024-08-31 | 2024-07-08 |  | 13708224.43 | 12097203.53 |  |  |  |  | 13708224.43 | 12097203.53 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/28/1335509-DR4339PR-SOW (2) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2463885.54 |  | 1 | 1 |  | 724601RFI28 | 724601 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724600 | 11735 | FAASt [Jayuya Streetlighting] (Distribution) | 14F018050000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/3/2023 | 2024-02-28 | 2024-04-09 |  |  |  |  | 5077221 | 8628211.52 | 1350541 | 1704126 | 7277670 | 419107.52 | 931433.48 | 8628211 | 10332337 | 2024-06-30 | 2024-08-31 | 2024-05-31 |  | 8628211.52 | 7277670.2 |  |  |  |  | 8628211.52 | 7277670.2 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/29/1335507-DR4339PR-SOW (2) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1704125.72 |  | 1 | 1 |  | 724600RFI29 | 724600 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
724599 | 11738 | FAASt [Sabana Grande Streetlighting] (Distribution) | 14F018100000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-02-29 | 2023-07-01 | 7/3/2023 | 2024-02-28 | 2025-07-02 |  |  |  |  | 7576997 | 10744021.82 | 725698.37 | 1906868.06 | 11479468.51 | 110216.6 | 615481.77 | 12205166.88 | 14112034.94 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/30/1335504-DR4339PR-SOW (2) (1).pdf | 2/28/2024: QC Review Complete 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88028 | 1 |  | 724599RFI30 | 724599 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
723883 | 11696 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 15F019300000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | 406 | FALSE |  | Past |  |  |  |  | 1200000000 | 2023-04-24 | 2023-05-05 |  | 2023-05-24 |  |  |  | 2023-06-30 | 2023-05-10 | 6/26/2023 | 2023-07-18 | 2025-01-28 | 2025-04-04 | 2025-03-17 |  |  | 1200000000 | 18151116.72 | 145069437.94 |  |  | 23074.58 | 145046363.36 | 145069437.94 | 145069437.94 | 2024-06-30 | 2024-08-31 | 2024-06-05 | 01/28/2025 | 18151116.72 | 0 | 18151116.72 | 0 | 24989414.28 | 0 | 24989414.28 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/31/38kV%20and%20below%20DSOW-%20Region%201%20San%20Juan%20(1).pdf?web=1 | Project advancing in the project process flow. Refer to Process Status History for more details. | 2025-07-29 10:17 | 2023-08-14 11:09 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Maria Mujica Gonzalez | 0 Months |  | 0 |  | 0.12512 | 5 |  | 723883RFI31 | 723883 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
723078 | 11555 | FAASt - EPC - [San Juan SP TC] (Substation) | 14F009040000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 89700000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 |  |  |  | 2023-06-30 | 2023-06-16 | 6/16/2023 | 2023-06-16 | 2023-10-31 |  |  |  |  | 89700000 | 61558468.95 |  | 3713097 | 61558469 | 0 | 0 | 61558469 | 65271566 |  |  | 2023-12-19 |  | 61558468.95 | 61558468.95 |  |  |  |  | 61558468.95 | 61558468.95 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/32/723078%20-%20DR-4339PR-%20San%20Juan%20SP%20Transmission%20Center%20-%20FEMA%20Detailed%20Scope%20of%20Work%208.15.23%20rev.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | San Juan SP TC | Rey Roldan Rodríguez |  |  | 3713096.54 |  | 1 | 1 |  | 723078RFI32 | 723078 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
723077 | 11556 | FAASt - EPC - [Sabana Llana TC] (Substation) | 14F009060000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE |  | Past |  |  |  |  | 125500000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 |  |  |  | 2023-06-30 | 2023-06-16 | 6/16/2023 | 2023-06-16 | 2025-04-11 | 2025-03-11 | 2025-02-25 |  |  | 125500000 | 100686731.41 | 0 | 583002.82 | 3281329.98 | 0 | 0 | 3281329.98 | 3864332.8 |  |  | 2023-12-19 | 04/28/2025 | 100686731.41 | 100686731.41 | 46643078.39 | 46643078.39 |  |  | 46643078.39 | 46643078.39 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/33/723077-%20Sabana%20LLana%20FEMA%20Detailed%20Scope%20of%20Work%209.15.23%20rev.pdf | 4/24/2024: QC Review Complete | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Sabana Llana TC | Rey Roldan Rodríguez |  |  | 4850983.03 |  | 30.6847 | 1 |  | 723077RFI33 | 723077 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
723002 | 107888 | FAASt - EPC - Jobos TC (Substation) | 14F009050000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 42900000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 |  |  |  | 2023-06-30 | 2023-06-16 | 6/15/2023 | 2023-06-15 | 2024-11-26 | 2025-07-30 | 2025-07-24 | Field EHP: RFI response received on 7/23/2025 under EHP specialist revision. Expected Completion Date (ECD) 7/30/2025. |  | 42900000 | 70090705.72 | 0 | 6191932.29 | 69904580.54 | 0 | 0 | 69904580.54 | 76096512.83 | 2025-02-28 | 2025-05-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/34/723002%20-DR-4339PR-%20Jobos%20TC%20-%20FEMA%20Project%20Detailed%20Scope%20of%20Work%20rev%208.17.23%20(2).pdf |  | 2025-07-28 16:00 | 2023-08-14 11:09 | Jahdiel Franqui | Jobos TC | Maria Mujica Gonzalez | 0 Months |  |  |  | 1.0027 | 1 |  | 723002RFI34 | 723002 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
718971 | 107884 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | 14F015610000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 173630000 | 2023-04-27 | 2023-05-05 |  | 2023-05-27 |  |  |  | 2023-07-31 | 2023-05-09 | 5/11/2023 | 2023-07-11 | 2023-08-07 |  |  |  |  | 917700007 | 917523716 | 901810364 | 176291 | 15713352 | 10005336 | 891805028 | 917523716 | 917700007 | 2025-05-31 | 2025-10-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/35/718971-DR4339-PR%20DSOW-0001_Rev1%20-%20T%20Line%2050300%20from%20Costa%20Sur%20SP%20to%20Aguirre%20SP%20-%20signed%20(2).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Line 50300 from Costa Sur Steam Plant to Aguirre Steam Plant | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 718971RFI35 | 718971 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
718955 | 107883 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) | 14F015630000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 279240000 | 2023-04-27 | 2023-05-05 |  | 2023-05-27 |  |  |  | 2023-07-31 | 2023-05-09 | 5/11/2023 | 2023-07-11 | 2023-10-31 |  |  |  |  | 279240000 | 219184721 | 88423396 | 6123395 | 146779642 | 4590570 | 83832826 | 235203038 | 241326433 | 2025-05-31 | 2025-10-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/36/718955-DR4339PR-DSOW-0001_Rev1-%20Line%2050200%20from%20Costa%20Sur%20SP%20to%20Bayamon%20TC%20-%20signed.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Line 50200 from Costa Sur SP to Bayamon TC | Rey Roldan Rodríguez |  |  |  |  | 0.9319 | 1 |  | 718955RFI36 | 718955 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
718951 | 107882 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | 14F015620000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 161130000 | 2023-04-27 | 2023-05-05 |  | 2023-05-27 |  |  |  | 2023-07-31 | 2023-05-09 | 5/11/2023 | 2023-07-11 | 2023-10-31 |  |  |  |  | 161140000 | 143758497 | 64652304 | 4748151 | 91592573 | 3186387 | 61465917 | 156244877 | 160993028 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/37/718951-DR4339PR-DSOW-0001_Rev1%20-%20Line%2051200%20from%20Costa%20Sur%20SP%20to%20Cambalache%20GP%207723%20-%20signed%20(1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Line 51200 from Costa Sur Steam Plant to Cambalache Gas Plant | Rey Roldan Rodríguez |  |  |  |  | 0.92008 | 1 |  | 718951RFI37 | 718951 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
715610 | 107877 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) |  | PBUT13 - T Priority Pole Repl | Transmission | PREB Mandate | Restoration | FALSE |  | Past |  |  |  |  | 78300000 | 2023-01-30 | 2023-02-22 |  | 2023-03-01 |  |  |  |  | 2023-01-10 | 4/28/2023 | 2023-11-21 | [5 empty] | 78300000 | 118409122.46 | 0 | 26336371 | 118409122 | 0 | 0 | 118409122 | 144745493 | 2024-07-31 | 2024-10-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/38/[715610] FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | PREB Mandate | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 715610RFI38 | 715610 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
714654 | 11583 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 14F000000000 | PBUT36 - AMI Implementation Prog | Telecommunications | AMI Implementation Program | Restoration | FALSE | [6 empty] | 780000000 | 2023-03-29 | 2023-04-05 |  | 2023-04-28 |  |  |  | 2023-07-31 | 2023-04-18 | 4/20/2023 | 2023-07-11 | 2023-12-15 |  |  |  |  | 780000000 | 876270176 | 544207595 | 16450923 | 317095666 | 2421276 | 541786319 | 861303261 | 877754184 |  |  | 2023-12-08 | 05/01/2024 | 873848901 | 873848901 | 332062581 | 332062581 | 876270176 | 332062581 | 876270176 | 332062581 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/39/714654-DR4339PR-DSOW%20AMI%20V2%20(2).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Advanced Metering Infrastructure (AMI) | Rey Roldan Rodríguez |  |  | 1484008 |  | 1.0174 | 1 |  | 714654RFI39 | 714654 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
714641 | 11630 | FAASt [Rincón Streetlighting] (Distribution) | 14F017260000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2023-10-31 | 2023-04-19 | 4/20/2023 | 2023-12-01 | 2025-06-18 | 2025-07-31 | 2025-07-08 |  |  | 6614287 | 10689504.94 | 694470.58 | 1946225.97 | 11592957.26 | 106422.03 | 588048.55 | 12287427.84 | 14233653.81 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/40/[714641] FAASt [Distribution Streetlighting - Rincón] (Distribution)iSOW (2) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.86995 | 1 |  | 714641RFI40 | 714641 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713795 | 11624 | FAASt [Lares Streetlighting] (Distribution) | 14F017010000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2023-12-31 | 2023-04-03 | 4/12/2023 | 2023-12-01 | 2025-07-02 |  |  |  |  | 5994964 | 11909808.29 | 712022.01 | 1974624.75 | 12615988.1 | 101922.08 | 610099.93 | 13328010.11 | 15302634.86 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/41/[713795] DR4339PR- FEMA iSOW Distribution Streetlighting - Lares (Distribution).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89359 | 1 |  | 713795RFI41 | 713795 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713592 | 107874 | FAASt [Telecom Infrastructure – Group F] (Telecommunications) | 14F019040000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2024-11-14 | [5 empty] | 2023-04-05 | 4/11/2023 | [6 empty] | 4600000 | 4600000 |  |  |  |  | 0 | 4600000 | 4600000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/42/713592-DR4339PR-Telecom Infrastructure.pdf | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date 5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 11/15/2024. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713592RFI42 | 713592 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713497 | 107873 | FAASt [Substation Minor Repairs - Group C-1] |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-04-05 | 4/10/2023 | [6 empty] | 2800000 | 2800000 |  |  |  |  | 0 | 2800000 | 2800000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/43/1313998-DR4339PR-FEMA Initial Scope of Work - Substation Minor Repairs - Group C-1 Rev0 (2) (2).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713497RFI43 | 713497 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713496 | 107872 | FAASt [Substation Minor Repairs - Group - H] (Substations) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-04-05 | 4/10/2023 | [6 empty] | 3500000 | 3500000 |  |  |  |  | 0 | 3500000 | 3500000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/44/[713496] DR4339PR FAASt [Substation Minor Repairs - Group H] (Substations) Initial SOW CE (2).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713496RFI44 | 713496 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713491 | 107871 | FAASt [Substation Minor Repairs - Group A-1] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-04-05 | 4/10/2023 | [6 empty] | 3800000 | 3800000 |  |  |  |  | 0 | 3800000 | 3800000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/45/713491-DR4339PR-FEMA Initial Scope of Work - Substation Minor Repairs - Group A-1 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713491RFI45 | 713491 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713459 | 107870 | FAASt [Substation Minor Repairs - Group A-2] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-04-05 | 4/10/2023 | [6 empty] | 3450000 | 3450000 |  |  |  |  | 0 | 3450000 | 3450000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/46/713459-DR4339PR-Substation Minor Repairs - Group A-2 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713459RFI46 | 713459 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713181 | 107869 | FAASt [ Substation Minor Repairs - Group E-2] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-04-05 | 4/5/2023 | [6 empty] | 2600000 | 2600000 |  |  |  |  | 0 | 2600000 | 2600000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/47/713181-FEMA Initial Scope of Work - Substation Minor Repairs - Group E-2 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713181RFI47 | 713181 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713179 | 107868 | FAASt [ Minor Repairs - Group D-1] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-04-05 | 4/5/2023 | [6 empty] | 1800000 | 1800000 |  |  |  |  | 0 | 1800000 | 1800000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/48/FEMA Project Scope of Work - Substation Minor Repairs - Group D-1 Rev0.pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713179RFI48 | 713179 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
713149 | 107867 | FAASt [Substation Minor Repairs - Group E-1] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-04-05 | 4/5/2023 | [6 empty] | 2000000 | 2000000 |  |  |  |  | 0 | 2000000 | 2000000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/49/FEMA Initial Scope of Work - Substation Minor Repairs - Group E-1 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 713149RFI49 | 713149 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712988 | 107866 | FAASt [Minor Protection, Automation, and Control (PAC) Replacement] (Substation) |  | PBUT07 - Substation Reliability | Substation | Substation Reliability |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created |  | 70500000 |  |  | 2024-04-15 |  |  |  |  | 2024-03-31 | 2023-03-09 | 4/4/2023 | [6 empty] | 70500000 | 70500000 |  |  |  |  | 0 | 70500000 | 70500000 | [10 empty] | 0 | 0 |  | Automation,, and Control (PAC) Replacement (1).pdf, https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/50/712988-DR4339PR-Minor Protection, Automation, and Control (PAC) Replacement (1).pdf | 4/8/2024 - Email notification received from Kevin Smeltzer for this FAASt #, placed under a new FAASt # 7466604/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. DSOW for Group 1 we tried to submitted in March 28, but project is withdrawn from GP. DSOW Group 1 is ready to be submitted, as soon the project are active in GP. 3/27/2024: QC Review Complete | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Substation Reliability | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 712988RFI50 | 712988 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712982 | 107865 | FAASt [Distribution Pole and Conductor Repair – Mayaguez Group 23] (Distribution) | 14F017000000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-03-29 | 4/4/2023 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/51/FEMA Project Scope of Work Distribution Pole and Conductor Repair -Mayaguez Group 23.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 712982RFI51 | 712982 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712981 | 107864 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) | 14F016960000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-03-29 | 4/4/2023 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/52/FEMA Project Scope of Work Distribution Pole and Conductor Repair - Ponce Group 24.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 712981RFI52 | 712981 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712980 | 11754 | FAASt [T-Pole Program Line 3000] (Transmission) | 14F017350000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | Restoration | FALSE |  | Past | [12 empty] | 2023-12-31 | 2023-03-09 | 4/4/2023 | 2024-01-26 | 2024-03-07 |  |  |  |  | 616000 | 631194.26 | 72118 | 72788 | 559077 | 13981.67 | 58136.33 | 631195 | 703983 | 2024-08-31 | 2024-11-30 | 2024-11-01 |  | 631194.26 | 559076.77 |  |  |  |  | 631194.26 | 559076.77 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/53/1312596-DR4339PR-FEMA Scope of Work Line 3000 Caguax Sect - Juncos TC.DOC (1) (1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 72787.96 |  | 1 | 1 |  | 712980RFI53 | 712980 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712979 | 107863 | FAASt [TL 12600 Humacao TC to Verde Mar] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-03-09 | 4/4/2023 | [6 empty] | 539000 | 539000 |  |  |  |  | 0 | 539000 | 539000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/54/[712979] DR4339 FAASt [TL 12600 Humacao TC to Verde Mar] (Transmission) Initial SOW and Cost Estimate.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 712979RFI54 | 712979 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712978 | 107862 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) | 14F017340000 |  | Transmission | Transmission – Pole Replacement |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2024-04-10 | [5 empty] | 2023-03-09 | 4/4/2023 | [6 empty] | 1848000 | 1848000 |  |  |  |  | 0 | 1848000 | 1848000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/55/712978-DR4339PR-Scope of Work L2000 Once de Agosto Sect. - San Sebastian TC.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 712978RFI55 | 712978 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712977 | 107861 | FAASt [L3000 Caguas TC - Caguax Sect] (Transmission) | 14F017350000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-12-31 | 2023-03-09 | 4/4/2023 | [6 empty] | 154000 | 154000 |  |  |  |  | 0 | 154000 | 154000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/56/[712977] DR4339PR FAASt [L3000 Caguas TC - Caguax Sect] Initial SOW CE.pdf | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided.". | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 712977RFI56 | 712977 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712968 | 11666 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 14F016510000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE |  | Past | [12 empty] | 2023-10-31 | 2023-03-29 | 4/4/2023 | 2023-11-01 | 2024-05-01 |  |  |  |  | 3000000 | 5807772.97 | 178713 | 503551 | 5629060 | 35903.97 | 142809.03 | 5807773 | 6311324 | 2024-06-30 | 2024-11-30 | 2024-11-01 |  | 5807772.97 | 5629060 |  |  |  |  | 5807772.97 | 5629060 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/57/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Arecibo%20Group%202%20-%20Phase%202%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 503550 |  | 1 | 1 |  | 712968RFI57 | 712968 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
712963 | 107860 | FAASt [Mayaguez GP - Leon Sect 38kV Line 1600] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-03-09 | 4/4/2023 | [6 empty] | 231000 | 231000 |  |  |  |  | 0 | 231000 | 231000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/58/712963-DR4339PR-Project Scope of Work L1600 Mayaguez GP - Leon Sect.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 712963RFI58 | 712963 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711962 | 107859 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) | 14F016950000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-03-29 | 4/4/2023 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/59/711962-DR4339PR-Project Scope of Work Distribution Pole and Conductor Repair -Mayaguez Group 21.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 711962RFI59 | 711962 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711909 | 107858 | FAASt [ TL100 Jobos TC to Guayama TO] (Transmission) | 14F017290000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-12-31 | 2023-03-09 | 4/3/2023 | [6 empty] | 231000 | 231000 |  |  |  |  | 0 | 231000 | 231000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/60/711909-DR4339PR-FEMA Scope of Work TL100 Jobos TC to Guayama TO.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 711670. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 711909RFI60 | 711909 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711888 | 11640 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 14F016970000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-09-30 | 2023-03-29 | 4/3/2023 | 2023-10-05 | 2023-12-12 |  |  |  |  | 3000000 | 5591713.87 | 165903 | 434785 | 5425810 | 0 | 165903 | 5591713 | 6026498 | 2024-06-30 | 2024-08-31 | 2024-03-22 |  | 5591713.87 | 5425810.57 |  |  |  |  | 5591713.87 | 5425810.57 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/61/711888-DR4339PR-FEMA SOW Distribution Pole and Conductor Repair - Caguas Group 1 - Phase 2.pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 434784.65 |  | 1 | 1 |  | 711888RFI61 | 711888 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711862 | 107857 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) | 14F017300000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-03-09 | 4/3/2023 | [6 empty] | 1232000 | 1232000 |  |  |  |  | 0 | 1232000 | 1232000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/62/711862 DR4339PR- FAASt FEMA Scope of Work TL100 Ponce TC to Santa Isabel Sect.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 711862RFI62 | 711862 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711856 | 11746 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 14F016980000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE |  | Past | [12 empty] | 2023-11-30 | 2023-03-29 | 4/3/2023 | 2023-12-01 | 2023-12-11 |  |  |  |  | 3000000 | 11335984.34 | 395663 | 891094 | 10940321 | 67251.43 | 328411.57 | 11335984 | 12227078 | 2024-06-30 | 2024-11-30 | 2024-08-26 | 12/16/2024 | 11335984.34 | 10940320.91 | 11335984.34 | 10940320.91 |  |  | 11335984.34 | 10940320.91 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/63/711856-DR4339PR-FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%203%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 891093.89 |  | 1 | 1 |  | 711856RFI63 | 711856 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711829 | 107856 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) | 14F017310000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-03-09 | 4/3/2023 | [6 empty] | 1309000 | 1309000 |  |  |  |  | 0 | 1309000 | 1309000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/64/711829-DR4339PR-Project Scope of Work L100 Santa Isabel Sect. - Salinas Sect..DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 711829RFI64 | 711829 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711819 | 11840 | FAASt [TL 13400 TC-San German Sect-La Parguera Sect] (Transmission) | 14F017330000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | Restoration | FALSE |  | Current | [12 empty] | 2023-12-31 | 2023-03-09 | 4/3/2023 | 2023-12-21 | 2025-07-14 | 2025-04-02 | 2025-03-18 |  |  | 1617000 | 1804189 | 332405.64 | 271489.55 | 2124155.13 | 37653.59 | 294752.05 | 2456560.77 | 2728050.32 | 2025-04-30 | 2025-07-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/65/711819 DR4339PR-FAASt TL 13400 TC-San German Sect-La Parguera Sect.DOC.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 0.73444 | 2 |  | 711819RFI65 | 711819 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711670 | 11719 | FAASt [T-Pole Program Line 100] (Transmission) | 14F017290000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | Restoration | FALSE |  | Past | [12 empty] | 2023-12-31 | 2023-03-09 | 3/31/2023 | 2023-12-18 | 2024-02-19 |  |  |  |  | 462000 | 118160.28 | 23372 | 12341 | 94787 | 0 | 23372 | 118159 | 130500 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 118160.28 | 94787.57 |  |  |  |  | 118160.28 | 94787.57 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/66/711670-DR4339PR-Project Scope of Work L100 Salinas Sect. - Jobos TC.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 12340.69 |  | 1 | 1 |  | 711670RFI66 | 711670 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711291 | 107855 | FAASt [Telecom Infrastructure – Group E] (Telecommunication) | 14F008930000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2025-02-03 | [5 empty] | 2023-03-06 | 3/29/2023 | [6 empty] | 5600000 | 5600000 |  |  |  |  | 0 | 5600000 | 5600000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/67/711291-DR4339PR_ISOW_Telecomm Antennas_Moca_Quebradillas_San Sebastian.pdf | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date 5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 10/30/2024. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 711291RFI67 | 711291 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
711172 | 107854 | FAASt [L3700 Jobos TC - Maunabo TC] (Transmission) | 14F017400000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-01-20 | 3/28/2023 | [6 empty] | 539739 | 539739 |  |  |  |  | 0 | 539739 | 539739 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/68/711172-DR4339PR-ISOW- Line 3700 Jobos TC - Maunabo TC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 708637. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 711172RFI68 | 711172 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
710498 | 107851 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) | 14F016490000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-03-17 | 3/22/2023 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/69/[710498] DR4339 FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) ISOW CE.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 710498RFI69 | 710498 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
710363 | 107850 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) | 14F016500000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-03-17 | 3/22/2023 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/70/1310158-DR4339PR-FEMA Project Scope of Work Distribution Pole and Conductor Repair - Bayamon Group 15 (1).pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 710363RFI70 | 710363 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
710110 | 11534 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 14F016550000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-08-31 | 2023-03-17 | 3/20/2023 | 2023-08-22 | [5 empty] | 2000000 | 87774.8 | 2478.06 | 14756 | 85297 | 478.06 | 2000 | 87775.06 | 102531.06 |  |  | 2023-10-23 |  | 87774.8 | 85296.74 |  |  |  |  | 87774.8 | 85296.74 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/71/710110-DR4339PR-Detailed%20SOW%20Bayamon%20Group%202%20-%20phase%202%20Rev0%20(2).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 14756.12 |  | 1 | 1 |  | 710110RFI71 | 710110 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
710099 | 11667 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 14F016530000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE |  | Past | [12 empty] | 2023-09-30 | 2023-03-17 | 3/20/2023 | 2023-10-05 | 2024-04-10 | 2024-11-08 | 2024-10-31 |  |  | 3000000 | 6943798.62 | 239377 | 602047 | 6704422 | 42926.93 | 196450.07 | 6943799 | 7545846 | 2024-06-30 | 2024-11-30 | 2025-01-07 |  | 6943798.62 | 6704421.69 |  |  |  |  | 6943798.62 | 6704421.69 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/72/710099-DR4339PR-FEMA SOW Distribution Pole and Conductor Repair - Arecibo Group 1 - Phase 2.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 602047.2 | 620667.23 | 1 | 1 |  | 710099RFI72 | 710099 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
710094 | 11639 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 14F016990000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE |  | Past | [12 empty] | 2023-08-31 | 2023-03-17 | 3/20/2023 | 2023-09-06 | 2024-04-15 |  |  |  |  | 3500000 | 7291385.82 | 195136 | 614123 | 7096250 | 29565.32 | 165570.68 | 7291386 | 7905509 | 2024-06-30 | 2024-11-30 | 2024-11-01 |  | 7291385.82 | 7096249.5 |  |  |  |  | 7291385.82 | 7096249.5 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/73/710094-DR4339PR-Detailed%20SOW%20Bayamon%20Group%201%20-%20Phase%202%20Rev0.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 614123.07 |  | 1 | 1 |  | 710094RFI73 | 710094 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
710045 | 107849 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) | 14F016540000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-03-17 | 3/20/2023 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/74/710045-DR4339PR- FEMA Project Scope of Work Distribution Pole and Conductor Repair - Mayaguez Group 20 (1).pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 710045RFI74 | 710045 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
710026 | 107849 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) | 14F016520000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-03-17 | 3/20/2023 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/75/710026-DR4339PR-FEMA Project Scope of Work Distribution Pole and Conductor Repair - Arecibo Group 17.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 710026RFI75 | 710026 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
709631 | 11627 | FAASt [Morovis Streetlighting] (Distribution) | 14F017270000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2023-03-13 | 3/15/2023 | 2023-12-01 | [5 empty] | 8987336 | 15230881.12 | 1744482 | 2499521 | 13486399 | 487450.7 | 1257031.3 | 15230881 | 17730402 | 2024-06-30 | 2024-08-31 | 2024-03-22 |  | 15230881.12 | 13486398.85 |  |  |  |  | 15230881.12 | 13486398.85 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/76/709631-DR4339PR- ISOW - FEMA Project Scope of Work - Morovis.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2499521.06 |  | 1 | 1 |  | 709631RFI76 | 709631 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708951 | 107846 | FAASt [L6500 Toro Negro 1 H.P. - Barranquitas T.C.] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-01-20 | 3/8/2023 | [6 empty] | 510000 | 510000 |  |  |  |  | 0 | 510000 | 510000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/77/[708951] DR4339PR FAASt [Line 6500 Toro Negro 1 HP - Barranquitas TC] (Transmission) Initial SOW and CE (2).docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708951RFI77 | 708951 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708909 | 107845 | FAASt [L3000 Juncos TC - Rio Blanco HP] (Transmission) | 14F017380000 | PBUT33 - T Line Rebuild | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-01-20 | 3/7/2023 | [6 empty] | 600000 | 600000 |  |  |  |  | 0 | 600000 | 600000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/78/[708909] DR4339PR FAASt [Line 3000 Juncos TC - Rio Blanco HP] (Transimission) ISOW CE.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 712980. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708909RFI78 | 708909 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708819 | 107844 | FAASt [L2000 Once de Agosto Sect. - San Sebastian TC ] (Transmission) | 14F017340000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-01-20 | 3/7/2023 | [6 empty] | 761985 | 761985 |  |  |  |  | 0 | 761985 | 761985 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/79/708819-DR4339PR-ISOW-EN-SOW-0001_Rev1 - Line 2000 Once de Agosto Sect - San Sebastian TC.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Duplicate FAASt. Project under 712978. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708819RFI79 | 708819 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708734 | 107843 | FAASt Line 800 Comsat Sect - Cidra Sect. (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2024-06-01 | [5 empty] | 2023-01-20 | 3/6/2023 | [6 empty] | 349243 | 349243 |  |  |  |  | 0 | 349243 | 349243 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/80/1305869-DR4339PR- Line 800 Comsat Sect - Cidra Sect (1).pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708734RFI80 | 708734 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708637 | 11723 | FAASt [T-Pole Program Line 3700] (Transmission) | 14F017400000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | Restoration | FALSE |  | Past | [12 empty] | 2023-12-31 | 2023-01-20 | 3/3/2023 | 2024-01-12 | 2024-04-03 |  |  |  |  | 480000 | 377354.58 | 73394 | 39574 | 303960 | 14229.08 | 59164.92 | 377354 | 416928 | 2024-11-30 | 2025-02-28 | 2024-08-26 | 12/16/2024 | 377354.58 | 303960.92 | 377354.58 | 303960.92 |  |  | 377354.58 | 303960.92 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/81/708637-DR4339PR-Line 3700 Maunabo TC - Humacao TC.docx |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 39573.63 | 8454.62 | 1 | 1 |  | 708637RFI81 | 708637 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708630 | 107842 | FAASt L37400 Dorado TC - Vega Baja TC] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2024-07-01 | [5 empty] | 2023-01-20 | 3/3/2023 | [6 empty] | 285744 | 285744 |  |  |  |  | 0 | 285744 | 285744 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/82/708630-DR4339PR-Line 37400 Dorado TC - Vega Baja TC.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708630RFI82 | 708630 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708599 | 107841 | FAASt [L700 Costa Sur SP - Yauco 2 HP] (Transmission) | 14F015420000 | PBUT33 - T Line Rebuild | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2024-04-15 | [5 empty] | 2023-01-20 | 3/3/2023 | [6 empty] | 380992 | 380992 |  |  |  |  | 0 | 380992 | 380992 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/83/ISOW-EN-SOW-0001_Rev1 - Line 700 Costa Sur SP - Yauco 2 HP.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708599RFI83 | 708599 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708579 | 11508 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | 14F014730000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-04-30 | 2023-02-27 | 3/3/2023 | 2023-06-28 | 2023-07-20 | [5 empty] | 2154006.76 | 389437.84 | 343118 | 1764569 | 0 | 389437.84 | 2154006.84 | 2497124.84 |  |  | 2023-10-23 |  | 2154006.76 | 1764568.92 |  |  |  |  | 2154006.76 | 1764568.92 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/84/708579-DR4339PR-Detailed%20SOW%20Ponce%20Group%2016-17-18-19%20Rev0%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 343118.15 |  | 1 | 1 |  | 708579RFI84 | 708579 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708577 | 107840 | FAASt Transmission Line 4800 (38KV) Santa Isabel TC - Santa Isabel SECT |  |  | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2024-04-25 | [5 empty] | 2023-01-20 | 3/3/2023 | [6 empty] | 190496 | 190496 |  |  |  |  | 0 | 190496 | 190496 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/85/708577-DR4339PR- ISOW Transmission Line 4800 Santa Isabel TC - Santa Isabel Sect.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708577RFI85 | 708577 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
708575 | 107839 | FAASt Transmission Line 37400 (115KV) Cambalache TC - Dos Bocas Hydro Plant |  |  | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 318800000 |  |  | 2024-07-01 | [5 empty] | 2023-01-20 | 3/3/2023 | [6 empty] | 380992 | 380992 |  |  |  |  | 0 | 380992 | 380992 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/86/708575-DR4339PR- ISOW Transmission Line 37400 Cambalache TC - Dos Bocas Hydro Plant.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 708575RFI86 | 708575 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
706498 | 107832 | FAASt Transmission and Distribution Automation Program Installation of Intelligent Reclosers, Single Phase Reclosers and Fault Current Indicators Group 4 | 14F003280000 | PBUT04 - Distribution Automation | Distribution | Distribution Automation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created | [9 empty] | 2023-12-31 | 2023-02-07 | 2/15/2023 | [6 empty] | 5800000 | 5800000 |  |  |  |  | 0 | 5800000 | 5800000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/87/1302760-DR4339PR-Applicant SOW Transmission and Distribution Group 4 Feb072022.pdf | 4/3/2024 - Received withdrawal status data/info from Project Manager Oscar Fuentes Garcia. FEMA Canceled this FAASt because it wasn’t included in 90 Plan, new FAASt was assigned to this group on December 2023 - 740662 (initial DSOW submission - 12/13/2024) | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 706498RFI87 | 706498 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
705657 | 107826 | FAASt [Automation Program Group 3] (TL/Distribution) | 14F004910000, 14F004930000, 14F004950000, 14F004980000, 14F004940000, 14F004900000, 14F004990000, 14F003330000, 14F004920000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation | Restoration | FALSE |  | Past | [12 empty] | 2023-10-31 | 2023-02-07 | 2/9/2023 | 2023-10-31 | 2023-12-28 |  |  |  |  | 6300000 | 6300000 | 19657460 | 466338 | 4462681 | 1859214 | 17798246 | 24120141 | 24586479 | 2024-12-31 | 2025-06-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/88/705657-DR433PR-FEMA SOW Transmission and Distribution Automation - Group 03.pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.26119 | 4 |  | 705657RFI88 | 705657 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
705584 | 11365 | FAASt [Pole and Conductor Repair - Ponce Groups 14 & 15] (Distribution) | 14F014420000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-04-30 | 2023-02-06 | 2/9/2023 | 2023-04-19 | [5 empty] | 1250000 | 1842979 | 378483 | 284698 | 1464496 | 0 | 378483 | 1842979 | 2127677 |  |  | 2023-06-16 |  | 1842979 | 1464496 |  |  |  |  | 1842979 | 1464496 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/89/705584-DR4339PR-Detailed%20SOW%20Ponce%20Group%2014-15%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 284698 |  | 1 | 1 |  | 705584RFI89 | 705584 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
705527 | 11449 | FAASt [Distribution Pole and Conductor Repair – San Juan 17-18-19-20-21] (Distribution) | 14F014430000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-03-31 | 2023-02-06 | 2/8/2023 | 2023-04-13 | 2023-04-25 |  |  |  |  | 1250000 | 767854 | 125133 | 125147 | 642721 | 0 | 125133 | 767854 | 893001 |  |  | 2023-07-28 |  | 767854 | 642721 |  |  |  |  | 767854 | 642721 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/90/705527%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2017-18-19-20-21%20Rev1%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 125147 |  | 1 | 1 |  | 705527RFI90 | 705527 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
705503 | 11476 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | 14F014410000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-04-30 | 2023-02-06 | 2/8/2023 | 2023-06-21 | [5 empty] | 1250000 | 1176665.69 | 192105 | 221088 | 1396854 | 21294 | 170811 | 1588959 | 1810047 | 2025-01-31 | 2025-06-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/91/705503-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2015-16-17-18-19%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 0.74053 | 2 |  | 705503RFI91 | 705503 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704943 | 11664 | FAASt [Naranjito Streetlighting] (Distribution) | 14F014700000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2023-01-27 | 2/3/2023 | 2023-12-27 | [5 empty] | 6978114 | 13759586.8 | 2115538 | 2348210 | 11644048 | 613589.66 | 1501948.34 | 13759586 | 16107796 | 2024-06-30 | 2024-08-31 | 2024-04-12 |  | 13759586.8 | 11644048.42 |  |  |  |  | 13759586.8 | 11644048.42 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/92/1297186-DR4339PR-Applicant SOW 01-31-2023 (1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2348209.91 |  | 1 | 1 |  | 704943RFI92 | 704943 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704933 | 11465 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 14F014460000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-04-30 | 2023-01-27 | 2/3/2023 | 2023-03-31 | 2023-04-25 |  |  |  |  | 1250000 | 1426151 | 224731 | 231255 | 1201420 | 47078 | 177653 | 1426151 | 1657406 |  |  | 2023-08-04 |  | 1426151 | 1201420 |  |  |  |  | 1426151 | 1201420 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/93/704933%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2013-14-15-16%20Rev1%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 231255 |  | 1 | 1 |  | 704933RFI93 | 704933 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704931 | 11651 | FAASt [Camuy Streetlighting] (Distribution) | 14F014680000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-10-31 | 2023-01-27 | 2/3/2023 | 2023-12-01 | 2023-12-26 |  |  |  |  | 11239791 | 15436783.23 | 2269186 | 2828651 | 15436783 | 351414 | 1917772 | 17705969 | 20534620 | 2024-08-31 | 2025-01-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/94/704931-DR4339PR-FEMA Project Scope of Work - Distribution Streetlighting - Camuy.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87184 | 1 |  | 704931RFI94 | 704931 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704929 | 11635 | FAASt [San Lorenzo Streetlighting] (Distribution) | 14F014710000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2023-01-27 | 2/3/2023 | 2023-12-01 | [5 empty] | 11082405 | 14343817.06 | 2284857 | 2780414 | 14343817 | 370986 | 1913871 | 16628674 | 19409088 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/95/704929-DR4339PR-FEMA Project Scope of Work - Distribution Streetlighting - San Lorenzo.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.8626 | 1 |  | 704929RFI95 | 704929 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704938 | 11633 | FAASt [Las Piedras Streetlighting] (Distribution) | 14F014610000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2023-01-27 | 2/3/2023 | 2023-12-01 | [5 empty] | 11100801 | 15615524.51 | 1807601 | 2760454 | 13807923 | 522246.69 | 1285354.31 | 15615524 | 18375978 | 2024-06-30 | 2024-08-31 | 2024-04-12 |  | 15615524.51 | 13807923.4 |  |  |  |  | 15615524.51 | 13807923.4 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/96/1297192-DR4339OPR-Applicant SOW 01-31-2023.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2760454.04 |  | 1 | 1 |  | 704938RFI96 | 704938 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704927 | 11711 | FAASt [Añasco Streetlighting] (Distribution) | 14F014720000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [12 empty] | 2024-01-31 | 2023-01-27 | 2/3/2023 | 2024-01-19 | [5 empty] | 7572909 | 13908238.09 | 1820362 | 2420466 | 12087876 | 0 | 1820362 | 13908238 | 16328704 | 2024-06-30 | 2024-08-31 | 2024-07-08 |  | 13908238.09 | 12087876.17 |  |  |  |  | 13908238.09 | 12087876.17 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/97/1297195-DR4339PR-Applicant SOW 01-31-2023.pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2420466.41 |  | 1 | 1 |  | 704927RFI97 | 704927 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704921 | 11675 | FAASt [Barranquitas Streetlighting] (Distribution) | 14F014640000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-01-31 | 2023-01-27 | 2/3/2023 | 2024-01-19 | [5 empty] | 5782391 | 11007375.31 | 1577046 | 2048083 | 9430329 | 472894.36 | 1104151.64 | 11007375 | 13055458 | 2024-06-30 | 2024-08-31 | 2024-05-31 |  | 11007375.31 | 9430329.22 |  |  |  |  | 11007375.31 | 9430329.22 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/98/704921-DR4339PR-FEMA Project Scope of Work - Distribution Streetlighting - Barranquitas.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2048083.31 |  | 1 | 1 |  | 704921RFI98 | 704921 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704916 | 11312 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | 14F013920000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-03-31 | 2023-02-03 | 2/3/2023 | 2023-02-28 | 2023-03-08 |  |  |  |  | 1250000 | 303970 | 29974 | 49755 | 273996 | 6279 | 23695 | 303970 | 353725 |  |  | 2023-04-06 |  | 303970 | 273996 |  |  |  |  | 303970 | 273996 | 2027-09-20 | https://aeepr.sharepoint.com/:b:/r/sites/Test4552/Shared%20Documents/General/ISOW%20DSOW%20Information%20(Attachments)/704916-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2013-14-15-16%20Rev1%20-%20signed.pdf?csf=1&web=1&e=aNrEX2 |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49755 |  | 1 | 1 |  | 704916RFI99 | 704916 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704868 | 11650 | FAASt [Ceiba Streetlighting] (Distribution) | 14F014630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2023-01-27 | 2/2/2023 | 2023-12-27 | [5 empty] | 5590258 | 5869029.74 | 716919 | 1481547 | 5152111 | 244786.81 | 472132.19 | 5869030 | 7350577 | 2024-06-30 | 2024-08-31 | 2024-07-08 |  | 5869029.74 | 5152111.14 |  |  |  |  | 5869029.74 | 5152111.14 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/100/[704868] DR4339PR - FAASt [Distribution Streetlighting - Ceiba] (Distribution) SOW CE.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:09 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1481546.84 |  | 1 | 1 |  | 704868RFI100 | 704868 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704862 | 11728 | FAASt [Fajardo Streetlighting] (Distribution) | 14F014600000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-02-29 | 2023-01-27 | 2/2/2023 | 2024-02-28 | 2024-04-09 |  |  |  |  | 11724212 | 11333806.13 | 1104923 | 2297198 | 11333806 | 186210 | 918713 | 12438729 | 14735927 | 2024-07-31 | 2024-12-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/101/%5B704862%5D%20DR4339PR%20-%20Distribution%20Streetlighting%20-%20Fajardo%20(Distribution)%20SOW%20CE.pdf?web=1 | QC Review Complete: 2/28/2024 | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.91117 | 1 |  | 704862RFI101 | 704862 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704849 | 11658 | FAASt [Naguabo Streetlighting] (Distribution) | 14F014620000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2023-01-27 | 2/2/2023 | 2023-12-27 | [5 empty] | 9670022 | 13290413.39 | 1669737 | 2380243 | 11620676 | 0 | 1669737 | 13290413 | 15670656 | 2024-06-30 | 2024-08-31 | 2024-05-10 |  | 13290413.39 | 11620676.42 |  |  |  |  | 13290413.39 | 11620676.42 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/102/704849%20-%20DR4339PR%20FAASt%20%5BDistribution%20Streetlightling%20-%20Naguabo%5D%20(Ditribution)%20SOW%20CE.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2380242.99 |  | 1 | 1 |  | 704849RFI102 | 704849 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704844 | 11340 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 14F014450000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-03-31 | 2023-01-30 | 2/2/2023 | 2023-03-31 | [5 empty] | 1250000 | 409298 | 88558 | 62490 | 320740 | 18552 | 70006 | 409298 | 471788 |  |  | 2023-05-17 |  | 409298 | 320740 |  |  |  |  | 409298 | 320740 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/103/704844-DR4339PR-Detailed%20SOW%20Caguas%20Group%2016-17-18-19-20%20Rev0.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 62490 |  | 1 | 1 |  | 704844RFI103 | 704844 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704805 | 11863 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 14F008600000, 14F008620000, 14F008610000, 14F008630000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  | TRUE | 2025-07-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-02-02 | 2/2/2023 | [6 empty] | 6905000 | 6905000 |  |  |  |  | 0 | 6905000 | 6905000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/104/704805-DR4339PR-Telecom%20Infrastructure%20%E2%80%93%20Group%20D-Rev.%201.pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date 5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 9/30/2024. 9/12/2024 - "6/25/2024 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1122383" Grants Portal 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | 704805RFI104 | 704805 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704793 | 11691 | FAASt [Yauco Streetlighting] (Distribution) | 14F014590000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-01-31 | 2023-01-27 | 2/2/2023 | 2024-01-22 | [5 empty] | 13804973 | 14713958.38 | 1639888 | 2718070 | 14713958 | 255698 | 1384190 | 16353846 | 19071916 | 2024-08-31 | 2025-01-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/105/704793-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20Yauco.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89972 | 1 |  | 704793RFI105 | 704793 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704763 | 107825 | FAASt [Telecom Infrastructure – Group C] (Telecommunication) | 14F004650000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  |  |  | 2025-11-14 | [5 empty] | 2023-02-02 | 2/2/2023 | [6 empty] | 2800000 | 2800000 |  |  |  |  | 0 | 2800000 | 2800000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/106/704763-DR4339PR-Telecom%20Infrastructure%20%E2%80%93%20Group%20C-Rev.%201.pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project will need low level support as we work to procure land needed for the project 5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 12/20/2025. | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 704763RFI106 | 704763 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704757 | 11638 | FAASt [Santa Isabel Streetlighting] (Distribution) | 14F014660000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2023-01-27 | 2/2/2023 | 2023-12-01 | [5 empty] | 7826361 | 7956662 | 820333 | 1750406 | 7956663 | 147924 | 672409 | 8776996 | 10527402 | 2024-08-31 | 2025-01-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/107/704757-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20Santa%20Isabel.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.90654 | 1 |  | 704757RFI107 | 704757 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704755 | 11352 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 14F014440000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-03-31 | 2023-01-20 | 2/2/2023 | 2023-03-31 | [5 empty] | 1250000 | 524391.61 | 86181.92 | 83451 | 438210 | 0 | 86181.92 | 524391.92 | 607842.92 |  |  | 2023-05-17 |  | 524391.61 | 438209.69 |  |  |  |  | 524391.61 | 438209.69 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/108/704755-DR4339PR-Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%2012-13-14.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 83450.9 |  | 1 | 1 |  | 704755RFI108 | 704755 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704751 | 11311 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | 14F013940000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-03-31 | 2023-01-20 | 2/2/2023 | 2023-03-01 | [5 empty] | 435167 | 435167 | 96676 | 66168 | 338491 | 20252 | 76424 | 435167 | 501335 |  |  | 2023-04-06 |  | 435167 | 338491 |  |  |  |  | 435167 | 338491 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/109/704751-DR4339PR-Detailed%20SOW%20Bayamon%20Group%2011%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 66168 |  | 1 | 1 |  | 704751RFI109 | 704751 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704750 | 11314 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | 14F013930000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-03-31 | 2023-01-20 | 2/2/2023 | 2023-02-28 | 2023-03-07 |  |  |  |  | 1250000 | 578629 | 92244 | 92511 | 486385 | 19324 | 72920 | 578629 | 671140 |  |  | 2023-04-06 |  | 578629 | 486385 |  |  |  |  | 578629 | 486385 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/110/704750-DR4339PR-Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%2010.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 92511 |  | 1 | 1 |  | 704750RFI110 | 704750 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704744 | 11626 | FAASt [San Sebastian Streetlighting] (Distribution) | 14F014690000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-10-31 | 2023-01-27 | 2/2/2023 | 2023-12-01 | [5 empty] | 12472305 | 22246737.73 | 3663221 | 3725225 | 22246738 | 525425 | 3137796 | 25909959 | 29635184 | 2024-08-31 | 2025-01-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/111/704744-DR4339PR-%20FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20San%20Sebasti%C3%A1n.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.85862 | 1 |  | 704744RFI111 | 704744 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704741 | 11737 | FAASt [Moca Streetlighting] (Distribution) | 14F014650000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Current | [12 empty] | 2024-02-29 | 2023-01-27 | 2/2/2023 | 2024-02-28 | 2025-07-02 |  |  |  |  | 12034895 | 17686091.97 | 1110824.64 | 3152500.55 | 19122669.84 | 167188.56 | 943636.08 | 20233494.48 | 23385995.03 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/112/704741-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20Moca.pdf?web=1 | 2/28/2024: QC Review Complete 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.8741 | 1 |  | 704741RFI112 | 704741 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
704679 | 11524 | FAASt [Coamo Streetlighting] (Distribution) | 14F014670000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2023-01-27 | 2/1/2023 | 2023-06-30 | 2023-07-01 |  |  |  |  | 12196369 | 16372823.8 | 2060901.35 | 2687464 | 14311922 | 0 | 2060901.35 | 16372823.35 | 19060287.35 |  |  | 2023-11-03 |  | 16372823.8 | 14311922.45 |  |  |  |  | 16372823.8 | 14311922.45 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/113/704679-DR4339PR-Detailed%20SOW%20Coamo%20Rev0%20-%20DSOW%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2687463.9 |  | 1 | 1 |  | 704679RFI113 | 704679 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
703535 | 11636 | FAASt [Toa Baja Streetlighting] (Distribution) | 14F013890000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-10-31 | 2022-12-13 | 1/23/2023 | 2023-12-01 | [5 empty] | 18518368 | 10149325.06 | 620135 | 1814022 | 9529190 | 0 | 620135 | 10149325 | 11963347 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 10149325.06 | 9529190.37 |  |  |  |  | 10149325.06 | 9529190.37 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/114/703535%20-%20DR4339%20-%20FAASt%20%5BDistribution%20Streetlighting%20-%20Toa%20Baja%5D%20(Distribution)%20CE-ISOW.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1814022.36 |  | 1 | 1 |  | 703535RFI114 | 703535 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
703222 | 107824 | FAASt [Transmission and Distribution Automation Program Installation of Intelligent Reclosers, Single Phase Reclosers and Fault Current Indicators Group 2] (Transmission and Distribution) | 14F000800000 | PBUT04 - Distribution Automation | Distribution | Distribution Automation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created |  | 230370000 |  |  | 2023-12-13 |  |  |  |  | 2023-10-31 | 2022-12-07 | 1/19/2023 | [6 empty] | 4500000 | 4500000 |  |  |  |  | 0 | 4500000 | 4500000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/115/703222-DR4339PR-T%20ad%20D%20intelligent%20Re0closers,%20Single%20Phase%20Reclosers%20and%20Fault%20Current%20Indicators%20Group%202.pdf | 4/3/2024 - Received withdrawal status data/info from Project Manager Oscar Fuentes Garcia. FEMA Canceled this FAASt because it wasn’t included in 90 Plan, new FAASt was assigned to this group on December 2023 - 740662 (initial DSOW submission - 12/13/2024) | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 703222RFI115 | 703222 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701679 | 11267 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | 14F010320000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-12-22 | 1/4/2023 | 2023-01-31 | [5 empty] | 850000 | 80651.6 | 16226.16 | 12535 | 64425 | 3399.16 | 12827 | 80651.16 | 93186.16 |  |  | 2023-03-02 |  | 80651.6 | 64425.44 |  |  |  |  | 80651.6 | 64425.44 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/116/701679-DR4339PR-FEMA%20iSOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20San%20Juan%20Group%2012.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12535.35 |  | 1 | 1 |  | 701679RFI116 | 701679 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701555 | 11275 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | 14F010350000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-01-31 | 2022-12-22 | 1/3/2023 | 2023-01-27 | [5 empty] | 1250000 | 649427 | 102417 | 104535 | 547010 | 21455 | 80962 | 649427 | 753962 |  |  | 2023-03-08 |  | 649427 | 547010 |  |  |  |  | 649427 | 547010 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/117/701555-DR4339PR-Detailed%20SOW%20Ponce%20Group%2013%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 104535 |  | 1 | 1 |  | 701555RFI117 | 701555 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701552 | 11257 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | 14F010360000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-01-31 | 2022-12-22 | 1/3/2023 | 2023-01-20 | [5 empty] | 1250000 | 238162 | 51841 | 36670 | 186321 | 10860 | 40981 | 238162 | 274832 |  |  | 2023-03-08 |  | 238162 | 186321 |  |  |  |  | 238162 | 186321 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/118/701552-DR4339PR-Detailed%20SOW%20Ponce%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 36670 |  | 1 | 1 |  | 701552RFI118 | 701552 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701545 | 11269 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | 14F010370000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-12-22 | 1/3/2023 | 2023-01-20 | [5 empty] | 1250000 | 616229 | 129039 | 95198 | 487190 | 27032 | 102007 | 616229 | 711427 |  |  | 2023-03-08 |  | 616229 | 487190 |  |  |  |  | 616229 | 487190 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/119/701545-DR4339PR-Detailed%20SOW%20Ponce%20Group%2011%20Rev0%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 95198 |  | 1 | 1 |  | 701545RFI119 | 701545 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701504 | 11268 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | 14F010450000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-01-31 | 2022-12-22 | 1/3/2023 | 2023-01-27 | [5 empty] | 1250000 | 188223 | 37878 | 29252 | 150345 | 7935 | 29943 | 188223 | 217475 |  |  | 2023-03-08 |  | 188223 | 150345 |  |  |  |  | 188223 | 150345 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/120/701504-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 29252 | 4491 | 1 | 1 |  | 701504RFI120 | 701504 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701495 | 11263 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | 14F010400000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-01-31 | 2022-12-22 | 1/3/2023 | 2023-01-27 | [5 empty] | 1250000 | 25678.75 | 5830.39 | 3960 | 19848 | 1221.39 | 4609 | 25678.39 | 29638.39 |  |  | 2023-03-02 |  | 25678.75 | 19848.36 |  |  |  |  | 25678.75 | 19848.36 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/121/701495-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2014%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 3959.6 |  | 1 | 1 |  | 701495RFI121 | 701495 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701473 | 11693 | FAASt [Canovanas Streetlighting] (Distribution) | 14F013770000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-09-30 | 2022-12-14 | 1/3/2023 | 2023-09-28 | 2024-01-18 |  |  |  |  | 11554562 | 14314798.95 | 1574362 | 2681107 | 14314799 | 248356 | 1326006 | 15889161 | 18570268 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/122/701473-DR4339PR-Distribution%20Streetlight%20-%20Can%C3%B3vanas.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.90092 | 1 |  | 701473RFI122 | 701473 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
701472 | 11727 | FAASt [Comerio Streetlighting] (Distribution) | 14F013760000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-03-31 | 2022-12-14 | 1/3/2023 | 2024-02-28 | 2024-04-09 |  |  |  |  | 4664340 | 7400895.19 | 862126 | 1640383 | 6538769 | 0 | 862126 | 7400895 | 9041278 | 2024-06-30 | 2024-08-31 | 2024-05-10 |  | 7400895.19 | 6538769.44 |  |  |  |  | 7400895.19 | 6538769.44 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/123/701472-DR4339PR-Distribution%20Streetlight%20-%20Comer%C3%ADo.pdf?web=1 | 2/28/2024: QC Review Complete 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1640382.7 |  | 1 | 1 |  | 701472RFI123 | 701472 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
699814 | 11576 | FAASt [Juana Diaz Streetlighting] (Distribution) | 14F013900000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-09-30 | 2022-12-13 | 12/23/2022 | 2023-09-28 | 2024-01-15 |  |  |  |  | 13124331 | 15781505 | 1909452 | 2898942 | 15781505 | 296320 | 1613132 | 17690957 | 20589899 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/124/699814-DR4339PR-%20ISOW-%20Project%20Scope%20of%20work-Juana%20D%C3%ADaz.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89207 | 1 |  | 699814RFI124 | 699814 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698579 | 11629 | FAASt [Orocovis Streetlighting] (Distribution) | 14F013800000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2022-12-14 | 12/20/2022 | 2023-12-01 | [5 empty] | 3973478 | 9410766.24 | 1339801 | 1873982 | 8070965 | 414167.51 | 925633.49 | 9410766 | 11284748 | 2024-06-30 | 2024-08-31 | 2024-03-22 |  | 9410766.24 | 8070964.96 |  |  |  |  | 9410766.24 | 8070964.96 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/125/698579-DR4339PR-ISOW%20Distribution%20Streetlight%20-%20Orocovis.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1873982.08 |  | 1 | 1 |  | 698579RFI125 | 698579 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698570 | 11560 | FAASt [Corozal Streetlighting] (Distribution) | 14F013750000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-08-31 | 2022-12-14 | 12/20/2022 | 2023-08-23 | 2023-09-18 |  |  |  |  | 10808513 | 15946081.93 | 2225874 | 2501126 | 13720208 | 0 | 2225874 | 15946082 | 18447208 |  |  | 2023-12-29 |  | 15946081.93 | 13720208.31 |  |  |  |  | 15946081.93 | 13720208.31 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/126/698570-DR4339PR-ISOW%20Distribution%20Streetlight%20-%20Corozal.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2501126.14 |  | 1 | 1 |  | 698570RFI126 | 698570 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698522 | 11582 | FAASt [Vieques Streetlighting] (Distribution) | 14F013790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-09-30 | 2022-12-14 | 12/20/2022 | 2023-09-28 | 2024-01-15 |  |  |  |  | 3832444 | 4386770.2 | 519326 | 1374011 | 4386770 | 123865 | 395461 | 4906096 | 6280107 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/127/698522-DR4339PR-Distribution%20Streetlighting%20-%20Vieque.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89415 | 1 |  | 698522RFI127 | 698522 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698511 | 11680 | FAASt [Culebra Streetlighting] (Distribution) | 14F013910000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2022-12-14 | 12/20/2022 | 2023-12-01 | 2024-01-24 |  |  |  |  | 1036293 | 1309407 | 153603 | 476439 | 1155804 | 62197 | 91406 | 1309407 | 1785846 | 2024-06-30 | 2024-07-31 | 2024-04-12 |  | 1309407 | 1155804 |  |  |  |  | 1309407 | 1155804 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/128/698511-DR4339PR-Distribution%20Streetlighting%20-%20Culebra.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 476440 |  | 1 | 1 |  | 698511RFI128 | 698511 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698458 | 11518 | FAASt [Guaynabo Streetlighting] (Distribution) | 14F013840000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-12-14 | 12/20/2022 | 2023-07-01 | 2023-07-27 |  |  |  |  | 10334312 | 10615811.01 | 853056.42 | 1979750 | 9762755 | 0 | 853056.42 | 10615811.42 | 12595561.42 |  |  | 2023-11-03 |  | 10615811.01 | 9762754.59 |  |  |  |  | 10615811.01 | 9762754.59 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/129/698458-DR4339PR-Detailed%20SOW%20Guaynabo%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(2).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1979750.26 |  | 1 | 1 |  | 698458RFI129 | 698458 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698439 | 11526 | FAASt [Las Marias Streetlighting] (Distribution) | 14F013820000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-12-14 | 12/20/2022 | 2023-06-30 | 2023-08-09 |  |  |  |  | 3525848 | 8360922 | 1287705 | 1653390 | 7073217 | 0 | 1287705 | 8360922 | 10014312 |  |  | 2023-11-03 |  | 8360922 | 7073217 |  |  |  |  | 8360922 | 7073217 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/130/698439-DR4339PR-Detailed%20SOW%20Las%20Mar%C3%ADas%20Rev1%20-%20DSOW%20-%20signed%20(2).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1653390 |  | 1 | 1 |  | 698439RFI130 | 698439 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698432 | 11523 | FAASt [Hormigueros Streetlighting] (Distribution) | 14F013830000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-12-14 | 12/20/2022 | 2023-06-30 | 2023-12-27 |  |  |  |  | 5171244 | 6920157.56 | 968057 | 1698467 | 6920158 | 190774 | 777283 | 7888215 | 9586682 | 2024-12-31 | 2025-05-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/131/698432-DR4339PR-Detailed%20SOW%20Hormigueros%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87728 | 1 |  | 698432RFI131 | 698432 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698427 | 11525 | FAASt [Maricao Streetlighting] (Distribution) | 14F013810000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-12-14 | 12/20/2022 | 2023-07-01 | 2023-12-19 |  |  |  |  | 1250000 | 4846034.89 | 1028907 | 1377820 | 4846035 | 227776 | 801131 | 5874942 | 7252762 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/132/698427-DR4339PR-Detailed%20SOW%20Maricao%20Rev0%20-%20DSOW%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.82487 | 1 |  | 698427RFI132 | 698427 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
698424 | 11344 | FAASt [Florida Streetlighting] (Distribution) | 14F013850000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-03-31 | 2022-12-14 | 12/20/2022 | 2023-03-31 | [5 empty] | 4130863 | 10309031.53 | 997190 | 1705096 | 9311842 | 277173 | 720017 | 10309032 | 12014128 |  |  | 2023-10-23 |  | 10309031.53 | 9311841.53 |  |  |  |  | 10309031.53 | 9311841.53 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/133/698424-DR4339PR-Detailed%20SOW%20Florida%20Rev0%20-%20signed%20-%20DSOW%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1705096.48 |  | 1 | 1 |  | 698424RFI133 | 698424 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
697183 | 11668 | FAASt [Vega Baja Streetlighting] (Distribution) | 14F013860000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-12-31 | 2022-12-06 | 12/15/2022 | 2023-12-27 | [5 empty] | 16684927 | 9248657.11 | 1117331 | 1940155 | 9248657 | 193746 | 923585 | 10365988 | 12306143 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/134/1272890-DR4339PR-Applicant%20Scope%20of%20Work%20Vega%20Baja.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89221 | 1 |  | 697183RFI134 | 697183 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
693788 | 11547 | FAASt [Toa Alta Streetlighting] (Distribution) | 14F013870000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-08-31 | 2022-12-09 | 12/9/2022 | 2023-08-23 | 2023-12-19 |  |  |  |  | 6721337.37 | 5847563.41 | 481369 | 1617458 | 5847563 | 104298 | 377071 | 6328932 | 7946390 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/135/693788-DR4339PR-Detailed%20SOW%20Toa%20Alta%20Phase%201%20High%20Priority%20Rev0%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.92394 | 1 |  | 693788RFI135 | 693788 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
693615 | 11685 | FAASt [Rio Grande Streetlighting] (Distribution) | 14F013880000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-09-30 | 2022-12-08 | 12/8/2022 | 2023-09-28 | 2024-01-18 |  |  |  |  | 14880102 | 6376770.32 | 700108 | 1579242 | 6376770 | 138969 | 561139 | 7076878 | 8656120 | 2024-07-31 | 2024-12-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/136/920554-DR4339PR-Distribution%20Streetlighting%20-%20Rio%20Grande.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.90107 | 1 |  | 693615RFI136 | 693615 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
693543 | 11634 | FAASt [Juncos Streetlighting] (Distribution) | 14F013780000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-10-31 | 2022-12-08 | 12/8/2022 | 2023-12-01 | 2024-09-06 |  |  |  |  | 10957723 | 12854140.62 | 1643590 | 1899782 | 11568798 | 260418 | 1383172 | 13212388 | 15112170 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/137/936204-DR4339PR-Distribution%20Streetlighting%20-%20Juncos.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.97289 | 1 |  | 693543RFI137 | 693543 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
691702 | 11326 | FAASt [Trujillo Alto Streetlighting] (Distribution) | 14F012860000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-03-31 | 2022-11-30 | 11/30/2022 | 2023-03-13 | [5 empty] | 16750334 | 26286925 | 1009578 | 3389490 | 25277347 | 246446 | 763132 | 26286925 | 29676415 |  |  | 2023-05-17 |  | 26286925 | 25277347 |  |  |  |  | 26286925 | 25277347 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/138/FEMA%20Detailed%20Scope%20of%20Work%20Trujillo%20Alto%20Phase%201%20High%20Priority%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3389490 |  | 1 | 1 |  | 691702RFI138 | 691702 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
691246 | 11231 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | 14F010340000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-01 | 11/28/2022 | 2022-12-21 | 2023-01-16 |  |  |  |  | 3000000 | 245340.07 | 33717.31 | 41364 | 211623 | 0 | 33717.31 | 245340.31 | 286704.31 |  |  | 2023-02-16 12:50 |  | 245340.07 | 211622.76 |  |  |  |  | 245340.07 | 211622.76 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/139/691246%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2010%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 41363.6 |  | 1 | 1 |  | 691246RFI139 | 691246 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
690721 | 11531 | FAASt [Guayama Streetlighting] (Distribution) | 14F012830000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-11-22 | 11/22/2022 | 2023-07-01 | 2023-12-19 |  |  |  |  | 16731938 | 5525916.66 | 542958 | 1519802 | 5525917 | 117119 | 425839 | 6068875 | 7588677 | 2025-01-31 | 2025-06-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/140/690721-DR4339PR-Detailed%20SOW%20Guayama%20Rev0%20-%20DSOW%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.91053 | 1 |  | 690721RFI140 | 690721 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
690545 | 11319 | FAASt [Aguadilla Streetlighting] (Distribution) | 14F012780000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-03-31 | 2022-11-21 | 11/21/2022 | 2023-03-13 | [5 empty] | 19301209 | 21092584 | 1295775 | 3021242 | 19796808 | 333333 | 962442 | 21092583 | 24113825 |  |  | 2023-05-17 | 05/15/2024 | 21092584 | 19796809 | 21092584 | 19796809 |  |  | 21092584 | 19796809 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/141/FEMA%20Detailed%20Scope%20of%20Work%20Aguadilla%20Municipality%20Phase%201%20High%20Priority%20-%20Signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3021242 |  | 1 | 1 |  | 690545RFI141 | 690545 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
690483 | 11552 | FAASt [Cayey Streetlighting] (Distribution) | 14F012820000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-08-31 | 2022-11-21 | 11/21/2022 | 2023-08-23 | 2023-12-19 |  |  |  |  | 13498378 | 13343261.38 | 1319139 | 2650718 | 13343261 | 218624 | 1100515 | 14662400 | 17313118 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/142/690483-DR4339PR-Detailed%20SOW%20Cayey%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.91003 | 1 |  | 690483RFI142 | 690483 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
690480 | 11683 | FAASt [Humacao Streetlighting] (Distribution) | 14F012870000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-09-30 | 2022-11-21 | 11/21/2022 | 2023-09-28 | 2024-01-15 |  |  |  |  | 17827506 | 7598892 | 922000 | 1719130 | 7598892 | 170104 | 751896 | 8520892 | 10240022 | 2024-09-30 | 2025-02-28 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/143/690480-DR4339PR-ISOW%20-%20FEMA%20Project%20Scope%20of%20Work%20-%20Humacao.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.8918 | 1 |  | 690480RFI143 | 690480 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
689071 | 11256 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | 14F010460000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-01 | 11/9/2022 | 2023-01-27 | 2023-02-01 |  |  |  |  | 3500000 | 77036.24 | 17491.16 | 11879 | 59545 | 3664.16 | 13827 | 77036.16 | 88915.16 |  |  | 2023-03-02 12:24 |  | 77036.24 | 59545.08 |  |  |  |  | 77036.24 | 59545.08 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/144/689071-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2011%20Rev%201.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 11878.8 |  | 1 | 1 |  | 689071RFI144 | 689071 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688774 | 11207 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | 14F010390000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-01 | 11/7/2022 | 2022-12-21 | [5 empty] | 3000000 | 541815 | 98484 | 86719 | 443331 | 20631 | 77853 | 541815 | 628534 |  |  | 2023-01-31 12:56 |  | 541815 | 443331 |  |  |  |  | 541815 | 443331 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/145/688774-DR4339PR-Detailed%20SOW%20Ponce%20Group%209%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 86719 | 11678 | 1 | 1 |  | 688774RFI145 | 688774 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688630 | 11273 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | 14F010420000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-01 | 11/7/2022 | 2023-01-20 | [5 empty] | 3000000 | 52719.38 | 9990.97 | 8327 | 42728 | 0 | 9990.97 | 52718.97 | 61045.97 |  |  | 2023-03-08 12:36 |  | 52719.38 | 42728.41 |  |  |  |  | 52719.38 | 42728.41 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/146/688630-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 8327.05 |  | 1 | 1 |  | 688630RFI146 | 688630 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688629 | 11277 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | 14F010410000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-01 | 11/7/2022 | 2023-01-27 | [5 empty] | 3000000 | 134828.92 | 27886.93 | 20834 | 106942 | 5841.93 | 22045 | 134828.93 | 155662.93 |  |  | 2023-03-08 12:36 |  | 134828.92 | 106941.99 |  |  |  |  | 134828.92 | 106941.99 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/147/688629-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2013%20Rev0%20-%20signed%20(2).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 20833.9 |  | 1 | 1 |  | 688629RFI147 | 688629 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688627 | 11193 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | 14F010480000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-01 | 11/7/2022 | 2022-12-20 | [5 empty] | 3000000 | 375962.49 | 72188.49 | 58918 | 303774 | 0 | 72188.49 | 375962.49 | 434880.49 |  |  | 2023-01-31 12:56 |  | 375962.49 | 303774 |  |  |  |  | 375962.49 | 303774 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/148/688627-DR4339PR-Detailed%20SOW%20Arecibo%20Group%209%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 58918 |  | 1 | 1 |  | 688627RFI148 | 688627 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688625 | 11279 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | 14F010380000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-02 | 11/7/2022 | 2023-01-20 | [5 empty] | 3000000 | 901290.28 | 191275.59 | 139358 | 710015 | 0 | 191275.59 | 901290.59 | 1040648.59 |  |  | 2023-03-20 11:45 |  | 901290.28 | 710014.69 |  |  |  |  | 901290.28 | 710014.69 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/149/688625-DR4339PR-Detailed%20SOW%20Ponce%20Group%2010%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 139357.85 |  | 1 | 1 |  | 688625RFI149 | 688625 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688623 | 107781 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | 14F005200000, 14F000350000, 14F000160000, 14F003260000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation | Restoration | TRUE | 2025-07-31 | Past |  |  |  |  | 230370000 | 2022-07-29 | 2022-08-25 |  | 2022-08-28 |  |  |  | 2023-05-31 | 2022-11-08 | 11/7/2022 | 2023-05-01 | 2023-12-28 |  |  |  |  | 900000 | 5145417.32 | 1877045 | 130382 | 874904 | 243445 | 1633600 | 2751949 | 2882331 | 2025-08-31 | 2026-01-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/150/688623-DR4339PR-DSOW%20Automation%20Group%201%2006142023%5B22070%5D%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.8697 | 1 |  | 688623RFI150 | 688623 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688472 | 11217 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | 14F010430000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-04 | 11/4/2022 | 2022-12-21 | 2023-01-04 |  |  |  |  | 3000000 | 179894.86 | 14986 | 29922 | 164909 | 0 | 14986 | 179895 | 209817 |  |  | 2023-02-16 |  | 179894.86 | 164908.86 |  |  |  |  | 179894.86 | 164908.86 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/151/688472-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2011%20Rev0%20(1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 29921.55 |  | 1 | 1 |  | 688472RFI151 | 688472 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688198 | 11276 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | 14F010470000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-03 | 11/3/2022 | 2023-01-20 | [5 empty] | 2500000 | 76862.24 | 16023.76 | 12053 | 60838 | 3356.76 | 12667 | 76861.76 | 88914.76 |  |  | 2023-03-20 |  | 76862.24 | 60838.48 |  |  |  |  | 76862.24 | 60838.48 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/152/688198-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2010%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12052.8 |  | 1 | 1 |  | 688198RFI152 | 688198 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688109 | 11264 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | 14F010330000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-02 | 11/2/2022 | 2023-01-20 | [5 empty] | 3000000 | 563429.26 | 114710.2 | 87444 | 448719 | 0 | 114710.2 | 563429.2 | 650873.2 |  |  | 2023-03-08 |  | 563429.26 | 448719.06 |  |  |  |  | 563429.26 | 448719.06 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/153/688109%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2011%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 87443.55 |  | 1 | 1 |  | 688109RFI153 | 688109 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
688096 | 11214 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | 14F010440000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-11-02 | 11/2/2022 | 2022-12-20 | [5 empty] | 3000000 | 27238.64 | 5830.39 | 4169 | 21408 | 1221.39 | 4609 | 27238.39 | 31407.39 |  |  | 2023-01-31 |  | 27238.64 | 21408.25 |  |  |  |  | 27238.64 | 21408.25 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/154/688096-DR4339PR-Detailed%20SOW%20Caguas%20Group%2015%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 4169.45 | 691.35 | 1 | 1 |  | 688096RFI154 | 688096 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
686482 | 11572 | FAASt [Isabela Streetlighting] (Distribution) | 14F012880000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-09-30 | 2022-09-08 | 10/20/2022 | 2023-09-18 | 2024-01-15 |  |  |  |  | 16599080 | 7013624.27 | 733835 | 1698664 | 7013624 | 143078 | 590757 | 7747459 | 9446123 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/155/686482%20-DR4339PR%20-ISOW%20-%20FEMA%20Project%20Scope%20of%20Work%20-%20Isabela.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.90528 | 1 |  | 686482RFI155 | 686482 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
686480 | 11229 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | 14F008880000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-01 | 10/20/2022 | 2022-12-07 | 2023-01-09 |  |  |  |  | 3000000 | 632056 | 108652 | 101359 | 523404 | 22761 | 85891 | 632056 | 733415 |  |  | 2023-02-16 |  | 632056 | 523404 |  |  |  |  | 632056 | 523404 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/156/686480-DR4339PR-Detailed%20SOW%20Ponce%20Group%207%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 101359 |  | 1 | 1 |  | 686480RFI156 | 686480 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
686471 | 11116 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | 14F008640000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-10-06 | 10/20/2022 | 2022-11-17 | [5 empty] | 3000000 | 319606 | 68700 | 49227 | 250906 | 14392 | 54308 | 319606 | 368833 |  |  | 2022-12-27 | 4/17/2024 | 319606 | 250906 | 319606 | 250906 |  |  | 319606 | 250906 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/157/686471-DR4339PR-Detailed%20SOW%20Arecibo%20Group%205%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49227 |  | 1 | 1 |  | 686471RFI157 | 686471 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
686453 | 11152 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | 14F008700000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-10-20 | 10/20/2022 | 2022-11-21 | [5 empty] | 3000000 | 25579 | 4995 | 4059 | 20584 | 1046 | 3949 | 25579 | 29638 |  |  | 2022-12-27 |  | 25579 | 20584 |  |  |  |  | 25579 | 20584 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/158/686453-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%207%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 4059 |  | 1 | 1 |  | 686453RFI158 | 686453 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
685943 | 11138 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | 14F008720000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-10-06 | 10/18/2022 | 2022-11-21 | [6 empty] | 318232.22 | 63260 | 49774 | 254972 | 13252 | 50008 | 318232 | 368006 |  |  | 2023-01-10 |  | 318232.22 | 254972.22 |  |  |  |  | 318232.22 | 254972.22 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/159/685943-DR4339PR-Detailed%20SOW%20Ponce%20Group%205%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49774.2 | 7501.2 | 1 | 1 |  | 685943RFI159 | 685943 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
685869 | 107780 | FAASt [Mayagüez TC] (Substation) | 14F016580000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | TRUE | 2025-09-30 | [14 empty] | 2022-10-17 | 10/17/2022 | [6 empty] | 3200000 | 14464362 |  |  |  |  | 0 | 3200000 | 3200000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/160/685869-DR4339PR0ISOW-Substation%20Minor%20Repairs%20Group%20G.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 4.5201 | 1 |  | 685869RFI160 | 685869 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
685477 | 11171 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | 14F008650000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-10-06 | 10/13/2022 | 2022-11-22 | 2022-12-13 |  |  |  |  | 3000000 | 413482 | 58304 | 67123 | 355178 | 12214 | 46090 | 413482 | 480605 |  |  | 2023-01-24 |  | 413482 | 355178 |  |  |  |  | 413482 | 355178 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/161/685477-DR4339PR-Detailed%20SOW%20Arecibo%20Group%206%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 67123 | 6914 | 1 | 1 |  | 685477RFI161 | 685477 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
685370 | 11150 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | 14F008710000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-10-06 | 10/12/2022 | 2022-11-20 | [5 empty] | 3000000 | 83809 | 14986 | 13127 | 68823 | 3139 | 11847 | 83809 | 96936 |  |  | 2023-01-10 |  | 83809 | 68823 |  |  |  |  | 83809 | 68823 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/162/685370-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13127 | 1777 | 1 | 1 |  | 685370RFI162 | 685370 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
685263 | 11143 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | 14F008730000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-10-12 | 10/11/2022 | 2022-11-21 | [5 empty] | 3000000 | 672383 | 134695 | 103281 | 537688 | 28217 | 106478 | 672383 | 775664 |  |  | 2022-12-27 |  | 672383 | 537688 |  |  |  |  | 672383 | 537688 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/163/685263-DR4339PR-Detailed%20SOW%20Ponce%20Group%206%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 103281 | 15972 | 1 | 1 |  | 685263RFI163 | 685263 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
684920 | 11573 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 14F019940000, 14F019930000, 14F019950000, 14F008410000, 14F019960000 | PBUT07 - Substation Reliability | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 75700000 | 2022-07-29 | 2022-08-25 |  | 2022-08-28 |  |  |  | 2023-06-30 | 2022-10-06 | 10/6/2022 | 2023-06-30 | 2023-11-14 |  |  |  |  | 9410000 | 6929384 | 0 | 958084 | 6929383 | 0 | 0 | 6929383 | 7887467 |  |  | 2023-12-29 |  | 6929384 | 6929384 |  |  |  |  | 6929384 | 6929384 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/164/684920-DR4339PR-Detail%20SOW%20-%20Sub%20HV%20Replacement_Group%201%20-%20Rev%200%20(1)%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Substation High Voltage Equipment Replacement | Rey Roldan Rodríguez |  |  | 958084 |  | 1 | 1 |  | 684920RFI164 | 684920 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682910 | 11212 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | 14F008670000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-19 | 9/19/2022 | 2022-11-18 | [5 empty] | 3000000 | 622823 | 105667 | 99229 | 517156 | 22135.72 | 83531.28 | 622823 | 722052 |  |  | 2023-01-31 |  | 622823 | 517156 |  |  |  |  | 622823 | 517156 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/165/682910-DR4339PR-Detailed%20SOW%20Bayamon%20Group%207%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 99229 | 12530 | 1 | 1 |  | 682910RFI165 | 682910 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682898 | 11183 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | 14F008660000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-19 | 9/19/2022 | 2022-11-17 | 2022-12-13 |  |  |  |  | 3000000 | 744027.12 | 108700.19 | 120284 | 635327 | 22771.19 | 85929 | 744027.19 | 864311.19 |  |  | 2023-01-24 |  | 744027.12 | 635326.93 |  |  |  |  | 744027.12 | 635326.93 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/166/682898-DR4339PR-Detailed%20SOW%20Bayamon%20Group%206%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 120284.25 | 12889.35 | 1 | 1 |  | 682898RFI166 | 682898 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682890 | 11136 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | 14F008690000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-19 | 9/19/2022 | 2022-11-21 | [5 empty] | 3000000 | 612378.63 | 102310.67 | 98276 | 510068 | 21432.67 | 80878 | 612378.67 | 710654.67 |  |  | 2022-12-27 |  | 612378.63 | 510067.96 |  |  |  |  | 612378.63 | 510067.96 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/167/682890-DR4339PR-Detailed%20SOW%20Caguas%20Group%2012%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 98275.6 | 12131.7 | 1 | 1 |  | 682890RFI167 | 682890 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682882 | 11130 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | 14F008680000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-19 | 9/19/2022 | 2022-11-18 | [5 empty] | 3500000 | 659039.4 | 113378.16 | 104353 | 545661 | 23751.16 | 89627 | 659039.16 | 763392.16 |  |  | 2023-01-10 |  | 659039.4 | 545661.24 |  |  |  |  | 659039.4 | 545661.24 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/168/682882-DR4339PR-Detailed%20SOW%20Caguas%20Group%2011%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 104353.35 |  | 1 | 1 |  | 682882RFI168 | 682882 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682870 | 11137 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | 14F008740000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-19 | 9/19/2022 | 2022-11-22 | [5 empty] | 3500000 | 103412.77 | 17491 | 16717 | 85922 | 0 | 17491 | 103413 | 120130 |  |  | 2022-12-27 |  | 103412.77 | 85921.77 |  |  |  |  | 103412.77 | 85921.77 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/169/682870-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%206%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 16716.65 |  | 1 | 1 |  | 682870RFI169 | 682870 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682865 | 11123 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | 14F008750000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-19 | 9/19/2022 | 2022-11-17 | [5 empty] | 3000000 | 91831 | 21148 | 13377 | 70683 | 4430 | 16718 | 91831 | 105208 |  |  | 2022-12-27 |  | 91831 | 70683 |  |  |  |  | 91831 | 70683 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/170/682865-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%207%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13377 | 2508 | 1 | 1 |  | 682865RFI170 | 682865 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682834 | 11402 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | 14F008420000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE |  | Current |  |  |  |  | 161980000 | 2023-12-28 | 2024-01-30 |  | 2024-01-27 |  |  |  | 2023-03-31 | 2022-09-16 | 9/16/2022 | 2023-03-31 | 2025-03-24 |  |  |  |  | 161980000 | 61444255.52 | 0 | 1345002.69 | 10983086.42 | 0 | 0 | 10983086.42 | 12328089.11 |  |  | 2024-02-13 | 2/13/2024 | 61444255.52 | 61444255.52 | 36917509.58 | 61444255.52 |  |  | 36917509.58 | 61444255.52 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/171/Estimates%20LPCE%20(Costa%20Sur%20Scope%203)%20With%20Out%20D%20&%20T%201-9-2024%20Rev.1%20(1).xlsx?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Costa Sur TC (Guaypao TC) - Phase II & III | Rey Roldan Rodríguez | 0 Months |  | 5090347 |  | 5.5944 | 1 |  | 682834RFI171 | 682834 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682645 | 107779 | FAASt [Maunabo TC] (Substation) | 14F016570000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | FALSE | [15 empty] | 2022-09-15 | 9/15/2022 | 2025-04-24 |  | 2025-05-21 | 2025-05-08 |  |  | 2400000 | 96115838 | 0 | 1605121.68 | 13016336.93 | 0 | 0 | 13016336.93 | 14621458.61 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/172/682645-DR4339PR-ISOW-Substation%20Minor%20Repairs%20Group%20F.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 7.3842 | 1 |  | 682645RFI172 | 682645 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682373 | 11165 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | 14F008850000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-14 | 9/12/2022 | 2022-12-08 | [5 empty] | 3000000 | 77605 | 11661 | 12740 | 65944 | 2443 | 9218 | 77605 | 90345 |  |  | 2023-01-10 |  | 77605 | 65944 |  |  |  |  | 77605 | 65944 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/173/682373-DR4339PR-Detailed%20SOW%20Caguas%20Group%2014%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12740 | 1383 | 1 | 1 |  | 682373RFI173 | 682373 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682331 | 107777 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) | 14F004430000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2022-09-12 | 9/12/2022 | [6 empty] | 4360000 | 4360000 |  |  |  |  | 0 | 4360000 | 4360000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/174/1241927-DR4339PR-SOW.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | 682331RFI174 | 682331 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682328 | 11876 | FAASt [Bayamón TC - Rebuild] (Substation) | 14F008430000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | FALSE | [6 empty] | 71000000 | 2022-07-29 | 2022-08-25 |  | 2022-08-28 |  |  |  | 2023-11-30 | 2022-09-12 | 9/12/2022 | 2023-11-27 | 2024-06-12 |  |  |  |  | 71000000 | 2637502.74 | 0 | 267793.34 | 2637502.74 | 0 | 0 | 2637502.74 | 2905296.08 | 2025-01-31 | 2025-04-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/175/682328-DR4339PR-Bayamon%20TC%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Bayamon TC - Phase II | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 682328RFI175 | 682328 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682324 | 11145 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | 14F008840000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-12 | 9/12/2022 | 2022-11-28 | [5 empty] | 3000000 | 709229.55 | 136182.31 | 110616 | 573047 | 28528.31 | 107654 | 709229.31 | 819845.31 |  |  | 2023-01-10 |  | 709229.55 | 573047.24 |  |  |  |  | 709229.55 | 573047.24 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/176/%5B682324%5D%20DR4339PR%20-%20FAASt%20%5BDistribution%20Pole%20and%20Conductor%20Repair%20-%20Caguas%20Group%2013%5D%20(Distribution)-%20SOW%20CE.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 110616.4 | 16148.1 | 1 | 1 |  | 682324RFI176 | 682324 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682228 | 11196 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | 14F008890000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-08 | 9/8/2022 | 2022-12-15 | [5 empty] | 3000000 | 952661.42 | 176882.42 | 150784 | 775779 | 37054.42 | 139828 | 952661.42 | 1103445.42 |  |  | 2023-01-31 |  | 952661.42 | 775779 |  |  |  |  | 952661.42 | 775779 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/177/682228-DR4339PR-Detailed%20SOW%20Ponce%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 150784 | 20974 | 1 | 1 |  | 682228RFI177 | 682228 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682210 | 11169 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | 14F008860000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-08 | 9/8/2022 | 2022-12-07 | [5 empty] | 3000000 | 239847.61 | 41796.87 | 38248 | 198051 | 8755.87 | 33041 | 239847.87 | 278095.87 |  |  | 2023-01-24 |  | 239847.61 | 198050.74 |  |  |  |  | 239847.61 | 198050.74 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/178/682210-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%209%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 38248.35 | 4956.15 | 1 | 1 |  | 682210RFI178 | 682210 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682180 | 11168 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | 14F008870000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-30 | 2022-09-08 | 9/8/2022 | 2022-12-08 | [5 empty] | 3000000 | 54402 | 11028 | 8414 | 43374 | 2310 | 8718 | 54402 | 62816 |  |  | 2023-01-10 |  | 54402 | 43374 |  |  |  |  | 54402 | 43374 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/179/682180-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2010%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 8414 | 1308 | 1 | 1 |  | 682180RFI179 | 682180 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682178 | 11201 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | 14F008800000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-08 | 9/8/2022 | 2022-12-07 | [5 empty] | 3000000 | 262290.31 | 53746.06 | 40949 | 208544 | 11259.06 | 42487 | 262290.06 | 303239.06 |  |  | 2023-01-31 | 4/17/2024 | 262290.31 | 208544.25 | 262290.31 | 208544.25 |  |  | 262290.31 | 208544.25 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/180/682178-DR4339PR-Detailed%20SOW%20Arecibo%20Group%207%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 40949.45 |  | 1 | 1 |  | 682178RFI180 | 682178 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682172 | 11182 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | 14F008810000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-08 | 9/8/2022 | 2022-12-15 | [5 empty] | 3500000 | 266071.35 | 57671.35 | 40930 | 208400 | 12081.35 | 45590 | 266071.35 | 307001.35 |  |  | 2023-01-24 |  | 266071.35 | 208400 |  |  |  |  | 266071.35 | 208400 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/181/682172-DR4339PR-Detailed%20SOW%20Arecibo%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 40930 | 6838 | 1 | 1 |  | 682172RFI181 | 682172 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682136 | 11203 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | 14F008830000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-07 | 9/7/2022 | 2022-12-15 | 2023-01-04 |  |  |  |  | 3500000 | 565605 | 95954.05 | 90260 | 469651 | 20101.05 | 75853 | 565605.05 | 655865.05 |  |  | 2023-01-31 |  | 565605 | 469650.95 |  |  |  |  | 565605 | 469650.95 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/182/682136-DR4339PR-Detailed%20SOW%20Bayamon%20Group%209%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 90259.5 | 11377.95 | 1 | 1 |  | 682136RFI182 | 682136 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682135 | 11149 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | 14F008820000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-11-30 | 2022-09-07 | 9/7/2022 | 2022-11-28 | [5 empty] | 3000000 | 693780.53 | 116779.74 | 109859 | 577001 | 24463.74 | 92316 | 693780.74 | 803639.74 |  |  | 2023-01-10 |  | 693780.53 | 577000.79 |  |  |  |  | 693780.53 | 577000.79 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/183/682135-DR4339PR-Detailed%20SOW%20Bayamon%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 109858.85 | 13847.4 | 1 | 1 |  | 682135RFI183 | 682135 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682121 | 11652 | FAASt - EPC -Aguirre TC-Phase II (Substation) | 14F008450000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 192270000 | 2023-12-28 | 2024-01-30 |  | 2024-01-27 |  |  |  | 2023-06-30 | 2022-09-07 | 9/7/2022 | 2023-06-01 | [5 empty] | 192270000 | 82726096.38 |  | 11520000 | 180750000 | 0 | 0 | 180750000 | 192270000 | 2024-06-01 | 2025-08-31 | 2024-03-22 |  | 82726096.38 | 82726096.38 |  |  |  |  | 82726096.38 | 82726096.38 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/184/Aguirre%20(%20El%20coqui%20TC)%20-%20FEMA%20Project%20Detailed%20Scope%20of%20Work%20rev%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Aguirre TC (El Coqui) - Phase II and Phase III | Rey Roldan Rodríguez |  |  | 7789677.44 |  | 0.45768 | 3 |  | 682121RFI184 | 682121 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682031 | 11181 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | 14F008910000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-06 | 9/6/2022 | 2022-12-19 | [5 empty] | 3000000 | 625198 | 108247 | 94044 | 516951 | 22676 | 85571 | 625198 | 719242 |  |  | 2023-01-31 |  | 625198 | 516951 |  |  |  |  | 625198 | 516951 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/185/682031-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%209%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 94044 | 12836 | 1 | 1 |  | 682031RFI185 | 682031 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
682028 | 11166 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | 14F008900000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-12-31 | 2022-09-06 | 9/6/2022 | 2022-12-07 | [5 empty] | 3000000 | 537125.3 | 105743.62 | 83822 | 431382 | 22151.62 | 83592 | 537125.62 | 620947.62 |  |  | 2023-01-10 |  | 537125.3 | 431381.68 |  |  |  |  | 537125.3 | 431381.68 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/186/682028-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%208%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 83822 | 12539 | 1 | 1 |  | 682028RFI186 | 682028 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
681672 | 11184 | FAASt Transmission Priority Pole Replacements –38kV Line 2300 (Transmission) | 14F008920000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | Restoration | FALSE | [14 empty] | 2022-09-30 | 2022-08-31 | 8/31/2022 | 2022-09-16 | 2022-12-22 |  |  |  |  | 330000 | 216367 | 2243 | 26175 | 214124 | 699 | 1544 | 216367 | 242542 |  |  | 2023-01-31 | 4/18/2024 | 216367 | 214124 | 216367 | 214124 |  |  | 216367 | 214124 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/187/681672-DR4339PR-Detailed%20SOW%20-%20Line%202300%20Rev.2.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 26175 |  | 1 | 1 |  | 681672RFI187 | 681672 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679780 | 11540 | FAASt [Bayamón Streetlighting] (Distribution) | 14F012800000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-10-31 | 2022-08-04 | 8/8/2022 | 2023-08-08 | 2023-08-29 |  |  |  |  | 46886628 | 21886903 | 1176376 | 3212958 | 20710527 | 0 | 1176376 | 21886903 | 25099861 |  |  | 2023-11-03 |  | 21886903 | 20710527 |  |  |  |  | 21886903 | 20710527 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/188/679780-DR4339PR-Detailed%20SOW%20Bayam%c3%b3n%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3212958 |  | 1 | 1 |  | 679780RFI188 | 679780 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679458 | 11114 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | 14F008580000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2023-07-31 | 2022-08-03 | 8/3/2022 | 2022-09-15 | 2022-11-17 |  |  |  |  | 3000000 | 593918 | 95482 | 95421 | 498436 | 20002 | 75480 | 593918 | 689339 |  |  | 2023-01-10 |  | 593918 | 498436 |  |  |  |  | 593918 | 498436 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/189/679458-DR4339PR-Detailed%20SOW%20Ponce%20Group%204%20Rev1%20New%20Template.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 95421 | 11322 | 1 | 1 |  | 679458RFI189 | 679458 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679457 | 11105 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | 14F008520000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-08-03 | 8/3/2022 | 2022-09-08 | 2022-11-18 |  |  |  |  | 3000000 | 746488 | 157153 | 115386 | 589335 | 33921 | 123232 | 746488 | 861874 |  |  | 2022-12-27 |  | 746488 | 589335 |  |  |  |  | 746488 | 589335 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/190/679457-DR4339PR-Detailed%20SOW%20Ponce%20Group%203%20Rev3.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 115386 |  | 1 | 1 |  | 679457RFI190 | 679457 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679153 | 11106 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | 14F008570000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-09-30 | 2022-07-28 | 7/28/2022 | 2022-09-16 | 2022-11-17 |  |  |  |  | 3000000 | 215184.01 | 51337.5 | 31068 | 163847 | 10754.5 | 40583 | 215184.5 | 246252.5 |  |  | 2022-12-27 |  | 215184.01 | 163846.51 |  |  |  |  | 215184.01 | 163846.51 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/191/679153-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%206%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 31068.05 |  | 1 | 1 |  | 679153RFI191 | 679153 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679149 | 11089 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | 14F008510000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-07-28 | 7/28/2022 | 2022-09-08 | 2022-11-15 |  |  |  |  | 3000000 | 157187 | 27443 | 25191 | 129744 | 5749 | 21694 | 157187 | 182378 |  |  | 2022-12-27 |  | 157187 | 129744 |  |  |  |  | 157187 | 129744 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/192/679149-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%205%20Rev2%20New%20Template.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 25191 |  | 1 | 1 |  | 679149RFI192 | 679149 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679134 | 11109 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | 14F008560000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-09-30 | 2022-07-28 | 7/28/2022 | 2022-09-15 | 2022-11-16 |  |  |  |  | 3000000 | 563557.15 | 110600.22 | 86724 | 452957 | 23169.22 | 87431 | 563557.22 | 650281.22 |  |  | 2023-01-10 |  | 563557.15 | 452956.93 |  |  |  |  | 563557.15 | 452956.93 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/193/679134-DR4339PR-Detailed%20SOW%20Caguas%20Group%2010%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 86724.25 | 13114.65 | 1 | 1 |  | 679134RFI193 | 679134 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679133 | 11090 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 4] (Distribution) | 14F008540000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-09-30 | 2022-07-29 | 7/28/2022 | 2022-09-14 | 2022-11-17 | 2025-05-13 | 2025-05-09 |  |  | 3000000 | 21362 | 633 | 4078 | 20729 | 133 | 500 | 21362 | 25440 |  |  | 2022-12-27 |  | 21362 | 20729 |  |  |  |  | 21362 | 20729 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/194/679133-DR4339PR-Detailed%20SOW%20Arecibo%20Group%204%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 4078 |  | 1 | 1 |  | 679133RFI194 | 679133 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679127 | 11096 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | 14F008480000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-07-29 | 7/28/2022 | 2022-08-31 | 2022-11-15 |  |  |  |  | 3000000 | 217162.81 | 46010.58 | 33340 | 46010.58 | 9638.58 | 36372 | 92021.16 | 125361.16 |  |  | 2022-12-27 |  | 217162.81 | 171152.23 |  |  |  |  | 217162.81 | 171152.23 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/195/679127-DR4339PR-Detailed%20SOW%20Arecibo%20Group%203%20Rev2%20New%20Template.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 33340.3 |  | 2.3599 | 1 |  | 679127RFI195 | 679127 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679039 | 11351 | FAASt [Caguas Streetlighting] (Distribution) | 14F009270000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-03-31 | 2022-07-27 | 7/27/2022 | 2023-03-31 | [5 empty] | 37416915 | 75586568.64 | 1849344.06 | 8534897 | 73737225 | 426651.06 | 1422693 | 75586569.06 | 84121466.06 |  |  | 2023-07-05 |  | 75586568.64 | 73737224.58 |  |  |  |  | 75586568.64 | 73737224.58 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/196/679039-DR4339PR-Detailed%20SOW%20Caguas%20Phase%201%20High%20Priority%20Rev0%20-%20signed%20-%20DSOW.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 8534896.89 |  | 1 | 1 |  | 679039RFI196 | 679039 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679035 | 11861 | FAASt [Telecom Infrastructure – Group A] (Telecommunication) | 14F004570000, 14F004550000, 14F004560000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  | TRUE | 2025-07-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2022-07-27 | 7/27/2022 | [6 empty] | 5900000 | 5900000 |  |  |  |  | 0 | 5900000 | 5900000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/197/PR679035%20-%20DR4339PR%20-%20Telecom%20Infraestructure%20-%20Group%20A%20SOW.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | 679035RFI197 | 679035 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679033 | 11098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | 14F008500000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-07-27 | 7/27/2022 | 2022-09-08 | 2022-11-15 |  |  |  |  | 3000000 | 908942 | 179902 | 140628 | 729040 | 37687 | 142215 | 908942 | 1049570 |  |  | 2022-12-27 |  | 908942 | 729040 |  |  |  |  | 908942 | 729040 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/198/679033-DR4339PR-Detailed%20SOW%20Caguas%20Group%209%20Rev2%20New%20Template.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 140628 |  | 1 | 1 |  | 679033RFI198 | 679033 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679026 | 11107 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | 14F008590000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-09-30 | 2022-07-27 | 7/27/2022 | 2022-09-15 | 2022-11-17 |  |  |  |  | 3000000 | 590296 | 106510 | 93451 | 483786 | 22312 | 84198 | 590296 | 683747 |  |  | 2022-12-27 |  | 590296 | 483786 |  |  |  |  | 590296 | 483786 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/199/679026-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%205%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 93451 | 12630 | 1 | 1 |  | 679026RFI199 | 679026 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679025 | 11101 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | 14F008530000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-07-27 | 7/27/2022 | 2022-09-08 | 2022-11-15 |  |  |  |  | 3000000 | 298631 | 55558 | 46884 | 243073 | 11639 | 43919 | 298631 | 345515 |  |  | 2022-12-27 |  | 298631 | 243073 |  |  |  |  | 298631 | 243073 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/200/679025-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%204%20Rev2%20New%20Template.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 46884 | 6588 | 1 | 1 |  | 679025RFI200 | 679025 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
679006 | 11862 | FAASt [Test and Technology Laboratory] (Building) | 14F019640000 | PBFM01 - Facilities Dev & Implem | Building | IT OT Telecom Systems and Network | Improved | FALSE | [6 empty] | 11880000 | 2022-05-20 | 2022-07-11 |  | 2022-06-19 |  |  |  | 2022-11-30 | 2022-07-27 | 7/26/2022 | 2022-11-02 | 2024-05-20 |  |  |  |  | 11880000 | 25192128 | 8186857 | 386408 | 12739422 | 500959 | 7685898 | 20926279 | 21312687 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/201/10163-FA-SOW-0003-Rev%201%202023.05%2030.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Test and Technology Laboratory | Rey Roldan Rodríguez |  |  |  |  | 1.2039 | 1 |  | 679006RFI201 | 679006 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
678988 | 11113 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | 14F008550000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-09-30 | 2022-07-26 | 7/26/2022 | 2022-09-15 | 2022-11-17 |  |  |  |  | 3000000 | 1117787.16 | 206650.4 | 175441 | 911137 | 0 | 206650.4 | 1117787.4 | 1293228.4 |  |  | 2022-12-27 |  | 1117787.16 | 911136.76 |  |  |  |  | 1117787.16 | 911136.76 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/202/678988-DR4339PR-Detailed%20SOW%20Bayamon%20Group%205%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 175440.55 |  | 1 | 1 |  | 678988RFI202 | 678988 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
678985 | 11103 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | 14F008490000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-07-26 | 7/26/2022 | 2022-08-29 | 2022-11-15 |  |  |  |  | 3000000 | 407945.84 | 54317.84 | 66915 | 353628 | 11378.84 | 42939 | 407945.84 | 474860.84 |  |  | 2022-12-27 |  | 407945.84 | 353628 |  |  |  |  | 407945.84 | 353628 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/203/678985-DR4339PR-Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%204.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 66915 |  | 1 | 1 |  | 678985RFI203 | 678985 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
678800 | 11425 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 14F004590000, 14F004580000, 14F004620000, 14F004610000, 14F004600000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | Restoration | FALSE | [15 empty] | 2022-07-22 | 7/22/2022 | 2024-05-14 | 2025-07-17 |  |  |  |  | 10500000 |  | 55895.84 | 2828793.1 | 13148929.44 | 10487.44 | 45408.4 | 13204825.28 | 16033618.38 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/204/1237892-DR4339PR-SOW%20(2).pdf?web=1 | 4/04/2024: QC Review Complete | 2025-07-23 13:44 | 2023-08-14 11:10 | Jahdiel Franqui | Telecom Infrastructure | Marlina Crespo | 7-12 months |  |  |  | 0 | 5 |  | 678800RFI204 | 678800 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
678795 | 11535 | FAASt [Arecibo Streetlighting] (Distribution) | 14F012790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-07-22 | 7/22/2022 | 2023-06-30 | 2023-12-19 |  |  |  |  | 32568618 | 14607500.56 | 1527389 | 2673960 | 14601018 | 222962 | 1304427 | 16128407 | 18802367 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/205/678795-DR4339PR-Detailed%20SOW%20Arecibo%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.9057 | 1 |  | 678795RFI205 | 678795 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
678794 | 11527 | FAASt [Ponce Streetlighting] (Distribution) | 14F012850000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-07-22 | 7/22/2022 | 2023-06-30 | 2023-12-19 |  |  |  |  | 44090477 | 16043135.52 | 1444528 | 2808935 | 16043136 | 215232 | 1229296 | 17487664 | 20296599 | 2024-12-31 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/206/678794-DR4339PR-Detailed%20SOW%20Ponce%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.9174 | 1 |  | 678794RFI206 | 678794 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
678793 | 11532 | FAASt [Mayagüez Streetlighting] (Distribution) | 14F012840000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-07-22 | 7/22/2022 | 2023-07-01 | 2023-07-27 |  |  |  |  | 24355947 | 12371384.46 | 1352204.36 | 2291581 | 11019180 | 0 | 1352204.36 | 12371384.36 | 14662965.36 |  |  | 2023-11-03 |  | 12371384.46 | 11019180.1 |  |  |  |  | 12371384.46 | 11019180.1 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/207/678793-DR4339PR-Detailed%20SOW%20Mayaguez%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2291580.6 |  | 1 | 1 |  | 678793RFI207 | 678793 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
678789 | 11533 | FAASt [Carolina Streetlighting] (Distribution) | 14F012810000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-07-22 | 7/22/2022 | 2023-07-01 | 2023-07-27 |  |  |  |  | 37245221 | 16024559.58 | 1158946.56 | 2559493 | 14865613 | 0 | 1158946.56 | 16024559.56 | 18584052.56 |  |  | 2023-11-03 |  | 16024559.58 | 14865613.02 |  |  |  |  | 16024559.58 | 14865613.02 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/208/678789-DR4339PR-Detailed%20SOW%20Carolina%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(1).pdf |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2559492.85 |  | 1 | 1 |  | 678789RFI208 | 678789 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
675406 | 107767 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) | 14F003900000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 46200000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  |  | 2022-06-15 | 6/15/2022 | [6 empty] | 46200000 | 46200000 |  |  |  |  | 0 | 46200000 | 46200000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/209/675406-DR4339PR-Two-Way%20Land%20Mobile%20Radio%20Network.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Two Way Land Mobile Radio Network | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | 675406RFI209 | 675406 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
675345 | 107766 | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) |  | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | Restoration | FALSE | [6 empty] | 35700000 | 2022-08-10 | 2022-08-25 |  | 2022-09-09 |  |  |  | 2023-04-30 | 2022-06-14 | 6/14/2022 | 2023-04-10 | 2024-02-14 |  |  |  |  | 35700000 | 21640536 | 0 | 798980.71 | 8378200.51 | 0 | 0 | 8378200.51 | 9177181.22 | 2025-01-31 | 2025-06-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/210/675345-%20IT-OT%20System%20Reparation%20Detailed%20%20Scope%20of%20Work%20-%20signed.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | IT OT Technology Systems Reparations | Rey Roldan Rodríguez |  |  |  |  | 2.583 | 1 |  | 675345RFI210 | 675345 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
674506 | 107765 | FAASt [Field Area Network (FAN)] (Telecommunication) | 14F002090000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 330000000 |  |  | 2025-02-07 | [5 empty] | 2022-06-03 | 6/3/2022 | [6 empty] | 330000000 | 330000000 |  |  |  |  | 0 | 330000000 | 330000000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/211/921840-DR4339PR-SOW%20(1).pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch.This project is being developed and internal strategy needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 8/26/2024. | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Field Area Network(FAN) | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 674506RFI211 | 674506 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
674098 | 10824 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | 14F004040000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-06-02 | 5/27/2022 | 2022-06-27 | [5 empty] | 2500000 | 107755 | 23322 | 16516 | 84433 | 0 | 23322 | 107755 | 124271 |  |  | 2022-08-08 |  | 107755 | 84433 |  |  |  |  | 107755 | 84433 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/212/674098-DR4339PR-Detailed%20SOW%20Caguas%20Group%207%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 16517 |  | 1 | 1 |  | 674098RFI212 | 674098 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
674096 | 10935 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | 14F004030000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-06-02 | 5/27/2022 | 2022-07-15 | 2022-08-23 |  |  |  |  | 3000000 | 2092280 | 318852 | 332705 | 1773428 | 66795 | 252057 | 2092280 | 2424985 |  |  | 2022-10-17 |  | 2092280 | 1773428 |  |  |  |  | 2092280 | 1773428 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/213/674096-DR4339PR-Detailed%20SOW%20Caguas%20Group%206%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 332705 |  | 1 | 1 |  | 674096RFI213 | 674096 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
674092 | 10893 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | 14F004020000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-06-02 | 5/27/2022 | 2022-06-24 | 2022-08-08 |  |  |  |  | 3000000 | 531730 | 90422 | 82578 | 441308 | 18942 | 71480 | 531730 | 614308 |  |  | 2022-09-16 |  | 531730 | 441308 |  |  |  |  | 531730 | 441308 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/214/674092-DR4339PR-Detailed%20SOW%20Caguas%20Group%205%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 82578 |  | 1 | 1 |  | 674092RFI214 | 674092 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
674088 | 10933 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | 14F004000000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-06-02 | 5/27/2022 | 2022-07-14 | [5 empty] | 3500000 | 1702021 | 289653 | 267370 | 1412368 | 60678 | 228975 | 1702021 | 1969391 |  |  | 2022-10-17 |  | 1702021 | 1412368 |  |  |  |  | 1702021 | 1412368 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/215/674088-DR4339PR-Detailed%20SOW%20Caguas%20Group%203%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 267370 |  | 1 | 1 |  | 674088RFI215 | 674088 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
674083 | 10827 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | 14F003990000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-06-02 | 5/27/2022 | 2022-07-01 | [5 empty] | 3000000 | 2110462 | 362533 | 335721.9 | 1747928.9 | 75946 | 286587 | 2110461.9 | 2446183.8 |  |  | 2022-08-08 |  | 2110462 | 1747929 |  |  |  |  | 2110462 | 1747929 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/216/674083-DR4339PR-Detailed%20SOW%20Caguas%20Group%202%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 335722 |  | 1 | 1 |  | 674083RFI216 | 674083 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
674072 | 10906 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | 14F003980000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-06-02 | 5/27/2022 | 2022-07-06 | [5 empty] | 3000000 | 1111094 | 238203 | 171585 | 872891 | 49900.3 | 188302.7 | 1111094 | 1282679 |  |  | 2022-09-16 |  | 1111094 | 872891 |  |  |  |  | 1111094 | 872891 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/217/674072-DR4339PR-Detailed%20SOW%20Caguas%20Group%201%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 171585 |  | 1 | 1 |  | 674072RFI217 | 674072 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673920 | 107764 | FAASt [Isla Grande 1101] (Substation) | 14F001860000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 600000 | [8 empty] | 2022-06-21 | 5/25/2022 | [6 empty] | 600000 | 600000 |  |  |  |  | 0 | 600000 | 600000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/218/673920-DR4339PR-ISOW-Isla%20Grande%201101-Substation.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Isla Grande 1101 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 673920RFI218 | 673920 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673848 | 10751 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | 14F004080000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-05-25 | 5/25/2022 | 2022-06-02 | 2022-06-24 |  |  |  |  | 2500000 | 49345 | 5620 | 13281 | 43725 | 1177 | 4443 | 49345 | 62626 |  |  | 2022-07-12 |  | 49345 | 43725 |  |  |  |  | 49345 | 43725 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/219/673848-DR4339PR-Detalied%20SOW%20Carolina%20Group%203%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13281 |  | 1 | 1 |  | 673848RFI219 | 673848 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673847 | 10812 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | 14F004070000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-05-25 | 5/25/2022 | 2022-06-22 | 2022-07-19 |  |  |  |  | 2500000 | 240513 | 49943 | 37242 | 190570 | 10462 | 39481 | 240513 | 277755 |  |  | 2022-08-08 |  | 240513 | 190570 |  |  |  |  | 240513 | 190570 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/220/673847-DR4339PR-Detalied%20SOW%20Carolina%20Group%202%20Rev2.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 37242 |  | 1 | 1 |  | 673847RFI220 | 673847 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673844 | 10864 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | 14F004170000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-05-25 | 5/25/2022 | 2022-07-07 | [5 empty] | 2500000 | 1392064.88 | 319213.9 | 208800.6 | 1072851 | 0 | 319213.9 | 1392064.9 | 1600865.5 |  |  | 2022-08-24 |  | 1392064.88 | 1072850.98 |  |  |  |  | 1392064.88 | 1072850.98 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/221/673844-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%203%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 208800.58 |  | 1 | 1 |  | 673844RFI221 | 673844 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673843 | 10922 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | 14F003970000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-05-25 | 5/25/2022 | 2022-07-11 | [5 empty] | 3000000 | 1131855 | 227661 | 175796 | 904194 | 47692 | 179969 | 1131855 | 1307651 |  |  | 2022-10-17 |  | 1131855 | 904194 |  |  |  |  | 1131855 | 904194 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/222/673843-DR4339PR-Detailed%20SOW%20Bayamon%20Group%203%20Rev0.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 175796 |  | 1 | 1 |  | 673843RFI222 | 673843 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673839 | 10742 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | 14F003960000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-05-31 | 2022-05-25 | 5/25/2022 | 2022-06-01 | 2022-06-21 |  |  |  |  | 2500000 | 26298 | 5830 | 10153 | 20468 | 1221 | 4609 | 26298 | 36451 |  |  | 2022-07-12 |  | 26298 | 20468 |  |  |  |  | 26298 | 20468 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/223/673839-DR4339PR-Detailed%20SOW%20Bayamon%20Group%202%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 10152 |  | 1 | 1 |  | 673839RFI223 | 673839 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673838 | 10764 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | 14F004160000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-05-25 | 5/25/2022 | 2022-06-02 | 2022-06-24 |  |  |  |  | 2500000 | 357614 | 73265 | 55024 | 284348 | 15348 | 57917 | 357613 | 412637 |  |  | 2022-07-12 |  | 357614 | 284349 |  |  |  |  | 357614 | 284349 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/224/673838-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%202%20Rev1.pdf?web=1 |  | 2025-07-18 18:27 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 55025 |  | 1 | 1 |  | 673838RFI224 | 673838 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673836 | 11041 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | 14F003950000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-05-25 | 5/25/2022 | 2022-07-01 | 2022-10-10 |  |  |  |  | 3500000 | 5751036.48 | 1064121.8 | 900015 | 4686915 | 0 | 1064121.8 | 5751036.8 | 6651051.8 |  |  | 2022-12-21 |  | 5751036.48 | 4686914.68 |  |  |  |  | 5751036.48 | 4686914.68 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/225/673836-DR4339PR-Detailed%20SOW%20Bayamon%20Group%201%20Rev3.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 900014.8 |  | 1 | 1 |  | 673836RFI225 | 673836 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673818 | 10821 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | 14F004150000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-05-25 | 5/25/2022 | 2022-06-30 | [5 empty] | 3500000 | 793418 | 171614 | 121044 | 621804 | 0 | 171614 | 793418 | 914462 |  |  | 2022-08-08 |  | 793418 | 621804 |  |  |  |  | 793418 | 621804 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/226/673818-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%201%20Rev0.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 121044 |  | 1 | 1 |  | 673818RFI226 | 673818 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673795 | 10777 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | 14F004120000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-05-26 | 5/24/2022 | 2022-06-13 | 2022-06-29 |  |  |  |  | 3500000 | 1794117 | 368954 | 278117 | 1425163 | 77291 | 291663 | 1794117 | 2072234 |  |  | 2022-08-02 |  | 1794117 | 1425163 |  |  |  |  | 1794117 | 1425163 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/227/673795-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%204%20Rev1.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 278116 |  | 1 | 1 |  | 673795RFI227 | 673795 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673775 | 10962 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | 14F004110000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-05-24 | 5/24/2022 | 2022-07-26 | 2022-11-01 |  |  |  |  | 4000000 | 4432647.91 | 859175 | 689888 | 3575455 | 79570.1 | 779604.9 | 4434630 | 5124518 |  |  | 2022-12-27 |  | 4432647.91 | 3575454.81 |  |  |  |  | 4432647.91 | 3575454.81 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/228/673775-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%203%20Rev3.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 689888.45 |  | 0.99955 | 1 |  | 673775RFI228 | 673775 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673774 | 10773 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | 14F004090000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-05-24 | 5/24/2022 | 2022-06-13 | 2022-06-30 |  |  |  |  | 4000000 | 1766951 | 358420 | 273831 | 1408531 | 75084 | 283336 | 1766951 | 2040782 |  |  | 2022-08-02 |  | 1766951 | 1408531 |  |  |  |  | 1766951 | 1408531 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/229/673774-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%201%20Rev1.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 273831 |  | 1 | 1 |  | 673774RFI229 | 673774 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673772 | 10919 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | 14F004100000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-05-24 | 5/24/2022 | 2022-07-19 | 2022-09-09 |  |  |  |  | 4500000 | 4122520 | 835984 | 636837 | 3286536 | 175127 | 660857 | 4122520 | 4759357 |  |  | 2022-10-24 |  | 4122520 | 3286536 |  |  |  |  | 4122520 | 3286536 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/230/673772-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%202%20Rev1.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 636837 |  | 1 | 1 |  | 673772RFI230 | 673772 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673771 | 10909 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | 14F003930000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [6 empty] | 600000000 | [7 empty] | 2022-07-31 | 2022-05-24 | 5/24/2022 | 2022-07-11 | [5 empty] | 3000000 | 2366560.53 | 472527 | 370850 | 1894034 | 98988 | 373539 | 2366561 | 2737411 |  |  | 2022-10-17 |  | 2366560.53 | 1894033.53 |  |  |  |  | 2366560.53 | 1894033.53 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/231/673771-DR4339PR-Detailed%20SOW%20Arecibo%20Group%201%20Rev0.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 370850.25 |  | 1 | 1 |  | 673771RFI231 | 673771 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673691 | 10710 | FAASt [Equipment and Materials] | 14F008760000 | PBOP06 - Materials Management | Other | TBD | NA | [16 empty] | 2022-05-26 | 5/23/2022 | [7 empty] | 3075694700.2 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2022-06-10 | 12/29/2023 | 1506189735.2 |  | 797183125.2 | 797183125.2 | 1733204375 | 1733204375 | 1733204375 | 1733204375 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/232/PRJ_Report_673691_20241106.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  | 0 |  |  |  |  | 673691RFI232 | 673691 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673504 | 11317 | FAASt [Gurabo Streetlighting] (Distribution) | 14F004630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-02-28 | 2022-05-19 | 5/19/2022 | 2023-02-28 | [5 empty] | 12840220 | 20742294 | 1533300 | 3043675 | 19208994 | 400644 | 1132656 | 20742294 | 23785969 |  |  | 2023-05-17 |  | 20742294 | 19208994 |  |  |  |  | 20742294 | 19208994 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/233/673504-FEMA%20Detailed%20SOW-Streetlight-%20Gurabo.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3043676 |  | 1 | 1 |  | 673504RFI233 | 673504 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
673292 | 11452 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 14F004510000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | Restoration | FALSE | [6 empty] | 96500000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2024-03-31 | 2022-05-17 | 5/17/2022 | 2024-02-05 | 2025-04-03 | 2025-07-25 | 2025-05-30 | Previous Comment Applies: Field EHP: ESA Consultation letter submitted to USFWS on 5/28/2025. Waiting for response. ECD 7/25/2025. |  | 4800000 | 6767654.15 | 49577.82 | 1075319.59 | 8129023.86 | 49577.82 | 0 | 8178601.68 | 9253921.27 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/234/1230468%20D4339PR-ISOW-Telecom%20Infrastructure-Cerro%20Puntas%20(2).pdf?web=1 |  | 2025-07-25 15:30 | 2023-08-14 11:10 | Jahdiel Franqui | Telecom Infrastructure | Maria Mujica Gonzalez |  |  |  |  | 0.82748 | 1 |  | 673292RFI234 | 673292 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
671502 | 11522 | FAASt [Yabucoa Streetlighting] (Distribution) | 14F004530000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-04-26 | 4/26/2022 | 2023-07-01 | 2023-07-27 |  |  |  |  | 11205044 | 16883989.33 | 1986076 | 2741367 | 14918273 | 0 | 1986076 | 16904349 | 19645716 |  |  | 2023-12-29 |  | 16883989.33 | 14918381.07 |  |  |  |  | 16883989.33 | 14918381.07 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/235/671502-DR4339PR-Detailed%20SOW%20Yabucoa%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2742910.41 |  | 0.9988 | 1 |  | 671502RFI235 | 671502 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
671400 | 11529 | FAASt [Barceloneta Streetlighting] (Distribution) | 14F004540000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-04-25 | 4/25/2022 | 2023-07-01 | 2023-12-19 |  |  |  |  | 6352659 | 8163052.71 | 1109633 | 1890247 | 8163053 | 198246 | 911387 | 9272686 | 11162933 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/236/671400-DR4339PR-Detailed%20SOW%20Barceloneta%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88033 | 1 |  | 671400RFI236 | 671400 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
671396 | 11530 | FAASt [Utuado Streetlighting] (Distribution) | 14F004520000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-04-25 | 4/25/2022 | 2023-07-01 | 2024-01-16 |  |  |  |  | 10162619 | 17961216.53 | 2911033 | 3174654 | 17961217 | 437244 | 2473789 | 20872250 | 24046904 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/237/671396-DR4339PR-Detailed%20SOW%20Utuado%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.86053 | 1 |  | 671396RFI237 | 671396 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
668669 | 107754 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | 14F003670000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements | Restoration |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 31300000 | [7 empty] | 2022-04-30 | 2022-03-30 | 3/30/2022 | 2022-04-04 | [5 empty] | 110470000 | 307465 | 0 |  | 307465 | 0 | 0 | 307465 | 307465 | 2025-08-31 | 2026-01-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/238/668669-DR4339PR-Detailed%20SOW%20-Transmission%20Priority%20Pole%20Replacement-%20Mora%2050500%20Rev0.pdf?web=1 | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | 230 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 668669RFI238 | 668669 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
668665 | 107753 | FAASt [Cybersecurity Program Implementation] (Telecommunication) | 14F002070000 | PBIT02 - Cybersecurity Program | Telecommunications | IT OT Cybersecurity Program | Restoration | FALSE | [6 empty] | 24500000 | 2022-01-24 | 2022-03-15 |  | 2022-02-23 |  |  |  | 2023-10-31 | 2022-03-30 | 3/30/2022 | 2023-10-31 | 2024-05-08 |  |  |  |  | 24500000 | 24500000 | 3619308 | 1973160 | 32570697 | 206736 | 3412572 | 36190005 | 38163165 | 2024-08-31 | 2024-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/239/668665-DR4339PR-Cybersecurity%20Program%20Implementation%20(Telecommunication).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Cybersecurity Implementation Program | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.67698 | 2 |  | 668665RFI239 | 668665 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
668592 | 10891 | FAASt [Transmission Priority Pole Replacement – Line 9800] (Transmission) | 14F004460000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-03-29 | 3/29/2022 | 2022-07-07 | [5 empty] | 2200000 | 420866 | 0 | 43984 | 420867 | 0 | 0 | 420867 | 464851 |  |  | 2022-09-16 |  | 420866 | 420866 |  |  |  |  | 420866 | 420866 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/240/668592-DR4339PR-Detailed%20SOW%20-%20Line%209800%20Rev.0.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 43984 |  | 1 | 1 |  | 668592RFI240 | 668592 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
668583 | 10800 | FAASt [Transmission Priority Pole Replacements – Line 13300] (Transmission) | 14F004470000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | Restoration | FALSE | [14 empty] | 2022-06-30 | 2022-03-29 | 3/29/2022 | 2022-06-08 | [5 empty] | 2830000 | 453597 | 0 | 81996 | 453597 | 0 | 0 | 453597 | 535593 |  |  | 2022-08-02 |  | 453597 | 453597 |  |  |  |  | 453597 | 453597 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/241/668583-DR4339PR-Detailed%20SOW%20-%20Line%2013300%20Rev1.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 81996 |  | 1 | 1 |  | 668583RFI241 | 668583 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
666894 | 11519 | FAASt [San Juan Streetlighting] (Distribution) | 14F008790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2024-07-31 | 2022-03-16 | 3/16/2022 | 2023-07-01 | 2023-12-19 |  |  |  |  | 73611536 | 30550204.86 | 3532039 | 4738922 | 30543791 | 474312 | 3057727 | 34075830 | 38814752 | 2024-08-31 | 2024-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/242/666894-DR4339PR-Detailed%20SOW%20San%20Juan%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.89654 | 1 |  | 666894RFI242 | 666894 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
662238 | 107742 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 14F004500000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | Restoration | FALSE | [6 empty] | 6000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2023-05-31 | 2022-02-14 | 2/14/2022 | 2023-05-23 | 2024-09-13 |  |  |  |  | 6000000 | 16046926.54 | 1247527.04 | 1081553.96 | 14800399.5 | 84956.04 | 1162571 | 16047926.54 | 17129480.5 | 2024-07-31 | 2024-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/243/662238%20FEMA%20DSOW%20Microwave%20PTP%20Backbone%20Signed%20EP%20ML%20TP%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Microwave Point-to-Point | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.99994 | 1 |  | 662238RFI243 | 662238 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
660437 | 11097 | FAASt [Manati Streetlighting] (Distribution) | 14F004190000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-02-02 | 1/27/2022 | 2022-07-29 | 2022-11-14 |  |  |  |  | 12758461 | 28636829 | 1568964 | 5821636 | 27067865 | 380359 | 1188605 | 28636829 | 34458465 |  |  | 2023-01-24 |  | 28636829 | 27067865 |  |  |  |  | 28636829 | 27067865 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/244/660437-Streetlight-Manati%20DSOW_Rev1.pdf?web=1 |  | 2025-07-21 15:24 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 5821635 |  | 1 | 1 |  | 660437RFI244 | 660437 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
660422 | 11566 | FAASt [Physical Security - Group 4] (Substation) | 14F003870000, 14F003750000 | PBUT18 - Substation Security | Substation | Substation Security | Restoration | FALSE | [14 empty] | 2023-06-30 | 2022-02-22 | 1/27/2022 | 2023-06-05 | 2023-09-21 |  |  |  |  | 800000 | 3816798 | 338280 | 766618 | 3478518 | 0 | 338280 | 3816798 | 4583416 |  |  | 2023-12-29 |  | 3816798 | 3478518 |  |  |  |  | 3816798 | 3478518 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/245/660422%20DR4339PR%20Physical%20Security%20Group%204%20SOW.pdf?web=1 |  | 2025-07-21 15:30 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Jose J Ramos Figueroa |  |  | 460523 |  | 1 | 1 |  | 660422RFI245 | 660422 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
660239 | 10857 | FAASt [Villalba Streetlighting] (Distribution) | 14F004200000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-01-26 | 1/26/2022 | 2022-07-07 | 2022-07-21 |  |  |  |  | 5577994 | 10872401.71 | 681865.66 | 2630719 | 10190536 | 84516.08 | 597349.58 | 10872401.66 | 13503120.66 |  |  | 2022-08-24 |  | 10872401.71 | 10190536.05 |  |  |  |  | 10872401.71 | 10190536.05 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/246/660239-DSOW-Distribution%20Streetlighting%20-%20Villalba_Rev3.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2630718.61 |  | 1 | 1 |  | 660239RFI246 | 660239 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
660227 | 11095 | FAASt [Hatillo Streetlighting] (Distribution) | 14F004340000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-01-27 | 1/26/2022 | 2022-08-08 | 2022-11-11 |  |  |  |  | 12447777 | 20334482.95 | 1764387.7 | 4317860 | 18570180 | 448282.64 | 1316105.06 | 20334567.7 | 24652427.7 |  |  | 2023-01-24 |  | 20334482.95 | 18570095.25 |  |  |  |  | 20334482.95 | 18570095.25 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/247/660227-DR4339PR-Distribution%20Streetlighting%20-%20DSOW-Aibonito_Rev2.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 4317860.43 |  | 1 | 1 |  | 660227RFI247 | 660227 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
659968 | 11318 | FAASt [San Germán Streetlighting] (Distribution) | 14F004330000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2023-03-31 | 2022-01-24 | 1/24/2022 | 2023-03-14 | [5 empty] | 13034397 | 34882926 | 4033578 | 4619207 | 30849348 | 1029513 | 3004065 | 34882926 | 39502133 |  |  | 2023-05-04 |  | 34882926 | 30849348 |  |  |  |  | 34882926 | 30849348 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/248/FEMA%20Detailed%20Scope%20of%20Work%20San%20Germ%C3%A1n%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 4619207 |  | 1 | 1 |  | 659968RFI248 | 659968 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
659715 | 10876 | FAASt [Aibonito Streetlighting] (Distribution) | 14F004210000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-01-21 | 1/21/2022 | 2022-07-07 | 2022-11-14 |  |  |  |  | 6013360 | 7253285 | 178787 | 1880873 | 7074498 | 49247 | 129540 | 7253285 | 9134158 |  |  | 2022-12-27 |  | 7253285 | 7074498 |  |  |  |  | 7253285 | 7074498 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/249/659715-DR4339PR-Distribution%20Streetlighting%20-%20DSOW-Aibonito_Rev2.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1880873 |  | 1 | 1 |  | 659715RFI249 | 659715 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
659625 | 11099 | FAASt [Dorado Streetlighting] (Distribution) | 14F004350000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-08-31 | 2022-01-20 | 1/20/2022 | 2022-09-08 | 2022-11-11 |  |  |  |  | 11389001 | 24370617 | 1505645 | 4716594 | 22864972 | 355973 | 1149672 | 24370617 | 29087211 |  |  | 2023-01-24 |  | 24370617 | 22864972 |  |  |  |  | 24370617 | 22864972 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/250/659625-DR4339PR-SOW-Distribution%20Streetlighting%20-%20Dorado_Rev2.pdf?web=1 |  | 2025-07-21 16:23 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 3031749 | 165500 | 1 | 1 |  | 659625RFI250 | 659625 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
659623 | 10884 | FAASt [Cataño Streetlighting] (Distribution) | 14F004180000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-07-31 | 2022-01-20 | 1/20/2022 | 2022-07-07 | 2022-11-11 |  |  |  |  | 5191684 | 17562047 | 565289 | 3574763 | 16996758 | 49247 | 516042 | 17562047 | 21136810 |  |  | 2022-12-27 |  | 17562047 | 16996758 |  |  |  |  | 17562047 | 16996758 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/251/659623-DSOW-Distribution%20Streetlighting%20-%20Cata%C3%B1o-Rev0.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3574763 |  | 1 | 1 |  | 659623RFI251 | 659623 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
657300 | 10957 | FAASt [ENERGY MANAGEMENT SYSTEM (EMS)] (Telecommunication) | 14F000020000 | PBUT22 - Critical Energy Mgmt Sy | Telecommunications | IT OT Telecom Systems and Network | Improved | FALSE |  | Past |  |  |  |  | 42000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2022-06-30 | 2022-01-19 | 1/19/2022 | 2022-06-27 | 2024-08-26 |  |  |  |  | 126000000 | 48941484 | 0 | 2041312 | 48941484 | 0 | 0 | 48941484 | 50982796 |  |  | 2022-10-17 | PENDING | 48941484 | 48941484 | 164579862 | 164579862 |  |  | 48941484 | 48941484 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/252/55110%20-%20FAASt%20657300_Phase%202%20EMS_FEMA%20Project%20Detailed%20Scope%20of%20Work_2023.8.21%20Rev%202%20-%20signed.pdf | 5/16/2024 - Previously, 657300 included the EMS (software / servers) and the PCC / SCC (2 buildings) projects. The PCC / SCC projects have been moved to 746545. This means 657300 includes only the EMS (software / servers) scope. Therefore, 657300 is a Telecommunications project, not a Building project. [Update provided by Andrew Buresh, PM for 746545. Phil Vallejo is the PM for 65730] | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Primary Control Center Secondary Data Center & Control Room | Rey Roldan Rodríguez | 0 Months |  | 2041312 |  | 1 | 1 |  | 657300RFI252 | 657300 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551963 | 11859 | FAASt [Transport Network] (Telecommunication) | 14F002140000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | Restoration | FALSE |  | Current |  |  |  |  | 185000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2023-07-31 | 2022-02-01 | 12/22/2021 | 2023-07-29 | 2025-03-21 | 2025-05-30 | 2025-05-22 |  |  | 185000000 | 84287009 | 0 | 836416.02 | 6633463.21 | 0 | 0 | 6633463.21 | 7469879.23 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/253/551963%20Transport%20Network%20DSOW%20Rev%203%207-28-23%20(EP%20ML%20JC)%20-%20signed.pdf?web=1 | 3/27/2024: QC Review Complete 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Transport Network | Rey Roldan Rodríguez | 0 Months |  |  |  | 12.7063 | 1 |  | 551963RFI253 | 551963 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551927 | 107736 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | 14F003910000 | PBUT07 - Substation Reliability | Substation | IT OT Telecom Systems and Network | Restoration | FALSE | [14 empty] | 2024-01-31 | 2022-01-10 | 12/22/2021 | 2024-04-30 | 2025-07-06 | 2024-10-29 | 2024-10-15 |  |  | 17000000 | 26178032.7 | 3299617.88 | 2431898.51 | 16781290.09 | 409517.03 | 2890100.85 | 20080907.97 | 22512806.48 | 2025-04-30 | 2024-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/254/551927-DR4339PR-SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group%203.pdf?web=1 | 4/17/2024: QC Review Complete | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Rey Roldan Rodríguez |  |  |  |  | 1.3036 | 1 |  | 551927RFI254 | 551927 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551926 | 107735 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 14F002130000 | PBUT07 - Substation Reliability | Telecommunications | IT OT Telecom Systems and Network | Restoration | FALSE | [14 empty] | 2023-09-30 | 2022-01-10 | 12/22/2021 | 2023-09-29 | 2025-06-05 | 2025-08-08 | 2025-07-14 |  |  | 5600000 | 8456184.1 | 1073462.61 | 800287.41 | 5664186.55 | 134453.44 | 939009.17 | 6737649.16 | 7537936.57 | 2024-11-30 | 2025-02-28 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/255/551926-DR4339PR-SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group%202.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Rey Roldan Rodríguez |  |  |  |  | 1.2551 | 1 |  | 551926RFI255 | 551926 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551925 | 11537 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 14F002120000, 10F007390000, 10F007430000, 10F007400000, 10F007410000, 10F007420000, 10F007440000 | PBUT07 - Substation Reliability | Telecommunications | IT OT Telecom Systems and Network | Restoration | FALSE |  | Past |  |  |  |  | 30000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2022-07-31 | 2022-01-10 | 12/22/2021 | 2022-07-15 | 2024-07-18 |  |  |  |  | 7000000 | 7664336.14 | 1701923.62 | 1248409.29 | 5962412.52 | 680597.9 | 1021325.72 | 7664336.14 | 8912745.43 | 2024-06-30 | 2024-11-30 | 2024-11-01 |  | 7664336.14 | 5962412.52 |  |  |  |  | 7664336.14 | 5962412.52 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/256/551925-DR4339PR-Detailed%20Scope%20of%20Work%20SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group1_Revised%207-25-23%20LPCE%20Adjusted%20to%20HM.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short & Long List | 2025-07-21 16:34 | 2023-08-14 11:10 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Jose J Ramos Figueroa |  |  | 1248409.19 | 294727.35 | 1 | 1 |  | 551925RFI256 | 551925 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551918 | 11409 | FAASt [Crematorio - 1512] (Substation) | 14F001810000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 10600000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-12-21 | 12/21/2021 | 2023-06-30 | [5 empty] | 10600000 | 0 | 6048401 | 1241556 | 11476729 | 590443 | 5457958 | 17525130 | 18766686 | 2025-12-31 | 2025-02-28 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/257/551918-DR4339-PR%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Crematorio%201512%20Substation%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Crematorio - 1512 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 551918RFI257 | 551918 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551916 | 107734 | FAASt [Dorado TC Relocation] (Substation) | 14F003140000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 40100000 | [8 empty] | 2021-12-21 | 12/21/2021 | [6 empty] | 40100000 | 40100000 |  |  |  |  | 0 | 40100000 | 40100000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/258/551916%20-%20DR4339PR%20-%20Dorado%20TC%20Relocation%20(Substation)%20SOW%20CE.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Dorado TC Relocation | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 551916RFI258 | 551916 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551914 | 11470 | FAASt [Caparra 1911 & 1924] (Substation) | 14F001930000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 6600000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  |  | 2022-01-31 | 12/21/2021 | 2024-06-28 | 2025-03-10 |  |  |  |  | 6600000 | 0 | 5838512.8 | 1069270.88 | 8228185.09 | 671468.81 | 5167043.99 | 14066697.89 | 15135968.77 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/259/551914-DR4339PR-Caparra%201911%20&%201924.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Caparra 1911 & 1924 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 551914RFI259 | 551914 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551912 | 107733 | FAASt [Puerto Nuevo - 1520] (Substation) | 14F001780000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 10600000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-12-21 | 12/21/2021 | 2023-06-30 | 2023-10-11 |  |  |  |  | 10600000 | 16844776 | 6035307 | 1382809 | 10809469 | 684505 | 5350802 | 16844776 | 18227585 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/260/551912-DR4339PR%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Puerto%20Nuevo%201520%20(1)%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Puerto Nuevo - 1520 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 551912RFI260 | 551912 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551911 | 11434 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) | 14F002520000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [8 empty] | 5050000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2024-03-31 | 2021-12-21 | 12/21/2021 | [6 empty] | 5050000 | 0 |  |  |  |  | 0 | 5050000 | 5050000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/261/551911%20-%20DR4339PR%20-%20Line%209100%20Guaraguao%20TC%20to%20Bayamon%20Pueblo%20Sect.%20SOW%20-%20CE.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 9100 Guaraguao TC to Bayamon Pueblo Sect. | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 551911RFI261 | 551911 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551861 | 11372 | FAASt [Physical Security - Group 3] (Substation) | 14F003850000, 14F003740000, 14F003860000 | PBUT18 - Substation Security | Substation | Substation Security | Restoration | FALSE | [14 empty] | 2022-12-31 | 2021-12-23 | 12/21/2021 | 2022-12-14 | 2023-04-28 |  |  |  |  | 1200000 | 4133339.83 | 436383.23 | 844837 | 3696956 | 73108.14 | 363275.09 | 4133339.23 | 4978176.23 |  |  | 2023-06-16 |  | 4133339.83 | 3696956.6 |  |  |  |  | 4133339.83 | 3696956.6 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/262/551861-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Physical%20Security%20-%20Group%203%20(40000-CP-SOW-0009Rev5)(2023-04-27)%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Rey Roldan Rodríguez |  |  | 844836.71 |  | 1 | 1 |  | 551861RFI262 | 551861 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551827 | 107732 | FAASt [San Juan Region Repair] (Building) | 14F002030000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 31030000 | [8 empty] | 2022-04-15 | 12/21/2021 | [6 empty] | 31028730 | 31028730 |  |  |  |  | 0 | 31028730 | 31028730 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/263/551827-DR4339PR-10038-FA-SOW-0001_Rev0-%20San%20Juan%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | San Juan Region Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 551827RFI263 | 551827 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551260 | 107727 | FAASt [Guaynabo Pueblo Substation] (Substation) | 14F001850000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 17200000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2024-10-02 | 2021-12-16 | 12/16/2021 | 2023-10-02 | 2025-06-05 |  |  |  |  | 17200000 | 22373983 | 10941966.54 | 2334521.27 | 20046985.57 | 1141020.24 | 9800946.3 | 30988952.11 | 33323473.38 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/264/551260-DR43339PR-00%20FEMA%20DSOW%20for%20Guaynabo%20Pueblo%20Rev.%202%2004012024%20-%20signed.pdf?web=1 | 3/27/2024: QC Review Complete | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Guaynabo Pueblo Substation | Rey Roldan Rodríguez |  |  |  |  | 0.722 | 2 |  | 551260RFI264 | 551260 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551247 | 11570 | FAASt [Palo Seco South Building Repairs] (Building) | 14F002000000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  | FALSE | [6 empty] | 11170000 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 |  |  |  | 2024-03-31 | 2021-12-16 | 12/16/2021 | [6 empty] | 11170493 | 0 |  |  |  |  | 0 | 11170493 | 11170493 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/265/551247-DR4339PR-10035-FA-SOW-0001_Rev0-%20Palo%20Seco%20South%20Building%20Repairs.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Palo Seco South Building Repairs | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 551247RFI265 | 551247 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551242 | 107726 | FAASt [Bayamon Region Repairs] (Building) | 14F002010000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 15450000 | [8 empty] | 2021-12-16 | 12/16/2021 | [6 empty] | 15451305 | 15451305 |  |  |  |  | 0 | 15451305 | 15451305 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/266/551242-DR4339PR-10036-FA-SOW-0001_Rev0-Bayamon%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Bayamon Region Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 551242RFI266 | 551242 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551100 | 107725 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) | 14F001890000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 16700000 | [8 empty] | 2021-12-15 | 12/15/2021 | [6 empty] | 16700000 | 16700000 |  |  |  |  | 0 | 16700000 | 16700000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/267/551100-DR4339PR-10024-EN-SOW-0001_Rev0%20-%20Bayview%20Sectionalizer%201802%20Relocation.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Bayview Sectionalizer 1802 Relocation | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 551100RFI267 | 551100 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
551067 | 11687 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | 14F002540000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | FALSE | [6 empty] | 3790000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2024-03-31 | 2021-12-15 | 12/15/2021 |  |  | 2025-03-14 | 2025-03-10 |  |  | 3790000 | 3790000 |  |  |  |  | 0 | 3790000 | 3790000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/268/551067-DR4339PR-10093-EN-SOW-0001_Rev0%20-%20Line%2011100%20Canovanas%20Sect.%20to%20GOAB%2011115.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 11100 Canovanas Sect. to GOAB 11115 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 551067RFI268 | 551067 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550998 | 107724 | FAASt [Santurce Planta (Sect) 1116] (Substation) | 14F001870000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | 2024-11-22 | 9900000 | 2024-12-12 | 2025-01-11 |  | 2025-01-11 |  |  |  |  | 2021-12-14 | 12/14/2021 | [6 empty] | 9900000 | 9900000 |  |  |  |  | 0 | 9900000 | 9900000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/269/550998-DR4339PR-10022-EN-SOW-0001_Rev0%20-%20Santurce%20Planta%20(Sect)%201116(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Santurce Planta (Sect) 1116 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550998RFI269 | 550998 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550986 | 107723 | FAASt [Condado - 1133] (Substation) | 14F001800000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 10600000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-12-14 | 12/14/2021 | 2023-06-30 | [5 empty] | 10600000 | 14709154 | 5427167 | 1367924 | 9281987 | 697091 | 4730076 | 14709154 | 16077078 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/270/550986-4339%20DR-PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Condado%201133-6-30-2023%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Condado - 1133 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550986RFI270 | 550986 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550980 | 107722 | FAASt [Parques y Recreos - 1002] (Substation) | 14F001770000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 7700000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-12-14 | 12/14/2021 | 2023-06-30 | 2024-02-16 |  |  |  |  | 7700000 | 20916860 | 8962734.08 | 1608592.37 | 10128904.68 | 1227475.29 | 7735258.79 | 19091638.76 | 20700231.13 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/271/550980-DR4339PR-FEMA%20Detailed%20Scope%20of%20Work%20for%20ParqueRecreo%201002%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Parques y Recreos - 1002 | Rey Roldan Rodríguez |  |  |  |  | 1.0956 | 1 |  | 550980RFI271 | 550980 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550972 | 107721 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) | 14F001840000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 31400000 | [8 empty] | 2021-12-14 | 12/14/2021 | [6 empty] | 31400000 | 31400000 |  |  |  |  | 0 | 31400000 | 31400000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/272/550972-DR4339PR-10019-EN-SOW-0001_Rev0%20-%20Fonalledas%20GIS%20Rebuilt%201401%201421(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Fonalledas GIS Rebuilt 1401 1421 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550972RFI272 | 550972 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550950 | 11557 | FAASt - EPC - [Monacillo TC] (Substations) | 14F003150000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE |  | Past |  |  |  |  | 105230000 | 2023-12-21 | 2024-01-18 |  | 2024-01-20 |  |  |  | 2023-05-31 | 2021-12-14 | 12/14/2021 | 2023-05-31 | 2025-06-13 | 2025-07-11 | 2025-06-30 |  |  | 105230000 | 88096455.73 | 0 | 2179830 | 13072870.61 | 0 | 0 | 13072870.61 | 15252700.61 |  |  | 2023-12-19 | 12/19/2023 | 88096455.73 | 88096455.73 | 58195134.17 | 88096455.73 |  |  | 58195134.17 | 88096455.73 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/273/550950%20-Monacillo%20TC%20(Substations)-%20FEMA%20Project%20Detailed%20Scope%20of%20Work%209.15.23%20rev.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Monacillo TC | Rey Roldan Rodríguez |  |  | 4443609.52 |  | 6.7389 | 1 |  | 550950RFI273 | 550950 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550910 | 10841 | FAASt [Physical Security - Group 1] (Substation) | 14F003820000, 14F003810000, 14F003800000, 14F003830000, 14F003720000 | PBUT18 - Substation Security | Substation | Substation Security | Restoration | FALSE | [6 empty] | 53800000 | [7 empty] | 2022-04-30 | 2021-12-23 | 12/14/2021 | 2022-04-04 | 2022-12-14 |  |  |  |  | 2000000 | 6691229.18 | 665958.96 | 1278328 | 6025270 | 0 | 665958.96 | 6691228.96 | 7969556.96 |  |  | 2023-05-04 |  | 6691229.18 | 6025270.22 |  |  |  |  | 6691229.18 | 6025270.22 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/274/550910-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Physical%20Security%20-%20Group%201%20(2023-03-17)%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Rey Roldan Rodríguez |  |  | 1278327.97 |  | 1 | 1 |  | 550910RFI274 | 550910 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550902 | 11688 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | 14F002530000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [8 empty] | 2320000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2024-03-31 | 2021-12-14 | 12/14/2021 | [6 empty] | 2320000 | 2320000 |  |  |  |  | 0 | 2320000 | 2320000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/275/550902-DR4339PR-10092-EN-SOW-0001_Rev0%20-%20Line%209700%20Palo%20Seco%20SP%20to%20Bay%20View%20Sect(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 9700 Palo Seco SP to Bay View Sect. | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550902RFI275 | 550902 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550896 | 10837 | FAASt [Transmission Priority Pole Replacements – Line 6700] (Transmission) | 14F004450000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Line Rebuild | Restoration | FALSE | [14 empty] | 2023-02-28 | 2021-02-14 | 12/14/2021 | 2022-06-24 | [5 empty] | 6010000 | 690703 | 0 | 133416 | 690703 | 0 | 0 | 690703 | 824119 |  |  | 2022-08-08 |  | 690703 | 690703 |  |  |  |  | 690703 | 690703 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/276/550896-DR4339PR-Detailed%20SOW%20-%20Line%206700%20Rev.0%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 133416 |  | 1 | 1 |  | 550896RFI276 | 550896 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550894 | 107720 | FAASt [Baldrich - 1422] (Substation) | 14F001790000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 10500000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-09-30 | 2021-12-14 | 12/14/2021 | 2023-09-29 | 2024-04-15 |  |  |  |  | 10500000 | 26709229 | 28669863 | 88908 | 884190 | 2619452 | 26050411 | 29554053 | 29642961 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/277/550894%20-%20DR4339PR%20-%20%20FAASt%20Baldrich%20Sectionalizer%201422%20-%20SOW%20CE.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Baldrich - 1422 | Rey Roldan Rodríguez |  |  |  |  | 0.90374 | 1 |  | 550894RFI277 | 550894 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550771 | 107719 | FAASt [Caguas TC] (Substation) | 14F002930000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 2500000 | [8 empty] | 2022-01-28 | 12/13/2021 | [6 empty] | 2500000 | 2500000 |  |  |  |  | 0 | 2500000 | 2500000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/278/550771%20-%20DR4339%20-%20Caguas%20TC%20(Substation)%20Initial%20SOW.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Caguas TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550771RFI278 | 550771 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550500 | 107718 | FAASt - Ponce Region Repairs (Building) | 14F002050000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 16300000 | [8 empty] | 2021-12-17 | 12/10/2021 | [6 empty] | 20294279 | 20294279 |  |  |  |  | 0 | 20294279 | 20294279 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/279/550500-DR4339PR-10040-FA-SOW-0001_Rev0-Ponce%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Ponce Region Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550500RFI279 | 550500 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550498 | 107717 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | 14F001910000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | FALSE | [6 empty] | 16300000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-12-31 | 2021-12-10 | 12/10/2021 | [6 empty] | 16300000 | 5844709 |  |  |  |  | 0 | 16300000 | 16300000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/280/921048-DR4339PR-10026-EN-SOW-0001_Rev0%20-%20Pampanos%20Sect%20Relocation.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Pampanos Relocation | Rey Roldan Rodríguez |  |  |  |  | 0.35857 | 4 |  | 550498RFI280 | 550498 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550162 | 11813 | FAASt [Berwind TC - 1336] (Substation) | 14F002920000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 13400000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-10-31 | 2021-12-07 | 12/7/2021 | 2023-10-02 | 2023-12-20 |  |  |  |  | 13400000 | 51763597 | 6718315 | 4182974 | 40767573 | 625188 | 6093127 | 47485888 | 51668862 | 2024-12-31 | 2025-03-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/281/550162%20-%20DR4339PR%20-%20%20Berwind%20TC%20-%201336%20(Transmission).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Berwind TC - 1336 | Rey Roldan Rodríguez |  |  |  |  | 1.0901 | 1 |  | 550162RFI281 | 550162 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550106 | 107714 | FAASt [Conquistador CH] (Substation) | 14F003170000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 5100000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-12-07 | 12/7/2021 | 2023-06-30 | 2024-04-01 |  |  |  |  | 5100000 | 11639958 | 1101071.22 | 1478605.83 | 9827316 | 143115.56 | 957955.66 | 10928387.22 | 12406993.05 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/282/550106-DR4339PR-%20Detail%20Scope%20of%20Work%20Conquistador%20CH%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Conquistador - CH | Rey Roldan Rodríguez |  |  |  |  | 1.0651 | 1 |  | 550106RFI282 | 550106 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550099 | 107713 | FAASt [Esc. Industrial M. Such - 1423] (Substation) | 14F001830000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 10600000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-12-07 | 12/7/2021 | 2023-06-30 | 2024-03-26 |  |  |  |  | 10600000 | 14335434 | 6851320.87 | 1112050.13 | 8804423.21 | 762291.03 | 6089029.84 | 15655744.08 | 16767794.21 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/283/550099-DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Esc%20Industrial%20Miguel%20Such%201423%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Esc. Industrial M. Such - 1423 | Rey Roldan Rodríguez |  |  |  |  | 0.91567 | 1 |  | 550099RFI283 | 550099 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550070 | 107712 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) | 14F002510000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 22330000 |  |  | 2024-07-18 | [5 empty] | 2021-12-07 | 12/7/2021 | [6 empty] | 22330000 | 22330000 |  |  |  |  | 0 | 22330000 | 22330000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/284/550070%20-%20DR4339PR%20-%20Line%204000%20Comerio%20HP%20to%20Escuela%20Francisco%20Morales%20Initial%20SOW%20CE.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 7/18/2024. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 4000 Comerio HP to Escuela Francisco Morales | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550070RFI284 | 550070 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550060 | 107711 | FAASt [Caguas Region Repairs] (Building) | 14F002020000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 14470000 | [8 empty] | 2021-12-07 | 12/7/2021 | [6 empty] | 14472109 | 14472109 |  |  |  |  | 0 | 14472109 | 14472109 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/285/550060%20-DR4339PR%20-%20Caguas%20Region%20Repairs%20Initial%20SOW%20CE.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Caguas Region Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 550060RFI285 | 550060 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
550019 | 107710 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | 14F002470000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [5 empty] | 2024-10-03 | 10110000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-09-30 | 2021-12-07 | 12/7/2021 | 2023-09-25 | 2024-04-25 |  |  |  |  | 10110000 | 21404169 | 4035264 | 2943392 | 19190123 | 488834 | 3546430 | 23225387 | 26168779 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/286/550019%20-%20DR4339PR%20FAASt%20Line%20600%20Caguas%20TC%20to%20Gautier%20Benitez%20%20Sect%20(Transmission)Applicant%20provided%20SOW%20CE.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 600 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 600 Caguas TC to Gautier Benitez Sect. | Rey Roldan Rodríguez |  |  |  |  | 0.92159 | 1 |  | 550019RFI286 | 550019 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
549768 | 107709 | FAASt Physical Security - Group 5 (Substation) | 14F003880000 | PBUT18 - Substation Security | Substation | Substation Security | Restoration | TRUE | 2025-07-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2021-12-03 | 12/3/2021 | [6 empty] | 1200000 | 1200000 |  |  |  |  | 0 | 1200000 | 1200000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/287/549768-DR4339PR-Physical%20Security%2040000-EN-SOW-0007_Rev0.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 549768RFI287 | 549768 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
549764 | 11350 | FAASt [Physical Security - Group 2] (Substation) | 14F003840000, 14F003730000 | PBUT18 - Substation Security | Substation | Substation Security | Restoration | FALSE | [6 empty] | 53800000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2022-12-31 | 2021-12-03 | 12/3/2021 | 2022-12-14 | 2023-05-01 |  |  |  |  | 800000 | 2383692.99 | 224680.68 | 529771 | 2159012 | 0 | 224680.68 | 2383692.68 | 2913463.68 |  |  | 2023-06-16 |  | 2383692.99 | 2159012.31 |  |  |  |  | 2383692.99 | 2159012.31 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/288/549764-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20Physical%20Security%20Group%202%20(40000-CP-SOW-0012Rev2%20)(2023-03-23)%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Physical Security | Rey Roldan Rodríguez |  |  | 529771.49 |  | 1 | 1 |  | 549764RFI288 | 549764 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
549725 | 11707 | FAASt [Substation Minor Repairs - Group E] (Substation) | 14F002910000, 14F002890000, 14F002900000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [14 empty] | 2023-06-30 | 2021-12-03 | 12/3/2021 | 2023-06-30 | 2024-02-07 |  |  |  |  | 1200000 | 4503783.21 | 579768 | 818227 | 3924016 | 22126.13 | 557641.87 | 4503784 | 5322011 | 2024-06-30 | 2024-07-31 | 2024-05-10 |  | 4503783.21 | 3924015.69 |  |  |  |  | 4503783.21 | 3924015.69 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/289/549725-DR4339PR-00%20Detailed%20Scope%20of%20Work%20for%20Minor%20Repairs%20-%20Group%20E%20Rev.0%20(2023-06-30)%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-24 14:44 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Jose J Ramos Figueroa |  |  | 98349.5 | 11328.47 | 1 | 1 |  | 549725RFI289 | 549725 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
549715 | 11682 | FAASt Substation Minor Repairs - Group D (Substation) | 14F003000000, 14F003010000, 14F003020000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [14 empty] | 2023-06-30 | 2021-12-03 | 12/3/2021 | 2023-06-30 | 2024-01-04 |  |  |  |  | 1200000 | 2871257.17 | 288124 | 580189 | 2583134 | 0 | 288124 | 2871258 | 3451447 | 2024-06-30 | 2024-07-31 | 2024-04-12 |  | 2871257.17 | 2583133.54 |  |  |  |  | 2871257.17 | 2583133.54 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/290/549715-DR4339PR-00%20Detailed%20Scope%20of%20Work%20for%20Minor%20Repairs%20-%20Group%20D%20Rev.0%20(2023-06-30)%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  | 580188.69 |  | 1 | 1 |  | 549715RFI290 | 549715 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
548598 | 11494 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | 14F002350000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 44310000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-12-01 | 12/1/2021 | 2023-06-30 | 2024-05-08 |  |  |  |  | 44310000 | 0 | 15963429 | 4765220 | 37425267 | 1717803 | 14245626 | 53388696 | 58153916 | 2024-10-31 | 2024-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/291/548598%20-%20DR4339PR%20-%20Line%2036200%20Fajardo%20to%20Rio%20Blanco%20Applicant%20SOW.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 36200 Fajardo to Rio Blanco | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 548598RFI291 | 548598 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
548596 | 107708 | FAASt [San German Electrical Service Center] (Building) | 14F001980000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 2480000 | [8 empty] | 2021-12-01 | 12/1/2021 | [6 empty] | 2478182 | 2478182 |  |  |  |  | 0 | 2478182 | 2478182 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/292/548596-DR4339PR-10033-FA-SOW-0001_Rev0-San%20German%20ESC.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | San German Electrical Service Center | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 548596RFI292 | 548596 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
548440 | 107707 | FAASt [Mayaguez Region Repairs] (Building) | 14F002040000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 13350000 | [8 empty] | 2021-11-30 | 11/30/2021 | [6 empty] | 13346360 | 13346360 |  |  |  |  | 0 | 13346360 | 13346360 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/293/548440-DR4339PR--FA-SOW-0001_Rev0-%20Mayaguez%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Mayaguez Region Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 548440RFI293 | 548440 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
548393 | 107705 | FAASt Arecibo Region Repairs (Buildings) | 14F001990000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 9230000 | [8 empty] | 2021-12-27 | 11/29/2021 | [6 empty] | 9226902 | 9226902 |  |  |  |  | 0 | 9226902 | 9226902 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/294/548393%20DR4339PR%20Arecibo%20Region%20Repairs%20(Building).pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Arecibo Region Repairs | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 548393RFI294 | 548393 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547350 | 11854 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | 14F002460000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | FALSE | [6 empty] | 5390000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2024-03-31 | 2021-11-17 | 11/17/2021 |  |  | 2024-12-16 | 2024-12-02 |  |  | 5390000 | 5390000 |  |  |  |  | 0 | 5390000 | 5390000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/295/547350%20-%20DR4339PR%20-%20%20FAASt%20-%20Line%2013300%20Bayam%C3%B3n%20TC%20to%20Plaza%20del%20Sol%20(Transmission)%20FEMA%20SOW%20CE.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 13300 Bayamon TC to Plaza del Sol | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547350RFI295 | 547350 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547344 | 107702 | FAASt [Acacias 6801 TC Relocation] (Substation) | 14F003120000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | FALSE | [6 empty] | 29100000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-12-31 | 2021-11-17 | 11/17/2021 | 2024-03-08 | [5 empty] | 29100000 | 29100000 | 42895135.02 | 677999.83 | 8196442.68 | 3277151.71 | 39617983.31 | 51091577.7 | 51769577.53 | 2025-10-31 | 2026-03-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/296/921982-DR4339PR-10115-EN-SOW-0001_Rev0%20-%20Acacias%206801%20TC%20Relocation.pdf?web=1 | 2/28/2024: QC Review Complete | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Acacias 6801 TC Relocation | Rey Roldan Rodríguez |  |  |  |  | 0.56957 | 3 |  | 547344RFI296 | 547344 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547343 | 107701 | FAASt [Victoria TC 7008 Relocation] (Substation) | 14F003160000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 5500000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-12-31 | 2021-11-17 | 11/17/2021 | 2024-06-29 | [5 empty] | 5500000 | 5500000 | 54844288.98 | 606808.32 | 6239636.58 | 4859932.94 | 49984356.04 | 61083925.56 | 61690733.88 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/297/921981-DR4339PR-10119-EN-SOW-0001_Rev0%20-%20Victoria%20TC%207008.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Victoria TC 7008 | Rey Roldan Rodríguez |  |  |  |  | 0.09004 | 5 |  | 547343RFI297 | 547343 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547342 | 107700 | FAASt [Line 1500 Mayaguez GP to GOAB 1515] (Transmission) | 14F002490000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 58610000 | [8 empty] | 2021-11-17 | 11/17/2021 | [6 empty] | 58610000 | 58610000 |  |  |  |  | 0 | 58610000 | 58610000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/298/921980-DR4339PR-10088-EN-SOW-0001_Rev0%20Line%201500%20Mayaguez%20GP%20to%20GOAB%201515.pdf?web=1 | 9/12/2024 - GP Notes "The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 1500 Mayaguez GP to GOAB 1515 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547342RFI298 | 547342 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547273 | 107699 | FAASt Charco Hondo Substation 8008 Relocation (Substation) | 14F001900000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | FALSE | [6 empty] | 16300000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  |  | 2021-11-16 | 11/16/2021 | [6 empty] | 16300000 | 16300000 |  |  |  |  | 0 | 16300000 | 16300000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/299/547273%20DR4339PR%20Charco%20Hondo%208008%20Relocation%20SOW%20and%20Cost%20Estimate%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Charco Hondo 8008 Relocation | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547273RFI299 | 547273 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547271 | 107698 | FAASt San Jose Substation 8104 Relocation (Substation) | 14F001920000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 17000000 |  |  | 2024-08-30 | [5 empty] | 2021-11-16 | 11/16/2021 | [6 empty] | 17000000 | 17000000 |  |  |  |  | 0 | 17000000 | 17000000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/300/921686%20DR4339PR-%20San%20Jose%20Relocation%20SOW%20and%20Cost%20Estimate.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Pending Task Order signature to complete Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | San Jose Relocation | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547271RFI300 | 547271 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547269 | 11481 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | 14F002430000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 3140000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2023-06-30 | 2021-11-16 | 11/16/2021 | 2023-06-30 | 2024-04-25 |  |  |  |  | 3140000 | 0 | 11466633 | 3954335 | 32159582 | 1250116 | 10216517 | 43626215 | 47580550 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/301/Revised%20FEMA%20SOW%20-%20547269-DR4339PR-TL2800%20DSOW-38kv%20Aguadilla%20Hosp.%20Dist.%20Sect.%20to%20T-Bone%20TO-Rev%200%20-%20signed%20(1).pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2800 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 547269RFI301 | 547269 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547259 | 11480 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | 14F002420000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 41270000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2023-06-30 | 2021-11-16 | 11/16/2021 | 2023-06-30 | 2024-01-12 |  |  |  |  | 41270000 | 0 | 55843908 | 6838079 | 64136647 | 5366230 | 50477678 | 119980555 | 126818634 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/302/Revised%20FEMA%20SOW%20-%20547259-DR4339PR-TL2700%20DSOW-38%20kV%20Victoria%20TC%20to%20Quebradillas%20Sect-%20Rev%200.pdf%20-%20signed%20(1).pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2700 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 2700 Victoria TC to Quebradillas Sect. | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 547259RFI302 | 547259 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547251 | 11807 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 14F002480000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | TRUE | 2025-07-31 |  |  |  |  | 2024-07-22 | 54600000 | 2024-07-31 | 2024-08-22 |  | 2024-08-30 |  |  |  | 2024-03-31 | 2021-11-16 | 11/16/2021 | 2025-07-01 |  | 2025-08-08 | 2025-07-15 |  |  | 21470000 | 21470000 |  | 433482.47 | 6482242.86 |  | 0 | 6482242.86 | 6915725.33 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/303/921824-DR4339PR-10087-EN-SOW-0001_Rev0%20-%20Line%202400%20Dos%20Bocas%20HP%20to%20America%20Apparel.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2400 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 2400 Dos Bocas HP to America Apparel | Rey Roldan Rodríguez | 0 Months |  |  |  | 3.3121 | 1 |  | 547251RFI303 | 547251 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547248 | 107695 | FAASt Canas TC 5002 5018 (Substation) | 14F002940000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 1700000 | [8 empty] | 2021-11-16 | 11/16/2021 | [6 empty] | 1700000 | 1700000 |  |  |  |  | 0 | 1700000 | 1700000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/304/921822-DR4339PR-10109-EN-SOW-0001_Rev0%20-%20Canas%20TC.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Canas TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547248RFI304 | 547248 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547247 | 107694 | FAASt Cambalache TC Relocation (Substation) | 14F003130000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | FALSE | [5 empty] | 2024-10-03 | 30700000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2024-03-31 | 2021-11-16 | 11/16/2021 | 2024-07-31 | [5 empty] | 30700000 | 30700000 | 84733286.06 | 319703.09 | 5143802.81 | 2090449.36 | 82642836.7 | 89877088.87 | 90196791.96 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/305/921812-DR4339PR-10116-EN-SOW-0001_Rev0%20-%20Cambalache%20TC%20Relocation.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Cambalache TC Relocation | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.34158 | 4 |  | 547247RFI305 | 547247 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547243 | 107693 | FAASt Egozcue - 1109 (Substation) | 14F001820000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 10500000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-11-16 | 11/16/2021 | 2023-06-30 | 2024-02-09 |  |  |  |  | 10500000 | 21850323 | 6952342.26 | 1400260.82 | 12496184.94 | 700164.05 | 6252178.21 | 19448527.2 | 20848788.02 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/306/547243-DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Egozcue%201109%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Egozcue - 1109 | Rey Roldan Rodríguez |  |  |  |  | 1.1235 | 1 |  | 547243RFI306 | 547243 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547241 | 11448 | FAASt Tallaboa 5402 (Substation) | 14F001940000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 6900000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2023-06-30 | 2021-11-16 | 11/16/2021 | 2023-06-30 | [5 empty] | 6900000 | 0 | 5628609 | 1268607 | 9655829 | 653626 | 4974983 | 15284438 | 16553045 | 2024-12-31 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/307/547241-DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Tallaboa%205402%20Substation%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Tallaboa 5402 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 547241RFI307 | 547241 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547226 | 11689 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | 14F002680000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | FALSE | [6 empty] | 13810000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2024-03-31 | 2021-11-16 | 11/16/2021 | [6 empty] | 13810000 | 13810000 |  |  |  |  | 0 | 13810000 | 13810000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/308/547226%20DR4339PR%20Line%2011400%20Barceloneta%20TC%20to%20Florida%20TO.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 11400 Barceloneta TC to Florida TO | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547226RFI308 | 547226 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547221 | 107692 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) | 14F002450000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 39980000 |  |  | 2024-09-09 | [5 empty] | 2021-11-16 | 11/16/2021 | [6 empty] | 39980000 | 39980000 |  |  |  |  | 0 | 39980000 | 39980000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/309/547221%20-%20DR4339PR%20%20Line%203600%20Monacillos%20TC%20to%20Martin%20Pe%C3%B1a%20TC%20(Transmission).pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 9/9/2024. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 3600 Monacillos TC to Martin Peña TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547221RFI309 | 547221 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547187 | 107690 | FAASt - [Substation Component Replacement Program] (Substation) | 14F001880000, 14F020180000, 14F020090000, 14F020120000, 14F020130000, 14F020190000 | PBUT7 | Substation | Substation Rebuilds |  | FALSE |  | Current |  |  |  |  | 17100000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  | 2024-01-31 | 2021-11-16 | 11/15/2021 | 2025-03-10 | [5 empty] | 17100000 | 330300000 | 308929.24 | 2069220.14 | 6551618.4 | 66626.67 | 242302.57 | 6860547.64 | 8929767.78 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/310/547187%20DR4339PR%20Arecibo%20Pueblo%208002%20Relocation%20SOW%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Arecibo Pueblo 8002 Relocation | Rey Roldan Rodríguez |  |  |  |  | 48.1448 | 1 |  | 547187RFI310 | 547187 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
547160 | 107689 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | 14F002370000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [8 empty] | 55370000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  |  | 2021-11-15 | 11/15/2021 | [6 empty] | 55370000 | 55370000 |  |  |  |  | 0 | 55370000 | 55370000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/311/921046-DR4339PR-10076-EN-SOW-0001_Rev0%20-%20Line%201200%20Mayaguez%20GP%20to%20Yauco%202%20HP.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 1200 Mayaguez GP to Yauco 2 HP | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 547160RFI311 | 547160 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
546386 | 107558 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | 14F003490000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 14600000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2023-09-30 | 2021-11-09 | 11/9/2021 | 2023-10-02 | [5 empty] | 14600000 | 28991235 | 23252037 | 825193 | 5739198 | 2922954 | 20329083 | 28991235 | 29816428 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/312/546386-DR4339PR-10156-EN-SOW-0001_Rev0%20(El%20Yunque%202305-01%20Supply).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | El Yunque 2305-01 Supply | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 546386RFI312 | 546386 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
546374 | 107556 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | 14F001590000, 14F001580000, 14F001560000, 14F001570000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 27280000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2023-08-31 | 2021-11-09 | 11/9/2021 | 2023-08-31 | 2023-11-30 |  |  |  |  | 27280000 | 38107125 | 12777559 | 2091400 | 18966760 | 1260325 | 11517234 | 31744319 | 33835719 | 2025-05-31 | 2025-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/313/546374-DR4339PR%20-10143-EN-SOW-0001_Rev0%20(Distribution%20Feeders-San%20Juan%20Short%20Term%20Group%203).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders - San Juan Short Term Group 3 | Rey Roldan Rodríguez | 0 Months |  |  |  | 1.2004 | 1 |  | 546374RFI313 | 546374 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
546371 | 11478 | FAASt- Substation Minor Repairs Group C (Substation) | 14F003030000, 14F003060000, 14F003050000, 14F003040000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [14 empty] | 2022-06-30 | 2021-11-09 | 11/9/2021 | 2022-06-17 | 2023-06-27 |  |  |  |  | 1600000 | 3032891.2 | 384632.14 | 646473 | 2648259 | 25197.64 | 359434.5 | 3032891.14 | 3679364.14 |  |  | 2023-08-22 |  | 3032891.2 | 2648259.06 |  |  |  |  | 3032891.2 | 2648259.06 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/314/546371-DR4339PR-00%20FEMA%20DSOW%20for%20Sub.%20Minor%20Repairs%20-Group%20C%20(43001-CP-SOW-0009_Rev7)%20(2023-06-26)%20-%20signed.pdf |  | 2025-07-24 14:47 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Jose J Ramos Figueroa |  |  | 173985.91 |  | 1 | 1 |  | 546371RFI314 | 546371 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
546370 | 10858 | FAASt - Substation Minor Repairs Group A (Substation) | 14F002840000, 14F002830000, 14F002870000, 14F002860000, 14F002880000, 14F002850000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 400000000 | [8 empty] | 2021-11-09 | 11/9/2021 | 2022-05-31 | 2023-10-17 |  |  |  |  | 2400000 | 4971175.09 | 488203 | 996359 | 4482973 | 0 | 488203 | 4971176 | 5967535 |  |  | 2024-02-13 |  | 4971175.09 | 4482972.51 |  |  |  |  | 4971175.09 | 4482972.51 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/315/546370~1.PDF?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Rey Roldan Rodríguez |  |  | 996359.11 |  | 1 | 1 |  | 546370RFI315 | 546370 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
542762 | 10690 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | 14F003940000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-01-31 | 2021-10-26 | 10/26/2021 | 2022-01-28 | 2022-05-13 |  |  |  |  | 3000000 | 767868 | 157420 |  | 661242 | 0 | 157420 | 818662 | 818662 |  |  | 2022-06-03 11:23 |  | 767868 | 610448 |  |  |  |  | 767868 | 610448 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/316/Revised%20FEMA%20SOW%20-%20542762-DR4339PR-Detalied%20SOW%20Arecibo%20Group%202%20Rev1.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 50794 |  | 0.93795 | 1 |  | 542762RFI316 | 542762 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
542758 | 11385 | FAASt [Minor Repairs -Group B] (Substation) | 14F002950000, 14F002970000, 14F002980000, 14F002960000, 14F002990000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 400000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2022-07-31 | 2021-10-26 | 10/26/2021 | 2022-07-11 | 2023-05-04 |  |  |  |  | 2000000 | 3412576 | 439541 | 723314 | 2973035 | 27113 | 412428 | 3412576 | 4135890 |  |  | 2023-07-07 |  | 3412576 | 2973035 |  |  |  |  | 3412576 | 2973035 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/317/Revised%20FEMA%20SOW%20-%20542758-DR4339PR-%200%20FEMA%20DSOW%20Group%20B%20Minor%20Repairs%20(43001-CP-SOW-0012_Rev5)%20(2023-05-03)%20-%20signed.pdf?web=1 |  | 2025-07-24 14:51 | 2023-08-14 11:10 | Jahdiel Franqui | Substation Minor Repairs | Jose J Ramos Figueroa |  |  | 152806 | 14467 | 1 | 1 |  | 542758RFI317 | 542758 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
542756 | 10538 | FAASt [Guánica Streetlighting] (Distribution) | 14F003710000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-03-31 | 2021-10-26 | 10/26/2021 | 2022-03-08 | 2022-04-07 |  |  |  |  | 6757365 | 10058046 | 370808 | 2237386 | 9687238 | 0 | 370808 | 10058046 | 12295432 |  |  | 2022-05-26 |  | 10058046 | 9687238 |  |  |  |  | 10058046 | 9687238 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/318/4.18.22%20%20%20PW%20542756%20%20%20Revised%20FEMA%20SOW.pdf?web=1 |  | 2025-07-24 14:57 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 2237386 |  | 1 | 1 |  | 542756RFI318 | 542756 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
542690 | 10499 | FAASt [Maunabo Streetlighting] (Distribution) | 14F003680000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-02-28 | 2021-10-28 | 10/26/2021 | 2022-02-04 | 2022-04-07 |  |  |  |  | 4821725 | 6443757.4 | 243880.33 | 1530438 | 6199878 | 243880.33 | 0 | 6443758.33 | 7974196.33 |  |  | 2022-05-05 11:19 |  | 6443757.4 | 6199877.07 |  |  |  |  | 6443757.4 | 6199877.07 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/319/Revised%20FEMA%20SOW%20-%20542690-DR4339PR-Detailed%20SOW%20Maunabo%20Rev0%20-%20signed%20-%20DSOW.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1530438.49 |  | 1 | 1 |  | 542690RFI319 | 542690 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
542688 | 10539 | FAASt [Aguada Streetlighting] (Distribution) | 14F003630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-03-31 | 2021-10-26 | 10/26/2021 | 2022-03-08 | 2022-04-08 |  |  |  |  | 12580635 | 18571716.38 | 807222 | 4104786 | 17764494 | 0 | 807222 | 18571716 | 22676502 |  |  | 2022-05-05 |  | 18571716.38 | 17764494.34 |  |  |  |  | 18571716.38 | 17764494.34 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/320/Detailed%20SOW-542688.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 4104785.76 |  | 1 | 1 |  | 542688RFI320 | 542688 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
542687 | 10521 | FAASt [Lajas Streetlighting] (Distribution) | 14F003700000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [14 empty] | 2022-03-31 | 2021-10-26 | 10/26/2021 | 2022-03-08 | 2022-04-11 |  |  |  |  | 9453361 | 10704668.57 | 426332 | 2512854 | 10278336 | 0 | 426332 | 10704668 | 13217522 |  |  | 2022-05-20 |  | 10704668.57 | 10278336.09 |  |  |  |  | 10704668.57 | 10278336.09 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/321/Revised%20FEMA%20SOW%20542687.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2512853.73 |  | 1 | 1 |  | 542687RFI321 | 542687 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
542517 | 10515 | FAASt [Luquillo Streetlighting] (Distribution) | 14F003690000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE | [6 empty] | 1220000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2022-03-31 | 2021-10-25 | 10/25/2021 | 2022-03-08 | 2022-04-11 |  |  |  |  | 6346527 | 8810325.37 | 181658.08 | 2004233 | 8628668 | 0 | 181658.08 | 8810326.08 | 10814559.08 |  |  | 2022-05-20 |  | 8810325.37 | 8628667.29 |  |  |  |  | 8810325.37 | 8628667.29 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/322/542517-10515%20Luquillo%20Streetlights%20Detailed%20SOW%20Rev.3.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2004233.23 |  | 1 | 1 |  | 542517RFI322 | 542517 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
436616 | 107551 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 14F000040000, 14F000050000, 14F000080000, 14F000060000, 14F000070000, 14F000090000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 53580000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-10-12 | 10/12/2021 | 2023-09-01 | 2023-12-11 |  |  |  |  | 53580000 | 51555365 | 14494388 | 2468970 | 24725318 | 1315945 | 13178443 | 39219706 | 41688676 | 2025-05-31 | 2025-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/323/436616-%20DR4339PR-%20DSOW%20-Arecibo%20Short%20Term%20Group%201.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Arecibo Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1.3145 | 1 |  | 436616RFI323 | 436616 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
435257 | 107545 | FAASt [Line 3000 Monacillos TC - Bairoa TO] (Transmission) | 14F017370000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  |  |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [9 empty] | 2023-12-31 | 2021-09-29 | 9/29/2021 | [6 empty] | 924000 | 924000 |  |  |  |  | 0 | 924000 | 924000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/324/FEMA%20Scope%20of%20Work%20Line%203000%20Monacillos%20TC%20-%20Bairoa%20TO.DOC%20(1).pdf?web=1 | 9/12/2024 - GP Notes "The project was withdrawn with the comment "8/15/2024 - Applicant requested to withdraw the reference project. Please see document with the naming convention "435257-DR4339PR-Withdrawn Confirmation.msg"". | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 435257RFI324 | 435257 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
335168 | 9510 | FAASt A&E PREPA | 14F001650000 | PBFM03 - Financial Mgmt Functions | Other | TBD | [18 empty] | 9/21/2021 | [7 empty] | 1086406842.43 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2021-10-07 11:39 | 06/21/2023 | 1086406842.43 |  | 486406842.43 | 486406842.43 | 1058513052.43 | 1058513052.43 | 1058513052.43 | 1058513052.43 | 2027-09-20 |  |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  | 0 |  |  |  |  | 335168RFI325 | 335168 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334527 | 10701 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | 14F004050000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-02-28 | 2021-09-10 | 9/10/2021 | 2022-02-08 | 2022-05-24 | [5 empty] | 123721 | 14874 |  | 102513 | 0 | 14874 | 117387 | 117387 |  |  | 2022-06-10 11:48 |  | 123721 | 108847 |  |  |  |  | 123721 | 108847 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/326/Revised%20FEMA%20SOW%20-%20334527-DR4339PR-Detalied%20SOW%20Caguas%20Group%208%20Rev3.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 8540 |  | 1.054 | 1 |  | 334527RFI326 | 334527 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334518 | 107532 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 14F000580000, 14F000650000, 14F000530000, 14F000770000, 14F000540000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 49180000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-10 | 9/10/2021 | 2023-09-01 | 2023-11-30 |  |  |  |  | 49180000 | 36582202 | 7784267 | 1942279 | 10283602 | 1224114 | 6560153 | 18067869 | 20010148 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/327/334518%20-%20DR4339PR%20-%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%207.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 7 | Rey Roldan Rodríguez |  |  |  |  | 2.0247 | 1 |  | 334518RFI327 | 334518 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334497 | 107531 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 14F000460000, 14F000660000, 14F000380000, 14F000640000, 14F000450000, 14F000470000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 76650000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-10 | 9/10/2021 | 2023-09-01 | [5 empty] | 72650000 | 83151265 | 22180767 | 6980220 | 60970498 | 2278513 | 19902254 | 83151265 | 90131485 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/328/334497-DR4339PR-%20DSWOR-%20Caguas%20Short%20Term%20Group%206-Signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 6 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 334497RFI328 | 334497 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334491 | 107530 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 14F000420000, 14F000390000, 14F000600000, 14F000750000, 14F000730000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 72350000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-10 | 9/10/2021 | 2023-09-01 | 2023-11-30 |  |  |  |  | 72350000 | 38058553 | 13582684 | 3119148 | 16427785 | 2165073 | 11417611 | 30010469 | 33129617 | 2025-01-31 | 2025-07-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/329/334491-DR4339PR-10149-Caguas%20Short%20Term%20Group%205%20%20DSOW%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 5 | Rey Roldan Rodríguez | 0 Months |  |  |  | 1.2682 | 1 |  | 334491RFI329 | 334491 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334488 | 10635 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | 14F004010000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-02-28 | 2021-09-10 | 9/10/2021 | 2022-02-04 | 2022-05-09 |  |  |  |  | 44710000 | 153743 | 10826 | 19965 | 134417 | 0 | 10826 | 145243 | 165208 |  |  | 2022-05-26 |  | 153743 | 142917 |  |  |  |  | 153743 | 142917 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/330/10148-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%204%20Signed%20-%20Copy.pdf?web=1 |  | 2025-07-24 15:09 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Jose J Ramos Figueroa |  |  | 11465 |  | 1.0585 | 1 |  | 334488RFI330 | 334488 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334482 | 11450 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) | 14F002440000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 90440000 | [8 empty] | 2021-09-14 | 9/10/2021 | [6 empty] | 90440000 | 0 |  |  |  |  | 0 | 90440000 | 90440000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/331/334482-DR4339PR-10083-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%203000%20Monacillos%20TC%20to%20Juncos%20TC%20Signed%20-%20Copy.pdf?web=1 | 9/12/2024 - GP notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 3000 Monacillos TC to Juncos TC | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 334482RFI331 | 334482 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334477 | 107529 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | 14F000860000, 14F000890000, 14F000870000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 60760000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-14 | 9/10/2021 | 2023-09-01 | 2023-11-30 |  |  |  |  | 60760000 | 39416251 | 23907802 | 2623895 | 20298233 | 2736726 | 21171076 | 44206035 | 46829930 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/332/334477-DR4339PR-10137-Carolina%20Short%20Term%20Group%203%20DSOW%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Carolina Short Term Group 3 | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.89165 | 1 |  | 334477RFI332 | 334477 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334476 | 107528 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 14F000840000, 14F000820000, 14F000830000, 14F000810000, 14F000850000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 40500000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-11-30 | 2021-09-15 | 9/10/2021 | 2023-11-30 | [5 empty] | 40500000 | 40500000 | 18767542 | 4031089 | 14254294 | 3637670 | 15129872 | 33021836 | 37052925 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/333/334476-DR4339PR-10010-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20Carolina%20Short%20Term%20Group%202%20Signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Carolina Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 1.2265 | 1 |  | 334476RFI333 | 334476 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334475 | 107527 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | 14F000250000, 14F000240000, 14F000290000, 14F000280000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 65680000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-15 | 9/10/2021 | 2023-09-01 | 2023-11-30 |  |  |  |  | 65680000 | 67962252 | 17884283 | 4579075 | 45856819 | 1623714 | 16260569 | 63741102 | 68320177 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/334/334475-DR4339PR-%20DSOW%20Bayamon%20Short%20Term%20Group%203_.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 3 | Rey Roldan Rodríguez |  |  |  |  | 1.0662 | 1 |  | 334475RFI334 | 334475 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334474 | 107526 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | 14F000320000, 14F000330000, 14F000310000, 14F000340000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 10350000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-07-31 | 2021-09-15 | 9/10/2021 | 2023-07-01 | 2023-11-30 |  |  |  |  | 40500000 | 4337037 | 659178 | 384975 | 804315 | 213377 | 445801 | 1463493 | 1848468 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/335/Revised%20FEMA%20SOW%20-%20334474-DR4339PR-%20DSOW%2010136-BAYAMONN%20STG2%20-%20signed%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 2.9635 | 1 |  | 334474RFI335 | 334474 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334473 | 107525 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | 14F000230000, 14F000180000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 85000000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-15 | 9/10/2021 | 2023-09-29 | 2025-07-09 |  |  |  |  | 85000000 | 61103928 | 1173247.16 | 1298493.93 | 16234566.74 | 135257.91 | 1037989.25 | 17407813.9 | 18706307.83 | 2025-04-30 | 2025-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/336/334473-DR4339PR-10008-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20Bayamon%20Short%20Term%20Group%201%20Signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 3.5101 | 1 |  | 334473RFI336 | 334473 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334472 | 107524 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 14F001550000, 14F001520000, 14F001510000, 14F001530000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 10560000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-16 | 9/10/2021 | 2023-09-01 | 2023-12-06 |  |  |  |  | 10560000 | 27652844 | 5366655 | 3690321 | 15093429 | 1052352 | 4314303 | 20460084 | 24150405 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/337/334472-DR4339PR-DSOW-%20San%20Juan%20Short%20Term%20Group%202.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ San Juan Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 1.3516 | 1 |  | 334472RFI337 | 334472 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334471 | 107523 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | 14F001450000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 40690000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-16 | 9/10/2021 | 2023-09-29 | [5 empty] | 40690000 | 62894812 | 26997816 | 7053158 | 35896996 | 4433509 | 22564307 | 62894812 | 69947970 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/338/334471-DR4339PR-10013-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20San%20Juan%20Short%20Term%20Group%201%20Signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ San Juan Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 334471RFI338 | 334471 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334470 | 11708 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 14F002390000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE |  | Current |  |  |  |  | 113330000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-12-31 | 2021-09-16 | 9/10/2021 | 2024-09-30 | 2025-06-13 | 2025-08-05 | 2025-07-21 | Field EHP: Formal Request for Information (RFI) sent to Applicant on 7/21/2025. ECD: 8/05/2025. |  | 113330000 | 113330000 |  | 5039983.61 | 49383355.93 |  | 0 | 49383355.93 | 54423339.54 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/339/334470-DR4339PR-10078-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%203100%20Monacillos%20TC%20to%20Daguao%20TC%20Signed%20-%20Copy.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 3100 | 2025-07-25 16:07 | 2023-08-14 11:10 | Jahdiel Franqui | Line 3100 Monacillos TC to Daguao TC | Maria Mujica Gonzalez | 0 Months |  |  |  | 2.2949 | 1 |  | 334470RFI339 | 334470 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334469 | 107522 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) | 14F002360000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 11510000 |  |  | 2024-06-26 | [5 empty] | 2021-09-16 | 9/10/2021 | [6 empty] | 11510000 | 11510000 |  |  |  |  | 0 | 11510000 | 11510000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/340/334469-DR4339PR-10075-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%208900%20Monacillos%20TC%20to%20Adm%20Signed%20-%20Copy.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 6/26/2024. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 8900 Monacillos TC to Adm. Tribunal Apelaciones | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 334469RFI340 | 334469 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334468 | 10679 | FAASt [Transmission Priority Pole Replacements – Line 2200] (Transmission) | 14F004440000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 378800000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2022-05-31 | 2021-09-16 | 9/10/2021 | 2022-05-02 | 2022-05-02 |  |  |  |  | 103800000 | 1217429 | 0 | 242850 | 1217429 | 0 | 0 | 1217429 | 1460279 |  |  | 2022-07-13 | 03/28/2024 | 1217429 | 1217429 | 1217429 | 1217429 |  |  | 1217429 | 1217429 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/341/334468-DR4339PR-DSOW%20-TL%202200-Transmission%20Priority%20Pole%20Replacement-%20V0%20(4).pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2200 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 242850 |  | 1 | 1 |  | 334468RFI341 | 334468 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334452 | 107521 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 14F000550000, 14F000400000, 14F000560000, 14F000360000, 14F000720000, 14F000740000, 14F000760000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 82070000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-10 | 9/9/2021 | 2023-09-01 | 2023-11-30 |  |  |  |  | 82070000 | 79565087 | 20046792 | 6235944 | 39516463 | 2749314 | 17297478 | 59563255 | 65799199 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/342/334452-DR4339PR-DSOW-%20Caguas%20Short%20Term%20Group%203.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 3 | Rey Roldan Rodríguez |  |  |  |  | 1.3358 | 1 |  | 334452RFI342 | 334452 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334443 | 107520 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 14F000430000, 14F000500000, 14F000610000, 14F000570000, 14F000620000, 14F000410000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 111970000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-09 | 9/9/2021 | 2023-09-29 | [5 empty] | 111960000 | 104883530 | 51954249 | 8863340 | 52929281 | 7448718 | 44505531 | 104883530 | 113746870 | 2025-01-31 | 2025-07-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/343/334443%20-%20DR4339PR%20%20-%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%202.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 334443RFI343 | 334443 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334420 | 107519 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 14F000440000, 14F000710000, 14F000680000, 14F000590000, 14F000700000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 59850000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-09-30 | 2021-09-09 | 9/9/2021 | 2023-09-29 | [5 empty] | 59850000 | 70560944 | 25596317 | 8617160 | 44964627 | 3805840 | 21790477 | 70560944 | 79178104 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/344/334420%20-%20DR4339PR%20-%20FEMA%20SOW%20%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%201.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 334420RFI344 | 334420 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334334 | 107518 | FAASt Line 500 Ponce TC to Costa Sur SP (Transmission) | 14F002400000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 36590000 | [7 empty] | 2024-03-31 | 2021-09-08 | 9/8/2021 | [6 empty] | 36590000 | 36590000 |  |  |  |  | 0 | 36590000 | 36590000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/345/DI%20661562%20-%20DR%204339%20-10079-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%20500%20Ponce%20TC%20to%20Costa%20Sur%20SP%20Signed.pdf?web=1 | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn.The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Line 500 Ponce TC to Costa Sur SP | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 334334RFI345 | 334334 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334331 | 11528 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | 14F002410000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [5 empty] | 2024-07-22 | 117600000 | 2024-07-31 | 2024-08-22 |  | 2024-08-30 |  |  |  | 2023-12-31 | 2021-09-07 | 9/8/2021 | 2024-09-30 | 2025-07-01 | 2025-08-18 | 2025-07-18 | Mitigation information reset because the project was sent back. Insurance information reset because the project was sent back. |  | 51200000 | 0 |  | 2009300.52 | 31788090.96 |  | 0 | 31788090.96 | 33797391.48 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/346/DI%20661466%20-%20DR4339%2010080-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%201900%20Dos%20Bocas%20HP%20to%20San%20Sebastian%20TC%20Signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 1900 | 2025-07-28 16:16 | 2023-08-14 11:10 | Jahdiel Franqui | Line 1900 Dos Bocas HP to San Sebastian TC | Maria Mujica Gonzalez | 0 Months |  |  |  | 0 | 5 |  | 334331RFI346 | 334331 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334329 | 10629 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | 14F004140000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [14 empty] | 2022-01-31 | 2021-09-07 | 9/8/2021 | 2022-01-28 | 2022-05-04 |  |  |  |  | 42380000 | 380253 | 64134 | 25530 | 316119 | 0 | 64134 | 380253 | 405783 |  |  | 2022-05-20 |  | 380253 | 316119 |  |  |  |  | 380253 | 316119 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/347/DSOW%205.4.22.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 25530 |  | 1 | 1 |  | 334329RFI347 | 334329 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334323 | 10630 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | 14F004130000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | Restoration | FALSE | [6 empty] | 600000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  | 2022-01-31 | 2021-09-08 | 9/8/2021 | 2022-01-28 | 2022-05-04 |  |  |  |  | 40600000 | 392822 | 69130 | 26179 | 323152 | 0 | 69130 | 392282 | 418461 |  |  | 2022-05-26 |  | 392822 | 323692 |  |  |  |  | 392822 | 323692 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/348/334323-DR4339PR-Detailed%20SOW-Distribution%20Pole%20and%20Conductor%20Repair%20%E2%80%93%20Ponce%20Group%201-Rev3%20(3).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 26179 |  | 1.0014 | 1 |  | 334323RFI348 | 334323 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334308 | 107517 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 14F001040000, 14F001030000, 14F001010000, 14F000990000, 14F001020000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 74170000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-07-31 | 2021-09-08 | 9/8/2021 | 2023-07-01 | [5 empty] | 74170000 | 72626419 | 32030114 | 7650658 | 37671047 | 5407189 | 26622925 | 69701161 | 77351819 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/349/334308-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%201.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1.042 | 1 |  | 334308RFI349 | 334308 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334293 | 107516 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 14F003450000, 14F003440000, 14F003480000, 14F003420000, 14F003460000, 14F003430000, 14F003470000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 98490000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-07-31 | 2021-09-08 | 9/8/2021 | 2023-06-30 | 2023-11-30 |  |  |  |  | 98500000 | 86877699 | 45582792 | 5930015 | 41294907 | 5327428 | 40255364 | 86877699 | 92807714 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/350/Revised%20FEMA%20SOW%20-%20334293-DR4339PR-DSOW-%20Mayag%C3%BCez%20STG4%20-%20signed%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 4 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 334293RFI350 | 334293 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334285 | 107514 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 14F001100000, 14F001110000, 14F001070000, 14F001130000, 14F001120000, 14F001090000, 14F001060000, 14F001050000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 108840000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-07-31 | 2021-09-08 | 9/8/2021 | 2023-06-30 | 2023-11-30 |  |  |  |  | 108850000 | 81195988 | 35887745 | 6284173 | 42366398 | 4489868 | 31397877 | 78254143 | 84538316 | 2025-05-31 | 2025-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/351/334285-DR4339PR-DSOW%2010139%20-%20Mayag%C3%BCez%20STG2%20-%20signed%20(1)%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List 8/13/2024 Removed from Priority Projects, broken down further with pending faast number | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 1.0376 | 1 |  | 334285RFI351 | 334285 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
334191 | 107513 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 14F001200000, 14F001140000, 14F001190000, 14F001210000, 14F001160000, 14F001180000, 14F001170000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 134670000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  | 2023-07-31 | 2021-09-07 | 9/7/2021 | 2023-06-30 | 2023-11-30 |  |  |  |  | 134670000 | 98525716 | 38483744 | 7245123 | 37430424 | 6091551 | 32392193 | 75914168 | 83159291 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/352/334191-DR4339PR-%20DSOW%2010140%20-%20Mayag%C3%BCez%20STG3%20-%20signed%20(1)%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 3 | Rey Roldan Rodríguez |  |  |  |  | 1.2979 | 1 |  | 334191RFI352 | 334191 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
180326 | 11441 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | 14F002190000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 56130000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-08-31 | 2021-04-16 | 4/16/2021 | 2022-08-30 | 2024-01-12 |  |  |  |  | 70310000 | 0 | 32488767 | 6478150 | 60760627 | 3117231 | 29371536 | 93249394 | 99727544 | 2024-07-31 | 2024-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/353/180326-DR4339PR-%20Detailed%20SOW%20Line%2036800%20(10054-CP-SOW-0003_Rev.0).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 180326RFI353 | 180326 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
180052 | 11453 | FAASt Ponce TC to Jobos TC - 38kV 100 & 200 (Transmission) | 14F002170000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE |  | Current |  |  |  |  | 87280000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-08-31 | 2021-09-20 | 4/14/2021 | 2022-08-30 | 2025-06-13 | 2025-07-25 | 2025-07-22 | Field EHP: A Formal EHP Request for Information was initiated on 7/25/2025. EHP is requesting additional information for the subject project. This RFI is needed for compliance. To determine compliance with Endangered Species Act (ESA) the information requested (Refer RFI tab) should be provided by PA to EHP no later that 15 days. |  | 42900000 | 0 | 0 | 9582455.16 | 99892053.94 | 0 | 0 | 99892053.94 | 109474509.1 | 2024-06-30 | 2024-08-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/354/180052%20-%20DR4339PR-00%20FEMA%20DSOW%20-%20Existing%2038%20kV%20TLines%20100,%20200%20PonceTC-Jobos%20TC%2010052-CP-SOW-0003%20Rev%201.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 100/200 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-28 15:52 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Ponce TC to Jobos TC - 100 (Transmission) FASSt Ponce TC to Jobos TC - 200 (Transmission) | Maria Mujica Gonzalez | 0 Months |  |  |  | 0 | 5 |  | 180052RFI354 | 180052 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
179988 | 107305 | FAASt [Las Lomas – XFMR 1525] (Substation) | 14F003090000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2021-04-14 | 4/14/2021 | [6 empty] | 2400000 | 2400000 |  |  |  |  | 0 | 2400000 | 2400000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/355/179988-DR4339PR-Las%20Lomas%20-%20XFMER%201525%20-%20FEMA%20SOW%20CE%201-27-21.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 179988RFI355 | 179988 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
179558 | 10632 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 14F002820000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 1800000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-05-31 | 2021-04-09 | 4/9/2021 | 2022-05-02 | [5 empty] | 1800000 | 1593443 | 0 | 688917 | 1593443 | 0 | 0 | 1593443 | 2282360 |  |  | 2022-05-26 |  | 1593443 | 1593443 |  |  |  |  | 1593443 | 1593443 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/356/179558-DR4339PR%20-%20Detailed%20SOW%20-%20Manati%20TC%20-%20BRKS%20230kV%20(10106-CP-SOW-0002%20Rev1)%20(2).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Manati TC - BRKS 230 kv (Substation) | Rey Roldan Rodríguez |  |  | 688917 |  | 1 | 1 |  | 179558RFI356 | 179558 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
178577 | 11507 | FAASt [Cachete – MC 1526] (Substations) | 14F002810000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 4000000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2023-10-31 | 2021-04-01 | 4/1/2021 | 2023-10-02 | 2024-02-16 |  |  |  |  | 4000000 | 0 | 16340158.71 | 3196266.58 | 24361713.92 | 1892257.29 | 14447901.42 | 40701872.63 | 43898139.21 | 2025-02-28 | 2025-04-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/357/178577%20-%20DR4339PR%20-%20Cachete%20-%20MC%201526%20-%20FEMA%20SOW%20%20CE%201-27-21%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Cachete – MC 1526 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 178577RFI357 | 178577 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
178503 | 11100 | FAASt [Aguirre TC - BKRS] (Substations) | 14F002800000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 12200000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-10-31 | 2021-04-01 | 4/1/2021 | 2022-10-31 | 2023-03-22 |  |  |  |  | 12000000 | 39034592 | 0 | 5171019 | 39034592 | 0 | 0 | 39034592 | 44205611 |  |  | 2022-12-27 | 04/14/2023 | 39034592 | 39034592 | 39034592 | 39034592 |  |  | 39034592 | 39034592 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/358/178503-DR4339PR-%20Detail%20SOW-Aguirre%20TC%20-%20BKRS%20-%20(10104-CP-SOW-0002_Rev%201)%20(3).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Aguirre TC - BRKS | Rey Roldan Rodríguez |  |  | 5171019 |  | 1 | 1 |  | 178503RFI358 | 178503 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
178258 | 11721 | FAASt - [Taft - MC 1105] (Substations) | 14F002790000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 4100000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-05-31 | 2021-03-30 | 3/31/2021 | 2022-05-31 | 2024-05-10 | 2024-12-06 | 2024-11-29 |  |  | 4100000 | 13486572.33 | 4123842.4 | 1302381.39 | 9362729.93 | 961993.54 | 3161848.86 | 13486572.33 | 14788953.72 | 2024-10-31 | 2025-01-31 | 2025-02-06 |  | 13486572.33 | 9362729.93 |  |  |  |  | 13486572.33 | 9362729.93 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/359/178258-DR43339PR-%2000%20FEMA%20Detailed%20Scope%20Of%20Work%20REV.4%20Taft%20MC%201105%202023-07-06%20-%20signed.PDF?web=1 |  | 2025-07-24 15:17 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Taft – MC 1105 | Jose J Ramos Figueroa |  |  | 1302381.39 | 503587.39 | 1 | 1 |  | 178258RFI359 | 178258 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
177191 | 11433 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | 14F002340000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 9700000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2023-06-30 | 2021-03-24 | 3/24/2021 | 2022-09-08 | 2024-05-09 |  |  |  |  | 9700000 | 0 | 906873 | 2036324 | 17371561 | 93989 | 812884 | 18278434 | 20314758 | 2024-10-31 | 2025-01-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/360/177191%20DR4339PR-Detailed%20SOW%2039000%20Aguas%20Buenas%20TC%20to%20Caguas%20TC_Rev%200%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Aguas Buenas TC to Caguas TC - 39000 (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 177191RFI360 | 177191 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
177134 | 11440 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | 14F002330000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [5 empty] | 2024-10-03 | 25280000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2023-06-30 | 2021-03-26 | 3/24/2021 | 2023-06-08 | 2024-06-18 |  |  |  | 4 | 25280000 | 0 | 7821691 | 5401272 | 54274064 | 471725 | 7349966 | 62095755 | 67497027 | 2024-11-30 | 2025-01-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/361/177134-DR4339PR-10071-CP-SOW-0003_Rev0%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Guaraguao TC to Comerio TCLine-4100 (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 177134RFI361 | 177134 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
176971 | 11373 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 14F002320000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE |  | Current |  |  |  |  | 8070000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-07-31 | 2021-03-23 | 3/23/2021 | 2022-07-29 | 2025-06-13 | 2025-07-30 | 2025-07-18 | Field EHP: Formal Request for Information (RFI) sent to Applicant on 07/14/2025. ECD: 07/30/2025. | 6 | 8070000 | 15567361 | 0 | 3250894.37 | 23193643.55 | 0 | 0 | 23193643.55 | 26444537.92 | 2024-07-31 | 2024-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/362/176971-DR4339PR-Detailed%20SOW%20-%20TL8200%20Cata%C3%B1o%20Sect.%20to%20San%20Juan%20SP%20Rev.2.pdf?web=1 |  | 2025-07-25 15:51 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt San Juan SP to Catano SectLine-8200 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0.67119 | 2 |  | 176971RFI362 | 176971 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
176954 | 11439 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | 14F002310000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Improved | FALSE | [5 empty] | 2024-11-15 | 3580000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2023-06-30 | 2021-03-23 | 3/23/2021 | 2022-08-29 | 2023-07-03 |  |  |  |  | 3580000 | 0 | 4127356 | 571113 | 2791523 | 700994 | 3426362 | 6918879 | 7489992 | 2024-07-31 | 2024-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/363/176954%20Detail%20Scope%20of%20Work%2010069-CP-SOW-0003%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Garzas 1 HP to Garzas 2 HP - Line 1100 (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 176954RFI363 | 176954 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
176913 | 11432 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 14F002300000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE |  | Current |  |  |  |  | 6710000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-08-31 | 2021-03-23 | 3/23/2021 | 2022-07-29 | 2025-06-13 | 2025-08-11 | 2025-07-21 | Field EHP: EHP Formal Request for Information Initiated on 07/21/2025. EHP is requesting additional information for the subject project. This RFI is needed for Completeness and Compliance. To determine compliance, the following information should be provided no later than 15 business days (08/11/2025) from the date of this request. |  | 6710000 | 11649409 | 0 | 4817554.82 | 35985053.2 | 0 | 0 | 35985053.2 | 40802608.02 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/364/176913-DR4339-Detailed%20SOW%209500%20Palo%20Seco%20SP%20to%20Catano%20Sect.%20%20Line%209500%20(10068-CP-SOW-0003%20Rev%200)%20-%20signed.pdf?web=1 |  | 2025-07-25 15:50 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Palo Seco SP to Catano SectLine-9500 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0.32373 | 4 |  | 176913RFI364 | 176913 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
174422 | 10496 | FAASt - Catano-Rebuild 1801(Substation) | 14F002770000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 11300000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2021-10-31 | 2021-03-04 | 3/4/2021 | 2021-10-28 | 2022-04-08 |  |  |  |  | 11300000 | 23255048.94 | 807222.04 | 4104786 | 18571716 | 0 | 807222.04 | 19378938.04 | 23483724.04 |  |  | 2022-05-18 |  | 23255048.94 | 16359899.17 |  |  |  |  | 23255048.94 | 16359899.17 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/365/10000-CP-SOW-0001Rev2%20(3).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Cataño – Rebuilt 1801 | Rey Roldan Rodríguez |  |  | 1211174.91 |  | 1.2 | 1 |  | 174422RFI365 | 174422 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169896 | 10788 | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | 14F002750000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 3600000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-06-30 | 2021-02-02 | 2/2/2021 | 2022-06-07 | [5 empty] | 3600000 | 23251835 | 0 | 4734912 | 23251835 | 0 | 0 | 23251835 | 27986747 |  |  | 2022-08-02 |  | 23251835 | 23251835 |  |  |  |  | 23251835 | 23251835 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/366/169896%20-%20DR-4339-PR%20-%20Detailed%20Scope%20of%20Work%20-%20Costs%20Sur%20230kV%2010101%20(2).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Costa Sur SP TC – Equipment Repair and Replacement | Rey Roldan Rodríguez |  |  | 4734912 |  | 1 | 1 |  | 169896RFI366 | 169896 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169804 | 107227 | FAASt Aguadilla Electric Service Center (Building) | 14F001970000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 3500000 | [8 empty] | 2021-02-03 | 2/1/2021 | [6 empty] | 3500000 | 3500000 |  |  |  |  | 0 | 3500000 | 3500000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/367/%5B169804%5D-DR4339PR-Aguadilla%20Electric%20Service%20Center.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Buildings - Aguadilla Electric Service Center | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 169804RFI367 | 169804 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169798 | 107226 | FAASt Arecibo Electric Service Center (Building) | 14F001960000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 2320000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  |  | 2021-02-03 | 2/1/2021 | [6 empty] | 2320000 | 2320000 |  |  |  |  | 0 | 2320000 | 2320000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/368/%5B169798%5D-DR4339PR-Arecibo%20Electric%20Service%20Center.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Buildings - Arecibo Electric Service Center | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | 169798RFI368 | 169798 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169576 | 107225 | FAASt Arecibo Regional Office Building (Building) | 14F001950000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 1800000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  |  | 2021-02-03 | 1/29/2021 | [6 empty] | 1800000 | 1800000 |  |  |  |  | 0 | 1800000 | 1800000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/369/%5B169576%5D-DR4339PR-Arecibo%20Regional%20Office%20Building.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Buildings - Arecibo Regional Office Building | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | 169576RFI369 | 169576 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169503 | 107224 | FAASt [Ceiba Baja TRF 7012] (Substation) | 14F003080000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2021-01-29 | 1/29/2021 | [6 empty] | 2700000 | 2700000 |  |  |  |  | 0 | 2700000 | 2700000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/370/DI433943-DR4339PR-Substations%20-%20Ceiba%20Baja%20TRF%207012%20%20Intial%20SOW%20&%20CE%201-11-21%20(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 169503RFI370 | 169503 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169500 | 11347 | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | 14F002740000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [5 empty] | 2024-05-31 | 5700000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-06-30 | 2021-01-29 | 1/29/2021 | 2022-07-25 | 2023-05-02 |  |  |  |  | 5700000 | 6372063 | 3575881 | 634045 | 2796182 | 1496809 | 2079072 | 6372063 | 7006108 |  |  | 2023-06-16 |  | 6372063 | 2796182 |  |  |  |  | 6372063 | 2796182 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/371/169500-DR4339PR%20-%20FEMA%20DSOW%20-%20Bayamon%20TC%20(10100-CP-SOW-0002_Rev.4)%202023-04-2700-CP-SOW-0002_Rev.4.pdf |  | 2025-07-24 15:20 | 2023-08-14 11:10 | Jahdiel Franqui | Substations – Bayamon TC – MC-BKRS-Y1 | Jose J Ramos Figueroa |  |  | 634046 |  | 1 | 1 |  | 169500RFI371 | 169500 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169495 | 11479 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | 14F001760000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 23000000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-05-31 | 2021-01-29 | 1/29/2021 | 2022-05-31 | 2023-06-15 |  |  |  |  | 23000000 | 15339932.33 | 7159883.3 | 1397860 | 8180049 | 1044957.8 | 6114925.5 | 15339932.3 | 16737792.3 |  |  | 2023-08-22 |  | 15339932.33 | 8180049.03 |  |  |  |  | 15339932.33 | 8180049.03 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/372/169495-DR4339PR-%2000%20Detailed%20SOW%20Tapia%20Substation%20-%20(10059-CP-SOW-0002Rev6)(rev%202023-06-14)%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Tapia GIS Rebuilt - Equipment Repair and Replacement | Rey Roldan Rodríguez |  |  | 1397859.52 |  | 1 | 1 |  | 169495RFI372 | 169495 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169276 | 107222 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement [Substation] | 14F002730000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 4000000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2023-03-31 | 2021-01-28 | 1/28/2021 | 2023-03-31 | 2024-04-03 |  |  |  |  | 4000000 | 20425907 | 3661876.82 | 5917803.36 | 75107786 | 267449.67 | 3394427.15 | 78769662.82 | 84687466.18 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/373/169276-DR4339PR-10099-CP-SOW-0001_Rev.2%20-%20signed%202023-08-23%2012_08_10-1.pdf?web=1 | 3/27/2024: QC Review Complete | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substations) | Rey Roldan Rodríguez |  |  |  |  | 0.25931 | 4 |  | 169276RFI373 | 169276 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169266 | 11489 | FAASt Centro Medico 1327/1359 Equipment Repair & Replacement (Substation) | 14F002720000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 11700000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-05-31 | 2021-01-28 | 1/28/2021 | 2022-05-26 | 2023-07-27 |  |  |  |  | 11700000 | 21332361 | 6537037 | 1810918 | 14795324 | 0 | 6537037 | 21332361 | 23143279 |  |  | 2023-11-03 |  | 21332361 | 14795324 |  |  |  |  | 21332361 | 14795324 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/374/169266-DR4439PR-Detailed%20SOW-Centro%20Medico%201327%201359%20Equipment%20Repair%20&%20Replacement%20(Substation).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Centro Medico 1327/1359 Equipment Repair and Replacement | Rey Roldan Rodríguez |  |  | 1810918 |  | 1 | 1 |  | 169266RFI374 | 169266 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
169058 | 107220 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 14F002710000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Improved | FALSE | [6 empty] | 4000000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-05-31 | 2021-01-27 | 1/27/2021 | 2022-05-04 | 2025-05-05 |  |  |  |  | 4000000 | 18279001 | 13265333.34 | 1213803.7 | 23342346.17 | 655599.77 | 12609733.57 | 36607679.51 | 37821483.21 | 2024-12-31 | 2025-06-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/375/169058-DR4339PR-10097-CP-SOW-0002_Rev%204%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Substations - Llorens Torres MC 1106 - Equipment Repair & Replacement | Rey Roldan Rodríguez |  |  |  |  | 0.49932 | 3 |  | 169058RFI375 | 169058 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
168483 | 11241 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | 14F002290000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 83260000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-08-31 | 2021-01-22 | 1/22/2021 | 2022-08-29 | 2024-05-09 | 2025-07-30 | 2025-05-30 | Previous Comment Applies: Field EHP: ESA Consultation letter submitted to USFWS on 5/29/2025. Waiting for response. ECD 7/30/2025. |  | 87440000 | 0 | 8111071 | 10145828 | 96749488 | 339692 | 7771379 | 104860559 | 115006387 | 2024-06-30 | 2024-09-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/376/168483-DR4339PR-Detail%20SOW%20TL36400%20Dos%20Bocas%20HP%20to%20Ponce%20TC%20(10067-CP-SOW-0002_Rev0)%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 36400 | 2025-07-25 15:08 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission - Line 36400 - Dos Bocas HP to Ponce TC | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 |  | 168483RFI376 | 168483 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
168226 | 10978 | FAASt San Juan 115kV Underground Transmission Loop (Transmission) | 14F002280000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 11600000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-05-31 | 2021-01-20 | 1/20/2021 | 2022-05-02 |  | 2024-09-20 | 2024-09-16 |  |  | 89700000 | 14746039.57 | 0 | 584325 | 16420054 | 0 | 0 | 16420054 | 17004379 |  |  | 2022-12-21 | PENDING | 14746039.57 | 14746039.57 | 14746039.57 | 14746039.57 |  |  | 14746039.57 | 14746039.57 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/377/168226%20-Detailed%20SOW-115kV-%20TL%2038000%20%20San%20Juan-Isla%20Grande%20Underground%20Loop.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission - San Juan 115-kV Underground Transmission Loop | Rey Roldan Rodríguez |  |  | 2258339.67 |  | 0.89805 | 1 |  | 168226RFI377 | 168226 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
167508 | 11250 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | 14F002270000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 41390000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-11-30 | 2021-07-01 | 1/13/2021 | 2022-11-28 | 2024-05-14 |  |  |  |  | 43470000 |  | 4609955 | 7023284 | 71765405 | 200381 | 4409574 | 76375360 | 83398644 | 2024-07-31 | 2024-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/378/10065-%20TL-50100-%20Detailed%20SOW%20May%2026%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 50100 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission - Line 50100 - Cambalache GP TC to Manati TC (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 167508RFI378 | 167508 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
167446 | 11307 | FAASt - Line 36100 (115kV) - Dos Bocas HP to Monacillos TC (Transmission) | 14F002260000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE |  | Current |  |  |  | 2024-11-15 | 109970000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2023-06-30 | 2021-01-13 | 1/13/2021 | 2023-06-30 | 2025-07-18 | 2025-07-29 | 2025-07-08 | Field EHP - Historic: Initial review. Expected Completion Date (ECD) for initial review 08/15/2025. |  | 115490000 |  | 0 | 3374394.5 | 32930591.92 | 0 | 0 | 32930591.92 | 36304986.42 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/379/167446-DR4339PR-TL36100%20Detailed%20SOW%20-%20Dos%20Bocas%20HP%20to%20Monacillos%20TC%20-29JUNE2023-final%20signed%20(1)%20(1).pdf?web=1 |  | 2025-07-28 16:23 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt - Line 36100 - Dos Bocas HP to Monacillos TC (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 |  | 167446RFI379 | 167446 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
167443 | 11251 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | 14F002250000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [5 empty] | 2024-10-03 | 40690000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2023-07-31 | 2021-01-13 | 1/13/2021 | 2022-09-02 | 2024-01-19 |  |  |  |  | 42730000 | 0 | 15967020 | 6485111 | 62522200 | 1461125 | 14505895 | 78489220 | 84974331 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/380/167443-DR4339PR-Detailed%20SOW%20-%20TL36200%20Monacillos%20TC%20to%20Juncos%20TC%20rev%201%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 36200 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt - Line 36200 - Monacillos TC to Juncos TC (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 167443RFI380 | 167443 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
167168 | 11246 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | 14F002240000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 87590000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-09-30 | 2021-01-11 | 1/11/2021 | 2022-09-01 | 2023-06-30 |  |  |  |  | 91990000 |  | 24646695 | 10274876 | 96370356 | 2374619 | 22272076 | 121017051 | 131291927 | 2025-08-31 | 2025-01-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/381/167168-DR4339PR-%20Detailed%20SOW%20Line%2037100%20(10062-CP-SOW-0002_Rev1)%2028JUNE2023.pdf?web=1 | 13SEPTEMBER2024 DSOW Rev. 2 was removed from GP. It was originally submitted on January 12, 2024 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt_TRANSMISSION-LINE-37100_COSTA SUR-ST_ACACIAS-TC | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 167168RFI381 | 167168 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
166904 | 11451 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | 14F002230000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 32400000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-08-31 | 2021-01-07 | 1/7/2021 | 2022-08-01 | 2024-01-12 |  |  |  |  | 33400000 |  | 9229435 | 4855883 | 45544705 | 881999 | 8347436 | 54774140 | 59630023 | 2024-07-31 | 2024-10-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/382/166904-DR4339-Detailed%20SOW%2037800%20Caguas%20TC%20-%20Monacillos%20TC%20(10060-CP-SOW-0003%20Rev%200)%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 166904RFI382 | 166904 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
166860 | 11255 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | 14F002220000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 49510000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-08-31 | 2021-01-07 | 1/7/2021 | 2022-08-30 | 2024-03-22 |  |  |  |  | 52000000 | 0 | 19709323 | 7900833 | 74111756 | 1889975 | 17819348 | 93821079 | 101721912 | 2024-09-30 | 2025-02-28 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/383/166860-DSOW-115kV%20Transmission%20Line%2037800%20%E2%80%93%20Jobos%20TC%20to%20Caguas%20TC-Rev0.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 166860RFI383 | 166860 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
166834 | 107214 | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) |  | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 30430000 | [8 empty] | 2021-01-07 | 1/7/2021 | [6 empty] | 15980000 | 15980000 |  |  |  |  | 0 | 15980000 | 15980000 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/384/166834-DR4339PR-Transmission%20%20Line%2040100%20&%2040200%20-%20Aguirre%20SP%20TC%20to%20Jobos%20TC%20(1).pdf?web=1 | 9/12/2024 - GP Notes6/18/2024 - The project is not included in the 90-Day Plan submitted in June 2024. Forecast have been requested to the applicant.6/25/2024- The project was withdrawn | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 166834RFI384 | 166834 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
166707 | 11431 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | 14F002210000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 24840000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-11-30 | 2021-01-06 | 1/6/2021 | 2022-11-29 | 2024-02-02 |  |  |  |  | 26080000 | 0 | 16781976 | 3528829 | 28280524 | 1774233 | 15007743 | 45062500 | 48591329 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/385/166707-10057-DSOW-TL-51300.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | FAASt Transmission Line 51300 - Ponce TC to Costa Sur SP TC | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 166707RFI385 | 166707 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
165268 | 11045 | FAASt Rio Grande Estate Substation CH-2306 (Substation) | 14F001750000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Improved | FALSE | [5 empty] | 2024-11-22 | 3970000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-05-31 | 2020-12-18 | 12/18/2020 | 2022-05-20 | 2022-11-14 |  |  |  |  | 3700000 | 11683614.71 | 4585370.95 | 1391013 | 7098243 | 1768433.49 | 2816937.46 | 11683613.95 | 13074626.95 |  |  | 2022-12-21 |  | 11683614.71 | 7098243.76 |  |  |  |  | 11683614.71 | 7098243.76 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/386/165268-DR4339PR-%2000%20-%20Rio%20Grande%20Estates%20CH%202306%20Detailed%20Scope%20of%20Work%20Rev.%203%20(10055-CP-SOW-0003Rev3)%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Rio Grande Estates - CH - 2306 | Rey Roldan Rodríguez |  |  | 1391012.61 |  | 1 | 1 |  | 165268RFI386 | 165268 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
165226 | 107206 | FAASt [Feeders Vieques & Culebra] (Distribution) | 14F000930000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Current |  |  |  |  | 31130000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-12-31 | 2020-12-18 | 12/18/2020 | 2022-12-28 | 2024-09-18 |  |  |  |  | 28810000 | 57351920 | 27689656.16 | 7514394.03 | 59069587.62 | 3124702.64 | 24564953.52 | 86759243.78 | 94273637.81 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/387/165226-DR4339PR%20Detailed%20SOW%20Vieques%20&%20Culebra%20-%20signed%20(2).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Distribution – Vieques Feeders 2501-01, 2501-02, 2501-03 and Culebra Feeders 3801-01, 3801-02 | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.66105 | 2 |  | 165226RFI387 | 165226 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
165225 | 10624 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | 14F002700000, 14F008780000, 14F000940000, 14F000910000, 14F000930000, 14F000920000, 14F000950000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 37910000 | 2023-12-28 | 2024-01-30 |  | 2024-01-27 |  |  |  | 2022-03-31 | 2020-12-22 | 12/18/2020 | 2023-05-31 | 2025-01-30 | 2025-06-09 | 2025-05-09 |  |  | 37910000 | 14704637.25 | 0 | 1491087 | 13495526 | 0 | 0 | 13495526 | 14986613 |  |  | 2022-06-10 | PENDING | 1313648.1 | 1209111 | 15237167.97 | 15058858.97 |  |  | 1313648.1 | 1209111 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/388/165225-Detailed%20SOW-Vieques%20NEW%20Substation%20V1%20(2)%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Vieques 2501 & New Vieques Substation 2502 | Rey Roldan Rodríguez |  |  | 531763 |  | 1.0896 | 1 |  | 165225RFI388 | 165225 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
165213 | 11244 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 14F002200000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | Restoration | FALSE | [6 empty] | 73060000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 |  |  |  | 2022-11-30 | 2020-12-18 | 12/18/2020 | 2022-11-29 | 2024-11-11 |  |  |  |  | 73060000 | 0 | 39446157.65 | 6015993.93 | 80817479.56 | 2588226.22 | 36857931.43 | 120263637.21 | 126279631.14 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 | 2027-09-20 |  | Use this link: https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/389/165213-DR4339PR%20DSOW%20TL%205400%20Rio%20Blanco%20HP%20to%20DaguaoTC%20to%20Vieques%20To%20Culebra%20&%20Vieques%20and%20Culebra%20Microgrid%20Rev-3%2011-11-24.pdf?web=1 Combine the two DSOWs | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Rey Roldan Rodríguez | 0 Months |  |  |  | 0 | 5 |  | 165213RFI389 | 165213 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
165209 | 10626 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | 14F002690000, 14F008770000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | Restoration | FALSE | [6 empty] | 39100000 | 2023-12-28 | 2024-01-30 |  | 2024-01-27 |  |  |  | 2022-03-31 | 2020-12-18 | 12/18/2020 | 2023-05-31 | 2024-07-15 | 2024-11-01 | 2024-10-22 |  |  | 1200000 | 14048046 | 0 | 1493591 | 12765829 | 0 | 0 | 12765829 | 14259420 |  |  | 2022-06-10 | PENDING | 1387420 | 1282218 | 1387420 | 14314307.92 |  |  | 1387420 | 1282218 | 2027-09-20 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/390/165209-DR-4339PR-Culebra%20Substation%203801%20and%20New%20Culebra%20Substation%203802%20FEMA%20Detailed%20Scope%20of%20Work%20Rev.%208%20(7.12.2024)%20-%20signed.pdf?web=1 | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Culebra 3801 & New Culebra Substation 3802 | Rey Roldan Rodríguez |  |  | 522360 |  | 1.1004 | 1 |  | 165209RFI390 | 165209 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
165208 | 107205 | FAASt Transmission Access Roads (Environmental) | 10F000180000 |  | Transmission | To be allocated to appropriate program |  |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 16970000 | [8 empty] | 2020-12-18 | 12/18/2020 | [6 empty] | 15186702.6 | 15186702.6 |  |  |  |  | 0 | 15186702.6 | 15186702.6 | [10 empty] | 0 | 0 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/391/165208-DR4339PR-Transmission%20Access%20Roads-11.24.2020.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Manager Joanna Dlugopolski. | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui | Transmission Access Roads | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 165208RFI391 | 165208 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
136271 | 6099 | MEPA078 Puerto Rico Electrical Power Authority Island Wide FAASt Project |  |  | Other | TBD |  | FALSE | [16 empty] | 4/23/2020 | [7 empty] | 4132895287.7 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2020-09-24 | 9/18/2024 | 6129706543.59 | 6323452979.59 | 5955252831.92 | 6148999267.92 | 4106613749.59 | 4300360185.59 | 4106613749.59 | 4300360185.59 | 2027-09-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/392/PRJ_Report_136271_20241106.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez | [7 empty] | 136271RFI392 | 136271 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
83182 | 1294 | MEPA181-Others- PREPA Management Costs | 14F003210000 | PBCP04 - PM Software & Tools | Other | TBD | [18 empty] | 3/20/2019 | [7 empty] | 620193956.54 |  |  | 620193956.5 | 0 | 0 | 620193956.5 | 620193956.5 |  |  | 2020-02-05 | 04/14/2023 | 52465131.5 | 52465131.5 | 620193956.54 | 620193956.54 |  |  | 620193956.54 | 620193956.54 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/393/PRJ_Report_83182_20240219.pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  | 0 |  | 1 | 1 |  | 83182RFI393 | 83182 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
68753 | 1165 | MEPA149- A&E Services-PW 01165 |  |  | Other | TBD | [18 empty] | 11/28/2018 | [7 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2019-09-06 18:37 | [7 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-08-14 11:10 | Jahdiel Franqui |  | Rey Roldan Rodríguez | [7 empty] | 68753RFI394 | 68753 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
728832 | 11718 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 15F019860000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Current | [12 empty] | 2023-07-31 | 2023-07-31 | 08/17/2023 | 2023-08-17 | 2024-11-18 | 2025-03-21 | 2025-03-18 |  | 2 |  | 2380535.97 | 23418437.42 |  |  | 203638.57 | 23214798.85 | 23418437.42 | 23418437.42 | 2024-08-31 | 2024-11-30 | 2025-04-28 |  | 14260691.9 | 3767690.42 |  |  |  |  | 14260691.9 | 3767690.42 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/395/38kV%20and%20below%20DSOW-%20Region%205_%20Mayaguez%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 13:37 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  | 0 |  | 0.10165 | 5 |  | 728832RFI395 | 728832 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
728827 | 11714 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 14F019550000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Current | [12 empty] | 2023-07-31 | 2023-07-31 | 08/17/2023 | 2023-08-17 | 2024-11-18 | 2025-03-28 | 2025-03-17 |  | 2 |  | 3036845.07 | 29878565.39 |  |  | 259813.59 | 29618751.8 | 29878565.39 | 29878565.39 | 2024-09-30 | 2024-12-31 | 2025-04-28 |  | 18194308.81 | 4807675.47 |  |  |  |  | 18194308.81 | 4807675.47 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/396/38kV%20and%20below%20DSOW-%20Region%202_%20Arecibo%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-14 13:38 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  | 0 |  | 0.10164 | 5 |  | 728827RFI396 | 728827 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
729522 | 107905 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | 14F019070000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation |  |  |  | Past | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-08-10 | 8/25/2023 | [6 empty] | 700000000 | 700000000 |  |  |  |  | 0 | 700000000 | 700000000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/398/DR4339PR%20-%20ISOW%20T%20and%20D%20Auto.%20Prog.%20Intelligent%20Recls,%20Single%20Ph%20Rec%20and%20Fault%20Current%20Indicators.pdf | 9/12/2024 - GP Notes "9/5/2024 The project was withdrawn with the comment "Applicant requested project withdrawal, for reference see: 729522-DR4339PR-Applicant requested project withdrawal.pdf". | 2025-07-18 18:28 | 2023-08-22 10:38 | Gabriel Licha | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | 729522RFI397 | 729522 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
729286 | 11726 | FAASt HV Equipment Replacement Group 2 (Substation) | 14F019990000, 14F020000000, 14F020100000, 14F019980000, 14F020200000, 14F021120000, 14F021130000, 14F019970000 | PBUT07 - Substation Reliability | Substation | Substation Rebuilds | Restoration | FALSE |  | Past | [12 empty] | 2023-09-30 | 2023-07-17 | 8/23/2023 | 2023-09-29 | 2024-03-28 |  |  |  | 5 | 25611121 | 15413889.89 | 0 | 2006783 | 15413890 | 0 | 0 | 15413890 | 17420673 | 2024-06-30 | 2024-08-31 | 2024-07-08 |  | 15413889.89 | 15413889.89 |  |  |  |  | 15413889.89 | 15413889.89 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/400/729286%20DR4339PR%20FAASt%20HV%20Equipment%20Replacement%20Group%202%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-08-24 08:11 | Gabriel Licha | Substation High Voltage Equipment Replacement | Rey Roldan Rodríguez |  |  | 2006782.81 |  | 1 | 1 |  | 729286RFI398 | 729286 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
730821 | 107911 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 14F000140000, 14F000150000, 14F000120000, 14F000110000, 14F000130000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 73900000 | 2021-08-30 | 2021-08-20 |  | 2021-09-29 |  |  |  | 2023-09-30 | 2023-08-31 | 09/11/2023 | 2023-09-29 |  |  |  |  | 2 | 73910000 | 80513487 | 27363279 | 6380697 | 53150208 | 2513389 | 24849890 | 80513487 | 86894184 | 2025-04-30 | 2025-10-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/402/10134-EN-SOW-0001_Rev%20ARECIBO%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-09-01 14:29 | Marlina Crespo | Distribution Feeders - Arecibo Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 730821RFI399 | 730821 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
730824 | 107912 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 14F001400000, 14F001370000, 14F001390000, 14F001380000, 14F001410000, 14F001420000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 42380000 | [7 empty] | 2023-11-30 | 2023-08-31 | 09/11/2023 | 2023-11-30 |  |  |  |  | 1 | 42380000 | 42380000 | 2840853 | 1157768 | 2957665 | 799199 | 2041654 | 5798518 | 6956286 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/403/10141-EN-SOW-0001_Rev%20Ponce%202%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-09-01 14:30 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 7.3088 | 1 |  | 730824RFI400 | 730824 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
730513 | 107907 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | 14F000670000, 14F000690000, 14F000780000, 14F000630000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 44710000 | [7 empty] | 2023-09-30 | 2023-08-31 | 09/07/2023 | 2023-09-29 | 2023-11-30 |  |  |  | 2 | 44710000 | 38886020 | 10929872 | 3184390 | 24634172 | 1251143 | 9678729 | 35564044 | 38748434 | 2024-11-30 | 2025-05-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/404/10148-EN-ISOW-0001_Rev%20Caguas%204%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-09-01 14:32 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 4 | Rey Roldan Rodríguez |  |  |  |  | 1.0934 | 1 |  | 730513RFI401 | 730513 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
730541 | 107908 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | 14F000370000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE |  | Past |  |  |  |  | 23640000 | [7 empty] | 2023-09-30 | 2023-08-31 | 09/07/2023 | 2023-09-30 |  |  |  |  | 2 | 23650000 | 31124653 | 18671456 | 2070079 | 12453197 | 2618347 | 16053109 | 31124653 | 33194732 | 2024-10-31 | 2025-04-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/405/10152-EN-ISOW-0001_Rev%20Caguas%208%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-09-01 14:34 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 8 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 730541RFI402 | 730541 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
730586 | 107909 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 14F001300000, 14F001310000, 14F001330000, 14F001350000, 14F001320000, 14F001340000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild | Restoration | FALSE | [6 empty] | 40610000 | [7 empty] | 2023-09-30 | 2023-08-31 | 09/08/2023 | 2023-09-29 |  |  |  |  | 2 | 40600000 | 26972761 | 12719346 | 4716393 | 14253415 | 3101803 | 9617543 | 26972761 | 31689154 | 2025-06-30 | 2025-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/406/10012-EN-SOW-0001_Rev%20Ponce%201%20-%20signed%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2023-09-01 14:35 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 730586RFI403 | 730586 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738972 | 107931 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3 - Phase 2] (Distribution) | 14F018500000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-09-13 | 11/17/2023 | [6 empty] | 3500000 | 3500000 |  |  |  |  | 0 | 3500000 | 3500000 | [10 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/407/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Caguas%20Group%203%20-%20Phase%202%20(2).pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:28 | 2023-09-07 15:51 | Gabriel Licha | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 738972RFI404 | 738972 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738971 | 11812 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 14F018490000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  | Restoration | FALSE |  | Past | [13 empty] | 2023-09-07 | 11/17/2023 | 2024-02-06 | 2024-05-13 | 2025-01-10 | 2025-01-03 |  | 2 | 3000000 | 14261249.67 | 377124 | 1643630 | 13884126 | 66835.67 | 310288.33 | 14261250 | 15904880 | 2024-07-31 | 2024-10-31 | 2025-02-06 |  | 14261249.67 | 13884126 |  |  |  |  | 14261249.67 | 13884126 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/408/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Caguas%20Group%202%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:28 | 2023-09-07 15:54 | Gabriel Licha | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 1643630 | 33543 | 1 | 1 |  | 738971RFI405 | 738971 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
730657 | 11559 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | FALSE | [6 empty] | 103810000 | 2021-07-04 | 2021-08-20 |  | 2021-08-03 |  |  |  | 2024-03-31 | 2023-09-08 | 09/08/2023 | [6 empty] | 103800000 | 0 |  |  |  |  | 0 | 103800000 | 103800000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/409/334468-DR4339PR-Initial%20SOW%20(2).pdf?web=1 |  | 2025-07-18 18:28 | 2023-09-11 14:48 | Marlina Crespo | Line 2200 Dos Bocas HP to Dorado TC | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 730657RFI406 | 730657 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
730784 | 107910 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) | 14F002500000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 6010000 |  |  | 2024-05-24 | [5 empty] | 2023-09-11 | 09/11/2023 | [6 empty] | 6010000 | 6010000 |  |  |  |  | 0 | 6010000 | 6010000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/410/73784-DR4339PR-Line%206700%20Martin%20Pe%C3%B1a%20TC%20to%20Villamar%20Sect.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 5/24/2024. | 2025-07-18 18:28 | 2023-09-12 08:43 | Marlina Crespo | Line 6700 Martin Peña TC to Villamar Sect. | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 730784RFI407 | 730784 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738670 | 11712 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 14F018990000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  | Restoration | FALSE |  | Past | [12 empty] | 2023-12-31 | 2023-10-06 | 11/15/2023 | 2024-01-19 | 2024-02-16 | 2024-10-25 | 2024-10-22 |  | 3 | 7140000 | 5074511.01 | 147871 | 439975 | 4926640 | 31370.9 | 116500.1 | 5074511 | 5514486 | 2024-06-30 | 2024-11-30 | 2024-11-25 |  | 5074511.01 | 4926640 |  |  |  |  | 5074511.01 | 4926640 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/436/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Ponce%20Group%201%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:28 | 2023-10-09 08:57 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 439974.62 |  | 1 | 1 |  | 738670RFI408 | 738670 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
737825 | 107925 | FAAST[Distribution Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 14F019010000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created | [9 empty] | 2023-12-31 | 2023-10-06 | 11/07/2023 | [6 empty] | 7140000 | 7140000 |  |  |  |  | 0 | 7140000 | 7140000 | [10 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/437/-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%201%20-%20Phase%202%20Rev0%201.pdf?web=1 | Project was resubmitted into Grants Portal under a new FAAst #. Old number was 737825. New number is 742070. Edited on 01/10/2024 by J Fournier. 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:28 | 2023-10-09 09:00 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 737825RFI409 | 737825 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738667 | 107927 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | 14F019000000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  | Restoration | FALSE | [14 empty] | 2024-03-31 | 2023-10-06 | 11/15/2023 | 2024-07-15 | 2025-06-13 |  |  |  |  | 6120000 | 6120000 | 33268.04 | 1724241.14 | 14893960.55 | 17535.19 | 15732.85 | 14927228.59 | 16651469.73 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/438/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Ponce%20Group%202%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:28 | 2023-10-09 09:02 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 0.40999 | 3 |  | 738667RFI410 | 738667 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738143 | Project Not In GP | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 14F019020000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created | [9 empty] | 2023-12-31 | 2023-10-06 | 11/09/2023 | [6 empty] | 5100000 | 5100000 |  |  |  |  | 0 | 5100000 | 5100000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/439/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20San%20Juan%20Group%202%20-%20Phase%202.pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. Project was resubmitted into Grants Portal under a new FAAst #7420269/13/2024 - GP Notes "11/29/2023 The project was deleted" - GP Query pulls as old status "Pending Formulation Completion" ensure to filter out project | 2025-07-18 18:28 | 2023-10-09 09:04 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 738143RFI411 | 738143 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738672 | 11686 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 14F018870000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  | Restoration | FALSE |  | Past | [12 empty] | 2023-11-30 | 2023-10-06 | 11/15/2023 | 2023-12-04 | 2024-04-17 | 2024-10-22 | 2024-10-15 |  | 2 | 8160000 | 10619758.37 | 306131 | 834793 | 10313627 | 63002.37 | 243128.63 | 10619758 | 11454551 | 2024-06-30 | 2024-11-30 | 2024-11-25 |  | 10619758.37 | 10313627 |  |  |  |  | 10619758.37 | 10313627 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/440/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Mayaguez%20Group%201%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:28 | 2023-10-09 09:05 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 834793 |  | 1 | 1 |  | 738672RFI412 | 738672 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738674 | 107928 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | 14F018960000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  | Restoration | FALSE |  | Past | [12 empty] | 2024-03-31 | 2023-10-06 | 11/15/2023 | 2024-07-03 | 2025-06-13 |  |  |  |  | 9180000 | 9180000 | 28130.53 | 922352.8 | 8013484.69 | 14786.8 | 13343.73 | 8041615.22 | 8963968.02 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/441/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Mayaguez%20Group%202%20-%20Phase%202.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-09 09:07 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez | 0 months |  |  |  | 1.1416 | 1 |  | 738674RFI413 | 738674 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738696 | 107930 | FAASt [Distribution Pole and Conductor Repair - Carolina Group 2 - Phase 2] (Distribution) | 14F018940000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2023-10-06 | 11/15/2023 | [6 empty] | 5100000 | 5100000 |  |  |  |  | 0 | 5100000 | 5100000 | [10 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/442/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Carolina%20Group%202%20-%20Phase%202.pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 2025-07-18 18:28 | 2023-10-09 09:09 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 738696RFI414 | 738696 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738692 | 107929 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | 14F018930000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | TRUE | 2025-08-31 | [14 empty] | 2023-10-06 | 11/15/2023 | [6 empty] | 5100000 | 5100000 |  |  |  |  | 0 | 5100000 | 5100000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/443/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Carolina%20Group%201%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:28 | 2023-10-09 09:10 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 738692RFI415 | 738692 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734393 | 11805 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | 14F018570000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/11/23 | 2024-04-30 |  |  |  |  | 1 | 6205493 | 7838709 | 1016421 | 1851275 | 7838709 | 194188 | 822233 | 8855130 | 10706405 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/444/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Cabo%20Rojo%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:35 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88522 | 1 |  | 734393RFI416 | 734393 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735474 | 107918 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 14F018500000 | PBUT05 - Distr Streetlighting | Distribution – Pole Replacement |  |  | FALSE |  | Current | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-03-27 | [5 empty] | 2023-10-10 | 10/20/2023 | 2025-01-31 | 2025-04-24 | 2025-05-14 | 2025-05-02 |  |  | 11758959 | 3500000 | 0 | 1962097 | 16785005 | 0 | 0 | 16785005 | 18747102 | 2026-05-31 | 2026-09-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/445/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Caguas%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. DSOW was submitted 3.27.2024 on project 136271 for FEMA revision and project formulation. 3/25/2024: QC Review Complete 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 | 2025-07-18 18:28 | 2023-10-11 10:36 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.20852 | 4 |  | 735474RFI417 | 735474 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734396 | 107915 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | 14F018580000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/11/23 | 2024-07-12 | [5 empty] | 6205493 | 6205493 | 1169678 | 1692815 | 6988631 | 228078 | 941600 | 8158309 | 9851124 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/446/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Cabo%20Rojo%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:37 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.76063 | 2 |  | 734396RFI418 | 734396 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735483 | 107919 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | 14F018860000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-06-28 | [5 empty] | 2023-10-10 | 10/20/2023 | [6 empty] | 5377685 | 5377685 |  |  |  |  | 0 | 5377685 | 5377685 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/447/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Vega%20Baja%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:39 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | 735483RFI419 | 735483 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734760 | 11830 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | 14F018740000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/13/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 14475396 | 13799462 | 1946734 | 2696696 | 13799462 | 318240 | 1628494 | 15746196 | 18442892 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/448/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Ponce%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:40 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87637 | 1 |  | 734760RFI420 | 734760 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735360 | 11832 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | 14F018720000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/19/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 8010318 | 13951292 | 2189842 | 2675465 | 13951292 | 352374 | 1837468 | 16141134 | 18816599 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/449/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Mayaguez%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:40 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.86433 | 1 |  | 735360RFI421 | 735360 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734728 | 11774 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | 14F018730000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/13/2023 | 2024-03-27 | 2024-04-12 |  |  |  | 2 | 14475396 | 12998720.23 | 1402396 | 2475101 | 12998720 | 224318 | 1178078 | 14401116 | 16876217 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/450/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Ponce%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-11 10:44 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.90262 | 1 |  | 734728RFI422 | 734728 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735357 | 11777 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | 14F018710000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/19/2023 | 2024-03-27 | 2024-04-12 |  |  |  | 2 | 8010318 | 7368131.58 | 1097078 | 1731118 | 7368132 | 208717 | 888361 | 8465210 | 10196328 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/451/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Mayaguez%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-11 10:45 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.8704 | 1 |  | 735357RFI423 | 735357 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734928 | 107917 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | 14F018700000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/16/2023 | [6 empty] | 5293882 | 5293882 |  |  |  |  | 0 | 5293882 | 5293882 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/452/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Isabela%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:46 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | 734928RFI424 | 734928 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734927 | 11773 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | 14F018690000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/16/2023 | 2024-03-27 | 2024-04-12 |  |  |  | 2 | 5293882 | 8007445.57 | 1301829 | 1834728 | 8007445 | 242681 | 1059148 | 9309274 | 11144002 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/453/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Isabela%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/25/2024: QC Review Complete 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:48 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.86016 | 1 |  | 734927RFI425 | 734927 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735487 | 107920 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | 14F018680000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-06-28 | [5 empty] | 2023-10-10 | 10/20/2023 | 2024-08-22 | [5 empty] | 5817139 | 5817139 | 916292 | 1627090 | 7901161 | 188693 | 727599 | 8817453 | 10444543 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/454/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Humacao%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:49 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.65973 | 2 |  | 735487RFI426 | 735487 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734791 | 11808 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | 14F018630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/13/2023 | 2024-04-30 |  |  |  |  | 1 | 5424696 | 5650820 | 757008 | 1536868 | 5650820 | 161863 | 595145 | 6407828 | 7944696 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/455/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guayama%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-11 10:55 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88186 | 1 |  | 734791RFI427 | 734791 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735493 | 11799 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | 14F018670000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-04-30 | [5 empty] | 2023-10-10 | 10/20/2023 | 2024-04-30 |  |  |  |  | 1 | 5817139 | 6274071 | 916292 | 1627090 | 6274071 | 188693 | 727599 | 7190363 | 8817453 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/456/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Humacao%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-11 10:56 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87257 | 1 |  | 735493RFI428 | 735493 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734789 | 107916 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | 14F018640000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/13/2023 | 2024-08-22 | [5 empty] | 5424696 | 5424696 | 635977 | 1444780 | 6296106 | 145939 | 490038 | 6932083 | 8376863 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/457/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guayama%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 10:57 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.78255 | 2 |  | 734789RFI429 | 734789 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735496 | 11835 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | 14F018620000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-05-31 | [5 empty] | 2023-10-10 | 10/20/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 11936785 | 14764763 | 2019124 | 2756137 | 14764763 | 317620 | 1701504 | 16783887 | 19540024 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/458/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Carolina%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:05 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.8797 | 1 |  | 735496RFI430 | 735496 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735499 | 107921 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | 14F018660000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-06-28 | [5 empty] | 2023-10-10 | 10/20/2023 | [6 empty] | 7033301 | 7033301 |  |  |  |  | 0 | 7033301 | 7033301 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/459/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guaynabo%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:07 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | 735499RFI431 | 735499 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735665 | 11783 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | 14F018610000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/23/2023 | 2024-03-28 | 2024-04-12 |  |  |  | 2 | 11936785 | 12296300.92 | 557536 | 2334972 | 12296301 | 88976 | 468560 | 12853837 | 15188809 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/460/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Carolina%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/25/2024: QC Review Complete 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-11 11:08 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.95662 | 1 |  | 735665RFI432 | 735665 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735672 | 11838 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | 14F018600000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/23/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 11758959 | 11986815 | 1624355 | 2432645 | 11986815 | 274039 | 1350316 | 13611170 | 16043815 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/461/FEMA%20ISOW%20Distribution%20Streetlighting%20-%20Caguas%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:09 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.88066 | 1 |  | 735672RFI433 | 735672 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735677 | 11801 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | 14F018650000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/23/2023 | 2024-04-30 |  |  |  |  | 1 | 7033301 | 7566377 | 1014066 | 1759349 | 7566377 | 191308 | 822758 | 8580443 | 10339792 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/462/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guaynabo%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:10 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88182 | 1 |  | 735677RFI434 | 735677 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735940 | 11806 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | 14F018850000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/25/2023 | 2024-04-30 |  |  |  |  | 1 | 5377685 | 7551926.09 | 1067250 | 1758054 | 7551927 | 201535 | 865715 | 8619177 | 10377231 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/463/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Vega%20Baja%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:10 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87618 | 1 |  | 735940RFI435 | 735940 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735952 | 11831 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | 14F018840000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/25/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 5588214 | 7111974 | 1149506 | 1726148 | 7111974 | 224507 | 924999 | 8261480 | 9987628 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/464/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Trujillo%20Alto%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:12 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.86086 | 1 |  | 735952RFI436 | 735952 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735954 | 11772 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | 14F018830000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/25/2023 | 2024-03-27 | 2024-04-12 |  |  |  | 2 | 5588214 | 6426439.39 | 884864 | 1636132 | 6426439 | 179565 | 705299 | 7311303 | 8947435 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/465/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Trujillo%20Alto%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-11 11:16 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87897 | 1 |  | 735954RFI437 | 735954 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735959 | 107922 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | 14F018820000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/25/2023 | [6 empty] | 5878458 | 5878458 |  |  |  |  | 0 | 5878458 | 5878458 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/466/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Baja%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:17 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | 735959RFI438 | 735959 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735960 | 11803 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | 14F018810000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-10 | 10/25/2023 | 2024-04-30 |  |  |  |  | 1 | 5878458 | 7964179 | 1238774 | 1818344 | 7964179 | 230260 | 1008514 | 9202953 | 11021297 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/467/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Baja%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:18 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.86539 | 1 |  | 735960RFI439 | 735960 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
737699 | 107923 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | 14F018800000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-06-28 | [5 empty] | 2023-10-10 | 11/07/2023 | [6 empty] | 5526895 | 5526895 |  |  |  |  | 0 | 5526895 | 5526895 | [10 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/468/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Alta%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:18 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | 737699RFI440 | 737699 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
737707 | 11797 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | 14F018790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-04-30 | [5 empty] | 2023-10-10 | 11/07/2023 | 2024-04-30 |  |  |  |  | 1 | 5526895 | 7066938 | 979674 | 1741115 | 7066938 | 193656 | 786018 | 8046612 | 9787727 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/469/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Alta%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:20 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87825 | 1 |  | 737707RFI441 | 737707 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
737712 | 11836 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | 14F018780000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-05-31 | [5 empty] | 2023-10-10 | 11/07/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 24022779 | 27223280 | 3250259 | 4358459 | 27223280 | 448553 | 2801706 | 30473539 | 34831998 | [10 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/470/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20San%20Juan%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:23 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.89334 | 1 |  | 737712RFI442 | 737712 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738120 | 11850 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 14F018940000 | PBUT05 - Distr Streetlighting | Distribution – Pole Replacement | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-03-27 | [5 empty] | 2023-10-10 | 11/09/2023 | 2024-05-24 |  | 2024-11-05 | 2024-10-28 |  | 1 | 24022779 | 11451170.81 | 286036 | 1159111 | 11041271 | 175368.81 | 110667.19 | 11327307 | 12486418 | 2024-06-30 | 2024-11-30 | 2024-11-25 |  | 11451170.81 | 11041271 |  |  |  |  | 11451170.81 | 11041271 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/471/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20San%20Juan%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. DSOW was submitted 3.27.2024 on project 136271 for FEMA revision and project formulation. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:24 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 1159111 |  | 1.0109 | 1 |  | 738120RFI443 | 738120 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
737798 | 107924 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | 14F018760000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-06-28 | [5 empty] | 2023-10-10 | 11/07/2023 | 2024-08-22 | [5 empty] | 4962759 | 4962759 | 877731 | 1513312 | 7059041 | 188168 | 689563 | 7936772 | 9450084 | [10 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/472/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Rio%20Grande%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-11 11:25 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.62529 | 2 |  | 737798RFI444 | 737798 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
737804 | 11809 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | 14F018750000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-04-30 | [5 empty] | 2023-10-10 | 11/07/2023 | 2024-04-30 |  |  |  |  | 1 | 4962759 | 6104606.88 | 838135 | 1588337 | 6104607 | 173048 | 665087 | 6942742 | 8531079 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 | 2019-03-20 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/473/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Rio%20Grande%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-11 11:27 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87928 | 1 |  | 737804RFI445 | 737804 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735131 | 11775 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | 14F018530000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-11 | 10/18/2023 | 2024-03-27 | 2024-04-12 |  |  |  | 2 | 10338400 | 11247096.52 | 1546160 | 2337125 | 11247096 | 266012 | 1280148 | 12793256 | 15130381 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/474/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Arecibo%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | QC Review Complete: Mar 25 2024 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-12 08:53 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.87914 | 1 |  | 735131RFI446 | 735131 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734853 | 11837 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | 14F018540000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-11 | 10/16/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 10338400 | 15679863.58 | 2684586 | 2921897 | 15679863 | 421685 | 2262901 | 18364449 | 21286346 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/475/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Arecibo%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-12 08:54 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.85382 | 1 |  | 734853RFI447 | 734853 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
734859 | 11780 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | 14F018510000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | [13 empty] | 2023-10-11 | 10/16/2023 | 2024-03-27 | 2024-04-12 |  |  |  | 2 | 6655166 | 8885681.25 | 1346103 | 1987953 | 8885681 | 246099 | 1100004 | 10231784 | 12219737 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/476/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20iSOW%20Aguadilla%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | QC Review Complete: 3/25/2024 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-12 08:55 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.86844 | 1 |  | 734859RFI448 | 734859 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735472 | 11833 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | 14F018560000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-05-31 | [5 empty] | 2023-10-11 | 10/20/2023 | 2024-05-31 | 2024-06-05 |  |  |  | 2 | 14963904 | 18291400 | 2632407 | 3249865 | 18291400 | 397144 | 2235263 | 20923807 | 24173672 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/477/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Bayam%C3%B3n%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-12 08:56 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.87419 | 1 |  | 735472RFI449 | 735472 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735470 | 11804 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | 14F018550000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted |  |  |  |  | 2024-04-30 | [5 empty] | 2023-10-11 | 10/20/2023 | 2024-04-30 |  |  |  |  | 1 | 14963904 | 17963819 | 1727642 | 3031817 | 17963819 | 249476 | 1478166 | 19691461 | 22723278 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/478/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Bayam%C3%B3n%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn. 4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:28 | 2023-10-12 08:57 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.91226 | 1 |  | 735470RFI450 | 735470 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
735338 | 11834 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | 14F018520000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | FALSE |  | Past | [13 empty] | 2023-10-19 | 10/19/2023 | 2024-05-31 |  |  |  |  | 1 | 6655166 | 8195391 | 1423703 | 1856753 | 8195391 | 262975 | 1160728 | 9619094 | 11475847 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/479/735338-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Aguadilla%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-10-20 13:30 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.85199 | 1 |  | 735338RFI451 | 735338 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738671 | 11819 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | 14F019600000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  |  | FALSE | [6 empty] | 216580000 | 2023-08-25 | 2023-08-30 |  | 2023-09-24 |  |  |  | 2024-03-31 | 2023-10-25 | 11/15/2023 | 2025-04-25 | [5 empty] | 216800000 | 216800000 | 55941767.5 | 0 | 0 | 5211394.35 | 50730373.15 | 55941767.5 | 55941767.5 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/480/FEMA%20ISOW%2025MW%20BESS%20102423%20v1%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-10-25 17:00 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez |  |  |  |  | 3.8755 | 1 |  | 738671RFI452 | 738671 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
749060 | 11874 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | 14F020780000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | Restoration | FALSE |  | Current | [13 empty] | 2023-11-14 | 06/05/2024 | 2024-06-05 | 2025-07-10 |  |  |  | 2 | 924000 | 717817.65 | 191065.8 | 154904.41 | 1211818.22 | 21644.91 | 169420.89 | 1402884.02 | 1557788.43 | 2024-08-31 | 2024-12-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/481/136271-DR4339PR-TL5600%20Priority%20Pole%20Replacement-Initial%20Scope%20of%20Work.pdf?web=1 |  | 2025-07-18 18:28 | 2023-11-14 09:14 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.51167 | 3 |  | 749060RFI453 | 749060 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
749072 | 11877 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | 14F020680000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | Restoration | TRUE | 2025-09-30 | Current | [13 empty] | 2023-11-27 | 06/05/2024 | 2024-06-05 | 2025-01-02 |  |  |  | 2 | 693000 | 158495.32 | 30755.87 | 20635.01 | 158495.32 | 3542.94 | 27212.93 | 189251.19 | 209886.2 | 2024-08-31 | 2024-12-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/482/136271-DR4339PR%20TL%202700%20Priority%20Pole%20Replacement%20Initial%20Scope%20of%20Work%20Aguadilla%20Hospital%20Distrito%20Sect%20-%20Mora%20TC%20-%20signed.pdf |  | 2025-07-18 18:28 | 2023-11-27 12:32 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.83749 | 1 |  | 749072RFI454 | 749072 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
740406 | 107933 | FAASt [Region 1-San Juan Group B] (Vegetation) | 15F019320000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Past | FALSE | [11 empty] | 2023-11-30 | 2023-12-08 | 12/08/2023 | 2023-12-11 | 2025-03-07 |  |  |  | 1 |  | 691016.47 | 5894785.29 |  |  | 1682447.99 | 4212337.3 | 5894785.29 | 5894785.29 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/483/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20San%20Juan.xlsx?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:36 PM AST Project Updated Title: FAASt [Region 1-San Juan Group B] High Density (Vegetation) -> FAASt [Region 1-San Juan Group B] (Vegetation) FAASt #756472 merged under project | 2025-07-18 18:28 | 2023-12-11 09:28 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.11723 | 5 |  | 740406RFI455 | 740406 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
740408 | 107934 | FAASt [Region 3-Bayamon Group B] (Vegetation) | 15F019520000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Past | FALSE | [11 empty] | 2023-11-30 | 2023-12-08 | 12/08/2023 | 2023-12-11 | 2025-03-07 |  |  |  | 1 |  | 1049080.08 | 11782088.78 | 0 | 0 | 1838308.82 | 9943779.96 | 11782088.78 | 11782088.78 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/484/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20Bayamon.xlsx?web=1 | 10/22/2024 - Grants Portal 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 3-Bayamon Group B] High Density (Vegetation) -> FAASt [Region 3-Bayamon Group B] (Vegetation) FAASt #756474 merged under project | 2025-07-18 18:28 | 2023-12-11 09:29 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.08904 | 5 |  | 740408RFI456 | 740408 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
740409 | 107935 | FAASt [Region 4-Caguas Group B] (Vegetation) | 15F019470000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Past | FALSE | [11 empty] | 2023-12-31 | 2023-12-08 | 12/08/2023 | 2023-12-11 | 2025-03-07 | [5 empty] | 3068261.01 | 23846154.02 |  |  | 2150317.53 | 21695836.49 | 23846154.02 | 23846154.02 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/485/Region%204_Caguas%20Group%20B%20-%20PW%20740409%20DSOW%2012_19_25.pdf?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 4-Caguas Group B] High Density (Vegetation) -> FAASt [Region 4-Caguas Group B] (Vegetation) FAASt 756476 MERGED UNDER PROJECT | 2025-07-18 18:28 | 2023-12-11 09:29 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.12867 | 5 |  | 740409RFI457 | 740409 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
740410 | 107936 | FAASt [Region 2-Arecibo Group B] (Vegetation) | 15F019570000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Past | FALSE | [11 empty] | 2023-12-31 | 2023-12-08 | 12/08/2023 | 2023-12-11 | 2025-03-07 | [5 empty] | 30966.29 | 5425376.76 | 0 | 0 | 1658267.85 | 3767108.91 | 5425376.76 | 5425376.76 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/486/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20Arecibo.xlsx?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:40 PM AST Project Updated Title: FAASt [Region 2-Arecibo Group B] High Density (Vegetation) -> FAASt [Region 2-Arecibo Group B] (Vegetation) FAASt 756475 MERGED UNDER PROJECT | 2025-07-18 18:28 | 2023-12-11 09:30 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.0057077 | 5 |  | 740410RFI458 | 740410 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
740411 | 107937 | FAASt [Region 5-Mayaguez Group B] (Vegetation) | 14F019420000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Past | FALSE | [11 empty] | 2023-12-31 | 2023-12-08 | 12/08/2023 | 2023-12-11 | 2025-03-07 |  |  |  | 1 |  | 720951.73 | 3777166.88 | 0 | 0 | 1618073.62 | 2159093.26 | 3777166.88 | 3777166.88 | 2024-09-30 | 2025-02-28 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/487/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20Mayaguez.xlsx?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:47 PM AST Project Updated Title: FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) -> FAASt [Region 5-Mayaguez Group B] (Vegetation) FAASt 756477 MERGED UNDER PROJECT | 2025-07-18 18:28 | 2023-12-11 09:31 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.19087 | 5 |  | 740411RFI459 | 740411 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
740414 | 107938 | FAASt [Region 6-Ponce Group B] High Density (Vegetation) | 15F019370000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  | Past | FALSE | [11 empty] | 2023-12-31 | 2023-12-08 | 12/08/2023 | 2023-12-19 | 2025-03-07 |  |  |  | 1 |  | 1316423.25 | 13788400.37 | 0 | 0 | 1887413.02 | 11900987.35 | 13788400.37 | 13788400.37 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/488/Region%206_Ponce%20Group%20B%20-%20PW%20740414%20DSOW%202_19_25.pdf?web=1 |  | 2025-07-18 18:28 | 2023-12-11 09:31 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.095473 | 5 |  | 740414RFI460 | 740414 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
740662 | 107939 | FAASt [Automation Program Group 2] (TL/ Distribution) | 14F003310000, 14F003320000, 14F005110000, 14F003590000, 14F001610000, 14F003510000, 14F005180000, 14F004820000, 14F003270000, 14F005090000, 14F003570000, 14F000800000, 14F001430000, 14F004840000, 14F004710000, 14F005080000, 14F003560000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation |  | TRUE | 2025-09-30 | Past | FALSE | [11 empty] | 2023-10-31 | 2023-12-08 | 12/11/2023 | 2023-12-13 |  |  |  |  | 1 | 4500000 | 4500000 | 7224272 | 314567 | 2285726 | 873947 | 6350325 | 9509998 | 9824565 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/489/703222-DR4339PR-APPENDIX%20B-%20Initial%20SOW%20T&D%20Automation%20-%20Group%2002.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-12-11 10:19 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.47319 | 3 |  | 740662RFI461 | 740662 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741097 | 107940 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | 14F019290000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | FALSE | [12 empty] | 2023-12-15 | 12/15/2023 | 2023-12-19 |  |  |  |  | 1 |  | 1267726 | 1347191.63 |  |  |  | 1347191.63 | 1347191.63 | 1347191.63 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/491/Appendix%20C%20_Region%201%20San%20Juan%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 2025-07-18 18:28 | 2023-12-18 14:58 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.94101 | 1 |  | 741097RFI462 | 741097 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741098 | 107941 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | 14F019490000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-12-15 | 12/15/2023 | 2023-12-19 |  |  |  |  | 1 |  | 961519 | 961518.65 |  |  |  | 961518.65 | 961518.65 | 961518.65 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/492/Appendix%20C%20_Region%203%20Bayamon%20Substation%20and%20Telecom%20location.xlsx?web=1 | 07JULY2025 - The project was withdrawn | 2025-07-18 18:28 | 2023-12-18 15:00 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-07-07 | 741098RFI463 | 741098 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741100 | 107942 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | 14F019440000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-12-15 | 12/15/2023 | 2023-12-19 |  |  |  |  | 1 |  | 1428326.03 | 1428325.86 |  |  |  | 1428325.86 | 1428325.86 | 1428325.86 | 2024-10-31 | 2025-03-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/493/Appendix%20C%20_Region%204%20Caguas%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 2025-07-18 18:28 | 2023-12-18 15:01 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-07-07 | 741100RFI464 | 741100 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741101 | 107943 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | 14F019540000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-12-15 | 12/15/2023 | 2023-12-19 |  |  |  |  | 1 |  | 956850.56 | 1058188.92 |  |  |  | 1058188.92 | 1058188.92 | 1058188.92 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/494/Appendix%20C%20_Region%202%20Arecibo%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 2025-07-18 18:28 | 2023-12-18 15:02 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.90423 | 1 | 2025-07-07 | 741101RFI465 | 741101 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741102 | 107944 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | 14F019390000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-12-15 | 12/15/2023 | 2023-12-19 |  |  |  |  | 1 |  | 956850.56 | 1516985.37 |  |  |  | 1516985.37 | 1516985.37 | 1516985.37 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/495/Appendix%20C%20_Region%205%20Mayaguez%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 2025-07-18 18:28 | 2023-12-18 15:03 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.63076 | 2 | 2025-07-07 | 741102RFI466 | 741102 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741104 | 107945 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | 14F019340000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2023-12-15 | 12/15/2023 | 2023-12-18 | 2023-12-19 |  |  |  | 1 |  | 1538820 | 1992973.53 |  |  |  | 1992973.53 | 1992973.53 | 1992973.53 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/496/Region%201%20San%20Juan%20Substation%20and%20Telecom%20location%20(1).xlsx?web=1 |  | 2025-07-18 18:28 | 2023-12-18 15:04 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.77212 | 2 | 2025-07-07 | 741104RFI467 | 741104 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741105 | 107946 | FAASt [All Regions TL - 230kV] (Vegetation) | 14F019590000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  | FALSE |  |  | FALSE | [12 empty] | 2023-12-15 | 12/15/2023 | 2023-12-18 | 2025-03-07 |  |  |  | 1 |  | 27012545.63 | 157385518.05 |  |  | 2593672.87 | 154791845.18 | 157385518.05 | 157385518.05 | 2025-02-28 | 2025-08-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/497/Appendix%20C%20-%20Island-wide%20Cost%20Estimate%20for%20230KV%20.xlsx?web=1 |  | 2025-07-18 18:28 | 2023-12-18 15:05 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0.17163 | 5 |  | 741105RFI468 | 741105 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 1 |  | Substations HV Equipment Replacement (Group 3) |  |  | Substation | [5 empty] | FALSE | [11 empty] | 2024-03-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-20 15:25 | Marlina Crespo | Substation High Voltage Equipment Replacement | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 1RFI469 | FAASt Number Pending 1 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 4 |  | Vieques & Culebra Microgrid |  |  | Grid Modernization |  |  | FALSE |  | Past | FALSE |  |  |  | 122250000 | [7 empty] | 2024-01-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:04 | Marlina Crespo | Vieques and Culebra Microgrid | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 4RFI470 | FAASt Number Pending 4 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 5 |  | Island Wide Vegetation Clearing: Region 6 Ponce Substations & Telecommunications Sites |  |  | Vegetation | [5 empty] | FALSE | [11 empty] | 2023-12-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:05 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 5RFI471 | FAASt Number Pending 5 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 6 |  | Island Wide Vegetation Clearing: Region 5 Mayaguez Substations & Telecommunications Sites |  |  | Vegetation | [5 empty] | FALSE | [11 empty] | 2023-12-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:07 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 6RFI472 | FAASt Number Pending 6 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 7 |  | Island Wide Vegetation Clearing: Region 4 Caguas Substations & Telecommunications Sites |  |  | Vegetation | [5 empty] | FALSE | [11 empty] | 2023-12-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:07 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 7RFI473 | FAASt Number Pending 7 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 8 |  | Island Wide Vegetation Clearing: Region 3 Bayamon Substations & Telecommunications Sites |  |  | Vegetation | [5 empty] | FALSE | [11 empty] | 2023-12-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:08 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 8RFI474 | FAASt Number Pending 8 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 9 |  | Island Wide Vegetation Clearing: Region 2 Arecibo Substations & Telecommunications Sites |  |  | Vegetation | [5 empty] | FALSE | [11 empty] | 2023-12-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:09 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 9RFI475 | FAASt Number Pending 9 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 10 |  | Island Wide Vegetation Clearing: Region 1 San Juan Substations & Telecommunications Sites |  |  | Vegetation | [5 empty] | FALSE | [11 empty] | 2023-12-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:10 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 10RFI476 | FAASt Number Pending 10 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 11 |  | Island Wide Vegetation Clearing: All Regions Transmission - 230 kV |  |  | Vegetation | [5 empty] | FALSE | [11 empty] | 2023-12-31 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:10 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 11RFI477 | FAASt Number Pending 11 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 12 |  | Carolina Group 2 – Phase 2 |  |  | Distribution – Pole Replacement | [5 empty] | FALSE | [11 empty] | 2024-02-29 | [14 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-21 12:11 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 12RFI478 | FAASt Number Pending 12 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
749124 | 107963 | FAASt [Automation Program Group 7] (Distribution) | 10F001780000, 14F004770000, 10F001790000, 10F001770000, 10F001750000, 14F004780000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  |  | FALSE | [11 empty] | 2024-01-31 | 2024-01-31 | 06/05/2024 | [7 empty] | 3342857 |  |  |  |  | 0 | 0 | 0 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/517/729522-DR4339PR-DSOW%20Automation%20Group%207-%20DAR%20-%20BAYAMON%201709,%201719%20-%20FY24%20-%20signed%20(1).pdf?web=1 |  | 2025-07-18 18:28 | 2023-12-21 12:16 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | 749124RFI479 | 749124 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 25 |  | DAR - BAYAMON 9401, 9801, 9802 - FY24 |  |  | Grid Automation |  | Restoration |  |  |  | FALSE | [11 empty] | 2024-01-31 | [10 empty] | 1776856 | 124341 | 725740 | 182964 | 1593892 | 2502596 | 2626937 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/522/729522-DR4339PR-%20DSOW-%20Group%208-%20DAR%20-%20BAYAMON%209401%209801%209802%20-%20FY24%20-%20signed.pdf?web=1 | 7AUGUST2024 ISOW / DSOW submitted on 1/31/24 - this project was replaced with another project - MC22JANUARY2025 - Removing the DSOW date - MC | 2025-07-18 18:28 | 2023-12-21 12:19 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | FAASt Number Pending 25RFI480 | FAASt Number Pending 25 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
745854 | 107955 | FAASt [ Automation Program Group 9] (Distribution) | 10F001850000, 10F001890000, 10F001870000, 10F001900000, 10F001860000, 10F001880000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  |  | FALSE | [11 empty] | 2024-01-31 | 2024-01-31 | 03/22/2024 | 2024-01-31 | 2024-06-18 |  |  |  | 2 |  | 1711509 | 1164604 | 52795 | 494110 | 112423 | 1052181 | 1658714 | 1711509 | 2025-01-31 | 2025-07-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/526/729522-DR4339PR-DSOW-Group%209%20-%20DAR%20-%20BAYAMON%201703,%201704%20-FY24%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-12-21 12:21 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.0318 | 1 |  | 745854RFI481 | 745854 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
745871 | 107958 | FAASt [Automation Program Group 10] (Distribution) | 10F001920000, 14F004800000, 10F001910000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  |  | FALSE | [11 empty] | 2024-01-31 | 2024-01-31 | 03/22/2024 | 2024-01-31 |  |  |  |  | 1 |  | 861045 | 582637 | 26876 | 251532 | 56244 | 526393 | 834169 | 861045 | 2025-08-31 | 2026-01-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/527/729522-DR4339PR-DSOW-%2010%20-%20DAR%20-%20BAYAMON%201717%209503%20-FY24%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-12-21 12:23 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.0322 | 1 |  | 745871RFI482 | 745871 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
745851 | 107953 | FAASt [Automation Program Group 11] (Distribution) | 10F001940000, 10F001950000, 14F004790000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  |  | FALSE | [11 empty] | 2024-01-31 | 2024-01-31 | 03/22/2024 | 2024-01-31 | [6 empty] | 1532152 | 1052298 | 46322 | 433532 | 101582 | 950716 | 1485830 | 1532152 | 2024-07-31 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/528/729522-DR4339PR-DSOW%20Automation%20Group-%20Group%2011%20DAR%20Bayamon%201901,%201907-FY24%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-12-21 12:24 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.0312 | 1 |  | 745851RFI483 | 745851 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
745859 | 11839 | FAASt [Automation Program Group 18] (Distribution) | 10F000550000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  | Past | FALSE | [11 empty] | 2024-01-31 | 2024-01-31 | 03/22/2024 | 2024-01-31 | 2024-07-26 |  |  |  | 6 |  | 467287.59 | 0 | 60837.64 | 467287.59 | 0 | 0 | 467287.59 | 528125.23 | 2024-10-31 | 2025-01-31 | 2024-09-18 |  | 467287.59 | 467287.59 |  |  |  |  | 467287.59 | 467287.59 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/550/729522-DR4339PR-DSOW%20Automation%20%20Group%2018%20-%20DAR%20-%20SAN%20JUAN%202001%20-%20FY24%20-%20signed%20(1).pdf?web=1 | 4/01/2024: QC Review Complete 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-24 15:35 | 2023-12-21 12:44 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Jose J Ramos Figueroa | 0 Months |  | 60837.65 |  | 1 | 1 |  | 745859RFI484 | 745859 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 56 |  | DAR - SAN JUAN 2403,2404 - FY24 |  |  | Grid Automation |  | Restoration | FALSE |  |  | FALSE | [11 empty] | 2024-01-31 | [10 empty] | 570640 | 41953 | 322238 | 65735 | 504905 | 892878 | 934831 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/552/729522-DR4339PR-DSOW%20Group%2017-%20DAR%20-%20SAN%20JUAN%202403,2404%20-%20FY24%20-%20signed.pdf?web=1 | 7AUGUST2024 ISOW / DSOW submitted on 1/31/24 - this project was replaced with another project - MC 22JANUARY2025 - Removing the DSOW date - MC | 2025-07-18 18:28 | 2023-12-21 12:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | FAASt Number Pending 56RFI485 | FAASt Number Pending 56 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
745861 | 107957 | FAASt [Automation Program Group 12] (Distribution) | 10F000610000, 10F000630000, 10F000620000, 10F000640000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  | Past | FALSE | [11 empty] | 2024-02-29 | 2024-01-31 | 03/22/2024 | 2024-06-20 | 2024-10-21 | 2024-12-16 | 2024-12-03 |  | 2 |  | 2360527 | 0 | 477953.55 | 3664210.1 | 0 | 0 | 3664210.1 | 4142163.65 | 2025-01-31 | 2025-07-31 | 2025-02-06 |  | 3664210.1 | 3664210.1 |  |  |  |  | 3664210.1 | 3664210.1 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/553/745861-DR4339PR-DSOW-%20Group%2012-%20DAR%20-%20ARECIBO%207402%207403%207702-%20FY24%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-12-21 12:45 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  | 477953.55 |  | 0.64421 | 2 |  | 745861RFI486 | 745861 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
745852 | 107954 | FAASt [Automation Program Group 13] (Distribution) | 10F001020000, 10F001050000, 10F001040000, 10F001060000, 10F001030000, 14F004690000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  |  | FALSE | [11 empty] | 2024-01-31 | 2024-01-31 | 03/22/2024 | 2024-01-31 | 2024-03-25 |  |  |  | 1 |  | 2854430 | 1966004 | 85763 | 802663 | 189786 | 1776218 | 2768667 | 2854430 | 2025-01-31 | 2025-07-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/555/729522-DR4339PR-DSOW%20Group%2013%20-%20DAR%20-%20ARECIBO%208010,%208013,%208015%20-%20FY24%20-%20signed.pdf?web=1 |  | 2025-07-18 18:28 | 2023-12-21 12:46 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.031 | 1 |  | 745852RFI487 | 745852 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
745856 | 107956 | FAASt [Automation Program Group 14] (Distribution) | 10F000570000, 10F000580000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  | Past | FALSE | [11 empty] | 2024-01-31 | 2024-01-31 | 03/22/2024 | 2024-01-31 | 2024-10-04 | 2024-12-26 | 2024-12-10 |  | 1 |  | 1237309 | 0 | 208604.89 | 1640186.96 | 0 | 0 | 1640186.96 | 1848791.85 | 2025-01-31 | 2025-07-31 | 2025-02-06 |  | 1640186.96 | 1640186.96 |  |  |  |  | 1640186.96 | 1640186.96 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/557/729522-DR4339PR-DSOW%20Group%2014%20-%20DAR%20-%20ARECIBO%208404%20-%20FY24.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-12-21 12:47 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | 0 Months |  | 208604.89 |  | 0.75437 | 2 |  | 745856RFI488 | 745856 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
741678 | 107947 | FAASt [Automation Program Group 4] (TL/Distribution) | 14F005130000, 14F005190000, 14F003290000, 14F004810000, 14F005170000, 14F003350000, 14F005120000, 14F003280000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation | Restoration | TRUE | 2025-08-31 | Past | FALSE | [12 empty] | 2023-12-21 | 12/22/2023 | 2023-12-22 | [5 empty] | 5800000 | 13712378.94 | 10499139.71 | 360048.57 | 2853190.65 | 1176445.32 | 9322694.39 | 13352330.36 | 13712378.93 | 2025-07-31 | 2025-12-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/561/741678%20DR4339PR%20DSOW%20Automation%20Group%204-%20SAN%20JUAN%20BAYAMON%20REGION%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:28 | 2023-12-22 16:08 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.027 | 1 |  | 741678RFI489 | 741678 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana Llana |  |  |  |  | Transmission | [5 empty] | FALSE |  |  | 2024-02-01 | [17 empty] | 3000000000 | [5 empty] | 0 | 3000000000 | 3000000000 | [10 empty] | 0 | 0 |  |  | 3/20/2024 LUMA Regulatory notes on ISOW submission to PREB - On hold. Awaiting guidance | 2025-07-18 18:28 | 2023-12-27 09:56 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana LlanaRFI490 | Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana Llana | Item | sites/Test4552/Lists/ISOW DSOW Tracker
3700 - Striker to Arroyo |  |  |  |  | Transmission | [5 empty] | FALSE |  |  | 2024-01-12 |  | 2024-04-18 | 2024-05-07 |  | 2024-05-18 | 2024-04-17 | 2024-03-22 | [10 empty] | 2083233 | [5 empty] | 0 | 2083233 | 2083233 | [10 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (6 - no PLRC) | 2025-07-18 18:28 | 2023-12-27 09:56 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 3700 - Striker to ArroyoRFI491 | 3700 - Striker to Arroyo | Item | sites/Test4552/Lists/ISOW DSOW Tracker
36600 115kV San Sebastian – Dos Bocas (Batch 6) |  |  |  |  | Transmission | [5 empty] | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:56 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | 36600 115kV San Sebastian – Dos Bocas (Batch 6)RFI492 | 36600 115kV San Sebastian – Dos Bocas (Batch 6) | Item | sites/Test4552/Lists/ISOW DSOW Tracker
San Juan UG 115 KV Rebuild |  |  |  |  | Transmission | [5 empty] | FALSE | [20 empty] | 195373742 | [5 empty] | 0 | 195373742 | 195373742 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:56 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | San Juan UG 115 KV RebuildRFI493 | San Juan UG 115 KV Rebuild | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending |  | Sub Rebuilds - Substation that have Functional Specs/will have functional specs |  | PBUT08 - Substation Rebuilds | Substation | [5 empty] | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:58 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | PendingRFI494 | Pending494 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending |  | Sub Rebuild - Canas TC |  | PBUT08 - Substation Rebuilds | Substation | [5 empty] | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:59 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | PendingRFI495 | Pending495 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending |  | Sub Rebuild - Santurce Planta |  | PBUT08 - Substation Rebuilds | Substation | [5 empty] | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 09:59 | Gabriel Licha | Santurce Planta (Sect) 1116 | Rey Roldan Rodríguez | [7 empty] | PendingRFI496 | Pending496 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Sub Rebuild - Fajardo Sect |  |  |  | PBUT08 - Substation Rebuilds | Substation | [5 empty] | FALSE |  |  | 2024-01-25 | [17 empty] | 101312645.45 | [5 empty] | 0 | 101312645.45 | 101312645.45 | [10 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Regulatory Notes on ISOW to PREB - PREB Submittal Target Date: On Hold, Notes: On hold. Awaiting guidance | 2025-07-18 18:28 | 2023-12-27 09:59 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer1 | Sub Rebuild - Fajardo Sect | Item | sites/Test4552/Lists/ISOW DSOW Tracker
T&D Model Upgrades and Repair |  |  |  |  | Distribution | [5 empty] | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:28 | 2023-12-27 10:00 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | qwer2 | T&D Model Upgrades and Repair | Item | sites/Test4552/Lists/ISOW DSOW Tracker
742026 | 11716 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 14F019020000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-01-04 | 01/04/2024 | 2024-01-04 | 2024-02-20 |  |  |  | 4 |  | 1117411.77 | 84036 | 83943 | 1033376 | 0 | 84036 | 1117412 | 1201355 | 2024-06-30 | 2024-08-31 | 2024-05-31 |  | 1117411.77 | 1033375.81 |  |  |  |  | 1117411.77 | 1033375.81 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/584/742026-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%202%20-%20Phase%202%20Rev0.pdf?web=1 | Project created with the following damages initially assigned: 661700. 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2024-01-04 11:32 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 83942.74 |  | 1 | 1 |  | qwer3 | 742026 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
742070 | 11753 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 14F019010000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-01-05 | 01/05/2024 | 2024-01-05 | 2024-03-04 |  |  |  | 2 | 7140000 | 5666787.43 | 205587 | 491327 | 5461200 | 35032.38 | 170554.62 | 5666787 | 6158114 | 2024-06-30 | 2024-08-31 | 2024-06-18 |  | 5666787.43 | 5461200.05 |  |  |  |  | 5666787.43 | 5461200.05 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/585/742070-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%201%20-%20Phase%202%20Rev0%201.pdf?web=1 | Project was resubmitted into Grants Portal under a new FAAst #. Old number was 737825. New number is 742070. Edited on 01/10/2024 by J Fournier. 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 2025-07-18 18:28 | 2024-01-12 16:33 | Jason Fournier | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 491326.68 |  | 1 | 1 |  | qwer4 | 742070 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
TBD L37400 Barceloneta TC - Cambalache TC |  |  |  |  | Transmission | [5 empty] | TRUE | [12 empty] | 2024-01-17 | [7 empty] | 927000 | [5 empty] | 0 | 927000 | 927000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/586/136271-DR4339PR-INITIAL%20SOW-Line%2037400%20Priority%20Pole%20Replacement%20Barceloneta%20TC%20-%20Cambalache%20TC%20-%20signed%5B25319%5D.pdf?web=1 | 02MAY2025 37400 is not a priority, and we dont know when it will be requested as a fasst - MC | 2025-07-18 18:30 | 2024-01-17 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer5 | TBD L37400 Barceloneta TC - Cambalache TC | Item | sites/Test4552/Lists/ISOW DSOW Tracker
743399 | 11764 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 14F021320000, 14F021330000, 14F021310000 | PBUT07 - Substation Reliability | Substation |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-01-18 | 01/29/2024 | 2024-03-28 |  |  |  |  | 1 | 22777596 | 17307539.01 | 0 | 2253323.31 | 17307538.97 | 0 | 0 | 17307538.97 | 19560862.28 | 2024-06-30 | 2024-11-30 | 2024-08-26 |  | 17307539.01 | 17307539.01 |  |  |  |  | 17307539.01 | 17307539.01 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/587/DR4339PR%20-FEMA%20ISOW%20HV%20Equipment%20Replacement%20Group%203%20Rev%200%20-%20signed.pdf?web=1 |  | 2025-07-24 15:41 | 2024-01-24 17:17 | Marlina Crespo | Substation High Voltage Equipment Replacement | Jose J Ramos Figueroa |  |  | 2253322.97 |  | 1 | 1 |  | qwer6 | 743399 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
744072 | 107948 | FAASt [IT OT Technology Systems Reparations] Group 2 (Telecommunication) |  | PBIT01 - Telecom Sys & Network | Telecommunications |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-02-09 | 02/09/2024 | 2025-03-21 | [5 empty] | 42700000 | 42700000 | 490438.07 | 181440.64 | 1893141.74 | 42892.47 | 447545.6 | 2383579.81 | 2565020.45 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/588/744072-DR4339PR-FEMA%20Initial%20Scope%20of%20Work%20Network%20%20Communication%20Rev%200_01312024.pdf?web=1 | ISOW was never submitted to the Island Wide FAASt Project | 2025-07-18 18:30 | 2024-02-12 09:14 | Marlina Crespo | IT OT Technology Systems Reparations | Rey Roldan Rodríguez |  |  |  |  | 17.9142 | 1 |  | qwer7 | 744072 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 65 |  | T-Pole L700 - Costa Sur SP - Yauco 2 HP |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-15 12:39 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer8 | FAASt Number Pending 65 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 66 |  | T-Pole L6500 -Toro Negro HP-Barranquitas TC |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-15 12:40 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer9 | FAASt Number Pending 66 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 72 |  | DAR - CAGUAS 2603, 2801, 2803, 2906 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 11:00 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer10 | FAASt number pending 72 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 73 |  | DAR - CAGUAS 3004, 3007, 3009 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 12:17 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer11 | FAASt number pending 73 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 74 |  | DAR - CAGUAS 3014, 3015 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 12:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer12 | FAASt number pending 74508 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 74 |  | DAR - CAGUAS 3101, 3103, 3205 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:02 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer13 | FAASt number pending 74509 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 75 |  | DAR - CAGUAS 3302, 3401, 3406, 3502 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:02 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer14 | FAASt number pending 75 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 76 |  | DAR - CAGUAS 3601, 3602, 3604, 3701 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer15 | FAASt number pending 76 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 77 |  | DAR - CAGUAS 9601, 9605, 8703 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:07 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer16 | FAASt number pending 77 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 78 |  | DAF - Fuse Cutout Installation – Group B |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:08 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer17 | FAASt number pending 78 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 80 |  | DAR - PONCE 5002, 5004, 5007 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:51 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer18 | FAASt number pending 80 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 81 |  | DAR - PONCE 5018, 5019 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:52 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer19 | FAASt number pending 81 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 82 |  | DAR - PONCE 5301, 5302, 5304 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:54 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer20 | FAASt number pending 82 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 83 |  | DAR - PONCE 5501, 5802, 5803, 5817, 5901 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:54 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer21 | FAASt number pending 83 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 84 |  | DAF - Fuse Cutout Installation – Group D |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:56 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer22 | FAASt number pending 84 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 85 |  | DAF - Fuse Cutout Installation – Group C |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:56 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer23 | FAASt number pending 85 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 86 |  | DAR - ARECIBO 8404, 8405 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 13:57 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer24 | FAASt number pending 86 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 87 |  | DAR - ARECIBO 9004 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:42 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer25 | FAASt number pending 87 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 88 |  | DAR - SAN JUAN 1204, 1346 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:42 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer26 | FAASt number pending 88 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 89 |  | DAR - CAGUAS 2601, 2602, 2701, 2702 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:43 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer27 | FAASt number pending 89 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 90 |  | DAR - CAGUAS 2901, 3006 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:43 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer28 | FAASt number pending 90 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 91 |  | DAR - CAGUAS 3010, 3013 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer29 | FAASt number pending 91 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 92 |  | DAR - CAGUAS 3102, 3201, 3301 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer30 | FAASt number pending 92 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 93 |  | DAR - CAGUAS 3405, 3501 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer31 | FAASt number pending 93 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 94 |  | DAR - CAGUAS 9901, 9902 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:46 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer32 | FAASt number pending 94 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 95 |  | DAR - SAN JUAN 1646 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:50 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer33 | FAASt number pending 95 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 96 |  | DAR – BAYAMON 9501, 9502 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:50 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer34 | FAASt number pending 96530 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 96 |  | DAR - ARECIBO 9101, 9105, 9201 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:52 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer35 | FAASt number pending 96531 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 97 |  | DAR - PONCE 4001, 5602, 6601 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:30 | 2024-03-18 14:57 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer36 | FAASt number pending 97 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
746309 | 107959 | FAASt [Automation Program Group 30] (TL/Distribution) | 10F000560000 | PBUT04 - Distribution Automation | Grid Automation |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 2024-04-01 | 04/02/2024 | 2024-04-01 | 2025-07-18 |  |  |  | 4 | 448084 | 425975.74 | 251311.27 | 51889.2 | 379772.1 | 30200.94 | 221110.33 | 631083.37 | 682972.57 | 2024-11-30 | 2025-04-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/632/746309-DR4339PR-DSOW-%20Group%2030-%20DAR%20-%20BAYAMON%20%209203%20-%20FY24%20%20Rev1%20-%20signed.pdf?web=1 | QC Review Complete: 4/01/2024 | 2025-07-23 13:47 | 2024-03-18 14:58 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  |  |  | 0.67499 | 2 |  | qwer37 | 746309 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 99 |  | DAR - BAYAMON 1803, 1806 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 14:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer38 | FAASt number pending 99 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 100 |  | DAR - BAYAMON 1716, 1734 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 14:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer39 | FAASt number pending 100 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 101 |  | DAR - BAYAMON 1710,1711,1713, 1714 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:00 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer40 | FAASt number pending 101 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 102 |  | DAR - BAYAMON 1706, 1708 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:11 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer41 | FAASt number pending 102 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 103 |  | DAR - BAYAMON 1909 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:11 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer42 | FAASt number pending 103 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 104 |  | DAR - ARECIBO 8005, 8101, 8103 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:12 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer43 | FAASt number pending 104 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 105 |  | DAR - ARECIBO 8202 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:12 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer44 | FAASt number pending 105 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 106 |  | DAR - ARECIBO 8701, 9001 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer45 | FAASt number pending 106 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 107 |  | DAR - PONCE 4003, 4101 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer46 | FAASt number pending 107 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 108 |  | DAR - PONCE 4201, 4301, 4401 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:14 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer47 | FAASt number pending 108 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 109 |  | DAR - PONCE 4601 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:15 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer48 | FAASt number pending 109 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 110 |  | DAR - ARECIBO 8801 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:15 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months | [6 empty] | qwer49 | FAASt number pending 110 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 111 |  | DAR - SAN JUAN 1336 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:16 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer50 | FAASt number pending 111 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 112 |  | DAR - SAN JUAN 1424, 1619, 1620, 2001, 2005, 2006 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer51 | FAASt number pending 112 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 113 |  | DAR - SAN JUAN 2201, 2302, 2305, 2306 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:18 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer52 | FAASt number pending 113 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 114 |  | DAR – ARECIBO 8010, 8015, 8101 – FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:18 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer53 | FAASt number pending 114 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 115 |  | DAR – ARECIBO 8104, 8202, 8203, 8301 – FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:19 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer54 | FAASt number pending 115 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 116 |  | DAR - ARECIBO 7403, 8302, 8501, 8504 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer55 | FAASt number pending 116 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 117 |  | DAR - ARECIBO 8602, 8801, 9001, 9002 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer56 | FAASt number pending 117 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 118 |  | DAR - BAYAMON 1529, 1701, 1704, 1707 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer57 | FAASt number pending 118 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 120 |  | DAR – SAN JUAN 1110, 1206, 1416 – FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer58 | FAASt number pending 120 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 121 |  | DAR - SAN JUAN 1343, 1437, 1525 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer59 | FAASt number pending 121 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 122 |  | DAR - BAYAMON 1711, 1717, 1718 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:25 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer60 | FAASt number pending 122 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 123 |  | DAR - BAYAMON 9202, 9203, 9207 - FY24 |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:26 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer61 | FAASt number pending 123 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 124 |  | DAR - PONCE 4401, 4602, 4603, - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:27 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer62 | FAASt number pending 124 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 125 |  | DAR - ARECIBO 9002, 9003, 9004, 9101 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:28 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer63 | FAASt number pending 125 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 126 |  | DAR - SAN JUAN 2403, 2404, 3801, 1118, 1646 – FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:28 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer64 | FAASt number pending 126560 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 126 |  | DAR - BAYAMON 9801, 1705 – FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:29 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer65 | FAASt number pending 126561 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 127 |  | DAR - PONCE 5303, 5401, 4101, 5901 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:30 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer66 | FAASt number pending 127 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 128 |  | DAR - CAGUAS 2604, 3006, 3010, 3405, 3501, 3202 – FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:30 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer67 | FAASt number pending 128 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 129 |  | DAR - BAYAMON 9501, 1529, 1706 – FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:31 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer68 | FAASt number pending 129 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 130 |  | DAR - BAYAMON 9502, 9503, 1711, 1901 – FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer69 | FAASt number pending 130 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 131 |  | DAR - SAN JUAN 1114, 1620 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer70 | FAASt number pending 131 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 132 |  | DAR - ARECIBO 7402, 7601 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:34 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer71 | FAASt number pending 132 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 133 |  | DAR - ARECIBO 8007, 8011 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:34 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer72 | FAASt number pending 133 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 134 |  | DAR - ARECIBO 9103 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:35 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer73 | FAASt number pending 134 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 135 |  | DAR - PONCE 4502 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer74 | FAASt number pending 135 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 136 |  | DAR - PONCE 5304, 5802 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer75 | FAASt number pending 136 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 137 |  | DAR - MAYAGUEZ 6001, 7104 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer76 | FAASt number pending 137 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 138 |  | DAR -MAYAGUEZ 6008 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer77 | FAASt number pending 138 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 139 |  | DAR -MAYAGUEZ 7502, 7802 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer78 | FAASt number pending 139 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 140 |  | DAR -CAGUAS 3009, 3101 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:14 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer79 | FAASt number pending 140 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 141 |  | DAR -CAGUAS 2601, 2604, 3016 – FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:14 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer80 | FAASt number pending 141 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 142 |  | DAR -CAGUAS 3402 - FY25 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:15 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer81 | FAASt number pending 142 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 143 |  | 38kV Reclosers TLine 4800 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:15 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer82 | FAASt number pending 143 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 144 |  | 38kV Reclosers TLine 1500 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:16 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer83 | FAASt number pending 144 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 145 |  | 38kV Reclosers TLine 3700 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:16 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer84 | FAASt number pending 145 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 146 |  | 38kV Reclosers TLine 1900 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:17 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer85 | FAASt number pending 146 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 147 |  | 38kV Reclosers TLine 2100 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:18 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer86 | FAASt number pending 147 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 148 |  | 38kV Reclosers TLine 7800 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:18 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer87 | FAASt number pending 148 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 149 |  | 38kV Reclosers TLine 800 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:18 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer88 | FAASt number pending 149 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 150 |  | 38kV Reclosers TLine 13400 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer89 | FAASt number pending 150 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 151 |  | 38kV Reclosers TLine 12600 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:19 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer90 | FAASt number pending 151 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 152 |  | 38kV Reclosers TLine 100 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer91 | FAASt number pending 152 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 153 |  | 38kV Reclosers TLine 8100 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer92 | FAASt number pending 153 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 154 |  | 38kV Reclosers TLine 1600 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer93 | FAASt number pending 154 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 155 |  | 38kV Reclosers TLine 2000 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer94 | FAASt number pending 155 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 156 |  | 38kV Reclosers TLine 2200 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer95 | FAASt number pending 156 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 157 |  | 38kV Reclosers TLine 3100 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:22 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer96 | FAASt number pending 157 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 158 |  | 38kV Reclosers TLine 3000 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:22 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer97 | FAASt number pending 158 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 159 |  | 38kV Reclosers TLine 3600 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer98 | FAASt number pending 159 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 160 |  | 38kV Reclosers TLine 6500 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer99 | FAASt number pending 160 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 161 |  | 38kV Reclosers TLine 5600 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer100 | FAASt number pending 161 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 162 |  | 38kV Reclosers TLine 8200 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer101 | FAASt number pending 162 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 163 |  | 38kV Reclosers TLine 3200 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-18 16:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer102 | FAASt number pending 163 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 164 |  | Distribution Pole and Conductor Repair – Mayaquez Group 3 – Phase 2 |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-19 12:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer103 | FAASt Number Pending 164 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738671-1 | 11819 | 4 x 25 MW BESS Interconnections Barceloneta TC |  |  | Grid Modernization |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-19 14:59 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez | [7 empty] | qwer104 | 738671-1 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738671-2 | 11819 | 4 x 25 MW BESS Interconnections Vega Baja TC |  |  | Grid Modernization |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-19 15:00 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez | [7 empty] | qwer105 | 738671-2 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738671-3 | 11819 | 4 x 25 MW BESS Interconnections Aguadilla TC |  |  | Grid Modernization |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-19 15:01 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez | [7 empty] | qwer106 | 738671-3 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 165 |  | Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC) |  |  | Grid Modernization |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-19 15:02 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer107 | FAASt number pending 165 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 166 |  | DAF Fuse Cutout Installation - Group A |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-19 17:38 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer108 | FAASt Number Pending 166 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 167 |  | DAR - PONCE 5011, 5013, 5016 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-19 17:39 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer109 | FAASt Number Pending 167 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
700 - Costa Sur to Yauco Plaza |  |  |  |  | Transmission |  |  | FALSE |  |  | FALSE |  |  | 2024-01-23 |  | 2024-04-18 | 2024-05-07 |  | 2024-05-18 | 2024-04-17 | 2024-03-22 | [10 empty] | 24998791 | [5 empty] | 0 | 24998791 | 24998791 | [10 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (18 - PLRC Approval Required) | 2025-07-18 18:31 | 2024-03-20 16:05 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer110 | 700 - Costa Sur to Yauco Plaza | Item | sites/Test4552/Lists/ISOW DSOW Tracker
41200 - Sabana Llana to Canóvanas |  |  |  |  | Transmission |  |  | FALSE |  |  | FALSE |  |  | 2024-01-23 | [6 empty] | 2024-03-22 | [10 empty] | 48460000 | [5 empty] | 0 | 48460000 | 48460000 | [10 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (18 - PLRC Approval Required)3/19/2024 LUMA Regulatory ISOW to PREB Notes - TBD for PREB Submittal Target DateOn Hold. Daniel Haughton is working with PM to update initial SOW. Once they complete that they will send it back to us for submittal. | 2025-07-18 18:31 | 2024-03-20 16:16 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer111 | 41200 - Sabana Llana to Canóvanas | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Sub Rebuild - Fajardo TC |  |  |  | PBUT08 - Substation Rebuilds | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-01-26 | [23 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Regulatory Notes on ISOW to PREB - PREB Submittal Target Date: TBD, Notes: need the ISOW | 2025-07-18 18:31 | 2024-03-20 17:00 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer112 | Sub Rebuild - Fajardo TC | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 168 |  | DAR - BAYAMON 1708, 1734, 1801, 1901 - FY24 |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-21 14:57 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer113 | FAASt Number Pending 168 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Dorado Pueblo 9202-04 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 3000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 9800000 | [5 empty] | 0 | 9800000 | 9800000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 12:41 | Jeremy Malone | Distribution Feeder Dorado Pueblo 8.32 kV 9202-04 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer114 | Dorado Pueblo 9202-04 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Hato Tejas TC 1713-05 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 12300000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 12300000 | [5 empty] | 0 | 12300000 | 12300000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 12:42 | Jeremy Malone | Distribution Feeder Hato Tejas 1713-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer115 | Hato Tejas TC 1713-05 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
El Abanico PDS 9605-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 20400000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 20400000 | [5 empty] | 0 | 20400000 | 20400000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 12:43 | Jeremy Malone | Distribution Feeder El Abanico PDS 9605-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer116 | El Abanico PDS 9605-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Humacao Pueblo 2601-01 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 11200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 11200000 | [5 empty] | 0 | 11200000 | 11200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 12:43 | Jeremy Malone | Distribution Feeder Humacao Pueblo 2601-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer117 | Humacao Pueblo 2601-01 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Cachete 13KV 1529-11 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 8100000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 8100000 | [5 empty] | 0 | 8100000 | 8100000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 12:49 | Jeremy Malone | Distribution Feeder Cachete 13 kV 1529-11 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer118 | Cachete 13KV 1529-11 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Fort Allen 13KV 5803-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 18000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 18000000 | [5 empty] | 0 | 18000000 | 18000000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:17 | Jeremy Malone | Distribution Feeder Fort Allen 5803-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer119 | Fort Allen 13KV 5803-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Berwind 13KV 1336-07 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 11200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 11200000 | [5 empty] | 0 | 11200000 | 11200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:23 | Jeremy Malone | Distribution Feeder Berwin 13 kV 1336-07 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer120 | Berwind 13KV 1336-07 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Encantada 1206-03 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 12700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 12700000 | [5 empty] | 0 | 12700000 | 12700000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:25 | Jeremy Malone | Distribution Feeder Encantada 1206-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer121 | Encantada 1206-03 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Buen Pastor 1908-03 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 20700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 20700000 | [5 empty] | 0 | 20700000 | 20700000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:26 | Jeremy Malone | Distribution Feeder Buen Pastor 1908-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer122 | Buen Pastor 1908-03618 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning Bayamón F |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 119100000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 119100000 | [5 empty] | 0 | 119100000 | 119100000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:43 | Jeremy Malone | Area Planning - Bayamón F | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer123 | Area Planning Bayamón F | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning Bayamón G |  |  |  |  | Distribution | [5 empty] | FALSE |  |  | 2024-02-01 | 42400000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 42200000 | [5 empty] | 0 | 42200000 | 42200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:43 | Jeremy Malone | Area Planning - Bayamón G | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer124 | Area Planning Bayamón G | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning San Juan B |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 58200000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 58200000 | [5 empty] | 0 | 58200000 | 58200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:54 | Jeremy Malone | Area Planning - San Juan B | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer125 | Area Planning San Juan B | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning San Juan C |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 150700000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 1507000 | [5 empty] | 0 | 1507000 | 1507000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:55 | Jeremy Malone | Area Planning - San Juan C | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer126 | Area Planning San Juan C | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning San Juan D |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 71800000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 71800000 | [5 empty] | 0 | 71800000 | 71800000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:55 | Jeremy Malone | Area Planning - San Juan D | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer127 | Area Planning San Juan D | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning San Juan F |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 30300000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 30300000 | [5 empty] | 0 | 30300000 | 30300000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:55 | Jeremy Malone | Area Planning - San Juan F | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer128 | Area Planning San Juan F | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning San Juan G |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 39500000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 39500000 | [5 empty] | 0 | 39500000 | 39500000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:56 | Jeremy Malone | Area Planning - San Juan G | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer129 | Area Planning San Juan G | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning San Juan K |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 45400000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 45400000 | [5 empty] | 0 | 45400000 | 45400000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:56 | Jeremy Malone | Area Planning - San Juan K | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer130 | Area Planning San Juan K | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning Bayamón A |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 89400000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 89400000 | [5 empty] | 0 | 89400000 | 89400000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:56 | Jeremy Malone | Area Planning ‐ Bayamón A | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer131 | Area Planning Bayamón A | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning Bayamón C |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 | 64800000 | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 64800000 | [5 empty] | 0 | 64800000 | 64800000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-03-22 13:57 | Jeremy Malone | Area Planning ‐ Bayamón C | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer132 | Area Planning Bayamón C | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Substation Component Replacement Program |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-01-27 |  | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 330300000 | [5 empty] | 0 | 330300000 | 330300000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/782/DR4339PR-FEMA%20ISOW%20Substation%20Component%20Replacement%20Program%20Rev%200%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 3/26/2024 but has since been removed | 2025-07-18 18:31 | 2024-03-26 11:49 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer133 | Substation Component Replacement Program | Item | sites/Test4552/Lists/ISOW DSOW Tracker
746108 | 11779 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | 14F018770000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 2024-03-27 | 03/27/2024 | 2024-03-27 | 2024-04-12 |  |  |  | 3 | 34002129 | 26445766.74 | 3331645 | 4224718 | 26445767 | 458919 | 2872726 | 29777412 | 34002130 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/783/746108-DR4339PR-Detailed%20SOW%20Streetlight%20San%20Juan%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:31 | 2024-03-28 10:08 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88812 | 1 |  | qwer134 | 746108 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
746111 | 11778 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | 14F018590000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 2024-03-27 | 03/27/2024 | 2024-03-27 | 2024-04-12 |  |  |  | 3 | 13628925 | 10160311.88 | 1317294 | 2151320 | 10160312 | 230183 | 1087111 | 11477606 | 13628926 | 2024-06-30 | 2024-11-30 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/784/746111-DR4339PR-Detailed%20SOW%20Streetlight%20Caguas%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 2025-07-18 18:31 | 2024-03-28 10:12 | Marlina Crespo | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 0.88523 | 1 |  | qwer135 | 746111 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
TBD UG Feeder Rebuilds - Phase 1 |  |  |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | TRUE |  |  | 2024-01-30 |  | 2024-02-27 | 2024-03-13 |  | 2024-03-28 |  |  |  |  | 2024-03-27 | [7 empty] | 249921003 | [5 empty] | 0 | 249921003 | 249921003 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/785/DR-4339%20ISOW-UG%20Feeder%20Rebuilds%20-%20Phase%201_Rev.0%20-%20signed.pdf?web=1 | 02MAY2025 Taking the funds off the tracker. This is an island wide project and we already have 2 projects under this project umbrella - MC | 2025-07-18 18:31 | 2024-03-28 14:20 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer136 | TBD UG Feeder Rebuilds - Phase 1 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Maunabo TC Rev 2 |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-01-26 |  | 2024-03-06 | 2024-03-27 |  | 2024-04-05 | [12 empty] | 96115838 | [5 empty] | 0 | 96115838 | 96115838 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/786/DR4339PR%20-%20FEMA%20ISOW%20Maunabo%20TC%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA4/1/2024 but has since been removed | 2025-07-18 18:31 | 2024-04-01 09:36 | Marlina Crespo | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer137 | Maunabo TC Rev 2 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Mayaguez TC Rev 2 |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 14400000 | 2024-03-06 | 2024-03-27 |  | 2024-04-05 | [12 empty] | 14464362 | [5 empty] | 0 | 14464362 | 14464362 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/787/DR4339PR-FEMA%20ISOW%20Mayaguez%20TC%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA4/1/2024 but has since been removed | 2025-07-18 18:31 | 2024-04-01 09:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer138 | Mayaguez TC Rev 2 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
748180 | 107961 | FAASt [Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC)] (Telecommunication) | 14F020010000 | PBUT07 - Substation Reliability | Grid Modernization |  | Restoration | FALSE |  |  | FALSE |  |  | 2024-01-30 | 49750000 | 2024-03-06 | 2024-03-27 |  | 2024-04-05 |  |  |  |  | 2024-04-01 | 05/09/2024 | 2024-10-01 | 2025-03-25 |  |  |  |  | 49755331 | 49755331 | 52804979.05 | 0 | 0 | 5250645.64 | 47554333.41 | 52804979.05 | 52804979.05 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/788/DR4339PR-FEMA%20ISOW%20PAC%20WAMPAC%20Program%20Rev%200%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-04-01 09:37 | Marlina Crespo | Deployment of Advanced Sensors, Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC) | Rey Roldan Rodríguez | 0 Months |  |  |  | 0.94225 | 1 |  | qwer139 | 748180 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Adjuntas Pueblo 8.32kV 8202-01 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 4500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 4500000 | [5 empty] | 0 | 4500000 | 4500000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:01 | Jeremy Malone | Distribution Feeder Adjuntas Pueblo 8.32 kV 8202-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer140 | Adjuntas Pueblo 8.32kV 8202-01 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Aguada 7205-01 4.16kV |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 13500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 13500000 | [5 empty] | 0 | 13500000 | 13500000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:01 | Jeremy Malone | Distribution Feeder Aguada 7205-01 4.16 kV | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer141 | Aguada 7205-01 4.16kV | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Aguas Buenas 3701-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 5200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 5200000 | [5 empty] | 0 | 5200000 | 5200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:02 | Jeremy Malone | Distribution Feeder Aguas Buenas 3701-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer142 | Aguas Buenas 3701-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Añasco 6101-04 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 12600000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 12600000 | [5 empty] | 0 | 12600000 | 12600000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:02 | Jeremy Malone | Distribution Feeder Añasco 6101-04 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer143 | Añasco 6101-04 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Añasco 6101-05 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 10500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 10500000 | [5 empty] | 0 | 10500000 | 10500000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:02 | Jeremy Malone | Distribution Feeder Añasco 6101-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer144 | Añasco 6101-05 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Buen Pastor 1908-03 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 20700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 20700000 | [5 empty] | 0 | 20700000 | 20700000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:04 | Jeremy Malone | Distribution Feeder Buen Pastor 1908-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer145 | Buen Pastor 1908-03641 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Cana (Interamericana) 1719-15 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 7500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 7500000 | [5 empty] | 0 | 7500000 | 7500000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:04 | Jeremy Malone | Distribution Feeder Cana (Interamericana) 1719-15 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer146 | Cana (Interamericana) 1719-15 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Cana (Interamericana) 1719-18 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 11200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 11200000 | [5 empty] | 0 | 11200000 | 11200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:04 | Jeremy Malone | Distribution Feeder Cana (Interamericana) 1719-18 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer147 | Cana (Interamericana) 1719-18 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Candelero 2604-01 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 12700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 12700000 | [5 empty] | 0 | 12700000 | 12700000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:05 | Jeremy Malone | Distribution Feeder Candelero 2604-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer148 | Candelero 2604-01 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Coamo PDS 4603-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 12000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 12000000 | [5 empty] | 0 | 12000000 | 12000000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:08 | Jeremy Malone | Distribution Feeder Coamo PDS 4603-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer149 | Coamo PDS 4603-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Crea 1717-01 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 7500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 7500000 | [5 empty] | 0 | 7500000 | 7500000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:08 | Jeremy Malone | Distribution Feeders Crea 1717-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer150 | Crea 1717-01 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Cuatro Hermanos 6004-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 13900000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 13900000 | [5 empty] | 0 | 13900000 | 13900000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:08 | Jeremy Malone | Distribution Feeder Cuatro Hermanos 6004-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer151 | Cuatro Hermanos 6004-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Grana PDS 1907-05 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 3000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 3000000 | [5 empty] | 0 | 3000000 | 3000000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:09 | Jeremy Malone | Distribution Feeder Grana PDS 1907-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer152 | Grana PDS 1907-05 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Humacao TC 13 kV 2603-09 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 17600000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 17600000 | [5 empty] | 0 | 17600000 | 17600000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:12 | Jeremy Malone | Distribution Feeder Humacao TC 13 kV 2603-09 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer153 | Humacao TC 13 kV 2603-09 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Isabela Planta 3 7504-01 4.16kV |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 6900000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 6900000 | [5 empty] | 0 | 6900000 | 6900000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:12 | Jeremy Malone | Distribution Feeder Isabela Planta 3 7504-01 4.16 kV | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer154 | Isabela Planta 3 7504-01 4.16kV | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Juncos 3201-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 15000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 15000000 | [5 empty] | 0 | 15000000 | 15000000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:18 | Jeremy Malone | Distribution Feeder Juncos 3201-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer155 | Juncos 3201-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Llorens Torres 13 kV 1118-08 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 4200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 4200000 | [5 empty] | 0 | 4200000 | 4200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:18 | Jeremy Malone | Distribution Feeder Llorens Torres 13 kV 1118-08 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer156 | Llorens Torres 13 kV 1118-08 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Llorens Torres 13 kV 1118-09 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 4500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 4500000 | [5 empty] | 0 | 4500000 | 4500000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:19 | Jeremy Malone | Distribution Feeder Llorens Torres 13 kV 1118-09 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer157 | Llorens Torres 13 kV 1118-09 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Monacillos 13 kV 1346-03 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 8200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 8200000 | [5 empty] | 0 | 8200000 | 8200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:19 | Jeremy Malone | Distribution Feeder Monacillos 13 kV 1346-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer158 | Monacillos 13 kV 1346-03 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Monterrey PDS 13 kV 9503-06 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 11700000 | [5 empty] | 0 | 11700000 | 11700000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:27 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer159 | Monterrey PDS 13 kV 9503-06 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Peñuelas Pueblo 5401-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 8300000 | [5 empty] | 0 | 8300000 | 8300000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:28 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer160 | Peñuelas Pueblo 5401-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Rio Bayamon 1709-05 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 11100000 | [5 empty] | 0 | 11100000 | 11100000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:28 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer161 | Rio Bayamon 1709-05 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Rio Bayamon 1709-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 8200000 | [5 empty] | 0 | 8200000 | 8200000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:30 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer162 | Rio Bayamon 1709-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
San Jose 8104-02 4.16 kV |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 12000000 | [5 empty] | 0 | 12000000 | 12000000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:30 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer163 | San Jose 8104-02 4.16 kV | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Unibon 9.32 kV 9501-01 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 11300000 | [5 empty] | 0 | 11300000 | 11300000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:30 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer164 | Unibon 9.32 kV 9501-01 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Vega Baja TC 13 kV 9004-08 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 22800000 | [5 empty] | 0 | 22800000 | 22800000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:35 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer165 | Vega Baja TC 13 kV 9004-08 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Vega Baja TC 13 kV 9004-10 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 21400000 | [5 empty] | 0 | 21400000 | 21400000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:35 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer166 | Vega Baja TC 13 kV 9004-10 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Sabana Grande 4.16 kV 6501-04 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 9700000 | [5 empty] | 0 | 9700000 | 9700000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:36 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer167 | Sabana Grande 4.16 kV 6501-04 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Yabucoa Pueblo 2901-04 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 12770000 | [5 empty] | 0 | 12770000 | 12770000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-03 13:53 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer168 | Yabucoa Pueblo 2901-04 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Buildings Island-Wide Program |  |  |  |  | Building |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 97477246.69 | 2024-07-19 | 2024-08-12 |  | 2024-08-18 | 2024-05-22 | 2024-04-26 | [10 empty] | 97477246.69 | [5 empty] | 0 | 97477246.69 | 97477246.69 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-05 16:23 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer169 | Buildings Island-Wide Program | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Cerro las Mesas 6010-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 15000000 | [5 empty] | 0 | 15000000 | 15000000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-05 17:06 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer170 | Cerro las Mesas 6010-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Bayamon TC 4kV 1714-02 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 3750000 | [5 empty] | 0 | 3750000 | 3750000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-05 17:06 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer171 | Bayamon TC 4kV 1714-02 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Villa del Carmen 5016-01 |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | 2024-04-05 | 2024-03-28 | [10 empty] | 11100000 | [5 empty] | 0 | 11100000 | 11100000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-05 17:06 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer172 | Villa del Carmen 5016-01 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Area Planning San Juan A |  |  |  |  | Distribution |  |  | FALSE |  |  | FALSE |  |  | 2024-02-01 |  | 2024-02-27 | 2024-03-13 |  | 2024-03-28 | [12 empty] | 120100000 | [5 empty] | 0 | 120100000 | 120100000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-05 17:11 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer173 | Area Planning San Juan A | Item | sites/Test4552/Lists/ISOW DSOW Tracker
746545 | 11824 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 14F000010000 | PBUT24 - Ctrl Ctr Const & Refurb | Building |  | Improved | FALSE |  | Current | FALSE |  |  | 2024-04-02 | 146000000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-04-04 | 04/04/2024 | 2024-04-19 | 2024-05-13 | 2025-01-13 | 2024-12-30 |  | 2 | 146000000 | 115638378 | 0 | 15530896 | 115638378 | 0 | 0 | 115638378 | 131169274 | 2024-10-31 | 2025-01-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/830/DR4339PR-FASST-iSOW%20Primary%20Control%20Center%20%20(CC)%20-%2004.01.2024%20-%20signed.pdf?web=1 | 4/17/2024: QC Review Complete | 2025-07-18 18:31 | 2024-04-08 10:00 | Marlina Crespo | IT OT Telecom Systems & Network | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer174 | 746545 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Morovis 8801 Rev 2 |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-01-23 | 5840000 | 2024-03-06 | 2024-03-27 |  | 2024-04-05 | [12 empty] | 5844709 | [5 empty] | 0 | 5844709 | 5844709 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/831/DR4339PR-FEMA%20ISOW%20Morovis%208801%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 4/8/2024 but has since been removed | 2025-07-18 18:31 | 2024-04-08 10:43 | Marlina Crespo | Pampanos Relocation | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer175 | Morovis 8801 Rev 2 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
746660 | 107960 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 14F019740000, 14F019710000, 14F019730000, 14F019670000, 14F019700000, 14F019750000, 14F019690000, 14F019660000, 14F019720000, 14F019680000, 14F019660000, 14F019760000, 14F019650000, 14F019810000, 14F019790000, 14F019780000, 14F019800000, 14F019870000 | PBUT07 - Substation Reliability | Substation |  | Restoration | FALSE |  | Past | FALSE |  |  |  | 70500000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 |  |  |  |  | 2024-04-08 | 04/08/2024 | 2024-04-11 | 2025-05-06 |  |  |  | 1 | 70500000 | 70500000 | 1640072.56 | 1712811.61 | 13405694.32 | 186981.52 | 1453091.04 | 15045766.88 | 16758578.49 | 2025-04-30 | 2025-10-31 | [8 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/832/746660-DR4339PR-%20DSOW%20Minor%20PAC%20Replacement%20%20Group%201%2004112024.pdf?web=1 |  | 2025-07-18 18:31 | 2024-04-09 08:54 | Marlina Crespo | Minor PAC Replacement and Hazard Mitigation | Rey Roldan Rodríguez |  |  |  |  | 4.6857 | 1 |  | qwer176 | 746660 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Transmission Program ISOW |  |  |  |  | Transmission |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 |  | 2024-06-21 | 2024-07-02 |  | 2024-07-21 |  | 2024-03-22 | [10 empty] | 501947756 | [5 empty] | 0 | 501947756 | 501947756 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-19 10:45 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer177 | Transmission Program ISOW | Item | sites/Test4552/Lists/ISOW DSOW Tracker
751656 | 107983 | FAASt [Culebra Microgrid] (Transmission) | 14F021690000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2023-03-28 | 07/18/2024 | 2024-07-19 | [5 empty] | 125117462.87 | 40846080 | 38954081 |  |  | 1696346 | 37257735 | 38954081 | 38954081 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/836/4339-0280_Phase%201%20Approval_VC%20Microgrids_20230328%20(002).pdf?web=1 |  | 2025-07-18 18:31 | 2024-04-25 16:03 | Marlina Crespo | Vieques and Culebra Microgrid | Rey Roldan Rodríguez |  |  |  |  | 1.0486 | 1 |  | qwer178 | 751656 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
TBD Remaining Vegetation Funds |  |  |  |  | Vegetation |  |  | FALSE |  |  | FALSE | [12 empty] | 2023-05-10 | [7 empty] | -63127338.59 | [5 empty] | 0 | -63127338.59 | -63127338.59 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-25 16:12 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer179 | TBD Remaining Vegetation Funds | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Sub Rebuild - Santurce Planta |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE | [20 empty] | 40362715 | [5 empty] | 0 | 40362715 | 40362715 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-26 11:03 | Jeremy Malone | Santurce Planta (Sect) 1116 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer180 | Sub Rebuild - Santurce Planta | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Sub - Rebuild Canas TC |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE | [20 empty] | 71817966 | [5 empty] | 0 | 71817966 | 71817966 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-26 11:03 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer181 | Sub - Rebuild Canas TC | Item | sites/Test4552/Lists/ISOW DSOW Tracker
T/D Asset Model Verification |  |  |  |  | Transmission |  |  | FALSE |  |  | FALSE | [20 empty] | 53716202 | [5 empty] | 0 | 53716202 | 53716202 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-26 11:03 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer182 | T/D Asset Model Verification | Item | sites/Test4552/Lists/ISOW DSOW Tracker
36600 115kV San Sabastian - Dos Bocas (Batch 5) |  |  |  |  | Transmission |  |  | FALSE |  |  | FALSE | [20 empty] | 107109345 | [5 empty] | 0 | 107109345 | 107109345 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-04-26 11:04 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer183 | 36600 115kV San Sabastian - Dos Bocas (Batch 5) | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Asset Management System Implementation |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-05-25 | 9737556 | 2024-06-28 | 2024-07-24 |  | 2024-07-28 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-05-30 16:36 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer184 | Asset Management System Implementation | Item | sites/Test4552/Lists/ISOW DSOW Tracker
TBD Venezuela Substation Transformer Replacement |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-01-31 | 3150000 | 2024-04-04 | 2024-04-22 |  | 2024-05-04 |  |  |  |  | 2024-05-31 | [7 empty] | 3156254 | [5 empty] | 0 | 3156254 | 3156254 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/844/DR4339PR-FEMA%20ISOW%20Venezuela%20Substation%20Transformer%20Replacement%20Rev.3%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-06-03 13:35 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer185 | TBD Venezuela Substation Transformer Replacement | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 171 |  | FAASt - Morovis (Substation) |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:27 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer186 | FAASt number pending 171 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 172 |  | FAASt - Maunabo TC (Substation) |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:27 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer187 | FAASt number pending 172 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 173 |  | FAASt - Mayagüez (Substation) |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:28 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer188 | FAASt number pending 173 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 176 |  | Substation Component Replacements |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:29 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer189 | FAASt number pending 176 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 178 |  | FAASt [T-Pole Program Line 37400 Dorado TC - Vega Baja TC] (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:31 | Marlina Crespo | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez | [7 empty] | qwer190 | FAASt number pending 178 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 179 |  | FAASt [T-Pole Program Line 37400 Barceloneta TC - Cambalache TC] (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:32 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer191 | FAASt number pending 179 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 180 |  | FAASt [T-Pole Program Line 16500 Fajardo TC - Dos Marinas] (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:33 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer192 | FAASt number pending 180 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 181 |  | FAASt [T-Pole Program Line 800 Comsat Sect - Cidra Sect] (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-12 16:34 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months | [6 empty] | qwer193 | FAASt number pending 181 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 184 |  | Group 15 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:20 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months | [6 empty] | qwer194 | FAASt number pending 184 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 185 |  | Group 19 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer195 | FAASt number pending 185 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 186 |  | Group 20 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:22 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer196 | FAASt number pending 186 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 187 |  | Group 21 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer197 | FAASt number pending 187 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 188 |  | Group 22 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer198 | FAASt number pending 188 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 189 |  | Group 24 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer199 | FAASt number pending 189 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 190 |  | Group 26 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:25 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer200 | FAASt number pending 190 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 191 |  | Group 27 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:27 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer201 | FAASt number pending 191 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 192 |  | Group 31 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:27 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer202 | FAASt number pending 192 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 193 |  | Group 32 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:28 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer203 | FAASt number pending 193 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 194 |  | Group 33 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:30 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer204 | FAASt number pending 194 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 195 |  | Group 34 - DAUT |  |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:30 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer205 | FAASt number pending 195 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 196 |  | Group 35 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:31 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer206 | FAASt number pending 196 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 197 |  | FAASt [Feeders - San Juan Short Term Group 3] (Distribution) - 1620-02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:32 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer207 | FAASt number pending 197 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 198 |  | FAASt [Feeders - Carolina Short Term Group 3] (Distribution) - 2402-02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:33 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer208 | FAASt number pending 198 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 199 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1303-01 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:34 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer209 | FAASt number pending 199 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 200 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1204-05 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer210 | FAASt number pending 200 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 201 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1204-04 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:37 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer211 | FAASt number pending 201 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 202 |  | FAASt [Feeders - Mayagüez Short Term Group 4] (Distribution )- 7805-11 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:38 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer212 | FAASt number pending 202 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 203 |  | FAASt [Feeders - Carolina Short Term Group 3] (Distribution) - 2402-02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:38 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer213 | FAASt number pending 203 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 204 |  | FAASt [Feeders - Bayamón Short Term Group 1] (Distribution)-1806- 02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:39 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer214 | FAASt number pending 204 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 205 |  | FAASt [Feeders - Mayagüez Short Term Group 3] (Distribution)-6601- 03 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:40 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer215 | FAASt number pending 205 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 206 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1303-05 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:40 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer216 | FAASt number pending 206 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 207 |  | FAASt [Feeders - Mayagüez Short Term Group 2] (Distribution )- 6305-03 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 12:41 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer217 | FAASt number pending 207 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 208 |  | FAASt [Feeders - Bayamón Short Term Group 1] (Distribution)-1720- 07 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:43 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez | [7 empty] | qwer218 | FAASt number pending 208 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 209 |  | FAASt [Feeders - Bayamón Short Term Group 1] (Distribution)-1716- 03 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:43 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez | [7 empty] | qwer219 | FAASt number pending 209 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 210 |  | FAASt [Feeders - Bayamón Short Term Group 3] (Distribution)-9501- 02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer220 | FAASt number pending 210 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 211 |  | Feeder 1115-02, 1115-03, 1115-04, 1117-07, 1117-08 - Santurce UG Rebuilt |  |  | Distribution – Underground |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer221 | FAASt number pending 211 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 212 |  | Feeder 1424-07, 1424-08 - Hato Rey UG Rebuilt |  |  | Distribution – Underground |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer222 | FAASt number pending 212 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 214 |  | FAASt [Pole and Conductor Repair - Caguas Group 3 - Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer223 | FAASt number pending 214 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 215 |  | FAASt [Pole and Conductor Repair - Mayagüez Group 4 - Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 12:48 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer224 | FAASt number pending 215 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
738671-4 | 11819 | 4 x 25 MW BESS Interconnections Monacillos TC |  |  | Grid Modernization |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-06-13 13:06 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez | [7 empty] | qwer225 | 738671-4 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 216 |  | Vieques & Culebra Microgrid |  |  | Grid Modernization |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 2025-07-18 18:31 | 2024-06-13 13:09 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer226 | FAASt number pending 216 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750068 | 107969 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 15F019400000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-06-18 | 6/18/2024 | 2024-11-21 | 2024-11-21 | 2025-08-19 | 2025-06-03 | Field EHP: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/19/2025. |  | 14252476.97 | 7000000 | 98723529.73 |  |  | 858465.45 | 97865064.28 | 98723529.73 | 98723529.73 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/909/Region%205%20Mayaguez%20Group%20A%20Low%20Density%20-%20PW%20750068%20DSOW%2011_4_2024.pdf?web=1 |  | 2025-07-25 15:27 | 2024-06-20 09:32 | Marlina Crespo | Island-Wide Vegetation Clearing | Maria Mujica Gonzalez |  |  |  |  | 0.070905 | 5 |  | qwer227 | 750068 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750067 | 107968 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 15F019550000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-06-18 | 06/18/2024 | 2024-11-21 | 2024-11-21 | 2025-08-19 | 2025-06-03 | Field EHP: ESA and CBRA Consultation letter submitted to USFWS on 06/05/2025. Waiting for response. ECD 08/19/2025 |  | 18122150.56 | 9000000 | 107170415.13 |  |  | 931916.64 | 106238498.49 | 107170415.13 | 107170415.13 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/910/Region%202%20Arecibo%20Group%20A%20Low%20Density%20-%20PW%20750067%20DSOW%2011_4_2024.pdf?web=1 | 10/2/2024 FEMA comment via GP: 10/01/2024 01:08 PM AST, GARCIA DIAZ, CHRISTIAN D. Commented: "10/1/2024 - LUMA sent the documents on 9/20/2024. FEMA performed a pre-review and email with feedback was sent to LUMA on 10/1/2024 for their action to remove duplicity found between Distribution and Transmission. Deadline stablished is 10/3/2024 for LUMA submit documents corrected."10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language | 2025-07-25 15:17 | 2024-06-20 09:39 | Marlina Crespo | Island-Wide Vegetation Clearing | Maria Mujica Gonzalez |  |  |  |  | 0.083978 | 5 |  | qwer228 | 750067 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750066 | 107967 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 15F019450000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-06-18 | 06/18/2024 | 2024-11-21 |  | 2025-08-12 | 2025-06-30 | Field EHP - Environmental: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/12/2025 |  | 33799537.58 | 16000000 | 3142832.19 |  |  | 2059216.24 | 1083615.95 | 3142832.19 | 3142832.19 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/911/Region%204%20Caguas%20Group%20A%20Low%20Density%20-%20PW%20750066%20DSOW%2011_4_2024.pdf?web=1 | 10/2/2024 FEMA comment via GP: 10/01/2024 01:04 PM AST, GARCIA DIAZ, CHRISTIAN D. Commented: "10/1/2024 - LUMA sent the documents on 9/20/2024. FEMA performed a pre-review and email with feedback was sent to LUMA on 10/1/2024 for their action to remove duplicity found between Distribution and Transmission. Deadline stablished is 10/3/2024 for LUMA submit documents corrected." 10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language | 2025-07-25 15:09 | 2024-06-20 09:40 | Marlina Crespo | Island-Wide Vegetation Clearing | Maria Mujica Gonzalez |  |  |  |  | 5.0909 | 1 |  | qwer229 | 750066 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750065 | 107966 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 15F019500000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-06-18 | 06/18/2024 | 2024-11-21 | 2024-11-21 | 2025-07-28 | 2025-06-02 | Field EHP: Previous EHP Status applies. ECD stays the same (7/28/2025). |  | 29267077.73 | 15000000 | 132424167.91 |  |  | 1151514.49 | 131272653.42 | 132424167.91 | 132424167.91 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/912/Region%203%20Bayamon%20Group%20A%20Low%20Density%20-%20PW%20750065%20DSOW%2011_5_2024.pdf?web=1 | 10/2/2024 FEMA comment via GP:10/01/2024 11:52 AM AST, GARCIA DIAZ, CHRISTIAN D. - Commented: "10/1/2024 - LUMA provided respond for email of duplicity. Still pending to confirm if LUMA used the rural ROW for their review." 10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language | 2025-07-25 15:16 | 2024-06-20 09:41 | Marlina Crespo | Island-Wide Vegetation Clearing | Maria Mujica Gonzalez |  |  |  |  | 0.11327 | 5 |  | qwer230 | 750065 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750063 | 107965 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 15F019350000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-06-18 | 06/18/2024 | 2024-11-21 | 2024-11-21 | 2025-08-08 | 2025-06-03 | Field EHP: (ESA) Consultation letter submitted to (USFWS) on 05/29/2025. Waiting for response. (Updated ECD to 08/08/2025). |  | 20024132.24 | 11000000 | 113327804.46 |  |  | 985459.15 | 112342345.31 | 113327804.46 | 113327804.46 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/913/Region%206%20Ponce%20Group%20A%20Low%20Density%20-%20PW%20750063%20DSOW%2011_4_2024.pdf?web=1 |  | 2025-07-25 15:15 | 2024-06-20 09:42 | Marlina Crespo | Island-Wide Vegetation Clearing | Maria Mujica Gonzalez |  |  |  |  | 0.097064 | 5 |  | qwer231 | 750063 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750150 | 107970 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | 14F020790000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 2024-06-20 | 06/20/2024 | 2024-06-20 | 2025-02-14 |  |  |  | 1 | 64660.36 | 58488 | 20679.11 | 16583.7 | 129733.64 | 2343.11 | 18336 | 150412.75 | 166996.45 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/914/136271-DR4339PR-Detailed%20SOW-T-Pole%20TL4800%20Santa%20Isabel%20TC%20%20Toro%20Negro%201%20HP%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-06-20 12:18 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 0.38885 | 4 |  | qwer232 | 750150 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750151 | 107971 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | 14F020640000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-06-20 | 06/20/2024 | 2024-06-20 | 2024-08-20 |  |  |  | 1 | 136702.29 | 123160.67 | 11027.93 | 16034.68 | 123160.67 | 1270.36 | 9757.57 | 134188.6 | 150223.28 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/915/136271-DR4339PR-Detailed%20SOW-%20T-Pole%20TL700%20Costa%20Sur%20SP%20-%20Yauco%202%20HP%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-06-20 12:19 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 0.91782 | 1 |  | qwer233 | 750151 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750168 | 107972 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | 14F020800000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 2024-06-20 | 06/20/2024 | 2024-06-20 | 2025-06-19 | [5 empty] | 375810.42 | 54814.29 | 55871.29 | 437063.41 | 6207.89 | 48606.4 | 491877.7 | 547748.99 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/916/136271-DR4339PR-Detailed%20SOW-T-Pole%20TL4800%20Santa%20Isabel%20TC%20-%20Aibonito%20TO%20Rev0%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-06-21 09:26 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 0.76403 | 2 |  | qwer234 | 750168 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750502 | 107977 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | 14F019620000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-06-27 | 06/27/2024 | 2025-06-06 |  | 2025-02-28 | 2025-02-25 |  |  | 3370000 | 3370000 | 52720520.35 | 0 | 0 | 3340630.47 | 49379889.88 | 52720520.35 | 52720520.35 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/918/750502%20-%20DR4339PR-%20FEMA%20DSOW%20for%2025%20MW%20BESS%20Installation%20and%20Integration%20-%20Aguadilla%20(Substation)%20signed.pdf?web=1 | Still pending SOW documentation | 2025-07-18 18:31 | 2024-06-28 11:04 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez |  |  |  |  | 0.063922 | 5 |  | qwer235 | 750502 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750503 | 107978 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | 14F019610000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-06-27 | 06/27/2024 | 2025-06-06 |  | 2024-12-10 | 2024-11-26 |  |  |  | 0 | 55503065.56 | 0 | 0 | 3187811.29 | 52315254.27 | 55503065.56 | 55503065.56 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/919/750503%20-%20DR4339PR%20-%20FEMA%20DSOW%20for%2025%20MW%20BESS%20Installation%20and%20Integration%20-%20San%20Juan%20(6.6.2025)%20signed.pdf?web=1 | Still pending SOW documentation | 2025-07-18 18:31 | 2024-06-28 11:05 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer236 | 750503 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750692 | 107979 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 14F018970000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-07-02 | 07/02/2024 | 2025-01-31 | 2025-04-24 | 2025-08-08 | 2025-06-27 | Field EHP: (ESA/CBRS) Consultation letter submitted to USFWS on 05/29/2025. Waiting for response. ECD 08/08/2025. |  | 8160000 | 8160000 | 0 | 1799743 | 15430664 | 0 | 0 | 15430664 | 17230407 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/922/ISOW%20-%20Pole%20and%20Conductor%20-%20%20Mayaguez%20Group%203%20-%20Phase%202.pdf |  | 2025-07-25 15:35 | 2024-07-02 11:23 | Marlina Crespo | Distribution Pole & Conductor Replacement | Maria Mujica Gonzalez | 0 Months |  |  |  | 0.52882 | 3 |  | qwer237 | 750692 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750729 | 107980 | FAASt [Transmission Line 3700 GOAB 3797 to Arroyo Substation 4101] (Transmission) | 14F015440000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | FALSE |  |  |  | 2080000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-02 | 07/02/2024 | [6 empty] | 2083232.55 | 2083232.55 |  |  |  |  | 0 | 2083232.55 | 2083232.55 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/923/750729-DR4339PR-Transmission%20Line%203700%20GOAB%203797%20to%20Arroyo%20Substation%204101.pdf?web=1 | 02JULY2025 Project is being administratively use as a placeholder since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project for the 33 DI's included in this project at the request of the Applicant and COR3 if a SOW submittal date is provided. | 2025-07-18 18:31 | 2024-07-03 10:35 | Marlina Crespo | Transmission Line 3700 GOAB 3797 to Arroyo Substation 4101 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer238 | 750729 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
750730 | 107981 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | 14F002400000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | FALSE |  |  |  | 36590000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  |  | 2024-07-02 | 07/02/2024 | [6 empty] | 36590000 | 36590000 |  |  |  |  | 0 | 36590000 | 36590000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/924/750730-DR4339PR-Line%20500%20Ponce%20TC%20to%20Costa%20Sur%20SP.pdf?web=1 |  | 2025-07-18 18:31 | 2024-07-03 10:39 | Marlina Crespo | Line 500 Ponce TC to Costa Sur SP | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer239 | 750730 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
751655 | 107982 | FAASt [Vieques Microgrid] (Transmission) | 14F021650000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | Restoration | FALSE |  |  | FALSE |  |  |  | 122250000 | 2024-02-02 | 2024-02-15 |  | 2024-03-03 |  |  |  |  | 2023-03-28 | 07/18/2024 | 2024-07-19 | [5 empty] | 125117462.87 | 81410371 | 105481956 |  |  | 2621438 | 102860518 | 105481956 | 105481956 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/927/4339-0280_Phase%201%20Approval_VC%20Microgrids_20230328%20(002)%20(1).pdf?web=1 |  | 2025-07-18 18:31 | 2024-07-19 10:12 | Marlina Crespo | Vieques and Culebra Microgrid | Rey Roldan Rodríguez |  |  |  |  | 0.77179 | 2 |  | qwer240 | 751655 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752039 | 107984 | FAASt [Transmission Line 10000 Sierra Linda TO to Magnolia TO] (Transmission) | 14F015550000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 7030000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 7032180.12 | 7032180.12 |  |  |  |  | 0 | 7032180.12 | 7032180.12 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/929/752039-DR4339PR-Transmission%20Line%2010000%20Sierra%20Linda%20TO%20to%20Magnolia%20TO.pdf | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:38 | Marlina Crespo | Transmission Line 10000 Sierra Linda TO to Magnolia TO | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer241 | 752039 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752041 | 107985 | FAASt [Transmission Line 1000 Venezuela Sect to Capuchinos Sect] (Transmission) | 14F015560000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 4060000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 4060000 | 4060000 |  |  |  |  | 0 | 4060000 | 4060000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/930/752041-DR4339PR-Transmission%20Line%201000%20Venezuela%20Sect%20to%20Capuchinos%20Sect.pdf | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:53 | Marlina Crespo | Transmission Line 1000 Venezuela Sect to Capuchinos Sect | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer242 | 752041 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752047 | 107986 | FAASt [Transmission Line 3300 Chardon Sect to Egozcue Sect] (Transmission) | 14F015460000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 6540000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 6540000 | 6540000 |  |  |  |  | 0 | 6540000 | 6540000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/931/752047-DR4339PR-Transmission%20Line%203300%20Chardon%20Sect%20to%20Egozcue%20Sect.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:55 | Marlina Crespo | Transmission Line 3300 Chardon Sect to Egozcue Sect | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer243 | 752047 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752048 | 107987 | FAASt [Transmission Line 3500 Las Lomas Sect to Monacillos TC] (Transmission) | 14F015450000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 8120000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 8120000 | 8120000 |  |  |  |  | 0 | 8120000 | 8120000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/932/752048-DR4339PR-Transmission%20Line%203500%20Las%20Lomas%20Sect%20to%20Monacillos%20TC.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 10:57 | Marlina Crespo | Transmission Line 3500 Las Lomas Sect to Monacillos TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer244 | 752048 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752049 | 107988 | FAASt [Transmission Line 5600 Hotel Rincon to Rincon Substation7301] (Transmission) | 14F015430000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 5200000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 5200000 | 5200000 |  |  |  |  | 0 | 5200000 | 5200000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/933/752049-DR4339PR-Transmission%20Line%205600%20Hotel%20Rincon%20to%20Rincon%20Substation7301.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 11:00 | Marlina Crespo | Transmission Line 5600 Hotel Rincon to Rincon Substation7301 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer245 | 752049 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752050 | 107989 | FAASt [Transmission Line 9300 Gautier Benitez Sect to ACB 9323] (Transmission) | 14F015410000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 20320000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 20320000 | 20320000 |  |  |  |  | 0 | 20320000 | 20320000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/934/752050-DR4339PR-Transmission%20Line%209300%20Gautier%20Benitez%20Sect%20to%20ACB%209323.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 11:02 | Marlina Crespo | Transmission Line 9300 Gautier Benitez Sect to ACB 9323 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer246 | 752050 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752051 | 107990 | FAASt [Transmission Line 9300 Juncos TC to ACB 9301] (Transmission) | 14F015400000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 16250000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 16250000 | 16250000 |  |  |  |  | 0 | 16250000 | 16250000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/935/752051-DR4339PR-Transmission%20Line%209300%20Juncos%20TC%20to%20ACB%209301.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 11:04 | Marlina Crespo | Transmission Line 9300 Juncos TC to ACB 9301 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer247 | 752051 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752052 | 107991 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | 14F015390000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | FALSE |  |  | 2024-01-12 | 32110000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 |  |  | 2025-03-11 | 2025-03-03 |  |  | 32110000 | 32110000 |  |  |  |  | 0 | 32110000 | 32110000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/936/752052-DR4339PRE-Transmission%20Line%209900%20TAP9905A%20to%20Rio%20Blanco%20HP.pdf?web=1 |  | 2025-07-18 18:31 | 2024-07-24 11:09 | Marlina Crespo | Transmission Line 9900 TAP9905A to Rio Blanco HP | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer248 | 752052 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752053 | 107992 | FAASt [Transmission Line 13400 Boqueron TO to Acacias TC] (Transmission) | 14F015540000 | PBUT33 - T Line Rebuild | Transmission |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | 2024-01-12 | 33330000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 |  |  |  |  | 2024-07-23 | 07/23/2024 | [6 empty] | 33330000 | 33330000 |  |  |  |  | 0 | 33330000 | 33330000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/937/752053-DR4339PR-Transmission%20Line%2013400%20Boqueron%20TO%20to%20Acacias%20TC.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-07-24 11:11 | Marlina Crespo | Transmission Line 13400 Boqueron TO to Acacias TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer249 | 752053 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Victoria TC |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-07-24 |  | 2024-07-31 | 2024-08-23 |  | 2024-08-30 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-07-26 09:46 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer250 | Victoria TC | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Arecibo Sectionalizer |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-07-20 |  | 2024-07-31 | 2024-08-23 |  | 2024-08-30 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-07-26 10:19 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer251 | Arecibo Sectionalizer | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752277 | 107995 | FAASt [Substation Ciales 8701] (Substation) | 14F016640000 |  | Substation |  | Restoration | FALSE |  |  | FALSE |  |  | 2024-05-24 | 5820000 | 2024-06-28 | 2024-07-24 |  | 2024-07-28 |  |  |  |  | 2024-07-26 | 07/29/2024 | 2024-11-26 | [5 empty] | 5825951 | 5825951 | 4177144.45 | 35108.3 | 324066.94 | 554759.8 | 3622384.65 | 4501211.39 | 4536319.69 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/944/DR4339PR%20-%20FEMA%20ISOW%20Ciales%208701%20Rev%207%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-07-29 12:55 | Marlina Crespo | Substation Ciales 8701 | Rey Roldan Rodríguez |  |  |  |  | 1.2943 | 1 |  | qwer252 | 752277 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752276 | 107994 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | 14F016660000 |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-05-24 | 39600000 | 2024-06-28 | 2024-07-24 |  | 2024-07-28 |  |  |  |  | 2024-07-26 | 07/29/2024 | [6 empty] | 39664220 | 39664220 |  |  |  |  | 0 | 39664220 | 39664220 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/945/DR4339PR-FEMA%20ISOW%20Monterrey%209502-9503%20Rev%205%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-07-29 12:56 | Marlina Crespo | Substation Monterey 9502 & 9503 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer253 | 752276 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752275 | 107993 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | 14F016650000 |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-05-24 | 9100000 | 2024-06-28 | 2024-07-24 |  | 2024-07-28 |  |  |  |  | 2024-07-26 | 07/29/2024 | [6 empty] | 9157533 | 9157533 |  |  |  |  | 0 | 9157533 | 9157533 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/946/DR4339PR-FEMA%20ISOW%20Unib%C3%B3n%209501%20Rev%207%20-%20signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-07-29 12:56 | Marlina Crespo | Substation Unibón 9501 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer254 | 752275 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752500 | 107996 | FAASt [Automation Program Group 1B-6 Feeders] (Distribution) | 14F001290000 |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [12 empty] | 2024-08-01 | 08/01/2024 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2025-07-18 18:31 | 2024-08-01 12:11 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer255 | 752500 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752502 | 107997 | FAASt [Automation Program Group 1C-7 Feeders] (Distribution) | 14F003520000, 14F003550000 |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [12 empty] | 2024-08-01 | 08/01/2024 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2025-07-18 18:31 | 2024-08-01 12:13 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer256 | 752502 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752503 | 107998 | FAASt [Automation Program Group 1D-7 Feeders] (Distribution) | 14F003340000, 14F003300000 |  | Grid Automation |  |  | FALSE |  | Past | FALSE | [12 empty] | 2024-08-01 | 08/01/2024 | [6 empty] | 1250000 | 1250000 |  |  |  |  | 0 | 1250000 | 1250000 | [10 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2025-07-18 18:31 | 2024-08-01 12:14 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer257 | 752503 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752540 | 107999 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 14F018980000 |  | Distribution – Pole Replacement |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-08-01 | 08/01/2024 | 2025-01-31 | 2025-04-24 | 2025-07-29 | 2025-07-18 | Field EHP - Environmental: In Review. Expected Completion Date (ECD) 07/30/2025. |  | 1250000 | 9107127 | 0 | 991212 | 8487643 | 0 | 0 | 8487643 | 9478855 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/950/752540-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%204%20-%20Phase%202%20Rev0%20.pdf?web=1 | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 2025-07-25 15:33 | 2024-08-01 12:15 | Marlina Crespo | Distribution Pole & Conductor Replacement | Maria Mujica Gonzalez |  |  |  |  | 1.073 | 1 |  | qwer258 | 752540 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752808 | 108000 | FAASt [Automation Program Group 19] (Distribution) | 10F000670000, 10F000660000, 10F000680000 |  | Grid Automation |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 2024-08-07 | 08/07/2024 | 2024-09-04 | 2024-10-04 | 2024-12-27 | 2024-12-09 |  |  | 1250000 | 1482000 | 0 | 348510.65 | 2753627.24 | 0 | 0 | 2753627.24 | 3102137.89 |  |  | 2025-02-06 |  | 2753627.24 | 2753627.24 |  |  |  |  | 2753627.24 | 2753627.24 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/952/1310158-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%2015%20(2).pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-08 09:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  | 348510.65 |  | 0.5382 | 3 |  | qwer259 | 752808 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752810 | 108001 | FAASt [Automation Program Group 20] (Distribution) | 10F001070000, 10F001080000, 10F001120000, 10F001090000 |  | Grid Automation |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 2024-08-07 | 08/07/2024 | 2024-09-04 |  | 2024-12-12 | 2024-12-05 |  |  |  | 1740000 | 0 | 333695.7 | 2623262.08 | 0 | 0 | 2623262.08 | 2956957.78 |  |  | 2025-02-06 |  | 2623262.08 | 2623262.08 |  |  |  |  | 2623262.08 | 2623262.08 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/953/752810-%20DR4339PR-%20DSOW%20Group%2020-%20DAUT.pdf?web=1 | Pending ISOW documentation 8/8/24 - MC | 2025-07-18 18:31 | 2024-08-08 09:20 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | 0 Months |  | 333695.7 |  | 0.6633 | 2 |  | qwer260 | 752810 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
752972 | 108002 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | 14F019630000 |  | Substation |  |  | FALSE |  |  | FALSE |  |  |  | 216580000 | [8 empty] | 2024-08-09 | 08/09/2024 | 2025-04-25 |  | 2025-03-24 | 2025-03-10 |  |  | 54200000 | 54200000 | 57640005.67 | 0 | 0 | 3414922.97 | 54225082.7 | 57640005.67 | 57640005.67 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/954/752972%20-%20FEMA%20DSOW%2025%20MW%20BESS%20Installation%20%26%20Integration%20-%20Manat%C3%AD%20sigend.pdf?web=1 | no ISOW was provided at the moment | 2025-07-18 18:31 | 2024-08-12 11:01 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Rey Roldan Rodríguez |  |  |  |  | 0.94032 | 1 |  | qwer261 | 752972 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 217 |  | FAASt [Feeders - Mayaguez Short Term Group 4] (Distribution ) - 7805-13 |  |  | Distribution |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:00 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer262 | FAASt Number Pending 217 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 218 |  | FAASt [Feeders - San Juan Short Term Group 3] (Distribution) - 1336-08 |  |  | Distribution |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:03 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer263 | FAASt Number Pending 218 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 219 |  | Line 100/200 - phase 1 |  |  | Transmission |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:05 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer264 | FAASt Number Pending 219 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 220 |  | Santa Isabel Transformer - Stabilization Project |  |  | Substation |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:07 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer265 | FAASt Number Pending 220 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 221 |  | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) - 1801-03 |  |  | Distribution |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:14 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer266 | FAASt Number Pending 221 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 223 |  | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) - 6802-04 |  |  | Distribution |  |  | FALSE |  | Past | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 2025-07-18 18:31 | 2024-08-13 09:29 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer267 | FAASt Number Pending 223 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753302 | 108004 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | 14F020240000, 14F020250000 |  | Telecommunications |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-08-15 | 08/15/2024 | [6 empty] | 8381000 | 8381000 |  |  |  |  | 0 | 8381000 | 8381000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/963/753302-DR4339PR-ISOW%20Telecom%20Infrastructure%20Group%20G%20signed%208-7-2024.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-16 16:47 | Marlina Crespo | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer268 | 753302 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753301 | 108003 | FAASt [Telecom Infrastructure Group H] (Telecommunication) | 14F020210000, 14F020220000, 14F020230000 |  | Telecommunications |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-08-15 | 08/15/2024 | [6 empty] | 7256000 | 7256000 |  |  |  |  | 0 | 7256000 | 7256000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/964/-DR4339PR-ISOW%20Telecom%20Infrastructure%20Group%20H%20Signed%208-7-2024.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-08-16 16:51 | Marlina Crespo | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer269 | 753301 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Venezuela Sectionalizer |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-08-12 |  | 2024-08-22 | 2024-08-28 |  | 2024-09-21 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-08-22 15:22 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer270 | Venezuela Sectionalizer | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Caparra Sectionalizer |  |  |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2024-08-12 |  | 2024-08-22 | 2024-08-28 |  | 2024-09-21 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-08-22 16:06 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer271 | Caparra Sectionalizer | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753788 | 108014 | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) | 14F020660000 |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-08-23 | 08/23/2024 | 2024-08-23 | [5 empty] | 840422.28 | 840422.28 | 0 | 217503.32 | 840422.28 | 0 | 0 | 840422.28 | 1057925.6 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/968/753788-DR4339PR-Detailed%20SOW-TPole%20TL1900%20Dos%20Bocas%20HP%20-%20San%20Sebastian%20TC.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-23 10:24 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer272 | 753788 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753787 | 108013 | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) | 14F020630000 |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-08-23 | 08/23/2024 | 2024-08-23 | [5 empty] | 553203.43 | 553203.43 | 0 | 70371.06 | 553203.43 | 0 | 0 | 553203.43 | 623574.49 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/969/753787-DR4339PR-Detailed%20SOW-T-Pole%20TL13700%20Mora%20TC-Isabela%20TO%20(1).pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-23 10:38 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer273 | 753787 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753786 | 108012 | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) | 14F020610000 |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-08-23 | 08/23/2024 | 2024-08-23 | [5 empty] | 599861.6 | 599861.6 | 0 | 79596.2 | 599861.6 | 0 | 0 | 599861.6 | 679457.8 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/970/753786-DR4339PR-Detailed%20SOW-TPole%205900%20San%20Juan%20SP%20-%20CrematorioTO.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-23 10:45 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer274 | 753786 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753785 | 108011 | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) | 14F020600000 |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-08-23 | 08/23/2024 | 2024-08-23 | [5 empty] | 298678.49 | 298678.49 | 0 | 38000.29 | 298678.49 | 0 | 0 | 298678.49 | 336678.78 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/971/753785-DR4339PR-Detailed%20SOW-TPole%20TL3300%20San%20Gerardo%20Sect%20-%20Venezuela%20Sect.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-23 10:49 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer275 | 753785 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753782 | 108010 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | 14F020580000 |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-08-23 | 08/23/2024 | 2024-08-23 | 2025-06-23 |  |  |  |  | 199697.38 | 199697.38 | 5236.77 | 16491.53 | 128962.93 | 592.79 | 4643.98 | 134199.7 | 150691.23 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/972/753782-DR4339PR-Detailed%20SOW-TPole%20TL3100%20Monacillos%20TC%20-%20Sabana%20Llana%20TC.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-23 10:51 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 1.4881 | 1 |  | qwer276 | 753782 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753781 | 108009 | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) | 14F020560000 |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-08-23 | 08/23/2024 | 2024-08-23 | 2025-07-09 |  |  |  |  | 1569945.94 | 1569945.94 | 38921.42 | 78345.34 | 612950.66 | 4410.86 | 34510.56 | 651872.08 | 730217.42 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/973/753781-DR4339PR-Detailed%20SOW-T-Pole%20TL800%20Comsat%20Sect%20-%20Cidra%20Sect.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-23 10:54 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  |  |  | 2.4084 | 1 |  | qwer277 | 753781 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
753777 | 108008 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | 14F002490000 |  | Transmission |  |  | FALSE |  |  | FALSE |  |  |  | 58610000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  |  | 2024-08-23 | 08/23/2024 |  |  | 2024-10-28 | 2024-10-15 |  |  | 58661000 | 0 |  |  |  |  | 0 | 58661000 | 58661000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-08-23 10:57 | Jason Fournier | Transmission Line Rebuild | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer278 | 753777 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
754351 | 108016 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | 14F020360000, 14F020350000 |  | Distribution – Underground |  | Improved | FALSE |  |  | FALSE | [12 empty] | 2024-08-26 | 08/26/2024 | 2024-10-22 | [5 empty] | 7066632.8 | 7066632.8 | 7066632.8 | 0 | 0 | 931013.36 | 6135619.44 | 7066632.8 | 7066632.8 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/975/75435-DR4339PR-Distribution%20Underground%20Circuit%20Feeders%20-%20San%20Juan%20Group%202_Detailed%20Scope%20of%20Work%20Rev.1v4%20-%20Signed.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-26 08:31 | Jason Fournier | Distribution Underground Circuit Rebuilds - Phase 1 | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | qwer279 | 754351 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
754350 | 108015 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 14F020320000, 14F020300000, 14F020310000, 14F020340000, 14F020330000 |  | Distribution – Underground |  | Improved | FALSE |  |  | FALSE |  |  |  | 250000000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 |  |  |  |  | 2024-08-26 | 08/26/2024 | 2024-10-16 | [5 empty] | 15123199.33 | 15123199.33 | 15123199.33 | 0 | 0 | 1419257.38 | 13703941.95 | 15123199.33 | 15123199.33 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/976/754350-DR4339PR-Underground%20%20Circuit%20Feeders-San%20Juan%20Group%201-Detailed%20Scope%20of%20Work.pdf?web=1 |  | 2025-07-18 18:31 | 2024-08-26 08:36 | Jason Fournier | Distribution Underground Circuit Rebuilds - Phase 1 | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | qwer280 | 754350 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
755211 | 108022 | FAASt [Automation Program Group 15] (Distribution) | 10F000650000 |  | Grid Automation |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-09-05 | 09/05/2024 | 2024-09-06 | 2024-10-04 | 2024-12-18 | 2024-12-10 |  |  | 324000 | 324000 | 0 | 81858.57 | 643560.85 | 0 | 0 | 643560.85 | 725419.42 |  |  | 2025-02-06 |  | 643560.85 | 643560.85 |  |  |  |  | 643560.85 | 643560.85 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/985/755211-%20DR4339PR%20-%20DSOW%20Group%2015%20DAUT.pdf?web=1 | 13MAY2025 Version 1 was created to address fund code correction from FC6E to FC06 for FAASt projects. This administrative amendment does not change the previously approved scope of work or costs, however, to be able to process the correction a version is being submitted for de-obligating the available balance in this PW, and a next version will be submitted to reconcile available funding in the correct code. Per the Financial Management Section, the amount to be de-obligated in this version is -$643,560.85 (100%) / -$579,204.77 (90%). 06SEPTEMBER2024 No ISOW provided in Grants Portal at this time - MC | 2025-07-18 18:31 | 2024-09-06 09:14 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  | 0 |  | 0.50345 | 3 |  | qwer281 | 755211 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
800361 | 108078 | FAASt [Automation Program Group 37] (Distribution) | 10F005220000, 10F005120000, 10F004760000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-12-31 | 12/31/2024 | 2025-04-28 |  | 2025-06-09 | 2025-05-30 |  |  | 2148000 | 2148000 |  | 297988.09 | 2069863.13 |  | 0 | 2069863.13 | 2367851.22 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/993/800361-DR4339PR-%20DSOW%20Group%2037-Rev.%201.pdf?web=1 |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.0377 | 1 |  | qwer282 | 800361 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
800369 | 108079 | FAASt [Automation Program Group 38] (Distribution) | 10F000970000, 10F000950000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-12-31 | 12/31/2024 | [6 empty] | 1335000 | 1335000 |  |  |  |  | 0 | 1335000 | 1335000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer283 | 800369 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
800394 | 108080 | FAASt [Automation Program Group 39] (Distribution) | 10F002180000, 10F002200000, 10F002190000, 10F001350000, 10F002170000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-12-31 | 12/31/2024 | [6 empty] | 3084000 | 3084000 |  |  |  |  | 0 | 3084000 | 3084000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer284 | 800394 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
800399 | 108081 | FAASt [Automation Program Group 40] (Distribution) | 10F001460000, 10F002280000, 10F001420000, 10F005290000, 10F005530000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-12-31 | 12/31/2024 | [6 empty] | 2577000 | 2577000 |  |  |  |  | 0 | 2577000 | 2577000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer285 | 800399 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 357 |  | FAASt [Distribution Feeder Rebuild # 1620-02] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer286 | FAASt number pending 357 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 358 |  | FAASt [Distribution Feeder Rebuild # 2404-06] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer287 | FAASt number pending 358 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 361 |  | FAASt [Distribution Feeder Rebuild # 6406-02] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer288 | FAASt number pending 361 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
797148 | 108074 | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) | 14F000100000 |  | Distribution – Feeder Rebuild |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 2024-12-06 | 12/06/2024 | 2025-01-17 | 2025-06-02 | 2025-06-02 | 2025-05-30 |  |  | 4700455 | 4700455 | 0 | 777847.24 | 2605318.99 | 0 | 0 | 2605318.99 | 3383166.23 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1002/797148-DR4339PR-Feeder%20Rebuild%208101-03-DSOW%20Rev.%200.pdf?web=1 | 09DECEMBER2024 No ISOW in Grants Portal - MC | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez | Distribution Feeders - Arecibo Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 1.8042 | 1 |  | qwer289 | 797148 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 363 |  | FAASt [Distribution Feeder Rebuild # 1801-03] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer290 | FAASt number pending 363 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 364 |  | FAASt [Distribution Feeder Rebuild # 3502-02] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer291 | FAASt number pending 364 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 365 |  | FAASt [Distribution Feeder Rebuild # 6802-04] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer292 | FAASt number pending 365 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 366 |  | FAASt [Distribution Feeder Rebuild # 7805-13] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer293 | FAASt number pending 366 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 367 |  | FAASt [Distribution Feeder Rebuild # 1336-08] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer294 | FAASt number pending 367 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
767387 | 108068 | FAASt # [Distribution Feeder Rebuild # 1303-01] (Distribution) | 14F001480000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-22 | 11/22/2024 | [6 empty] | 4798378.99 | 4798378.99 |  |  |  |  | 0 | 4798378.99 | 4798378.99 | [10 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 2 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer295 | 767387 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
767381 | 108067 | FAASt [Distribution Feeder Rebuild # 1204-04] (Distribution) | 14F001460000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-09-30 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-22 | 11/22/2024 | [6 empty] | 9998489 | 9998489 |  |  |  |  | 0 | 9998489 | 9998489 | [10 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer296 | 767381 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 371 |  | FAASt [Distribution Feeder Rebuild # 1806-02] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:36 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer297 | FAASt number pending 371 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 372 |  | FAASt #[Distribution Feeder Rebuild # 6601-03] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer298 | FAASt number pending 372 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 373 |  | FAASt [Distribution Feeder Rebuild # 6603-01] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer299 | FAASt number pending 373 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801197 | 108084 | FAASt [Distribution Feeder Rebuild # 1204-02 | 14F001440000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-09-30 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2025-01-08 | 1/8/2025 | [6 empty] | 3863358 | 3863358 |  |  |  |  | 0 | 3863358 | 3863358 | [10 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer300 | 801197 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
767005 | 108062 | FAASt [Distribution Feeder Rebuild # 1303-05] | 14F001500000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-21 | 11/21/2024 | [6 empty] | 12631766 | 12631766 |  |  |  |  | 0 | 12631766 | 12631766 | [10 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer301 | 767005 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 376 |  | FAASt [Distribution Feeder Rebuild # 7805-11] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer302 | FAASt number pending 376 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 377 |  | FAASt [Distribution Feeder Rebuild # 6305-03] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer303 | FAASt number pending 377 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 378 |  | FAASt [Distribution Feeder Rebuild # 2402-02] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer304 | FAASt number pending 378 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 379 |  | FAASt [Distribution Feeder Rebuild # 9501-02] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer305 | FAASt number pending 379 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 384 |  | FAASt [Distribution Feeder Rebuild #- 1303-02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer306 | FAASt number pending 384 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 385 |  | FAASt [Distribution Feeder Rebuild #- 6010-01 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer307 | FAASt number pending 385 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 386 |  | FAASt [Distribution Feeder Rebuild #- 6306-02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer308 | FAASt number pending 386 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 389 |  | FAASt [Distribution Feeder Rebuild # - 1529-15 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer309 | FAASt number pending 389 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 390 |  | FAASt [Distribution Feeder Rebuild #- 3006-05 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer310 | FAASt number pending 390 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 391 |  | FAASt [Distribution Feeder Rebuild #- 3007-03 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer311 | FAASt number pending 391 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 392 |  | FAASt [Distribution Feeder Rebuild #- 6704-03 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer312 | FAASt number pending 392 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 393 |  | FAASt [Distribution Feeder Rebuild # - 2603-08 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer313 | FAASt number pending 393 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 395 |  | FAASt [Pole and Conductor Repair- Caguas Group 4-Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer314 | FAASt number pending 395 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 396 |  | FAASt [Pole and Conductor Repair-San Juan Group 3- Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:39 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer315 | FAASt number pending 396 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 397 |  | FAASt [Pole and Conductor Repair- Caguas Group 5-Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:40 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer316 | FAASt number pending 397 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 398 |  | FAASt [Pole and Conductor Repair- Arecibo Group 3-Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:40 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer317 | FAASt number pending 398 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 250 |  | FAASt Salinas TC to Jobos TC – 38kV 100 & 200 (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 13:58 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer318 | FAASt number pending 250 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 258 |  | FAASt - Line 36100(115kV) - Unibon to Monterrey (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer319 | FAASt number pending 258 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 259 |  | FAASt - Line 36100(115kV) - Monterrey to Pinas (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer320 | FAASt number pending 259 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 260 |  | FAASt - Line 36100(115kV) - Pinas to Cana (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer321 | FAASt number pending 260 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 261 |  | FAASt [T-Pole Program Line 16500 Fajardo TC - Dos Marinas] (Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer322 | FAASt number pending 261 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 262 |  | FAASt [T-Pole Program Line 800 Comsat Sect - Cidra Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer323 | FAASt number pending 262 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 263 |  | TL 2000 - Once De Agosto Sect - San Sebastian TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer324 | FAASt number pending 263 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 264 |  | TL 3100 Monacillos TC - Sabana Llana TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer325 | FAASt number pending 264 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 265 |  | TL1500 Once De Agosto Sect - Sabana Grande TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer326 | FAASt number pending 265 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 266 |  | TL 3300 San Gerardo Sect-Venezuela Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer327 | FAASt number pending 266 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 267 |  | TL 5900 San Juan SP- Crematorio TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer328 | FAASt number pending 267 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 268 |  | TL 1200 San German Sect-San German TC- Yauco 2HP |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer329 | FAASt number pending 268 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 269 |  | TL 13700 Mora TC -Isabela TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer330 | FAASt number pending 269 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 270 |  | TL 1600 Leon Sect - Acacias TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer331 | FAASt number pending 270 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 271 |  | TL 1900 Dos Bocas Hp-San Sebastian TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer332 | FAASt number pending 271 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 272 |  | TL 10100 - LASLomas Sect-Reparto Metropolitano TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer333 | FAASt number pending 272 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 273 |  | TL 2400 - Dos Bocas Hp-Caonillas 2 Hp |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer334 | FAASt number pending 273 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 274 |  | TL 200 Ponce TC - Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer335 | FAASt number pending 274 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 275 |  | TL 4800 Santa Isabel TC- Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer336 | FAASt number pending 275 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 276 |  | TL 9600 Bayamon TC - Cataño Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer337 | FAASt number pending 276 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 277 |  | TL 7800 - Dorado Tc- Vega Alta Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer338 | FAASt number pending 277 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 278 |  | TL6700 - Seboruco To- Tapia TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer339 | FAASt number pending 278 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 279 |  | TL 7500 - Tres Monjitas Sect-Puerto Nuevo TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer340 | FAASt number pending 279 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 280 |  | TL 10700 - Hato Tejas Tc-Hato Tejas Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:00 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer341 | FAASt number pending 280 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 281 |  | TL 6000 - Aguadilla Hospital Distrito To-T- Bone TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer342 | FAASt number pending 281 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 282 |  | TL 10500-Chardon Sect- Las Monjas TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer343 | FAASt number pending 282 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 283 |  | TL 14100 Barceloneta Tc-Merck |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer344 | FAASt number pending 283 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 284 |  | FAASt [T-Pole Program Line 37400 Dorado TC - Vega Baja TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez | [7 empty] | qwer345 | FAASt number pending 284 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 285 |  | FAASt [T-Pole Program Line 37400 Barceloneta TC - Cambalache TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer346 | FAASt number pending 285 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 286 |  | TL 1700 - Guanica Tc- Yauco 2 Hp |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer347 | FAASt number pending 286 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 287 |  | TL 18400 -Barranquitas Tc-El Abanico |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer348 | FAASt number pending 287 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 288 |  | TL 2200 -Barceloneta TC-Manati TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer349 | FAASt number pending 288 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 289 |  | TL 2200 - Vega Baja TC-Vega Alta Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer350 | FAASt number pending 289 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 290 |  | TL 6900 -Cambalache Tc-Mirador Azul Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer351 | FAASt number pending 290 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 291 |  | TL 6900 - Mirador Azul Sect-Hatillo TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer352 | FAASt number pending 291 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 292 |  | TL 8100 - Yauco 1 Hp- Adjuntas TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer353 | FAASt number pending 292 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 293 |  | TL 9200 - Añasco TC- Añasco |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer354 | FAASt number pending 293 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 294 |  | TL 9900 - Rio Blanco Hp-Humacao Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer355 | FAASt number pending 294 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 295 |  | TL 2700 - Aguadilla Hospital Distrito Sect - Mora TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer356 | FAASt number pending 295 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 296 |  | TL 5600 Anasco TC- Mayaguez GP |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer357 | FAASt number pending 296 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 297 |  | TL 3500 Cachete Sect- Caparra Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:01 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer358 | FAASt number pending 297 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 303 |  | TL 36800 Canovanas TC - Palmer TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer359 | FAASt number pending 303 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 304 |  | TL 14400 - Caguax Sect- Veredas Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer360 | FAASt number pending 304 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 305 |  | TL 6100 Mayaguez GP - Radial |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer361 | FAASt number pending 305 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 306 |  | TL 14400 - Veredas Sect- Gautier Benitez Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer362 | FAASt number pending 306 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 307 |  | TL 37400 Cambalache TC- Dos Bocas HP |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez | [7 empty] | qwer363 | FAASt number pending 307 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 308 |  | TL 10300 - Canovanas TC- Canovanas Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer364 | FAASt number pending 308 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 309 |  | TL 10700 - Hato Tejas Sect-Bayamon Pueblo Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer365 | FAASt number pending 309 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 310 |  | TL 10900 - Jobos Tc-Pfizer Guayama |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer366 | FAASt number pending 310 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 311 |  | TL 13200 - Dorado Tc-Hato Tejas TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer367 | FAASt number pending 311 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 312 |  | TL 13200 - Hato Tejas TC- Hato Tejas Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer368 | FAASt number pending 312 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 313 |  | TL 13600 - Arecibo Sect-Mirador Azul Sect- |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer369 | FAASt number pending 313 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 314 |  | TL 14700 Manati TC - Manati Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer370 | FAASt number pending 314 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 315 |  | TL 14900-Quebradillas Sect-Quebradillas TO- |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer371 | FAASt number pending 315 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 316 |  | TL 15900-Victoria TC- Aguada TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer372 | FAASt number pending 316 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 317 |  | TL 1800 - Ponce TC -Villa Del Carmen TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer373 | FAASt number pending 317 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 318 |  | TL 200-Santa Isabel Sect-Salinas Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer374 | FAASt number pending 318 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 319 |  | TL 2900 Toro Negro 1 HP -Toro Negro 2 HP |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer375 | FAASt number pending 319 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 320 |  | TL 300 - Juana Diaz Tc- La Rambla Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer376 | FAASt number pending 320 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 321 |  | TL 300 - Toro Negro 1 Hp-Juana Diaz TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer377 | FAASt number pending 321 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 322 |  | TL 3200 - Hato Rey Tc- Baldrich Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer378 | FAASt number pending 322 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 323 |  | TL 3400 - Monacillos TC-Guaynabo Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer379 | FAASt number pending 323 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 324 |  | TL 37500-Rio Bayamon Sect-Monacillos TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer380 | FAASt number pending 324 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 325 |  | TL 37800 Monacillos TC - Buen Pastor Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer381 | FAASt number pending 325 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 326 |  | TL 37800 Caguas TC - Buen Pastor Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer382 | FAASt number pending 326 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 327 |  | TL 400 Caguas TC - Gautier Benitez Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer383 | FAASt number pending 327 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 328 |  | TL 8700-Costa Sur SP- Garzas 1 Hp |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer384 | FAASt number pending 328 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 329 |  | TL 38900 Martin Peña GIS - Berwind TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer385 | FAASt number pending 329 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 330 |  | TL 5400 Rio Blanco HP - Daguao TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | Transmission – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Rey Roldan Rodríguez | [7 empty] | qwer386 | FAASt number pending 330 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 331 |  | TL 9500-Palo Seco SP - Cataño Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Palo Seco SP to Catano SectLine-9500 (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer387 | FAASt number pending 331 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 332 |  | TL 500-Ponce TC-Costa Sur SP-Canas TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | Line 500 Ponce TC to Costa Sur SP | Rey Roldan Rodríguez | [7 empty] | qwer388 | FAASt number pending 332 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 333 |  | TL 2600-San Sebastian TC-Quebradillas Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer389 | FAASt number pending 333 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 334 |  | TL 36200 Monacillos TC- Juncos TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer390 | FAASt number pending 334 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 335 |  | TL 37400-Barceloneta TC-Cambalache TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer391 | FAASt number pending 335 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 336 |  | TL 37400-Dorado TC-Vega Baja TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer392 | FAASt number pending 336 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 337 |  | TL 38200-Palo Seco Power Plant-Monacillos TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer393 | FAASt number pending 337 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 338 |  | TL 7200-Baldrich Sect- Escuela Industrial TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer394 | FAASt number pending 338 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 339 |  | TL 7300-Baldrich Sect- San Jose TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer395 | FAASt number pending 339 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 340 |  | TL 37800-Cayey TC-Jobos TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer396 | FAASt number pending 340 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 341 |  | TL 37800-Cayey TC-Caguas TC- |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer397 | FAASt number pending 341 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 343 |  | Group 22 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer398 | FAASt number pending 343 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 344 |  | Group 24 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer399 | FAASt number pending 344 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 345 |  | Group 26 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer400 | FAASt number pending 345 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 346 |  | Group 27 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer401 | FAASt number pending 346 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 347 |  | Group 31 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer402 | FAASt number pending 347 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 348 |  | Group 32 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer403 | FAASt number pending 348 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 349 |  | Group 33 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer404 | FAASt number pending 349 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 350 |  | Group 34 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer405 | FAASt number pending 350 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 351 |  | Group 35 - DAUT |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer406 | FAASt number pending 351 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
800286 | 108077 | FAASt [Automation Program Group 36] (Distribution) | 10F002670000, 10F004180000, 10F004160000, 10F006580000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-12-30 | 12/30/2024 | 2025-04-28 |  | 2025-06-09 | 2025-05-30 |  |  | 2175000 | 2175000 |  | 300364.95 | 2301102.91 |  | 0 | 2301102.91 | 2601467.86 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1142/800286-DR4339PR-%20DSOW%20Group%2036.%20Rev.%201.pdf?web=1 | 30DECEMBER2024 No ISOWs in GP at this time MC | 2025-07-18 18:31 | 2024-09-11 14:07 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.9452 | 1 |  | qwer407 | 800286 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 251 |  | FAASt {Region 1- San Juan Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer408 | FAASt number pending 251 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 252 |  | FAASt {Region 2- Arecibo Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer409 | FAASt number pending 252 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 253 |  | FAASt {Region 3 - Bayamon Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer410 | FAASt number pending 253 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 254 |  | FAASt {Region 4 - Caguas Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer411 | FAASt number pending 254 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 255 |  | FAASt {Region 5 - Mayaguez Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:37 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer412 | FAASt number pending 255 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 298 |  | TL 1600 - SanGerman Sect-San German Tc |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer413 | FAASt number pending 298 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 299 |  | TL 1600 - San German Tc- Yauco 1 Hp |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer414 | FAASt number pending 299 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 300 |  | TL 2800 - Aguadilla Hospital Distrito Sect-T- Bone TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Rey Roldan Rodríguez | [7 empty] | qwer415 | FAASt number pending 300 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 301 |  | TL 3200 - Viaducto Tc- Martin Peña TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer416 | FAASt number pending 301 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 302 |  | TL 3200 Hato Rey - Baldrich Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:31 | 2024-09-11 14:43 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer417 | FAASt number pending 302 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756472 | 108024 | FAASt [Region 1-San Juan Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 2024-09-19 | 09/19/2024 | [6 empty] | 691016.47 | 691016.47 |  |  |  |  | 0 | 691016.47 | 691016.47 | [10 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded 18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT2024 10/22/2024 - Merged w/ 740406 10/17/2024 02:36 PM AST Project Updated Title: FAASt [Region 1-San Juan Group B] High Density (Vegetation) -> FAASt [Region 1-San Juan Group B] (Vegetation) FAASt #756472 added | 2025-07-18 18:31 | 2024-09-20 12:36 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer418 | 756472 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756474 | 108025 | FAASt [Region 3-Bayamon Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 2024-09-19 | 09/19/2024 | [6 empty] | 1049080.08 | 1049080.08 |  |  |  |  | 0 | 1049080.08 | 1049080.08 | [10 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded 18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740408 10/17/2024 02:39 PM AST 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 3-Bayamon Group B] High Density (Vegetation) -> FAASt [Region 3-Bayamon Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:36 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer419 | 756474 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756475 | 108026 | FAASt [Region 2-Arecibo Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 2024-09-19 | 09/19/2024 | [6 empty] | 30966.29 | 30966.29 |  |  |  |  | 0 | 30966.29 | 30966.29 | [10 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded 18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740410 10/17/2024 02:40 PM AST Project Updated Title: FAASt [Region 2-Arecibo Group B] High Density (Vegetation) -> FAASt [Region 2-Arecibo Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:37 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer420 | 756475 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756476 | 108027 | FAASt [Region 4-Caguas Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 2024-09-19 | 09/19/2024 | [6 empty] | 3068261.01 | 3068261.01 |  |  |  |  | 0 | 3068261.01 | 3068261.01 | [10 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded 18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740409 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 4-Caguas Group B] High Density (Vegetation) -> FAASt [Region 4-Caguas Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:38 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer421 | 756476 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756477 | 108028 | FAASt [Region 5-Mayaguez Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 2024-09-19 | 09/19/2024 | [6 empty] | 720951.73 | 720951.73 |  |  |  |  | 0 | 720951.73 | 720951.73 | [10 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded 18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - MERGED W/ 740411 10/17/2024 02:47 PM AST Project Updated Title: FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) -> FAASt [Region 5-Mayaguez Group B] (Vegetation) | 2025-07-18 18:31 | 2024-09-20 12:38 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer422 | 756477 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756479 | 108029 | FAASt [Region 6-Ponce Group B] Low Density (Vegetation) |  |  | Vegetation |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 2024-09-19 | 09/19/2024 | [6 empty] | 1316423.25 | 1316423.25 |  |  |  |  | 0 | 1316423.25 | 1316423.25 | [10 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded 18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT2024 & The project was withdrawn with the comment "LUMA requests the elimination of this project. The information of this project will be part of the one that is kept in the system as group B. For more details, please see attached document DR4339PR-Email confirmation to remove Group B Low Density 10.17.24.". | 2025-07-18 18:31 | 2024-09-20 12:39 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer423 | 756479 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756997 | 108030 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) |  |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-09-25 | 09/25/2024 | 2024-09-30 | 2025-07-01 | 2025-08-08 | 2025-07-25 | Field EHP - Historic: Previous status applies: In review. ECD: 8/08/2025. |  | 51200000 | 51200000 |  | 2671511.79 | 41068188.09 |  | 0 | 41068188.09 | 43739699.88 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1168/756997-DR4339PR-Detailed%20SOW-TLine%20%20Caguanas%20TC%20to%20Lares%20TO%20(Seg.%202)_Rev0.pdf?web=1 | 25SEPTEMBER2024 No ISOW submitted at this time | 2025-07-28 16:08 | 2024-09-25 09:25 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Maria Mujica Gonzalez |  |  |  |  | 1.2467 | 1 |  | qwer424 | 756997 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
756999 | 108031 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) |  |  | Transmission |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 2024-09-25 | 09/25/2024 | 2024-10-01 | 2025-07-01 | 2025-08-15 | 2025-07-15 | Field EHP - Historic: Previous status applies: In review. ECD: 8/15/2025. |  | 51200000 | 51200000 |  | 2088488.51 | 30407203.69 |  | 0 | 30407203.69 | 32495692.2 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1169/756999-DR4339PR-Detailed%20SOW-TLine%201900%20Lares%20TO%20-%20San%20Sebastian%20(Sec.%203)_Rev0.pdf?web=1 | 25SEPTEMBER2024 No ISOW submitted at this time | 2025-07-28 16:14 | 2024-09-25 09:29 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Maria Mujica Gonzalez |  |  |  |  | 1.6838 | 1 |  | qwer425 | 756999 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757662 | 108032 | FAASt [Automation Program Group 21] (Distribution) | 10F001150000, 10F001160000, 10F001140000, 10F001130000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-01-31 | 2025-06-19 | 2025-07-31 | 2025-07-09 |  |  | 1488000 | 1488000 | 0 | 280516.59 | 2223344.42 | 0 | 0 | 2223344.42 | 2503861.01 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1170/757662-DR4339PR-%20DSOW%20Group%2021%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 27SEPTEMBER2024 No ISOW in GP at this time | 2025-07-18 18:31 | 2024-09-27 10:08 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.66926 | 2 |  | qwer426 | 757662 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757700 | 108041 | FAASt [Automation Program Group 35] (Distribution) | 10F000920000, 10F000930000, 10F000910000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-03-11 | 2025-04-28 | 2025-07-07 | 2025-05-09 |  |  | 1023000 | 1023000 | 0 | 245359.86 | 1743076.28 | 0 | 0 | 1743076.28 | 1988436.14 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1171/757700-%20DR4339PR-%20DSOW%20Group%2035.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:26 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.58689 | 3 |  | qwer427 | 757700 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757699 | 108040 | FAASt [Automation Program Group 34] (Distribution) | 10F002870000, 10F002830000, 10F002860000, 10F002880000, 10F003870000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-03-11 | 2025-05-20 | 2025-06-24 | 2025-05-30 |  |  | 561000 | 561000 | 0 | 462362.68 | 3439728.11 | 0 | 0 | 3439728.11 | 3902090.79 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1172/757699-%20DR4339PR-%20DSOW%20Group%2034.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:28 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.16309 | 5 |  | qwer428 | 757699 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757698 | 108039 | FAASt [Automation Program Group 33] (Distribution) | 10F000860000, 10F000850000, 10F000840000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-03-11 | 2025-06-18 | 2025-07-07 | 2025-06-27 |  |  | 2226000 | 2226000 | 0 | 311582.64 | 2483045.65 | 0 | 0 | 2483045.65 | 2794628.29 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1173/757698-%20DR4339PR-%20DSOW%20Group%2033.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:30 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.89648 | 1 |  | qwer429 | 757698 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757697 | 108038 | FAASt [Automation Program Group 32] (Distribution) | 10F001290000, 10F001320000, 10F001310000, 10F001300000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-01-31 | 2025-07-04 | 2025-08-01 | 2025-07-11 |  |  | 798000 | 798000 | 0 | 339647.19 | 2663099.41 | 0 | 0 | 2663099.41 | 3002746.6 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1174/757697-DR4339PR-%20DSOW%20Group%2032%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:31 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.29965 | 4 |  | qwer430 | 757697 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757696 | 108037 | FAASt [Automation Program Group 31] (Distribution) | 10F000740000, 10F000770000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-01-31 | 2025-06-18 | 2025-06-20 | 2025-05-30 |  |  | 2085000 | 2085000 | 0 | 195175.66 | 1515001.61 | 0 | 0 | 1515001.61 | 1710177.27 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1175/757696-DR4339PR-%20DSOW%20Group%2031%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:32 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1.3762 | 1 |  | qwer431 | 757696 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757694 | 108036 | FAASt [Automation Program Group 27] (Distribution) | 10F001260000, 10F001240000, 10F001250000, 10F001230000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-01-31 | 2025-05-20 | 2025-07-03 | 2025-07-01 |  |  | 2364000 | 2364000 | 0 | 419922.13 | 3292670.74 | 0 | 0 | 3292670.74 | 3712592.87 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1176/757694-%20DR4339-PR-%20DSOW-%20Group%2027%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:33 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.71796 | 2 |  | qwer432 | 757694 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757692 | 108035 | FAASt [Automation Program Group 26] (Distribution) | 10F000730000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-01-31 | 2025-04-28 | 2025-05-23 | 2025-05-09 |  |  | 1194000 | 1194000 | 0 | 175325.33 | 1369120.11 | 0 | 0 | 1369120.11 | 1544445.44 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1177/757692-DR4339PR-%20DSOW%20Group%2026%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:33 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.87209 | 1 |  | qwer433 | 757692 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757689 | 108034 | FAASt [Automation Program Group 24] (Distribution) | 10F001210000, 10F001220000, 10F001200000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-01-31 | 2025-04-28 | 2025-05-23 | 2025-05-09 |  |  | 1836000 | 1836000 | 0 | 299299.32 | 2337650.4 | 0 | 0 | 2337650.4 | 2636949.72 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1178/757689-%20DR4339-PR-%20DSOW-%20Group%2024%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:35 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.7854 | 2 |  | qwer434 | 757689 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757687 | 108033 | FAASt [Automation Program Group 22] (Distribution) | 10F000700000, 10F000690000, 14F004700000, 10F000710000, 14F004720000 |  | Grid Automation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-27 | 09/27/2024 | 2025-01-31 | 2025-06-23 | 2025-07-31 | 2025-07-11 |  |  | 1671000 | 1671000 | 0 | 359230.44 | 2768746.03 | 0 | 0 | 2768746.03 | 3127976.47 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1179/FULL%20428%20757687-DR4339PR-%20DSOW%20Group%2022%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 30SEPTEMBER2024 - No ISOWs in GP | 2025-07-18 18:31 | 2024-09-30 12:35 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0.60352 | 2 |  | qwer435 | 757687 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
757945 | 108042 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | 14F020460000 |  | Distribution – Pole Replacement |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-09-30 | 10/01/2024 | 2025-07-10 | [5 empty] | 8540000 | 8540000 | 50517.25 | 358558.84 | 2730318.7 | 5864.07 | 44653.18 | 2780835.95 | 3139394.79 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1180/ISOW%20Pole%20and%20Conductor%20-%20Arecibo%20Group%203%20-%20Phase%202%20..pdf?web=1 |  | 2025-07-18 18:31 | 2024-10-01 09:00 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 3.071 | 1 |  | qwer436 | 757945 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
759051 | 108046 | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) | 14F021410000 |  | Distribution |  |  | TRUE | 2025-08-31 |  | FALSE | [12 empty] | 2024-10-08 | 10/11/2024 | [6 empty] | 3990000 | 3999999 |  |  |  |  | 0 | 3990000 | 3990000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1181/ISOW%20Pole%20and%20Conductor%20-%20Bayamon%20Group%204%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:32 | 2024-10-10 15:22 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1.0025 | 1 |  | qwer437 | 759051 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
759004 | 108045 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | 14F021390000 |  | Distribution |  |  | TRUE | 2025-08-31 |  | FALSE | [12 empty] | 2024-10-08 | 10/10/2024 | [6 empty] | 9280000 | 9280000 |  |  |  |  | 0 | 9280000 | 9280000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1182/ISOW%20Pole%20and%20Conductor%20-%20Arecibo%20Group%204%20-%20Phase%202.pdf?web=1 |  | 2025-07-18 18:32 | 2024-10-10 15:23 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer438 | 759004 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
760568 | 108048 | FAASt [Distribution Feeder Rebuild # 1710-01] (Distribution) | 14F000170000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-08-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-10-24 | 10/24/2024 | [6 empty] | 10467848 | 10467848 |  |  |  |  | 0 | 10467848 | 10467848 | [10 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-10-28 13:14 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer439 | 760568 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
760571 | 108049 | FAASt [Distribution Feeder Rebuild # 1720-07] (Distribution) | 14F000220000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-10-24 | 10/24/2024 | [6 empty] | 18005134 | 18005134 |  |  |  |  | 0 | 18005134 | 18005134 | [10 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-10-28 13:16 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer440 | 760571 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
760575 | 108050 | FAASt [Distribution Feeder Rebuild # 1716-03] (Distribution) | 14F000190000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-08-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-10-24 | 10/24/2024 | [6 empty] | 18102407 | 18102407 |  |  |  |  | 0 | 18102407 | 18102407 | [10 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-10-28 13:18 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer441 | 760575 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
760577 | 108051 | FAASt [Distribution Feeder Rebuild # 1718-02] (Distribution) | 14F000210000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-10-24 | 10/24/2024 | [6 empty] | 8421396 | 8421396 |  |  |  |  | 0 | 8421396 | 8421396 | [10 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-10-28 13:19 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer442 | 760577 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
760579 | 108052 | FAASt [Distribution Feeder Rebuild # 1717-03] (Distribution) | 14F000200000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-10-24 | 10/24/2024 | [6 empty] | 14143466 | 14143466 |  |  |  |  | 0 | 14143466 | 14143466 | [10 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-10-28 13:21 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer443 | 760579 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
764709 | 108060 | FAASt [Distribution Feeder Rebuild # 1204-05] (Distribution) | 14F001470000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-04 | 11/04/2024 | [6 empty] | 8740820.93 | 8740820.93 |  |  |  |  | 0 | 8740820.93 | 8740820.93 | [10 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-11-04 10:12 | Marlina Crespo | Distribution Feeders ‐ San Juan Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer444 | 764709 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
764708 | 108059 | FAASt [Distribution Feeder Rebuild # 5602-02] (Distribution) | 14F001360000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-09-30 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 40610000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 |  |  |  |  | 2024-11-04 | 11/04/2024 | [6 empty] | 5190387.52 | 5190387.52 |  |  |  |  | 0 | 5190387.52 | 5190387.52 | [10 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-11-04 10:13 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer445 | 764708 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
764707 | 108058 | FAASt [Distribution Feeder Rebuild # 6012-02] (Distribution) | 14F000970000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-04 | 11/04/2024 | [6 empty] | 5540622.64 | 5540622.64 |  |  |  |  | 0 | 5540622.64 | 5540622.64 | [10 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-11-04 10:14 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer446 | 764707 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
764706 | 108057 | FAASt [Distribution Feeder Rebuild # 7011-03] (Distribution) | 14F001000000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-04 | 11/04/2024 | [6 empty] | 9329781.4 | 9329781.4 |  |  |  |  | 0 | 9329781.4 | 9329781.4 | [10 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-11-04 10:15 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer447 | 764706 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
764705 | 108056 | FAASt [Distribution Feeder Rebuild # 6014-02] (Distribution) | 14F000980000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-08-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-04 | 11/04/2024 | [6 empty] | 13387462.29 | 13387462.29 |  |  |  |  | 0 | 13387462.29 | 13387462.29 | [10 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-11-04 10:15 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer448 | 764705 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
761563 | 108055 | FAASt [San Jose Relocation] (Substation) | 14F001920000 |  | Substation |  |  | FALSE |  |  | FALSE |  |  |  | 17000000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 |  |  |  |  | 2024-11-01 | 11/01/2024 | [6 empty] | 17000000 | 17000000 |  |  |  |  | 0 | 17000000 | 17000000 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1195/761563-DR4339PR-EN-SOW-0001_Rev0%20-%20San%20Jose%20Relocation.pdf?web=1 |  | 2025-07-18 18:32 | 2024-11-04 10:16 | Marlina Crespo | San Jose Relocation | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer449 | 761563 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
767139 | 108064 | FAASt [Distribution Feeder Rebuild # 2906-02] (Distribution) | 14F000510000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-11-21 | 11/21/2024 | [6 empty] | 3205041 | 3205041 |  |  |  |  | 0 | 3205041 | 3205041 | [10 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 2025-07-18 18:32 | 2024-11-22 15:04 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 1 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 2025-06-12 | qwer450 | 767139 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Guanica - Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 14:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer451 | FAASt Number Pending 400947 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Caguas – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:04 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer452 | FAASt Number Pending 400948 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Hato Rey – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer453 | FAASt Number Pending 400949 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Mora – Phase I (Substation) |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer454 | FAASt Number Pending 400950 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | San Jose (Utuado) – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:06 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer455 | FAASt Number Pending 400951 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Arecibo – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:07 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer456 | FAASt Number Pending 400952 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Pompanos – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:07 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer457 | FAASt Number Pending 400953 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Canas TC – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer458 | FAASt Number Pending 400954 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Fonalledas – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer459 | FAASt Number Pending 400955 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Naguabo – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer460 | FAASt Number Pending 400956 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Fajardo 2002 – Veve Calzada – Phase |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:08 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer461 | FAASt Number Pending 400957 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | Factor – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:09 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer462 | FAASt Number Pending 400958 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt Salinas TC to Jobos TC – 38kV 100 & 200 (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:10 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer463 | FAASt Number Pending 400959 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
811923 | 108100 | FAASt [Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | 14F020570000 |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-02-17 | 02/18/2025 | 2025-02-17 | [5 empty] | 28863.82 | 28863.82 | 35673.37 | 28863.82 | 190142.13 | 4040.9 | 31632.47 | 225815.5 | 254679.32 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:12 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0.12782 | 5 |  | qwer464 | 811923960 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
811913 | 108099 | FAASt [Transmission Priority Pole Replacement Program Line 9600 Bayamon TC – Catano Sect] (Transmission) | 14F020510000 |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-02-17 | 02/18/2025 | 2025-02-17 | [5 empty] | 335555.06 | 335555.06 | 64492.51 | 42887.43 | 271062.55 | 7307.99 | 57184.52 | 335555.06 | 378442.49 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1213/136271-DR4339PR-Detailed%20SOW-T-Pole%20TL9600%20Bayamon%20TC%20%E2%80%93%20Catano%20Sect_Rev.0_2-17-2025.pdf?web=1 |  | 2025-07-18 18:32 | 2024-12-11 15:14 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer465 | 811913961 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL1500 Once De Agosto Sect - Sabana Grande TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:14 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer466 | FAASt Number Pending 400962 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 1200 San German Sect-San German TC - Yauco 2HP |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer467 | FAASt Number Pending 400963 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 1600 Leon Sect - Acacias TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer468 | FAASt Number Pending 400964 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 6900 - Mirador Azul Sect-Hatillo TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:17 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer469 | FAASt Number Pending 400965 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 6700 - Seboruco To-Tapia TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:18 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer470 | FAASt Number Pending 400966 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 200 Ponce TC -Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:18 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer471 | FAASt Number Pending 400967 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 4800 Santa Isabel TC - Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:19 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer472 | FAASt Number Pending 400968 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
805521 | 108093 | FAASt [38kV Recloser TL 7800 Dorado TC to Vega Alta Sect.] (Transmission) | 14F019130000 |  | Transmission – Pole Replacement |  | Improved | FALSE |  |  | FALSE | [12 empty] | 2024-12-19 | 01/21/2025 | 2025-02-07 | 2025-07-15 | 2025-03-26 | 2025-03-17 |  |  | 2980000 | 2980000 | 725071.07 | 32294 | 252749.08 | 82142.46 | 642928.61 | 977820.15 | 1010114.15 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1221/805521-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%207800%20-%20FY25%20Revision%20000_Signed.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:32 | 2024-12-11 15:19 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 3.0476 | 1 |  | qwer473 | 969 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 7500 - Tres Monjitas Sect-Puerto Nuevo TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:19 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer474 | FAASt Number Pending 400970 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 10700 - Hato Tejas Tc-Hato Tejas Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:19 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer475 | FAASt Number Pending 400971 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 2400 - Dos Bocas Hp-Caonillas 2 Hp |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer476 | FAASt Number Pending 400972 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 10500-Chardon Sect-Las Monjas TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer477 | FAASt Number Pending 400973 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 14100 Barceloneta C-Merck |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer478 | FAASt Number Pending 400974 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 6000 - Aguadilla Hospital Distrito To-T-Bone TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer479 | FAASt Number Pending 400975 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 18400 - Barranquitas Tc-El Abanico |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:22 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer480 | FAASt Number Pending 400976 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 2200 -Barceloneta TC-Manati TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:22 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer481 | FAASt Number Pending 400977 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 2200 - Vega Baja TC-Vega Alta Sec |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:22 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer482 | FAASt Number Pending 400978 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 9200 - Añasco TC-Añasco |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer483 | FAASt Number Pending 400979 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 3500 Cachete Sect - Caparra Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer484 | FAASt Number Pending 400980 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 9900 - Rio Blanco Hp-Humacao Sec |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer485 | FAASt Number Pending 400981 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 8100 - Yauco 1 Hp-Adjuntas TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer486 | FAASt Number Pending 400982 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 1600 - San German Sect-San German Tc |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer487 | FAASt Number Pending 400983 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 1600 - San German Tc-Yauco 1 Hp |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:24 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer488 | FAASt Number Pending 400984 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 2800 - Aguadilla Hospital Distrito Sect-T-Bone TO |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:25 | Marlina Crespo | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Rey Roldan Rodríguez | [7 empty] | qwer489 | FAASt Number Pending 400985 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 300 - Juana Diaz Tc-La Rambla Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:25 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer490 | FAASt Number Pending 400986 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 300 - Toro Negro 1 Hp-Juana Diaz TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:25 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer491 | FAASt Number Pending 400987 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 3200 - Viaducto Tc-Martin Peña TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:26 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer492 | FAASt Number Pending 400988 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 3200 Hato Rey -Baldrich Sect |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:26 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer493 | FAASt Number Pending 400989 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 36800 Canovanas TC - Palmer TC |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:27 | Marlina Crespo | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer494 | FAASt Number Pending 400990 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | TL 6100 Mayaguez GP - Radial |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 15:28 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer495 | FAASt Number Pending 400991 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3B- 8 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:10 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer496 | FAASt Number Pending 400992 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3C- 7 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:10 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer497 | FAASt Number Pending 400993 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3D- 6 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:12 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer498 | FAASt Number Pending 400994 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3E- 9 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:12 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer499 | FAASt Number Pending 400995 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2B-8 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer500 | FAASt Number Pending 400996 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2C-10 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer501 | FAASt Number Pending 400997 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2D-8 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer502 | FAASt Number Pending 400998 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2E-9 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:13 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer503 | FAASt Number Pending 400999 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | [Automation Program Group 36](Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:32 | 2024-12-11 16:15 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | qwer504 | FAASt Number Pending 4001000 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | [Automation Program Group 37](Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:15 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1001 | FAASt Number Pending 4001001 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | [Automation Program Group 38](Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:15 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1002 | FAASt Number Pending 4001002 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | [Automation Program Group 39] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:15 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1003 | FAASt Number Pending 4001003 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | [Automation Program Group 40] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:15 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1004 | FAASt Number Pending 4001004 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801432 | 108085 | FAASt [Automation Program Group 41] (Distribution) | 10F002350000, 10F002360000, 10F002330000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-01-10 | 1/10/2025 | [6 empty] | 2391000 | 2391000 |  |  |  |  | 0 | 2391000 | 2391000 | [10 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 801432RFI1005 | 801432 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801437 | 108086 | FAASt [Automation Program Group 42] (Distribution) | 10F002110000, 10F002440000, 10F002370000, 10F002390000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-01-10 | 1/10/2025 | [6 empty] | 2883000 | 2883000 |  |  |  |  | 0 | 2883000 | 2883000 | [10 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 801437RFI1006 | 801437 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801438 | 108087 | FAASt [Automation Program Group 43] (Distribution) | 10F003450000, 10F003110000, 10F003440000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-01-10 | 1/10/2025 | [6 empty] | 2490000 | 2490000 |  |  |  |  | 0 | 2490000 | 2490000 | [10 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 801438RFI1007 | 801438 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801440 | 108088 | FAASt [Automation Program Group 44] (Distribution) | 10F002610000, 10F002630000, 10F002580000, 10F002600000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-01-10 | 1/10/2025 | [6 empty] | 3902000 | 3902000 |  |  |  |  | 0 | 3902000 | 3902000 | [10 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 801440RFI1008 | 801440 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801441 | 108089 | FAASt [Automation Program Group 45] (Distribution | 10F001480000, 10F001490000, 10F001470000 |  | Grid Automation |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-01-10 | 1/10/2025 | [6 empty] | 2400000 | 2400000 |  |  |  |  | 0 | 2400000 | 2400000 | [10 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-11 16:16 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 801441RFI1009 | 801441 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 1900 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1010 | FAASt Number Pending 4001010 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers Transmission TLine 2100 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1011 | FAASt Number Pending 4001011 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 3000 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1012 | FAASt Number Pending 4001012 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 7800 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:20 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1013 | FAASt Number Pending 4001013 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 1500 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1014 | FAASt Number Pending 4001014 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 5600 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1015 | FAASt Number Pending 4001015 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 6500 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1016 | FAASt Number Pending 4001016 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 8100 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:21 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1017 | FAASt Number Pending 4001017 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 800 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1018 | FAASt Number Pending 4001018 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38kV Reclosers TLine 12600 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1019 | FAASt Number Pending 4001019 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38kV Reclosers TLine 13400 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:23 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1020 | FAASt Number Pending 4001020 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38kV Reclosers TLine 1600 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:25 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1021 | FAASt Number Pending 4001021 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38kV Reclosers TLine 2000 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:25 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1022 | FAASt Number Pending 4001022 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38kV Reclosers TLine 3700 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:26 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1023 | FAASt Number Pending 4001023 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | 38kV Reclosers TLine 4800 |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:26 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1024 | FAASt Number Pending 4001024 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
798275 | 108075 | FAASt [Distribution Feeder Rebuild # 1620-02] (Distribution) | 14F001600000 |  | Distribution – Feeder Rebuild |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 2024-12-11 | 12/11/2024 | 2025-01-15 | 2025-04-24 | 2025-05-16 | 2025-05-05 |  |  | 6925970.19 | 6925970.19 | 0 | 954420.68 | 7464273.83 | 0 | 0 | 7464273.83 | 8418694.51 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1277/798275-DR4339PR-Feeders%20Rebuild%201620-02-DSOW%20Rev.%200.pdf?web=1 | 12DECEMBER2024 No ISOWs in GP at this time MC | 2025-07-18 18:35 | 2024-12-11 16:31 | Marlina Crespo | Distribution Feeders - San Juan Short Term Group 3 | Rey Roldan Rodríguez |  |  |  |  | 0.92788 | 1 |  | 798275RFI1025 | 798275 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:31 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1026 | FAASt Number Pending 4001026 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801172 | 108083 | FAASt [Distribution Feeder Rebuild # 1529-15] (Distribution) | 14F001540000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-01-08 | 1/8/2025 | 2025-01-31 | 2025-04-24 | 2025-06-05 | 2025-06-03 |  |  | 7155677 | 7155677 | 0 | 508777.01 | 2529247.52 | 0 | 0 | 2529247.52 | 3038024.53 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1279/801172-DR4339PR-Detailed%20Scope%20of%20Work-Rev.%201.pdf?web=1 | 14JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-11 16:33 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 2.8292 | 1 |  | 801172RFI1027 | 801172 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
801166 | 108082 | FAASt [Distribution Feeder Rebuild # 6601-03] (Distribution) | 14F001150000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-01-08 | 1/8/2025 | 2025-04-07 | 2025-06-12 | 2025-08-15 | 2025-07-25 | "Field EHP - Environmental: Initial review. Amended Expected Completion Date (08/15/2025). |  | 9010977 | 9010977 | 0 | 2734512.13 | 21387039.22 | 0 | 0 | 21387039.22 | 24121551.35 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1280/801166-DR4339PR-Distribution%20Feeder%20Rebuild%206601-03-Detailed%20Scope%20of%20Work%20Rev.0.pdf?web=1 | 14JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-25 15:42 | 2024-12-11 16:33 | Marlina Crespo |  | Maria Mujica Gonzalez |  |  |  |  | 0.42133 | 3 |  | 801166RFI1028 | 801166 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #6603-01] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:34 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1029 | FAASt Number Pending 4001029 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
812569 | 108102 | FAASt [Distribution Feeder Rebuild 3502-02] | 14F000490000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-02-20 | 02/20/2025 | 2025-03-19 | 2025-06-13 | 2025-07-29 | 2025-07-22 |  |  | 15430988 | 15430988 | 0 | 1403642.18 | 10978061.1 | 0 | 0 | 10978061.1 | 12381703.28 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1282/812569-DR4339PR-Feeder%20Rebuild%203502-02-Detailed%20Scope%20of%20Work.%20Rev.%200.pdf?web=1 | 21FEBRUARY2025 No ISOWs in GP at this time - MC | 2025-07-22 12:08 | 2024-12-11 16:34 | Marlina Crespo |  | Maria Mujica Gonzalez |  |  |  |  | 1.4056 | 1 |  | 812569RFI1030 | 812569 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #1303-02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:34 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1031 | FAASt Number Pending 4001031 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #-1718-02 |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:35 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1032 | FAASt Number Pending 4001032 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #1303-05] |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-11 16:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1033 | FAASt Number Pending 4001033 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild # 6406-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-12 14:28 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1034 | FAASt Number Pending 4001034 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2024-12-12 14:28 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1035 | FAASt Number Pending 4001035 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
806935 | 108097 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | 14F018900000 |  | Distribution – Pole Replacement |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-01-28 | 01/28/2025 | [6 empty] | 6120000 | 6120000 |  |  |  |  | 0 | 6120000 | 6120000 | [10 empty] | 0 | 0 |  |  | 28JANUARY2025 No ISOW docs in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-12 14:30 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 806935RFI1036 | 806935 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
806936 | 108098 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | 14F018950000 |  | Distribution – Pole Replacement |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-01-28 | 01/28/2025 | [6 empty] | 5100000 | 5100000 |  |  |  |  | 0 | 5100000 | 5100000 | [10 empty] | 0 | 0 |  |  | 28JANUARY2025 No ISOW docs in Grants Portal - MC | 2025-07-18 18:35 | 2024-12-12 14:30 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 806936RFI1037 | 806936 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
805519 | 108092 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) | 14F019110000 |  | Transmission |  |  | TRUE | 2025-07-31 |  | FALSE | [12 empty] | 2024-12-19 | 01/21/2025 | 2025-03-04 | [5 empty] | 3180000 | 3180000 | 0 | 140183.46 | 1097125.99 | 0 | 0 | 1097125.99 | 1237309.45 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1299/805519%20-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%201900%20Dos%20Bocas%20HP%20to%20San%20Sebastian%20TC%20Rev0%203.4.2025.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2025-01-22 11:42 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Rey Roldan Rodríguez |  |  |  |  | 2.8985 | 1 |  | 805519RFI1038 | 805519 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
805517 | 108091 | FAASt [38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect.] (Transmission) | 14F019120000 |  | Transmission |  |  | FALSE |  |  | FALSE | [12 empty] | 2024-12-19 | 01/21/2025 | 2025-03-04 | [5 empty] | 2990000 | 2990000 | 0 | 117407.32 | 918908.76 | 0 | 0 | 918908.76 | 1036316.08 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1300/805517%20-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%202100%20Hatillo%20TC%20to%20Quebradillas%20Sect.%20Rev0%203.4.2025.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-18 18:35 | 2025-01-22 11:45 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 3.2539 | 1 |  | 805517RFI1039 | 805517 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
805513 | 108090 | FAASt [38kV Recloser TL 3000 Monacillos TC to Bairoa TO] (Transmission) | 14F019230000 |  | Transmission |  |  | TRUE | 2025-07-31 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 2024-12-19 | 01/21/2025 | [6 empty] | 3250000 | 3250000 |  |  |  |  | 0 | 3250000 | 3250000 | [10 empty] | 0 | 0 |  |  | 22JANUARY2025 No ISOW in Grants Portal - MC | 2025-07-24 11:07 | 2025-01-22 11:45 | Marlina Crespo |  | Marlina Crespo |  |  |  |  | 1 | 1 |  | 805513RFI1040 | 805513 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 401 |  | System Stabilization Plan Monacillos TC, Sabana Llana TC & Costa Sur TC |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2025-01-17 |  | 2025-01-23 | 2025-02-06 |  | 2025-02-22 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-01-23 13:43 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 401RFI1041 | FAASt Number Pending 401 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
790427 | 108069 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) | 14F018890000 |  | Distribution |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-11-25 | 11/25/2024 | 2025-07-10 | [5 empty] | 5100000 | 5100000 | 71738.97 | 1002538.6 | 8239298.14 | 7782.12 | 63956.85 | 8311037.11 | 9313575.71 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1305/790427-DR4339PR-Detailed%20SOW%20Caguas%20Group%205%20-%20Phase%202%20Rev0%20428%20&%20406-1.pdf?web=1 |  | 2025-07-18 18:35 | 2025-02-05 20:37 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0.61364 | 2 |  | 790427RFI1042 | 790427 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
790443 | 108070 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 14F019030000 |  | Distribution |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-11-25 | 4/2/2025 | 2025-03-28 | 2025-04-24 | 2025-05-14 | 2025-05-09 |  |  | 5100000 | 5100000 | 0 | 25985 | 222321 | 0 | 0 | 222321 | 248306 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1306/790443-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%203%20-%20Phase%202%20Rev0.pdf?web=1 |  | 2025-07-18 18:35 | 2025-02-05 20:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 22.9398 | 1 |  | 790443RFI1043 | 790443 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
790446 | 108071 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | 14F018880000 |  | Distribution |  |  | FALSE |  | Current | FALSE | [12 empty] | 2024-11-25 | 11/25/2024 | 2025-07-10 | [5 empty] | 5100000 | 5100000 | 28582.12 | 523611.41 | 4138909.89 | 3209.84 | 25372.28 | 4167492.01 | 4691103.42 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1307/790446-DR4339PR-DPoles-Caguas%20Group%204%20-%20Phase%202-ISOW.pdf?web=1 |  | 2025-07-18 18:35 | 2025-02-05 20:44 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.2238 | 1 |  | 790446RFI1044 | 790446 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Pending |  | Substation System Improvement Plan |  |  | Substation |  |  | FALSE |  |  | FALSE |  |  | 2025-02-19 |  | 2025-02-21 | 2025-03-24 |  | 2025-03-23 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-02-21 09:26 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | FAASt PendingRFI1045 | FAASt Pending1045 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
812041 | 108101 | FAASt [Distribution Feeder Rebuild 9501-02] | 14F000270000 |  | Distribution |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-02-19 | 02/19/2025 | 2025-04-11 | 2025-07-07 |  |  |  |  | 13725835 | 13725835 | 0 | 3314820.98 | 25929254.07 | 0 | 0 | 25929254.07 | 29244075.05 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1310/812041-%20DR4339PR-%20Feeder%20Rebuild%209501-02-Detailed%20Scope%20of%20Work.pdf?web=1 | 20FEBRUARY2025 No ISOW in GP at this time - MC | 2025-07-18 18:35 | 2025-02-21 12:31 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0.52936 | 3 |  | 812041RFI1046 | 812041 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Pending |  | Fiber Optic Repair and Replacement |  |  | Telecommunications |  |  | FALSE |  |  | FALSE |  |  | 2025-02-27 |  | 2025-03-14 | 2025-04-13 |  | 2025-04-13 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-07 11:20 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | FAASt PendingRFI1047 | FAASt Pending1047 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
814792 | 108105 | FAASt [Telecom Infrastructure – Group E] | 14F009010000, 14F008930000, 14F009020000 |  | Telecommunications |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-07 | 03/07/2025 | [6 empty] | 5600000 | 5600000 |  |  |  |  | 0 | 5600000 | 5600000 | [10 empty] | 0 | 0 |  |  | 07MARCH2025 No ISOW in GP - MC | 2025-07-18 18:35 | 2025-03-07 12:13 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 814792RFI1048 | 814792 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
814793 | 108106 | FAASt [Telecom Infrastructure – Group F] | 14F019040000, 14F019050000, 14F019060000 |  | Telecommunications |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-07 | 03/07/2025 | [6 empty] | 4600000 | 4600000 |  |  |  |  | 0 | 4600000 | 4600000 | [10 empty] | 0 | 0 |  |  | 07MARCH2025 No ISOW in GP - MC | 2025-07-18 18:35 | 2025-03-07 12:17 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 814793RFI1049 | 814793 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Distribution Feeder Rebuild #6603-01] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:35 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1050 | FAASt number pending 5001050 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line San Juan Region Group 1](Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:37 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1051 | FAASt number pending 5001051 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817956 | 108119 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 14F001490000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | 2025-05-12 | 2025-06-20 | 2025-08-01 | 2025-07-25 | Field EHP: Previous status applies. Expected Completion Date (ECD) updated to 08/01/2025. |  |  | 6132436 | 0 | 1376522.26 | 2184086.98 | 0 | 0 | 2184086.98 | 3560609.24 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1316/817956-DR4339PR-Feeders%20Rebuild%201303-02-Detailed%20Scope%20of%20Work-Rev.%200.pdf?web=1 |  | 2025-07-25 15:40 | 2025-03-13 16:37 | Marlina Crespo |  | Maria Mujica Gonzalez |  |  |  |  | 2.8078 | 1 |  | 817956RFI1052 | 817956 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line Mayaguez Region Group1](Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:37 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1053 | FAASt number pending 5001053 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Distribution Feeder Rebuild # 6406-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:38 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1054 | FAASt number pending 5001054 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line Arecibo Region Group 1 (Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:38 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1055 | FAASt number pending 5001055 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:38 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1056 | FAASt number pending 5001056 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 9900 - RIO BLANCO HP-HUMACAO SECT](Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:38 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1057 | FAASt number pending 5001057 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending |  | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC - Santa Isabel Sect](Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:39 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pendingRFI1058 | FAASt number pending | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817961 | 108120 | FAASt [Feeder Rebuild # 2404-06] (Distribution) | 14F000900000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | 2025-07-08 | [5 empty] | 23882838 | 23882838 | 399260.06 | 1826739.4 | 19517674.31 | 50231.61 | 349028.45 | 19916934.37 | 21743673.77 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:39 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.1991 | 1 |  | 817961RFI1059 | 817961 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 1600 LEON SECT-ACACIAS TC](Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:39 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1060 | FAASt number pending 5001060 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
818006 | 108123 | FAASt [Feeder Rebuild #2402-02] (Distribution) | 14F000880000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | [6 empty] | 34516477 | 34516477 |  |  |  |  | 0 | 34516477 | 34516477 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 818006RFI1061 | 818006 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 1500 ONCE DE AGOSTO SECT - SABANA GRANDE TO](Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:40 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1062 | FAASt number pending 5001062 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817993 | 108122 | FAASt [Feeder Rebuild # 1801-03] (Distribution) | 14F000300000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | [6 empty] | 6131846 | 6131846 |  |  |  |  | 0 | 6131846 | 6131846 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:40 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 817993RFI1063 | 817993 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 2000 ONCE DE AGOSTO SECT - SAN SEBASTIAN TC](Transmission) |  |  | Transmission – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:40 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1064 | FAASt number pending 5001064 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
818056 | 108126 | FAASt [Feeder Rebuild # 6305-03] (Distribution) | 14F001080000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | [6 empty] | 22352214 | 22352214 |  |  |  |  | 0 | 22352214 | 22352214 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:41 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 818056RFI1065 | 818056 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Line 36100 Cana to Bayamon] (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:41 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1066 | FAASt number pending 5001066 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
818055 | 108125 | FAASt [Feeder Rebuild # 3006-05] (Distribution) | 14F000480000 |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | [6 empty] | 8829008 | 8829008 |  |  |  |  | 0 | 8829008 | 8829008 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:41 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 818055RFI1067 | 818055 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Transmission Line 36100 Dos Bocas to Ciales] (Transmission) |  |  | Transmission |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:41 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1068 | FAASt number pending 5001068 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
818041 | 108124 | FAASt [Feeder Rebuild # 3701-03] (Distribution) | 14F000520000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | [6 empty] | 24349603.89 | 24349603.89 |  |  |  |  | 0 | 24349603.89 | 24349603.89 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 818041RFI1069 | 818041 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817962 | 108121 | FAASt [Feeder Rebuild # 9403-03] (Distribution) | 14F000260000 |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-08-31 |  | FALSE | [12 empty] | 2025-03-26 | 03/26/2025 | [6 empty] | 5548949 | 5548949 |  |  |  |  | 0 | 5548949 | 5548949 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:42 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 817962RFI1070 | 817962 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Aguas Buenas - Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:42 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1071 | FAASt number pending 5001071 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 1806-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:43 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1072 | FAASt number pending 5001072 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Rincon - Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:43 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1073 | FAASt number pending 5001073 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 3007-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:43 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1074 | FAASt number pending 5001074 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Factor – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:43 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1075 | FAASt number pending 5001075 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Naguabo – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1076 | FAASt number pending 5001076 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 1909-09] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1077 | FAASt number pending 5001077 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Fonalledas – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1078 | FAASt number pending 5001078 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 2603-08] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1079 | FAASt number pending 5001079 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 7805-13] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1080 | FAASt number pending 5001080 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Canas TC – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1081 | FAASt number pending 5001081 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Pompanos – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1082 | FAASt number pending 5001082 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 1336-08] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1083 | FAASt number pending 5001083 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Arecibo – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:45 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1084 | FAASt number pending 5001084 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 6306-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1085 | FAASt number pending 5001085 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Mora – Phase I (Substation) |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1086 | FAASt number pending 5001086 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 6704-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1087 | FAASt number pending 5001087 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Hato Rey – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:46 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1088 | FAASt number pending 5001088 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 6010-01] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1089 | FAASt number pending 5001089 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Caguas – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:47 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1090 | FAASt number pending 5001090 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
825843 | 108134 | FAAST [Guanica Transformer Replacement] (Substation) |  |  | Substation |  |  | FALSE |  | Past | FALSE | [12 empty] | 2025-04-09 | 04/09/2025 | 2025-04-09 |  | 2025-07-29 | 2025-07-18 | Field EHP - Environmental: In Review. Expected Completion Date (ECD) 07/30/2025. |  |  |  |  | 826981.13 | 6521097.48 | 0 | 0 | 6521097.48 | 7348078.61 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1355/DR43339PR-FEMA%20DSOW%20Guanica%20TC%20signed%204.8.2025%20(002).pdf?web=1 |  | 2025-07-25 15:32 | 2025-03-13 16:47 | Maria Mujica Gonzalez |  | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 |  | 825843RFI1091 | 825843 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 7805-11] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1092 | FAASt number pending 5001092 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | Fajardo 2002 – Veve Calzada – Phase I |  |  | Substation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:47 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1093 | FAASt number pending 5001093 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [38kV Recloser TL 100 Ponce To Jobos (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:48 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1094 | FAASt number pending 5001094 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817249 | 108116 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) | 14F018910000 |  | Distribution – Pole Replacement |  |  | TRUE | 2025-07-31 |  | FALSE | [12 empty] | 2025-03-21 | 03/21/2025 | [6 empty] | 5100000 | 5100000 |  |  |  |  | 0 | 5100000 | 5100000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:49 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 817249RFI1095 | 817249 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [38kV Recloser TL 3600-SABANA LLANA TC-LOS ANGELES SECT-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:49 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1096 | FAASt number pending 5001096 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817242 | 108113 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution) | 14F018920000 |  | Distribution – Pole Replacement |  |  | TRUE | 2025-07-31 |  | FALSE | [12 empty] | 2025-03-21 | 03/21/2025 | [6 empty] | 2040000 | 2040000 |  |  |  |  | 0 | 2040000 | 2040000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:49 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 817242RFI1097 | 817242 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [38kV Recloser TL 3200-MONACILLOS TC-VENEZUELA SECT-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:49 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1098 | FAASt number pending 5001098 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [38kV Recloser TL 3100-MONACILLOS TC-SABANA LLANA TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:50 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1099 | FAASt number pending 5001099 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817247 | 108114 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2] (Distribution) | 14F021430000 |  | Distribution – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [12 empty] | 2025-03-21 | 03/21/2025 | [6 empty] | 11650000 | 11650000 |  |  |  |  | 0 | 11650000 | 11650000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:50 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 817247RFI1100 | 817247 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [38kV Recloser TL 2200-CAMBALACHE TC-Vega Alta SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:50 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1101 | FAASt number pending 5001101 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38kV Reclosers TLine 4800 SANTA ISABEL TC-AIBONITO TO] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:50 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1102 | FAASt number pending 5001102 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
817250 | 108117 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2] (Distribution) | 14F021420000 |  | Distribution – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [12 empty] | 2025-03-21 | 03/21/2025 | [6 empty] | 7610000 | 7610000 |  |  |  |  | 0 | 7610000 | 7610000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 817250RFI1103 | 817250 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38kV Reclosers TLine 3700 JOBOS TC to Humacao TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1104 | FAASt number pending 5001104 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38kV Reclosers TLine 2000 ONCE DE AGOSTO SECT to SAN SEBASTIAN TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1105 | FAASt number pending 5001105 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Pole and Conductor Repair -Mayaguez Group 5 - Phase 2 |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1106 | FAASt number pending 5001106 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38kV Reclosers TLine 1600 MAYAGUEZ GP to Acacias TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:51 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1107 | FAASt number pending 5001107 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20-21 - Phase 3 |  |  | Distribution – Pole Replacement |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:52 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1108 | FAASt number pending 5001108 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38kV Reclosers TLine 13400 ACACIAS TC-SAN GERMAN SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:52 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1109 | FAASt number pending 5001109 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38kV Reclosers TLine 12600 HUMACAO TC to VERDE MAR-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:52 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1110 | FAASt number pending 5001110 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38 kV ReclosersTLine 800 CAYEY TC to COMSAT SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:53 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1111 | FAASt number pending 5001111 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 2B-8 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:53 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1112 | FAASt number pending 5001112 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38 kV Reclosers TLine 8100 YAUCO 1 HP to Canas TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:53 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1113 | FAASt number pending 5001113 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 2C-10 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1114 | FAASt number pending 5001114 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38 kV Reclosers TLine 6500 TORO NEGRO 1 HP to Comerio TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1115 | FAASt number pending 5001115 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38 kV Reclosers TLine 5600 VICTORIA TC to AÑASCO TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1116 | FAASt number pending 5001116 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 2D-8 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1117 | FAASt number pending 5001117 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | 38 kV Reclosers TLine 1500 FAASt [38kV Recloser TL 1500-Yauco HP to San German TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:54 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1118 | FAASt number pending 5001118 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 2E-9 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:55 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1119 | FAASt number pending 5001119 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 4B- 6 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:57 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1120 | FAASt number pending 5001120 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 4C- 7 Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:57 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1121 | FAASt number pending 5001121 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 4D- 7Feeders] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:57 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1122 | FAASt number pending 5001122 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 46] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1123 | FAASt number pending 5001123 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 47] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1124 | FAASt number pending 5001124 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 48] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1125 | FAASt number pending 5001125 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 49] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1126 | FAASt number pending 5001126 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 50] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1127 | FAASt number pending 5001127 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 51] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1128 | FAASt number pending 5001128 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 52] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1129 | FAASt number pending 5001129 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 53] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1130 | FAASt number pending 5001130 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 54] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 16:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1131 | FAASt number pending 5001131 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 55] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:00 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1132 | FAASt number pending 5001132 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 56] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1133 | FAASt number pending 5001133 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 57] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1134 | FAASt number pending 5001134 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 58] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1135 | FAASt number pending 5001135 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 59] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1136 | FAASt number pending 5001136 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 60] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:01 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1137 | FAASt number pending 5001137 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 61] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:02 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1138 | FAASt number pending 5001138 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 62] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:02 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1139 | FAASt number pending 5001139 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 63] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:02 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1140 | FAASt number pending 5001140 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 64] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:02 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1141 | FAASt number pending 5001141 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 65] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1142 | FAASt number pending 5001142 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 66] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1143 | FAASt number pending 5001143 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 67] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:03 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1144 | FAASt number pending 5001144 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 68] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1145 | FAASt number pending 5001145 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 69] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1146 | FAASt number pending 5001146 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 70] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1147 | FAASt number pending 5001147 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 71] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1148 | FAASt number pending 5001148 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 72] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1149 | FAASt number pending 5001149 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 73] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:04 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1150 | FAASt number pending 5001150 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt number pending 500 |  | FAASt [Automation Program Group 74] (Distribution) |  |  | Grid Automation |  |  | FALSE |  |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-03-13 17:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1151 | FAASt number pending 5001151 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
825753 | 108133 | FAASt - EPC - [Guanica TC] (Substation) |  |  | Substation |  |  | FALSE |  |  | TRUE | [12 empty] | 2025-04-09 | 04/09/2025 | [6 empty] | 5750000 | [5 empty] | 0 | 5750000 | 5750000 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-10 13:01 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 825753RFI1152 | 825753 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | FAASt Caridad – XFMR MC 1714 (Substation) |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 5500000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:41 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1153 | Pending PREB Approval1153 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Transmission Access Roads |  |  | Transmission | To be allocated to appropriate program |  | FALSE |  |  | FALSE |  | Active |  | 16965451 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1154 | Pending PREB Approval1154 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 30428000 | 2021-06-08 | 2021-06-08 |  | 2021-07-08 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1155 | Pending PREB Approval1155 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 3000 Monacillos TC to Juncos TC |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 90440000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:48 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1156 | Pending PREB Approval1156 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 8900 Monacillos TC to Adm. Tribunal Apelaciones |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11510000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:51 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1157 | Pending PREB Approval1157 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders ‐ Caguas Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 44710000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:51 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1158 | Pending PREB Approval1158 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders ‐ Caguas Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 23640000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 12:53 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1159 | Pending PREB Approval1159 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders ‐ Ponce Short Term Group 2 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 42380000 | 2021-07-08 | 2021-08-20 |  | 2021-08-07 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1160 | Pending PREB Approval1160 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | 115 kV Transmission Priority Poles and Structures Replacements |  |  | Transmission | Transmission Priority Pole Replacements |  | FALSE |  |  | FALSE |  | Active |  | 318800000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1161 | Pending PREB Approval1161 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | 230 kV Transmission Priority Poles and Structures Replacements |  |  | Transmission | Transmission Priority Pole Replacements |  | FALSE |  |  | FALSE |  | Active |  | 31300000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:35 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1162 | Pending PREB Approval1162 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Fiber Optic Replacement |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  | FALSE |  |  | FALSE |  | Discontinued |  | 229500000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:36 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1163 | Pending PREB Approval1163 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 3600 Monacillos TC to Martin Peña TC |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 39980000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1164 | Pending PREB Approval1164 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Primary and Secondary Control Centers |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  | FALSE |  |  | FALSE |  | Discontinued |  | 84000000 | 2021-08-30 | 2021-09-22 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1165 | Pending PREB Approval1165 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Arecibo Region Repairs |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 9226902 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1166 | Pending PREB Approval1166 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Bayamon Region Repairs |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 15451304 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1167 | Pending PREB Approval1167 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Caguas Region Repairs |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 14472108 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1168 | Pending PREB Approval1168 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Mayaguez Region Repairs |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 13346360 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1169 | Pending PREB Approval1169 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Ponce Region Repairs |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 16300000 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:41 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1170 | Pending PREB Approval1170 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | San German Electrical Service Center |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 2478181 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:43 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1171 | Pending PREB Approval1171 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | San Juan Region Repairs |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 31028729 | 2021-08-30 | 2021-10-14 |  | 2021-09-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:44 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1172 | Pending PREB Approval1172 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 6700 Martin Peña TC to Villamar Sect. |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 6010000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:44 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1173 | Pending PREB Approval1173 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Bayview Sectionalizer 1802 Relocation |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 16700000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:45 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1174 | Pending PREB Approval1174 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Caguas TC |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 2500000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:45 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1175 | Pending PREB Approval1175 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Canas TC |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 1700000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1176 | Pending PREB Approval1176 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Dorado TC Relocation |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 40100000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1177 | Pending PREB Approval1177 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Fonalledas GIS Rebuilt 1401 1421 |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 31400000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:47 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1178 | Pending PREB Approval1178 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 4000 Comerio HP to Escuela Francisco Morales |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 22330000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 13:52 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1179 | Pending PREB Approval1179 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Santurce Planta (Sect) 1116 |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Discontinued |  | 9900000 | 2021-10-04 | 2021-10-18 |  | 2021-11-03 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1180 | Pending PREB Approval1180 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Isla Grande 1101 |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Discontinued |  | 600000 | 2022-01-24 | 2022-03-15 |  | 2022-02-23 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1181 | Pending PREB Approval1181 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Field Area Network(FAN) |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  | FALSE |  |  | FALSE |  | Active |  | 330000000 | 2022-01-24 | 2022-03-15 |  | 2022-02-23 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:03 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1182 | Pending PREB Approval1182 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 30360000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:04 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1183 | Pending PREB Approval1183 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 29040000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:35 | 2025-04-15 14:05 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1184 | Pending PREB Approval1184 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 36340000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:06 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1185 | Pending PREB Approval1185 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 3 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 34620000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:12 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1186 | Pending PREB Approval1186 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 31440000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:13 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1187 | Pending PREB Approval1187 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 23660000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:16 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1188 | Pending PREB Approval1188 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 30250000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:16 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1189 | Pending PREB Approval1189 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 27570000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1190 | Pending PREB Approval1190 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 30240000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:19 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1191 | Pending PREB Approval1191 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 26290000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:20 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1192 | Pending PREB Approval1192 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 29500000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1193 | Pending PREB Approval1193 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 23230000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:23 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1194 | Pending PREB Approval1194 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 30910000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:24 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1195 | Pending PREB Approval1195 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 35930000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:26 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1196 | Pending PREB Approval1196 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 29960000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:27 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1197 | Pending PREB Approval1197 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 31960000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:27 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1198 | Pending PREB Approval1198 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 24800000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:28 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1199 | Pending PREB Approval1199 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 32040000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:29 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1200 | Pending PREB Approval1200 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 13 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 23010000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1201 | Pending PREB Approval1201 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 14 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 34390000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1202 | Pending PREB Approval1202 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 31220000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1203 | Pending PREB Approval1203 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 33890000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:32 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1204 | Pending PREB Approval1204 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 31700000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:33 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1205 | Pending PREB Approval1205 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 19040000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:34 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1206 | Pending PREB Approval1206 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 15 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 29620000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:34 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1207 | Pending PREB Approval1207 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 13 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 25880000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:35 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1208 | Pending PREB Approval1208 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 22760000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:36 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1209 | Pending PREB Approval1209 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 14 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 25880000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1210 | Pending PREB Approval1210 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 24210000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1211 | Pending PREB Approval1211 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 34620000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1212 | Pending PREB Approval1212 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 25510000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1213 | Pending PREB Approval1213 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 26590000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1214 | Pending PREB Approval1214 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 24430000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:41 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1215 | Pending PREB Approval1215 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 30470000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:43 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1216 | Pending PREB Approval1216 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 23670000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:43 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1217 | Pending PREB Approval1217 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 3 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 33540000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:44 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1218 | Pending PREB Approval1218 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 13 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 20890000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:45 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1219 | Pending PREB Approval1219 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 22290000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1220 | Pending PREB Approval1220 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 31760000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:47 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1221 | Pending PREB Approval1221 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 29270000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:47 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1222 | Pending PREB Approval1222 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 25640000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:48 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1223 | Pending PREB Approval1223 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 21050000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:49 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1224 | Pending PREB Approval1224 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 16390000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:50 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1225 | Pending PREB Approval1225 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 23680000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:51 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1226 | Pending PREB Approval1226 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 20620000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:52 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1227 | Pending PREB Approval1227 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 24780000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:53 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1228 | Pending PREB Approval1228 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 32960000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:54 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1229 | Pending PREB Approval1229 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 26390000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:55 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1230 | Pending PREB Approval1230 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 32790000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:58 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1231 | Pending PREB Approval1231 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 26370000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:58 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1232 | Pending PREB Approval1232 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Discontinued |  | 24340000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 14:59 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1233 | Pending PREB Approval1233 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 17630000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1234 | Pending PREB Approval1234 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 25770000 | 2022-11-11 | 2022-12-10 |  | 2022-12-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1235 | Pending PREB Approval1235 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Protection Management Systems |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  | FALSE |  |  | FALSE |  | Active |  | 5800000 | 2022-11-16 | 2022-12-10 |  | 2022-12-16 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1236 | Pending PREB Approval1236 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Transmission and Distribution Automation Program Installation of Three Phase Reclosers, Single Phase Reclosers and Fault Circuit Indicators and Feeder Headend protection devices. |  |  | Distribution | Distribution Automation |  | FALSE |  |  | FALSE |  | Active |  | 469630000 | 2023-11-07 | 2023-11-27 |  | 2023-12-07 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:02 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1237 | Pending PREB Approval1237 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning ‐ Bayamón A |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 89400000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:06 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1238 | Pending PREB Approval1238 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning ‐ Bayamón C |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 64800000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:06 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1239 | Pending PREB Approval1239 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - Bayamón G |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 42200000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:07 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1240 | Pending PREB Approval1240 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - Bayamón F |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 119100000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:09 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1241 | Pending PREB Approval1241 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - San Juan A |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 120100000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:11 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1242 | Pending PREB Approval1242 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - San Juan B |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 58200000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:16 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1243 | Pending PREB Approval1243 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - San Juan C |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 150700000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:17 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1244 | Pending PREB Approval1244 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - San Juan D |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 71800000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1245 | Pending PREB Approval1245 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - San Juan F |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 30300000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1246 | Pending PREB Approval1246 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - San Juan G |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 39500000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1247 | Pending PREB Approval1247 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Area Planning - San Juan K |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 45400000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-15 15:19 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1248 | Pending PREB Approval1248 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Substation Component Replacement Program |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 330300000 | 2024-02-28 | 2024-03-13 |  | 2024-03-29 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:36 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1249 | Pending PREB Approval1249 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Substation Maunabo TC |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 96110000 | 2024-03-06 | 2024-03-27 |  | 2024-04-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1250 | Pending PREB Approval1250 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Substation Mayaguez TC |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 14400000 | 2024-03-06 | 2024-03-27 |  | 2024-04-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1251 | Pending PREB Approval1251 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Substation Morovis 8801 |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 5840000 | 2024-03-06 | 2024-03-27 |  | 2024-04-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:55 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1252 | Pending PREB Approval1252 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Venezuela Substation Transformer Replacement |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 3150000 | 2024-04-04 | 2024-05-22 |  | 2024-05-04 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:56 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1253 | Pending PREB Approval1253 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Adjuntas Pueblo 8.32 kV 8202-01 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 4500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:57 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1254 | Pending PREB Approval1254 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Aguada 7205-01 4.16 kV |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 13500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:57 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1255 | Pending PREB Approval1255 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Aguas Buenas 3701-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 5200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:58 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1256 | Pending PREB Approval1256 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Añasco 6101-04 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 12600000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:59 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1257 | Pending PREB Approval1257 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Añasco 6101-05 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 10500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 08:59 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1258 | Pending PREB Approval1258 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Bayamon TC 13 kV #1 1711-05 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 6000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1259 | Pending PREB Approval1259 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Bayamon TC 4 kV 1714-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 3750000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:00 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1260 | Pending PREB Approval1260 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Berwin 13 kV 1336-07 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:01 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1261 | Pending PREB Approval1261 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Buen Pastor 1908-03 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 20700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:02 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1262 | Pending PREB Approval1262 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Cachete 13 kV 1529-11 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 8100000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:03 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1263 | Pending PREB Approval1263 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Cana (Interamericana) 1719-15 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 7500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:04 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1264 | Pending PREB Approval1264 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Cana (Interamericana) 1719-18 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:04 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1265 | Pending PREB Approval1265 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Candelero 2604-01 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 12700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:05 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1266 | Pending PREB Approval1266 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Cerro las Mesas 6010-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 10500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:05 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1267 | Pending PREB Approval1267 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Coamo PDS 4603-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 12000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:07 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1268 | Pending PREB Approval1268 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeders Crea 1717-01 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 7500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:07 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1269 | Pending PREB Approval1269 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Cuatro Hermanos 6004-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 13900000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:08 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1270 | Pending PREB Approval1270 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Dorado Pueblo 8.32 kV 9202-04 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 9800000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:08 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1271 | Pending PREB Approval1271 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder El Abanico PDS 9605-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 20400000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:09 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1272 | Pending PREB Approval1272 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Encantada 1206-03 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 12700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:10 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1273 | Pending PREB Approval1273 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Fort Allen 5803-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 18000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:10 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1274 | Pending PREB Approval1274 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Grana PDS 1907-05 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 3000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:11 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1275 | Pending PREB Approval1275 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Hato Tejas 1713-05 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 12300000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:11 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1276 | Pending PREB Approval1276 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Humacao Pueblo 2601-01 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:12 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1277 | Pending PREB Approval1277 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Humacao TC 13 kV 2603-09 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 17600000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:13 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1278 | Pending PREB Approval1278 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Isabela Planta 3 7504-01 4.16 kV |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 6900000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:13 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1279 | Pending PREB Approval1279 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Juncos 3201-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 15000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:14 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1280 | Pending PREB Approval1280 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Llorens Torres 13 kV 1118-08 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 4200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:14 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1281 | Pending PREB Approval1281 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Llorens Torres 13 kV 1118-09 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 4500000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:15 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1282 | Pending PREB Approval1282 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Monacillos 13 kV 1346-03 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 8200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:15 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1283 | Pending PREB Approval1283 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Monterrey PDS 13 kV 9503-06 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:16 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1284 | Pending PREB Approval1284 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Peñuelas Pueblo 5401-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 8300000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:18 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1285 | Pending PREB Approval1285 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Rio Bayamon 1709-05 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11100000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:20 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1286 | Pending PREB Approval1286 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Rio Bayamon 1709-02 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 8200000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:21 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1287 | Pending PREB Approval1287 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder San Jose 8104-02 4.16 kV |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 12000000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1288 | Pending PREB Approval1288 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Unibon 9.32 kV 9501-01 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11300000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1289 | Pending PREB Approval1289 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Vega Baja TC 13 kV 9004-08 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 22800000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:31 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1290 | Pending PREB Approval1290 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Vega Baja TC 13 kV 9004-10 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 21400000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1291 | Pending PREB Approval1291 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Villa del Carmen 5016-01 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 11100000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1292 | Pending PREB Approval1292 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Sabana Grande 4.16 kV 6501-04 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 9700000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:45 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1293 | Pending PREB Approval1293 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Distribution Feeder Yabucoa Pueblo 2901-04 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 12770000 | 2024-04-05 | 2024-04-23 |  | 2024-05-05 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:46 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1294 | Pending PREB Approval1294 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Transmission Line 0700 Costa Sur SP to Yauco Pueblo 1 |  |  | Distribution | Distribution Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 24990000 | 2024-04-18 | 2024-05-07 |  | 2024-05-18 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 09:47 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1295 | Pending PREB Approval1295 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Bayamon TC - Rebuild |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 124500000 | 2024-06-13 | 2024-06-28 |  | 2024-07-13 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:22 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1296 | Pending PREB Approval1296 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | New Transmission Lines for System Resilience |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 321790000 | 2024-06-21 | 2024-06-28 |  | 2024-07-21 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:23 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1297 | Pending PREB Approval1297 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Asset Management System Implementation |  |  | IT and Telecommunications | IT OT Asset Management |  | FALSE |  |  | FALSE |  | Active |  | 9700000 | 2024-06-28 | 2024-07-24 |  | 2024-07-28 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:24 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1298 | Pending PREB Approval1298 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Building Island Wide Program |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Active |  | 97470000 | 2024-07-19 | 2024-08-08 |  | 2024-08-18 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:24 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1299 | Pending PREB Approval1299 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Victoria TC |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 61400000 | 2024-07-31 | 2024-08-22 |  | 2024-08-30 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:28 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1300 | Pending PREB Approval1300 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Arecibo Sectionalizer |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 46200000 | 2024-07-31 | 2024-08-22 |  | 2024-08-30 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1301 | Pending PREB Approval1301 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Venezuela Sectionalizer |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 43910000 | 2024-08-23 | 2024-08-28 |  | 2024-09-22 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:30 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1302 | Pending PREB Approval1302 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Caparra Sectionalizer |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 14200000 | 2024-08-23 | 2024-08-28 |  | 2024-09-22 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:33 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1303 | Pending PREB Approval1303 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | TL36200 – Monacillos TC to Juncos TC |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 84900000 | 2024-10-14 |  |  | 2024-11-13 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:33 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1304 | Pending PREB Approval1304 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 4100 Guaraguao TC to Comerío TC |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 72400000 | 2024-10-14 |  |  | 2024-11-13 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:34 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1305 | Pending PREB Approval1305 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 600 Caguas TC to Gautier Benitez Sect |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 26200000 | 2024-10-14 |  |  | 2024-11-13 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:34 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1306 | Pending PREB Approval1306 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Cambalache TC Relocation (Substation) |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 90100000 | 2024-10-14 |  |  | 2024-11-13 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1307 | Pending PREB Approval1307 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Line 36100 Dos Bocas HP to Monacillos TC Sections |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 178700000 | 2024-12-12 | 2025-02-07 |  | 2025-01-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:37 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1308 | Pending PREB Approval1308 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Santurce Planta Substations 1116 and 1117 |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 37700000 | 2024-12-12 | 2025-02-07 |  | 2025-01-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1309 | Pending PREB Approval1309 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Transmission Line 1100-Garzas 1 HP to Garzas 2 HP |  |  | Transmission | Transmission Line Rebuild |  | FALSE |  |  | FALSE |  | Active |  | 5200000 | 2024-12-12 | 2025-02-07 |  | 2025-01-11 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:38 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1310 | Pending PREB Approval1310 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Tranformer Replacements in Moncacillos TC, Costa Sur TC & Sabana LLana TC (System Improvements Plan) |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 44200000 | 2025-01-21 | 2025-02-06 |  | 2025-02-20 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:39 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1311 | Pending PREB Approval1311 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | System Improvement Plan – Replacement of Eight Transformers, Metalclad Switchgear, and GIS Repair |  |  | Substation | Substation Rebuilds |  | FALSE |  |  | FALSE |  | Active |  | 48400000 | 2025-02-25 | 2025-03-24 |  | 2025-03-27 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1312 | Pending PREB Approval1312 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Island-Wide Fiber Optic Repair & Replacement |  |  | Transmission |  |  | FALSE |  |  | FALSE |  | Active |  | 248000000 | 2025-03-14 |  |  | 2025-04-13 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1313 | Pending PREB Approval1313 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2 | [5 empty] | FALSE |  |  | FALSE |  |  |  | 882000 | [22 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-16 10:40 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1314 | Pending PREB Approval1314 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
Pending PREB Approval |  | Buildings - Aguadilla Electric Service Center |  |  | Building | Facilities Development & Implementation |  | FALSE |  |  | FALSE |  | Discontinued |  | 3500000 | 2021-04-28 | 2021-06-08 |  | 2021-05-28 | [18 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-04-17 12:02 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1315 | Pending PREB Approval1315 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
950482 | 108138 | FAASt [Feeder Rebuild #1710-03] (Distribution) | 14F000180000 |  | Distribution |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-05-07 | 05/07/2025 | [6 empty] | 4375640 | 4375640 |  |  |  |  | 0 | 4375640 | 4375640 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-05-08 09:34 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 950482RFI1316 | 950482 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild #6406-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:27 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1317 | FAASt Number Pending 6001317 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 3006-05] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:29 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1318 | FAASt Number Pending 6001318 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 6305-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:30 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1319 | FAASt Number Pending 6001319 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Feeder Rebuild # 1718-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:31 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1320 | FAASt Number Pending 6001320 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 1303-05] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:31 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1321 | FAASt Number Pending 6001321 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 1909-09] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:32 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1322 | FAASt Number Pending 6001322 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 3007-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1323 | FAASt Number Pending 6001323 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Distribution Feeder Rebuild #7805-11] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:33 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1324 | FAASt Number Pending 6001324 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 2603-08] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:34 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1325 | FAASt Number Pending 6001325 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 7805-13] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:34 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1326 | FAASt Number Pending 6001326 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Pole and Conductor Repair – Mayagüez Group 5 - Phase 2 |  |  | Distribution – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:35 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1327 | FAASt Number Pending 6001327 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20- 21 - Phase 3 |  |  | Distribution – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:35 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1328 | FAASt Number Pending 6001328 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 46] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1329 | FAASt Number Pending 6001329 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 47] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1330 | FAASt Number Pending 6001330 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 48] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1331 | FAASt Number Pending 6001331 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 49] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:36 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1332 | FAASt Number Pending 6001332 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 50] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1333 | FAASt Number Pending 6001333 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 51] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1334 | FAASt Number Pending 6001334 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 52] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1335 | FAASt Number Pending 6001335 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 53] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:37 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1336 | FAASt Number Pending 6001336 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 1B-6 Feeders] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:38 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1337 | FAASt Number Pending 6001337 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 4B- 6 Feeders] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:38 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1338 | FAASt Number Pending 6001338 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 54] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:40 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1339 | FAASt Number Pending 6001339 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 56] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:40 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1340 | FAASt Number Pending 6001340 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 55] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:40 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1341 | FAASt Number Pending 6001341 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 57] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:41 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1342 | FAASt Number Pending 6001342 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 58] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:41 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1343 | FAASt Number Pending 6001343 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 59] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:41 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1344 | FAASt Number Pending 6001344 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 60] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1345 | FAASt Number Pending 6001345 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 61] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1346 | FAASt Number Pending 6001346 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 62] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1347 | FAASt Number Pending 6001347 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 63] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1348 | FAASt Number Pending 6001348 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 4C- 7 Feeders] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:42 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1349 | FAASt Number Pending 6001349 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 4D7Feeders] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:43 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1350 | FAASt Number Pending 6001350 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 2A- 9 Feeders] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:43 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1351 | FAASt Number Pending 6001351 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 2B-8 Feeders] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1352 | FAASt Number Pending 6001352 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 2E-9 Feeders] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1353 | FAASt Number Pending 6001353 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 65] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1354 | FAASt Number Pending 6001354 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 66] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1355 | FAASt Number Pending 6001355 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 67] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1356 | FAASt Number Pending 6001356 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 68] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:44 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1357 | FAASt Number Pending 6001357 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 69] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1358 | FAASt Number Pending 6001358 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 70] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1359 | FAASt Number Pending 6001359 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 71] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1360 | FAASt Number Pending 6001360 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Automation Program Group 64] (Distribution) |  |  | Grid Automation |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:45 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1361 | FAASt Number Pending 6001361 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 1500 FAASt [38kV Recloser TL 1500-Yauco HP to San German TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1362 | FAASt Number Pending 6001362 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 5600 VICTORIA TC to AÑASCO TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1363 | FAASt Number Pending 6001363 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 6500 TORO NEGRO 1 HP to Comerio TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1364 | FAASt Number Pending 6001364 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 8100 YAUCO 1 HP to Canas TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1365 | FAASt Number Pending 6001365 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38kV Reclosers TLine 13400 ACACIAS TC- SAN GERMAN SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:47 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1366 | FAASt Number Pending 6001366 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 800 CAYEY TC to COMSAT SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:49 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1367 | FAASt Number Pending 6001367 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38kV Reclosers TLine 12600 HUMACAO TC to VERDE MAR-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:49 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1368 | FAASt Number Pending 6001368 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38kV Reclosers TLine 2000 ONCE DE AGOSTO SECT to SAN SEBASTIAN TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:49 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1369 | FAASt Number Pending 6001369 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38kV Reclosers TLine 1600 MAYAGUEZ GP to Acacias TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:50 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1370 | FAASt Number Pending 6001370 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | Recloser TL 100 Ponce to Jobos (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:50 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1371 | FAASt Number Pending 6001371 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 38kV Reclosers TLine 3700 JOBOS TC to Humacao TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:51 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1372 | FAASt Number Pending 6001372 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transport Network - Group 2] (Telecommunication) |  |  | IT & Telecommunications |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:51 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1373 | FAASt Number Pending 6001373 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | Hato Rey – Phase I |  |  | Substation |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:52 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1374 | FAASt Number Pending 6001374 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 36100 - Ciales to Morovis |  |  | Transmission |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:53 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1375 | FAASt Number Pending 6001375 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 36100 - Morovis to Unibon |  |  | Transmission |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:54 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1376 | FAASt Number Pending 6001376 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Line 36100 Dos Bocas to Ciales] (Transmission) |  |  | Transmission |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:54 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1377 | FAASt Number Pending 6001377 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Line 36100 Cana to Bayamón] (Transmission) |  |  | Transmission |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1378 | FAASt Number Pending 6001378 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 36100 - Unibon to Monterrey |  |  | Transmission |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1379 | FAASt Number Pending 6001379 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 36100 - Monterrey to Pina |  |  | Transmission |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1380 | FAASt Number Pending 6001380 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 2200 - Manatí to Vega Baja |  |  | Transmission |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1381 | FAASt Number Pending 6001381 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | 2200 - Vega Baja to San Demetrio |  |  | Transmission |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:58 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1382 | FAASt Number Pending 6001382 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 1600 LEON SECTACACIAS TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1383 | FAASt Number Pending 6001383 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC - Santa Isabel Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 15:59 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1384 | FAASt Number Pending 6001384 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 9900 - RIO BLANCO HPHUMACAO SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:00 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1385 | FAASt Number Pending 6001385 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2000 - ONCE DE AGOSTO SECT - SAN SEBASTIAN TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:00 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1386 | FAASt Number Pending 6001386 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line Arecibo Region Group 1 (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-07-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:00 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1387 | FAASt Number Pending 6001387 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line San Juan Region Group 1] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-08-31 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:03 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1388 | FAASt Number Pending 6001388 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line Mayagüez Region Group1] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1389 | FAASt Number Pending 6001389 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 1200 SAN GERMAN SECT-SAN GERMAN TCYAUCO 2 HP] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1390 | FAASt Number Pending 6001390 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 200 Ponce TC -Santa Isabel Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1391 | FAASt Number Pending 6001391 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC - Santa Isabel Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1392 | FAASt Number Pending 6001392 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 10700 - HATO TEJAS TCHATO TEJAS SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1393 | FAASt Number Pending 6001393 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 18400 - BARRANQUITAS TC-EL ABANICO] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1394 | FAASt Number Pending 6001394 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2200 -BARCELONETA TC-MANATI TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:05 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1395 | FAASt Number Pending 6001395 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2200 - VEGA BAJA TCVEGA ALTA SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:06 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1396 | FAASt Number Pending 6001396 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 9900 - RIO BLANCO HPHUMACAO SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:06 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1397 | FAASt Number Pending 6001397 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 1600 - SAN GERMAN SECT-SAN GERMAN TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:07 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1398 | FAASt Number Pending 6001398 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 8100 - YAUCO 1 HPADJUNTAS TO] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:07 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1399 | FAASt Number Pending 6001399 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 15900-VICTORIA TCAGUADA TO] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:07 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1400 | FAASt Number Pending 6001400 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2700 - Aguadilla Hospital Distrito Sect - Mora TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  | TRUE | 2025-09-30 |  | FALSE | [26 empty] | 0 | 0 | 0 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:07 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1401 | FAASt Number Pending 6001401 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956353 | 108158 | FAASt [Arecibo Region 2 Transmission Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-26 | [5 empty] | 37008593.33 | 37008593.33 | 27126607.1 | 757937.79 | 9124048.44 | 2079717.62 | 25046889.48 | 36250655.54 | 37008593.33 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1672/Signed%20956353%20FAASt%20Arecibo%20Region%202%20Transmission%20Line%2036100%20%E2%80%93%20Dos%20Bocas%20HP%20to%20Barrio%20Pina%20(Vegetation).pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-12 16:08 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956353RFI1402 | 956353 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956342 | 108153 | FAASt [Arecibo Region 2 Transmission Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-26 | [5 empty] | 44397505.59 | 44397505.59 | 32542541.69 | 909263.06 | 10945700.85 | 2494941.49 | 30047600.2 | 43488242.54 | 44397505.6 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1673/Signed%20956342%20FAASt%20Arecibo%20Region%202%20Transmission%20Line%2036400%20%E2%80%93%20Ponce%20TC%20to%20Dos%20Bocas%20HP%20(Vegetation).pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-12 16:09 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956342RFI1403 | 956342 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956348 | 108156 | FAASt [Bayamon Region 3 Transmission Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-26 | [5 empty] | 1193764.74 | 1193764.74 | 875007.19 | 24448.38 | 294309.16 | 67084.2 | 807922.99 | 1169316.35 | 1193764.73 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1674/Signed%20956348%20FAASt%20Bayamon%20Region%203%20Transmission%20Line%2010000%20%E2%80%93%20Bayamon%20Pueblo%20to%20Magnolia%20TO%20(Vegetation).pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-12 16:09 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956348RFI1404 | 956348 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956349 | 108157 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-26 | [5 empty] | 13853576.49 | 13853576.49 | 10154412.56 | 283721.94 | 3415441.98 | 778509.08 | 9375903.48 | 13569854.54 | 13853576.48 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1675/Signed%20956349%20FAASt%20San%20Juan%20Region%201%20Transmission%20Line%2036800%20%E2%80%93%20Canovanas%20TC%20to%20Palmer%20TC%20(Vegetation).pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-12 16:09 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956349RFI1405 | 956349 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956345 | 108155 | FAASt [Arecibo Region 2 Transmission Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-26 | [5 empty] | 7324652.18 | 7324652.18 | 5368833.09 | 150009.25 | 1805809.83 | 411612.69 | 4957220.4 | 7174642.92 | 7324652.17 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1676/Signed%2095634%20FAASt%20Arecibo%20Region%202%20Transmission%20Line%202400%20Dos%20Bocas%20HP%20to%20Coronillas%202%20Vegetation.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-12 16:09 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956345RFI1406 | 956345 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956357 | 108160 | FAASt [Mayaguez Region 5 Transmission Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-06-18 | 06/18/2025 | 2025-06-26 | [5 empty] | 12705648.38 | 12705648.38 | 9313002.71 | 260212.32 | 3132433.36 | 714000.65 | 8599002.06 | 12445436.07 | 12705648.39 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1677/Signed%20956357%20FAASt%20Mayaguez%20Region%205%20Transmission%20Line%201900%20%E2%80%93%20Dos%20Bocas%20HP%20to%20San%20Sebastian%20TC%20(Vegetation).pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-12 16:09 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956357RFI1407 | 956357 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956343 | 108154 | FAASt [Ponce Region 6 Transmission Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-26 | [5 empty] | 21381353.56 | 21381353.56 | 15672132.45 | 437891.18 | 5271329.93 | 1201536.52 | 14470595.93 | 20943462.38 | 21381353.56 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1678/Signed%20956343%20FAASt%20Ponce%20Region%206%20Transmission%20Line%204800%20%E2%80%93%20Toro%20Negro%20to%20Aibonito,%20Santa%20Isabel%20(Vegetation).pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-12 16:10 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956343RFI1408 | 956343 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956356 | 108159 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) |  |  | Vegetation |  |  | TRUE | 2025-07-31 |  | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-26 | [5 empty] | 3583135.14 | 3583135.14 | 2626357.86 | 113371.85 | 843405.43 | 311082.75 | 2315275.11 | 3469763.29 | 3583135.14 | [10 empty] | 0 | 0 |  |  |  | 2025-07-18 18:36 | 2025-06-12 16:10 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0327 | 1 |  | 956356RFI1409 | 956356 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
954184 | 108144 | FAASt [Carolina ESC Building Repairs] (Buildings) |  |  | Building |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-06-16 | 06/16/2025 | 2025-06-16 | 2025-07-07 | 2025-08-06 | 2025-07-23 |  |  | 2747126.23 | 2747126.23 | 0 | 293002.71 | 2454123.52 | 0 | 0 | 2454123.52 | 2747126.23 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1681/954184-DR4339PR-Carolina%20Electric%20Service%20Center%20Detailed%20Scope%20of%20Work%20-%20DRAFT.docx?web=1 |  | 2025-07-23 16:10 | 2025-06-18 15:06 | Marlina Crespo |  | Maria Mujica Gonzalez |  |  |  |  | 1.1194 | 1 |  | 954184RFI1410 | 954184 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956341 | 108152 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 06/18/2025 | 2025-06-27 | [5 empty] | 97672.18 | 97672.18 | 71591.83 | 2000.35 | 24080 | 5488.7 | 66103.13 | 95671.83 | 97672.18 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1682/956341%20FAASt%20Single%20Line%20DSOW%20Feeder%205803-02%20Ponce%20Region%206%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:02 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956341RFI1411 | 956341 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956340 | 108151 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-27 | [5 empty] | 6589894.87 | 6589894.87 | 4830269.73 | 1624663.76 | 134961.38 | 4830269.73 | 0 | 4965231.11 | 6589894.87 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1683/956340%20FAASt%20Single%20Line%20DSOW%20Feeder%205602-02%20Ponce%20Region%206%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:25 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 1.3272 | 1 |  | 956340RFI1412 | 956340 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956339 | 108150 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | [6 empty] | 12004333.95 | 12004333.95 | 8798952.37 | 2959532.24 | 245849.34 | 8798952.37 | 0 | 9044801.71 | 12004333.95 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1684/956339%20FAASt%20Single%20Line%20DSOW%20Feeder%203301-01%20Caguas%20Region%204%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:26 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 1.3272 | 1 |  | 956339RFI1413 | 956339 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956337 | 108149 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | [6 empty] | 7303974.78 | 7303974.78 | 5353676.97 | 149585.76 | 1800712.05 | 410450.73 | 4943226.24 | 7154389.02 | 7303974.78 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1685/956337%20FAASt%20Single%20Line%20DSOW%20Feeder%206012-02%20Mayaguez%20Region%205%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:28 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956337RFI1414 | 956337 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956335 | 108148 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-27 | [5 empty] | 7503713.1 | 7503713.1 | 5500081.4 | 153676.43 | 1849955.27 | 421675.11 | 5078406.29 | 7350036.67 | 7503713.1 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1686/956335%20FAASt%20Single%20Line%20DSOW%20Feeder%202301-02%20San%20Juan%20Region%201%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:29 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956335RFI1415 | 956335 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956332 | 108147 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-27 | [5 empty] | 11073220.77 | 11073220.77 | 8286164.87 | 231521.7 | 2787055.9 | 635275.99 | 7650888.88 | 11073220.77 | 11304742.47 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1687/956332%20FAASt%20Single%20Line%20DSOW%20Feeder%202401-01%20San%20Juan%20Region%201%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:30 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 956332RFI1416 | 956332 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956331 | 108146 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-27 | [5 empty] | 8021552.35 | 8021552.35 | 5879647.9 | 1977622.66 | 164281.79 | 5879647.9 | 0 | 6043929.69 | 8021552.35 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1688/956331%20FAASt%20Single%20Line%20DSOW%20Feeder%206014-02%20Mayaguez%20Region%205%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:31 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 1.3272 | 1 |  | 956331RFI1417 | 956331 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956330 | 108145 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) |  |  | Vegetation |  |  | FALSE |  | Current | FALSE | [12 empty] | 2025-06-18 | 6/18/2025 | 2025-06-27 | [5 empty] | 7985860.15 | 7985860.15 | 5853486.17 | 163550.83 | 1968823.15 | 448769.62 | 5404716.55 | 7822309.32 | 7985860.15 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1689/956330%20FAASt%20Single%20Line%20DSOW%20Feeder%203007-03%20Caguas%20Region%204%206-27-25.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-18 16:33 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez |  |  |  |  | 1.0209 | 1 |  | 956330RFI1418 | 956330 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956593 | 108161 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) |  |  | Substation |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-06-23 | 06/23/2025 | 2025-06-23 |  | 2025-08-06 | 2025-07-25 | Field EHP - Environmental: In review. Amended Expected Completion Date (ECD) 08/06/2025. |  | 5907319.61 | 5907319.61 | 0 | 414861.11 | 5492458.5 | 0 | 0 | 5492458.5 | 5907319.61 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1690/DR4339PR%20-%20Detail%20Scope%20of%20Work%20for%20Factor%20Sectionalizer%20signed%20(6.19.2025)%20(003).pdf?web=1 |  | 2025-07-28 15:53 | 2025-06-24 09:46 | Marlina Crespo |  | Maria Mujica Gonzalez |  |  |  |  | 1.0755 | 1 |  | 956593RFI1419 | 956593 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
956782 | 108162 | Feeder Rebuild #6802-04 (Distribution) |  |  | Distribution – Feeder Rebuild |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-06-25 | 06/25/2025 | 2025-06-25 | [5 empty] | 21957625.63 | 21957625.63 | 2769954.18 | 2489006.38 | 19468619.25 | 313928.68 | 2456025.5 | 22238573.43 | 24727579.81 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1691/956782-DR4339PR-6802-04%20DSOW%20Full%20428-406_06212025%20Rev%200.pdf?web=1 |  | 2025-07-18 18:36 | 2025-06-26 09:36 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0.98737 | 1 |  | 956782RFI1420 | 956782 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
957578 | 108163 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) |  |  | Substation |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-07-07 | 07/07/2025 | 2025-07-15 |  | 2025-08-16 | 2025-07-16 | Field EHP: Previous EHP Status applies. ECD stays the same. |  | 1250845.17 | 1250845.17 | 0 | 141856.25 | 1108989.51 | 0 | 0 | 1108989.51 | 1250845.76 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1692/957578%20-%20Costa%20Sur%20TC%20Underground%20Cable%20Failure%20Replacement%20on%20Transformer%20Lead%20Bank%202%20DSOW%20(7.15.2025)%20signed.pdf?web=1 |  | 2025-07-28 16:19 | 2025-07-09 09:23 | Marlina Crespo |  | Maria Mujica Gonzalez |  |  |  |  | 1.1279 | 1 |  | 957578RFI1421 | 957578 | Item | sites/Test4552/Lists/ISOW DSOW Tracker
958367 | 108164 | FAASt [Feeder Rebuild #6603-01] (Distribution) |  |  | Distribution |  |  | FALSE |  |  | FALSE | [12 empty] | 2025-07-15 | 07/15/2025 | 2025-07-15 | [5 empty] | 14474191.76 | 14474191.76 | 1172038.62 | 2885305.81 | 11588885.95 | 233606.49 | 938432.13 | 12760924.57 | 15646230.38 | [10 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1694/958367-DR4339PR-6603-01%20Detail%20Scope%20of%20Work%20Full%20428%20-%20406%20Rev_0.pdf?web=1 |  | 2025-07-18 18:36 | 2025-07-16 09:43 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 1.1343 | 1 |  | qwer506 | 958367 | Item | sites/Test4552/Lists/ISOW DSOW Tracker

## Rolando DATA Work Completed (hidden)
Program Brief | Project Financial Number | Project Name | 9510 | Project Specific | Total | GP Project Name | FAASt | PW
n/a | 10F000180000 | Category B - PREPA Support | $- | 308 | 308 | 0 | 0 | 0
n/a | 10F000230000 | FEMA A&E Legal Support | 435 | 2011 | 2446 | 0 | 0 | 0
n/a | 10F000240000 | FEMA A&E Procurement Support | 5841 | 13440 | 19281 | 0 | 0 | 0
n/a | 14F004320000 | HSE Program Management | 82135 | 8957 | 91092 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 10F000140000 | FMS Aguadilla Contact Center | 38966 | 861 | 39827 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 10F000150000 | FMS Hormigerous Contact Cent | 19618 | 789 | 20407 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 10F000160000 | FMS Humacao Contact Centre | 59143 | 1220 | 60364 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 10F000170000 | FMS Ponce Contact Centre | 37865 | 4295 | 42161 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 10F000430000 | FMS-Tenant Broker Rep FF Proj | 362 | $- | 362 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 14F001950000 | FAASt Arecibo Regional Off | 7662 | 499 | 8161 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 14F001960000 | FAASt Arecibo Electric Serv | 8626 | 681 | 9306 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 14F001970000 | FAASt Aguadilla Electric Serv | 3140 | $- | 3140 | FAASt Aguadilla Electric Service Center (Building) | 169804 | 107227
PBFM1 Facilities Dev & Implem | 14F001980000 | San GermÃ¡n ESC. | 26804 | $- | 26804 | FAASt [San German Electrical Service Center] (Building) | 548596 | 107708
PBFM1 Facilities Dev & Implem | 14F001990000 | Arecibo Regional Repairs | 7698 | 42 | 7740 | FAASt Arecibo Region Repairs (Buildings) | 548393 | 107705
PBFM1 Facilities Dev & Implem | 14F002000000 | Palo Seco South | $- | 30885 | 30885 | FAASt [Palo Seco South Building Repairs] (Building) | 551247 | 11570
PBFM1 Facilities Dev & Implem | 14F002010000 | Bayamon Regional Repairs | 49122 | 143 | 49265 | FAASt [Bayamon Region Repairs] (Building) | 551242 | 107726
PBFM1 Facilities Dev & Implem | 14F002020000 | Caguas Regional Repairs | 11203 | 2665 | 13868 | FAASt [Caguas Region Repairs] (Building) | 550060 | 107711
PBFM1 Facilities Dev & Implem | 14F002030000 | San Juan Regional Repairs | 11066 | 1313 | 12379 | FAASt [San Juan Region Repair] (Building) | 551827 | 107732
PBFM1 Facilities Dev & Implem | 14F002040000 | Mayaguez Regional Repairs | 14271 | 5833 | 20104 | FAASt [Mayaguez Region Repairs] (Building) | 548440 | 107707
PBFM1 Facilities Dev & Implem | 14F002050000 | Ponce Regional Repairs | 28640 | 406 | 29046 | FAASt - Ponce Region Repairs (Building) | 550500 | 107718
PBFM1 Facilities Dev & Implem | 14F003770000 | FMS - Primary Contact Centre | 166183 | 1038 | 167221 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 14F003920000 | Test and Technology Laboratory | $- | 70791 | 70791 | FAASt [Test and Technology Laboratory] (Building) | 679006 | 11862
PBFM1 Facilities Dev & Implem | 14F015260000 | FMS-Aviation Hangar BusnssCase | 2545 | 90 | 2634 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | 14F017420000 | FMS-LUMA EmerOperCentNewBldng | 372 | 179 | 551 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | PBFM1-F00000 | 0 | -150560 | $- | -150560 | 0 | 0 | 0
PBFM1 Facilities Dev & Implem | PBFM1-N00000 | 0 | 150560 | $- | 150560 | 0 | 0 | 0
PBIT1 Telecom Sys & Network | 14F002090000 | FIELD AREA NETWORK (FAN). | 2219713 | 502945 | 2722658 | FAASt [Field Area Network (FAN)] (Telecommunication) | 674506 | 107765
PBIT1 Telecom Sys & Network | 14F002100000 | TELECOM INFRASTRUCTUR | 231365 | 3128 | 234494 | 0 | 0 | 0
PBIT1 Telecom Sys & Network | 14F002140000 | Transport Network | $- | 1901232 | 1901232 | FAASt [Transport Network Group 1] (Telecommunication) | 551963 | 11859
PBIT1 Telecom Sys & Network | 14F003600000 | Fiber Optics Replacement -FEMA | 737787 | 616392 | 1354179 | 0 | 0 | 0
PBIT1 Telecom Sys & Network | 14F003900000 | LMR Two Way Radio | 446873 | 4885 | 451758 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) | 675406 | 107767
PBIT1 Telecom Sys & Network | 14F004430000 | RTU-Telecom ReplGrp1-Mayaguez | 168492 | 10706 | 179198 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) | 682331 | 107777
PBIT1 Telecom Sys & Network | 14F004500000 | Microwave Network Upgrade | $- | 200109 | 200109 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 662238 | 107742
PBIT1 Telecom Sys & Network | 14F004510000 | Telecom Infrast-Cerro Puntas | $- | 133849 | 133849 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 673292 | 11452
PBIT1 Telecom Sys & Network | 14F004550000 | El Yunque - Group A | 169695 | 38885 | 208580 | FAASt [Telecom Infrastructure – Group A] (Telecommunication) | 679035 | 11861
PBIT1 Telecom Sys & Network | 14F004560000 | Santa Ana - Group A | 129222 | 35972 | 165194 | FAASt [Telecom Infrastructure – Group A] (Telecommunication) | 679035 | 11861
PBIT1 Telecom Sys & Network | 14F004570000 | Santurce Luchetti - Group A | 126954 | 37452 | 164406 | FAASt [Telecom Infrastructure – Group A] (Telecommunication) | 679035 | 11861
PBIT1 Telecom Sys & Network | 14F004580000 | Atalaya - Group B | $- | 101938 | 101938 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 678800 | 11425
PBIT1 Telecom Sys & Network | 14F004590000 | El Gato - Group B | $- | 84917 | 84917 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 678800 | 11425
PBIT1 Telecom Sys & Network | 14F004600000 | Isabela - Group B | $- | 90659 | 90659 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 678800 | 11425
PBIT1 Telecom Sys & Network | 14F004610000 | La Santa - Group B | $- | 85943 | 85943 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 678800 | 11425
PBIT1 Telecom Sys & Network | 14F004620000 | Manati TC - Group B | $- | 51813 | 51813 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 678800 | 11425
PBIT1 Telecom Sys & Network | 14F004640000 | El ManÃ­ - Group C | 1546 | $- | 1546 | FAASt [Telecom Infrastructure – Group C] (Telecommunication) | 704763 | 107825
PBIT1 Telecom Sys & Network | 14F004650000 | Juana Diaz Loma - Group C | 26675 | 6676 | 33351 | FAASt [Telecom Infrastructure – Group C] (Telecommunication) | 704763 | 107825
PBIT1 Telecom Sys & Network | 14F004660000 | Monacillo TC- Group C | 10024 | 1444 | 11469 | FAASt [Telecom Infrastructure – Group C] (Telecommunication) | 704763 | 107825
PBIT1 Telecom Sys & Network | 14F008600000 | Fajardo Tecnica-Group D | 96574 | 62874 | 159448 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 704805 | 11863
PBIT1 Telecom Sys & Network | 14F008610000 | Humacao Tecnica-Group D | 87860 | 59950 | 147809 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 704805 | 11863
PBIT1 Telecom Sys & Network | 14F008620000 | Mayaguez (Mckinley)-Group D | 71414 | 57385 | 128799 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 704805 | 11863
PBIT1 Telecom Sys & Network | 14F008630000 | Sabana Llana TC-Group D | 16231 | 2437 | 18668 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 704805 | 11863
PBIT1 Telecom Sys & Network | 14F008930000 | Mora TC-Group E | $- | 131884 | 131884 | FAASt [Telecom Infrastructure – Group E] (Telecommunication) | 814792 | 108105
PBIT1 Telecom Sys & Network | 14F009010000 | Quebradillas TÃ©cnica-Group E | $- | 114449 | 114449 | FAASt [Telecom Infrastructure – Group E] (Telecommunication) | 814792 | 108105
PBIT1 Telecom Sys & Network | 14F009020000 | San SebastiÃ¡n TC-Group E | $- | 102123 | 102123 | FAASt [Telecom Infrastructure – Group E] (Telecommunication) | 814792 | 108105
PBIT1 Telecom Sys & Network | 14F012500000 | Telecom Infrastructure Grupo D | 2976 | 8102 | 11078 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 704805 | 11863
PBIT1 Telecom Sys & Network | 14F013950000 | Culebra 3801 Telecomm Tower | 16204 | 927 | 17131 | 0 | 0 | 0
PBIT1 Telecom Sys & Network | 14F019040000 | Telco Infra Guanica Group F | $- | 108592 | 108592 | FAASt [Telecom Infrastructure – Group F] (Telecommunication) | 814793 | 108106
PBIT1 Telecom Sys & Network | 14F019050000 | Telco Infra Barranquita GroupF | $- | 112176 | 112176 | FAASt [Telecom Infrastructure – Group F] (Telecommunication) | 814793 | 108106
PBIT1 Telecom Sys & Network | 14F019060000 | Telco Infra Barceloneta GroupF | $- | 90173 | 90173 | FAASt [Telecom Infrastructure – Group F] (Telecommunication) | 814793 | 108106
PBIT1 Telecom Sys & Network | 14F020210000 | Telco Infra AguasBuenasGroup H | 4915 | 8523 | 13438 | 0 | 0 | 0
PBIT1 Telecom Sys & Network | 14F020220000 | Telco Infra Utuado Tec Group H | 4755 | 11827 | 16582 | 0 | 0 | 0
PBIT1 Telecom Sys & Network | 14F020230000 | Telco Infra Manati Tec Group H | 4144 | 11035 | 15179 | 0 | 0 | 0
PBIT1 Telecom Sys & Network | 14F020240000 | Telco Infra Canov TC Group G | $- | 9731 | 9731 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | 753302 | 108004
PBIT1 Telecom Sys & Network | 14F020250000 | Telco Infra Juncos TC Group G | $- | 8781 | 8781 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | 753302 | 108004
PBIT1 Telecom Sys & Network | 14F020260000 | TelcoInfraS.IsabelTecnicaGrpG | 5479 | 8486 | 13966 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000060000 | Netwk EnhancmtsÂ - CAPEX FEMA | 94010 | 54485 | 148495 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000070000 | SDWAN Ntwrk Intg-CAPEX FEMA | 44151 | 1711 | 45862 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000080000 | PBX Replcmnt - CAPEX FEMA | 67749 | 28840 | 96589 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000120000 | Informational Technology | 109188 | 11256 | 120444 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000130000 | Operational Technology (Capex) | 223382 | 754 | 224136 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000190000 | Mass Storage&Backup Appliances | 148496 | 487 | 148983 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000340000 | HW Upg legacy equip-CPEX FEMA | 6910 | 1745 | 8655 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000350000 | TelCom Dev IT sensor-CAP FEMA | 1565 | 998 | 2564 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000360000 | WiFi 6 Integration- CAPEX | 255893 | 2548 | 258441 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000370000 | GPS Clock install - CAPEX FEMA | 37946 | 404 | 38350 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000380000 | Situational Awrness CAPEX FEMA | 21218 | 1103 | 22321 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000390000 | Ntwk Prof OMS CAPEX FEMA | 352499 | 6023 | 358522 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000400000 | Map Mgtion-Gtch OMS CPEX FMA | 50347 | 5818 | 56165 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000410000 | Cyber Sec System CAPEX FEMA | 12796 | 184 | 12980 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 10F000450000 | WFMS Intermediate Comms | 851181 | 96 | 851277 | 0 | 0 | 0
PBIT4 IT OT Asset Management | 14F003610000 | DR (IT) Facility Reloc FEMA | 25984 | 1643 | 27627 | 0 | 0 | 0
PBOP1 T&D Fleet | 10F000090000 | OPFLT10 FleetShopToolEq(Small) | -207 | $- | -207 | 0 | 0 | 0
PBOP1 T&D Fleet | 14F003650000 | OPFLT15 Fuel Tank Fleet Shop | 0 | $- | 0 | 0 | 0 | 0
PBOP6 Materials Management | 10F000100000 | OPMAT8 Fed WOilFiEqOilC(Small) | 8332 | 19232 | 27564 | 0 | 0 | 0
PBOP6 Materials Management | 10F000110000 | OPMAT16 Fed-WarFacImpr CapPlan | 1933 | 97 | 2030 | 0 | 0 | 0
PBOP6 Materials Management | 14F008760000 | FEMA Equipment & Materials PW | 37476 | $- | 37476 | FAASt [Equipment and Materials] (E&M) | 673691 | 10710
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019290000 | Vgtn - SJ - Substations/Tlcom | $- | $- | $- | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | 741097 | 107940
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019330000 | Vegetation - SJ - Group C | $- | 217 | 217 | FAASt [Region 1 -San Juan Group C] (Vegetation) | 727691 | 107902
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019340000 | Vegetation-Ponce-Substatn/Tele | $- | $- | $- | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | 741104 | 107945
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019360000 | Vegetation - Ponce - 115kV | $- | $- | $- | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 727529 | 107893
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019370000 | Vegetation - Ponce - Group B | $- | 217 | 217 | FAASt [Region 6-Ponce Group B] (Vegetation) | 740414 | 107938
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019380000 | Vegetation - Ponce - Group C | $- | $- | $- | FAASt [Region 6 -Ponce Group C] (Vegetation) | 727530 | 107894
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019390000 | Vegetation-Mayagu-Substn/Tlcom | 0 | $- | 0 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | 741102 | 107944
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019410000 | Vegetation - Mayaguez - 115kV | 0 | $- | 0 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 727657 | 107900
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019430000 | Vegetation - Mayaguez-Group C | $- | $- | $- | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | 727562 | 107897
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019440000 | Vegetation-Caguas-Sbstns/Tlcom | $- | $- | $- | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | 741100 | 107942
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019460000 | Vegetation - Caguas - 115kV | 0 | $- | 0 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 727606 | 107898
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019480000 | Vegetation - Caguas - Group C | $- | $- | $- | FAASt [Region 4 -Caguas Group C] (Vegetation) | 727694 | 107903
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019490000 | Vegetation-Bayamon-Sbstn/Tlcom | 0 | $- | 0 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | 741098 | 107941
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019510000 | Vegetation - Bayamon - 115kV | 14 | $- | 14 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 727522 | 107892
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019530000 | Vegetation - Bayamon - Group C | 6 | $- | 6 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | 727558 | 107896
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019540000 | Vegetation-Arecibo-Sbstn/Tlcom | $- | $- | $- | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | 741101 | 107943
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019560000 | Vegetation - Arecibo - 115kV | $- | $- | $- | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 727659 | 107901
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019580000 | Vegetation - Arecibo - Group C | 0 | $- | 0 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | 727540 | 107895
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 14F019590000 | Vegetation - All Regions-230kV | $- | $- | $- | FAASt [All Regions TL - 230kV] (Vegetation) | 741105 | 107946
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019290000 | Vgtn -SJ - Substations/Tlcom | $- | 7059 | 7059 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | 741097 | 107940
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019310000 | Vegetation -San Juan - 115kV | $- | 10422 | 10422 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 727608 | 107899
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019320000 | Vegetation -SJ - Group B | $- | 13305 | 13305 | FAASt [Region 1-San Juan Group B] (Vegetation) | 740406 | 107933
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019330000 | Vegetation -SJ - Group C | $- | 35050 | 35050 | FAASt [Region 1 -San Juan Group C] (Vegetation) | 727691 | 107902
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019340000 | Vegetation-Ponce-Substat/Tele | $- | 4437 | 4437 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | 741104 | 107945
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019350000 | Vegetation -Ponce - Group A | $- | 71708 | 71708 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 750063 | 107965
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019360000 | Vegetation -Ponce - 115kV | $- | 3266 | 3266 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 727529 | 107893
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019370000 | Vegetation -Ponce - Group B | $- | 6848 | 6848 | FAASt [Region 6-Ponce Group B] (Vegetation) | 740414 | 107938
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019380000 | Vegetation -Ponce - Group C | $- | 5028 | 5028 | FAASt [Region 6 -Ponce Group C] (Vegetation) | 727530 | 107894
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019390000 | Vegetation-Mayag-Substn/Tlcom | $- | 7137 | 7137 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | 741102 | 107944
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019400000 | Vegetation-Mayaguez -Group A | $- | 66702 | 66702 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 750068 | 107969
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019410000 | Vegetation -Mayaguez - 115kV | $- | 3940 | 3940 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 727657 | 107900
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019420000 | Vegetation -Mayaguez -Group B | $- | 5888 | 5888 | FAASt [Region 5-Mayaguez Group B] (Vegetation) | 740411 | 107937
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019430000 | Vegetation -Mayaguez-Group C | $- | 5451 | 5451 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | 727562 | 107897
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019440000 | Vegetation-Cagua-Sbstns/Tlcom | $- | 3227 | 3227 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | 741100 | 107942
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019450000 | Vegetation -Caguas - Group A | $- | 69618 | 69618 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 750066 | 107967
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019460000 | Vegetation -Caguas - 115kV | $- | 13748 | 13748 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 727606 | 107898
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019470000 | Vegetation -Caguas - Group B | $- | 7587 | 7587 | FAASt [Region 4-Caguas Group B] (Vegetation) | 740409 | 107935
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019480000 | Vegetation -Caguas - Group C | $- | 4800 | 4800 | FAASt [Region 4 -Caguas Group C] (Vegetation) | 727694 | 107903
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019490000 | Vegetation-Bayam-Sbstn/Tlcom | $- | 7804 | 7804 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | 741098 | 107941
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019500000 | Vegetation -Bayamon - Group A | $- | 123030 | 123030 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 750065 | 107966
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019510000 | Vegetation -Bayamon - 115kV | $- | 1968 | 1968 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 727522 | 107892
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019520000 | Vegetation -Bayamon - Group B | $- | 3952 | 3952 | FAASt [Region 3-Bayamon Group B] (Vegetation) | 740408 | 107934
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019530000 | Vegetation -Bayamon - Group C | $- | 2656 | 2656 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | 727558 | 107896
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019540000 | Vegetation-Arecib-Sbstn/Tlcom | $- | 6114 | 6114 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | 741101 | 107943
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019550000 | Vegetation -Arecibo - Group A | $- | 94399 | 94399 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 750067 | 107968
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019560000 | Vegetation -Arecibo - 115kV | $- | 1986 | 1986 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 727659 | 107901
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019570000 | Vegetation -Arecibo - Group B | $- | 7662 | 7662 | FAASt [Region 2-Arecibo Group B] (Vegetation) | 740410 | 107936
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019580000 | Vegetation -Arecibo - Group C | $- | 4661 | 4661 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | 727540 | 107895
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019590000 | Vegetation -All Regions-230kV | $- | 20415 | 20415 | FAASt [All Regions TL - 230kV] (Vegetation) | 741105 | 107946
PBOP7 Veg.Mngmt&Cap.Clear.Impl | 15F019880000 | Vgtn - Bayamon - Group A (HD) | $- | 336152 | 336152 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 727572 | 11720
PBUT1 Compliance & Studies | 10F000510000 | Transmiss Planning-Area Plans | 1135469 | 787315 | 1922783 | 0 | 0 | 0
PBUT1 Compliance & Studies | 14F003250000 | Grounding Program Studies | 44367 | 896 | 45263 | 0 | 0 | 0
PBUT1 Compliance & Studies | 14F003380000 | D Subs Sys Asset Plan & Size | 3181761 | 1509191 | 4690952 | 0 | 0 | 0
PBUT1 Compliance & Studies | 14F003390000 | Dist Line-Sys Lev Plan & Size | 8794776 | 3537733 | 12332509 | 0 | 0 | 0
PBUT1 Compliance & Studies | 14F003400000 | T Subs Sys Asset Plan & Size | 6089558 | 2774005 | 8863563 | 0 | 0 | 0
PBUT1 Compliance & Studies | 14F003410000 | T Line-Sys Lev A. Plan & Size | 5178261 | 3763018 | 8941279 | 0 | 0 | 0
PBUT1 Compliance & Studies | 14F003780000 | Dist Planning - Area Plans | 6942229 | 2901788 | 9844017 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002600000 | 230kV Trans Pole Repl | -2341 | 9907 | 7566 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002610000 | 115kV Trans Ple Repl | -972 | $- | -972 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002620000 | Transmission Priority Pole Rep | 6211856 | 6587225 | 12799081 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002630000 | 38kV Bayamon Trans Pole Repl | -733 | $- | -733 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002640000 | 38kV Mayaguez Trans Pole Repl | -393 | $- | -393 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002650000 | 38kV Arecibo Trans Pole Repl | -695 | $- | -695 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002660000 | 38kV Caguas Trans Pole Repl | -409 | 5082 | 4673 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F002670000 | 38kV Ponce Trans Pole Repl | -233 | $- | -233 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F003670000 | T.Priority Pole Repl.Mora50500 | 73849 | 144 | 73993 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | 668669 | 107754
PBUT13 T Priority Pole Repl | 14F004480000 | PRW Trans PoleRepl-JUL21-JAN22 | 952 | $- | 952 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F004490000 | PRW Tran PoleRepl-FEB22-MOVFWD | 1168 | $- | 1168 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F012580000 | T-Pole Replacement - L36100 | -46 | -12569 | -12614 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F017300000 | Tpole L100 Ponce TC-Sta Isabel | 84971 | 292 | 85262 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) | 711862 | 107857
PBUT13 T Priority Pole Repl | 14F017310000 | TPoleL100 SIsabelSecSalinasSec | 17205 | 431 | 17636 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) | 711829 | 107856
PBUT13 T Priority Pole Repl | 14F017330000 | TPoleL13400AcaciasSGermanPargu | $- | 844360 | 844360 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | 711819 | 11840
PBUT13 T Priority Pole Repl | 14F017340000 | Tpole L2000 11AgostoSSebastian | 366240 | 85115 | 451356 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) | 712978 | 107862
PBUT13 T Priority Pole Repl | 14F020470000 | Tpole 10100 Lomas-Reparto | 1760 | 34793 | 36554 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020480000 | Tpole 2400 DBocas-Caonill | 2178 | 49498 | 51676 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020490000 | Tpole 200 Ponce-StaIsabel | 1523 | 18957 | 20479 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020500000 | Tpole 4800 StaIsabel-StaIsabel | 1371 | 11038 | 12409 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020510000 | Tpole 9600 Bayamon-CataÃ±o | $- | 18472 | 18472 | FAASt [Transmission Priority Pole Replacement Program Line 9600 Bayamon TC – Catano Sect] (Transmission) | 811913 | 108099
PBUT13 T Priority Pole Repl | 14F020520000 | Tpole 7800 Dorado-Vega Alta | 2230 | 24800 | 27030 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020530000 | Tpole 6700 SeborucoTO-TapiaTO | 2624 | 84765 | 87388 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020540000 | TPole 7500 3Monjitas-PuertNu | 2063 | 14681 | 16744 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020550000 | Tpole 10700 HTejas-HTejas | 3282 | 111850 | 115132 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020560000 | Tpole 800-COMSAT SECT-CIDRA SE | $- | 51942 | 51942 | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) | 753781 | 108009
PBUT13 T Priority Pole Repl | 14F020570000 | Tpole16500Fajardo-2Marina | $- | 26116 | 26116 | FAASt [Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | 811923 | 108100
PBUT13 T Priority Pole Repl | 14F020580000 | Tpole3100MONCILLOSS.LLANA | $- | 10227 | 10227 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | 753782 | 108010
PBUT13 T Priority Pole Repl | 14F020590000 | Tpole 1500 11Agosto-SG TO | 1438 | 30994 | 32432 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020600000 | TPole 3300 SGerardo-Venezuela | $- | 14129 | 14129 | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) | 753785 | 108011
PBUT13 T Priority Pole Repl | 14F020610000 | Tpole 5900SJSP-Crematori | $- | 16624 | 16624 | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) | 753786 | 108012
PBUT13 T Priority Pole Repl | 14F020620000 | Tpole1200 SGSt-SG TC-Y2HP | 621 | 3204 | 3825 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020630000 | TPole 13700 Mora-Isabela | $- | 6984 | 6984 | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) | 753787 | 108013
PBUT13 T Priority Pole Repl | 14F020640000 | TPole 700CostaSur-Yauco2HP | $- | 16550 | 16550 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | 750151 | 107971
PBUT13 T Priority Pole Repl | 14F020650000 | Tpole1600LeonSectAcacias | 621 | 88347 | 88968 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020660000 | Tpole 19002Bocas-SSbstian | $- | 57375 | 57375 | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) | 753788 | 108014
PBUT13 T Priority Pole Repl | 14F020670000 | Tpole2000 11AgostoSt-SSTC | 2134 | 6242 | 8376 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020680000 | Tpole2700AGUADILLAH-MORA | $- | 152556 | 152556 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | 749072 | 11877
PBUT13 T Priority Pole Repl | 14F020690000 | Tpole6000AguadillaTBone | 2016 | 27089 | 29105 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020700000 | Tpole36200MncillosJuncos | 3258 | 39347 | 42605 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020710000 | TPole37800CaguasBuenPtSt | 4929 | 30955 | 35884 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020720000 | Tpole 37800MCILLOS-PASTOR | 1683 | 28705 | 30388 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020730000 | TPole14700Manati-ManatiSe | 3462 | 77544 | 81006 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020740000 | TPole 6100 MayaGP-Radial | 1851 | 23844 | 25695 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020750000 | TPole 2800 Tbone-RameyField2 | 2224 | 14057 | 16282 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020760000 | Tpole 5600 AnascoTC-MayaguezGP | 2026 | 25547 | 27573 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020770000 | TPole 3500 Cachete-Caparra | 1836 | 12855 | 14691 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F020780000 | Tpole5600 VictTcAÃ‘ASCOTC | $- | 119385 | 119385 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | 749060 | 11874
PBUT13 T Priority Pole Repl | 14F020790000 | TPole 4800 StaIsabel-ToroNegro | $- | 7555 | 7555 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | 750150 | 107970
PBUT13 T Priority Pole Repl | 14F020800000 | TPole 4800Sta.Isabel-Aibo | $- | 5568 | 5568 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | 750168 | 107972
PBUT13 T Priority Pole Repl | 14F021440000 | TPole 500 Ponce-C.Sur-Canas | $- | 2392 | 2392 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021450000 | TPole 2100-2Boca-Hatillo | $- | 1798 | 1798 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021460000 | TPole 2100 Hatillo-Quebra | $- | 1800 | 1800 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021470000 | TPole 9300 Juncos-GBenitez | $- | 2992 | 2992 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021480000 | TPole 13500 Acacias-C.Rojo | $- | 3742 | 3742 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021490000 | TPole 14400 Caguax-Veredas | $- | 2803 | 2803 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021500000 | TPole 37800-Cayey-Caguas | $- | 2052 | 2052 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021510000 | TPole 37800 Cayey TC-JobTC | $- | 2519 | 2519 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021530000 | TPole 6900MidorAzu-Hatllo | $- | 365 | 365 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021540000 | Tpole 6900CAMBTC-MIRAZUL | $- | 321 | 321 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021550000 | Tpole 7900TNEGROHP-JDIAZ | $- | 321 | 321 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021560000 | TPole 8200SJS-AmeSt-CatSt | $- | 321 | 321 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021570000 | Tpole 9500PSECOSP-CATAÃ‘O | $- | 321 | 321 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021580000 | TPole 9900RioBlncoHP-Huma | $- | 717 | 717 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021590000 | TPole10900JOBOSTC-PFIZERGUAYMA | $- | 597 | 597 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021600000 | Tpole 15900-VICTTC-ADATO | $- | 599 | 599 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021610000 | TPole14100 BarcelonetaTC-Merck | $- | 597 | 597 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021620000 | Tpole TL 4900QBRSec-QBRTo | $- | 597 | 597 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021630000 | Tpole 36400Ponce-2BocasHy | $- | 597 | 597 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021640000 | Tpole 38900Martin-Berwind | $- | 641 | 641 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021660000 | TPole 10300 Canovanas TC-Sect | $- | 690 | 690 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021670000 | TPole 10500 Chardon Las Monjas | $- | 1276 | 1276 | 0 | 0 | 0
PBUT13 T Priority Pole Repl | 14F021680000 | TPole 13200 DoraHatoT-HatoTS | $- | 921 | 921 | 0 | 0 | 0
PBUT17 D Meter Repl & Maint | 14F003620000 | Meter Inst(fail.TWACS meters) | 133551 | 61626 | 195176 | 0 | 0 | 0
PBUT18 Substation Security | 14F002160000 | PHYSICAL SECURITY FAC ASSES | 53270 | 799 | 54069 | 0 | 0 | 0
PBUT18 Substation Security | 14F003240000 | Physical Security Fence Repl | 83831 | 9878 | 93709 | 0 | 0 | 0
PBUT18 Substation Security | 14F003760000 | Physical Sec.Group 5-Bayamo.TC | 8316 | 5928 | 14243 | FAASt Physical Security - Group 5 (Substation) | 549768 | 107709
PBUT18 Substation Security | 14F003880000 | PHYS SEC Group 5 - Caguas TC | 26694 | 59 | 26752 | FAASt Physical Security - Group 5 (Substation) | 549768 | 107709
PBUT18 Substation Security | 14F003890000 | PHYS SEC Group 5 - Victoria TC | 6702 | 590 | 7292 | FAASt Physical Security - Group 5 (Substation) | 549768 | 107709
PBUT18 Substation Security | 14F004370000 | PHYSICAL SEC-CAPUCHINOS1329 | 12832 | $- | 12832 | 0 | 0 | 0
PBUT19 Tech Facilities Securit | 10F000010000 | Replace outside CCTV at Arecib | -6 | $- | -6 | 0 | 0 | 0
PBUT19 Tech Facilities Securit | 10F000020000 | Replace outside CCTV at Bayamo | -3 | -42 | -45 | 0 | 0 | 0
PBUT19 Tech Facilities Securit | 10F000040000 | Repairs to fence at Mayaguez T | -13 | $- | -13 | 0 | 0 | 0
PBUT20 Warehouse Security | 10F000030000 | CCTV for Regional Warehouses ( | -1 | $- | -1 | 0 | 0 | 0
PBUT24 Ctrl Ctr Const & Refurb | 14F000010000 | New Primary&Backup Ctrl Centrs | $- | 1780284 | 1780284 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 746545 | 11824
PBUT24 Ctrl Ctr Const & Refurb | 14F019920000 | Secondary Control Center | $- | 9394 | 9394 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 746545 | 11824
PBUT27 Asset Data Integrity | 14F002080000 | Prelim. Eng. Data Collection | 707363 | 12193 | 719556 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F001620000 | San Juan Region Pole & Cond | 4849 | $- | 4849 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F001630000 | Bayamon Region Pole & Cond | 2488 | $- | 2488 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F001640000 | Ponce Region Pole & Conduc | 2256 | $- | 2256 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F001650000 | Dist Pole and Conductor Repair | 4154540 | 386309 | 4540848 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F001660000 | Mayaguez Region Pole & Con | 2888 | $- | 2888 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F001670000 | Arecibo Region Pole & Cond | 1392 | $- | 1392 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004060000 | Dist.Pole&Cond Rep-Carolin G1 | -120 | -38 | -157 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004220000 | Distribution Pole and Cond Rep | 954 | $- | 954 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004230000 | Distr Pole and Cond Rep | 3162 | 14543 | 17705 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004240000 | Distribution Pole and Cond | 1375 | 7771 | 9147 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004250000 | Distribution Pole and | 1061 | 7241 | 8303 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004260000 | Distribution Pole | 879 | 5485 | 6363 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004270000 | Distribution Pol | 182 | $- | 182 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004280000 | PRW Dist.Pole Repl.JUN21-JAN22 | -579 | 205 | -374 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F004290000 | PRW DistPole ReplFEB22-MOVFWD | 20407 | 692279 | 712687 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F014410000 | DPole Mayaguez Grp. 15-to-19 | $- | 200562 | 200562 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | 705503 | 11476
PBUT30 D Pole & Conductor Repa | 14F016490000 | DPole Bayamon Grp. 16 | 3783 | 1300 | 5083 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) | 710498 | 107851
PBUT30 D Pole & Conductor Repa | 14F016500000 | DPole Bayamon Grp. 15 | 3294 | 1700 | 4994 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) | 710363 | 107850
PBUT30 D Pole & Conductor Repa | 14F016520000 | DPole Arecibo Grp. 17 | 5227 | 158 | 5385 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) | 710026 | 107848
PBUT30 D Pole & Conductor Repa | 14F016540000 | DPole Mayaguez Grp. 20 | 2335 | 604 | 2939 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) | 710045 | 107849
PBUT30 D Pole & Conductor Repa | 14F016950000 | DPole Mayaguez Grp. 21 | 1096 | 315 | 1411 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) | 711962 | 107859
PBUT30 D Pole & Conductor Repa | 14F016960000 | DPole Ponce Grp. 24 | 2346 | 1327 | 3672 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) | 712981 | 107864
PBUT30 D Pole & Conductor Repa | 14F017000000 | Dist Pole & Cond Rep Mayag G23 | 661 | 315 | 976 | FAASt [Distribution Pole and Conductor Repair – Mayaguez Group 23] (Distribution) | 712982 | 107865
PBUT30 D Pole & Conductor Repa | 14F018500000 | Dpole Caguas Grp. 3 -Ph 2 | $- | 4102 | 4102 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 735474 | 107918
PBUT30 D Pole & Conductor Repa | 14F018880000 | DPole Caguas Group 4 Ph 2 | $- | 5741 | 5741 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | 790446 | 108071
PBUT30 D Pole & Conductor Repa | 14F018890000 | DPole Caguas Group 5 Ph 2 | $- | 6012 | 6012 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) | 790427 | 108069
PBUT30 D Pole & Conductor Repa | 14F018900000 | DPole Caguas Group 6 Ph 2 | $- | 6151 | 6151 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | 806935 | 108097
PBUT30 D Pole & Conductor Repa | 14F018910000 | DPole Caguas Group 7 Ph 2 | $- | 4877 | 4877 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) | 817249 | 108116
PBUT30 D Pole & Conductor Repa | 14F018920000 | DPole Caguas Group 8 Ph 2 | $- | 6853 | 6853 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution) | 817242 | 108113
PBUT30 D Pole & Conductor Repa | 14F018930000 | DPole Carolina Group 1 Ph 2 | $- | 46850 | 46850 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | 738692 | 107929
PBUT30 D Pole & Conductor Repa | 14F018950000 | DPole Carolina Group 3 Ph 2 | $- | 5005 | 5005 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | 806936 | 108098
PBUT30 D Pole & Conductor Repa | 14F018960000 | DPole Mayaguez Group 2 Ph 2 | $- | 7341 | 7341 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | 738674 | 107928
PBUT30 D Pole & Conductor Repa | 14F018970000 | DPole Mayaguez Group 3 Ph 2 | $- | 3501 | 3501 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 750692 | 107979
PBUT30 D Pole & Conductor Repa | 14F018980000 | DPole Mayaguez Group 4 Ph 2 | $- | 2989 | 2989 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 752540 | 107999
PBUT30 D Pole & Conductor Repa | 14F019000000 | DPole Ponce Group 2 Ph2 | $- | 2614 | 2614 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | 738667 | 107927
PBUT30 D Pole & Conductor Repa | 14F019030000 | DPole San Juan Group 3 Ph 2 | $- | 1658 | 1658 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 790443 | 108070
PBUT30 D Pole & Conductor Repa | 14F020460000 | Dist.Pole&Cond.Rep.Are.Grp3Ph2 | $- | 3809 | 3809 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | 757945 | 108042
PBUT30 D Pole & Conductor Repa | 14F021390000 | Dpole&Cond.Rep.-Arec.Grp4Phs2 | $- | 131992 | 131992 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | 759004 | 108045
PBUT30 D Pole & Conductor Repa | 14F021400000 | Dpole&Cond.Rep.-Mayag.Grp5Phs2 | $- | 15186 | 15186 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021410000 | Dpole&Cond.Rep.-Baya.Grp4Phs2 | $- | 40684 | 40684 | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) | 759051 | 108046
PBUT30 D Pole & Conductor Repa | 14F021420000 | Dpole&Cond.Rep.-SJ.Grp4Phs2 | $- | 75592 | 75592 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2] (Distribution) | 817250 | 108117
PBUT30 D Pole & Conductor Repa | 14F021430000 | Dpole&Cond.Rep.-Pnce.Grp3Phs2 | $- | 261693 | 261693 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2] (Distribution) | 817247 | 108114
PBUT30 D Pole & Conductor Repa | 14F021710000 | DPole Arecibo 18-21 Phase 3 | $- | 31805 | 31805 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021720000 | DPole Bayamon 17-25 Phase 3 | $- | 106047 | 106047 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021730000 | DPole Caguas 21-25 Phase 3 | $- | 109447 | 109447 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021740000 | DPole Mayaguez 24-27 Phase 3 | $- | 38937 | 38937 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021750000 | DPole Ponce 20-28 Phase 3 | $- | 20076 | 20076 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021760000 | DPole San Juan 22-29 Phase 3 | $- | 45787 | 45787 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021770000 | DPole San Juan 30-39 Phase 3 | $- | 42639 | 42639 | 0 | 0 | 0
PBUT30 D Pole & Conductor Repa | 14F021780000 | DPole San Juan 40-54 Phase 3 | $- | 1451 | 1451 | 0 | 0 | 0
PBUT32 Inspection T Lines | 14F002550000 | Stage 3dÂ Cathodic Protection | 2565 | 1814 | 4379 | 0 | 0 | 0
PBUT32 Inspection T Lines | 14F002560000 | Stage 2cÂ Pole Inspection and | 3239 | 413 | 3651 | 0 | 0 | 0
PBUT32 Inspection T Lines | 14F002570000 | Stage 3cÂ Anchor and Guy Insp | 600 | $- | 600 | 0 | 0 | 0
PBUT32 Inspection T Lines | 14F002580000 | Stage 2dÂ Xray Sleeves | 820 | $- | 820 | 0 | 0 | 0
PBUT32 Inspection T Lines | 14F002590000 | Trans Lines High Lvl Assesment | 756183 | 1111073 | 1867256 | 0 | 0 | 0
PBUT32 Inspection T Lines | 14F008460000 | Assesment UG 38 kV Trans Syst | 9913 | 176920 | 186833 | 0 | 0 | 0
PBUT32 Inspection T Lines | 14F014580000 | Assesment UG Transmission Syst | 19034 | 16901 | 35935 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F002170000 | Existing 38 kV Line 100 Ponce | $- | 262674 | 262674 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | 180052 | 11453
PBUT33 T Line Rebuild | 14F002190000 | Existing 115kV Line 36800 Pa | $- | 274922 | 274922 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | 180326 | 11441
PBUT33 T Line Rebuild | 14F002200000 | 5400 RIO BLANCO HP DAGUAO | $- | 674104 | 674104 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 165213 | 11244
PBUT33 T Line Rebuild | 14F002210000 | 51300 PONCEÂ COSTA SUR | $- | 757147 | 757147 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | 166707 | 11431
PBUT33 T Line Rebuild | 14F002220000 | 37800 JOBOS - CAGUAS | $- | 248881 | 248881 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | 166860 | 11255
PBUT33 T Line Rebuild | 14F002230000 | 37800 CAGUASÂ MONACILLOS | $- | 142118 | 142118 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | 166904 | 11451
PBUT33 T Line Rebuild | 14F002240000 | 37100 COSTA SURÂ ACACIAS | $- | 315328 | 315328 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | 167168 | 11246
PBUT33 T Line Rebuild | 14F002250000 | 36200 MONACILLOSÂ JUNCOS | $- | 294143 | 294143 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | 167443 | 11251
PBUT33 T Line Rebuild | 14F002260000 | 36100 DOS BOCASÂ MONACILLOS | $- | 1630688 | 1630688 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | 167446 | 11307
PBUT33 T Line Rebuild | 14F002270000 | 50100 CAMBALACHEÂ MANATI | $- | 24883 | 24883 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | 167508 | 11250
PBUT33 T Line Rebuild | 14F002290000 | 36400 DOS BOCASÂ PONCE | $- | 602570 | 602570 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | 168483 | 11241
PBUT33 T Line Rebuild | 14F002300000 | 9500 PALO SECO SPÂ CATANO S | $- | 257719 | 257719 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 176913 | 11432
PBUT33 T Line Rebuild | 14F002310000 | 1100 GARZAS 1 HPÂ GARZAS 2 | $- | 167783 | 167783 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | 176954 | 11439
PBUT33 T Line Rebuild | 14F002320000 | 8200 SAN JUAN SPÂ CATANO SE | $- | 213785 | 213785 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 176971 | 11373
PBUT33 T Line Rebuild | 14F002330000 | 4100 GUARAGUO TCÂ COMERIO T | $- | 507142 | 507142 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | 177134 | 11440
PBUT33 T Line Rebuild | 14F002340000 | 39000 AGUAS BUENASÂ CAGUAS | $- | 483393 | 483393 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | 177191 | 11433
PBUT33 T Line Rebuild | 14F002350000 | Existing 115 kV - Line 36200 F | $- | 144984 | 144984 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | 548598 | 11494
PBUT33 T Line Rebuild | 14F002360000 | Existing 38 kV - Line 8900 Mon | 758672 | 29858 | 788529 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) | 334469 | 107522
PBUT33 T Line Rebuild | 14F002370000 | Existing 38kV - Line 1200 May | $- | 1582487 | 1582487 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | 547160 | 107689
PBUT33 T Line Rebuild | 14F002380000 | Existing 38 kV - Line 2200 Dos | $- | 523228 | 523228 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | 730657 | 11559
PBUT33 T Line Rebuild | 14F002390000 | Existing 38 kV - Line 3100 Mon | $- | 2304140 | 2304140 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 334470 | 11708
PBUT33 T Line Rebuild | 14F002400000 | Existing 38 kV - Line 500 Ponc | $- | 96679 | 96679 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | 750730 | 107981
PBUT33 T Line Rebuild | 14F002410000 | Existing 38 kV - Line 1900 Dos | $- | 627547 | 627547 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | 334331 | 11528
PBUT33 T Line Rebuild | 14F002420000 | Existing 38 kV - Line 2700 Vic | $- | 230163 | 230163 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | 547259 | 11480
PBUT33 T Line Rebuild | 14F002430000 | Existing 38 kV - Line 2800 Agu | $- | 214904 | 214904 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | 547269 | 11481
PBUT33 T Line Rebuild | 14F002440000 | Existing 38 kV - Line 3000 Mon | 2484722 | 997319 | 3482041 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) | 334482 | 11450
PBUT33 T Line Rebuild | 14F002450000 | Existing 38 kV - Line 3600 Mon | 1081043 | 125148 | 1206191 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) | 547221 | 107692
PBUT33 T Line Rebuild | 14F002460000 | Existing 38 kV - Line 13300 Ba | $- | 20016 | 20016 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | 547350 | 11854
PBUT33 T Line Rebuild | 14F002470000 | Existing 38 kV - Line 600 Cagu | $- | 120842 | 120842 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | 550019 | 107710
PBUT33 T Line Rebuild | 14F002480000 | Existing 38 kV - Line 2400 Dos | $- | 263757 | 263757 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 547251 | 11807
PBUT33 T Line Rebuild | 14F002490000 | Existing 38 kV - Line 1500 May | $- | 873835 | 873835 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | 753777 | 108008
PBUT33 T Line Rebuild | 14F002500000 | Existing 38 kV - Line 6700 Mar | 510542 | 34711 | 545253 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) | 730784 | 107910
PBUT33 T Line Rebuild | 14F002510000 | Existing 38 kV - Line 4000 Com | 742168 | 38965 | 781133 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) | 550070 | 107712
PBUT33 T Line Rebuild | 14F002520000 | Existing 38 kV - Line 9100 Gua | $- | 219401 | 219401 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) | 551911 | 11434
PBUT33 T Line Rebuild | 14F002530000 | Existing 38 kV - Line 9700 Pal | $- | 402585 | 402585 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | 550902 | 11688
PBUT33 T Line Rebuild | 14F002540000 | Existing 38 kV - Line 11100 Ca | $- | 500845 | 500845 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | 551067 | 11687
PBUT33 T Line Rebuild | 14F002680000 | Existing 38 kV - Line 11400 Ba | $- | 410462 | 410462 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | 547226 | 11689
PBUT33 T Line Rebuild | 14F003790000 | Distribution Line Rebu-PBUT33 | 19858 | 1494 | 21352 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F008470000 | UGÂ Transmission SystemRepairs | 44 | $- | 44 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015390000 | H Maria L9900 TAP9905A-RBlanco | $- | 181487 | 181487 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | 752052 | 107991
PBUT33 T Line Rebuild | 14F015400000 | H Maria L-9300 Juncos-ACB 9301 | 28937 | 5778 | 34715 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015410000 | H Maria L-9300GBenitez-ACB9323 | 29725 | $- | 29725 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015420000 | H MariaL700 Costa Sur-Yauco P | 131128 | 79534 | 210662 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015430000 | H MariaL-5600 H Rincon-Sub7113 | 6932 | 2106 | 9038 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015440000 | HMariaL3700-GOAB3797Arroyo4101 | 13539 | 707 | 14246 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015450000 | H Maria L3500 Lomas-Monacillos | 9078 | 795 | 9873 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015460000 | H Maria L-3300 Chardon-Egozcue | 13225 | 2495 | 15719 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015470000 | H Maria L-21000-Humacao-Arroyo | 3972 | 131 | 4102 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015480000 | H Maria L-20900-Bta-Cambalache | 1515 | $- | 1515 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015490000 | H Maria L20800Canas-BuenaVista | 3403 | 132 | 3535 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015500000 | H Maria L20600-SIsabel-Hamilto | 2403 | 632 | 3035 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015510000 | H Maria L20500-Juncos-Humacao | 1191 | 132 | 1323 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015520000 | H Maria L20300-Juncos-GBenÃ­tez | 2463 | 231 | 2693 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015530000 | H Maria L-20200-SGermÃ¡n-Agosto | 3368 | 87 | 3455 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015540000 | H Maria L13400 Boqueron-Acacia | 13800 | 5857 | 19656 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015550000 | H Maria L10000 Sierra-Magnolia | 4176 | 332 | 4508 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015560000 | H Maria 1000 Venez-Capuchinos | 11002 | 912 | 11914 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015570000 | H Maria L42600-SabLlana-Palmer | 3657 | 335 | 3992 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015580000 | H Maria L-39100-Hatillo-Mora | 2407 | 1209 | 3616 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015590000 | H Maria L41200 Sabana-CanÃ³vana | 96070 | 13912 | 109981 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015600000 | HMaria L42700Monacillo-Canovan | 2948 | 3324 | 6272 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015610000 | H MariaL50300 Costa S-Aguirre | $- | 57024 | 57024 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | 718971 | 107884
PBUT33 T Line Rebuild | 14F015620000 | H Maria L51200 CostaS-Cambala | $- | 46764 | 46764 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | 718951 | 107882
PBUT33 T Line Rebuild | 14F015630000 | H MariaL50200 Costa Sur-Bay TC | $- | 58915 | 58915 | FAASt [Line 50200 (230kv) from Manati TC to Bayamon TC] (Transmission) | 718955 | 107883
PBUT33 T Line Rebuild | 14F015640000 | H MariaL51000 Aguirre-SLlanaTC | 15281 | 760 | 16040 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015650000 | H MariaL-50900 Aguirre-Bay TC | 19150 | 573 | 19723 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015660000 | H Maria L50700Aguirre-YabuTCÂ¿ | 2130 | 133 | 2263 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015670000 | H Maria L50500-May-Cambalache | 4711 | 10549 | 15260 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015680000 | H Maria L-50400-May TC-Costa S | 1368 | 1340 | 2707 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F015690000 | H Maria L50800SLlanaTC-YabcoaT | 2970 | 133 | 3103 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F016830000 | HMariaL2500-Victoria-SSebastia | 1658 | 133 | 1791 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F016840000 | H Maria L2600-Ssebast-Quebradi | 2090 | 361 | 2451 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F016850000 | H Maria L36700-Mayague-SSebast | 2750 | 2687 | 5437 | 0 | 0 | 0
PBUT33 T Line Rebuild | 14F016860000 | H MariaL36600-SSebast-DosBocas | 1670 | 89 | 1759 | 0 | 0 | 0
PBUT34 D Lines Inspection | 14F001680000 | Distribution Lines Inspect | 8799603 | 4473943 | 13273547 | 0 | 0 | 0
PBUT34 D Lines Inspection | 14F004300000 | UG System Inspection | 207136 | 1075347 | 1282483 | 0 | 0 | 0
PBUT37 Microgrid Inst & Integ | 10F000530000 | Centro Medico Microgrid | 5197 | $- | 5197 | 0 | 0 | 0
PBUT37 Microgrid Inst & Integ | 14F000910000 | 2501-02 (L) | $- | 305222 | 305222 | FAASt [Feeders Vieques & Culebra] (Distribution) | 165226 | 107206
PBUT37 Microgrid Inst & Integ | 14F000920000 | 2501-03 | $- | 267377 | 267377 | FAASt [Feeders Vieques & Culebra] (Distribution) | 165226 | 107206
PBUT37 Microgrid Inst & Integ | 14F000930000 | 3801-02 | $- | 199609 | 199609 | FAASt [Feeders Vieques & Culebra] (Distribution) | 165226 | 107206
PBUT37 Microgrid Inst & Integ | 14F000940000 | 2501-01 | $- | 216719 | 216719 | FAASt [Feeders Vieques & Culebra] (Distribution) | 165226 | 107206
PBUT37 Microgrid Inst & Integ | 14F000950000 | 3801-01 | $- | 218491 | 218491 | FAASt [Feeders Vieques & Culebra] (Distribution) | 165226 | 107206
PBUT37 Microgrid Inst & Integ | 14F017280000 | Vieques & Culebra Microgrid In | 2455606 | -520389 | 1935217 | 0 | 0 | 0
PBUT37 Microgrid Inst & Integ | 14F019600000 | 25 MW BESS Instn & Intn Barcel | $- | 72277 | 72277 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | 738671 | 11819
PBUT37 Microgrid Inst & Integ | 14F019610000 | 25 MW BESS Instn & Intn San Ju | $- | 287783 | 287783 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | 750503 | 107978
PBUT37 Microgrid Inst & Integ | 14F019620000 | 25 MW BESS INST & INTE AGUADIL | $- | 99761 | 99761 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | 750502 | 107977
PBUT37 Microgrid Inst & Integ | 14F019630000 | 25 MW BESS Instn & Intn Manati | $- | 177538 | 177538 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | 752972 | 108002
PBUT37 Microgrid Inst & Integ | 14F020010000 | TSM, Adv.Sensors & WAMPAC Syst | $- | 222977 | 222977 | FAASt Transm. Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System (Telecommunication) | 748180 | 107961
PBUT37 Microgrid Inst & Integ | 14F021650000 | Vieques Microgrid | $- | 552027 | 552027 | FAASt [Vieques Microgrid] (Transmission) | 751655 | 107982
PBUT37 Microgrid Inst & Integ | 14F021690000 | Culebra Microgrid | $- | 593138 | 593138 | FAASt [Culebra Microgrid] (Transmission) | 751656 | 107983
PBUT4 Distribution Automation | 10F000050000 | Protection & Control Reposi | 54689 | 238 | 54927 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000540000 | DAR 1424-06 | 3082 | 44085 | 47167 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000560000 | DAR 9203-03 | $- | 12344 | 12344 | FAASt [Automation Program Group 30] (Distribution) | 746309 | 107959
PBUT4 Distribution Automation | 10F000590000 | DAR 1716-03 | 214 | 143 | 357 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000600000 | DAR 1734-01 | 396 | $- | 396 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000690000 | DAUT 3010-01 Caguas | $- | 27450 | 27450 | FAASt [Automation Program Group 22] (Distribution) | 757687 | 108033
PBUT4 Distribution Automation | 10F000700000 | DAUT 3013-01 Caguas | $- | 20836 | 20836 | FAASt [Automation Program Group 22] (Distribution) | 757687 | 108033
PBUT4 Distribution Automation | 10F000710000 | DAUT 3013-02 Caguas | $- | 10732 | 10732 | FAASt [Automation Program Group 22] (Distribution) | 757687 | 108033
PBUT4 Distribution Automation | 10F000720000 | DAUT 3013-03 Caguas | 13068 | 26935 | 40004 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000730000 | DAUT 9004-08 Arecibo | $- | 1638 | 1638 | FAASt [Automation Program Group 26] (TL / Distribution) | 757692 | 108035
PBUT4 Distribution Automation | 10F000740000 | DAUT 1803-03 Bayamon | $- | 6783 | 6783 | FAASt [Automation Program Group 31] (Distribution) | 757696 | 108037
PBUT4 Distribution Automation | 10F000750000 | DAUT 1806-01 Bayamon | 959 | 12653 | 13612 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000760000 | DAUT 1806-02 Bayamon | 38633 | 2115 | 40748 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000770000 | DAUT 1806-03 Bayamon | $- | 29442 | 29442 | FAASt [Automation Program Group 31] (Distribution) | 757696 | 108037
PBUT4 Distribution Automation | 10F000780000 | DAUT 1716-03 Bayamon | 2747 | 4770 | 7517 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000790000 | DAUT 1734-01 Bayamon | 37839 | 24538 | 62377 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000800000 | DAUT 1710-01 Bayamon | 17231 | 10804 | 28035 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000810000 | DAUT 1710-03 Bayamon | 24289 | 1466 | 25754 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000820000 | DAUT 1710-04 Bayamon | 27542 | 17822 | 45364 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000830000 | DAUT 1710-05 Bayamon | 20570 | 17631 | 38201 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000840000 | DAUT 1711-01 Bayamon | $- | 14411 | 14411 | FAASt [Automation Program Group 33] (Distribution) | 757698 | 108039
PBUT4 Distribution Automation | 10F000850000 | DAUT 1711-04 Bayamon | $- | 14384 | 14384 | FAASt [Automation Program Group 33] (Distribution) | 757698 | 108039
PBUT4 Distribution Automation | 10F000860000 | DAUT 1713-03 Bayamon | $- | 2853 | 2853 | FAASt [Automation Program Group 33] (Distribution) | 757698 | 108039
PBUT4 Distribution Automation | 10F000870000 | DAUT 1714-02 Bayamon | 21481 | 2381 | 23862 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000880000 | DAUT 1706-02 Bayamon | 1731 | 4000 | 5731 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000890000 | DAUT 1708-03 Bayamon | 4473 | 13293 | 17767 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000900000 | DAUT 1708-05 Bayamon | 3881 | 6338 | 10218 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000910000 | DAUT 1909-07 Bayamon | $- | 9246 | 9246 | FAASt [Automation Program Group 35] (TL / Distribution) | 757700 | 108041
PBUT4 Distribution Automation | 10F000920000 | DAUT 1909-08 Bayamon | $- | 1046 | 1046 | FAASt [Automation Program Group 35] (TL / Distribution) | 757700 | 108041
PBUT4 Distribution Automation | 10F000930000 | DAUT 1909-09 Bayamon | $- | 13363 | 13363 | FAASt [Automation Program Group 35] (TL / Distribution) | 757700 | 108041
PBUT4 Distribution Automation | 10F000940000 | DAUT 8701-01 Arecibo | 42284 | 3171 | 45455 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000950000 | DAUT 8701-02 Arecibo | $- | 3830 | 3830 | FAASt [Automation Program Group 38] (Distribution) | 800369 | 108079
PBUT4 Distribution Automation | 10F000960000 | DAUT 8701-03 Arecibo | $- | 1068 | 1068 | FAASt [Automation Program Group 38] (Distribution) | 800369 | 108079
PBUT4 Distribution Automation | 10F000970000 | DAUT 9001-01 Arecibo | $- | 4055 | 4055 | FAASt [Automation Program Group 38] (Distribution) | 800369 | 108079
PBUT4 Distribution Automation | 10F000980000 | DAUT 2603-09 Caguas | 6004 | 18594 | 24597 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F000990000 | DAUT 2801-03 Caguas | 1615 | 49422 | 51037 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001000000 | DAUT 2803-01 Caguas | 2353 | 21487 | 23840 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001010000 | DAUT 2803-03 Caguas | 8499 | 22978 | 31476 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001020000 | DAUT 8010-01 Arecibo | 22572 | 10167 | 32739 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001030000 | DAUT 8010-03 Arecibo | 4234 | 1367 | 5601 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001040000 | DAUT 8013-01 Arecibo | 5046 | 145 | 5191 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001050000 | DAUT 8013-02 Arecibo | 10091 | 284 | 10375 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001060000 | DAUT 8015-08 Arecibo | 898 | 689 | 1586 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001100000 | DAUT 2602-03 Caguas | 4726 | 1326 | 6052 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001110000 | DAUT 2701-03 Caguas | 4968 | $- | 4968 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001130000 | DAUT 2901-01 Caguas | $- | 30741 | 30741 | FAASt [Automation Program Group 21] (Distribution) | 757662 | 108032
PBUT4 Distribution Automation | 10F001140000 | DAUT 2901-02 Caguas | $- | 32969 | 32969 | FAASt [Automation Program Group 21] (Distribution) | 757662 | 108032
PBUT4 Distribution Automation | 10F001150000 | DAUT 2901-03 Caguas | $- | 564 | 564 | FAASt [Automation Program Group 21] (Distribution) | 757662 | 108032
PBUT4 Distribution Automation | 10F001160000 | DAUT 2901-04 Caguas | $- | 26219 | 26219 | FAASt [Automation Program Group 21] (Distribution) | 757662 | 108032
PBUT4 Distribution Automation | 10F001170000 | DAUT 3006-03 Caguas | 3825 | 4821 | 8646 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001180000 | DAUT 3006-05 Caguas | 71057 | 7720 | 78777 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001190000 | DAUT 3405-01 Caguas | 35971 | 1893 | 37864 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001200000 | DAUT 3405-02 Caguas | $- | 27625 | 27625 | FAASt [Automation Program Group 24] (TL/ Distribution) | 757689 | 108034
PBUT4 Distribution Automation | 10F001210000 | DAUT 3501-01 Caguas | $- | 11589 | 11589 | FAASt [Automation Program Group 24] (TL/ Distribution) | 757689 | 108034
PBUT4 Distribution Automation | 10F001220000 | DAUT 3501-03 Caguas | $- | 26048 | 26048 | FAASt [Automation Program Group 24] (TL/ Distribution) | 757689 | 108034
PBUT4 Distribution Automation | 10F001230000 | DAUT 9101-03 Arecibo | $- | 2936 | 2936 | FAASt [Automation Program Group 27] (Distribution) | 757694 | 108036
PBUT4 Distribution Automation | 10F001240000 | DAUT 9101-04 Arecibo | $- | 1494 | 1494 | FAASt [Automation Program Group 27] (Distribution) | 757694 | 108036
PBUT4 Distribution Automation | 10F001250000 | DAUT 9105-06 Arecibo | $- | 4991 | 4991 | FAASt [Automation Program Group 27] (Distribution) | 757694 | 108036
PBUT4 Distribution Automation | 10F001260000 | DAUT 9201-02 Arecibo | $- | 2328 | 2328 | FAASt [Automation Program Group 27] (Distribution) | 757694 | 108036
PBUT4 Distribution Automation | 10F001270000 | DAUT 9501-01 Bayamon | 51122 | 928 | 52050 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001280000 | DAUT 9502-03 Bayamon | 708 | 2714 | 3422 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001290000 | DAUT 8005-01 Arecibo | $- | 6235 | 6235 | FAASt [Automation Program Group 32] (TL / Distribution) | 757697 | 108038
PBUT4 Distribution Automation | 10F001300000 | DAUT 8101-02 Arecibo | $- | 3040 | 3040 | FAASt [Automation Program Group 32] (TL / Distribution) | 757697 | 108038
PBUT4 Distribution Automation | 10F001310000 | DAUT 8101-03 Arecibo | $- | 5891 | 5891 | FAASt [Automation Program Group 32] (TL / Distribution) | 757697 | 108038
PBUT4 Distribution Automation | 10F001320000 | DAUT 8103-01 Arecibo | $- | 1333 | 1333 | FAASt [Automation Program Group 32] (TL / Distribution) | 757697 | 108038
PBUT4 Distribution Automation | 10F001330000 | DAUT 8103-02 Arecibo | 10872 | 7844 | 18716 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001340000 | DAUT 8202-02 Arecibo | 3340 | 21659 | 24999 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001350000 | DAUT 4601-01 Ponce | $- | 21003 | 21003 | FAASt [Automation Program Group 39] (Distribution) | 800394 | 108080
PBUT4 Distribution Automation | 10F001360000 | DAUT 5011-03 Ponce | 1394 | 69 | 1463 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001370000 | DAUT 5013-01 Ponce | 113169 | 61258 | 174428 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001380000 | DAUT 5013-02 Ponce | 14925 | 8665 | 23590 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001390000 | DAUT 5013-03 Ponce | 885 | 796 | 1681 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001400000 | DAUT 5016-01 Ponce | 6176 | 873 | 7049 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001410000 | DAUT 5016-02 Ponce | 6424 | 49 | 6473 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001420000 | DAUT 5018-01 Ponce | $- | 4636 | 4636 | FAASt [Automation Program Group 40] (Distribution) | 800399 | 108081
PBUT4 Distribution Automation | 10F001430000 | DAUT 5018-02 Ponce | 931 | 4160 | 5091 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001440000 | DAUT 5018-03 Ponce | 14224 | 6654 | 20879 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001450000 | DAUT 5018-04 Ponce | 18630 | 4277 | 22907 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001460000 | DAUT 5019-01 Ponce | $- | 2972 | 2972 | FAASt [Automation Program Group 40] (Distribution) | 800399 | 108081
PBUT4 Distribution Automation | 10F001470000 | DAUT 3601-01 Caguas | 1062 | 13739 | 14801 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001480000 | DAUT 3601-02 Caguas | $- | 1918 | 1918 | FAASt [Automation Program Group 45] (Distribution) | 801441 | 108089
PBUT4 Distribution Automation | 10F001490000 | DAUT 3601-03 Caguas | $- | 10594 | 10594 | FAASt [Automation Program Group 45] (Distribution) | 801441 | 108089
PBUT4 Distribution Automation | 10F001500000 | DAUT 3601-04 Caguas | $- | 1156 | 1156 | FAASt [Automation Program Group 45] (Distribution) | 801441 | 108089
PBUT4 Distribution Automation | 10F001510000 | DAUT 3602-01 Caguas | 3033 | 490 | 3523 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001520000 | DAUT 3602-02 Caguas | 2965 | 570 | 3535 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001530000 | DAUT 3604-06 Caguas | 2834 | 283 | 3117 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001540000 | DAUT 3604-07 Caguas | 22232 | 27776 | 50009 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001550000 | DAUT 3701-02 Caguas | $- | 4548 | 4548 | FAASt [Automation Program Group 37] (Distribution) | 800361 | 108078
PBUT4 Distribution Automation | 10F001560000 | DAUT 3701-04 Caguas | 30966 | 5476 | 36443 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001570000 | DAUT 3301-02 Caguas | 36783 | 4604 | 41387 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001580000 | DAUT 3205-09 Caguas | 2208 | $- | 2208 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001590000 | DAUT 3401-01 Caguas | 1745 | 6175 | 7920 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001600000 | DAUT 1705-01 Bayamon | 6199 | 251 | 6450 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001610000 | DAUT 1705-02 Bayamon | 7392 | 1598 | 8990 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001620000 | DAUT 1705-05 Bayamon | 22583 | 10194 | 32776 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001630000 | DAUT 4101-03 Ponce | 49297 | 3119 | 52416 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001640000 | DAUT 3010-03 Caguas | 2848 | 64 | 2912 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001650000 | DAUT 1706-03 Bayamon | 20623 | 395 | 21018 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001660000 | DAUT 1204-02 San Juan | 977 | 1164 | 2141 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001670000 | DAUT 1204-04 San Juan | 2419 | 969 | 3388 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001680000 | DAUT 1204-05 San Juan | 13357 | 24148 | 37505 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001690000 | DAUT 1346-02 San Juan | 590 | 155 | 745 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001700000 | DAUT 1346-03 San Juan | 1180 | 429 | 1609 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001710000 | DAUT 1343-05 San Juan | 5466 | 17040 | 22506 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001720000 | DAUT 1437-03 San Juan | 1180 | 916 | 2096 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001730000 | DAUT 1437-05 San Juan | 826 | 2768 | 3594 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001740000 | DAUT 1525-04 San Juan | 826 | 2989 | 3815 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001750000 | DAUT 1709-02 Bayamon | $- | 14392 | 14392 | FAASt [Automation Program Group 7] (Distribution) | 749124 | 107963
PBUT4 Distribution Automation | 10F001760000 | DAUT 1709-03 Bayamon | 2557 | 8856 | 11414 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001770000 | DAUT 1709-05 Bayamon | $- | 236 | 236 | FAASt [Automation Program Group 7] (Distribution) | 749124 | 107963
PBUT4 Distribution Automation | 10F001780000 | DAUT 1719-15 Bayamon | $- | 8219 | 8219 | FAASt [Automation Program Group 7] (Distribution) | 749124 | 107963
PBUT4 Distribution Automation | 10F001790000 | DAUT 1719-18 Bayamon | $- | 2084 | 2084 | FAASt [Automation Program Group 7] (Distribution) | 749124 | 107963
PBUT4 Distribution Automation | 10F001800000 | DAUT 1719-19 Bayamon | 1661 | 9182 | 10843 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001810000 | DAUT 9401-01 Bayamon | 590 | 2811 | 3401 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001820000 | DAUT 9401-02 Bayamon | 944 | 668 | 1612 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001830000 | DAUT 9801-01 Bayamon | 4925 | 54445 | 59370 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001840000 | DAUT 9802-04 Bayamon | 944 | 1537 | 2481 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001850000 | DAUT 1703-01 Bayamon | $- | 15686 | 15686 | FAASt [ Automation Program Group 9] (Distribution) | 745854 | 107955
PBUT4 Distribution Automation | 10F001860000 | DAUT 1703-02 Bayamon | 16365 | 23250 | 39615 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001870000 | DAUT 1703-04 Bayamon | $- | 17080 | 17080 | FAASt [ Automation Program Group 9] (Distribution) | 745854 | 107955
PBUT4 Distribution Automation | 10F001900000 | DAUT 1704-02 Bayamon | 3015 | 8281 | 11296 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001910000 | DAUT 1717-04 Bayamon | 13479 | 1833 | 15311 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001920000 | DAUT 9503-06 Bayamon | 5896 | 1352 | 7247 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001930000 | DAUT 1901-04 Bayamon | 14314 | 2095 | 16409 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001940000 | DAUT 1907-04 Bayamon | $- | 10777 | 10777 | FAASt [Automation Program Group 11] (Distribution) | 745851 | 107953
PBUT4 Distribution Automation | 10F001950000 | DAUT 1907-05 Bayamon | $- | 8221 | 8221 | FAASt [Automation Program Group 11] (Distribution) | 745851 | 107953
PBUT4 Distribution Automation | 10F001960000 | DAUT 1336-06 San Juan | 2609 | 892 | 3501 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001970000 | DAUT 1336-08 San Juan | 28895 | 430655 | 459551 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001980000 | DAUT 1336-09 San Juan | 3744 | 3287 | 7031 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F001990000 | DAUT 1336-10 San Juan | 5297 | 2529 | 7826 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002000000 | DAUT 2403-02 San Juan | 21871 | 4381 | 26252 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002010000 | DAUT 2404-06 San Juan | 5356 | 11127 | 16483 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002020000 | DAUT 2404-07 San Juan | 31711 | 441287 | 472998 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002030000 | DAUT 2404-08 San Juan | 17779 | 2844 | 20624 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002040000 | DAUT 3102-01 Caguas | 4258 | 1160 | 5418 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002050000 | DAUT 3201-02 Caguas | 590 | 1636 | 2226 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002060000 | DAUT 3201-04 Caguas | 10156 | 42593 | 52749 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002070000 | DAUT 3301-01 Caguas | 5920 | 7168 | 13089 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002080000 | DAUT 9901-02 Caguas | 5068 | 22796 | 27864 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002090000 | DAUT 9902-02 Caguas | 885 | 7065 | 7950 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002100000 | DAUT 9902-03 Caguas | 11423 | 12280 | 23702 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002110000 | DAUT 4001-03 Ponce | $- | 2315 | 2315 | FAASt [Automation Program Group 42] (Distribution) | 801437 | 108086
PBUT4 Distribution Automation | 10F002120000 | DAUT 5602-02 Ponce | 23528 | 57456 | 80984 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002130000 | DAUT 5602-03 Ponce | 19789 | 5205 | 24994 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002140000 | DAUT 6601-03 Ponce | 49935 | 24334 | 74269 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002150000 | DAUT 6601-04 Ponce | 43868 | 15411 | 59278 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002160000 | DAUT 4003-01 Ponce | 28668 | 29539 | 58207 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002170000 | DAUT 4003-02 Ponce | $- | 8526 | 8526 | FAASt [Automation Program Group 39] (Distribution) | 800394 | 108080
PBUT4 Distribution Automation | 10F002180000 | DAUT 4003-03 Ponce | $- | 3627 | 3627 | FAASt [Automation Program Group 39] (Distribution) | 800394 | 108080
PBUT4 Distribution Automation | 10F002190000 | DAUT 4101-01 Ponce | 68170 | 13751 | 81921 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002200000 | DAUT 4101-04 Ponce | 30395 | 35834 | 66229 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002210000 | DAUT 4201-01 Ponce | 30646 | 12304 | 42950 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002220000 | DAUT 4201-02 Ponce | 27624 | 2292 | 29916 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002230000 | DAUT 4201-03 Ponce | 21757 | 1850 | 23607 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002240000 | DAUT 4201-04 Ponce | 27408 | 2254 | 29661 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002250000 | DAUT 4301-02 Ponce | 11403 | 25430 | 36832 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002260000 | DAUT 4401-02 Ponce | 33517 | 12050 | 45566 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002270000 | DAUT 4401-04 Ponce | 649 | 6744 | 7393 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002280000 | DAUT 5002-03 Ponce | $- | 3771 | 3771 | FAASt [Automation Program Group 40] (Distribution) | 800399 | 108081
PBUT4 Distribution Automation | 10F002290000 | DAUT 5004-06 Ponce | 8962 | 89201 | 98163 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002300000 | DAUT 5004-07 Ponce | 27841 | 1557 | 29398 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002310000 | DAUT 5004-09 Ponce | 36249 | 22662 | 58911 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002320000 | DAUT 5007-01 Ponce | 18244 | 27049 | 45292 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002330000 | DAUT 5302-01 Ponce | $- | 4159 | 4159 | FAASt [Automation Program Group 41] (Distribution) | 801432 | 108085
PBUT4 Distribution Automation | 10F002340000 | DAUT 5302-04 Ponce | 2509 | 35398 | 37907 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002350000 | DAUT 5304-01 Ponce | $- | 3426 | 3426 | FAASt [Automation Program Group 41] (Distribution) | 801432 | 108085
PBUT4 Distribution Automation | 10F002360000 | DAUT 5304-03 Ponce | $- | 1354 | 1354 | FAASt [Automation Program Group 41] (Distribution) | 801432 | 108085
PBUT4 Distribution Automation | 10F002370000 | DAUT 5501-01 Ponce | 13942 | 29073 | 43015 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002380000 | DAUT 5501-02 Ponce | 22112 | 12616 | 34728 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002390000 | DAUT 5501-03 Ponce | $- | 1310 | 1310 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002400000 | DAUT 5501-04 Ponce | 11473 | 9414 | 20887 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002410000 | DAUT 5802-03 Ponce | 41005 | 37578 | 78583 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002420000 | DAUT 5817-02 Ponce | 21787 | 7844 | 29631 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002430000 | DAUT 5901-01 Ponce | 5066 | 6123 | 11189 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002440000 | DAUT 5901-02 Ponce | 7024 | 6822 | 13846 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002450000 | DAUT 3004-01 Caguas | 42165 | 18496 | 60661 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002460000 | DAUT 3007-03 Caguas | 33805 | 62321 | 96127 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002470000 | DAUT 3009-01 Caguas | 2770 | 708 | 3478 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002480000 | DAUT 3014-01 Caguas | 15756 | 24717 | 40473 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002490000 | DAUT 3014-04 Caguas | 3663 | 14803 | 18466 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002500000 | DAUT 3015-06 Caguas | 39445 | 18766 | 58211 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002510000 | DAUT 3101-02 Caguas | 14848 | 8145 | 22994 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002520000 | DAUT 3103-01 Caguas | $- | 11933 | 11933 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002530000 | DAUT 3103-05 Caguas | 11630 | 1056 | 12687 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002540000 | DAUT 3205-07 Caguas | 8193 | 38737 | 46930 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002550000 | DAUT 3205-08 Caguas | $- | 16173 | 16173 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002560000 | DAUT 3302-03 Caguas | 1504 | 1310 | 2814 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002570000 | DAUT 3302-04 Caguas | 5977 | 1474 | 7451 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002580000 | DAUT 3401-02 Caguas | $- | 14997 | 14997 | FAASt [Automation Program Group 44] (Distribution) | 801440 | 108088
PBUT4 Distribution Automation | 10F002590000 | DAUT 3401-03 Caguas | 7538 | 13302 | 20840 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002600000 | DAUT 3406-02 Caguas | $- | 15848 | 15848 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002610000 | DAUT 3406-03 Caguas | $- | 28869 | 28869 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002620000 | DAUT 3502-01 Caguas | 11198 | 31894 | 43091 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002630000 | DAUT 3502-02 Caguas | 8061 | 1784 | 9845 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002640000 | DAUT 9601-01 Caguas | 802 | 65709 | 66512 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002650000 | DAUT 9601-02 Caguas | 26243 | 8173 | 34415 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002660000 | DAUT 1110-03 San Juan | 9636 | 2301 | 11937 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002670000 | DAUT 1204-03 San Juan | $- | 2096 | 2096 | FAASt [Automation Program Group 36] (TL / Distribution) | 800286 | 108077
PBUT4 Distribution Automation | 10F002680000 | DAUT 1206-04 San Juan | 27409 | 35017 | 62426 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002690000 | DAUT 1346-04 San Juan | $- | 2594 | 2594 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002700000 | DAUT 1346-05 San Juan | 1831 | 957 | 2788 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002710000 | DAUT 1416-05 San Juan | 5405 | 2286 | 7691 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002720000 | DAUT 1619-03 San Juan | 3771 | 2964 | 6735 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002730000 | DAUT 1620-05 San Juan | 1240 | 1812 | 3052 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002740000 | DAUT 2001-01 San Juan | 41985 | 6617 | 48602 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002750000 | DAUT 2005-09 San Juan | 24336 | 880 | 25216 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002760000 | DAUT 2006-03 San Juan | 6683 | 13521 | 20203 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002770000 | DAUT 2201-01 San Juan | $- | 12147 | 12147 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002780000 | DAUT 2201-02 San Juan | $- | 12728 | 12728 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002790000 | DAUT 2302-02 San Juan | 6820 | 1034 | 7854 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002800000 | DAUT 2305-02 San Juan | 210 | 33814 | 34024 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002810000 | DAUT 2305-03 San Juan | $- | 2217 | 2217 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002820000 | DAUT 2306-01 San Juan | 3789 | 1092 | 4882 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002830000 | DAUT 8010-02 Arecibo | $- | 15572 | 15572 | FAASt [Automation Program Group 34] (Distribution) | 757699 | 108040
PBUT4 Distribution Automation | 10F002840000 | DAUT 8015-07 Arecibo | 17538 | 1844 | 19382 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002850000 | DAUT 8015-09 Arecibo | 15162 | 919 | 16081 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002860000 | DAUT 8101-01 Arecibo | $- | 2881 | 2881 | FAASt [Automation Program Group 34] (Distribution) | 757699 | 108040
PBUT4 Distribution Automation | 10F002870000 | DAUT 8101-04 Arecibo | $- | 3656 | 3656 | FAASt [Automation Program Group 34] (Distribution) | 757699 | 108040
PBUT4 Distribution Automation | 10F002880000 | DAUT 8101-05 Arecibo | $- | 2872 | 2872 | FAASt [Automation Program Group 34] (Distribution) | 757699 | 108040
PBUT4 Distribution Automation | 10F002890000 | DAUT 8104-02 Arecibo | 36289 | 18120 | 54409 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002900000 | DAUT 8202-03 Arecibo | 16705 | 1444 | 18148 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002910000 | DAUT 8203-01 Arecibo | 21608 | 1264 | 22872 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002920000 | DAUT 8203-02 Arecibo | 10178 | 621 | 10800 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002930000 | DAUT 8301-01 Arecibo | 4893 | 34939 | 39831 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002940000 | DAUT 8301-03 Arecibo | $- | 22907 | 22907 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002950000 | DAUT 8404-01 Arecibo | 533 | 1170 | 1703 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002960000 | DAUT 8404-02 Arecibo | 1174 | 8103 | 9277 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002970000 | DAUT 8405-01 Arecibo | 5050 | 708 | 5758 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002980000 | DAUT 8405-02 Arecibo | 700 | 1112 | 1812 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F002990000 | DAUT 8405-03 Arecibo | 13717 | 1371 | 15088 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003000000 | DAUT 8405-04 Arecibo | 2690 | $- | 2690 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003010000 | DAUT 7403-03 Arecibo | 15129 | 613 | 15742 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003030000 | DAUT 8501-01 Arecibo | 14357 | $- | 14357 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003040000 | DAUT 8501-02 Arecibo | 97837 | 15246 | 113083 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003050000 | DAUT 8501-03 Arecibo | 11004 | 405 | 11410 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003060000 | DAUT 8504-03 Arecibo | 13531 | 3478 | 17009 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003070000 | DAUT 8602-01 Arecibo | 26787 | 8437 | 35223 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003080000 | DAUT 8602-02 Arecibo | 7519 | 2491 | 10010 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003090000 | DAUT 8602-03 Arecibo | 47737 | 4250 | 51986 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003100000 | DAUT 8801-04 Arecibo | 21617 | 201 | 21818 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003110000 | DAUT 9001-02 Arecibo | $- | 1569 | 1569 | FAASt [Automation Program Group 43] (Distribution) | 801438 | 108087
PBUT4 Distribution Automation | 10F003120000 | DAUT 9002-01 Arecibo | 4663 | 1129 | 5792 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003130000 | DAUT 9002-03 Arecibo | 13747 | 10211 | 23958 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003140000 | DAUT 1529-12 Bayamon | 5622 | 566 | 6189 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003150000 | DAUT 1701-03 Bayamon | 1126 | 5816 | 6942 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003160000 | DAUT 1704-03 Bayamon | 21112 | 9362 | 30473 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003170000 | DAUT 1704-05 Bayamon | 14233 | 3344 | 17577 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003180000 | DAUT 1707-01 Bayamon | 26847 | 15222 | 42069 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003190000 | DAUT 1707-04 Bayamon | 24467 | 18152 | 42619 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003200000 | DAUT 1708-02 Bayamon | 2186 | 1997 | 4183 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003210000 | DAUT 1708-04 Bayamon | 6541 | 1968 | 8510 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003220000 | DAUT 1734-02 Bayamon | 19645 | 29116 | 48761 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003230000 | DAUT 1801-02 Bayamon | 9937 | 14024 | 23960 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003240000 | DAUT 1801-05 Bayamon | 9513 | 731 | 10244 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003250000 | DAUT 1901-02 Bayamon | 354 | $- | 354 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003260000 | DAUT 1711-05 Bayamon | 3909 | 406 | 4314 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003270000 | DAUT 1717-01 Bayamon | 42494 | 1974 | 44467 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003280000 | DAUT 1717-03 Bayamon | 57985 | 16680 | 74665 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003290000 | DAUT 1718-01 Bayamon | 38490 | 32413 | 70904 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003300000 | DAUT 1718-02 Bayamon | 24068 | 28414 | 52482 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003310000 | DAUT 1718-03 Bayamon | 27719 | 23240 | 50958 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003320000 | DAUT 1903-05 Bayamon | 1661 | 16283 | 17944 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003330000 | DAUT 9202-01 Bayamon | 13522 | 12601 | 26123 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003340000 | DAUT 9202-03 Bayamon | 1087 | 1354 | 2441 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003350000 | DAUT 9202-04 Bayamon | 27368 | 5145 | 32513 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003360000 | DAUT 9203-04 Bayamon | 947 | 7355 | 8303 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003370000 | DAUT 9207-08 Bayamon | 1641 | 17426 | 19067 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003380000 | DAUT 4401-01 Ponce | 9778 | 46877 | 56655 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003390000 | DAUT 4602-01 Ponce | 43116 | 11216 | 54333 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003400000 | DAUT 4602-03 Ponce | 20028 | 26091 | 46119 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003410000 | DAUT 4602-04 Ponce | 1790 | 6065 | 7855 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003420000 | DAUT 4603-01 Ponce | 28486 | 5082 | 33568 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003430000 | DAUT 4603-02 Ponce | 10012 | 25413 | 35424 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003440000 | DAUT 9003-05 Arecibo | $- | 1409 | 1409 | FAASt [Automation Program Group 43] (Distribution) | 801438 | 108087
PBUT4 Distribution Automation | 10F003450000 | DAUT 9003-06 Arecibo | 44995 | 1166 | 46161 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003460000 | DAUT 9004-10 Arecibo | 13196 | 2530 | 15725 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003470000 | DAUT 9101-01 Arecibo | 10874 | 19247 | 30120 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003480000 | DAUT 1118-10 San Juan | 32559 | 7077 | 39636 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003490000 | DAUT 1646-01 San Juan | 60575 | 1579 | 62154 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003500000 | DAUT 1646-05 San Juan | 11606 | 707 | 12313 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003510000 | DAUT 2403-01 San Juan | 23082 | 6193 | 29275 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003520000 | DAUT 2404-05 San Juan | 34055 | 9992 | 44048 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003530000 | DAUT 3801-01 San Juan | 1424 | 3994 | 5418 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003540000 | DAUT 3801-02 San Juan | $- | 6285 | 6285 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003550000 | DAUT 1705-03 Bayamon | 13765 | 2155 | 15920 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003560000 | DAUT 1705-04 Bayamon | 3578 | 1790 | 5368 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003570000 | DAUT 9801-03 Bayamon | $- | 3891 | 3891 | FAASt [Automation Program Group 33] (Distribution) | 757698 | 108039
PBUT4 Distribution Automation | 10F003580000 | DAUT4101-02 Ponce | 16418 | 3552 | 19970 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003590000 | DAUT-5303-01 Ponce | 73568 | 18652 | 92220 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003600000 | DAUT-5401-02 Ponce | 4690 | 2688 | 7378 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003610000 | DAUT-5401-04 Ponce | 12120 | 2588 | 14708 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003620000 | DAUT-5901-03 Ponce | 14587 | 24056 | 38643 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003630000 | DAUT-3006-02 Caguas | 3314 | 16501 | 19815 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003640000 | DAUT-3202-01 Caguas | 2649 | 4061 | 6711 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003650000 | DAUT-3405-03 Caguas | 258 | 1652 | 1910 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003660000 | DAUT-3501-02 Caguas | $- | 20212 | 20212 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003670000 | DAUT-1529-11 Caguas | 182 | 9558 | 9740 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003680000 | DAUT-1529-13 Caguas | 5588 | 1790 | 7378 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003690000 | DAUT-1706-01 Bayamon | 10184 | 1790 | 11974 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003700000 | DAUT-9501-02 Bayamon | 42905 | 38946 | 81851 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003710000 | DAUT-9501-03 Bayamon | 2028 | 2625 | 4653 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003720000 | DAUT-1711-02 Bayamon | 25358 | 2096 | 27454 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003730000 | DAUT-1711-03 Bayamon | 1658 | 1790 | 3448 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003740000 | DAUT-1901-01 Bayamon | 69784 | 9069 | 78853 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003750000 | DAUT-1901-03 Bayamon | 5960 | 2236 | 8196 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003760000 | DAUT 1901-05 Bayamon | 17003 | 4087 | 21090 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003770000 | DAUT 9502-01 Bayamon | 576 | 4251 | 4827 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003780000 | DAUT 9503-05 Bayamon | $- | 3021 | 3021 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003790000 | DAUT 1114-01 San Juan | $- | 1284 | 1284 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003800000 | DAUT 1114-02 San Juan | 360 | 2534 | 2894 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003810000 | DAUT 1114-03 San Juan | 3255 | 1367 | 4622 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003820000 | DAUT 1707-05 BAYAMON | 19639 | 6487 | 26126 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003830000 | DAUT 1707-02 BAYAMON | 9059 | 1314 | 10373 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003840000 | DAUT 7402-05 ARECIBO | 58595 | 5820 | 64416 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003850000 | DAUT 7601-04 ARECIBO | 65850 | 2589 | 68439 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003860000 | DAUT 7602-05 ARECIBO | 57436 | 18152 | 75588 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003870000 | DAUT 7701-02 ARECIBO | $- | 19814 | 19814 | FAASt [Automation Program Group 34] (Distribution) | 757699 | 108040
PBUT4 Distribution Automation | 10F003880000 | DAUT 7701-04 ARECIBO | 19816 | 14709 | 34525 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003890000 | DAUT 8001-01 ARECIBO | 29399 | 3772 | 33171 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003900000 | DAUT 8001-02 ARECIBO | 6053 | 1086 | 7139 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003910000 | DAUT 8001-03 ARECIBO | 10942 | 1350 | 12292 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003920000 | DAUT 8001-04 ARECIBO | 18672 | 1169 | 19841 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003930000 | DAUT 8002-02 ARECIBO | 13204 | 1350 | 14553 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003940000 | DAUT 8002-05 ARECIBO | 24401 | 1285 | 25687 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003950000 | DAUT 8007-01 ARECIBO | 38480 | 3566 | 42046 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003960000 | DAUT 8104-01 ARECIBO | 28054 | 3395 | 31450 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003970000 | DAUT 8104-05 ARECIBO | 40470 | 7185 | 47654 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003980000 | DAUT 8401-01 ARECIBO | 24916 | 11253 | 36168 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F003990000 | DAUT 9002-02 ARECIBO | 16574 | 1860 | 18434 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004000000 | DAUT 1704-04 BAYAMON | 20318 | 2115 | 22433 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004010000 | DAUT 1716-01 BAYAMON | 9999 | 1322 | 11321 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004020000 | DAUT 1717-05 BAYAMON | 7591 | 1322 | 8913 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004030000 | DAUT 1719-16 BAYAMON | 4494 | 1041 | 5535 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004040000 | DAUT 1912-07 BAYAMON | 7151 | 1041 | 8192 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004050000 | DAUT 1912-08 BAYAMON | 16263 | 1041 | 17304 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004060000 | DAUT 1912-10 BAYAMON | 6319 | 1041 | 7360 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004070000 | DAUT 9201-01 BAYAMON | 17467 | 1041 | 18508 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004080000 | DAUT 9206-08 BAYAMON | 8298 | 1093 | 9391 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004090000 | DAUT 9206-09 BAYAMON | 3478 | 1041 | 4519 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004100000 | DAUT 9206-10 BAYAMON | 10590 | 1063 | 11653 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004110000 | DAUT 3005-02 CAGUAS | 17983 | 1425 | 19408 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004120000 | DAUT 3005-03 CAGUAS | 19355 | 1266 | 20621 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004130000 | DAUT 3006-01 CAGUAS | 11644 | 1317 | 12960 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004140000 | DAUT 3007-02 CAGUAS | 23286 | 1434 | 24720 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004150000 | DAUT 3010-04 CAGUAS | 12315 | 792 | 13108 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004160000 | DAUT 1102-03 SAN JUAN | $- | 8288 | 8288 | FAASt [Automation Program Group 36] (TL / Distribution) | 800286 | 108077
PBUT4 Distribution Automation | 10F004170000 | DAUT 1106-01 SAN JUAN | 4372 | 884 | 5256 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004180000 | DAUT 1106-05 SAN JUAN | $- | 1498 | 1498 | FAASt [Automation Program Group 36] (TL / Distribution) | 800286 | 108077
PBUT4 Distribution Automation | 10F004190000 | DAUT 1416-01 SAN JUAN | 17061 | 1255 | 18316 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004200000 | DAUT 1416-03 SAN JUAN | 8393 | 1681 | 10073 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004210000 | DAUT 1618-01 SAN JUAN | 10271 | 1358 | 11629 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004220000 | DAUT 1618-03 SAN JUAN | 7723 | 1348 | 9072 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004230000 | DAUT 1620-01 SAN JUAN | 10934 | 1676 | 12610 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004240000 | DAUT 1647-10 SAN JUAN | 17891 | 4067 | 21958 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004250000 | DAUT 1658-14 SAN JUAN | 4430 | 1213 | 5643 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004260000 | DAUT 2201-03 SAN JUAN | 6566 | 1213 | 7779 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004270000 | DAUT 2201-04 SAN JUAN | 46275 | 12597 | 58872 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004280000 | DAUT 2306-02 SAN JUAN | 2425 | 1387 | 3813 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004290000 | DAUT 7701-03 ARECIBO | 37860 | 13777 | 51637 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004300000 | DAUT 8007-03 ARECIBO | 28738 | 4166 | 32904 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004310000 | DAUT 8007-04 ARECIBO | 3934 | 1205 | 5139 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004320000 | DAUT 8401-03 ARECIBO | $- | 3007 | 3007 | FAASt [Automation Program Group 38] (Distribution) | 800369 | 108079
PBUT4 Distribution Automation | 10F004330000 | DAUT 1924-02 BAYAMON | 8128 | 1205 | 9333 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004340000 | DAUT 1924-05 BAYAMON | 6252 | 1355 | 7607 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004350000 | DAUT 9206-07 BAYAMON | 3357 | 1483 | 4840 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004360000 | DAUT 9206-11 BAYAMON | 1685 | 1483 | 3168 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004370000 | DAUT 2601-04 CAGUAS | 22462 | 12134 | 34595 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004380000 | DAUT 2801-01 CAGUAS | 15636 | 2969 | 18605 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004390000 | DAUT 3008-01 CAGUAS | 4209 | 1542 | 5750 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004400000 | DAUT 3008-04 CAGUAS | 3426 | 2024 | 5450 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004410000 | DAUT 1102-01 SAN JUAN | 3943 | 2275 | 6218 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004420000 | DAUT 1658-13 SAN JUAN | 25915 | 9007 | 34922 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004430000 | DAUT 2002-02 SAN JUAN | 13726 | 7986 | 21712 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004440000 | DAUT 2402-01 SAN JUAN | 10357 | 2625 | 12981 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004450000 | DAUT 8002-03 ARECIBO | 36624 | 2537 | 39161 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004460000 | DAUT 3004-03 CAGUAS | 27050 | 30100 | 57150 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004470000 | DAUT 7805-13 MAYAGUEZ | 21111 | 7402 | 28512 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004480000 | DAUT 2003-02 SAN JUAN | 12000 | 455 | 12455 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004490000 | DAUT 1334-01 SAN JUAN | 41690 | 11367 | 53057 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004500000 | DAUT 1106-04 SAN JUAN | 6145 | 10095 | 16240 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004510000 | DAUT 5803-02 PONCE | 6254 | 2954 | 9208 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004520000 | DAUT 5802-01 PONCE | 30939 | 8397 | 39336 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004530000 | DAUT 5305-04 PONCE | 2784 | 740 | 3525 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004540000 | DAUT 5010-06 PONCE | 4104 | 18504 | 22608 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004550000 | DAUT 5005-02 PONCE | 24202 | 6696 | 30899 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004560000 | DAUT 4502-01 PONCE | 4342 | 42577 | 46919 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004570000 | DAUT 4301-04 PONCE | 40369 | 44543 | 84911 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004580000 | DAUT 4002-03 PONCE | 36631 | 14882 | 51513 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004590000 | DAUT 4002-02 PONCE | 42141 | 46166 | 88306 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004600000 | DAUT 7901-02 MAYAGUEZ | 17228 | 18484 | 35711 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004610000 | DAUT 7503-05 MAYAGUEZ | 5729 | 46911 | 52641 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004620000 | DAUT 7502-02 MAYAGUEZ | 3621 | 23332 | 26953 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004630000 | DAUT 7201-05 MAYAGUEZ | 7152 | 2512 | 9663 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004640000 | DAUT 7101-06 MAYAGUEZ | 21668 | 2611 | 24279 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004650000 | DAUT 7101-04 MAYAGUEZ | 45263 | 15693 | 60956 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004660000 | DAUT 7101-03 MAYAGUEZ | 8741 | 6201 | 14942 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004670000 | DAUT 7012-01 MAYAGUEZ | 62113 | 5658 | 67771 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004680000 | DAUT 6014-03 MAYAGUEZ | 528 | 702 | 1231 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004690000 | DAUT 6012-05 MAYAGUEZ | 12217 | 14021 | 26238 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004700000 | DAUT 6012-01 MAYAGUEZ | 7147 | 6467 | 13614 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004710000 | DAUT 6002-05 MAYAGUEZ | 2028 | 17399 | 19427 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004720000 | DAUT 6002-04 MAYAGUEZ | 5208 | 22410 | 27618 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004730000 | DAUT 6002-03 MAYAGUEZ | 1911 | 8623 | 10535 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004740000 | DAUT 9901-01 CAGUAS | $- | 2566 | 2566 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004750000 | DAUT 3701-01 CAGUAS | $- | 2530 | 2530 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004760000 | DAUT 3406-01 CAGUAS | $- | 24470 | 24470 | FAASt [Automation Program Group 37] (Distribution) | 800361 | 108078
PBUT4 Distribution Automation | 10F004770000 | DAUT 3403-01 CAGUAS | 12906 | 2016 | 14922 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004780000 | DAUT 3402-06 CAGUAS | 5021 | 7721 | 12741 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004790000 | DAUT 3302-01 CAGUAS | $- | 1559 | 1559 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004800000 | DAUT 3301-03 CAGUAS | $- | 2834 | 2834 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004810000 | DAUT 3205-10 CAGUAS | 5359 | 24433 | 29791 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004820000 | DAUT 3101-04 CAGUAS | 36350 | 81379 | 117730 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004830000 | DAUT 3015-09 CAGUAS | 6676 | 5999 | 12675 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004840000 | DAUT 3007-04 CAGUAS | 4976 | 29228 | 34204 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004850000 | DAUT 3006-04 CAGUAS | 9631 | 37730 | 47360 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004860000 | DAUT 2702-02 CAGUAS | 10166 | 3309 | 13475 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004870000 | DAUT 9202-02 BAYAMON | 12790 | 6491 | 19281 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004880000 | DAUT 1802-01 BAYAMON | $- | 1842 | 1842 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004890000 | DAUT 1717-02 BAYAMON | 13049 | 3706 | 16755 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004900000 | DAUT 1707-03 BAYAMON | 39458 | 7307 | 46765 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004910000 | DAUT 7403-01 ARECIBO | 4280 | 26116 | 30396 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004920000 | DAUT 1530-10 BAYAMON | 16866 | 7811 | 24677 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004930000 | DAUT 9105-08 ARECIBO | 5298 | 4211 | 9508 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004940000 | DAUT 9004-11 ARECIBO | 1931 | 24337 | 26268 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004950000 | DAUT 8504-01 ARECIBO | 43500 | 2861 | 46361 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004960000 | DAUT 8013-04 ARECIBO | 15956 | 2399 | 18354 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004970000 | DAUT 8013-03 ARECIBO | $- | 359 | 359 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004980000 | DAUT 8004-02 ARECIBO | $- | 407 | 407 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F004990000 | DAUT 8002-04 ARECIBO | 10283 | 757 | 11040 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005000000 | DAUT 7702-01 ARECIBO | 14245 | 6461 | 20706 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005010000 | DAUT 1102-02 SAN JUAN | 3522 | 166 | 3689 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005020000 | DAUT 1102-05 SAN JUAN | 9058 | 3713 | 12771 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005030000 | DAUT 1203-01 SAN JUAN | 10477 | 12560 | 23037 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005040000 | DAUT 1203-02 SAN JUAN | 11989 | 36623 | 48612 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005050000 | DAUT 1203-03 SAN JUAN | 24805 | 4494 | 29299 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005060000 | DAUT 1657-02 SAN JUAN | 1382 | 3973 | 5355 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005070000 | DAUT 2501-01 SAN JUAN | 2402 | 1523 | 3925 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005080000 | DAUT 2501-02 SAN JUAN | 1605 | 736 | 2341 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005090000 | DAUT 2501-03 SAN JUAN | 1400 | 417 | 1817 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005100000 | DAUT 2604-02 CAGUAS | 6570 | 7606 | 14175 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005110000 | DAUT 2604-03 CAGUAS | 9265 | 12973 | 22238 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005120000 | DAUT 2701-02 CAGUAS | $- | 12688 | 12688 | FAASt [Automation Program Group 37] (Distribution) | 800361 | 108078
PBUT4 Distribution Automation | 10F005130000 | DAUT 2906-02 CAGUAS | 32357 | 94739 | 127096 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005140000 | DAUT 3005-01 CAGUAS | 28644 | 3566 | 32210 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005150000 | DAUT 3010-02 CAGUAS | 2070 | 538 | 2607 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005160000 | DAUT 3014-02 CAGUAS | 35788 | 1293 | 37081 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005170000 | DAUT 3014-03 CAGUAS | 1310 | 310 | 1620 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005180000 | DAUT 3016-05 CAGUAS | 4109 | 150 | 4259 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005190000 | DAUT 3101-01 CAGUAS | 9562 | 2182 | 11744 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005200000 | DAUT 3103-03 CAGUAS | 37387 | 480 | 37867 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005210000 | DAUT 3402-05 CAGUAS | 28015 | 1245 | 29260 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005220000 | DAUT 3602-03 CAGUAS | $- | 1840 | 1840 | FAASt [Automation Program Group 37] (Distribution) | 800361 | 108078
PBUT4 Distribution Automation | 10F005230000 | DAUT 3603-01 CAGUAS | 18147 | 5541 | 23688 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005240000 | DAUT 3603-02 CAGUAS | 11074 | 27397 | 38471 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005250000 | DAUT 4301-03 PONCE | 17110 | 9138 | 26247 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005260000 | DAUT 4501-01 PONCE | 32187 | 7368 | 39555 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005270000 | DAUT 4501-02 PONCE | 17572 | 5796 | 23369 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005280000 | DAUT 4501-03 PONCE | 46173 | 5545 | 51718 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005290000 | DAUT 4501-04 PONCE | $- | 7112 | 7112 | FAASt [Automation Program Group 40] (Distribution) | 800399 | 108081
PBUT4 Distribution Automation | 10F005300000 | DAUT 4501-05 PONCE | 13366 | 128 | 13494 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005310000 | DAUT 4502-02 PONCE | 33553 | 469 | 34022 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005320000 | DAUT 4503-02 PONCE | 33706 | 263 | 33968 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005330000 | DAUT 5002-01 PONCE | 52247 | 38184 | 90431 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005340000 | DAUT 5002-02 PONCE | 40196 | 10598 | 50794 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005350000 | DAUT 5002-04 PONCE | 40638 | 424 | 41062 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005360000 | DAUT 5012-04 PONCE | 21529 | 17217 | 38745 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005370000 | DAUT 5304-02 PONCE | 33018 | 1211 | 34229 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005380000 | DAUT 5304-05 PONCE | 39762 | 27282 | 67044 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005390000 | DAUT 5305-03 PONCE | 26196 | 1458 | 27654 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005400000 | DAUT 5602-01 PONCE | 3703 | 600 | 4303 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005410000 | DAUT 5802-05 PONCE | 10177 | 16047 | 26224 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005420000 | DAUT 5902-03 PONCE | 31633 | 12779 | 44413 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005430000 | DAUT 6001-01 MAYAGUEZ | 9287 | 1538 | 10825 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005440000 | DAUT 6001-02 MAYAGUEZ | 20349 | 1306 | 21655 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005450000 | DAUT 6005-01 MAYAGUEZ | 2372 | 33394 | 35767 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005460000 | DAUT 6008-02 MAYAGUEZ | 13755 | 100 | 13855 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005470000 | DAUT 6401-02 MAYAGUEZ | 8664 | 1206 | 9870 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005480000 | DAUT 6401-04 MAYAGUEZ | 45274 | 496 | 45769 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005490000 | DAUT 6404-01 MAYAGUEZ | 13726 | 187 | 13914 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005500000 | DAUT 6404-02 MAYAGUEZ | 11264 | 1377 | 12641 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005510000 | DAUT 6404-03 MAYAGUEZ | 41415 | 19224 | 60639 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005520000 | DAUT 6404-04 MAYAGUEZ | 35711 | 11486 | 47198 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005530000 | DAUT 6601-01 PONCE | $- | 4878 | 4878 | FAASt [Automation Program Group 40] (Distribution) | 800399 | 108081
PBUT4 Distribution Automation | 10F005540000 | DAUT 6601-02 PONCE | 29033 | 16961 | 45995 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005550000 | DAUT 7003-01 MAYAGUEZ | 358 | 75 | 433 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005560000 | DAUT 7003-04 MAYAGUEZ | 12523 | 410 | 12933 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005570000 | DAUT 7003-05 MAYAGUEZ | 23943 | 25625 | 49567 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005580000 | DAUT 7502-01 MAYAGUEZ | 10925 | 35239 | 46164 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005590000 | DAUT 7503-01 MAYAGUEZ | 10547 | 6592 | 17139 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005600000 | DAUT 7503-03 MAYAGUEZ | 24763 | 21821 | 46584 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005610000 | DAUT 7503-04 MAYAGUEZ | 8781 | 94 | 8875 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005620000 | DAUT 7801-02 MAYAGUEZ | 26015 | 254 | 26270 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005630000 | DAUT 7801-03 MAYAGUEZ | 39365 | 5131 | 44496 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005640000 | DAUT 7802-03 MAYAGUEZ | 28636 | 1769 | 30406 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005650000 | DAUT 7802-04 MAYAGUEZ | 29679 | 13473 | 43152 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005660000 | DAUT 1620-03 SAN JUAN | 3225 | $- | 3225 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005670000 | DAUT 1620-04 SAN JUAN | 5297 | $- | 5297 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005680000 | DAUT 1646-03 SAN JUAN | 359 | 628 | 987 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005690000 | DAUT 1647-06 SAN JUAN | 20 | $- | 20 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005700000 | DAUT 1647-07 SAN JUAN | 20 | $- | 20 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005710000 | DAUT 1647-08 SAN JUAN | 1695 | 7925 | 9620 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005720000 | DAUT 1647-09 SAN JUAN | 34958 | $- | 34958 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005730000 | DAUT 1657-01 SAN JUAN | 1229 | 100 | 1330 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005740000 | DAUT 1657-03 SAN JUAN | 286 | 100 | 386 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005750000 | DAUT 1657-04 SAN JUAN | 572 | 100 | 672 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005760000 | DAUT 1658-15 SAN JUAN | 1001 | $- | 1001 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005770000 | DAUT 1714-03 BAYAMON | $- | 104 | 104 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005780000 | DAUT 1714-05 BAYAMON | 326 | 1076 | 1402 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005790000 | DAUT 1715-02 BAYAMON | 3875 | $- | 3875 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005800000 | DAUT 1715-03 BAYAMON | 51 | $- | 51 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005810000 | DAUT 1715-05 BAYAMON | 3 | $- | 3 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005820000 | DAUT 1801-01 BAYAMON | 315 | 2708 | 3023 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005830000 | DAUT 1801-03 BAYAMON | 754 | 5471 | 6224 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005840000 | DAUT 1802-02 BAYAMON | 1689 | $- | 1689 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005850000 | DAUT 1803-05 BAYAMON | 3100 | 330 | 3430 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005860000 | DAUT 1924-01 BAYAMON | 6149 | 1738 | 7888 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005870000 | DAUT 1924-03 BAYAMON | 1154 | $- | 1154 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005880000 | DAUT 2002-03 SAN JUAN | 65726 | 2198 | 67924 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005890000 | DAUT 2005-10 SAN JUAN | $- | 1250 | 1250 | FAASt [Automation Program Group 36] (TL / Distribution) | 800286 | 108077
PBUT4 Distribution Automation | 10F005900000 | DAUT 2601-02 CAGUAS | 137 | 2629 | 2766 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005910000 | DAUT 2602-01 CAGUAS | 6974 | 8567 | 15541 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005920000 | DAUT 2604-01 CAGUAS | 6546 | 340 | 6886 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005930000 | DAUT 3007-01 CAGUAS | 20 | 327 | 347 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005940000 | DAUT 3008-03 CAGUAS | 4584 | 262 | 4846 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005950000 | DAUT 3009-02 CAGUAS | 3370 | 2564 | 5934 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005960000 | DAUT 3009-03 CAGUAS | 36127 | 1496 | 37623 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005970000 | DAUT 3009-04 CAGUAS | 16445 | 15178 | 31623 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005980000 | DAUT 3016-03 CAGUAS | 3666 | 890 | 4556 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F005990000 | DAUT 3101-03 CAGUAS | 1937 | 44 | 1981 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006000000 | DAUT 3103-02 CAGUAS | 22295 | 12176 | 34471 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006010000 | DAUT 4301-01 PONCE | 31398 | 25859 | 57257 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006020000 | DAUT 5005-01 PONCE | 144 | 335 | 479 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006030000 | DAUT 5005-03 PONCE | 46654 | 5712 | 52366 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006040000 | DAUT 5005-04 PONCE | 887 | 1060 | 1947 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006050000 | DAUT 5005-05 PONCE | 3737 | 427 | 4164 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006060000 | DAUT 5012-01 PONCE | 4379 | 160 | 4539 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006070000 | DAUT 5012-02 PONCE | 11739 | 461 | 12200 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006080000 | DAUT 5018-05 PONCE | 155 | 6481 | 6636 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006090000 | DAUT 5301-01 PONCE | 16845 | 581 | 17427 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006100000 | DAUT 5401-01 PONCE | 44743 | 6759 | 51503 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006110000 | DAUT 5401-03 PONCE | 49926 | 228 | 50154 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006120000 | DAUT 5802-02 PONCE | 9886 | 277 | 10163 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006130000 | DAUT 5902-02 PONCE | 31419 | 2181 | 33599 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006140000 | DAUT 6001-03 MAYAGUEZ | 7996 | 358 | 8354 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006150000 | DAUT 6001-04 MAYAGUEZ | 5547 | 438 | 5985 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006160000 | DAUT 6001-05 MAYAGUEZ | 3912 | 207 | 4119 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006170000 | DAUT 6005-02 MAYAGUEZ | 52077 | 268 | 52344 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006180000 | DAUT 6008-04 MAYAGUEZ | 31981 | 100 | 32081 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006190000 | DAUT 6008-05 MAYAGUEZ | 5008 | 268 | 5275 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006200000 | DAUT 6401-01 MAYAGUEZ | 2976 | 2831 | 5807 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006210000 | DAUT 6401-03 MAYAGUEZ | 82 | $- | 82 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006220000 | DAUT 7502-03 MAYAGUEZ | 30241 | 410 | 30651 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006230000 | DAUT 7502-04 MAYAGUEZ | 17399 | 2208 | 19607 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006240000 | DAUT 7503-02 MAYAGUEZ | 18215 | 75 | 18291 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006250000 | DAUT 7504-01 MAYAGUEZ | 1194 | 376 | 1570 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006260000 | DAUT 7601-01 ARECIBO | 591 | 100 | 691 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006270000 | DAUT 7601-03 ARECIBO | 7452 | 6299 | 13752 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006280000 | DAUT 7701-01 ARECIBO | 24047 | 2215 | 26261 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006290000 | DAUT 7801-04 MAYAGUEZ | 4898 | $- | 4898 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006300000 | DAUT 8004-01 ARECIBO | 5277 | 501 | 5778 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006310000 | DAUT 8004-03 ARECIBO | 4927 | 1059 | 5986 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006320000 | DAUT 8004-04 ARECIBO | 9195 | 1093 | 10288 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006330000 | DAUT 8011-01 ARECIBO | 10172 | 1051 | 11223 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006340000 | DAUT 8011-02 ARECIBO | 6534 | 699 | 7233 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006350000 | DAUT 8011-04 ARECIBO | 3382 | 907 | 4289 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006360000 | DAUT 8401-02 ARECIBO | 6939 | 1654 | 8593 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006370000 | DAUT 8401-04 ARECIBO | 3 | 205 | 209 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006380000 | DAUT 8701-04 ARECIBO | 6158 | 386 | 6544 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006390000 | DAUT 9103-01 ARECIBO | 3258 | 618 | 3876 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006400000 | DAUT 9103-02 ARECIBO | 409 | 225 | 634 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006410000 | DAUT 9103-04 ARECIBO | 94 | 372 | 466 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006420000 | DAUT 9703-01 CAGUAS | 2119 | 589 | 2708 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006430000 | DAUT 2003-01 SAN JUAN | 26038 | 22305 | 48343 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006440000 | DAUT 2001-04 SAN JUAN | 29913 | 5697 | 35610 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006450000 | DAUT 2001-03 SAN JUAN | 37146 | 3889 | 41035 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006460000 | DAUT 1620-02 SAN JUAN | 2546 | 33356 | 35903 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006470000 | DAUT 1619-01 SAN JUAN | 50 | 152 | 202 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006480000 | DAUT 1618-02 SAN JUAN | 8390 | 4448 | 12838 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006490000 | DAUT 1607-04 SAN JUAN | 3621 | 21379 | 25001 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006500000 | DAUT 1416-02 SAN JUAN | 1497 | 11945 | 13443 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006510000 | DAUT 1416-04 SAN JUAN | 5524 | 7485 | 13009 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006520000 | DAUT 1348-06 SAN JUAN | 1305 | 1194 | 2499 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006530000 | DAUT 1346-06 SAN JUAN | 1791 | 44 | 1834 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006540000 | DAUT 1346-01 SAN JUAN | 685 | 144 | 829 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006550000 | DAUT 1334-02 SAN JUAN | 29685 | 15987 | 45672 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006560000 | DAUT 1301-04 SAN JUAN | 8038 | 36628 | 44666 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006570000 | DAUT 1301-03 SAN JUAN | 10534 | 13095 | 23629 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006580000 | DAUT 1301-02 SAN JUAN | $- | 3116 | 3116 | FAASt [Automation Program Group 36] (TL / Distribution) | 800286 | 108077
PBUT4 Distribution Automation | 10F006590000 | DAUT 1301-01 SAN JUAN | 17361 | 6119 | 23481 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006600000 | DAUT 1106-02 SAN JUAN | 1677 | 5552 | 7229 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006610000 | DAUT 1102-04 SAN JUAN | 4670 | 22193 | 26862 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006620000 | DAUT 5805-01 PONCE | 151 | 747 | 898 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006630000 | DAUT 5802-04 PONCE | 23759 | 7128 | 30887 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006640000 | DAUT 5012-05 PONCE | 201 | $- | 201 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006650000 | DAUT 5010-04 PONCE | 75 | $- | 75 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006660000 | DAUT 5010-03 PONCE | 17000 | 5238 | 22238 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006670000 | DAUT 5003-04 PONCE | 10015 | 6731 | 16746 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006680000 | DAUT 5003-03 PONCE | 19454 | 13285 | 32739 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006690000 | DAUT 5003-02 PONCE | 5498 | 24653 | 30151 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006700000 | DAUT 5003-01 PONCE | 35083 | 10927 | 46010 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006710000 | DAUT 4503-01 PONCE | 44441 | 405 | 44846 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006720000 | DAUT 4006-05 PONCE | 22012 | 17011 | 39023 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006730000 | DAUT 4006-04 PONCE | 42633 | 1652 | 44284 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006740000 | DAUT 4006-02 PONCE | 11390 | 784 | 12174 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006750000 | DAUT 4002-01 PONCE | 27182 | 21165 | 48348 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006760000 | DAUT 7903-07 MAYAGUEZ | 75 | $- | 75 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006770000 | DAUT 7303-03 MAYAGUEZ | 31250 | 864 | 32113 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006780000 | DAUT 7303-02 MAYAGUEZ | 35931 | 30107 | 66039 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006790000 | DAUT 7201-04 MAYAGUEZ | 21457 | 1669 | 23127 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006800000 | DAUT 7201-01 MAYAGUEZ | 104 | $- | 104 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006810000 | DAUT 7101-02 MAYAGUEZ | 5207 | 42526 | 47733 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006820000 | DAUT 7012-02 MAYAGUEZ | 510 | 15074 | 15584 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006830000 | DAUT 7002-04 MAYAGUEZ | 6197 | 100 | 6298 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006840000 | DAUT 7002-03 MAYAGUEZ | 4957 | 100 | 5057 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006850000 | DAUT 7002-02 MAYAGUEZ | 13782 | 147 | 13929 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006860000 | DAUT 6014-01 MAYAGUEZ | 100 | 102 | 202 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006870000 | DAUT 6002-02 MAYAGUEZ | 13785 | 2642 | 16426 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006880000 | DAUT 6002-01 MAYAGUEZ | 13194 | 5332 | 18526 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006890000 | DAUT 3201-03 CAGUAS | 151 | 909 | 1060 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006900000 | DAUT 3201-01 CAGUAS | 6405 | 30185 | 36590 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006910000 | DAUT 3102-02 CAGUAS | 125 | 524 | 650 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006920000 | DAUT 3013-04 CAGUAS | 16138 | 10832 | 26969 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006930000 | DAUT 3004-04 CAGUAS | 9233 | 1389 | 10621 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006940000 | DAUT 3004-02 CAGUAS | 12193 | 2671 | 14864 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006950000 | DAUT 2906-04 CAGUAS | 25016 | 416 | 25432 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006960000 | DAUT 2906-03 CAGUAS | 13934 | $- | 13934 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006970000 | DAUT 2605-02 CAGUAS | 3112 | $- | 3112 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006980000 | DAUT 2603-10 CAGUAS | 45782 | 10662 | 56444 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F006990000 | DAUT 2603-08 CAGUAS | 6301 | 1569 | 7870 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007000000 | DAUT 2603-07 CAGUAS | 8037 | 4345 | 12382 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007010000 | DAUT 9404-01 BAYAMON | 22867 | 255 | 23122 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007020000 | DAUT 9403-02 BAYAMON | 4555 | 294 | 4849 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007030000 | DAUT 9403-01 BAYAMON | 7808 | 712 | 8520 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007040000 | DAUT 9401-03 BAYAMON | 26265 | 2851 | 29116 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007050000 | DAUT 9207-09 BAYAMON | 7374 | 9065 | 16439 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007060000 | DAUT 9207-05 BAYAMON | 33338 | 5326 | 38664 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007070000 | DAUT 1924-04 BAYAMON | 739 | 4033 | 4772 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007080000 | DAUT 1908-04 BAYAMON | 10230 | 558 | 10788 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007090000 | DAUT 1907-03 BAYAMON | 3513 | 4338 | 7851 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007100000 | DAUT 1903-03 BAYAMON | 19510 | $- | 19510 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007110000 | DAUT 1903-02 BAYAMON | 15133 | 69 | 15202 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007120000 | DAUT 1903-01 BAYAMON | 11450 | 21298 | 32748 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007130000 | DAUT 1803-04 BAYAMON | 8065 | 17964 | 26029 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007140000 | DAUT 1803-02 BAYAMON | 1204 | 8411 | 9615 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007150000 | DAUT 1716-02 BAYAMON | 383 | $- | 383 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007160000 | DAUT 1713-04 BAYAMON | 3647 | 5983 | 9630 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007180000 | DAUT 8504-02 ARECIBO | 41466 | 3547 | 45012 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007190000 | DAUT 8302-04 ARECIBO | 24640 | 15583 | 40223 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007200000 | DAUT 8301-02 ARECIBO | $- | 6163 | 6163 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007210000 | DAUT 8014-07 ARECIBO | 6407 | $- | 6407 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007220000 | DAUT 8014-06 ARECIBO | 22046 | 104 | 22150 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007250000 | DAUT 8002-01 ARECIBO | 11769 | 3512 | 15281 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007260000 | DAUT 7404-06 ARECIBO | 1117 | 94 | 1211 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007270000 | DAUT 7402-03 ARECIBO | 655 | 6772 | 7427 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007280000 | DAUT 7402-02 ARECIBO | 761 | 19061 | 19822 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007290000 | DAUT 7002-01 MAYAGUEZ | 1337 | 37032 | 38369 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007450000 | DAUT SAN JUAN 1110-01 | $- | 589 | 589 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007460000 | DAUT SAN JUAN 1110-02 | $- | 103 | 103 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007470000 | DAUT SAN JUAN 1110-05 | $- | 206 | 206 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007480000 | DAUT SAN JUAN 1111-01 | $- | 1444 | 1444 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007550000 | DAUT SAN JUAN 1512-04 | $- | 1314 | 1314 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007590000 | DAUT SAN JUAN1530-08 | $- | 399 | 399 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007610000 | DAUT SAN JUAN 1113-01 | $- | 424 | 424 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007650000 | DAUT SAN JUAN 1115-05 | $- | 1444 | 1444 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007660000 | DAUT MAYAGUEZÂ 7103-01 | $- | 8116 | 8116 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007670000 | DAUT MAYAGÃœEZ 7103-02 | $- | 5210 | 5210 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007680000 | DAUT MAYAGUEZ 7103-04 | $- | 4347 | 4347 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007710000 | DAUT SAN JUAN 1335-01 | $- | 1234 | 1234 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007890000 | DAUT MAYAG. 6702-03 | $- | 2323 | 2323 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007900000 | DAUT MAYAG. 6703-02 | $- | 6090 | 6090 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F007910000 | DAUT MAYAG. 6705-02 | $- | 3544 | 3544 | 0 | 0 | 0
PBUT4 Distribution Automation | 10F008050000 | DAUT SAN JUAN 1526-03 | $- | 1622 | 1622 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F000160000 | Arecibo Short Term Group 1 - D | $- | 140394 | 140394 | FAASt [Automation Program Group 1A] (Distribution) | 688623 | 107781
PBUT4 Distribution Automation | 14F000350000 | Bayamon Short Term Group 1 - D | $- | 756289 | 756289 | FAASt [Automation Program Group 1A] (Distribution) | 688623 | 107781
PBUT4 Distribution Automation | 14F000800000 | Cagus Short Term Group 1 - Dis | $- | 455565 | 455565 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F000960000 | Distribution Automation | 1860966 | 104276 | 1965242 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F001290000 | Mayaguez Short Term Group 3 | $- | 1642118 | 1642118 | FAASt [Automation Program Group 1B] (Distribution) | 752500 | 107996
PBUT4 Distribution Automation | 14F001430000 | Ponce ST2 Dist Automation | $- | 237233 | 237233 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F001610000 | San Juan T3 - Dist Automat | $- | 1109842 | 1109842 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F003260000 | Arecibo Short Term Group 2 - D | $- | 104603 | 104603 | FAASt [Automation Program Group 1A] (Distribution) | 688623 | 107781
PBUT4 Distribution Automation | 14F003270000 | Bayamon Short Term Group 3 - D | $- | 584781 | 584781 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F003280000 | Bayamon Short Term Group 2 - D | 97328 | 51834 | 149162 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F003290000 | Carolina Short Term Group 2 - | $- | 1726298 | 1726298 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F003300000 | Carolina Short Term Group 3 | $- | 1801075 | 1801075 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F003310000 | Mayaguez Short Term Group 1 | $- | 7087071 | 7087071 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F003320000 | Mayaguez Short Term Group 2 | $- | 3268463 | 3268463 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F003330000 | Ponce ST1 Dist Automation | 187723 | 178304 | 366027 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F003340000 | San Juan ST1 Dist Automa | $- | 3449791 | 3449791 | FAASt [Automation Program Group 1D] (Distribution) | 752503 | 107998
PBUT4 Distribution Automation | 14F003350000 | San Juan ST2 - Dist Automat | $- | 368909 | 368909 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F003510000 | Caguas ST G-2 Dist Autom | $- | 1011292 | 1011292 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F003520000 | Caguas ST G-3 Dist Autom | $- | 912993 | 912993 | FAASt [Automation Program Group 1C] (Distribution) | 752502 | 107997
PBUT4 Distribution Automation | 14F003530000 | Caguas ST G-4 Distr Automation | 155525 | 18384 | 173909 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F003540000 | Caguas ST G-5 Dist Automation | 182631 | 44856 | 227487 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F003550000 | Caguas ST G-6 Distr Automation | $- | 275198 | 275198 | FAASt [Automation Program Group 1C] (Distribution) | 752502 | 107997
PBUT4 Distribution Automation | 14F003560000 | Caguas ST G-7 Distr Automation | $- | 129845 | 129845 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F003570000 | Caguas ST G-8 Distr Automation | $- | 291173 | 291173 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F003580000 | Yunque2305-01 Supply Dist Auto | 12968 | 428 | 13396 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F003590000 | Mayag S T Group 4-Dist Automa | $- | 1552854 | 1552854 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004670000 | Arecibo Short TermGroup3 Autom | 42841 | 19530 | 62371 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004680000 | Arecibo Short TermGroup4 Autom | 39994 | 27848 | 67842 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004690000 | Arecibo Short TermGroup5 Autom | $- | 25220 | 25220 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F004700000 | Arecibo Short TermGroup6 Autom | 108562 | 255993 | 364554 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004710000 | Arecibo Short TermGroup7 Autom | $- | 223527 | 223527 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F004720000 | Arecibo Short TermGroup8 Autom | 63354 | 15867 | 79221 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004730000 | Arecibo Short TermGroup9 Autom | 129844 | 138655 | 268499 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004740000 | Arecibo Short TermGroup10 Auto | 60638 | 52094 | 112732 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004750000 | Arecibo Short TermGroup11 Auto | 147765 | 73538 | 221303 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004760000 | Arecibo Short TermGroup12 Auto | 146225 | 51467 | 197693 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004770000 | BayamÃ³n Short TermGroup4 Autom | $- | 565125 | 565125 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F004780000 | BayamÃ³n Short TermGroup5 Autom | 266509 | 56141 | 322650 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004790000 | BayamÃ³n Short TermGroup6 Autom | 152346 | 74396 | 226741 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004800000 | BayamÃ³n Short TermGroup7 Autom | 200456 | 162834 | 363290 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004810000 | BayamÃ³n Short TermGroup8 Autom | $- | 1471152 | 1471152 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F004820000 | Bayamon Short TermGroup9 Autom | $- | 787914 | 787914 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F004830000 | Caguas Short TermGroup9 Autom | 173119 | 86075 | 259194 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004840000 | Caguas Short TermGroup10 Autom | $- | 267435 | 267435 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F004850000 | Caguas Short TermGroup11 Autom | 188048 | 46054 | 234102 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004860000 | Caguas Short TermGroup12 Autom | 188050 | 67005 | 255055 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004870000 | Caguas Short TermGroup13 Autom | 132014 | 74799 | 206813 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004880000 | Caguas Short TermGroup14 Autom | 183835 | 80560 | 264395 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004890000 | Caguas Short TermGroup15 Autom | 153915 | 20227 | 174142 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004900000 | Mayaguez Short TermGroup5 Aut | $- | 778236 | 778236 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004910000 | Mayaguez Short TermGroup6 Auto | $- | 2452803 | 2452803 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004920000 | Mayaguez Short TermGroup7 Aut | $- | 294663 | 294663 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004930000 | Mayaguez Short TermGroup8 Aut | $- | 2232121 | 2232121 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004940000 | Mayaguez Short TermGroup9 Aut | $- | 821570 | 821570 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004950000 | Mayaguez Short TermGroup10 Aut | $- | 2025458 | 2025458 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004960000 | Mayaguez Short TermGroup11 Aut | $- | 2194986 | 2194986 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004970000 | Mayaguez Short TermGroup12 Aut | 67291 | 52992 | 120283 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F004980000 | Mayaguez Short TermGroup13 Aut | $- | 1668156 | 1668156 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F004990000 | Mayaguez Short TermGroup14 Aut | $- | 467040 | 467040 | FAASt [Automation Program Group 3] (Distribution) | 705657 | 107826
PBUT4 Distribution Automation | 14F005000000 | Ponce Short TermGroup3 Autom | 147354 | 145516 | 292870 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005010000 | Ponce Short TermGroup4 Autom | 89861 | 196532 | 286392 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005020000 | Ponce Short TermGroup5 Autom | 78267 | 48250 | 126517 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005030000 | Ponce Short TermGroup6 Autom | 51524 | 13286 | 64809 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005040000 | Ponce Short TermGroup7 Autom | 136757 | 25138 | 161895 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005050000 | Ponce Short TermGroup8 Autom | 195496 | 51605 | 247101 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005060000 | Ponce Short TermGroup9 Autom | 80671 | 29343 | 110013 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005070000 | Ponce Short TermGroup10 Autom | 106185 | 31271 | 137457 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005080000 | Ponce Short TermGroup11 Autom | $- | 126069 | 126069 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F005090000 | Ponce Short TermGroup12 Autom | $- | 769896 | 769896 | FAASt [Automation Program Group 2] (Distribution) | 740662 | 107939
PBUT4 Distribution Automation | 14F005100000 | Ponce Short TermGroup13 Autom | 80863 | 117002 | 197866 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005110000 | San Juan Short TermGroup4 Aut | $- | 2586179 | 2586179 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F005120000 | San Juan Short TermGroup5 Aut | $- | 181621 | 181621 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F005130000 | San Juan Short TermGroup6 Aut | $- | 2770909 | 2770909 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F005140000 | San Juan Short TermGroup7 Aut | 117865 | 44124 | 161989 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F005150000 | San Juan Short TermGroup8 Aut | $- | 163359 | 163359 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F005160000 | San Juan Short TermGroup9 Aut | $- | 157637 | 157637 | FAASt [Automation Program Group 1A] (Distribution) | 688623 | 107781
PBUT4 Distribution Automation | 14F005170000 | San Juan Short TermGroup10 Aut | $- | 1142312 | 1142312 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F005180000 | San Juan Short TermGroup11 Aut | $- | 792586 | 792586 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F005190000 | San Juan Short TermGroup12 Aut | $- | 1955764 | 1955764 | FAASt [Automation Program Group 4] (Distribution) | 741678 | 107947
PBUT4 Distribution Automation | 14F005200000 | Trans & Distribut Automation | 4052984 | 4126265 | 8179249 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019070000 | 38kV Reclosers Tline 4800 | 57128 | 328638 | 385766 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019080000 | 38kV Reclosers Tline 1500 | 32783 | 62969 | 95752 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019090000 | 38kV Reclosers TLine 3700 | 28541 | 59443 | 87984 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019100000 | 38kV Reclosers TLine 15700 | 9838 | 407 | 10245 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019110000 | 38kV Reclosers TLine 1900 | $- | 39089 | 39089 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) | 805519 | 108092
PBUT4 Distribution Automation | 14F019120000 | 38kV Reclosers TLine 2100 | $- | 45871 | 45871 | FAASt [38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect.] (Transmission) | 805517 | 108091
PBUT4 Distribution Automation | 14F019130000 | 38kV Reclosers TLine 7800 | $- | 61311 | 61311 | FAASt [38kV Recloser TL 7800 Dorado TC to Vega Alta Sect.] (Transmission) | 805521 | 108093
PBUT4 Distribution Automation | 14F019140000 | 38kV Reclosers TLine 800 | 44236 | 37027 | 81263 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019150000 | 38kV Reclosers TLine 13400 | 28922 | 49760 | 78683 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019160000 | 38kV Reclosers TLine 12600 | 30248 | 42883 | 73131 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019170000 | 38kV Reclosers TLine 100 | 28896 | 49922 | 78818 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019180000 | 38kV Reclosers TLine 8100 | 171783 | 49280 | 221063 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019190000 | 38kV Reclosers TLine 1600 | 36916 | 35719 | 72635 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019200000 | 38kV Reclosers TLine 2000 | 38490 | 59893 | 98383 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019210000 | 38kV Reclosers TLine 2200 | 33832 | 47350 | 81182 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019220000 | 38kV Reclosers TLine 3100 | 37786 | 42212 | 79998 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019230000 | 38kV Reclosers TLine 3000 | 29746 | 88868 | 118615 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019240000 | 38kV Reclosers TLine 3600 | 48253 | 57396 | 105649 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019250000 | 38kV Reclosers TLine 6500 | 36568 | 53919 | 90487 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019260000 | 38kV Reclosers TLine 5600 | 36890 | 71300 | 108190 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019270000 | 38kV Reclosers TLine 8200 | 35879 | 52925 | 88805 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019280000 | 38kV Reclosers TLine 3200 | 32195 | 35226 | 67420 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F019640000 | Test Laboratory Equipment | $- | 7134 | 7134 | FAASt [Test and Technology Laboratory] (Building) | 679006 | 11862
PBUT4 Distribution Automation | 14F021140000 | 38kv Reclosures TLine 300 | $- | 28927 | 28927 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021150000 | 38kv Reclosures TLine 500 | $- | 28677 | 28677 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021160000 | 38kv Reclosures TLine 700 | $- | 28203 | 28203 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021170000 | 38kv Reclosures TLine 2400 | $- | 16901 | 16901 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021180000 | 38kv Reclosures TLine 2600 | $- | 15730 | 15730 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021190000 | 38kv Reclosures TLine 2700 | $- | 16588 | 16588 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021200000 | 38kv Reclosures TLine 2800 | $- | 13992 | 13992 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021210000 | 38kv Reclosures TLine 4700 | $- | 16898 | 16898 | 0 | 759522 | 0
PBUT4 Distribution Automation | 14F021220000 | 38kv Reclosures TLine 5200 | $- | 13224 | 13224 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021230000 | 38kv Reclosures TLine 5400 | $- | 13355 | 13355 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021240000 | 38kv Reclosures TLine 6000 | $- | 14645 | 14645 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021250000 | 38kv Reclosures TLine 7100 | $- | 15506 | 15506 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021260000 | 38kv Reclosures TLine 8500 | $- | 7788 | 7788 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021270000 | 38kv Reclosures TLine 8900 | $- | 20374 | 20374 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021280000 | 38kv Reclosures TLine 9400 | $- | 15656 | 15656 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021290000 | 38kv Reclosures TLine 10000 | $- | 17054 | 17054 | 0 | 0 | 0
PBUT4 Distribution Automation | 14F021300000 | 38kv Reclosures TLine 13700 | $- | 14261 | 14261 | 0 | 0 | 0
PBUT5 Distr Streetlighting | 14F001690000 | Streetlighting Program | 2991198 | 1619499 | 4610697 | 0 | 0 | 0
PBUT5 Distr Streetlighting | 14F001700000 | Streetlight Region Ponce | 484 | -484 | $- | 0 | 0 | 0
PBUT5 Distr Streetlighting | 14F001710000 | Streetlight Region Mayaguez | 0 | $- | 0 | 0 | 0 | 0
PBUT5 Distr Streetlighting | 14F001720000 | Streetlight Region Bayamon | 0 | $- | 0 | 0 | 0 | 0
PBUT5 Distr Streetlighting | 14F001730000 | Streetlight Region Caguas | 0 | $- | 0 | 0 | 0 | 0
PBUT5 Distr Streetlighting | 14F001740000 | Streetlight Region Arecibo | 0 | $- | 0 | 0 | 0 | 0
PBUT5 Distr Streetlighting | 14F004520000 | Streetlighting Program-Utuado | $- | 1864554 | 1864554 | FAASt [Utuado Streetlighting] (Distribution) | 671396 | 11530
PBUT5 Distr Streetlighting | 14F004540000 | StreetlightingProg-Barceloneta | $- | 1356659 | 1356659 | FAASt [Barceloneta Streetlighting] (Distribution) | 671400 | 11529
PBUT5 Distr Streetlighting | 14F008790000 | Streetlighting Prog-San Juan | $- | 6793086 | 6793086 | FAASt [San Juan Streetlighting] (Distribution) | 666894 | 11519
PBUT5 Distr Streetlighting | 14F012790000 | Streetlighting Program-Arecibo | $- | 1936111 | 1936111 | FAASt [Arecibo Streetlighting] (Distribution) | 678795 | 11535
PBUT5 Distr Streetlighting | 14F012820000 | Streetlighting Program - Cayey | $- | 2336869 | 2336869 | FAASt [Cayey Streetlighting] (Distribution) | 690483 | 11552
PBUT5 Distr Streetlighting | 14F012830000 | Streetlighting Program-Guayama | $- | 1206602 | 1206602 | FAASt [Guayama Streetlighting] (Distribution) | 690721 | 11531
PBUT5 Distr Streetlighting | 14F012850000 | Streetlighting Program - Ponce | $- | 2689171 | 2689171 | FAASt [Ponce Streetlighting] (Distribution) | 678794 | 11527
PBUT5 Distr Streetlighting | 14F012870000 | Streetlighting Program-Humacao | $- | 836877 | 836877 | FAASt [Humacao Streetlighting] (Distribution) | 690480 | 11683
PBUT5 Distr Streetlighting | 14F012880000 | Streetlighting Program-Isabela | $- | 773179 | 773179 | FAASt [Isabela Streetlighting] (Distribution) | 686482 | 11572
PBUT5 Distr Streetlighting | 14F013770000 | Streetlighting Progr-Canovanas | $- | 1655341 | 1655341 | FAASt [Canovanas Streetlighting] (Distribution) | 701473 | 11693
PBUT5 Distr Streetlighting | 14F013780000 | Streetlighting Program-Juncos | $- | 1638341 | 1638341 | FAASt [Juncos Streetlighting] (Distribution) | 693543 | 11634
PBUT5 Distr Streetlighting | 14F013790000 | Streetlighting Program-Vieques | $- | 1021953 | 1021953 | FAASt [Vieques Streetlighting] (Distribution) | 698522 | 11582
PBUT5 Distr Streetlighting | 14F013810000 | Streetlighting Program-Maricao | $- | 515697 | 515697 | FAASt [Maricao Streetlighting] (Distribution) | 698427 | 11525
PBUT5 Distr Streetlighting | 14F013830000 | Streetlighting Prog-Hormiguero | $- | 903570 | 903570 | FAASt [Hormigueros Streetlighting] (Distribution) | 698432 | 11523
PBUT5 Distr Streetlighting | 14F013860000 | Streetlighting Progr-Vega Baja | $- | 1266487 | 1266487 | FAASt [Vega Baja Streetlighting] (Distribution) | 697183 | 11668
PBUT5 Distr Streetlighting | 14F013870000 | Streetlighting Progra-Toa Alta | $- | 1431769 | 1431769 | FAASt [Toa Alta Streetlighting] (Distribution) | 693788 | 11547
PBUT5 Distr Streetlighting | 14F013880000 | Streetlighting Prog-Rio Grande | $- | 632194 | 632194 | FAASt [Rio Grande Streetlighting] (Distribution) | 693615 | 11685
PBUT5 Distr Streetlighting | 14F013900000 | Streetlighting Prog-Juana Diaz | $- | 2240962 | 2240962 | FAASt [Juana Diaz Streetlighting] (Distribution) | 699814 | 11576
PBUT5 Distr Streetlighting | 14F014590000 | Streetlighting Program - Yauco | $- | 2911816 | 2911816 | FAASt [Yauco Streetlighting] (Distribution) | 704793 | 11691
PBUT5 Distr Streetlighting | 14F014600000 | Streetlighting Program-Fajardo | $- | 2125985 | 2125985 | FAASt [Fajardo Streetlighting] (Distribution) | 704862 | 11728
PBUT5 Distr Streetlighting | 14F014650000 | Streetlighting Program - Moca | $- | 5172 | 5172 | FAASt [Moca Streetlighting] (Distribution) | 704741 | 11737
PBUT5 Distr Streetlighting | 14F014660000 | Streetlighting Prog-Sta Isabel | $- | 2225116 | 2225116 | FAASt [Santa Isabel Streetlighting] (Distribution) | 704757 | 11638
PBUT5 Distr Streetlighting | 14F014680000 | Streetlighting Program - Camuy | $- | 2127320 | 2127320 | FAASt [Camuy Streetlighting] (Distribution) | 704931 | 11651
PBUT5 Distr Streetlighting | 14F014690000 | Streetlighting Prog-San Sebast | $- | 2719290 | 2719290 | FAASt [San Sebastian Streetlighting] (Distribution) | 704744 | 11626
PBUT5 Distr Streetlighting | 14F014710000 | Streetlighting Prog-SanLorenzo | $- | 1075038 | 1075038 | FAASt [San Lorenzo Streetlighting] (Distribution) | 704929 | 11635
PBUT5 Distr Streetlighting | 14F017010000 | Streetlighting Program - Lares | $- | 10275 | 10275 | FAASt [Lares Streetlighting] (Distribution) | 713795 | 11624
PBUT5 Distr Streetlighting | 14F017260000 | Streetlighting Program-Rincon | $- | 10050 | 10050 | FAASt [Rincón Streetlighting] (Distribution) | 714641 | 11630
PBUT5 Distr Streetlighting | 14F018000000 | Streetlighting Prog-Aguas Buen | $- | 4619 | 4619 | FAASt [Aguas Buenas Streetlighting] (Distribution) | 724941 | 11733
PBUT5 Distr Streetlighting | 14F018010000 | Streetlighting Prog-Cabo Rojo | $- | 1831335 | 1831335 | FAASt [Cabo Rojo Streetlighting] (Distribution) | 724603 | 11684
PBUT5 Distr Streetlighting | 14F018020000 | Streetlighting Program-Ciales | $- | 4459 | 4459 | FAASt [Ciales Streetlighting] (Distribution) | 724669 | 11730
PBUT5 Distr Streetlighting | 14F018040000 | Streetlighting Prog-Guayanilla | $- | 6888 | 6888 | FAASt [Guayanilla Streetlighting] (Distribution) | 724605 | 11732
PBUT5 Distr Streetlighting | 14F018060000 | Streetlighting Program - LoÃ­za | $- | 1132121 | 1132121 | FAASt [Loiza Streetlighting] (Distribution) | 724828 | 11692
PBUT5 Distr Streetlighting | 14F018070000 | Streetlighting Prog - Patillas | $- | 4594 | 4594 | FAASt [Patillas Streetlighting] (Distribution) | 724670 | 11731
PBUT5 Distr Streetlighting | 14F018080000 | Streetlighting Prog - PeÃ±uelas | $- | 3506 | 3506 | FAASt [Penuelas Streetlighting] (Distribution) | 724781 | 11736
PBUT5 Distr Streetlighting | 14F018090000 | Streetlighting Prog-Quebradill | $- | 8003 | 8003 | FAASt [Quebradillas Streetlighting] (Distribution) | 724716 | 11729
PBUT5 Distr Streetlighting | 14F018100000 | Streetlighting Prog-SÃ¡bana Gra | $- | 4650 | 4650 | FAASt [Sabana Grande Streetlighting] (Distribution) | 724599 | 11738
PBUT5 Distr Streetlighting | 14F018510000 | Streetlighting Prog-AguadillP2 | $- | 7868 | 7868 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | 734859 | 11780
PBUT5 Distr Streetlighting | 14F018520000 | Streetlighting Prog-AguadillP3 | $- | 14217 | 14217 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | 735338 | 11834
PBUT5 Distr Streetlighting | 14F018530000 | Streetlighting Prog-Arecibo P2 | $- | 6901 | 6901 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | 735131 | 11775
PBUT5 Distr Streetlighting | 14F018540000 | Streetlighting Prog-Arecibo P3 | $- | 11217 | 11217 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | 734853 | 11837
PBUT5 Distr Streetlighting | 14F018550000 | Streetlighting Prog-Bayamon P2 | $- | 11728 | 11728 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | 735470 | 11804
PBUT5 Distr Streetlighting | 14F018560000 | Streetlighting Prog-Bayamon P3 | $- | 13328 | 13328 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | 735472 | 11833
PBUT5 Distr Streetlighting | 14F018570000 | Streetlighting Prog-CaboRojoP2 | $- | 5613 | 5613 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | 734393 | 11805
PBUT5 Distr Streetlighting | 14F018580000 | Streetlighting Prog-CaboRojoP3 | $- | 9254 | 9254 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | 734396 | 107915
PBUT5 Distr Streetlighting | 14F018590000 | Streetlighting Prog-Caguas P2 | $- | 3222 | 3222 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | 746111 | 11778
PBUT5 Distr Streetlighting | 14F018600000 | Streetlighting Prog-Caguas P3 | $- | 11802 | 11802 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | 735672 | 11838
PBUT5 Distr Streetlighting | 14F018610000 | Streetlighting Prog-CarolinaP2 | $- | 5454 | 5454 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | 735665 | 11783
PBUT5 Distr Streetlighting | 14F018620000 | Streetlighting Prog-CarolinaP3 | $- | 20314 | 20314 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | 735496 | 11835
PBUT5 Distr Streetlighting | 14F018630000 | Streetlighting Prog-Guayama P2 | $- | 7100 | 7100 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | 734791 | 11808
PBUT5 Distr Streetlighting | 14F018640000 | Streetlighting Prog-Guayama P3 | $- | 9244 | 9244 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | 734789 | 107916
PBUT5 Distr Streetlighting | 14F018650000 | Streetlighting Prog-GuaynaboP2 | $- | 35292 | 35292 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | 735677 | 11801
PBUT5 Distr Streetlighting | 14F018660000 | Streetlighting Prog-GuaynaboP3 | $- | 19949 | 19949 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | 735499 | 107921
PBUT5 Distr Streetlighting | 14F018670000 | Streetlighting Prog-Humacao P2 | $- | 4952 | 4952 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | 735493 | 11799
PBUT5 Distr Streetlighting | 14F018680000 | Streetlighting Prog-Humacao P3 | $- | 8294 | 8294 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | 735487 | 107920
PBUT5 Distr Streetlighting | 14F018690000 | Streetlighting Prog-Isabela P2 | $- | 2404 | 2404 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | 734927 | 11773
PBUT5 Distr Streetlighting | 14F018700000 | Streetlighting Prog-Isabela P3 | $- | 10787 | 10787 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | 734928 | 107917
PBUT5 Distr Streetlighting | 14F018710000 | Streetlighting Prog-MayaguezP2 | $- | 2170 | 2170 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | 735357 | 11777
PBUT5 Distr Streetlighting | 14F018720000 | Streetlighting Prog-MayaguezP3 | $- | 262735 | 262735 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | 735360 | 11832
PBUT5 Distr Streetlighting | 14F018730000 | Streetlighting Prog-Ponce P2 | $- | 5434 | 5434 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | 734728 | 11774
PBUT5 Distr Streetlighting | 14F018740000 | Streetlighting Prog-Ponce P3 | $- | 10174 | 10174 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | 734760 | 11830
PBUT5 Distr Streetlighting | 14F018750000 | Streetlighting Prog-RioGrandP2 | $- | 3453 | 3453 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | 737804 | 11809
PBUT5 Distr Streetlighting | 14F018760000 | Streetlighting Prog-RioGrandP3 | $- | 11010 | 11010 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | 737798 | 107924
PBUT5 Distr Streetlighting | 14F018770000 | Streetlighting Prog-SanJuan P2 | $- | 4118 | 4118 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | 746108 | 11779
PBUT5 Distr Streetlighting | 14F018780000 | Streetlighting Prog-SanJuan P3 | $- | 5150 | 5150 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | 737712 | 11836
PBUT5 Distr Streetlighting | 14F018790000 | Streetlighting Prog-ToaAlta P2 | $- | 13710 | 13710 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | 737707 | 11797
PBUT5 Distr Streetlighting | 14F018800000 | Streetlighting Prog-ToaAlta P3 | $- | 6398 | 6398 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | 737699 | 107923
PBUT5 Distr Streetlighting | 14F018810000 | Streetlighting Prog-ToaBaja P2 | $- | 6110 | 6110 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | 735960 | 11803
PBUT5 Distr Streetlighting | 14F018820000 | Streetlighting Prog-ToaBaja P3 | $- | 15586 | 15586 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | 735959 | 107922
PBUT5 Distr Streetlighting | 14F018830000 | Streetlighting Prog-TrujilloP2 | $- | 6084 | 6084 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | 735954 | 11772
PBUT5 Distr Streetlighting | 14F018840000 | Streetlighting Prog-TrujilloP3 | $- | 12567 | 12567 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | 735952 | 11831
PBUT5 Distr Streetlighting | 14F018850000 | Streetlighting Prog-VegaBajaP2 | $- | 9890 | 9890 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | 735940 | 11806
PBUT5 Distr Streetlighting | 14F018860000 | Streetlighting Prog-VegaBajaP3 | $- | 11259 | 11259 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | 735483 | 107919
PBUT6 Distr Line Rebuild | 14F000040000 | 8010-01Â Dominguito | $- | 20497 | 20497 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 436616 | 107551
PBUT6 Distr Line Rebuild | 14F000050000 | ManatÃ­Â 13.2 kVÂ 8404-03 | $- | 76816 | 76816 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 436616 | 107551
PBUT6 Distr Line Rebuild | 14F000060000 | ManatÃ­Â 13.2 kVÂ 8404-04 | $- | 23453 | 23453 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 436616 | 107551
PBUT6 Distr Line Rebuild | 14F000070000 | Cruce Davila 8501-02 | $- | 9588 | 9588 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 436616 | 107551
PBUT6 Distr Line Rebuild | 14F000080000 | CialesÂ 8701-01 | $- | 36985 | 36985 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 436616 | 107551
PBUT6 Distr Line Rebuild | 14F000090000 | CialesÂ 8701-02 | $- | 18488 | 18488 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 436616 | 107551
PBUT6 Distr Line Rebuild | 14F000100000 | Utuado Pueblo 8101-03 (L) | $- | 209247 | 209247 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | 797148 | 108074
PBUT6 Distr Line Rebuild | 14F000110000 | Caguana 8103-01 | $- | 8202 | 8202 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 730821 | 107911
PBUT6 Distr Line Rebuild | 14F000120000 | Caguana 8103-02 | $- | 19358 | 19358 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 730821 | 107911
PBUT6 Distr Line Rebuild | 14F000130000 | Yahuecas 8203-02 | $- | 12345 | 12345 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 730821 | 107911
PBUT6 Distr Line Rebuild | 14F000140000 | Jayuya 8301-03 | $- | 25883 | 25883 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 730821 | 107911
PBUT6 Distr Line Rebuild | 14F000150000 | Jayuya II 8302-05 | $- | 24032 | 24032 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 730821 | 107911
PBUT6 Distr Line Rebuild | 14F000170000 | CanaÂ 1710-01 (L) | 1353458 | 89788 | 1443246 | FAASt [Feeder Rebuild # 1710-01] (Distribution) | 760568 | 108048
PBUT6 Distr Line Rebuild | 14F000180000 | CanaÂ 1710-03 | $- | 23766 | 23766 | FAASt [Feeder Rebuild #1710-03] (Distribution) | 950482 | 108138
PBUT6 Distr Line Rebuild | 14F000190000 | BayamÃ³nÂ Tc 13kV #2Â 1716-03 | 1535392 | 55492 | 1590884 | FAASt [Feeder Rebuild # 1716-03] (Distribution) | 760575 | 108050
PBUT6 Distr Line Rebuild | 14F000200000 | CreaÂ 1717-03 | 1339260 | 93800 | 1433060 | FAASt [Feeder Rebuild # 1717-03] (Distribution) | 760579 | 108052
PBUT6 Distr Line Rebuild | 14F000210000 | Candelaria ArenasÂ 1718-02 | 1141069 | 96141 | 1237211 | FAASt [Feeder Rebuild # 1718-02] (Distribution) | 760577 | 108051
PBUT6 Distr Line Rebuild | 14F000220000 | RioÂ BayamÃ³nÂ IiÂ 1720-07 | 1852288 | 135267 | 1987556 | FAASt [Feeder Rebuild # 1720-07] (Distribution) | 760571 | 108049
PBUT6 Distr Line Rebuild | 14F000230000 | LevittownÂ 1806-02 | $- | 86572 | 86572 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | 334473 | 107525
PBUT6 Distr Line Rebuild | 14F000240000 | Vega Baja 1Â 9001-02 (L) | $- | 16185 | 16185 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | 334475 | 107527
PBUT6 Distr Line Rebuild | 14F000250000 | Toa AltaÂ 9401-01 | $- | 44667 | 44667 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | 334475 | 107527
PBUT6 Distr Line Rebuild | 14F000260000 | Barrio PiÃ±as 9403-03 | $- | 131065 | 131065 | FAASt [Feeder Rebuild # 9403-03] (Distribution) | 817962 | 108121
PBUT6 Distr Line Rebuild | 14F000270000 | UnibonÂ 9501-02 | $- | 272580 | 272580 | FAASt [Distribution Feeder Rebuild 9501-02] (Distribution) | 812041 | 108101
PBUT6 Distr Line Rebuild | 14F000280000 | MonterreyÂ 9502-01 | $- | 15920 | 15920 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | 334475 | 107527
PBUT6 Distr Line Rebuild | 14F000290000 | MonterreyÂ 9502-02 | $- | 29767 | 29767 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | 334475 | 107527
PBUT6 Distr Line Rebuild | 14F000300000 | 1801-03 (L) | $- | 229155 | 229155 | FAASt [Feeder Rebuild # 1801-03] (Distribution) | 817993 | 108122
PBUT6 Distr Line Rebuild | 14F000310000 | 1801-05 | $- | 820 | 820 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | 334474 | 107526
PBUT6 Distr Line Rebuild | 14F000320000 | 1801-02 | $- | 1478 | 1478 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | 334474 | 107526
PBUT6 Distr Line Rebuild | 14F000330000 | 1801-01 | $- | 16704 | 16704 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | 334474 | 107526
PBUT6 Distr Line Rebuild | 14F000340000 | 1801-04 | $- | 14072 | 14072 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | 334474 | 107526
PBUT6 Distr Line Rebuild | 14F000360000 | 3205-07 (L) | $- | 21588 | 21588 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 334452 | 107521
PBUT6 Distr Line Rebuild | 14F000370000 | 2603-08 | $- | 80437 | 80437 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | 730541 | 107908
PBUT6 Distr Line Rebuild | 14F000380000 | 9703-01 | $- | 31080 | 31080 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 334497 | 107531
PBUT6 Distr Line Rebuild | 14F000390000 | 3601-02 | $- | 21070 | 21070 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 334491 | 107530
PBUT6 Distr Line Rebuild | 14F000400000 | 3301-01 | $- | 32642 | 32642 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 334452 | 107521
PBUT6 Distr Line Rebuild | 14F000410000 | 9902-01 | $- | 5941 | 5941 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 334443 | 107520
PBUT6 Distr Line Rebuild | 14F000420000 | 3601-04 | $- | 111686 | 111686 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 334491 | 107530
PBUT6 Distr Line Rebuild | 14F000430000 | 9902-02 | $- | 31349 | 31349 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 334443 | 107520
PBUT6 Distr Line Rebuild | 14F000440000 | 2605-01 | $- | 3984 | 3984 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 334420 | 107519
PBUT6 Distr Line Rebuild | 14F000450000 | 9703-03 | $- | -106 | -106 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 334497 | 107531
PBUT6 Distr Line Rebuild | 14F000460000 | 3007-03 | $- | 105024 | 105024 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 334497 | 107531
PBUT6 Distr Line Rebuild | 14F000470000 | 9703-02 | $- | 17339 | 17339 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 334497 | 107531
PBUT6 Distr Line Rebuild | 14F000480000 | 3006-05 | $- | 313917 | 313917 | FAASt [Feeder Rebuild # 3006-05] (Distribution) | 818055 | 108125
PBUT6 Distr Line Rebuild | 14F000490000 | 3502-02 | $- | 178074 | 178074 | FAASt [Feeder Rebuild 3502-02] (Distribution) | 812569 | 108102
PBUT6 Distr Line Rebuild | 14F000500000 | 9901-02 | $- | 23333 | 23333 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 334443 | 107520
PBUT6 Distr Line Rebuild | 14F000510000 | 2906-02 | 695094 | 598037 | 1293132 | FAASt [Feeder Rebuild # 2906-02] (Distribution) | 767139 | 108064
PBUT6 Distr Line Rebuild | 14F000520000 | 3701-03 | $- | 195002 | 195002 | FAASt [Feeder Rebuild # 3701-03] (Distribution) | 818041 | 108124
PBUT6 Distr Line Rebuild | 14F000530000 | 3102-01 | $- | 3767 | 3767 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 334518 | 107532
PBUT6 Distr Line Rebuild | 14F000540000 | 3103-01 | $- | 2176 | 2176 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 334518 | 107532
PBUT6 Distr Line Rebuild | 14F000550000 | 2803-02 | $- | 15457 | 15457 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 334452 | 107521
PBUT6 Distr Line Rebuild | 14F000560000 | 3302-02 | $- | 6636 | 6636 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 334452 | 107521
PBUT6 Distr Line Rebuild | 14F000570000 | 9601-02 | $- | 10635 | 10635 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 334443 | 107520
PBUT6 Distr Line Rebuild | 14F000580000 | 3103-04 | $- | 3481 | 3481 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 334518 | 107532
PBUT6 Distr Line Rebuild | 14F000590000 | 2602-03 | $- | 10316 | 10316 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 334420 | 107519
PBUT6 Distr Line Rebuild | 14F000600000 | 3401-02 | $- | 3196 | 3196 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 334491 | 107530
PBUT6 Distr Line Rebuild | 14F000610000 | 9602-04 | $- | 51128 | 51128 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 334443 | 107520
PBUT6 Distr Line Rebuild | 14F000620000 | 9601-01 | $- | 5123 | 5123 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 334443 | 107520
PBUT6 Distr Line Rebuild | 14F000630000 | 3006-03 | $- | 3363 | 3363 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | 730513 | 107907
PBUT6 Distr Line Rebuild | 14F000640000 | 3010-01 | $- | 10601 | 10601 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 334497 | 107531
PBUT6 Distr Line Rebuild | 14F000650000 | 3103-05 | $- | 5943 | 5943 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 334518 | 107532
PBUT6 Distr Line Rebuild | 14F000660000 | 3015-05 | $- | 181300 | 181300 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 334497 | 107531
PBUT6 Distr Line Rebuild | 14F000670000 | 3013-02 | $- | 2151 | 2151 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | 730513 | 107907
PBUT6 Distr Line Rebuild | 14F000680000 | 2901-03 | $- | 12316 | 12316 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 334420 | 107519
PBUT6 Distr Line Rebuild | 14F000690000 | 3004-01 | $- | 6434 | 6434 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | 730513 | 107907
PBUT6 Distr Line Rebuild | 14F000700000 | 2701-01 | $- | 10185 | 10185 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 334420 | 107519
PBUT6 Distr Line Rebuild | 14F000710000 | 2701-03 | $- | 33600 | 33600 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 334420 | 107519
PBUT6 Distr Line Rebuild | 14F000720000 | 2801-03 | $- | 4534 | 4534 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 334452 | 107521
PBUT6 Distr Line Rebuild | 14F000730000 | 3405-01 | $- | 18068 | 18068 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 334491 | 107530
PBUT6 Distr Line Rebuild | 14F000740000 | 2801-02 | $- | 5923 | 5923 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 334452 | 107521
PBUT6 Distr Line Rebuild | 14F000750000 | 3405-03 | $- | 5496 | 5496 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 334491 | 107530
PBUT6 Distr Line Rebuild | 14F000760000 | 3201-04 | $- | 1356 | 1356 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 334452 | 107521
PBUT6 Distr Line Rebuild | 14F000770000 | 3101-02 | $- | 9579 | 9579 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 334518 | 107532
PBUT6 Distr Line Rebuild | 14F000780000 | 3006-02 | $- | 2947 | 2947 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | 730513 | 107907
PBUT6 Distr Line Rebuild | 14F000810000 | FajardoÂ PdsÂ 2005-10 (L) | $- | 3988 | 3988 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 334476 | 107528
PBUT6 Distr Line Rebuild | 14F000820000 | Rio Grande 8kVÂ 2301-02 | $- | 22527 | 22527 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 334476 | 107528
PBUT6 Distr Line Rebuild | 14F000830000 | Palmer TcÂ 2305-02 | $- | 3392 | 3392 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 334476 | 107528
PBUT6 Distr Line Rebuild | 14F000840000 | CanovanasÂ PuebloÂ 2401-01 | $- | 13205 | 13205 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 334476 | 107528
PBUT6 Distr Line Rebuild | 14F000850000 | Las MercedesÂ 2403-01 | $- | 14164 | 14164 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 334476 | 107528
PBUT6 Distr Line Rebuild | 14F000860000 | SabanaÂ LlanaÂ 13kV 1646-02 (L) | $- | 13056 | 13056 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | 334477 | 107529
PBUT6 Distr Line Rebuild | 14F000870000 | VillamarÂ 1657-02 | $- | 1604 | 1604 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | 334477 | 107529
PBUT6 Distr Line Rebuild | 14F000880000 | CanovanasÂ T.C. #1Â 2402-02 | $- | 73589 | 73589 | FAASt [Feeder Rebuild #2402-02] (Distribution) | 818006 | 108123
PBUT6 Distr Line Rebuild | 14F000890000 | CanovanasÂ T.C. #1Â 2402-03 | $- | 835 | 835 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | 334477 | 107529
PBUT6 Distr Line Rebuild | 14F000900000 | CanovanasÂ T.C. #2Â 2404-06 | $- | 72939 | 72939 | FAASt [Feeder Rebuild # 2404-06] (Distribution) | 817961 | 108120
PBUT6 Distr Line Rebuild | 14F000970000 | Alturas De MayagÂ 6012-02 (L) | 1711702 | 1044031 | 2755733 | FAASt [Feeder Rebuild # 6012-02] (Distribution) | 764707 | 108058
PBUT6 Distr Line Rebuild | 14F000980000 | Once De Agosto 13kVÂ 6014-02 | 2333972 | 189034 | 2523006 | FAASt [Feeder Rebuild # 6014-02] (Distribution) | 764705 | 108056
PBUT6 Distr Line Rebuild | 14F000990000 | Victoria 13.2 kVÂ 7008-05 | $- | 19896 | 19896 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 334308 | 107517
PBUT6 Distr Line Rebuild | 14F001000000 | T - BoneÂ 7011-03 | 1045810 | 199598 | 1245408 | FAASt [Feeder Rebuild # 7011-03] (Distribution) | 764706 | 108057
PBUT6 Distr Line Rebuild | 14F001010000 | MocaÂ IiÂ 7104-05 | $- | 9142 | 9142 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 334308 | 107517
PBUT6 Distr Line Rebuild | 14F001020000 | AguadaÂ 7201-02 | $- | 115023 | 115023 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 334308 | 107517
PBUT6 Distr Line Rebuild | 14F001030000 | RincÃ³nÂ 7301-03 | $- | 18023 | 18023 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 334308 | 107517
PBUT6 Distr Line Rebuild | 14F001040000 | AtalayaÂ 7303-01 | $- | 27355 | 27355 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 334308 | 107517
PBUT6 Distr Line Rebuild | 14F001050000 | Once De AgostoÂ 6001-05 (L) | $- | 10935 | 10935 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 334285 | 107514
PBUT6 Distr Line Rebuild | 14F001060000 | Cerro Las MesasÂ 6010-01 | $- | 83543 | 83543 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 334285 | 107514
PBUT6 Distr Line Rebuild | 14F001070000 | CentroÂ MÃ©dico 13kVÂ 6015-02 | $- | 13817 | 13817 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 334285 | 107514
PBUT6 Distr Line Rebuild | 14F001080000 | IndieraÂ AltaÂ 6305-03 | $- | 96081 | 96081 | FAASt [Feeder Rebuild # 6305-03] (Distribution) | 818056 | 108126
PBUT6 Distr Line Rebuild | 14F001090000 | Las VegasÂ 6306-02 | $- | 178927 | 178927 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 334285 | 107514
PBUT6 Distr Line Rebuild | 14F001100000 | Acacias 13.2 kVÂ 6802-04 | $- | 108980 | 108980 | Feeder Rebuild #6802-04 (Distribution) | 956782 | 108162
PBUT6 Distr Line Rebuild | 14F001110000 | Acacias 13.2 kVÂ 6802-05 | $- | 6766 | 6766 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 334285 | 107514
PBUT6 Distr Line Rebuild | 14F001120000 | BartoloÂ 7902-01 | $- | 7279 | 7279 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 334285 | 107514
PBUT6 Distr Line Rebuild | 14F001130000 | BartoloÂ 7902-03 | $- | 4932 | 4932 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 334285 | 107514
PBUT6 Distr Line Rebuild | 14F001140000 | San GermÃ¡n 13kVÂ 6406-02 (L) | $- | 69110 | 69110 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 334191 | 107513
PBUT6 Distr Line Rebuild | 14F001150000 | LajasÂ 6601-03 | $- | 206484 | 206484 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | 801166 | 108082
PBUT6 Distr Line Rebuild | 14F001160000 | PargueraÂ PdsÂ 6603-01 | $- | 99195 | 99195 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 334191 | 107513
PBUT6 Distr Line Rebuild | 14F001170000 | BoquerÃ³nÂ 6702-01 | $- | 2516 | 2516 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 334191 | 107513
PBUT6 Distr Line Rebuild | 14F001180000 | CaboÂ RojoÂ 6703-01 | $- | 15768 | 15768 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 334191 | 107513
PBUT6 Distr Line Rebuild | 14F001190000 | CombateÂ 6704-02 | $- | 30123 | 30123 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 334191 | 107513
PBUT6 Distr Line Rebuild | 14F001200000 | CombateÂ 6704-03 | $- | 38283 | 38283 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 334191 | 107513
PBUT6 Distr Line Rebuild | 14F001210000 | Puerto RealÂ 6705-01 | $- | 10870 | 10870 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 334191 | 107513
PBUT6 Distr Line Rebuild | 14F001300000 | Rambla 13 kVÂ 5004-06 (L) | $- | 14080 | 14080 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 730586 | 107909
PBUT6 Distr Line Rebuild | 14F001310000 | Rambla 13 kVÂ 5004-07 | $- | 35846 | 35846 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 730586 | 107909
PBUT6 Distr Line Rebuild | 14F001320000 | Rambla 13 kVÂ 5004-09 | $- | 15929 | 15929 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 730586 | 107909
PBUT6 Distr Line Rebuild | 14F001330000 | CanasÂ T.C. 13 kVÂ 5018-03 | $- | 17250 | 17250 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 730586 | 107909
PBUT6 Distr Line Rebuild | 14F001340000 | YaucoÂ HidroÂ IiÂ 5303-01 | $- | 6927 | 6927 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 730586 | 107909
PBUT6 Distr Line Rebuild | 14F001350000 | GuayanillaÂ PuebloÂ 5501-04 | $- | 10378 | 10378 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 730586 | 107909
PBUT6 Distr Line Rebuild | 14F001360000 | GuanicaÂ TcÂ 5602-02 | 1309887 | 208295 | 1518182 | FAASt [Feeder Rebuild # 5602-02] (Distribution) | 764708 | 108059
PBUT6 Distr Line Rebuild | 14F001370000 | JobosÂ T.C.Â 4003-01 (L) | $- | 6003 | 6003 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 730824 | 107912
PBUT6 Distr Line Rebuild | 14F001380000 | PatillasÂ 4201-01 | $- | 2959 | 2959 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 730824 | 107912
PBUT6 Distr Line Rebuild | 14F001390000 | CoamoÂ UrbanoÂ 4602-01 | $- | 5461 | 5461 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 730824 | 107912
PBUT6 Distr Line Rebuild | 14F001400000 | CoamoÂ PdsÂ 4603-01 | $- | 6501 | 6501 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 730824 | 107912
PBUT6 Distr Line Rebuild | 14F001410000 | Ponce Distr. HospitalÂ 5012-03 | $- | 9535 | 9535 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 730824 | 107912
PBUT6 Distr Line Rebuild | 14F001420000 | AguilitaÂ 4 kVÂ 5817-02 | $- | 6431 | 6431 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 730824 | 107912
PBUT6 Distr Line Rebuild | 14F001440000 | ConquistadorÂ 1204-02 (L) | 1987216 | 144755 | 2131971 | FAASt [Feeder Rebuild # 1204-02] (Distribution) | 801197 | 108084
PBUT6 Distr Line Rebuild | 14F001450000 | ConquistadorÂ 1204-03 | $- | 32753 | 32753 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | 334471 | 107523
PBUT6 Distr Line Rebuild | 14F001460000 | ConquistadorÂ 1204-04 | 1248848 | 54441 | 1303289 | FAASt [Feeder Rebuild # 1204-04] (Distribution) | 767381 | 108067
PBUT6 Distr Line Rebuild | 14F001470000 | ConquistadorÂ 1204-05 | 1289128 | 49058 | 1338186 | FAASt [Feeder Rebuild # 1204-05] (Distribution) | 764709 | 108060
PBUT6 Distr Line Rebuild | 14F001480000 | VillaÂ BetinaÂ 1303-01 | 1034675 | 47484 | 1082159 | FAASt [Feeder Rebuild # 1303-01] (Distribution) | 767387 | 108068
PBUT6 Distr Line Rebuild | 14F001490000 | VillaÂ BetinaÂ 1303-02 | $- | 192169 | 192169 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 817956 | 108119
PBUT6 Distr Line Rebuild | 14F001500000 | VillaÂ BetinaÂ 1303-05 | 1344170 | 209168 | 1553337 | FAASt [Feeder Rebuild # 1303-05] (Distribution) | 767005 | 108062
PBUT6 Distr Line Rebuild | 14F001510000 | MonacilloÂ 4kVÂ 1330-01 | $- | 270573 | 270573 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 334472 | 107524
PBUT6 Distr Line Rebuild | 14F001520000 | MonacillosÂ 13kVÂ 1346-02 | $- | 152510 | 152510 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 334472 | 107524
PBUT6 Distr Line Rebuild | 14F001530000 | Venezuela 13kVÂ 1348-06 | $- | 5142 | 5142 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 334472 | 107524
PBUT6 Distr Line Rebuild | 14F001540000 | CacheteÂ 13kVÂ 1529-15 | $- | 204882 | 204882 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | 801172 | 108083
PBUT6 Distr Line Rebuild | 14F001550000 | GranaÂ PdsÂ IiÂ 1909-09 | $- | 75276 | 75276 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 334472 | 107524
PBUT6 Distr Line Rebuild | 14F001560000 | SanturceÂ Planta 2Â 1117-11 | $- | 13662 | 13662 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | 546374 | 107556
PBUT6 Distr Line Rebuild | 14F001570000 | LlorensÂ Torres 13kVÂ 1118-10 | $- | 8924 | 8924 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | 546374 | 107556
PBUT6 Distr Line Rebuild | 14F001580000 | BerwindÂ 13kVÂ 1336-06 | $- | 14842 | 14842 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | 546374 | 107556
PBUT6 Distr Line Rebuild | 14F001590000 | BerwindÂ 13kVÂ 1336-08 | $- | 66811 | 66811 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | 546374 | 107556
PBUT6 Distr Line Rebuild | 14F001600000 | Parque EscorialÂ 1620-02 | $- | 268787 | 268787 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | 798275 | 108075
PBUT6 Distr Line Rebuild | 14F003420000 | Las Marias 6201-01 | $- | 31778 | 31778 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 334293 | 107516
PBUT6 Distr Line Rebuild | 14F003430000 | San Sebastian 2 7802-4 | $- | 4687 | 4687 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 334293 | 107516
PBUT6 Distr Line Rebuild | 14F003440000 | San Sebastian 7805-13 | $- | 121384 | 121384 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 334293 | 107516
PBUT6 Distr Line Rebuild | 14F003450000 | San Sebastian 7805-11 | $- | 174315 | 174315 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 334293 | 107516
PBUT6 Distr Line Rebuild | 14F003460000 | Lares 7901-02 | $- | 3690 | 3690 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 334293 | 107516
PBUT6 Distr Line Rebuild | 14F003470000 | Lares Prov. 7903-06 | $- | 8900 | 8900 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 334293 | 107516
PBUT6 Distr Line Rebuild | 14F003480000 | Lares 7901-01 | $- | 16669 | 16669 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 334293 | 107516
PBUT6 Distr Line Rebuild | 14F003490000 | El Yunque 2305-01 Supply | $- | 32270 | 32270 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | 546386 | 107558
PBUT6 Distr Line Rebuild | 14F004310000 | UG System Repairs - CAPEX FED | 140 | 106 | 246 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005210000 | Arecibo Distr.Hospital 8001-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005220000 | Arecibo Hosp.Distr13KV 8015-09 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005230000 | Cambalache 8004-02 | 206 | $- | 206 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005240000 | Cambalache 8004-03 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005250000 | Cambalache 8004-04 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005260000 | Dos Bocas 8005-01 | 38 | 13624 | 13662 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005290000 | Factor 1 8011-01 | 2420 | 5245 | 7665 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005300000 | Mirador Azul 8007-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005330000 | Camuy 7601-03 | 117 | $- | 117 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005340000 | Camuy 7601-04 | 117 | $- | 117 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005350000 | Camuy Provisional 7602-06 | 58 | $- | 58 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005360000 | Factor 13 KV 8014-08 | 38 | 143 | 181 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005370000 | Hatillo 7701-01 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005380000 | Hatillo 7701-03 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005390000 | Guajataca 7403-02 | 241 | $- | 241 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005400000 | Pajuil 7702-02 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005410000 | Pajuil 7702-03 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005420000 | Quebradilla 7402-01 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005430000 | Quebradilla 7402-05 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005440000 | San Daniel 8013-01 | 58 | $- | 58 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005450000 | Adjuntas Pueblo 8202-01 | 4549 | 840 | 5389 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005460000 | Adjuntas Pueblo 8202-02 | 222 | 73 | 294 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005470000 | Adjuntas Pueblo 8202-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005480000 | Guajataca 7403-03 | 142 | $- | 142 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005490000 | Jayuya 8301-01 | 107 | $- | 107 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005500000 | Yahuecas 8203-01 | 508 | $- | 508 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005510000 | Jayuya II 8302-04 | 163 | $- | 163 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005520000 | San Jose 8104-02 | 2440 | 5587 | 8027 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005530000 | San Jose 8104-05 | 79 | $- | 79 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005540000 | Utuado Pueblo 8101-01 | 301 | $- | 301 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005550000 | Utuado Pueblo 8101-04 | 57 | $- | 57 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005560000 | Utuado Pueblo 8101-05 | 76 | $- | 76 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005570000 | Barceloneta Pueblo 8504-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005580000 | Ciales 8701-04 | 51 | 25945 | 25996 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005590000 | Cruce Davila 8501-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005600000 | Florida 8602-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005610000 | Florida 8602-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005620000 | ManatÃ­ Pueblo 8405-01 | 270 | $- | 270 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005640000 | ManatÃ­ Pueblo 8405-03 | 34 | $- | 34 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005650000 | Morovis 8801-01 | 77 | $- | 77 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005660000 | Morovis 8801-02 | 228 | -176 | 53 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005670000 | Morovis 8801-03 | 324 | $- | 324 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005680000 | Morovis 8801-04 | 3815 | $- | 3815 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005690000 | BreÃ±as 9201-02 | 17 | $- | 17 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005700000 | Santa Ana 9103-01 | 17 | $- | 17 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005710000 | Vega Alta 8KV 9101-01 | 68 | 5409 | 5477 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005720000 | Vega Alta 8KV 9101-03 | 17 | $- | 17 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005730000 | Vega Alta 8KV 9101-04 | 34 | $- | 34 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005740000 | Vega Alta 13KV 9105-08 | 155 | $- | 155 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005750000 | Vega Baja 2 9003-06 | 155 | $- | 155 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005760000 | San Demetrio 9002-01 | $- | -221 | -221 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005770000 | San Demetrio 9002-03 | 17 | $- | 17 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005780000 | Vega Alta 13KV 9105-06 | 92 | $- | 92 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005790000 | Vega Baja 1 9001-01 | 134 | $- | 134 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005800000 | Vega Baja 2 9003-05 | 34 | $- | 34 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005810000 | Vega Baja TC 13KV 9004-08 | 1554 | -263 | 1291 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005820000 | Vega Baja TC 13KV 9004-10 | 4666 | $- | 4666 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005830000 | BayamÃ³n TC 13KV #1 1711-04 | 38 | -263 | -225 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005840000 | BayamÃ³n TC 13KV #1 1711-05 | 204 | 2207 | 2411 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005850000 | Buena Vista 1734-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005860000 | Buena Vista 1734-02 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005870000 | Cana (Interamericana)1719-15 | 4278 | 4021 | 8299 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005880000 | Cana (Interamericana)1719-18 | 1691 | $- | 1691 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005890000 | Grana PDS 1907-04 | 273 | $- | 273 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005900000 | Grana PDS 1907-05 | 185 | 93 | 278 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005910000 | Grana PDS II 1909-08 | 60 | $- | 60 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005940000 | Unibon 9501-01 | 1852 | $- | 1852 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005950000 | Dorado Pueblo 9202-04 | 1556 | 9150 | 10706 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005960000 | Dorado TC 9203-04 | 60 | $- | 60 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005970000 | Dorado TC PDS 13KV 9207-08 | 36 | $- | 36 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005980000 | Monterrey 9502-03 | 18 | $- | 18 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F005990000 | Monterrey PDS 13KV 9503-06 | 166 | 12882 | 13047 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006000000 | Naranjito 9801-01 | 202 | $- | 202 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006010000 | Barrio PiÃ±as 13KV 9405-05 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006020000 | Barrio PiÃ±as 9403-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006030000 | Naranjito 2 9802-04 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006070000 | BayamÃ³n TC 13KV #1 1711-01 | 2505 | $- | 2505 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006080000 | Cana 1710-04 | 1231 | 128 | 1360 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006090000 | Cana 1710-05 | 501 | $- | 501 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006100000 | Rio BayamÃ³n 1709-02 | 2110 | 1075 | 3186 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006110000 | Rio BayamÃ³n 1709-05 | 4612 | $- | 4612 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006120000 | Rio BayamÃ³n 1709-03 | 363 | 129 | 492 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006140000 | Crea 1717-01 | 1436 | 1315 | 2751 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006150000 | Dorado TC 9203-02 | 1140 | $- | 1140 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006160000 | Hato Tejas TC 1713-03 | 298 | $- | 298 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006170000 | Hato Tejas TC 1713-05 | 5867 | $- | 5867 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006180000 | Levittown 1806-01 | 1033 | 1064 | 2097 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006190000 | Levittown 1806-03 | 562 | -73 | 488 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006200000 | Aguas Buenas 3701-02 | 672 | 6255 | 6927 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006210000 | Aguas Buenas 3701-04 | $- | -105 | -105 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006220000 | Aibonito 3501-01 | 67 | $- | 67 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006230000 | Aibonito 3501-02 | 235 | $- | 235 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006260000 | Barranquitas II 9602-03 | 766 | 4931 | 5697 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006270000 | Cayey Rural 3405-02 | 406 | $- | 406 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006280000 | Cayey T.C. 3401-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006290000 | El Abanico PDS 9605-01 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006300000 | El Abanico PDS 9605-02 | 35877 | 17948 | 53824 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006310000 | Jajome 3403-01 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006340000 | Comsat 3406-02 | 435 | $- | 435 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006350000 | Comsat 3406-03 | 17 | $- | 17 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006360000 | Las Cruces 3602-01 | 17 | 3802 | 3819 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006380000 | Caguax 3009-01 | $- | -59 | -59 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006400000 | Rio CaÃ±as 3014-01 | 813 | -262 | 551 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006410000 | Sabanera II 3604-06 | 167 | $- | 167 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006420000 | Sabanera II 3604-07 | 79 | $- | 79 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006430000 | Villas de Castro 3013-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006440000 | Gurabo 3101-04 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006460000 | Juncos 3201-02 | 558 | $- | 558 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006470000 | Rio CaÃ±as 3014-04 | 36 | 1166 | 1202 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006490000 | Veredas 3103-02 | 434 | $- | 434 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006500000 | Candelero 2604-01 | 2908 | $- | 2908 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006530000 | Humacao Pueblo 2601-01 | 587 | 10660 | 11247 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006540000 | Humacao T.C. 13 KV 2603-09 | 392 | $- | 392 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006550000 | San Lorenzo II 3302-04 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006620000 | Aguada 7201-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006630000 | Aguada 7201-05 | 9377 | 3530 | 12906 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006640000 | Aguadilla Distr.Hosp 7003-02 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006660000 | Ojo de Agua 7002-03 | $- | 4542 | 4542 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006680000 | Aguadilla Distr.Hosp 7003-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006690000 | Ramey Field 2 7005-03 | 279 | 2839 | 3118 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006700000 | Ramey Field 3 7006-01 | 399 | $- | 399 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006710000 | Ramey Field 3 7006-03 | 366 | $- | 366 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006720000 | T-Bone 7011-01 | 9 | -314 | -305 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006730000 | Victoria 13.2 KV 7008-04 | 48 | 1420 | 1468 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006740000 | Campamento Mora 7502-01 | 265 | $- | 265 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006750000 | Campamento Mora 7502-02 | 170 | $- | 170 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006770000 | Ceiba Baja 7012-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006780000 | Isabela 7503-04 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006790000 | T-Bone 7011-02 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006800000 | Isabela 7503-05 | $- | 120 | 120 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006810000 | Isabela Planta 3 7504-01 | 815 | $- | 815 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006840000 | Las MarÃ­as 6201-02 | 1699 | $- | 1699 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006850000 | Mora 13.2 KV 7505-05 | 408 | $- | 408 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006860000 | Capa 7103-01 | 83 | 4131 | 4213 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006870000 | Capa 7103-04 | $- | -102 | -102 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006880000 | Moca 7101-03 | 181 | -105 | 77 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006890000 | Moca II 7104-06 | 354 | -105 | 249 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006900000 | San SebastÃ­an 1 7801-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006920000 | AÃ±asco 6101-02 | 488 | $- | 488 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006930000 | AÃ±asco 6101-04 | 4474 | 3351 | 7825 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006940000 | AÃ±asco 6101-05 | 628 | 139 | 767 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006950000 | BoquerÃ³n 6702-04 | 68 | $- | 68 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006960000 | San SebastÃ­an 2 7802-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006980000 | Acacias 4.16 KV 6801-01 | 152 | $- | 152 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F006990000 | Acacias 4.16 KV 6801-02 | 494 | $- | 494 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007000000 | Acacias 4.16 KV 6801-03 | 190 | $- | 190 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007010000 | Acacias 13.2 KV 6802-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007020000 | Acacias 13.2 KV 6802-02 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007030000 | Cabo Rojo 6703-03 | 89 | $- | 89 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007040000 | Centro MÃ©dico 6008-04 | 340 | -498 | -158 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007050000 | Cerro las Mesas 6010-02 | 286 | $- | 286 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007060000 | Cuatro Hermanos 6004-02 | 1891 | $- | 1891 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007100000 | Alturas de Mayaguez 6012-03 | 205 | $- | 205 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007120000 | Once de Agosto 13KV 6014-01 | 139 | $- | 139 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007130000 | Once de Agosto 13KV 6014-03 | 39 | $- | 39 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007140000 | RincÃ³n 7301-02 | 87 | $- | 87 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007150000 | RincÃ³n 7301-04 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007160000 | Punta del Mar 7302-01 | 273 | $- | 273 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007170000 | RincÃ³n 7301-05 | $- | -68 | -68 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007180000 | San GermÃ¡n 6401-02 | 137 | -237 | -101 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007190000 | San GermÃ¡n 6401-04 | 76 | -102 | -26 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007210000 | San GermÃ¡n Industrial 6404-03 | $- | -204 | -204 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007220000 | Arroyo 4101-01 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007230000 | Arroyo 4101-04 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007240000 | Coamo PDS 4603-02 | 223 | 4643 | 4866 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007250000 | Coamo Urbano 4602-03 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007260000 | Coamo Urbano 4602-04 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007270000 | Guayama 4001-03 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007280000 | Jobos T.C. 4003-02 | 305 | $- | 305 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007290000 | Jobos T.C. 4003-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007320000 | Maunabo 4301-03 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007330000 | Patillas 4201-02 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007400000 | Fort Allen 13 KV 5803-02 | 1383 | 24 | 1406 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007410000 | Juana Diaz 4 KV 5802-01 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007420000 | Juana Diaz 4 KV 5802-03 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007430000 | Santa Isabel 4401-02 | 38 | -237 | -199 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007440000 | Usera 4601-01 | 19 | $- | 19 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007450000 | Usera 4601-04 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007460000 | Ave Hostos 13 KV 5011-03 | 18 | $- | 18 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007470000 | Ave Hostos 13 KV 5011-04 | 18 | $- | 18 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007480000 | Buena Vista 5007-01 | 18 | $- | 18 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007490000 | Canas T.C. 4.16 KV 5002-03 | 69 | $- | 69 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007500000 | Canas T.C. 4.16 KV 5002-04 | 48 | $- | 48 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007510000 | Pampanos 5005-03 | 73 | $- | 73 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007520000 | Canas T.C. 13 KV 5018-02 | 205 | $- | 205 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007550000 | Inabon 4 KV 5013-02 | 17 | $- | 17 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007570000 | Villa del Carmen 5016-01 | 34 | 1827 | 1862 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007580000 | Canas T.C. 13 KV 5018-05 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007590000 | Portugues 4 KV 5021-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007610000 | Villalba 4 KV 5901-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007620000 | Villalba 4 KV 5901-02 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007630000 | Villalba 4 KV 5901-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007640000 | Guanica TC 5602-01 | 2591 | $- | 2591 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007650000 | Guanica TC 5602-03 | 95 | $- | 95 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007660000 | Guayanilla Pueblo 5501-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007670000 | Guayanilla Pueblo 5501-02 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007680000 | Guayanilla Pueblo 5501-03 | 76 | -170 | -94 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007700000 | Lajas 6601-04 | 76 | $- | 76 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007720000 | PeÃ±uelas Pueblo 5401-02 | 179 | 254 | 433 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007750000 | Sabana Grande 6501-01 | 672 | 4602 | 5274 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007760000 | Sabana Grande 6501-02 | 38 | 3531 | 3569 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007770000 | Sabana Grande 6501-03 | 67 | 4602 | 4669 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007780000 | Sabana Grande 6501-04 | 4587 | 2645 | 7233 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007800000 | Yauco Pueblo 1 5302-01 | 208 | $- | 208 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007820000 | Yauco Plaza PDS 5305-03 | 98 | $- | 98 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007830000 | Yauco Pueblo II 5304-01 | 133 | -102 | 31 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007840000 | Yauco Pueblo II 5304-02 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007860000 | Yauco Pueblo II 5304-05 | 38 | $- | 38 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007910000 | Canovanas T.C. #2 2404-08 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007930000 | Ceramica 13 KV 1619-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F007980000 | Villamar 1657-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008000000 | Alturas RioGrande 13KV 2302-02 | 45 | $- | 45 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008010000 | Alturas RioGrande 13KV 2302-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008060000 | Fajardo Pueblo 2002-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008170000 | Buen Pastor 1908-03 | 128 | -73 | 54 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008180000 | Cachete 4KV 1530-09 | 22000 | $- | 22000 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008220000 | Minillas 1114-01 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008240000 | Isla Grande GIS I 1119-04 | $- | -73 | -73 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008250000 | Llorens Torres 13KV 1118-08 | 4756 | 1126 | 5883 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008260000 | Llorens Torres 13KV 1118-09 | 2309 | $- | 2309 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008270000 | Viaducto 13KV 1115-04 | $- | -45 | -45 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008280000 | Villa Betina 1303-03 | $- | $- | $- | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008290000 | Berwind 13KV 1336-07 | 5938 | 78 | 6015 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008300000 | La Muda 1343-01 | 768 | -236 | 532 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008320000 | Monacillos 13KV 1346-03 | 26 | -471 | -445 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008350000 | Encantada 1206-03 | 1080 | $- | 1080 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F008380000 | Quebrada Negritos 1205-03 | $- | -73 | -73 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020300000 | UG Feeder 1115-02 Santurce | $- | 77422 | 77422 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 754350 | 108015
PBUT6 Distr Line Rebuild | 14F020310000 | UG Feeder 1115-03 Santurce | $- | 58641 | 58641 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 754350 | 108015
PBUT6 Distr Line Rebuild | 14F020320000 | UG Feeder 1115-04 - Santurce | $- | 70986 | 70986 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 754350 | 108015
PBUT6 Distr Line Rebuild | 14F020330000 | UG Feeder 1117-07 - Santurce | $- | 53012 | 53012 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 754350 | 108015
PBUT6 Distr Line Rebuild | 14F020340000 | UG Feeder 1117-08 - Santurce | $- | 33195 | 33195 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 754350 | 108015
PBUT6 Distr Line Rebuild | 14F020350000 | UG Feeder 1424-07 - Santurce | $- | 101811 | 101811 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | 754351 | 108016
PBUT6 Distr Line Rebuild | 14F020360000 | UG Feeder 1424-08 - Santurce | $- | 66547 | 66547 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | 754351 | 108016
PBUT6 Distr Line Rebuild | 14F020370000 | UG Feeder 1204-02-Conquistador | 3483 | 3357 | 6840 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020380000 | UG Feeder 1204-03-Conquistador | 2014 | 806 | 2819 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020390000 | UG Feeder 1204-04-Conquistador | 1689 | 8222 | 9911 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020400000 | UG Feeder 1204-05-Conquistador | 1038 | 4886 | 5924 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020410000 | UG Feeder 1711-04 - Levittown | 948 | 1271 | 2220 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020420000 | UG Feeder 1717-01 - Levittown | 941 | 1692 | 2633 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020430000 | UG Feeder 1806-01 - Levittown | 1451 | 2728 | 4179 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020440000 | UG Feeder 1806-02 - Levittown | 314 | 1007 | 1321 | 0 | 0 | 0
PBUT6 Distr Line Rebuild | 14F020450000 | UG Feeder 1806-03 - Levittown | 1543 | 751 | 2293 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F000146000 | Mobile Sub Repairs | 20319 | 103949 | 124268 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F002130000 | SCADA Access & RTU Repl.Group2 | $- | 540185 | 540185 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 551926 | 107735
PBUT7 Substation Reliability | 14F003070000 | Mobile Substation | 30682 | 8733 | 39415 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F003910000 | SCADA accesRTU Repl.Group 3 | $- | 229141 | 229141 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | 551927 | 107736
PBUT7 Substation Reliability | 14F019650000 | AMELIA SECT PAC Upgrade | $- | 9594 | 9594 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019660000 | SAN GERMAN SECT PAC Upgrade | $- | 9123 | 9123 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019670000 | LAS LOMAS TC PAC Upgrade | $- | 14091 | 14091 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019680000 | CIALES PAC Upgrade | $- | 136 | 136 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019690000 | CONQUISTADOR PAC Upgrade | $- | 10038 | 10038 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019700000 | PALMER TC PAC Upgrade | $- | 8224 | 8224 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019710000 | DAGUAO TC PAC Upgrade | $- | 473 | 473 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019720000 | ARECIBO SECT PAC Upgrade | $- | 209 | 209 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019730000 | VEGA ALTA SECT PAC Upgrade | $- | 805 | 805 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019740000 | COVADONGA TC PAC Upgrade | $- | 45216 | 45216 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019750000 | ANASCO TC PAC Upgrade | $- | 17124 | 17124 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019760000 | AGUAS BUENAS TC PAC Upgrade | $- | 41253 | 41253 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019770000 | BARCELONETA TC PAC Upgrade | $- | 3044 | 3044 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019810000 | GUARAGUAO SECT PAC Upgrade | $- | 2602 | 2602 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F019880000 | SAN SEBASTIAN TC PAC Upgrade | $- | 26 | 26 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 746660 | 107960
PBUT7 Substation Reliability | 14F020020000 | Humacao TC-IWT | 94042 | 17542 | 111584 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020030000 | San German TC-IWT | 27983 | 3089 | 31073 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020040000 | Vega Baja-IWT | 98988 | 32102 | 131090 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020050000 | Atalaya 67303 | $- | 1480 | 1480 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT7 Substation Reliability | 14F020090000 | Colegio Sect 66006 | $- | 21683 | 21683 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT7 Substation Reliability | 14F020120000 | Grana 71907 | $- | 4425 | 4425 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT7 Substation Reliability | 14F020130000 | Guayama PDS 64006 | $- | 6136 | 6136 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT7 Substation Reliability | 14F020140000 | Humacao TC 72603 | $- | 22708 | 22708 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT7 Substation Reliability | 14F020180000 | Villa Betina 71303 | $- | 27921 | 27921 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT7 Substation Reliability | 14F020190000 | Yauco Plaza 65305 | $- | 7001 | 7001 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT7 Substation Reliability | 14F020810000 | Las Marias | 4168 | 19829 | 23996 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020820000 | Mayaguez TC | 38465 | 136170 | 174635 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020830000 | Mckinley 6002 | 14180 | 82505 | 96685 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020840000 | Moca 7101/7104 | $- | 8225 | 8225 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020850000 | Monacillo TC | 3208 | 7603 | 10811 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020860000 | Mora TC | 3727 | 13806 | 17533 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020870000 | Parguera | 3795 | 126265 | 130060 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020880000 | Puerto Del Mar 7302 | 5243 | $- | 5243 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020890000 | Rincon | 37865 | 4898 | 42762 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020900000 | San German 6401 | 220092 | 124879 | 344970 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020910000 | San German 6404 | 4168 | 96624 | 100792 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020920000 | San German TC | 22739 | 94949 | 117688 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020930000 | San Sebastian TC | 5373 | 282884 | 288257 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020940000 | Tbone 7011 | 1148 | $- | 1148 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020950000 | Victoria TC | 25286 | 321644 | 346930 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020960000 | Yabucoa TC | $- | 312 | 312 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020970000 | Acacias TC | 34868 | 256975 | 291843 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020980000 | 6501 Sabana Grande | 2126 | 20762 | 22888 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F020990000 | 7702 Pajuil | $- | 1323 | 1323 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021000000 | Aguada 7201 | 1263 | $- | 1263 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021010000 | Aguadilla HospitalDistrict7703 | 7493 | 8160 | 15653 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021020000 | Aguirre | $- | 1410 | 1410 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021030000 | Alturas Mayaguez | 1716 | 22518 | 24233 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021040000 | Anasco TC | 18231 | 216872 | 235103 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021050000 | Arecibo Rural | 8879 | $- | 8879 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021060000 | Bayamon TC | 3700 | $- | 3700 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021070000 | Berwind TC | 1983 | 607 | 2591 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021080000 | Canas TC | 2304 | 13409 | 15713 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021090000 | Colegio | 2006 | 29668 | 31675 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021100000 | Combate | 966 | 29714 | 30680 | 0 | 0 | 0
PBUT7 Substation Reliability | 14F021110000 | Dos Bocas 8005 | $- | 3855 | 3855 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F001770000 | Parques y Recreos Metalclad | $- | 40088 | 40088 | FAASt [Parques y Recreos - 1002] (Substation) | 550980 | 107722
PBUT8 Substation Rebuilds | 14F001780000 | Puerto Nuevo Metalclad 15 | $- | 132567 | 132567 | FAASt [Puerto Nuevo - 1520] (Substation) | 551912 | 107733
PBUT8 Substation Rebuilds | 14F001790000 | Baldrich -Â Metalclad- 1422 | $- | 10022 | 10022 | FAASt [Baldrich - 1422] (Substation) | 550894 | 107720
PBUT8 Substation Rebuilds | 14F001800000 | Condado - Metalclad - 1133 | $- | 97138 | 97138 | FAASt [Condado - 1133] (Substation) | 550986 | 107723
PBUT8 Substation Rebuilds | 14F001810000 | Crematorio - Metalclad - 1512 | $- | 115841 | 115841 | FAASt [Crematorio - 1512] (Substation) | 551918 | 11409
PBUT8 Substation Rebuilds | 14F001820000 | Egozcue - Metalclad - 1109 | $- | 86165 | 86165 | FAASt Egozcue - 1109 (Substation) | 547243 | 107693
PBUT8 Substation Rebuilds | 14F001830000 | Esc. Industrial M. Such - Meta | $- | 65343 | 65343 | FAASt [Esc. Industrial M. Such - 1423] (Substation) | 550099 | 107713
PBUT8 Substation Rebuilds | 14F001840000 | Fonalledas GIS Rebuilt 1401 14 | 53971 | 1434 | 55405 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) | 550972 | 107721
PBUT8 Substation Rebuilds | 14F001850000 | Guaynabo Pueblo Subst. Rebuild | $- | 21636 | 21636 | FAASt [Guaynabo Pueblo Substation] (Substation) | 551260 | 107727
PBUT8 Substation Rebuilds | 14F001860000 | Isla Grande 1101 Metalclad | 37162 | 1453 | 38615 | FAASt [Isla Grande 1101] (Substation) | 673920 | 107764
PBUT8 Substation Rebuilds | 14F001870000 | Santurce Planta (Sect) 1116 Me | 52578 | 12338 | 64915 | FAASt [Santurce Planta (Sect) 1116] (Substation) | 550998 | 107724
PBUT8 Substation Rebuilds | 14F001880000 | Arecibo Pueblo 8002 Reloc | $- | 12359 | 12359 | FAASt - [Substation Component Replacement Program] (Substation) | 547187 | 107690
PBUT8 Substation Rebuilds | 14F001890000 | Bayview Sectionalizer 1802 Rel | 36512 | 1123 | 37635 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) | 551100 | 107725
PBUT8 Substation Rebuilds | 14F001900000 | Charco Hondo 8008Â Reloc | $- | 13012 | 13012 | FAASt Charco Hondo Substation 8008 Relocation (Substation) | 547273 | 107699
PBUT8 Substation Rebuilds | 14F001910000 | Pampanos Relocation | 597628 | 22124 | 619753 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F001920000 | San Jose Relocation | $- | 38721 | 38721 | FAASt [San Jose Relocation] (Substation) | 761563 | 108055
PBUT8 Substation Rebuilds | 14F001930000 | Caparra 1911 & 1924 (Elevated | $- | 437697 | 437697 | FAASt [Caparra 1912 & 1924] (Substation) | 551914 | 11470
PBUT8 Substation Rebuilds | 14F001940000 | Tallaboa 5402Â (Elevated Contr | $- | 115368 | 115368 | FAASt Tallaboa 5402 (Substation) | 547241 | 11448
PBUT8 Substation Rebuilds | 14F002710000 | LLORENS TORRESÂ MCÂ 1106 | $- | 286773 | 286773 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 169058 | 107220
PBUT8 Substation Rebuilds | 14F002730000 | VIADUCTO TCÂ MC 1100 | $- | 709739 | 709739 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | 169276 | 107222
PBUT8 Substation Rebuilds | 14F002760000 | CARIDADÂ MCÂ 1714 | 123840 | 1502 | 125342 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F002810000 | CACHETEÂ MCÂ 1526 | $- | 392030 | 392030 | FAASt [Cachete – MC 1526] (Substations) | 178577 | 11507
PBUT8 Substation Rebuilds | 14F002920000 | Berwind TC-Â Metalclad - 1336 | $- | 47708 | 47708 | FAASt [Berwind TC - 1336] (Substation) | 550162 | 11813
PBUT8 Substation Rebuilds | 14F002930000 | Caguas TC BKRS 115kV | 50971 | 358645 | 409615 | FAASt [Caguas TC] (Substation) | 550771 | 107719
PBUT8 Substation Rebuilds | 14F002940000 | Canas TC BKRS 115kV | 51540 | 10383 | 61924 | FAASt Canas TC 5002 5018 (Substation) | 547248 | 107695
PBUT8 Substation Rebuilds | 14F003080000 | Ceiba Baja 7012 Transformer Re | 2132 | 692 | 2824 | FAASt [Ceiba Baja TRF 7012] (Substation) | 169503 | 107224
PBUT8 Substation Rebuilds | 14F003090000 | Las Lomas 1525 Transformer Rep | 12554 | $- | 12554 | FAASt [Las Lomas – XFMR 1525] (Substation) | 179988 | 107305
PBUT8 Substation Rebuilds | 14F003100000 | Bartolo 7902Â Transformer Repl | 194 | $- | 194 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003110000 | Sabanera 3603Â Transformer Rep | 668 | 121 | 789 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003120000 | Acacias 6801 TC Relocation | $- | 31636 | 31636 | FAASt [Acacias 6801 TC Relocation] (Substation) | 547344 | 107702
PBUT8 Substation Rebuilds | 14F003130000 | Cambalache TC Relocation | $- | 559068 | 559068 | FAASt Cambalache TC Relocation (Substation) | 547247 | 107694
PBUT8 Substation Rebuilds | 14F003140000 | Dorado TC Relocation | 64172 | 3596 | 67768 | FAASt [Dorado TC Relocation] (Substation) | 551916 | 107734
PBUT8 Substation Rebuilds | 14F003160000 | Victoria TC 7008 (Elevated Con | $- | 1390881 | 1390881 | FAASt [Victoria TC 7008 Relocation] (Substation) | 547343 | 107701
PBUT8 Substation Rebuilds | 14F003170000 | Conquistador - CH | $- | 795090 | 795090 | FAASt [Conquistador CH] (Substation) | 550106 | 107714
PBUT8 Substation Rebuilds | 14F003220000 | Guanica TC - Circuit Switch Re | 21460 | 938 | 22398 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003230000 | Buen Pastor 115/13.2kV Transfo | 12208 | $- | 12208 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003360000 | Substation Inspect | 1883766 | 138394 | 2022161 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003370000 | Substation Repair | 41181 | 2736 | 43917 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003500000 | T & G Demarcation | 2373 | 0 | 2373 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003640000 | Aguas Buenas TC | 3457 | 9086 | 12544 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F003660000 | Fajardo TC | 2437 | 7900 | 10337 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008400000 | Guajataca substation | -22 | $- | -22 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008430000 | BayamÃ³n TC - Part 2 | $- | 16001713 | 16001713 | FAASt [Bayamón TC - Rebuild] (Substation) | 682328 | 11876
PBUT8 Substation Rebuilds | 14F008440000 | Manati TC BRKS - Phase II | 12121 | 2297 | 14418 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008940000 | SubMinorRepair GRP F-AÃ±asco TC | 122982 | 102882 | 225864 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008950000 | SubMinorRepar GRP F-Guanica TC | 50271 | 91979 | 142250 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008960000 | SubMinorRepr GRP F-Maunabo TC | 115387 | 3221 | 118608 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008970000 | SubMinorRepr GRP G-SanJuan GIS | 133661 | 95583 | 229245 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008980000 | SubMinorRepr GRP G-Chardon GIS | 129519 | 51523 | 181042 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F008990000 | SubMinorRepr GRP G-Bo PiÃ±asGIS | 119216 | 43776 | 162993 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F009000000 | SubMinrReprGRP G-Matin PeÃ±aGIS | 112414 | 12033 | 124447 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F009030000 | Viaducto 115kV Prot&ContrlSyst | 134552 | 17857 | 152409 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F009050000 | Jobos TC | $- | 45642 | 45642 | FAASt - EPC - Jobos TC (Substation) | 723002 | 107888
PBUT8 Substation Rebuilds | 14F009070000 | New Guayanilla TC | 63941 | 30768 | 94710 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F009080000 | New Salinas TC | 72019 | 25562 | 97581 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016560000 | Hato Rey | 104337 | 6892 | 111230 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016570000 | MAUNABO TC | $- | 977579 | 977579 | FAASt [Maunabo TC] (Substation) | 682645 | 107779
PBUT8 Substation Rebuilds | 14F016580000 | Mayaguez | $- | 499437 | 499437 | FAASt [Mayagüez TC] (Substation) | 685869 | 107780
PBUT8 Substation Rebuilds | 14F016590000 | Naguabo | 14928 | 3768 | 18696 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016600000 | Palo Seco | 24549 | 2217 | 26766 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016610000 | Punta Lima Sect. | 55875 | 3173 | 59048 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016620000 | San Juan S.P. Rebuild-Phase 2 | 67347 | 304 | 67652 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016630000 | SanJuan SP New Substat-Phase3 | 3335 | $- | 3335 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016640000 | Ciales | $- | 50092 | 50092 | FAASt [Substation Ciales 8701] (Substation) | 752277 | 107995
PBUT8 Substation Rebuilds | 14F016650000 | Unibon (Corozal) | $- | 121343 | 121343 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | 752275 | 107993
PBUT8 Substation Rebuilds | 14F016660000 | Monterey | $- | 117087 | 117087 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | 752276 | 107994
PBUT8 Substation Rebuilds | 14F016670000 | Morovis | $- | 114642 | 114642 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | 550498 | 107717
PBUT8 Substation Rebuilds | 14F016680000 | JAYUYA 1 | 8615 | 151 | 8765 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016690000 | JUANA DIAZ TC | 9310 | 1128 | 10437 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016700000 | Fort Allen | 9607 | 100430 | 110037 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016710000 | Venezuela | 853553 | 1553899 | 2407452 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016720000 | Quebrada Negrito | 3109 | 3271 | 6380 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016730000 | Pastillo | 101444 | 126174 | 227618 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016740000 | Ponce TC | 4951 | 52 | 5003 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016750000 | ONCE DE AGOSTO 13 KV | 5240 | 358 | 5598 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016760000 | Buena Vista Sec | 4656 | $- | 4656 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016770000 | Brenas | 2766 | $- | 2766 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016780000 | Rambla Sec | 4278 | $- | 4278 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016790000 | Sierra Linda | 8597 | 1322 | 9919 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016800000 | AÃ±asco TC | 43125 | 1999 | 45124 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016810000 | DOS BOCAS HP | 5858 | 1189 | 7047 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F016820000 | Isla Grande GIS II | 5053 | 161 | 5214 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F020280000 | Substation Rebuild-Fajardo TC | 14887 | 3930 | 18818 | 0 | 0 | 0
PBUT8 Substation Rebuilds | 14F020290000 | Santa Rita Sectionalizer | 3621 | 2594 | 6215 | 0 | 0 | 0

## SOY_2025_Top Pri in Order (hidden)
Asset Category | FEMA Project # where applicable | Project Name (90 Day Plan) | Process Step | Total Project Cost | Date added to Priority list | Obligation Need By Date | Notes | Latest Update / Comments | Primary PDMG | LUMA PROJECT MANAGER | ASSET LEAD
Vegetation | 727531 | Island Wide Vegetation Clearing: Region 6 – Ponce Group A - LD | Obligated | 20024388.95 | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 727572 | Island Wide Vegetation Clearing: Region 3 – Bayamon Group A - HD & LD | Pending Applicant Project Review | 29267077.62 | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. High Density (HD) Bayamon: Awaiting Corps of Engineers vendor review. The COE has not renewed the contract with their vender. Awaiting date of ECD. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 727692 | Island Wide Vegetation Clearing Region 4 -- Caguas Group A - LD | Obligated | 33353341.65 | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 728827 | Island Wide Vegetation Clearing: Region 2 – Arecibo Group A - LD | Obligated | 4339077.99 | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 728832 | Island Wide Vegetation Clearing: Region 5 – Mayaguez Group A - LD | Obligated | 17078572.78 | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956332 | 2401-01 - Distribution - (San Juan - Group C) Single Line Project | Pending Formulation Completion | 11073220.77 | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956330 | 3007-03 - Distribution - (Caguas - Group C) Single Line Project | Pending Formulation Completion | 7822309.32 | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956339 | 3301-01 - Distribution - (Caguas - Group C) Single Line Project | Pending Formulation Completion | 9044801.71 | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956335 | 2301-02 - Distribution - (San Juan - Group C) Single Line Project | Pending Formulation Completion | 7350036.67 | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956337 | 6012-02 - Distribution - (Mayaguez - Group C) Single Line Project | Pending Formulation Completion | 7154389.02 | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956353 | 36100 - Transmission - (Arecibo - Group D) Single Line Project | Pending Formulation Completion | 36250655.54 | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956342 | 36400 - Transmission - (Arecibo - Group D) Single Line Project | Pending Formulation Completion | 43488242.54 | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956348 | 10000 - Transmission - (Bayamon - Group B) Single Line Project | Pending Formulation Completion | 1169316.35 | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956349 | 36800 - Transmission - (San Juan - Group D) Single Line Project | Pending Formulation Completion | 13569854.54 | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956345 | 2400 - Transmission - (Arecibo - Group B) Single Line Project | Pending Formulation Completion | 7174642.92 | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956341 | 5803-02 - Distribution - (Ponce - Group C) Single Line Project | Pending Formulation Completion | 95671.83 | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956331 | 6014-02 - Distribution - (Mayaguez - Group C) Single Line Project | Pending Formulation Completion | 6043929.69 | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956340 | 5602-02 - Distribution - (Ponce - Group C) Single Line Project | Pending Formulation Completion | 4965231.11 | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956357 | 1900 - Transmission - (Mayaguez - Group C) Single Line Project | Pending Formulation Completion | 12445436.07 | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Vegetation | 956343 | 4800 - Transmission - (Ponce - Group C) Single Line Project | Pending Formulation Completion | 0 | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | Rene Baptiste
Substations | 682834 | Costa Sur Transformer Replacement - Stabilization phase | Applicant Signed Project | 61444255.52 | 2024-11-24 | 2025-02-25 | Critical Stabilization to enable full project execution | Project is under FEMA phase 5, Applicant signed project on 5/27/25. Pending obligation, no further actions from LUMA | VALENTIN QUIRINDO, NORMANDO A. | Luderis Berrios Pastrana | Gabriel Torres Arroyo
Substations | 547187 | FAASt - [Substation Component Replacement Program] (Substation) - Group 1 | Pending Scope & Cost Completion by Applicant | 6860547.64 | 2024-09-15 |  | Will need expedited EHP support - needed to support restoration of OOS equipment | On 6/5/2025 LUMA uploaded Hazard Mitigation RFI regarding each substation clasification according to: Substation Rebuild Program, Substation Component Replacement Program, SCADA Remote Access and RTU Replacements, Substation Protection, Automation, and Control (PAC) Upgrades, Advanced Sensors (PMUs) & Wide-Area Monitoring, Protection & Control (WAMPAC). LUMA is currently pending FEMA Mitigation approval of RFI to continue process. FEMA forecast 7/15 | VALENTIN QUIRINDO, NORMANDO A. | Aaron Akens | Gabriel Torres Arroyo
Automation | 746309 | Group 30- DAUT BAYMON 9203-03 | Pending PDMG Scope & Cost Routing | 631083.37 | 2024-03-15 | July 15 2024 | The benchmark/template project for Distribution Automation to align on HM splits across the porgram - has been in discussion for over a year with HM team prompting current submissions to need to be 100% 428 in order to advance to obligation and enable execution | This project has been shifted to full 428/406 and is the pilot project/template for establishing the HM proposal and aligning toi the FEMA HM resilution documnet and resiliency plan. The final version is under FEMA review and is fully aligned to COR3 and FEMA feedback and guidance. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757662 | FAASt [Automation Program Group 21 (Distribution) | Pending EHP Review | 2223344.42 | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under FEMA EHP review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757687 | FAASt [Automation Program Group 22 (Distribution) | Pending EHP Review | 2768746.03 | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under FEMA EHP review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757689 | FAASt [Automation Program Group 24 (Distribution) | Pending Large Project Review | 2337650.4 | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | Signed project awaiting full obligation as of Thrusday July 3rd. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757692 | FAASt [Automation Program Group 26 (Distribution) | Applicant Signed Project | 1369120.11 | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | Signed project awaiting full obligation as of Thrusday July 3rd. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757694 | FAASt [Automation Program Group 27 (Distribution) | Pending Final FEMA Review | 3292670.74 | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under FEMA EHP review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757696 | FAASt [Automation Program Group 31 (Distribution) | Pending Recipient Final Review | 1515001.61 | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under PDMG project review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757697 | FAASt [Automation Program Group 32 (Distribution) | Pending EHP Review | 2663099.41 | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under FEMA EHP review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757698 | FAASt [Automation Program Group 33] (Distribution) | Pending Final FEMA Review | 2483045.65 | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under FEMA EHP review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757699 | FAASt [Automation Program Group 34] (Distribution) | Pending PDMG Application Review | 3439728.11 | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currentlyunder PDMG application review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 757700 | FAASt [Automation Program Group 35] (Distribution) | Pending Recipient Final Review | 1743076.28 | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under FEMA EHP review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 800286 | [Automation Program Group 36] (Distribution) | Pending Recipient Final Review | 2301102.91 | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under PDMG project review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Automation | 800361 | [Automation Program Group 37] (Distribution) | Pending Recipient Final Review | 2069863.13 | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Final FEMA review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | Amaury Pachecho
Transmission | 711819 | T Priority Pole Replacement - 13400-ACACIAS TC-SAN GERMAN SECT-LA PARGUERA SECT | Pending Scope & Cost Completion by Applicant | 1705844 | 2024-09-15 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | On PM review of COR3 comments completion forecasted 7/11/25 | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | Jose Cruz Figueroa
Transmission | 749060 | Transmission Priority Pole Replacement - 5600-VICTORIA TC-AÑASCO TC | Pending Scope & Cost Completion by Applicant | 860152.65 | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | On 7/9/2025 Project was created for approval/signatures | Gutierrez Rivera, Raymond A. | Aaron Akens | Jose Cruz Figueroa
Transmission | 749072 | Transmission Priority Pole Replacement - 2700-AGUADILLA HOSPITAL DISTRITO SECT-MORA TC- | Pending Scope & Cost Completion by Applicant | 189251.19 | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | Pending QA/QC completion | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | Jose Cruz Figueroa
Transmission | 750168 | Transmission Priority Pole Replacement - 4800 Santa Isabel TC-Aibonito TO | Pending Scope & Cost Completion by Applicant | 491877.7 | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | On 6/19/2025 RFI response package and DSOW were submitted to FEMA, Currently under review by FEMA Hazard Mitigation | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | Jose Cruz Figueroa
Transmission | 750150 | Transmission Priority Pole Replacement - 4800 Santa Isabel TC-Toro Negro 1HP | Pending Scope & Cost Completion by Applicant | 150412.75 | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | Under QA/QC COR3 comments | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | Jose Cruz Figueroa
Transmission | 180052 | Line 100/200 - Ponce - Salinas | Pending EHP Review | 99892053.94 | 2024-07-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Matthew Dawson | Jose Cruz Figueroa
Transmission | 176913 | 9500 - Palo Seco SP - Catano Sect | Pending EHP Review | 35985053.2 | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Aaron Akens | Jose Cruz Figueroa
Transmission | 176971 | 8200 - San Juan SP - Catano Sect | Pending EHP Review | 15567361 | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Aaron Akens | Jose Cruz Figueroa
Transmission | 334470 | 3100 - Monacillos TC - Sabana Llana | Pending EHP Review | 49383355.93 | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Matthew Dawson | Jose Cruz Figueroa
Transmission | 167446 | 36100 - Bayamon - Monacillos | Pending EHP Review | 35849889.47 | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Ted Hicks | Jose Cruz Figueroa
Streetlighting | 704741 | Distribution Streetlighting Moca | Pending Scope & Cost Completion by Applicant | 17686091.97 | 2024-03-15 | 2024-08-15 |  | The project was submitted on July 3rd and is currently under FEMA review. | Rivera Hernandez, Jacklyn | Mariano Perez Portocarrero | Amaury Pachecho
Distribution | 735474 | Caguas Group 3 - Phase 2 | Pending Large Project Review | 16785005 | 2025-02-10 | ASAP | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under Large Project review by FEMA. | Rivera Hernandez, Jacklyn | Ted Hicks | Amaury Pachecho
Distribution | 750692 | Mayaguez Group 3 - Phase 2 | Pending EHP Review | 15430664 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under EHP review by FEMA. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | Amaury Pachecho
Distribution | 752540 | Mayaguez Group 4 - Phase 2 | Pending EHP Review | 8487643 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under EHP review by FEMA. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | Amaury Pachecho
Distribution | 790443 | San Juan Group 3 - Phase 2 | Applicant Signed Project | 222321 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under applicant signed by FEMA. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | Amaury Pachecho
Distribution | 757945 | Arecibo Group 3-Phase 2 | Pending Scope & Cost Completion by Applicant | 8540000 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 17. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | Amaury Pachecho
Distribution | 790446 | Caguas Group 4-Phase 2 | Pending Scope & Cost Completion by Applicant | 5100000 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 17. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | Amaury Pachecho
Distribution | 790427 | Caguas Group 5-Phase 2 | Pending Scope & Cost Completion by Applicant | 5100000 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 17. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | Amaury Pachecho
Distribution | 806935 | Caguas Group 6 - Phase 2 | Pending Scope & Cost Completion by Applicant | 6120000 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 31. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz | Amaury Pachecho
Distribution | 806936 | Carolina Group 3 - Phase 2 | Pending Scope & Cost Completion by Applicant | 5100000 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 31. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz | Amaury Pachecho
Distribution | 165226 | Vieques Feeders 2501-01, 2501-02, 2501-03 and Culebra Feeders 3801-01, 3801-02 | Pending Scope & Cost Completion by Applicant | 86759243.78 | 2024-03-15 | 2024-12-01 | V&C Microgrid Feeders discussed at length with HM team to establish 406 | The project was submitted to COR3 for review on July 3rd, and we are currently awaiting their feedback. The forecasted submission to FEMA is July 15th. | Diaz Munoz, Orlando | Jorge Lopez Burgos | Amaury Pachecho
Distribution | 798275 | FAASt [Distribution Feeder Rebuild #1620-02] | Pending Large Project Review | 7464273.83 | 2025-02-10 | 2025-07-01 | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA on April 1, 2025, and its current status is pending obligation since June 27. | Diaz Munoz, Orlando | Christian Tejada Marrero | Amaury Pachecho
Distribution | 797148 | FAASt [Distribution Feeder Rebuild # 8101-03] | Pending Large Project Review | 2605318.99 | 2025-02-10 |  | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA and is currently pending recipient (COR3) review in order to move forward. This status has been in place since June 27. | Diaz Munoz, Orlando | Leonardo Aquino | Amaury Pachecho
Distribution | 801166 | FAASt # [Distribution Feeder Rebuild #6601-03] | Pending EHP Review | 21387039.22 | 2025-02-10 |  | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA and is currently under FEMA EHP review. This status has been in place since July 8. | Diaz Munoz, Orlando | Joel Berrios | Amaury Pachecho
Distribution | 801172 | FAASt [Distribution Feeder Rebuild #1529-15 | Pending Large Project Review | 2529247.52 | 2025-02-10 |  | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA and is currently pending recipient (COR3) review in order to move forward. This status has been in place since June 27. | Diaz Munoz, Orlando | Leonardo Aquino | Amaury Pachecho
IT & Telecom | 551963 | Transport Network Group 1 | Pending Recipient Final Review | 84287009 | 2024-08-15 | 2025-09-15 | First 3 core sites being resubmitted March 2025 | This Project was submitted to FEMA on 3/21/2025 and has been in "Pending Recipient Final Review" in Phase 4 of the FEMA National Workflow since 6/20/2025. During the weekly follow-up on 7/7, COR3 informed that the Project cannot move forward to obligation because it is not included in the PREPA priority list. | Diaz Munoz, Orlando | Mario Santiago | Axel Rodriguez Moreno
PCC & Telecom | 746545 | Primary Control Center | Pending PDMG Scope & Cost Routing | 115638378 | 2025-04-23 | 2025-09-15 | Need TEA complete | PREPA sent letter refuting Historical District determination to FEMA. FEMA responded letter on 7/7/2025 to PREPA to provide backup documentation or explanation to why the site should NOT be a historical district and gave 30 days to answer. | Diaz Munoz, Orlando | Pete Giles | Axel Rodriguez Moreno

## Editable COPY (hidden)
isow dsow tracker? | Asset Category | FEMA Project # where applicable | Project Name (90 Day Plan) | Date added to Priority list | Obligation Need By Date | Notes | Latest Update / Comments | Primary PDMG | LUMA PROJECT MANAGER | ASSET LEAD
| Vegetation | 727531 | Island Wide Vegetation Clearing: Region 6 – Ponce Group A - LD | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 750065 | Island Wide Vegetation Clearing: Region 3 – Bayamon Group A - LD |  |  | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 727572 | Island Wide Vegetation Clearing: Region 3 – Bayamon Group A - HD | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: High Density (HD) Bayamon: Awaiting Corps of Engineers vendor review. The COE has not renewed the contract with their vender. Awaiting date of ECD. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 727692 | Island Wide Vegetation Clearing Region 4 -- Caguas Group A - LD | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 728827 | Island Wide Vegetation Clearing: Region 2 – Arecibo Group A - LD | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 728832 | Island Wide Vegetation Clearing: Region 5 – Mayaguez Group A - LD | 2024-03-15 | ASAP | Vegetation remains a priority - every day of delay imparts further damage across the system and reduces the longevity of other grid improvements in motion where they serve areas of unestablished ROW/incomplete vegetation management. Clearing teams are not as productive due to one side of the stree being obligated and the other side of the street not being obligated yet. | The vegetation management project team reached out to FEMA for status and was provided with the following: Low Density (LD): Pending EHP Review. It has been in this status since April 25. In grants portal it says: 7/8/2025 Field EHP- Enviromental: ESA Consultation letter submitted to USFWS on 6/3/25. Waiting for response. ECD 8/19/25. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956332 | 2401-01 - Distribution - (San Juan - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956330 | 3007-03 - Distribution - (Caguas - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956339 | 3301-01 - Distribution - (Caguas - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956335 | 2301-02 - Distribution - (San Juan - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956337 | 6012-02 - Distribution - (Mayaguez - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Distribution Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956353 | 36100 - Transmission - (Arecibo - Group D) Single Line Project | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956342 | 36400 - Transmission - (Arecibo - Group D) Single Line Project | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956348 | 10000 - Transmission - (Bayamon - Group B) Single Line Project | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956349 | 36800 - Transmission - (San Juan - Group D) Single Line Project | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956345 | 2400 - Transmission - (Arecibo - Group B) Single Line Project | 2025-03-15 | 2025-09-01 | Top Transmission Veg Reliability Impact | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956341 | 5803-02 - Distribution - (Ponce - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956331 | 6014-02 - Distribution - (Mayaguez - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956340 | 5602-02 - Distribution - (Ponce - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956357 | 1900 - Transmission - (Mayaguez - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Vegetation | 956343 | 4800 - Transmission - (Ponce - Group C) Single Line Project | 2025-03-15 | 2025-09-01 | Top Wildfire Risk | All Single Line project have been submitted to FEMA and are awaiting review. | ACEVEDO CHAPARRO, JONATHAN | Matt Watson | RENE BAPTISTE
| Substations | 682834 | Costa Sur Transformer Replacement - Stabilization phase | 2024-11-24 | 2025-02-25 | Critical Stabilization to enable full project execution | Project is under FEMA phase 5, Applicant signed project on 5/27/25. Pending obligation, no further actions from LUMA | VALENTIN QUIRINDO, NORMANDO A. | Luderis Berrios Pastrana | GABRIEL TORRES ARROYO
| Substations | 547187 | FAASt - [Substation Component Replacement Program] (Substation) - Group 1 | 2024-09-15 |  | Will need expedited EHP support - needed to support restoration of OOS equipment | On 6/5/2025 LUMA uploaded Hazard Mitigation RFI regarding each substation clasification according to: Substation Rebuild Program, Substation Component Replacement Program, SCADA Remote Access and RTU Replacements, Substation Protection, Automation, and Control (PAC) Upgrades, Advanced Sensors (PMUs) & Wide-Area Monitoring, Protection & Control (WAMPAC). LUMA is currently pending FEMA Mitigation approval of RFI to continue process. FEMA forecast 7/15 | VALENTIN QUIRINDO, NORMANDO A. |  | GABRIEL TORRES ARROYO
| Automation | 746309 | Group 30- DAUT BAYMON 9203-03 | 2024-03-15 | July 15 2024 | The benchmark/template project for Distribution Automation to align on HM splits across the porgram - has been in discussion for over a year with HM team prompting current submissions to need to be 100% 428 in order to advance to obligation and enable execution | This project has been shifted to full 428/406 and is the pilot project/template for establishing the HM proposal and aligning toi the FEMA HM resilution documnet and resiliency plan. The final version is under FEMA EHP review and is fully aligned to COR3 and FEMA feedback and guidance. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757662 | FAASt [Automation Program Group 21 (Distribution) | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending Final FEMA Review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757687 | FAASt [Automation Program Group 22 (Distribution) | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending Final FEMA Review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757689 | FAASt [Automation Program Group 24 (Distribution) | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | Signed project awaiting full obligation as of Thrusday July 3rd. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757692 | FAASt [Automation Program Group 26 (Distribution) | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | Signed project awaiting full obligation as of Thrusday July 3rd. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757694 | FAASt [Automation Program Group 27 (Distribution) | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending Final FEMA Review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757696 | FAASt [Automation Program Group 31 (Distribution) | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending Large Project Review | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757697 | FAASt [Automation Program Group 32 (Distribution) | 2025-01-31 | 2025-06-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under FEMA EHP review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757698 | FAASt [Automation Program Group 33] (Distribution) | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending Final FEMA Review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757699 | FAASt [Automation Program Group 34] (Distribution) | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending FEMA 406 HMP Completion. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 757700 | FAASt [Automation Program Group 35] (Distribution) | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending Large Project Review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 800286 | [Automation Program Group 36] (Distribution) | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Pending Large Project Review | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Automation | 800361 | [Automation Program Group 37] (Distribution) | 2025-02-25 | 2025-07-10 | Material and Engineering available and waiting - reliability work that can be accelerated with expedited obligation… project submitted at 100% 428 to expedite initial obligation in parallel to alignment/collaboration with the FEMA HM team. | The project was submitted to FEMA in April and is currently under Final FEMA review. | Rivera Hernandez, Jacklyn | Angelica Rosario Davila | AMAURY PACHECHO
| Transmission | 711819 | T Priority Pole Replacement - 13400-ACACIAS TC-SAN GERMAN SECT-LA PARGUERA SECT | 2024-09-15 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | On PM review of COR3 comments completion forecasted 7/11/25 | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | JOSE CRUZ FIGUEROA
| Transmission | 749060 | Transmission Priority Pole Replacement - 5600-VICTORIA TC-AÑASCO TC | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | On 7/9/2025 Project was created for approval/signatures | Gutierrez Rivera, Raymond A. | Aaron Akens | JOSE CRUZ FIGUEROA
| Transmission | 749072 | Transmission Priority Pole Replacement - 2700-AGUADILLA HOSPITAL DISTRITO SECT-MORA TC- | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | Pending QA/QC completion | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | JOSE CRUZ FIGUEROA
| Transmission | 750168 | Transmission Priority Pole Replacement - 4800 Santa Isabel TC-Aibonito TO | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | On 6/19/2025 RFI response package and DSOW were submitted to FEMA, Currently under review by FEMA Hazard Mitigation | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | JOSE CRUZ FIGUEROA
| Transmission | 750150 | Transmission Priority Pole Replacement - 4800 Santa Isabel TC-Toro Negro 1HP | 2025-02-10 |  | ** Transmission Poles & Critial Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Shorter term fixes to support reliability on Transmision** | Under QA/QC COR3 comments | Gutierrez Rivera, Raymond A. | Carlos Samalot Gomez | JOSE CRUZ FIGUEROA
| Transmission | 180052 | Line 100/200 - Ponce - Salinas | 2024-07-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Matthew Dawson | JOSE CRUZ FIGUEROA
| Transmission | 176913 | 9500 - Palo Seco SP - Catano Sect | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Aaron Akens | JOSE CRUZ FIGUEROA
| Transmission | 176971 | 8200 - San Juan SP - Catano Sect | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Aaron Akens | JOSE CRUZ FIGUEROA
| Transmission | 334470 | 3100 - Monacillos TC - Sabana Llana | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Matthew Dawson | JOSE CRUZ FIGUEROA
| Transmission | 167446 | 36100 - Bayamon - Monacillos | 2024-10-15 |  | combined DSOWs - Vegetation + Line Section Rebuilds at the same time | On 7/9/25 All 5 TL priority projects in FEMA Phase 4 | Gutierrez Rivera, Raymond A. | Ted Hicks | JOSE CRUZ FIGUEROA
| Streetlighting | 704741 | Distribution Streetlighting Moca | 2024-03-15 | 2024-08-15 |  | The project was submitted on July 3rd and is currently under FEMA review. | Rivera Hernandez, Jacklyn | Mariano Perez Portocarrero | AMAURY PACHECHO
| Distribution | 735474 | Caguas Group 3 - Phase 2 | 2025-02-10 | ASAP | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under Large Project review by FEMA. | Rivera Hernandez, Jacklyn | Ted Hicks | AMAURY PACHECHO
| Distribution | 750692 | Mayaguez Group 3 - Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under EHP review by FEMA. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | AMAURY PACHECHO
| Distribution | 752540 | Mayaguez Group 4 - Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under EHP review by FEMA. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | AMAURY PACHECHO
| Distribution | 790443 | San Juan Group 3 - Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | This project was submitted to FEMA in January and is currently under applicant signed by FEMA. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | AMAURY PACHECHO
| Distribution | 757945 | Arecibo Group 3-Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 17. Project was uploaded to GP on 7/10/25. A soft RFI was sent by FEMA requesting some clarification related to pole cost. Team is working with the clarifications. Forecast is for 08/01/25. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | AMAURY PACHECHO
| Distribution | 790446 | Caguas Group 4-Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 17. Project was uploaded to GP on 7/10/25. A soft RFI was sent by FEMA requesting some clarification related to pole cost. Team is working with the clarifications. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | AMAURY PACHECHO
| Distribution | 790427 | Caguas Group 5-Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 17. Project was uploaded to GP on 7/10/25. A soft RFI was sent by FEMA requesting some clarification related to pole cost. Team is working with the clarifications. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz; Angel Marcano Soto | AMAURY PACHECHO
| Distribution | 806935 | Caguas Group 6 - Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 31. In process. Submission Forecast: 07/31/25. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz | AMAURY PACHECHO
| Distribution | 806936 | Carolina Group 3 - Phase 2 | 2025-02-10 |  | ** Distribution Pole & Conductor Repairs - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project is currently under development, and the forecasted submission date is July 31.In process. Submission Forecast: 07/31/25. | Rivera Hernandez, Jacklyn | Yaritza Acevedo Ortiz | AMAURY PACHECHO
| Distribution | 165226 | Vieques Feeders 2501-01, 2501-02, 2501-03 and Culebra Feeders 3801-01, 3801-02 | 2024-03-15 | 2024-12-01 | V&C Microgrid Feeders discussed at length with HM team to establish 406 | The project was submitted to COR3 for review on July 3rd, and we are currently awaiting their feedback. The forecasted submission to FEMA is July 15th. Team is working with modifications on DSOW and CE based on QA/QC and COR3 recommendations + modifications to align DSOW with the IFC package. An extension of RFI submission will be requested to FEMA for 08/31/25. | Diaz Munoz, Orlando | Jorge Lopez Burgos | AMAURY PACHECHO
| Distribution | 798275 | FAASt [Distribution Feeder Rebuild #1620-02] | 2025-02-10 | 2025-07-01 | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA on April 1, 2025, and its current status is pending obligation since June 27. | Diaz Munoz, Orlando | Christian Tejada Marrero | AMAURY PACHECHO
| Distribution | 797148 | FAASt [Distribution Feeder Rebuild # 8101-03] | 2025-02-10 |  | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA and is currently pending recipient (COR3) review in order to move forward. This status has been in place since June 27. | Diaz Munoz, Orlando | Leonardo Aquino | AMAURY PACHECHO
| Distribution | 801166 | FAASt # [Distribution Feeder Rebuild #6601-03] | 2025-02-10 |  | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA and is currently under FEMA EHP review. This status has been in place since July 8. | Diaz Munoz, Orlando | Joel Berrios | AMAURY PACHECHO
| Distribution | 801172 | FAASt [Distribution Feeder Rebuild #1529-15 | 2025-02-10 |  | ** Distribution Feeders - materials on hand, engineering on hand - labor expansion in contracting now - Submission as 100% 428 to expedite execution while collaborating with HM team on %406** | The project was submitted to FEMA and is currently pending recipient (COR3) review in order to move forward. This status has been in place since June 27. | Diaz Munoz, Orlando | Leonardo Aquino | AMAURY PACHECHO
| IT & Telecom | 551963 | Transport Network Group 1 | 2024-08-15 | 2025-09-15 | First 3 core sites being resubmitted March 2025 | This Project was submitted to FEMA on 3/21/2025 and has been in "Pending Recipient Final Review" in Phase 4 of the FEMA National Workflow since 6/20/2025. During the weekly follow-up on 7/7, COR3 informed that the Project cannot move forward to obligation because it is not included in the PREPA priority list. | Diaz Munoz, Orlando | Mario Santiago | AXEL RODRIGUEZ MORENO
| PCC & Telecom | 746545 | Primary Control Center | 2025-04-23 | 2025-09-15 | Need TEA complete | PREPA sent letter refuting Historical District determination to FEMA. FEMA responded letter on 7/7/2025 to PREPA to provide backup documentation or explanation to why the site should NOT be a historical district and gave 30 days to answer. | Diaz Munoz, Orlando | Pete Giles | AXEL RODRIGUEZ MORENO

## LUMA - Projects to Add to Pri (hidden)
Priority Group | Notes | DOE Scope Support | Project # | Title | Asset | SUB ASSET | Process Step | Project costs - Submitted to FEMA * | 428 Allocation * | 406 Allocation * | Project Status | Additional comments
7 | First 3 core sites upgrades (note - original project was all sites (and project A&E was for portfolio of all sites that needs to be distributed) - broken into groups focusing on core sites first) |  | 551963 | Transport Network Group 1 | IT/OT | N/A | FEMA CRC Status: "Pending Recipient Final Review" | 7469879.23 | 7469879.23 | 0 |  | WTBC
7 | Tower upgrades for top priority wireless traffic |  | 673292 | Telecom Cerro Punta | IT/OT | N/A | FEMA CRC Status: "Pending EHP Review" | 9215279.16 | 8133945.24 | 38642.11 |  | WTBC
7 | Tower upgrades for top priority wireless traffic |  | 678800 | Telecom Infrastructure – Group B | IT/OT | N/A | FEMA CRC Status: "Pending Scope and Cost Development" | 16033618.38 | 13148929.44 | 55895.84 |  | WTBC
7 | Core network resilience and redundancy |  | 662238 | Microwave Point to Point Backbone Group A | IT/OT | N/A | COR3: Pending review to submit to FEMA. | 17156972.98 | 14142413.06 | 3199102 |  | WTBC
8 | Pipeline of RTU upgrade work supports system visibility & stability - Group 1 is very advanced in construction |  | 551926 | SCADA Remote Access RTU Replacements Group 2 | IT/OT | N/A | FEMA CRC Status: "Pending EHP Review" | 6464473.96 | 5267467.99 | 1073462.61 |  | WTBC
8 | Pipeline of RTU upgrade work supports system visibility & stability - Group 1 is very advanced in construction |  | 551927 | SCADA Remote Access RTU Replacements Group 3 | IT/OT | N/A | FEMA PDMG: Pending pre-review to submit to CRC. | 19213188.6 | 14955608.63 | 3299617.88 |  | WTBC
9 | Stabilization for systems that support T&D |  | 668665 | Cybersecurity Program Implementation | IT/OT | N/A | Pending LRC to submit to FEMA. | 24587256.15 | 24587256.15 | 0 |  | WTBC
9 | Stabilization for systems that support T&D |  | 675345 | IT OT Technology Systems Reparations Group 1 | IT/OT | N/A | LUMA PM Collaboration review | 21970036.67 | 20714180.51 | 864148.83 |  | WTBC
9 | Stabilization for systems that support T&D |  | 756545 | Primary Control Center | IT/OT | N/A | TEA | 131700000
6 | Costa Sur Cable project to enable full capacity of stabilization work |  | 957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | N/A |  | 1250845.76 |  |  |  | WTBC
6 | PAC supports system stabilization and operational efficacy to protect equipment |  | 746660 | PAC Replacement | Substation | PAC |  | 15096658.56 | 1617375.6 | 16713944.15 |  | WTBC
Notes:
Project costs - Submitted to FEMA = Cost presented herein are based on scope of works presented by LUMA and available in Grants Portal
Current PW Version Gross Cost & 428 allocation = Amount is the estimated amount allocated to 428 as per scope of work presented
406 Allocation = Amount is the estimated amount allocated to 428 as per SOW available on Grants Portal
A&E-PW 9510 & E&M-PW 10710 = Amount as per cost allocation on SOW available on Grants Portal
A&E Costs Incurred-Luma Provided & E&M Cost - Luma Provided = Amounts provided on LUMA P3A Prority Project list
Vegetation Projects- Cost presented are LUMA estimates. Amounts are subject to change due to FEMA Validation Analysis and HMP Approach- Distribution and Transmission