## Consolidated
FEMA Project # | Title | Asset | Obligation Date | Design Start | Design End | Construction Percentage | Construction Start | Construction Completion | Close Out Start
801166 | FAASt [Distribution Feeder Rebuild # 6601-03] (Distribution) | Distribution – Feeder Rebuild | 2026-01-08 | 2022-08-30 | 2026-05-15 | 0% | 2026-11-03 08:00 | 2028-01-25 17:00 | 2028-07-23 17:00
812569 | FAASt [Distribution Feeder Rebuild 3502-02] | Distribution – Feeder Rebuild | 2025-09-25 04:00 | 2023-01-02 17:00 | 2025-12-19 | 0% | 2026-06-01 08:00 | 2026-10-17 17:00 | 2027-04-15 17:00
797148 | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) | Distribution – Feeder Rebuild | 2025-09-17 04:00 | 2022-09-27 | 2026-03-05 | 0% | 2026-05-27 08:00 | 2026-09-25 17:00 | 2027-03-24 17:00
798275 | FAASt [Distribution Feeder Rebuild # 1620-02] (Distribution) | Distribution – Feeder Rebuild | 2025-09-17 04:00 | 2023-03-23 17:00 | 2025-11-19 | 0% | 7/20/2026 | 2027-04-12 | 2027-10-09
801172 | FAASt [Distribution Feeder Rebuild # 1529-15] (Distribution) | Distribution – Feeder Rebuild | 2025-09-17 04:00 | 2022-11-14 | 2026-03-20 | 0% | 2026-07-14 08:00 | 2026-11-02 17:00 | 2027-05-01 17:00
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution – Feeder Rebuild | 2025-09-25 04:00 | 2023-02-24 | 2025-09-26 17:00 | 0% | 2026-04-07 08:00 | 2026-06-17 17:00 | 2026-12-14 17:00
334323 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 1] (Distribution) | Distribution – Pole Replacement | 2022-05-26 04:00 | 2021-09-13 | 2022-04-28 17:00 | 91% | 2022-03-15 08:00 | 2027-06-30 | 2027-12-27
334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution – Pole Replacement | 2022-05-20 04:00 | 2021-09-10 | 2022-04-29 08:00 | 87% | 2022-12-29 08:00 | 2027-06-30 | 2027-12-27
334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution – Pole Replacement | 2022-05-26 04:00 | 2021-11-10 | 2022-05-06 08:00 | 88% | 2023-02-10 08:00 | 2027-06-30 | 2027-12-27
334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution – Pole Replacement | 2022-06-10 15:48 | 2021-11-02 | 2022-05-04 08:00 | 97% | 2021-09-23 08:00 | 2027-06-30 | 2027-12-27
542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution – Pole Replacement | 2022-06-03 15:23 | 2021-10-29 | 2022-05-06 08:00 | 97% | 2022-03-21 08:00 | 2027-06-30 | 2027-12-27
673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution – Pole Replacement | 2022-10-17 04:00 | 2022-05-24 | 2022-06-28 17:00 | 86% | 2021-11-15 08:00 | 2027-06-30 17:00 | 2027-12-27 17:00
673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution – Pole Replacement | 2022-10-24 04:00 | 2022-06-29 | 2022-06-29 17:00 | 83% | 2022-07-14 08:00 | 2027-06-30 | 2027-12-27
673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution – Pole Replacement | 2022-08-02 04:00 | 2022-06-01 | 2022-06-01 17:00 | 62% | 2022-04-13 08:00 | 2027-06-30 | 2027-12-27
673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2023-03-30 | 2023-03-30 17:00 | 89% | 2022-01-12 08:00 | 2027-06-30 | 2027-12-27
673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution – Pole Replacement | 2022-08-02 04:00 | 2022-05-27 17:00 | 2022-05-27 17:00 | 89% | 2022-05-05 08:00 | 2027-06-30 | 2027-12-27
673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution – Pole Replacement | 2022-08-08 04:00 | 2022-05-30 | 2022-06-13 08:00 | 87% | 2022-03-24 08:00 | 2027-06-30 | 2027-12-27
673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution – Pole Replacement | 2022-12-21 04:00 | 2022-05-27 | 2022-06-30 17:00 | 86% | 2022-06-22 08:00 | 2027-06-30 | 2027-12-27
673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution – Pole Replacement | 2022-07-12 04:00 | 2022-05-30 | 2023-02-28 17:00 | 85% | 2023-05-17 17:00 | 2027-06-30 | 2027-12-27
673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution – Pole Replacement | 2022-07-12 04:00 | 2022-05-13 | 2022-05-13 | 100% | 2022-04-12 08:00 | 2023-09-05 17:00 | 2026-06-30
673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution – Pole Replacement | 2022-10-17 04:00 | 2022-05-27 | 2022-06-27 08:00 | 80% | 2022-11-30 08:00 | 2027-06-30 | 2027-12-27
673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution – Pole Replacement | 2022-08-24 04:00 | 2022-05-30 | 2022-06-29 08:00 | 87% | 2023-03-28 08:00 | 2027-06-30 | 2027-12-27
673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution – Pole Replacement | 2022-08-08 04:00 | 2022-06-07 17:00 | 2022-06-07 17:00 | 78% | 2024-04-15 17:00 | 2027-06-30 | 2027-12-27
673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution – Pole Replacement | 2022-07-12 04:00 | 2022-05-26 17:00 | 2022-05-26 17:00 | 56% | 2024-04-09 17:00 | 2026-12-30 | 2027-06-28
674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution – Pole Replacement | 2022-09-16 04:00 | 2022-05-31 | 2022-06-27 08:00 | 88% | 2022-11-22 17:00 | 2027-06-30 | 2027-12-27
674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution – Pole Replacement | 2022-08-08 04:00 | 2022-05-23 | 2022-06-23 08:00 | 80% | 2022-11-10 17:00 | 2027-06-30 | 2027-12-27
674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution – Pole Replacement | 2022-10-17 04:00 | 2022-06-06 | 2022-06-29 17:00 | 88% | 2023-01-31 08:00 | 2027-06-30 | 2027-12-27
674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution – Pole Replacement | 2022-09-16 04:00 | 2022-05-31 | 2022-06-10 08:00 | 78% | 2022-11-21 08:00 | 2027-06-30 | 2027-12-27
674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution – Pole Replacement | 2022-10-17 04:00 | 2022-05-31 | 2022-06-28 08:00 | 88% | 2023-02-15 08:00 | 2027-06-30 | 2027-12-27
674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution – Pole Replacement | 2022-08-08 04:00 | 2022-05-24 | 2022-06-21 08:00 | 100% | 2023-02-14 17:00 | 2023-05-04 17:00 | 2026-06-30
678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-07-26 | 2022-07-26 | 79% | 2022-10-30 15:27 | 2027-06-30 | 2027-12-27
678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-07-25 | 2022-07-25 | 87% | 2023-03-23 08:00 | 2027-06-30 | 2027-12-27
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | 2025-09-17 04:00 | 2025-10-28 | 2025-11-10 | 95% | 2025-11-14 17:00 | 2026-02-27 17:00 | 2026-08-26 17:00
956342 | FAASt [Arecibo Region 2 Transmission Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | 2025-09-18 | 2025-09-18 | 2026-04-16 | 0% | 2026-04-16 | 2028-06-01 | 2028-11-28
679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-02 | 2022-08-02 | 80% | 2024-04-05 17:00 | 2027-06-30 | 2027-12-27
679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-04 | 2022-08-04 | 78% | 2023-05-29 17:00 | 2027-06-30 | 2027-12-27
679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-07-27 | 2022-07-27 | 89% | 2023-04-03 08:00 | 2027-06-30 | 2027-12-27
679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-07-22 | 2022-07-22 | 88% | 2023-02-06 17:00 | 2027-06-30 | 2027-12-27
679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-07-29 | 2022-07-29 | 94% | 2023-05-10 08:00 | 2027-06-30 | 2027-12-27
679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-07-19 | 2022-07-20 | 88% | 2023-08-08 17:00 | 2027-06-30 | 2027-12-27
679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-07-20 | 2022-07-20 | 88% | 2023-05-08 17:00 | 2027-06-30 | 2027-12-27
679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-07-26 | 2022-07-27 | 86% | 2023-06-26 08:00 | 2027-06-30 | 2027-12-27
679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-07-26 | 2022-07-28 | 88% | 2023-07-05 17:00 | 2027-06-30 | 2027-12-27
682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-10-21 | 2022-10-28 08:00 | 75% | 2023-08-07 17:00 | 2027-06-30 | 2027-12-27
682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution – Pole Replacement | 2023-01-31 04:00 | 2022-09-09 | 2022-11-22 08:00 | 26% | 2023-12-19 08:00 | 2027-06-30 | 2027-12-27
682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-10-24 | 2022-10-25 08:00 | 86% | 2023-01-26 17:00 | 2027-06-30 | 2027-12-27
682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution – Pole Replacement | 2023-01-31 04:00 | 2022-10-24 | 2022-10-31 08:00 | 95% | 2023-03-19 08:00 | 2027-06-30 | 2027-12-27
682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution – Pole Replacement | 2023-01-24 04:00 | 2022-08-31 | 2022-11-08 17:00 | 83% | 2022-01-26 08:00 | 2027-06-30 | 2027-12-27
682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution – Pole Replacement | 2023-01-31 04:00 | 2022-10-31 17:00 | 2022-10-31 17:00 | 80% | 2023-07-17 17:00 | 2027-06-30 | 2027-12-27
682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-08-10 | 2022-10-31 17:00 | 51% | 2023-01-19 08:00 | 2027-06-30 | 2027-12-27
682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution – Pole Replacement | 2023-01-24 04:00 | 2022-10-24 17:00 | 2022-10-24 17:00 | 81% | 2023-04-28 17:00 | 2027-06-30 | 2027-12-27
682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution – Pole Replacement | 2023-01-31 04:00 | 2022-11-04 17:00 | 2022-11-04 17:00 | 88% | 2023-05-05 17:00 | 2027-06-30 | 2027-12-27
682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-10-27 | 2022-10-28 08:00 | 82% | 2022-11-19 08:00 | 2027-06-30 | 2027-12-27
682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-08-25 | 2022-10-31 08:00 | 90% | 2023-06-16 08:00 | 2027-06-30 | 2027-12-27
682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-17 | 2022-08-18 08:00 | 82% | 2023-08-24 17:00 | 2026-12-30 | 2027-06-28
682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-18 17:00 | 2022-08-18 08:00 | 89% | 2023-08-25 08:00 | 2027-06-30 | 2027-12-27
682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-08-18 17:00 | 2022-08-18 08:00 | 85% | 2023-01-27 08:00 | 2027-06-30 | 2027-12-27
682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-23 17:00 | 2022-08-23 08:00 | 88% | 2022-11-08 08:00 | 2027-06-30 | 2027-12-27
682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution – Pole Replacement | 2023-01-24 04:00 | 2022-08-24 17:00 | 2022-08-24 08:00 | 89% | 2022-03-01 08:00 | 2027-06-30 | 2027-12-27
682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution – Pole Replacement | 2023-01-31 04:00 | 2022-08-11 | 2022-08-11 | 97% | 2023-04-12 08:00 | 2027-06-30 | 2027-12-27
685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-19 17:00 | 2022-08-19 08:00 | 86% | 2023-07-14 17:00 | 2027-06-30 | 2027-12-27
685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-08-10 | 2022-08-11 17:00 | 100% | 2023-05-25 08:00 | 2023-08-17 08:00 | 2026-06-30
685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution – Pole Replacement | 2023-01-24 04:00 | 2022-08-19 17:00 | 2022-08-19 08:00 | 81% | 2023-06-28 08:00 | 2027-06-30 | 2027-12-27
685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution – Pole Replacement | 2023-01-10 04:00 | 2022-08-17 | 2022-08-18 08:00 | 88% | 2023-07-13 08:00 | 2027-06-30 | 2027-12-27
686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-11 | 2022-08-12 17:00 | 100% | 2023-05-18 17:00 | 2023-07-18 17:00 | 2026-06-30
686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution – Pole Replacement | 2022-12-27 04:00 | 2022-08-18 17:00 | 2022-08-18 08:00 | 97% | 2023-06-26 08:00 | 2027-06-30 | 2027-12-27
686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution – Pole Replacement | 2023-02-16 04:00 | 2022-10-25 17:00 | 2022-10-25 17:00 | 87% | 2023-05-10 17:00 | 2027-06-30 | 2027-12-27
688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution – Pole Replacement | 2023-01-31 04:00 | 2022-11-07 | 2022-11-16 08:00 | 100% | 2023-09-21 08:00 | 2023-10-27 08:00 | 2026-06-30
688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution – Pole Replacement | 2023-03-08 04:00 | 2022-11-07 | 2022-12-02 08:00 | 89% | 2023-04-13 08:00 | 2027-06-30 | 2027-12-27
688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution – Pole Replacement | 2023-03-20 04:00 | 2022-11-08 | 2022-12-02 17:00 | 85% | 2023-07-19 17:00 | 2027-09-30 | 2028-03-28
688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution – Pole Replacement | 2023-02-16 04:00 | 2022-11-04 | 2022-11-16 17:00 | 85% | 2023-05-18 17:00 | 2027-06-30 | 2027-12-27
688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution – Pole Replacement | 2023-03-20 15:45 | 2022-11-04 | 2022-12-02 17:00 | 87% | 2023-04-19 17:00 | 2027-06-30 | 2027-12-27
688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution – Pole Replacement | 2023-01-31 16:56 | 2022-11-04 | 2022-12-01 17:00 | 84% | 2023-05-30 17:00 | 2027-06-30 | 2027-12-27
688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution – Pole Replacement | 2023-03-08 16:36 | 2022-11-10 | 2022-12-16 17:00 | 89% | 2023-05-03 17:00 | 2027-06-30 | 2027-12-27
688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution – Pole Replacement | 2023-03-08 16:36 | 2022-11-04 | 2022-12-01 17:00 | 51% | 2024-01-25 17:00 | 2027-06-30 | 2027-12-27
688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution – Pole Replacement | 2023-01-31 16:56 | 2022-11-04 | 2022-11-16 17:00 | 87% | 2021-10-27 08:00 | 2027-06-30 | 2027-12-27
689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution – Pole Replacement | 2023-03-02 16:24 | 2022-11-04 | 2022-12-22 17:00 | 90% | 2023-07-20 17:00 | 2027-06-30 | 2027-12-27
691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution – Pole Replacement | 2023-02-16 16:50 | 2022-12-01 17:00 | 2022-12-01 08:00 | 88% | 2023-08-11 08:00 | 2026-12-30 | 2027-06-28
701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution – Pole Replacement | 2023-03-02 04:00 | 2022-08-23 | 2022-12-16 17:00 | 100% | 2023-04-27 17:00 | 2023-10-31 17:00 | 2026-06-30
701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution – Pole Replacement | 2023-03-08 04:00 | 2022-12-30 17:00 | 2022-12-30 17:00 | 100% | 2023-06-07 17:00 | 2023-10-25 17:00 | 2026-02-03 17:00
701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution – Pole Replacement | 2023-03-08 04:00 | 2022-12-21 17:00 | 2022-12-21 17:00 | 84% | 2023-05-11 17:00 | 2027-06-30 | 2027-12-27
701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution – Pole Replacement | 2023-03-08 04:00 | 2022-12-21 08:00 | 2022-12-21 08:00 | 90% | 2023-04-14 17:00 | 2027-06-30 | 2027-12-27
701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution – Pole Replacement | 2023-03-08 04:00 | 2022-12-16 17:00 | 2022-12-16 17:00 | 89% | 2023-06-08 17:00 | 2027-06-30 | 2027-12-27
701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution – Pole Replacement | 2023-03-02 04:00 | 2022-12-15 08:00 | 2022-12-15 08:00 | 67% | 2024-02-20 08:00 | 2027-06-30 | 2027-12-27
704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution – Pole Replacement | 2023-04-06 04:00 | 2023-02-02 17:00 | 2023-02-02 08:00 | 88% | 2023-07-26 08:00 | 2027-06-30 | 2027-12-27
704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution – Pole Replacement | 2023-04-06 04:00 | 2023-02-07 | 2023-02-09 08:00 | 91% | 2023-07-19 08:00 | 2027-06-30 | 2027-12-27
704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution – Pole Replacement | 2023-05-17 04:00 | 2023-02-21 | 2023-02-28 08:00 | 84% | 2022-09-12 08:00 | 2027-06-30 | 2027-12-27
704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution – Pole Replacement | 2023-05-17 04:00 | 2023-02-09 | 2023-02-24 17:00 | 86% | 2023-06-28 17:00 | 2027-06-30 | 2027-12-27
704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution – Pole Replacement | 2023-04-06 04:00 | 2023-01-25 | 2023-02-02 17:00 | 80% | 2023-05-31 17:00 | 2027-06-30 | 2027-12-27
704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution – Pole Replacement | 2023-08-04 04:00 | 2023-02-09 | 2023-02-28 08:00 | 50% | 2023-12-12 08:00 | 2026-12-30 | 2027-06-28
705527 | FAASt [Distribution Pole and Conductor Repair – San Juan 17-18-19-20-21] (Distribution) | Distribution – Pole Replacement | 2023-07-28 04:00 | 2023-02-13 | 2023-02-28 08:00 | 68% | 2023-12-13 08:00 | 2027-06-30 | 2027-12-27
705584 | FAASt [Pole and Conductor Repair - Ponce Groups 14 & 15] (Distribution) | Distribution – Pole Replacement | 2023-06-16 04:00 | 2023-02-14 | 2023-02-28 08:00 | 80% | 2023-01-15 08:00 | 2027-06-30 | 2027-12-27
708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution – Pole Replacement | 2023-10-23 04:00 | 2023-03-22 | 2023-03-30 08:00 | 89% | 2023-11-14 08:00 | 2027-06-30 | 2027-12-27
710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-11-01 04:00 | 2023-07-31 | 2023-07-31 | 71% | 2024-11-18 17:00 | 2027-06-30 | 2027-12-27
710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2025-01-07 04:00 | 2023-08-25 | 2023-08-25 | 93% | 2025-03-19 17:00 | 2027-06-30 | 2027-12-27
710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 Phase 2] (Distribution) | Distribution – Pole Replacement | 2023-10-23 04:00 | 2023-07-14 | 2023-07-14 | 100% | 2024-04-01 17:00 | 2024-11-25 17:00 | 2026-06-30
711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-08-26 04:00 | 2023-09-21 | 2023-10-31 | 89% | 2024-09-13 17:00 | 2027-06-30 | 2027-12-27
711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-03-22 04:00 | 2023-08-15 | 2023-09-15 | 92% | 2024-04-08 17:00 | 2027-06-30 | 2027-12-27
712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-11-01 04:00 | 2023-07-31 | 2023-09-29 | 84% | 2025-01-08 17:00 | 2027-06-30 | 2027-12-27
735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution – Pole Replacement | 2025-09-17 04:00 | 2024-06-28 17:00 | 2024-06-28 08:00 | 35% | 2025-10-29 08:00 | 2027-07-30 | 2028-01-26
738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-11-25 04:00 | 2023-12-19 | 2024-02-15 17:00 | 74% | 2025-01-10 17:00 | 2027-06-30 | 2027-12-27
738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-11-25 04:00 | 2023-09-26 | 2023-11-30 17:00 | 94% | 2025-02-13 17:00 | 2027-06-30 | 2027-12-27
738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-11-25 04:00 | 2023-09-22 | 2023-10-27 17:00 | 69% | 2025-01-22 17:00 | 2027-07-30 | 2028-01-26
738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2025-02-06 04:00 | 2023-11-21 | 2023-12-28 08:00 | 69% | 2025-05-16 08:00 | 2027-07-30 | 2028-01-26
742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-05-31 04:00 | 2023-09-22 | 2023-11-17 17:00 | 85% | 2024-05-31 08:00 | 2027-06-30 | 2027-12-27
542687 | FAASt [Lajas Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-05-20 04:00 | 2021-10-12 | 2022-03-08 | 93% | 2022-07-05 08:00 | 2026-09-11 17:00 | 2027-03-10 17:00
542688 | FAASt [Aguada Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-05-05 04:00 | 2021-10-29 | 2022-03-08 | 95% | 2022-06-15 08:00 | 2026-08-27 17:00 | 2027-02-23 17:00
542690 | FAASt [Maunabo Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-05-05 15:19 | 2021-10-05 | 2022-02-04 | 95% | 2022-06-20 08:00 | 2026-10-28 10:41 | 2027-04-26 10:41
659715 | FAASt [Aibonito Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-12-27 04:00 | 2022-02-15 | 2022-07-01 | 90% | 2022-11-22 08:00 | 2026-09-11 10:40 | 2027-03-10 10:40
542517 | FAASt [Luquillo Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-05-20 04:00 | 2021-11-05 | 2022-03-08 | 87% | 2022-06-27 08:00 | 2026-06-11 11:00 | 2026-12-08 11:00
542756 | FAASt [Guánica Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-05-26 04:00 | 2021-10-25 | 2022-03-08 | 89% | 2022-08-10 08:00 | 2026-05-25 17:00 | 2026-11-21 17:00
659623 | FAASt [Cataño Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-12-27 04:00 | 2022-02-15 | 2022-07-06 | 77% | 2022-11-28 08:00 | 2026-06-11 11:32 | 2026-12-08 11:32
659625 | FAASt [Dorado Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-01-24 04:00 | 2022-03-22 | 2022-08-18 | 79% | 2022-11-22 08:00 | 2026-06-11 10:32 | 2026-12-08 10:32
659968 | FAASt [San Germán Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-05-04 04:00 | 2022-03-17 | 2023-03-13 | 72% | 2023-05-08 08:00 | 2027-04-12 | 2027-10-09 17:00
660227 | FAASt [Hatillo Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-01-24 04:00 | 2022-03-31 | 2022-08-04 | 79% | 2022-11-22 08:00 | 2026-09-04 08:08 | 2027-03-03 08:08
660239 | FAASt [Villalba Streetlighting] (Distribution) | Distribution – Streetlighting | 2022-08-24 04:00 | 2022-02-01 | 2022-07-01 | 88% | 2022-10-28 08:00 | 2026-05-15 17:00 | 2026-11-11 17:00
660437 | FAASt [Manati Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-01-24 04:00 | 2022-02-15 | 2022-07-29 | 66% | 2022-11-04 08:00 | 2027-02-07 03:31 | 2027-08-06 03:31
671502 | FAASt [Yabucoa Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-12-29 04:00 | 2022-10-26 | 2023-06-27 | 68% | 2023-07-11 08:00 | 2026-07-11 19:17 | 2027-01-07 19:17
673504 | FAASt [Gurabo Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-05-17 04:00 | 2022-05-24 | 2023-02-28 | 69% | 2023-03-06 08:00 | 2027-06-13 06:35 | 2027-12-10 06:35
678789 | FAASt [Carolina Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-11-03 04:00 | 2022-12-05 | 2023-06-28 | 66% | 2023-08-18 08:00 | 2026-06-11 13:56 | 2026-12-08 13:56
678793 | FAASt [Mayagüez Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-11-03 04:00 | 2023-01-09 | 2023-06-27 | 55% | 2023-06-26 08:00 | 2027-04-07 14:36 | 2027-10-04 14:36
679039 | FAASt [Caguas Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-07-05 04:00 | 2022-10-31 | 2023-03-30 | 47% | 2023-05-05 08:00 | 2027-02-23 14:36 | 2027-08-22 14:36
679780 | FAASt [Bayamón Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-11-03 04:00 | 2023-01-17 | 2023-08-28 | 78% | 2023-10-16 08:00 | 2027-02-02 14:20 | 2027-08-01 14:20
690545 | FAASt [Aguadilla Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-05-17 04:00 | 2022-12-13 | 2023-03-13 | 48% | 2023-05-02 08:00 | 2027-02-23 14:32 | 2027-08-22 14:32
691702 | FAASt [Trujillo Alto Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-05-17 04:00 | 2022-12-12 | 2023-03-13 | 45% | 2023-04-25 08:00 | 2027-12-17 17:00 | 2028-06-14 17:00
698424 | FAASt [Florida Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-10-23 04:00 | 2023-01-09 | 2023-03-31 | 75% | 2023-04-05 08:00 | 2027-12-18 22:17 | 2028-06-15 22:17
698439 | FAASt [Las Marias Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-11-03 04:00 | 2023-02-02 | 2023-06-27 | 53% | 2023-05-31 08:00 | 2027-12-18 13:01 | 2028-06-15 13:01
698458 | FAASt [Guaynabo Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-11-03 04:00 | 2023-01-16 | 2023-06-27 | 76% | 2023-06-26 08:00 | 2026-06-11 11:00 | 2026-12-08 11:00
698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-04-12 04:00 | 2023-04-24 | 2023-12-01 | 83% | 2024-06-18 08:00 | 2026-06-11 08:08 | 2026-12-08 08:08
698570 | FAASt [Corozal Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-12-29 04:00 | 2023-02-02 | 2023-08-28 | 83% | 2023-09-13 08:00 | 2026-06-11 11:00 | 2026-12-08 11:00
698579 | FAASt [Orocovis Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-03-22 04:00 | 2023-03-08 | 2023-12-01 | 57% | 2024-04-16 08:00 | 2027-02-23 11:28 | 2027-08-22 11:28
701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-05-10 04:00 | 2023-05-15 | 2024-02-28 | 83% | 2024-12-11 08:00 | 2026-11-12 13:36 | 2027-05-11 13:36
703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-06-18 04:00 | 2023-05-02 | 2023-11-03 | 55% | 2024-02-05 08:00 | 2027-01-25 13:44 | 2027-07-24 13:44
704679 | FAASt [Coamo Streetlighting] (Distribution) | Distribution – Streetlighting | 2023-11-03 04:00 | 2023-02-03 | 2023-06-27 | 69% | 2023-08-29 08:00 | 2027-02-07 03:23 | 2027-08-06 03:23
704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-05-10 04:00 | 2023-06-15 | 2023-12-27 | 67% | 2024-06-13 08:00 | 2027-05-04 17:00 | 2027-10-31 17:00
704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-07-08 04:00 | 2023-05-15 | 2023-12-27 | 68% | 2024-02-05 08:00 | 2027-04-07 17:00 | 2027-10-04 17:00
704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-05-31 04:00 | 2023-05-15 | 2024-01-19 | 65% | 2024-03-19 08:00 | 2027-06-15 13:24 | 2027-12-12 13:24
704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-07-08 04:00 | 2023-05-15 | 2024-01-19 | 90% | 2024-12-06 08:00 | 2027-02-02 17:00 | 2027-08-01 17:00
704938 | FAASt [Las Piedras Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-04-12 04:00 | 2023-05-15 | 2023-12-01 | 70% | 2024-02-28 08:00 | 2027-02-07 19:23 | 2027-08-06 19:23
704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-04-12 04:00 | 2023-04-19 | 2023-12-27 | 64% | 2024-02-01 08:00 | 2027-10-08 17:00 | 2028-04-05 17:00
709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-03-22 04:00 | 2023-05-15 | 2023-12-01 | 80% | 2024-02-19 08:00 | 2027-03-22 08:12 | 2027-09-18 08:12
724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-05-31 04:00 | 2023-07-24 | 2024-02-28 | 73% | 2024-10-31 08:00 | 2027-02-02 11:16 | 2027-08-01 11:16
724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-07-08 04:00 | 2023-08-01 | 2024-02-28 | 79% | 2024-11-27 08:00 | 2027-04-08 11:24 | 2027-10-05 11:24
724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-06-18 04:00 | 2023-08-25 | 2024-02-28 | 79% | 2024-11-20 08:00 | 2027-02-07 05:23 | 2027-08-06 05:23
724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-06-18 04:00 | 2023-08-24 | 2023-12-28 | 60% | 2024-08-29 08:00 | 2026-11-30 17:00 | 2027-05-29 17:00
724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-05-10 04:00 | 2023-07-27 | 2024-02-28 | 66% | 2024-12-06 08:00 | 2027-03-21 13:27 | 2027-09-17 13:27
724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution – Streetlighting | 2024-05-10 04:00 | 2023-07-19 | 2024-01-19 | 59% | 2024-03-01 08:00 | 2027-04-25 21:35 | 2027-10-22 21:35
755211 | FAASt [Automation Program Group 15] (Distribution) | Grid Automation | 2025-02-06 04:00 | 2024-09-05 17:00 | 2024-09-05 17:00 | 72% | 2025-03-16 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757699 | FAASt [Automation Program Group 34] (Distribution) | Grid Automation | 2025-11-05 | 2024-03-14 | 2025-08-29 | 4% | 2026-01-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757700 | FAASt [Automation Program Group 35] (Distribution) | Grid Automation | 2025-09-17 04:00 | 2025-05-08 17:00 | 2025-05-08 17:00 | 8% | 2025-11-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
745856 | FAASt [Automation Program Group 14] (Distribution) | Grid Automation | 2025-02-06 04:00 | 2024-06-26 17:00 | 2024-06-26 17:00 | 92% | 2025-03-12 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
745859 | FAASt [Automation Program Group 18] (Distribution) | Grid Automation | 2024-09-18 04:00 | 2024-01-11 | 2024-05-10 | 72% | 2024-09-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
745861 | FAASt [Automation Program Group 12] (Distribution) | Grid Automation | 2025-02-06 04:00 | 2024-12-26 17:00 | 2024-12-26 17:00 | 76% | 2025-03-12 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
752808 | FAASt [Automation Program Group 19] (Distribution) | Grid Automation | 2025-02-06 04:00 | 2024-11-07 17:00 | 2024-11-07 17:00 | 85% | 2025-03-17 17:00 | 2026-06-30 17:00 | 2026-12-27 17:00
752810 | FAASt [Automation Program Group 20] (Distribution) | Grid Automation | 2025-02-06 04:00 | 2025-12-22 17:00 | 2025-12-22 17:00 | 77% | 2025-03-12 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757662 | FAASt [Automation Program Group 21] (Distribution) | Grid Automation | 2025-10-30 | 2024-02-15 | 2025-06-19 | 8% | 2026-01-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757687 | FAASt [Automation Program Group 22] (Distribution) | Grid Automation | 2025-10-30 | 2024-02-22 | 2026-01-23 | 6% | 2026-01-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757689 | FAASt [Automation Program Group 24] (Distribution) | Grid Automation | 2025-09-17 04:00 | 2025-12-11 17:00 | 2025-12-11 17:00 | 34% | 2025-11-30 00:43 | 2026-06-12 17:00 | 2026-12-09 17:00
757692 | FAASt [Automation Program Group 26] (Distribution) | Grid Automation | 2025-09-03 04:00 | 2024-08-29 17:00 | 2024-08-29 17:00 | 43% | 2025-09-08 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757694 | FAASt [Automation Program Group 27] (Distribution) | Grid Automation | 2025-09-25 04:00 | 2024-12-26 17:00 | 2024-12-26 17:00 | 15% | 2025-11-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757696 | FAASt [Automation Program Group 31] (Distribution) | Grid Automation | 2025-09-17 04:00 | 2024-04-26 17:00 | 2024-04-26 17:00 | 19% | 2025-11-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757697 | FAASt [Automation Program Group 32] (Distribution) | Grid Automation | 2025-09-25 04:00 | 2025-01-30 17:00 | 2025-01-30 17:00 | 17% | 2025-11-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
757698 | FAASt [Automation Program Group 33] (Distribution) | Grid Automation | 2025-09-25 04:00 | 2025-05-15 17:00 | 2025-05-15 17:00 | 9% | 2025-11-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
800286 | FAASt [Automation Program Group 36] (Distribution) | Grid Automation | 2025-09-17 04:00 | 2025-04-15 17:00 | 2025-04-15 17:00 | 17% | 2025-11-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
800361 | FAASt [Automation Program Group 37] (Distribution) | Grid Automation | 2025-09-17 04:00 | 2024-11-21 17:00 | 2024-11-21 17:00 | 31% | 2025-11-30 08:00 | 2026-06-30 17:00 | 2026-12-27 17:00
165268 | FAASt Rio Grande Estate Substation CH-2306 (Substation) | Substation | 2022-12-21 04:00 | 2022-02-04 | 2023-12-20 | 93% | 2023-09-07 | 2028-06-30 | 2028-12-27
174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | 2022-05-18 04:00 | 2021-07-16 | 2026-07-01 | 66% | 2023-09-05 | 2027-03-05 | 2027-09-01
682645 | FAASt [Maunabo TC] (Substation) | Substation | 2025-09-17 04:00 | 2024-12-09 | 2025-11-14 | 28% | 2024-04-15 | 2026-08-11 17:00 | 2027-02-07 17:00
169500 | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | Substation | 2023-06-16 04:00 | 2022-03-22 | 2024-09-12 | 42% | 2024-10-07 08:00 | 2027-06-08 17:00 | 2027-12-05 17:00
179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | 2022-05-26 04:00 | 2021-12-10 | 2022-11-14 | 100% | 2022-11-15 08:00 | 2022-12-12 17:00 | 2026-02-03
682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Substation | 2024-02-13 04:00 | 2023-05-30 | 2027-06-21 | 1% | 2025-04-25 08:00 | 2030-09-27 17:00 | 2031-03-26 17:00
743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | 2024-08-26 04:00 | 2024-11-20 | 2026-02-09 | 10% | 2025-01-18 08:00 | 2028-07-09 17:00 | 2029-01-05 17:00
729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | 2024-07-08 04:00 | 2023-05-11 | 2026-02-02 | 52% | 2024-07-15 08:00 | 2027-05-29 17:00 | 2027-11-25 17:00
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | 2022-06-10 04:00 | 2021-09-16 | 2028-04-28 | 44% | 2024-09-30 | 2031-03-20 | 2031-09-16
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | 2022-06-10 04:00 | 2021-12-01 | 2026-10-02 | 2% | 2024-09-30 | 2029-08-16 17:00 | 2030-02-12 17:00
178503 | FAASt [Aguirre TC - BKRS] (Substations) | Substation | 2022-12-27 04:00 | 2021-12-21 | 2023-11-02 | 33% | 2023-05-03 08:00 | 2031-04-30 | 2031-10-27
546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | 2023-08-22 04:00 | 2022-02-07 | 2025-05-30 | 76% | 2024-06-03 08:00 | 2027-06-30 17:00 | 2027-12-27 17:00
660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | 2023-12-29 04:00 | 2023-08-14 | 2025-05-30 | 39% | 2025-07-28 08:00 | 2027-06-30 17:00 | 2027-12-27 17:00
684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | 2023-12-29 04:00 | 2023-04-22 | 2023-04-22 | 95% | 2023-04-23 08:00 | 2026-12-15 08:07 | 2027-06-13 08:07
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | 2025-09-17 04:00 | 2025-03-19 | 2025-07-02 | 0% | 2026-07-07 08:00 | 2026-10-22 17:00 | 2027-04-20 17:00
169266 | FAASt Centro Medico 1327/1359 Equipment Repair & Replacement (Substation) | Substation | 2023-11-03 04:00 | 2022-05-04 | 2026-07-23 | 3% | 2024-09-30 08:00 | 2027-08-26 17:00 | 2028-02-22 17:00
169896 | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | Substation | 2022-08-02 04:00 | 2022-02-11 | 2023-10-12 | 43% | 2024-04-08 08:00 | 2027-05-05 17:00 | 2027-11-01 17:00
178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | 2025-02-06 04:00 | 2022-03-10 | 2026-04-28 | 0% | 2026-10-30 08:00 | 2028-03-03 08:00 | 2028-08-30 08:00
546370 | FAASt - Substation Minor Repairs Group A (Substation) | Substation | 2024-02-13 04:00 | 2022-02-07 | 2025-05-30 | 70% | 2024-04-17 08:00 | 2027-04-13 17:00 | 2027-10-10 17:00
549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | 2024-05-10 04:00 | 2022-12-06 | 2025-05-30 | 55% | 2025-04-07 08:00 | 2026-12-29 17:00 | 2027-06-27 17:00
169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | Substation | 2023-08-22 04:00 | 2021-10-20 | 2026-10-13 | 8% | 2025-02-15 08:00 | 2028-09-18 17:00 | 2029-03-17 17:00
550910 | FAASt [Physical Security - Group 1] (Substation) | Substation | 2023-05-04 04:00 | 2022-02-07 | 2025-05-30 | 81% | 2023-05-08 08:00 | 2027-06-30 | 2027-12-27
542758 | FAASt [Minor Repairs -Group B] (Substation) | Substation | 2023-07-07 04:00 | 2022-02-07 | 2025-05-30 | 76% | 2023-11-06 08:00 | 2027-09-03 17:00 | 2028-03-01 17:00
551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | 2023-06-16 04:00 | 2022-03-01 | 2025-05-30 | 48% | 2024-09-03 08:00 | 2027-06-30 | 2027-12-27
549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | 2024-04-12 04:00 | 2022-12-05 | 2025-05-30 | 33% | 2025-06-18 08:00 | 2026-08-28 17:00 | 2027-02-24 17:00
549764 | FAASt [Physical Security - Group 2] (Substation) | Substation | 2023-06-16 04:00 | 2022-10-31 | 2025-05-30 | 79% | 2025-04-23 08:00 | 2026-06-16 | 2026-12-13
550950 | FAASt - EPC - [Monacillo TC] (Substations) | Substation | 2023-12-19 04:00 | 2023-05-08 | 2026-12-04 | 11% | 2024-12-14 08:00 | 2029-04-24 17:00 | 2029-10-21 17:00
682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | 2024-03-22 04:00 | 2023-12-11 | 2027-08-24 | 4% | 2025-11-26 17:00 | 2033-02-09 17:00 | 2033-08-08 17:00
723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | 2023-12-19 04:00 | 2023-05-18 | 2026-11-13 | 2% | 2024-11-14 08:00 | 2029-10-16 17:00 | 2030-04-14 17:00
723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | 2023-12-19 04:00 | 2023-08-24 | 2027-02-26 | 10% | 2023-04-09 08:00 | 2029-09-05 17:00 | 2030-03-04 17:00
825843 | FAAST [Guanica Transformer Replacement] (Substation) | Substation | 2025-09-22 04:00 | 2025-02-10 | 2025-07-30 | 8% | 2025-09-01 08:00 | 2026-07-06 11:31 | 2027-01-02 11:31
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | 2025-09-22 04:00 | 2025-04-09 | 2025-12-12 | 10% | 2025-04-15 08:00 | 2026-05-13 17:00 | 2026-11-09 17:00
657300 | FAASt [ENERGY MANAGEMENT SYSTEM (EMS)] (Telecommunication) | Telecommunications | 2022-10-17 04:00 | 2023-09-15 | 2024-08-22 | 65% | 2023-10-16 08:00 | 2026-03-19 17:00 | 2026-09-15 17:00
714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Telecommunications | 2023-12-08 04:00 | 2024-01-01 | 2025-03-01 | 2% | 2025-03-25 | 2028-12-31 | 2029-06-29
551963 | FAASt [Transport Network] (Telecommunication) | Telecommunications | 2025-09-17 04:00 | 2024-04-26 | 2026-07-01 | 0% | 2026-02-26 08:00 | 2029-05-04 17:00 | 2029-10-31 17:00
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Telecommunications | 2025-10-30 | 2025-09-15 | 2026-07-22 | 0% | 2027-04-12 17:00 | 2027-09-09 17:00 | 2028-03-07 17:00
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Telecommunications | 2025-11-05 | 2025-09-15 | 2026-07-22 | 0% | 2027-01-12 17:00 | 2027-11-09 17:00 | 2028-05-07 17:00
551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Telecommunications | 2024-11-01 04:00 | 2022-07-18 | 2025-07-24 | 90% | 2024-12-02 08:00 | 2026-05-29 17:00 | 2026-11-25 17:00
167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos TC (Transmission) | Transmission | 2025-11-05 | 2021-10-13 | 2026-05-06 | 0% | 2026-09-10 | 2027-06-21 | 2027-12-18
168226 | FAASt San Juan 115kV Underground Transmission Loop (Transmission) | Transmission | 2022-12-21 04:00 | 2022-02-24 17:00 | 2027-04-12 17:00 | 0% | 2030-02-28 08:00 | 2030-11-04 17:00 | 2031-05-03 17:00
176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Transmission | 2025-11-05 | 2021-10-05 | 2026-05-21 | 0% | 2026-07-14 08:38 | 2028-08-11 08:38 | 2029-02-07 08:38
176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Transmission | 2025-11-05 | 2022-07-29 | 2026-05-15 | 0% | 2026-09-14 08:00 | 2027-07-14 17:00 | 2028-01-10 17:00
334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Transmission | 2025-11-05 | 2023-09-01 | 2026-06-17 | 0% | 2026-08-27 08:00 | 2028-08-14 17:00 | 2029-02-10 17:00
753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission – Pole Replacement | 2025-10-30 | 2024-07-09 | 2024-07-09 | 0% | 2026-04-23 08:00 | 2026-06-10 17:00 | 2026-12-07 17:00
180052 | FAASt Ponce TC to Jobos TC - 38kV 100 & 200 (Transmission) | Transmission | 2025-11-05 | 2022-06-13 | 2027-01-11 | 0% | 2027-06-10 | 2030-02-06 | 2030-08-05
750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission – Pole Replacement | 2026-01-16 | 2021-06-01 | 2021-07-12 | 0% | 2026-05-11 | 2026-07-10 | 2027-01-06
334468 | FAASt [Transmission Priority Pole Replacements – Line 2200] (Transmission) | Transmission – Pole Replacement | 2022-07-13 04:00 | 2022-04-20 | 2023-07-19 | 93% | 2023-11-20 08:00 | 2026-03-30 | 2026-09-26
550896 | FAASt [Transmission Priority Pole Replacements – Line 6700] (Transmission) | Transmission – Pole Replacement | 2022-08-08 04:00 | 2022-12-15 | 2023-06-21 | 90% | 2023-10-02 08:00 | 2026-03-30 | 2026-09-26
668583 | FAASt [Transmission Priority Pole Replacements – Line 13300] (Transmission) | Transmission – Pole Replacement | 2022-08-02 04:00 | 2022-04-07 | 2023-06-28 | 91% | 2023-11-02 08:00 | 2026-03-30 | 2026-09-26
668592 | FAASt [Transmission Priority Pole Replacement – Line 9800] (Transmission) | Transmission – Pole Replacement | 2022-09-16 04:00 | 2022-04-07 | 2023-06-28 | 94% | 2023-10-02 08:00 | 2026-03-30 | 2026-09-26
681672 | FAASt Transmission Priority Pole Replacements –38kV Line 2300 (Transmission) | Transmission – Pole Replacement | 2023-01-31 04:00 | 2022-08-18 | 2024-03-06 | 90% | 2024-04-02 08:00 | 2026-03-30 | 2026-09-26
708637 | FAASt [T-Pole Program Line 3700] (Transmission) | Transmission – Pole Replacement | 2024-08-26 04:00 | 2023-05-02 | 2023-08-15 | 90% | 2024-10-03 | 2026-03-30 | 2026-09-26
711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission – Pole Replacement | 2024-06-18 04:00 | 2023-04-04 | 2023-11-06 | 93% | 2024-07-17 | 2026-03-30 | 2026-09-26
712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission – Pole Replacement | 2024-11-01 04:00 | 2023-06-05 | 2024-03-19 | 77% | 2024-11-19 08:00 | 2027-11-15 17:00 | 2028-05-13 17:00
749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission – Pole Replacement | 2025-11-05 | 2024-05-31 | 2024-07-11 | 0% | 2026-04-01 | 2026-05-05 | 2026-11-01
750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission – Pole Replacement | 2025-11-05 | 2024-02-15 | 2024-09-06 | 0% | 2026-04-01 | 2026-05-05 | 2026-11-01
750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission – Pole Replacement | 2025-11-05 | 2024-03-05 | 2025-02-18 | 0% | 2026-04-01 | 2026-05-05 | 2026-11-01
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | 2024-06-05 04:00 | 2023-09-15 | 2029-06-30 | 11% | 2024-06-17 | 2028-04-18 17:00 | 2028-10-15 17:00
727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Vegetation | 2025-04-28 04:00 | 2025-01-10 | 2025-09-23 | 70% | 2025-05-05 08:00 | 2028-06-06 17:00 | 2028-12-03 17:00
728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Vegetation | 2025-04-28 04:00 | 2025-01-27 | 2025-12-26 | 81% | 2025-05-14 08:00 | 2026-07-28 17:00 | 2027-01-24 17:00
728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Vegetation | 2025-04-28 04:00 | 2025-05-01 | 2025-09-30 | 45% | 2025-05-19 17:00 | 2026-09-30 17:00 | 2027-03-29 17:00
727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Vegetation | 2025-04-28 04:00 | 2025-03-24 | 2025-12-31 | 57% | 2025-05-27 08:00 | 2026-03-30 17:00 | 2026-09-26 17:00
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | 2025-09-17 04:00 | 2025-11-04 | 2025-12-05 | 55% | 2025-12-09 17:00 | 2027-12-24 17:00 | 2028-06-21 17:00
956353 | FAASt [Arecibo Region 2 Transmission Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | 2025-09-17 04:00 | 2025-09-18 | 2026-04-03 | 0% | 2026-04-13 | 2028-06-15 | 2028-12-12
742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2024-06-18 04:00 | 2023-10-25 | 2023-11-30 17:00 | 85% | 2024-07-05 17:00 | 2027-06-30 | 2027-12-27
750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution – Pole Replacement | 2025-09-25 04:00 | 2024-05-31 17:00 | 2024-05-31 08:00 | 14% | 2025-11-19 17:00 | 2027-07-30 | 2028-01-26
752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Distribution – Pole Replacement | 2025-09-25 04:00 | 2024-07-31 17:00 | 2024-07-31 08:00 | 0% | 2026-03-02 08:00 | 2027-07-30 | 2028-01-26
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution – Pole Replacement | 2025-09-03 04:00 | 2024-10-01 17:00 | 2024-10-01 08:00 | 50% | 2026-01-15 08:00 | 2026-12-30 | 2027-06-28
165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution – Feeder Rebuild | Priority List | 2021-10-14 | 2026-03-06 | Not obligated | 2027-01-11 | 2029-05-29 | 2029-11-25
714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution – Streetlighting | Priority List | 2023-04-20 | 2023-11-03 | Not obligated | 2026-04-30 | 2026-12-29 | 2027-06-27
746309 | FAASt [Automation Program Group 30] (Distribution) | Grid Automation | Priority List | 2024-11-11 | 2024-11-11 | Not obligated | 2026-05-30 | 2026-08-04 | 2027-01-31
751655 | FAASt [Vieques Microgrid] (Transmission) | Grid Modernization | Priority List | 2026-04-14 | 2029-07-09 | Not obligated | 2029-07-10 | 2032-02-09 | 2032-08-07
751656 | FAASt [Culebra Microgrid] (Transmission) | Grid Modernization | Priority List | 2024-02-15 | 2029-07-09 | Not obligated | 2029-07-11 | 2032-02-09 | 2032-08-07
547187 | FAASt - [Substation Component Replacement Program] (Substation) | Substation | Priority List | 2024-09-06 | 2027-01-11 | Not obligated | 2027-01-12 | 2027-08-05 | 2028-02-01
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Priority List | 2024-04-18 | 2027-02-01 | Not obligated | 2026-08-03 | 2028-04-10 | 2028-10-07
723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Priority List | 2023-06-29 | 2027-08-27 | Not obligated | 2027-08-27 | 2030-06-26 | 2030-12-23
169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Substation | Priority List | 2021-10-26 | 2027-09-20 | Not obligated | 2027-12-08 | 2028-12-15 | 2029-06-13
178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Priority List | 2023-01-13 | 2027-02-12 | Not obligated | 2027-12-27 | 2029-01-16 | 2029-07-15
169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Priority List | 2022-02-02 | 2027-11-26 | Not obligated | 2026-05-29 | 2029-03-16 | 2029-09-12
550106 | FAASt [Conquistador CH] (Substation) | Substation | Priority List | 2022-10-21 | 2026-06-01 | Not obligated | 2023-02-08 | 2028-05-04 | 2028-10-31
551914 | FAASt [Caparra 1912 & 1924] (Substation) | Substation | Priority List | 2023-04-20 | 2026-05-19 | Not obligated | 2027-02-04 | 4/12/2027 | 2027-10-09
682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Priority List | 2024-04-18 | 2027-06-01 | Not obligated | 2024-10-07 | 2027-06-09 | 2027-12-06
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Telecommunications | Priority List | 2023-09-18 | 2026-10-01 | Not obligated | 2026-04-07 | 2026-12-11 | 2027-06-09
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Telecommunications | Priority List | 2023-04-28 | 2026-12-02 | Not obligated | 2026-06-03 | 2029-12-11 | 2030-06-09
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Telecommunications | Priority List | 2022-11-02 | 2025-02-27 | Not obligated | 2027-03-30 | 2028-10-16 | 2029-04-14
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Priority List | 2026-02-28 | 2026-10-22 | Not obligated | 2027-11-01 | 2028-04-28 | 2028-10-25
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Priority List | 2023-02-28 | 2027-06-17 | Not obligated | 2027-12-08 | 2028-01-12 | 2028-07-10
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Transmission | Priority List | 2021-10-21 | 2027-02-01 | Not obligated | 2027-02-01 | 2029-11-02 | 2030-05-01
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Priority List | 2024-09-16 | 2027-02-26 | Not obligated | 2027-11-05 | 2029-12-06 | 2030-06-04
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Priority List | 2023-07-03 | 2026-07-28 | Not obligated | 2026-12-28 | 2028-02-23 | 2028-08-21
711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Transmission – Pole Replacement | Priority List | 2023-06-05 | 2023-11-24 | Not obligated | 2026-07-30 | 2028-01-28 | 2028-07-26
749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission – Pole Replacement | Priority List | 2023-05-15 | 2023-06-23 | Not obligated | 2026-07-30 | 2026-08-21 | 2027-02-17
956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-10-02 | Not obligated | 2026-06-30 | 2026-10-23 | 2027-04-21
956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2027-01-15 | Not obligated | 2026-06-30 | 2027-07-30 | 2028-01-26
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-06-05 | Not obligated | 2026-06-30 | 2027-10-14 | 2028-04-11
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Vegetation | Priority List | 2026-04-30 | 2026-10-02 | Not obligated | 2026-06-30 | 2027-04-13 | 2027-10-10
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Priority List | 2026-04-01 | 2026-12-23 | Not obligated | 2026-06-30 | 2027-02-01 | 2027-07-31
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Priority List | 2026-04-01 | 2026-11-30 | Not obligated | 2026-06-30 | 2027-04-13 | 2027-10-10
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Priority List | 2026-04-01 | 2027-03-03 | Not obligated | 2026-06-30 | 2027-05-18 | 2027-11-14
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Priority List | 2026-04-01 | 2026-12-08 | Not obligated | 2026-06-30 | 2027-01-12 | 2027-07-11
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Priority List | 2026-04-01 | 2026-07-28 | Not obligated | 2026-06-30 | 2027-03-04 | 2027-08-31
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Priority List | 2026-04-08 | 2026-06-25 | Not obligated | 2026-06-30 | 2027-03-16 | 2027-09-12
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-05-18 | Not obligated | 2026-06-30 | 2027-06-16 | 2027-12-13
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Priority List | 2026-04-28 | 2027-01-11 | Not obligated | 2026-06-30 | 2027-06-25 | 2027-12-22
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-06-12 | Not obligated | 2026-06-30 | 2027-04-28 | 2027-10-25
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Priority List | 2026-05-06 | 2026-05-20 | Not obligated | 2026-06-30 | 2027-02-18 | 2027-08-17
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-05-18 | Not obligated | 2026-06-30 | 2027-06-16 | 2027-12-13
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Vegetation | Priority List | 2026-04-28 | 2026-11-06 | Not obligated | 2026-06-30 | 2026-10-08 | 2027-04-06
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-11-30 | Not obligated | 2026-06-30 | 2026-12-11 | 2027-06-09
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-09-14 | Not obligated | 2026-06-30 | 2027-03-19 | 2027-09-15
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-11-27 | Not obligated | 2026-06-30 | 2027-06-10 | 2027-12-07
956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-06-22 | Not obligated | 2026-06-30 | 2027-09-24 | 2028-03-22
956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-06-10 | Not obligated | 2026-06-30 | 2028-01-06 | 2028-07-04
956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Vegetation | Priority List | 2026-04-28 | 2026-07-06 | Not obligated | 2026-06-30 | 2027-04-29 | 2027-10-26
956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-05-28 | Not obligated | 2026-06-30 | 2027-08-05 | 2028-02-01
956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Vegetation | Priority List | 2026-05-01 | 2026-05-15 | Not obligated | 2026-06-30 | 2028-02-03 | 2028-08-01
956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Vegetation | Priority List | 2026-04-28 | 2026-07-07 | Not obligated | 2026-06-30 | 2027-01-26 | 2027-07-25
1064452 | FAASt [Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] / Former project 753781(Transmission) | Transmission – Pole Replacement | Reactivated Project | 2025-02-28 | 2027-11-15 | Not obligated | 2027-11-16 | 2027-12-31 | 2028-06-28
Construction start and end dates for projects that are not obligated are contingent on timely obligation.
Closeout phase dates are generally considered to be subject to change as they are highly dependent on construction end and processes to reconcile finances.
Projects with third party attachment items are pending resolution which affect construction end as well as closeout dates.
For Vegetation, Distribution Pole and Streetlight assets, design phase refers to assessments
For Vegetation projects, timeline of obligations and crew availability will impact execution duration. Design start is based on a presumed obligation date.
235 withdrawn projects have been excluded from this list as they were deactivated in Grants Portal at PREPA's request.
All data in this sheet is as of February 28, 2026 with the exception of construction percentages which reflect the most recent submitted report to FEMA (January 30, 2026)

## PREB Reactivated List
FEMA Project # | Title | Asset
740662 | FAASt [Automation Program Group 2] (TL/ Distribution) | Grid Automation
741678 | FAASt [Automation Program Group 4] (TL/Distribution) | Grid Automation
705657 | FAASt [Automation Program Group 3] (TL/Distribution) | Grid Automation
666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution – Streetlighting
730657 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | Transmission
704793 | FAASt [Yauco Streetlighting] (Distribution) | Distribution – Streetlighting
704744 | FAASt [San Sebastian Streetlighting] (Distribution) | Distribution – Streetlighting
678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution – Streetlighting
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission
690483 | FAASt [Cayey Streetlighting] (Distribution) | Distribution – Streetlighting
685869 | FAASt [Mayagüez TC] (Substation) | Substation
764707 | FAASt [Feeder Rebuild # 6012-02] (Distribution) | Distribution – Feeder Rebuild
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution – Streetlighting
704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution – Streetlighting
764705 | FAASt [Feeder Rebuild # 6014-02] (Distribution) | Distribution – Feeder Rebuild
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution – Streetlighting
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution – Streetlighting
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution – Streetlighting
671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution – Streetlighting
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Grid Automation
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution – Streetlighting
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution – Streetlighting
693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution – Streetlighting
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution – Streetlighting
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution – Streetlighting
704929 | FAASt [San Lorenzo Streetlighting] (Distribution) | Distribution – Streetlighting
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution – Streetlighting
690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution – Streetlighting
724828 | FAASt [Loiza Streetlighting] (Distribution) | Distribution – Streetlighting
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution – Streetlighting
698522 | FAASt [Vieques Streetlighting] (Distribution) | Distribution – Streetlighting
690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution – Streetlighting
686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution – Streetlighting
693615 | FAASt [Rio Grande Streetlighting] (Distribution) | Distribution – Streetlighting
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Grid Modernization
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Grid Modernization
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Grid Modernization
754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | Distribution – Feeder Rebuild
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Grid Modernization
754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | Distribution – Feeder Rebuild
698427 | FAASt [Maricao Streetlighting] (Distribution) | Distribution – Streetlighting
724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) | Distribution – Streetlighting
748180 | FAASt [Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC)] (Telecommunication) | Telecommunications
704741 | FAASt [Moca Streetlighting] (Distribution) | Distribution – Streetlighting
724605 | FAASt [Guayanilla Streetlighting] (Distribution) | Distribution – Streetlighting
724599 | FAASt [Sabana Grande Streetlighting] (Distribution) | Distribution – Streetlighting
752277 | FAASt [Substation Ciales 8701] (Substation) | Substation
724669 | FAASt [Ciales Streetlighting] (Distribution) | Distribution – Streetlighting
724716 | FAASt [Quebradillas Streetlighting] (Distribution) | Distribution – Streetlighting
713795 | FAASt [Lares Streetlighting] (Distribution) | Distribution – Streetlighting
724670 | FAASt [Patillas Streetlighting] (Distribution) | Distribution – Streetlighting
724781 | FAASt [Penuelas Streetlighting] (Distribution) | Distribution – Streetlighting
727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) | Vegetation
740406 | FAASt [Region 1-San Juan Group B] (Vegetation) | Vegetation
741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | Vegetation
741098 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | Vegetation
740410 | FAASt [Region 2-Arecibo Group B] (Vegetation) | Vegetation
740409 | FAASt [Region 4-Caguas Group B] (Vegetation) | Vegetation
727530 | FAASt [Region 6 -Ponce Group C] (Vegetation) | Vegetation
741102 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | Vegetation
727694 | FAASt [Region 4 -Caguas Group C] (Vegetation) | Vegetation
741101 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | Vegetation
740411 | FAASt [Region 5-Mayaguez Group B] (Vegetation) | Vegetation
727562 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | Vegetation
741104 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | Vegetation
727540 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | Vegetation
740408 | FAASt [Region 3-Bayamon Group B] (Vegetation) | Vegetation
741100 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | Vegetation
727558 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | Vegetation
740414 | FAASt [Region 6-Ponce Group B] High Density (Vegetation) | Vegetation