## Summary
Summary Construction Management
| February | 11387.25
| March | 78784.69
| April | 93481
| May | 116387.25
| June | 91378
| July | 16172
| CDM | 142035
| Total | 549625.19 | Actual
Demolition Cost
| Feb - Jul | 949600 | Actual
Geophysical (CAPTAs Invoice)
|  | 18350 | Actual
Community Engagement (Paola Arroyo)
Feb
Mar
| April | 2710.5
| May | 2432.5
| June | 6324.5
| July | 3162.25
| Total | 14629.75 | Actual
Actual |  | 1532204.94
Estimated |  | 2580944
| Percentage | 59.37%

## Feb
Entry Date | Client | Proj level1 | Proj level2 | Proj level3 | Client title | Asset | Task | Task Group | Task Description | Hours | Activity Rate | Activity Extended | Line Billable | Invoice Number | Narrative
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 970 | 970 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - Airline tickets to San Juan from Birmingham for jack darnall. 2 1/2 days of meetings
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 317.49 | 317.49 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - hotel for meetings in San Juan on genera. Planing, staffing, and organizational meetings $317.49 billable. Deleted $80 Did not include items charged to the room
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 317.49 | 317.49 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - Hotel for 2 days of meetings in San Juan for Genera project. General planning, staffing meetings, organizational meetings $317.49 billable, $80 non billable
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PMO Team coordination call to review staffing needs and current hiring status. Schedule review and new/open program needs. Meeting also attended by: Barry Scanlon (DCMC), Mark Merritt (DCMC), AJ Holton Williams (DCMC), Frances Vallejo (DCMC), Mike Merritt, (DCMC), Jack Darnall (DCMC), Foster Veazey (DCMC) and Lauren Wells (DCMC).
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore training schedule with comments to send to Nesty Delgado (Team 1144) for consulting.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating agenda and topic items to discuss during Procore Update meeting with Franklyn Colmenares (CSA) and others. Made some Procore permission adjustments.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training items. Documenting how long each on-line training session is so that we can incorporate it into our training session next week.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding new users to Procore for the Siemens Energy.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Nesty Delgado (Team 1144) to discuss Procore training consulting.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -Procore Project Weekly Discussion catch up with Franklyn Colmenares (CSA), Rafael Pabon (CDM Smith), Monica Ybarra (S&L), Ivette Miranda (S&L) to discuss Procore items and updates for the projects for Procore.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on documenting Procore task items to keep pipeline of work and items aligned with overall goals and deliver items on time.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Barry Scanlon (DCMC), Larry Hipsh (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Call with Rafael Pabon (CDM Smith) to summarize Document control path from previous meeting and next steps internally.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Genera/Siemens Document Control + Procore. In attendance was Rafael Pabon (CDM Smith), Jim Matlock (Siemens), Camilla Andersson (Siemens), Monica Ybarra (S&L), Ivette Rios (S&L)
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR 4339. Teams call with Mark Merritt, Mike Merritt, Barry Scanlon, Foster Veazey, Lauren Wells, Jack Darnell, Frances Vallejo, Larry Hipsh. Discussed update on project, job offers, trailers at sites, update on PROCORE training, potential other partners for PROCORE locally, safety KOM yesterday, safety manual update, status of scheduler, logistics and other interviews.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -Worked on Procore items for Financial follow ups from meeting. Sent out cost information to Procore (Tyler Scanlon) for building out concept map and setup meeting invite for our next call.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Procore WBS Financial Updates with Tyler Scanlon (Procore) and Lauren Kennedy (Procore).
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for defining Submittal Types for Procore.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configuration task sheet to review with Liz Fronduto (Procore).
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore financials to prepare for Procore Fin meeting with Tyler Scanlon (Procore).
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)Worked on correspondences for Procore items.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore project planner.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on updating Procore training tracker.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondences for Procore Tesla documentation help.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore settings to align correct address and other settings with Procore support.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items for questions about the system.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training materials for overall 6 month outlook.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore weekly update sheet to be used in Monday's update calls. Marc Maceria (DCMC) reports off this sheet in the calls.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP Master documentation document. This covers general setup and settings along with each tool set.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for setting up Procore meetings to discuss document control.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore permission review for Franklyn Colmenares (CSA) so that they can better understand the levels of permissions.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore financial buildout in the system. Continued work on setting up and adding in Catz so that we can see how Procore handles it.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore Permissions adjustments for Nelson Soler (CDM Smith) and correspondence for potential candidates for hire.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating the Procore Training Tracker.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore home page configurations so that when roles are entered they show on the home page. Also adjusted settings to show RFI and Submittal open item status.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding in new roles in Procore. This will help identify roles for each plant site. This will be posted on the home screen of each project.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP documentation to prepare users for how to use the system.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating the Procore configuration tasks list to be reviewed with Liz Fronduto (Procore).
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on running reports in Procore to asses the use of RFI's and Submittals to ensure users are using it correctly.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence and discussion around Procore document control person and scope with Rafael Pabon (CDM Smith) with scheduling meeting with Siemens and S&L.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating SOP document around Documents tool in Procore to prepare for meeting with Sargent and Lundy and Siemens teams on Friday.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence around Procore training and how we can leverage Team 1144 (Nesty Delgado).
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore weekly update document with recent activity and training tracker counts.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing Procore permission Matrix from Franklyn Colmenares (CSA) for use with Procore users so that project teams understand their roles and permissions.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore project tasks list to ensure all items are followed up with for users.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore General Settings with Procore support team as some adjustments in the system were not letting me make changes.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore user support for permission levels. Nelson Soler (CDM Smith) is unable to see Equipment logs in Daily Logs tool.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore support for Nelson Soler (CDM Smith) on behalf of Carirma Sanchez (Homeca) to enable Daily Log items for her to enter in as a Collaborator.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Barry Scanlon (DCMC), Larry Hipsh (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 225 | 168.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Weekly Peakers meeting to review progress against the program Tracker. Meeting also attended by: Kevin Futch (Genera), Rafael Pabon (CD Smith), Rafael Calderon (DCMC), Jean Pierre Meney (DCMC), Sierra Suleiman (Sargent/Lundy), Fernado O. Melendez (Genera), Miguel Del Valle (Sargent/Lundy), Mike Kuczynski (Sargent/Lundy), Frances Vallejo (DCMC)
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Weekly BESS program update call to review progress on the project tracker. Meeting also attended by: Gabe Perez (CD Smith), Enrique Laya (CD Smith), Mike Kuczynski (Sargent/Lundy), Frances Vallejo (DCMC), Fernado Ortiz (Genera), Carlos Palomares (CD Smith), Jean Pierre Menay (DCMC), Rafael Patron (CD Smith), Miguel Del Valle (Sargent/Lundy), Rafael Calderon (DCMC)
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing DCMC financial "MAP" to understand how we want to map out financials in Procore.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding users to Procore.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence to Gabriel Perez (Genera) to answer questions about Helpdesk tickets for Procore. I provided updates on each one and marked whether they were completed or not.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), and others attended to get project updates for the week.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on SOP documents for Procore Documents Tool.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore training tracker. This is used to track Procore certification completion.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Correspondence emails for Procore weekly update items.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial Mapping
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Franklyn Colmenares (CSA) and Rafael Pabon (CDM Smith) for Procore Items for BESS check-in meeting.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on different correspondences pertaining to information to build out Catz in Procore with Jose Ralat(DCMC).
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on mapping out new Procore financial structure to include all PW's.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Project Coordinator-Franklyn Colemaneras (CSA), Rafael Pabon (CDM Smith) to discuss Procore updates and configurations. Ivette Miranda Rios (Sargent & Lundy) is joining us today to get a Procore update.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up CATz in Procore so that we can use this project to see how Procore runs Financials.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Barry Scanlon (DCMC), Foster Veazy (Lemoine), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on support tickets for Procore. Jefferson Silver (Telsa) needed help with navigation. Also closed out ticket for training certification for Jaime Pesquea (DCMC).
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 225 | 168.75 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR 4339. Teams call with Mark Merritt, Mike Merritt, Barry Scanlon, Foster Veazey, Lauren Wells, Jack Darnell, Frances Vallejo. Discussed update on project, job offers, organization chart based on Genera edits, update on PROCORE.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on whiteboarding new Procore financial project structure based on information received from Jose Ralat (DCMC) and Johanna Diaz (DCMC).
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding Jose Ralat (DCMC) and Johanna Diaz (DCMC) to Procore so that they can take some training to understand the financial capabilities of Procore.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Jose Ralat (DCMC) and Johanna Diaz (DCMC) and Mark Merritt (DCMC) to discuss PW and DI for further scope work in Procore.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating the Procore configuration tasks list to be reviewed with Liz Fronduto (Procore).
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Liz Fronduto (Procore) to discuss implementation status and next steps. Liz is going to contact a Financial SPC to help with overall structure for moving forward.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing documentation that D'Alexzander Gonzalez (DCMC) sent regarding legacy PW's and cost associated with them and how we can work to get all accounting cost into Procore.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on several correspondences for Procore questions.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore training tracker to ensure users are completing their Certification and Marc Maceria (DCMC) can report from it on Monday's call.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on meeting agenda items for project team meeting tomorrow for Procore items. Gathered information for project document folder structure.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on materials for Procore training agenda for when we get someone in place to help with this.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on updating the Procore configuration tasks list to be reviewed with Liz Fronduto (Procore).
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on research for Procore Outlook Add-in. Marc Maceira (DCMC) is asking questions about BIC examples. This is to help cyber approve the use of this add-in.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -On-site Meetings Carlos Negron(Genera), and Joaquin Quinoy (Genera) We discussed Grant approval process challenges and Lean processes to improve and reduce the Approval process and scheduling and communication processes for current projects. All participants were in person at the Genera office.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 2.5 | 225 | 562.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management- DR 4339- On-site Meetings about Genera with Leon Foster (Lemoine), Jennifer Witeczek (Genera), Carlos Negron (Genera), and Joaquin Quinoy (Genera) Mark Merritt (DCMC), and Jack Darnall (Lemoine). We discussed Grant approval process challenges and Lean processes to improve and reduce the Approval process and scheduling and communication processes for current projects. All participants were in person at the Genera office.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1.25 | 225 | 281.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- After meeting follow-up discussion and alignment meeting with Leon Foster (Lemoine) to discuss the next steps and action items. Leon and I were at the Airport.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management- DR 4339- Pre-meeting preparation and alignment with Leon Foster (Lemoine), Mark Merritt (DCMC), and Jack Darnall (Lemoine) Security access into Genera Office and alignment discussion for deliverables and proposal. All participants met in person at the Genera office. We discussed Grant approval process challenges and Lean processes to improve and reduce the Approval process and scheduling and communication processes for current projects. All participants were in person at the Genera office.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management- DR 4339-On site Meetings about Genera with (Genera) Leon Foster(Lemoine), Jennifer Witeczek(Genera), Carlos Negron (Genera), and Joaquin Quinoy (Genera), Mark Merritt (DCMC), Jack Darnall (DCMC). Multiple consecutive breakout group discussions with Genera Leadership for introductions and discussion on the grant approval process. Brief introduction with Maria Sanchez Brief introduction with Jose Del Rio Brief introduction with Jennifer Witecek All participants were in person at the Genera office.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.25 | 225 | 281.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PMO team call to review staffing plan, hiring/offer status, hire date and new requests from owner. Barry Scanlon, Mark Merritt, Mike Merritt, AJ Holton-Williams, Frances Vallejo (DCMC), and Jack Darnall, and Foster Veazey (Lemoine)
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on documenting and processing financial data from the meeting with Jose Ralat (DCMC).I will use this information to restructure a plan for putting this in Procore.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP documentation.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on permissions adjustments for Nelson Soler (CDM Smith) to use equipment function in Daily Logs in Procore.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Jose Ralant (DCMC), Marc Maceria (DCMC), Mark Merritt (DCMC) to discuss PW 10710 and 9510 for structure for Procore.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Barry Scanlon (DCMC), Larry Hipsh (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on various Procore configurations for general settings to ensure accurate reporting.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on tracking Procore training. Documenting who has updated training and who hasn't enrolled in training yet.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating project schedule for milestones for Procore items.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore user/permission management for Siemens Energy. They had questions about their access and I provided them with needed information.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore Weekly Digest for Marc Maceira (DCMC) to have for the Monday DCMC/Genera update call. This will provide updates to the groups on weekly items
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.25 | 225 | 281.25 | Yes | 25-144600 | PREPA, Genera PR ¦ Deliverable 11- PMO ¦ DR 4339 - Mark Merritt, Lauren Wells, Jack Darnall, Frances Vallejo, Barry Scanlon, Larry Hipsh, Mike Merritt, DCMC. PMO Internal Catch-up meeting to discuss staffing request from Genera, offers to be made and strategy on site positions.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on evaluating processes for Daily Logs and Procore configurations. Evaluation of usage in tools in Procore for task module. Should this be used by teams and how.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore Weekly Digest for Marc Maceira (DCMC) to have for the Monday DCMC/Genera update call. This will provide updates to the groups on weekly items
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore training tracker as this is a manual process, I am going to keep trying to create a report in Procore that will track this.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on trying to run reports in Procore for custom fields. There doesn't seem to be a way to tie the custom field for certification to the actual directory and report from it.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing financial data discussed in our meeting with Procore. Trying to map out what we know and what we need and making sure the two align so that we have an accurate accounts.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Procore (Liz Fronduto), Breno Nasser (Procore), Marc Maceria (DCMC),Mark Merritt (DCMC), Jose Ralant (DCMC), to discuss next steps for Procore Financial Management.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations. Added in custom fields to help track certification better and run reports against it, faster than tracking it in Excel.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on various correspondences including some with Procore (Liz Fronduto) for scheduling of meetings. Franklyn Colmenares (CSA) for adding new users to Procore.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configuration task sheet. This tracks all the tasks for setup to ensure we setup each job and each company level configuration correctly. This is a list that we review with Procore (Liz Fronduto).
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on various correspondences including one for access to Procore for Herbert Guilbe (Genera) to access the safety manual.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding new users to Procore. This was for Jaime Pesquera(DCMC) and Gilberto Soto (DCMC).
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on pulling information together for Procore Financial Management meeting on 2/18. This is a meeting that will continue our build out of the financial process.
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore agenda and action items for meeting with project team leads Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith).
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permission matrix to help project team leads understand which roles have what access in Procore.
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on updating project roles in Procore for the purpose of helping assign permissions and training for existing users.
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on items for Procore Financial Management Implementation. Mapping out what pieces are left to implement so that we can go-live and start using it.
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching equipment tracking in Procore. There is a module that you can import your equipment and track it through Daily Logs.
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training tracker and updating Procore weekly digest sheet.
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing draft RFI and Submittal workflows to incorporate into Procore.
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Franklyn Colmenares (CSA) for Procore training certifications and other items
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO catch up call. Mark Merritt (DCMC), Jack Darnall(Lemoine), Barry Scanlon(DCMC), Frances Vallejo(DCMC) to discuss Procore updates and staffing for Vega Baja and
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on various correspondences, answering questions about Procore items pertaining to training, users permissions and tools.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore configurations for Financial Management.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore SOP Manual. This entails how the system was setup for Genera to use and who is responsible for what.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Project Coordinator-Franklyn Colmenares (CSA), Rafael Pabon (CDM Smith) to discuss Procore updates and configurations. Discussed RFI and Submittal Workflows.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating reports in Procore RFI tracking to share with Franklyn Colmenares (CSA) and Rafael Pabon (CDM Smith) so that they use the Procore reports and not have to recreate outside of Procore.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training tracker. Diving into details to see who has never logged in but has been give instruction to complete certification.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on document prep for Project team meeting today. We are discussing Procore and it's use on the Projects. I've defined an agenda to ensure we cover all topics and walk away with who is responsible. Topics covered will help determine some configurations in Procore.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences, review of emails and documents pertaining to the Tesla NDA. Need to review with teams on how this might affect any processes in Procore.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on various correspondences, answering questions about Procore items.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations. Scoped out what workflows would be beneficial to use at a company level vs per project level.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 225 | 168.75 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR 4339. Teams call with Mark Merritt, Mike Merritt, Barry Scanlon, Lauren Wells, Jack Darnell, Frances Vallejo. Discussed update on project, job offers, organization chart based on Genera edits, update on PROCORE.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating the Master Procore SOP document. The intent for this document would be an overall Manual that Genera can reference as it pertains to Procore usage.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on running reports in Procore. This is a way to gauge volume of users being added and their activity levels within the system.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tool set document to be used for discussion with new companies that come on board to the projects.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) project planning. Setting goals for items in Procore and assigning milestones. This includes items such as SOP documents, follow up discussions around equipment tracking, and other tasks.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding Companies to Procore so that they can be in the system and attached to all the new users that have been added.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Franklyn Colmenares (CSA) for Tesla company training and permissions. Discussed what they have access to in Procore. He has a meeting with them today and is going to discuss Procore certification.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on various correspondences pertaining to Procore project setup.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching new updates that Procore has coming out to see if any pertain to anything that we are doing or might want to do in the future.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on evaluating needs for custom fields in Procore. We can add these in most modules but need to evaluate if there is a need for any in the RFI's and Submittals. We most likely use custom fields sets when we start talking about Safety items being in Procore.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions. Looked into need to adjust permissions for suppliers vs general permission for contractors.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore training spreadsheet to keep track of what users are enrolled in Procore certification training and which ones have completed training.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating documentation for Project teams to use to show users what tools are available to them in Procore. This will help with discussion on-site for what tools to use so that users don't start the project with using emails or a shared drive to put documents.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding new Siemens users to Procore for projects. Added Siemens as a company in Procore and send email to all to instruct on how to complete training.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with PMO; Jack Darnall (DCMC), Frances Vallejo (DCMC), Barry Scanlon (DCMC), Larry Hipsh (DCMC) to discuss staffing with interviews and start dates for people on Vega Baja. Making final decisions on offering what positions to whom.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on support for Franklyn Colmenares (CSA) for submittal workflow approver in Procore. He closed a submittal but an optional "approver" was showing up red on the final cover page. Had to go in and try to remove user but once a workflow has started you cannot remove users. He is going to do a revision and comment on why she shows up in red.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore project setup questions for the BESS & Peakers teams to ensure we have the configurations correct when starting the projects. Franklyn Colmenares (CSA) and Rafael Pabon (CDM Smith) will review and make comments to help drive consistency.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore Weekly Digest for Marc Maceira (DCMC) to have for the Monday DCMC/Genera update call. This will provide updates to the groups on weekly items.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on various correspondences for setting up users in Procore, staffing questions and Procore training questions.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on creating a RACI chart to help with Procore items for Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith) to ensure we are all supporting each other to make Procore a success.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore support for Rafael Pabon (CDM Smith) for adding new users.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 PMO DR 4339. Teams call with Mark Merritt, Mike Merritt, Barry Scanlon, Larry Hipsh, Lauren Wells, Jack Darnell, Frances Vallejo. Discussed update on project, job offers, organization chart based on Genera edits, update on PROCORE.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.25 | 225 | 56.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Tesla team to get the correct email for Howen Lim (Tesla) so that we could get him signed in to Procore.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with PMO; Jack Darnall (DCMC), Frances Vallejo (DCMC), Barry Scanlon (DCMC) to discuss staffing with interviews and start dates for people on Vega Baja.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP's documents, schedule for setup and time to work with teams to define project specs.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Permission Matrix to share with Franklyn Colmenares (CSA) for discussion with project teams. We would like to discuss and evaluate templates that were brought over from CDM Smith Procore.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on project scheduling to ensure we're documenting milestones for future and seeing where gaps may be.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating a RACI chart to help with Procore items for Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith) to ensure we are all supporting each other to make Procore a success.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training tracker. Updating user status for those that have completed their certification.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating personal task list for Procore items to ensure items are being addressed and accounted for.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial Management. Worked on creating mapping and configurations.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations. I am outlining certain fields types that I would like to project teams to weigh in on and decide if they stay as out of the box or do we need to customize them to the projects.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attend BESS Check In meeting. Meeting is led by Gabriel Sepulveda (Genera) and each line item of the BESS Project Needs tracker is reviewed and updated by the team. Attended by Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), Lauren Wells, (Lemoine), Francisco Rivera (Genera), Frances Vallejo (DCMC), Alejandro Ronda (Genera).
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Rick Patterson (DCMC) to discuss Sharepoint site connection to Procore. Mark Merritt (DCMC) asked him to research information on making the connection between the two. I showed Rick how we have it set up in Procore so that he could better understand what was needed. We are going to setup a call with others, later this week to get final direction. This will be part of the Program workflows on document management.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on project planning for the week. Made adjustments to timelines for Financial Management Implementation.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence to users for our upcoming Financial Procore meetings. I explained the path that we are taking to configure and what next steps are.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check in Project Needs. In attendance: Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Frances Vallejo (DCMC), Larry Hipsh (DCMC), Rafael Calderon (DCMC) and others to discuss project needs and updates. I attended to discuss Procore items such as workflows and training.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences, one to Franklyn Colmenares (CSA) about Sargent and Lundy asking to change folder structure for Procore. He said this has been approved but is going to double check before I make any changes.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences and summary email to Jose Ralat (DCMC) about Procore Financials and set up.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore project milestones. This helps to clearly see what items are up next and what items are in the future to be accounted for.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting. Created some reports to gauge what is being used and also monitored already created reports. As we get more users and data in the system the reports will start to build up and tell a story of what is happening on the projects.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore Weekly Digest for Marc Maceira (DCMC) to have for the Monday DCMC/Genera update call. This will provide updates to the groups on weekly items.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore files. There were files that were deleted that needed to be recovered. Also, sent new file structure mock up to Sargent and Lundy for final approval
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training tracker again as the first version formatting did not save.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on project planning for the week. Scoped out what items for Procore will be a priority and gather information to prepare for BESS Weekly Update call today.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Training Tracker. This is used to make sure users are enrolled in on-line training and are completing their certification.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call to discuss where we are with hiring staff. Reviewed staffing spreadsheet with Michael Merritt. Jack Darnall, Mark Merritt (joined a few minutes late), Frances Vallejo, Lauren Wells, Annelia Holton-Williams and Barry Scanlon (Lemoine/ DCMC) Mark brought up a new candidate for the Program Coordinator role, Gabriel Salgado who currently works for COR3 and is very familiar with the BESS/Peakers program already.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Franklyn Colmenares (CSA), Rafael Pabon (CDM Smith), Juan Mendoza (CDM Smith), Gabriel Perez (CDM Smith) to discuss Procore items such as timelines, submittal setups, how will the financial management tool work and what should they be doing until it comes online. They are starting Vega Baja but wanted to know about future project start dates and alignment with Procore tools.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) had a meeting for an Intro call with Alexandra Martinez for the position of PM Procore Specialist. It was a great call. She has all the right experience for this position. She used to work at Procore, she has done a Procore implementation on the island before, she has worked as a Project Manager for a Utility company. I have asked her to submit her resume and talk with Mike Merritt (DCMC) for next steps.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences. Sent email to Procore (Elizabeth Fronduton) and Marc Maceira (DCMC) talking about Procore items.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence to Procore for rescheduling financial management calls and explaining to them that we are evaluating how we are going to rethink how we put budgets per site into Procore. Also sent emails about configure settings for name that appears on emails.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore Weekly Digest for Marc Maceira (DCMC) to have for the Monday DCMC/Genera update call. This will provide updates to the groups on weekly items.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching the schedule tool for Procore. Procore has changed the way they use/upload P6 schedules to the system and I want to ensure we are running from the latest knowledge. Marc Maceira (DCMC) had inquired about us obtaining a license and I'm not sure that is necessary to use the data in Procore.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on putting together a summary email for Jose Ralat (DCMC) to help better demonstrate our structure we are trying to achieve for Procore Financial Management. I am laying out all the details to help him with formulating budgets so that we can use this for each specific plant site.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on updating project roles in Procore for the purpose of helping assign permissions and training for existing users.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Esther Rohena(DCMC) and Jose Ralat (DCMC) to discuss Financial Management structure in Procore. We were at the point of entering budgets in per site per PW but it is not broken out that way so Jose said he could work on Estimated budgets based on a formula he can do and we can see if that will work to have as a budget in Procore.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO Catch up Call. Mark Merritt (DCMC), Frances Vallejo (DCMC), Annelilia Holton-Williams (DCMC),Michael Merritt (DCMC), Jack Darnall (Lemoine), Larry Hipsh (DCMC) were in attendance to discuss staffing, We reviewed the candidates that were up for an offer and discussed placement of others.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting. Ran reports to get an idea of volume of Submittals/RFI's that are coming through the project. This report also views other tools usage. This can tell us where users need training focus and knowledge of the system.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on document to help create SOP's for submittals, drawings, RFI's. Will use this document to ask project team questions to best setup the system from their perspective.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing resumes for PM Procore Specialist. Mike Merritt (DCMC) sent one for Dian Ramos. Would need to talk to her to gain insight into how much Procore experience she has.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR 4339. PMO Call. Frances Vallejo, Lauren Wells, Mark Merritt, Mike Merritt, Jack Darnall, Larry Hipsh, DCMC. Discussed update on hiring, procore and tasks still pending.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating SOP and questions for Vega Baja team for Procore settings. We need to define the submittal workflow and which roles will have which responsibilities.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meetings for Procore Project Timeline discussion and gathering of information needed.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Genera Helpdesk (Gabriel Perez Quiles) for open ticket status.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating a process map for Proof of Concept Cat z financials in Procore. I'm mapping out all the variables so that we can communicate the flow.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for email settings and Company system configurations so that communication from Procore doesn't say DCMC, it needs to read from Genera PR.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with New User setup with Samantha Jones (CDM Smith), sending emails to new users for how to get to training in Procore.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Permissions in Procore. Modifying permissions for Sam Jones (CDM Smith), to allow access to create RFI's. Checked other permissions to ensure consistency.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing Procore update for Genera/DCMC Weekly call on Monday 2/10.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Amol Daxikar (CDM Smith), Sam Jones (CDM Smith), Marc Maceira (DCMC) for our weekly Procore Status Call. We discussed Financial module, Submittal Workflows, and Directory.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on project scheduling for Procore Implementation projects such as Project Financials. Worked on putting dates with milestones so we can communicate to leadership and users when the tools will be ready to use.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on creating SOP and questions for Vega Baja team for Procore settings. I've created a document to ask all questions to get the project setup and ready to run smooth.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing Inegrum's Document Control Grants Connect to better understand how things are structured and give some back info for me.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing financial documents received from D'Alexzander Gonzalez (DCMC), Esther Rohena (DCMC) to better understand the PW's and Cost Codes along with how the different versions are revised and submitted. There are multiple contracts to consider when evaluating how to organize this into Procore.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on new user setup in Procore. New request are sent in to the Genera Helpdesk and then I create them in Procore and email the user instructions for next steps.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore directory and assigning roles to users for better reporting and permissions structure.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on inputting Job Titles and Project Roles that I received from Sam Jones (CDM Smith) into Procore for existing users. This will help us identify what training to direct users to based on their project roles/titles.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences and phone calls. Spoke to Mike Merritt (DCMC) about the hiring process for a candidate I found for the Procore PM position and answered various emails.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) had a meeting with Esther Rohena (DCMC) to discuss the plan for DI's, Cost codes and Budgets in Procore. After our call with the team earlier, she has some concerns on the separation of the PW and cost versions. We talked through different ways Procore might could handle it. We have decided to slow down the implementation and do a Proof of Concept using the Catz project. We feel this will give the team insight as to how Procore will work and also allow us to see any gaps in the system before adding the other PW for BESS and Peakers and others.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Breno Nasser (Procore), Esther Rohena (DCMC), Glorimel Torrado (DCMC), Rafael Calderon (DCMC), Marc Maceira (DCMC) to discuss Procore Budgets. This is a series of meetings to get all Financials setup and running. Today we discussed the DI's connecting to Cost Codes and then over to Budget. We looked at the views and how we can customize those.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore settings to prep for Budget call today. Ensured that all fields were correctly connected for DI's and Cost Codes so that we could start building out the budgets.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO team call reviewing hiring status and staffing needs. Mark Merritt, Mike Merritt, Frances Vallejo (DCMC) and Jack Darnall (Lemoine)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 3 | 225 | 675 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Coordination of upcoming interviews, review associated resumes and comment on earlier interviews held this morning.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on inputting Job Titles and Project Roles that I received from Sam Jones (CDM Smith) into Procore for existing users. This will help us identify what training to direct users to based on their project roles/titles.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more Procore Financial Management setup in preparation for the call tomorrow with Procore to continue setting up Financials in Procore.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Franklyn Colmenares (CSA) discussing Procore training, permissions and future meetings.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with D'Alexzander Gonzalez (DCMC) to discuss DI's for Critical Components for Procore. We discussed not having DI's yet for CC and that we could wait to set those up. What we need to factor for are NME and Fuel to be included. I will ask on the Procore call tomorrow 2/5.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on running reports from Procore to show what users have enrolled in Training and which ones have completed their certification, per Sam Jones (CDM Smith). Worked on collecting information for DI's and cost codes for my next meeting to discuss Critical Components setup in Procore.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Shellsea Maysonet (MZS) to go over Procore reporting and navigating through Procore.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up Procore permissions for internal reporting for Shellsea Maysonet (MZS). Created links for training so she can learn how reports work in Procore and how to run/create them.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 225 | 337.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding in DI Codes to Procore for each site project sub jobs. This will ensure we are setting up Financial Management tools in Procore correctly. Also worked on adding Cost codes to each project.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore list of users for assigning project roles/title so that we can know which training to send to users. Training is based on role. I sent Samantha Jones (CDM Smith) an email asking for CDM Smith project roles/titles.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on training materials for Procore. When a new user request access they will be added to Procore Training project and then sent an email (that I put together) informing them of training certification and next steps.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Called references Abe Velasquez provided: left messages with Ryan Smith and Christopher White of the Ryan Companies. Spoke to Jerome Hensley and his opinion is that Abe would excel in the position of Program Coordinator. Reviewed Jonathan Escobar resume for 2 PM interview - Procore Specialist roll
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2 | 225 | 450 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Working with the team on staffing recommendations and documenting those via emails with Mike Merritt (DCMC), Jack Darnall (Lemoine) and Frances Vallejo (DCMC). Coordinating with Mike Merritt on setting up an interview with another Program Coordinator candidate (Gilberto Sucre). Mark Merritt (DCMC) and Jack Darnall (Lemoine) in copy of that correspondence.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- BESS Check In Team's meeting. Discussion on overall BESS program progress and review of contracts, schedules and needs. I requested Frances Vallejo (DCMC) to get us a copy of the weekly meeting minutes to attach for our record.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Comment on staffing needs and follow up with Jack Darnall (Lemoine), Mark Merritt (DCMC) and Frances Vallejo (DCMC) on Abraham Velasquez's interview and references.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Hipsh, Larry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 225 | 450 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review email correspondence from last week and determine action plan for this week. Review resumes from Luis R Quinones, Jonathan Escobar, Abraham Velasquez, Claudia DeJesus and Rocio C Baez in preparation for interviews.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for submittals.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences. Answered emails to coordinate meetings with Shellsea Maysonet (DCMC) to discuss Procore reporting and current reporting that she is handling.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Esther Rohena (DCMC) to discuss DI and Sub jobs for setting up in Procore. This setup will be instrumental in working with the Financial Management section of Procore. We discussed how the PW, DI work to simplify the input that needs to go into Procore to make things align.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 225 | 225 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. This meeting included Jesus Cintron (Genera), Frances Vallejo (DCMC), Gabriel Perez (CDM Smith), Rafael Pabon (CDM Smith), Joaquin Quinoy (Genera), and others. We discuss updates to project needs. My role was to update on Procore items.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 225 | 112.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up meetings for Procore Financial Management setup. Coordinated the next four meetings to ensure we are properly planning and setting up the Procore financials and Invoice Management to reflect current operations.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Foster Veazey and Jack Darnall (Lemoine) worked on the organizational portions of Procore for the PMO group
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - call with Al Rocha (LEMOINE ) to discuss the next steps with the safety initiative
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 220 | 165 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - PMO call with Barry Scanlon, Mark Merritt, Mike Merritt, Frances Vallejo, Anneilia Holton (DCMC) and Lauren Wells, Foster Veazey ( Lemoine)
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Safety call discussing the safety manual for construction projects. Hebert Guilbe (Genera), Foster Veazey (Lemoine), Frances Vallejo (DCMC), Al Rocha (LEMOINE), Greg Landry (LEMOINE), Larry Hipsh (Lemoine), Jean Pierre Menay (DCMC)
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Reviewed the agenda and content for Thursday’s safety discussion
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - meeting via phone with Foster Veazey (Lemoine). Coordinated meeting schedules for the next two weeks on the islands.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.75 | 220 | 165 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - reviewed the project schedule with the hiring schedule to ensure start dates, hire dates are aligned
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - meeting with Foster Veazey (Lemoine) to organize the PMO structure
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 220 | 165 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -PMO call discussing the project Frances Vallejo, Anneilia Holton, Mark Merritt, Mike Merritt, Barry Scanlon, (DCMC) and Larry Hipsh, Lauren Wells, Foster Veazey (Lemoine)
2025-02-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- phone call with Foster Veazey (Lemoine) to discuss Genera project parameters and commitments.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.75 | 220 | 385 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Worked on PMO summary notes and outline next steps. Jack Darnall only
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.5 | 220 | 330 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Jack Darnall (Lemoine) summarized next steps based upon the days meetings to discuss implementation of a LEAN program for both operations and construction, organizational structure and the different opportunities for LEAN implementation, status of onboarding new employees, new project requests for position from Genera on critical components project, and other program related matters.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Met with Frances Vallejo DCMC. Reviewed and reorganized personnel deployment based upon new work requested from Genera. Talked with Carlos Gonzalez (Integrum) about revised start dates
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 220 | 330 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PMO meeting, attending were DCMC Barry Scanlon, Mark Merritt, Mike Merritt, Frances Vallejo, and Lemoine Larry Hipsh, Foster Veazey. Items discussed were status of onboarding new employees, new project requests for position from Genera on critical components project, onboarding of new management personnel, and other program related matters
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Let with Frances Vallejo of DCMC and Leon Foster of LEMOINE. Discussed the Genera organizational structure and the different opportunities for LEAN implementation
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.25 | 220 | 275 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Met with Heather Ormonde, Leon Foster of LEMOINE , and Frances Vallejo, Mark Merritt of DCMC to review the previous LEAN planning meeting and discuss the next steps for implementation
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Met with Heather Ormonde, and Leon Foster of LEMOINE , Frances Vallejo of DCMC, Joaquin Quinoy of Genera - Meeting was to discuss implementation of a LEAN program for both operations and construction
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Worked at the DCMC office preparing for the day. Reviewed plan for LEAN meeting
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Jack Darnall (Lemoine) only - overall review of upcoming tasks for San Juan trip. Reviewed project status
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.75 | 220 | 385 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Heather Ormonde, Leon Foster (Lemoine), Mark Merritt (DCMC)- Attended meeting to discuss the next day's lean discussion and topics
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Jack Darnall (Lemoine) only, prepared for San Juan meetings and updated staffing log and reviewed all needs for personnel
2025-02-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Call with Barry Scanlon (DCMC) about next 2 days in San Juan , the upcoming meetings, discussed goals and expectations
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PMO call with DCMC Frances Vallejo, Mark Merritt, Barry Scanlon, Mike Merritt. Mostly reviewed current status of hires and placement, updated group on safety manual
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Call with Larry Hipsh (Lemoine) to review c the project, his assignment, expectations, immediate needs for them project
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- phone meeting with Larry Hipsh (Lemoine) to discuss various candidates for onsite positions.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.5 | 220 | 330 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- meeting with Al Rocha (LEMOINE ) and Greg Landry (LEMOINE ) about producing the safety manual for Genera’s review. Went section by section to review
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PMO post call discussion with Barry Scanlon (DCMC)
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.25 | 220 | 275 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PMO call with Frances Vallejo, Mark Merritt, Mike Merritt (DCMC), Larry Hipsh, Lauren Wells (Lemoine)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- meeting with Larry Hipsh (Lemoine) via phone to discuss goals and needs for the week ahead. Genera organizational call
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Prepared safety manual email and program for distribution
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Call with Frances Vallejo (DCMC) about safety manual and next steps
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PMO call with Frances Vallejo, Mike Merritt, Barry Scanlon, Mark Merritt (DCMC). Discussed project updates and critical issues
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Jack Darnall only -reviewed resumes for the day's interviews. Reviewed safety manual from LEMOINE Program Services to be sent to Genera
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.75 | 220 | 165 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Jack Darnall only. Reviewed safety manual prior to sending out to Herbert Guilbe Marin (Genera)
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- meeting with Kylie Miller (Lemoine) to update the staffing log and worked thru a format change
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- phone call with Larry Hipsh on Ricky Benefield (applicant) role and need
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Phone call with Ricky Benefield (applicant), Larry Hipsh about schedule oversight consulting role
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- call with Mark Merritt (DCMC). Discussed de staffing needs and candidates
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PMO call with Mike Merritt, Mark Merritt, Frances Vallejo (DCMC), Larry Hipsh (Lemoine) to discuss status of the project, hiring and interview status
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- phone call with Larry Hipsh (Lemoine) about candidates' status and needs
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Met with Barry Scanlon (DCMC) about Genera / DCMC dynamics and workload.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Larry Hipsh ( Lemoine) call to discuss safety manual program and rollout
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Jack Darnall only - worked on safety program outline
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- phone call with Greg Landry , Al Rocha (Lemoine) to discuss safety manual deliverable and content for initializing the safety manual upgrade
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 220 | 220 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Jack Darnall only, worked on next steps for the Genera safety program deliverable
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Victor Rodriquez (Genera), Frances Vallejo (DCMC), Richards Tellers, Mike Merritt (DCMC), Larry Hipsh (Lemoine) to discuss needs for the safety program rollout. Next steps and actions
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- phone call with Larry Hipsh (Lemoine). Discussed job progress and immediate needs
2025-02-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.5 | 220 | 110 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurricane Maria - Phone call discussion with Larry Hipsh (Lemoine) to discuss potential program manager director candidates
2025-02-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 220 | 55 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurricane Maria - Frances Vallejo (DCMC) , Michael Merritt (DCMC), and Jack Darnall ( Lemoine) discussed the interview with candidate Abraham Velasquez and what type of next steps needed to be.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Identification | Direct-PA | Activities necessary for project identification (i.e., meetings, coordination, documentation request/review) | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review the notes generated in the site, complete the reports. Collect information about PPE need in the site. Review the Co2 cylinder issue.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | 4.5 | 184 | 828 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Site inspection, meeting with Site Manager Jaime Pesquera DCMC, Franklin Colmenares CDM, Nelson Soler CDM, and Carirma Sanchez (Homeca). Discussed and inspect Vega Baja Site as part of the monitoring and managing phase to keep the project expectations progressing as planned.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up meeting to discuss staffing update, contract budget, office space and Procore. Participants: Mark Merritt, Mike Merritt, Lauren Wells (DCMC), Jack Darnall (Lemoine).
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued reviewing the Genera Connect Financial Tracker application and documentation. Prepared a list of discussion items for the next technical meeting, ensuring that all necessary fixes are addressed before deploying the testing environment.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Financial Tracker Findings Review Meeting (4:00 PM – 4:30 PM) Held a review meeting with Integrum to discuss the findings from the Genera Connect Financial Tracker tests performed earlier. Reviewed the documentation and infrastructure setup to address any gaps before the next phase. Attendees: Integrum: Jorge Aponte, Aldwin Pagan DCMC: Marc Maceira
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Pre-Meeting (3:00 PM – 4:00 PM) Attended the DCMC pre-meeting to discuss ongoing projects, status updates, and coordination efforts across teams. Attendees: DCMC: D’Alexander Gonzalez, Christian Cruz, Danny Martinez, Eisha Mercader, Glorimel Torrado, Mark Merritt, Pedro Cabrera, Rafael Calderon, Roberto Bosch, Sheila Torres, Shellsea Maysonet, Victor Maldonado, Marc Maceira Integrum: Jorge Aponte, Liznette Guzman
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Client Update and Genera Connect Testing (1:30 PM – 3:00 PM) - Updated the weekly client update PowerPoint slides to include project progress, pending issues, and key milestones. - Conducted tests on Genera Connect Financial Tracker to verify alignment with documentation. Identified several findings related to infrastructure and application-level configurations and prepared a report highlighting required modifications.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 3 | 184 | 552 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Regulatory Reporting and Genera Connect Documentation Review (9:00 AM – 12:00 PM) - Provided additional January 2025 fuels availability reports by power plant to Romano Zampierollo from GeneraPR for regulatory reporting purposes. - Continued reviewing the Genera Connect Financial Tracker architecture documentation to ensure proper alignment with GeneraPR’s infrastructure and security requirements. - Reviewed Genera Connect Financial Tracker project documentation and provided comments and recommendations based on the review.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review and comments the Safety and Security Manual to Herbert Guilbe safety person by Genera.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 4.5 | 184 | 828 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Call meeting to discuss issues in Vega Baja Site. Review comments by Herbet Guilbe Safety officer by Costa Sur Genera Site, review the safety manual of Genera. Meeting with Franklin Colmenares (CDM) by Vega Baja site. Discussed Safety and Security concerns to the Vega Baja Site to ensure there are recommendations to fix them and provide protections or mitigation of the issues.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Identification | Direct-PA | Activities necessary for project identification (i.e., meetings, coordination, documentation request/review) | 3 | 184 | 552 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Review the safety and security and plans by Vega Baja project. Meeting with Franklin Colmenares (CD Smith) to discuss Vega Baja Safety Issues.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers Project Budget/Schedule meeting to discuss status on budget and master schedule. Participants: Alejandro Maymi (Genera), Gabriel Perez (CDM), Franklyn Colmenares (CSA), Rafael Pabon (CDM) and German Ojeda (Genera).
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2 | 184 | 368 | Yes | 25-144600 | Genera PR - Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Genera Safety Manual call with Herbert Guilbe (Genera), Jean Pierre Menay (DCMC), Jack Darnall (Lemoine) and Al Rocha )Lemoine) to discuss the Genera safety manual, updates to the Manual, support from DCMC and next steps.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Core Applications Separation Daily Meeting (6:00 PM – 6:30 PM) Participated in the daily Core Applications Separation project meeting to discuss pending items and readiness checks in preparation for the weekend cutover. Ensured that all critical tasks were being addressed to facilitate a smooth transition. Attendees: GeneraPR: maria Sanchez, Claudia Peña, Hector Vazquez, Yamaris Castro LUMA: Jim Seibert, Efrain Aguila, Maneesha Shah Accenture: Andy Quanch, Chandra Sekhar DCMC: Marc Maceira
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Plant Availability KPI Report Review (5:00 PM – 6:00 PM) Continued reviewing the plant availability KPI report provided by Vladimir Scutt from GeneraPR. Incorporated the required formulas and calculations to improve accuracy and enhance the reporting structure.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reporting and Standardization Meeting with Client (4:00 PM – 5:00 PM) Held a meeting with the client to review the proposed standardized reports for fuel consumption and power generation. Provided a demonstration of the new reporting format and discussed potential adjustments to better align with operational and compliance needs. Attendees: GeneraPR: Vladimir Scutt, William Rios, Hector Vazquez, Jose del Rio DCMC: Marc Maceira
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Standardization of Data Reporting for Fuel Consumption and Power Generation (1:00 PM – 3:30 PM) - Continued working on the standardization of data reporting for fuel consumption and power generation reports. Established a directory structure to organize reports efficiently for both power plants and GeneraPR headquarters using a centralized reporting system. Additionally, prepared sample data for demonstration to the client. - Prepared and sent Romano Zampierollo from GeneraPR additional reports related to fuels consumption and power generation for regulatory compliance.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Reviewed the Genera Connect Financial Tracker network diagram to ensure compliance with GeneraPR requirements and confirm that the design is functional before implementation. The review included verifying that resources are properly identified and configurations are accurately specified. - Discussed reporting needs for the Regulatory department with Romano Zampierrollo from GeneraPR. Additionally, provided the January fuel reports to support compliance and regulatory reporting efforts.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Identification | Direct-PA | Activities necessary for project identification (i.e., meetings, coordination, documentation request/review) | 3.25 | 184 | 598 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Site visit coordination, review the Vega Baja plans, security and safety documentation and coordinate resources for the site.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Attended Safety and Security and Safety training offered by Irving Babilonia (Genera Member).
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Scope of Work Development | Direct-PA | Activities necessary to develop/document project's scope of work (any level) | 3.25 | 184 | 598 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Start in Genera Offices, review the Health and Safety Manual proposed for Genera.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 184 | 138 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PM Meeting with Genera to discuss BESS and Peakers project status. Participants: Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA), Rafael Pabon (CDM Smith) and Jesus Cintron (Genera).
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Core Applications Separation Cutover Plan Review (6:00 PM – 7:00 PM) Held the daily Core Applications Separation meeting to discuss the cutover plan in preparation for the weekend cutover. Reviewed pending tasks, potential risks, and required stakeholder coordination to ensure a smooth transition. Attendees: GeneraPR: Claudia Peña, Maria Sanchez, Hector Vazquez, Yamaris Castro LUMA: Jim Seibert, Efrain Aguila, Maneesha Shah Accenture: Andy Quanch DCMC: Marc Maceira
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procurement Process Discovery Meeting (4:30 PM – 5:30 PM) Participated in a discovery meeting with GeneraPR’s IT and Procurement team to explore potential alternatives for streamlining the procurement process. Discussions focused on identifying inefficiencies, automation opportunities, and process enhancements. Attendees: GeneraPR: Sulinnette Perez, Victor Tellado, Bianca Crespo, Joel Pantojas DCMC: Marc Maceira
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Power Plant Generation Availability Indicators (11:00 AM – 12:30 PM) Began reviewing performance indicators provided by Vladimir Scutt from GeneraPR related to power plant generation availability. The focus was on establishing availability metrics based on existing plant performance to enhance operational reporting and analysis.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Financial Tracker Meeting (9:30 AM – 10:30 AM) Held a walkthrough session with GeneraPR’s cybersecurity and infrastructure team to review the Genera Connect Financial Tracker application from both a functional and technical perspective. The goal was to facilitate GeneraPR’s internal configuration to securely deploy the application's testing environment. Action items included updating the application documentation to reflect the latest configuration changes. Attendees: GeneraPR: Jean Carlos, Michael Silva, Mario Gomez Integrum: Aldwin Pagan, Keylamerari Sierra, Juan Carlos DCMC: Marc Maceira
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 2.25 | 184 | 414 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Collect quote for offices trailer need in Vega Baja Site.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review the Health and Safety actual Manual in Genera. Include the Puerto Rico OSHA requirements need.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2.25 | 184 | 414 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Procore training
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended internal PMO Catch up call to discuss project management update on staffing, Procore, contract amendment with Genera and trailers at the sites. Participants: Mark Merritt, Michael Merritt (DCMC), Lauren Wells (DCMC), Jack Darnall (Lemoine), Anneilia Holton (DCMC) and Foster Veazer (Lemoine).
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 3 | 184 | 552 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Siemens Kick Off meeting with Genera team to discuss contract review, invoicing, deliverables and project management. Participants: Genera Team; Joaquin Quiñoy, Germán Nuñez, Fernando Ortiz, Alejandro Maymi, and Kevin Futch. CDM Smith: Rafael Pabon, Carlos Palomares, and Enrique Laya. Sargent and Lundy: Mike Kuczynski – Miguel Del Valle, Bo Johnston, Christopher Mateo, Nelson Rosado, Reinaldo Romero, Ramon Vasquez, Angel Alicea , and Jason Janicki. DCMC: Rafael Calderón, and Frances Vallejo. Siemens Energy: Dennis Serra, Chris Bell, Stefan Linder, Jim Matlock, Keith Badger, ,Manoj Kunjappan, Mian Mubashar Ali, Cecilia Eriksson, and Peter Svensson.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Core Applications Separation Daily Meeting (6:00 PM – 6:30 PM) Attended the daily Core Applications Separation project meeting to review pending items, potential issues, and roadblocks in preparation for the upcoming weekend cutover. Attendees: GeneraPR: Claudia Peña, Maria Sanchez, Hector Vazquez, Jean Gonzalez, Yamaris Castro LUMA: Efrain Aguila, Maneesha Sha Accenture: Adrian Bazzini DCMC: Marc Maceira
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Core Applications Separation & Genera Connect Weekly Update (5:30 PM – 6:00 PM) Participated in a weekly meeting with Maria Sanchez from GeneraPR to provide updates on both the Core Applications Separation and Genera Connect projects. Attendees: GeneraPR: Maria Sanchez DCMC: Marc Maceira
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Standardizing Fuel Consumption and Power Generation Reporting (1:00 PM – 5:00 PM) Worked on standardizing the reporting of fuel consumption and power generation across power plants to reduce turnaround time for compliance reporting. This included designing a standardized reporting template for plant managers to self-report required data, ensuring consistency and efficiency in producing fuels consumption and power generation reports.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2 | 184 | 368 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued reviewing the Genera Connect Azure environment for Financial Tracker to verify configuration, security settings, and infrastructure readiness for deployment.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Technical Review Meeting (9:00 AM – 10:00 AM) Held a technical review meeting between Integrum and GeneraPR to go over the technical documentation and pending items necessary to launch the Financial Tracker within Genera Connect. Attendees: GeneraPR: Jean Gonzalez, Michael Silva Integrum: Aldwin Pagan DCMC: Marc Maceira
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Frances Vallejo (DCMC). Discuss batteries project in Puerto Rico by Genera.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review Health and safety aspect for the peakers and batteries project by Genera in Puerto Rico
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review the security document in meeting with Gabriel Sepulveda (CDMA), Jesus Cintron (Genera) by Genera Batteries project in Puerto Rico.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2.25 | 184 | 414 | Yes | 25-144600 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers project Check in with Genera team to discuss project status and pending items. Participants: Rafael Pabon (CDM). Gabriel Perez (CDM), Jesus Cintron (DCMC), Lauren Wells (DCMC), Carlos Palomares (CDM), Enrique Laya (CDM).
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Meeting with PMs for BESS and Peakers projects. The PM's provided an update on the projects. Participants: Gabriel Perez (CDM Smith), Jesus Cintron (Genera), Rafael Pabon (CDM Smith).
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 3 | 184 | 552 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Azure Environment and CSR Review (2:00 PM – 5:00 PM) - Reviewed the CSR (Certificate Signing Request) provided by Aldwin Pagan from Integrum to ensure proper configuration and compliance with GeneraPR's requirements. - Reviewed the current Azure environment setup for Genera Connect, verifying that its configuration aligns with the provided documentation and ensuring all necessary components are properly in place.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in the daily status meeting related to the Core Applications Separation project. The meeting was focused on preparing for the weekend cutover, ensuring all tasks are aligned and roadblocks are addressed to facilitate a smooth transition. Genera: Yamaris Castro, Maria Sanchez, Hector Vazquez LUMA: Jim Seibert, Efrain Aguila DCMC: Marc Maceira
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Roadblock Meeting (5:30 PM – 6:00 PM) Held a meeting to discuss roadblocks for launching Genera Connect, focusing on resolving outstanding issues. Attendees: GeneraPR: Maria Sanchez, Jean Gonzalez, Hector Vazquez Integrum: Carlos Gonzalez DCMC: Marc Maceira
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.25 | 184 | 230 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Security Certificate and Roadblock Coordination (11:00 AM – 12:15 PM) - Worked with Aldwin Pagan from Integrum to discuss requirements for generating the CSR (Certificate Signing Request) for Genera Connect’s security certificate required for the development environment in GeneraPR’s Azure infrastructure. - Coordinated a meeting with key stakeholders to address roadblocks in the Genera Connect project. Meeting Participants for Roadblock Discussion: GeneraPR: Jean Carlos, Hector Vazquez, Maria Sanchez Integrum: Carlos Gonzalez DCMC: Marc Maceira
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Updates and Client Meeting Preparation (8:45 AM – 9:45 AM) - Discussed Genera Connect project updates with Jorge Aponte from Integrum to review progress and any outstanding tasks. - Updated the client update slide for the weekly client meeting, ensuring the latest project status and key developments were accurately reflected in the presentation.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Attended the weekly client meeting to review project updates and pending items across projects. Discussions included progress tracking, issue resolution, and upcoming milestones for key projects. Attendees: GeneraPR: Maria Sanchez, Alejandro Maymi MZC: Shellsea Maysonet, Ginell Torres, DCMC: Mark Merritt, D’Alexander Gonzalez, Roberto Bosch, Jose Ralat, Eisha Mercader, Christian Cruz, Saul Falcon, Marc Maceira; from Integrum: Jorge Aponte, Carlos Gonzalez;
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 184 | 368 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Revise and draft amendment to the Master Service Agreement with Genera PR. Analyze the agreement to additional expenses required for the project management.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended PMO Catch up call to discuss staffing update, Budget and interview status for the project management team. Participants: Mark Merritt (DCMC), Mike Merritt (DCMC), Jack Darnall (Lemoine), Lauren Wells (DCMC) and Anneilia Holton (DCMC).
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Maintenance/Assets Team (2:30 PM – 3:30 PM) Held a meeting with GeneraPR’s Maintenance and Assets team to discuss potential efficiencies in the current maintenance process by leveraging existing data. Attendees: GeneraPR: Sulinnette Perez, Vladimir Scutt, Hector Vazquez, Hiram Medero, Maria Sanchez, Victor Torres DCMC: Marc Maceira
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with the client to discuss procurement process optimization to enhance sourcing efficiency using advanced analytics solutions. Attendees: GeneraPR: Victor Torres, Hiram Medero,Sulinnette Perez DCMC: Marc Maceira
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Generation Report Updates (5:30 PM – 6:30 PM) Continued updating the power generation report to include the total heat rate of the system, as requested by LUMA. Adjusted calculations and formatting to ensure accurate representation of metrics.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- GeneraPR Steering Committee Meeting – Core Apps Separation (5:00 PM – 5:30 PM) Participated in the steering committee meeting to present the cutover plan for Core Applications Separation to executive stakeholders. The main objective was to ensure that the downtime and impacts of the cutover process were clearly communicated to all relevant parties. Attendees: GeneraPR: Jose del Rio, William Rios, Kevin Futch, Vladimir Scutt, Maria Sanchez, Hiram Medero, Yamaris Castro, Joaquin Quinoy DCMC: Marc Maceira
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria KPI Reporting Discussion with Vladimir Scutt (2:30 PM – 3:00 PM) Met with Vladimir Scutt from GeneraPR to discuss enhancements to KPI reports to ensure greater data accuracy and alignment with operational performance metrics.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Generation/Fuels Reporting and Standardization Meeting (1:00 PM – 2:30 PM) Held a meeting with GeneraPR stakeholders to review compliance reporting requirements and discuss standardized reporting improvements. The end goal is to enhance efficiency, data accuracy, and reduce errors in compliance reporting. Attendees: GeneraPR: Josue, Vladimir Scutt, Jose del Rio, Hiram Medero, Eric Berrios, Cristina Ribas, Maria Sanchez, Ricardo Pallens, William Rios DCMC: Marc Maceira
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Report Review and Opralog Data Analysis (9:30 AM – 11:00 AM) - Discussed with Vladimir Scutt from GeneraPR the work completed on reports last week and the updates requested by LUMA during the current week. - Reviewed Opralog reports to identify key operational data points supporting the reporting of fuel consumption, power generation, and outages to ensure alignment with compliance and operational needs.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.25 | 184 | 230 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended PMO Internal Catch-up meeting to discuss staffing request from Genera, offers to be made and strategy on site positions. Participants: Mark Merritt (DCMC), Lauren Wells (DCMC), Foster Vizzy (Lemoine), Jack Darnall (Lemoine).
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended meeting at Genera office regarding Lean Management program for Genera. The meeting was with Joaquin Quinoy (Genera), Carlos Negron (Genera), Mark Merritt (DCMC), Jack Darnall (Lemoine) and Leon Foster (Lemoine).
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended PMO Catch up call to discuss staffing update, hiring status and next steps regarding Procore and hiring needs. Participants: Mark Merritt (DCMC), Lauren Wells (DCMC), Foster Vizzy (Lemoine), Jack Darnall (Lemoine).
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Fuel Consumption and Power Production Report Review Meeting (4:00 PM – 5:00 PM) Held a meeting with Jose del Rio from GeneraPR to review findings from the fuel consumption and power production reports. Addressed inquiries from LUMA regarding discrepancies between the reported fuel consumption and generation data. Discussion also clarified differences between gross and net power production for January 2025. Attendees: GeneraPR: Jose del Rio DCMC: Marc Maceira
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 184 | 138 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Weekly Meeting (10:00 AM – 10:45 AM) Attended the weekly client meeting to review project updates and pending items across projects. Discussions included progress tracking, issue resolution, and upcoming milestones for key projects. Attendees: GeneraPR: Maria Sanchez, Alejandro Maymi MZC: Shellsea Maysonet, Ginell Torres, DCMC: Mark Merritt, D’Alexander Gonzalez, Roberto Bosch, Jose Ralat, Eisha Mercader, Christian Cruz, Saul Falcon, Marc Maceira
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 0.75 | 184 | 138 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Fuel Consumption and Power Production Reports Review (2:15 PM – 3:00 PM) Reviewed the fuel consumption and power production reports submitted to LUMA to identify discrepancies related to reported fuel consumption and power generation by LUMA personnel. Analysis focused on reconciling data inconsistencies for accurate reporting.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Financials Configuration Review Meeting (3:00 PM – 4:00 PM) Participated in a continuation meeting focused on financial management configurations in Procore. The objective was to ensure real-time financial tracking related to project budgets, aligning system capabilities with financial reporting needs. Attendees: Procore: Breno Nasser, Lauren Kennedy DCMC: Lauren Wells, Mark Merritt, Jose Ralat, Marc Maceira
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.25 | 184 | 46 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Consolidation and Submission of Fuels Consumption and Power Generation Reports (5:00 PM – 5:15 PM) Finalized and consolidated the fuels consumption and power generation reports and submitted them to Francisco Santos and the Regulatory department from GeneraPR. Additionally, provided the official response to LUMA's inquiry regarding the difference between total gross and net production to clarify the reporting discrepancies.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 0.25 | 184 | 46 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Client Update Preparation for Weekly Meeting (7:30 AM – 7:45 AM) Prepared the latest weekly project updates and key discussion points to be presented during the client update meeting. Ensured that all relevant data, pending items, and progress updates were included for an informed discussion.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended PMO call for BESS and Peakers. Participants were: Gabriel Perez, Rafael Pabon (CDM) German Ojeda and Franklyn Colmenares (Genera)
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Call with Jesus Cintron (Genera) to discuss the positions that need to be filled and projects details.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended PMO Catch up call to discuss offers to candidates, positions for Vega Baja, positions for Cambalache and Procore status. Participants: DCMC Mark Merritt, Michael Merritt, Annelia Holton, and Lemoine Lauren Wells, Jack Darnall.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Review and comment responses received from Proponents. Discussed such with Miguel del Valle (S&L) and Joel Pantojas (Genera).
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria reviewed, analyzed and commented on Tesla NDA documents and procedures related to accesses required in Procore. Discussed such with Christian Torres (Genera) and Marc Maceira (DCMC)
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.75 | 184 | 322 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - A&E RFP - Discussed deliverable with Jesus Cintron (Genera). Discussed scope of work with Jorge Sanchez and Joaquin Quinoy (Genera).
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.75 | 184 | 138 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Genera Weekly Meeting Preparation to brief client on project updates and weekly progress with participation from DCMC: Mark Merritt, Eisha Mercader, D'Alexzander Gonzalez, Rafael Calderon, Victor Maldonado, Jose Ralat, Pedro Cabrera, Roberto Bosch, Marc Maceira and Shellsea Maysonet (independent contractor not DCMC).
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- RFP 205317 – Grid Support Units - Reviewed responses Proponent (Solar Turbine) shared with Genera in response to Genera's Request for Clarification and the meeting held on 02/11
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.75 | 184 | 322 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Reviewed COR3's Corrective Action Plan (CAP) response. Developed a timeline and outlined the necessary steps to resolve all open items. Coordinated meeting with Jesus Cintron, Ricardo Pallens (Genera) and D'Alexzander Gonzalez (DCMC) to discuss.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Finalized the Independent Cost Estimate for Legal Services requested by Genera (Sulinnette Perez). Sent to Rick Patterson and Jeremy Blakey (DCMC) for review.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of January 2025 Fuel Consumption and Power Generation Report Discrepancies (10:00 AM – 12:30 PM) Began reviewing discrepancies in the January 2025 Fuel Consumption and Power Generation Report, as referenced by Cristina Ribas from GeneraPR. The focus was on reconciling and identifying source of differences in fuel barrel consumption for power generation to ensure data accuracy and compliance with reporting requirements.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Finalization and Submission of Fuel Consumption and Power Generation Report (4:00 PM – 6:30 PM) Continued working on the review and reconciliation of discrepancies in the January 2025 fuel consumption and power generation report. Completed the analysis and sent the final report to Cristina Ribas, including a response to LUMA’s inquiries regarding discrepancies in reported fuel usage and power output.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended Meeting with Rick Patterson (DCMC), Mark Merritt (DCMC) and Lauren Wells (Lemoine) to discuss the integration of Procore and SharePoint to manage the documentation.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended BESS/Peakers Project Schedule & Budget Meeting to discuss project status. The participants were Alejandro Maymi (Genera), Gabriel Perez (CDM), Rafael Pabon (CDM), German Ojeda (Genera).
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing FEMA (09/26/22, 08/23/23, 08/04/24, 12/27/24 letters) COR3 (08/12/22, 08/11/23, 09/01/23, 08/27/24 letters) and LUMA (05/09/22, 07/07/23, 08/07/24 letters) for Self-Performed Work for Genera generation projects. Review FEMA appeals and other jurisprudence on the matter.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin developing the Independent Cost Estimate for Legal Services as requested by Genera (Sulinnette Perez). Researched, retrieved (from the Puerto Rico Comptroller Office website) and reviewed multiple proposals (Pietrantoni Méndez Alvarez, Ferraiouli).
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 3 | 184 | 552 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continued developing the Independent Cost Estimate for Legal Services as requested by Genera (Sulinnette Perez). Researched, retrieved (from the Puerto Rico Comptroller Office website) and reviewed multiple proposals (Goldman Antonetti, Cancio Nadal).
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.25 | 184 | 414 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Fuel Consumption and Power Generation Report Development (8:15 AM – 10:30 AM) Continued developing the fuel consumption and power generation report, incorporating feedback from José del Rio from GeneraPR to enhance data accuracy and ensure alignment with reporting requirements. Focused on refining data validation methods and structuring the report to improve clarity and usability for operational analysis.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 3.5 | 184 | 644 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing FEMA (09/26/22, 08/23/23, 08/04/24, 12/27/24 letters) COR3 (08/12/22, 08/11/23, 09/01/23, 08/27/24 letters) for Self-Performed Work for Genera generation projects. Finalize outline for White Paper as requested by Maria Sanchez Bras (Genera). Review and analyze Genera's Inter Company Agreement.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing FEMA and COR3 documentation for Self-Performed Work for Genera generation projects. Discuss Self-Performed Work and Genera's Inter Company Agreement with Christian Torres (Genera). Start drafting outline for White Paper as requested by Maria Sanchez Bras (Genera).
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Review and comment on email sent by Miguel del Valle (S&L) and Joel Pantojas (Genera) regarding additional request for information to be sent to proponent as agreed with Genera.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.75 | 184 | 322 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Josue Sanchez and Michael Silva from GeneraPR to review available operations reports related to fuel consumption and power generation. The meeting focused on validating data sources. Attendees: GeneraPR: Josue Sanchez, Michael Silva DCMC: Marc Maceira
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed reports shared by Josue Sanchez (Genera) related to fuel consumption and power production for the different power plants in order to generate the report required by the T&D OMA.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.75 | 184 | 138 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Report Development Continuation (1:15 PM – 2:00 PM) Continued working on the fuel's consumption report for the fuels department, now adding Costa Sur and Aguirre.
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Power Production and Fuel Consumption Report Preparation (11:00 AM – 12:30 PM) Began drafting the power production and fuel consumption report for the fuels department using data provided by Josue Sanchez from GeneraPR. The report focuses on consolidating critical metrics related to fuel usage and power generation across power plants. The initial draft includes San Juan and Palo Seco.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR - Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jesus Cintron (Genera) and Rafael Calderon (DCMC) to discuss Contract Management tasks, role and next steps within the project management team.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to provide an update on the client's need for staffing and project's status. The participants were Barry Scanlon (DCMC), Mike Merritt (DCMC), Lauren Wells (DCMC), Jack Darnall (Lemoine).
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Review FEMA and COR3 documentation for Self-Performed Work for Genera generation projects.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2 | 184 | 368 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units (Peakers RFP) - Proposal Clarifications discussion with Proponent (Solar Turbines) and Maria Sanchez Bras, Jesus Cintron, Joel Pantojas, Jorge Sanchez, Fernando Ortiz (Genera) Miguel del Valle (S&L) Rafael Pabon (CDM Smith). During this virtual meeting the Proponent clarified the remaining items (over 12) regarding the revised proposal they submitted on 01/27/2025.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 3 | 184 | 552 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units (Peakers RFP) - Proposal Clarifications discussion with Proponent (Solar Turbines) and Maria Sanchez Bras, Jesus Cintron, Joel Pantojas, Jorge Sanchez, Fernando Ortiz (Genera) Miguel del Valle (S&L) Rafael Pabon (CDM Smith). During this virtual meeting the Proponent clarified over 12 items regarding the revised proposal they submitted on 01/27/2025.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.25 | 184 | 230 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Prepare for Proposal Clarification call with Proponent and Genera at 9:00 am.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.25 | 184 | 230 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Operations Data Meeting (4:00 PM – 5:15 PM) Held a meeting with GeneraPR stakeholders to discuss the operational data needed to generate compliance reports. The discussion covered data sources, responsible stakeholders, and reporting processes to ensure all necessary information is properly captured and aligned with compliance requirements. Attendees: GeneraPR: Hector Vazquez, William Rios, Josue Sanchez, Miguel Cruz, Daniel Hernández DCMC: Marc Maceira
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.75 | 184 | 506 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Compliance Report Review (9:45 AM – 12:30 PM) Began reviewing compliance reports shared by Josue Sanchez from GeneraPR. The focus was on understanding the reporting structure and data requirements to ensure compliance with regulatory obligations.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2 | 184 | 368 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended BESS Check In meeting with Genera project managers. During the meeting it was discussed the BESS project status and next steps. DCMC provided an update about Procore training. Participants were: Gabriel Perez (CDM Smith), Lauren Wells (DCMC), D Alexander Gonzalez (DCMC), Alejandro Maymi (Genera), Mike Shawriski (S&L).
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended strategy call with Jesus Cintron (Genera) and Mike Merritt (DCMC) to discuss org chart and strategy with the two candidates that are been considered for program coordinator.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with Mark Merritt, Kelly George and Rick Patterson (DCMC) regarding Self-Performed Work for Genera generation projects.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2.5 | 184 | 460 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Proposal Clarifications call with Proponent and Maria Sanchez Bras, Jesus Cintron, Joel Pantojas, Joaquin Quinoy, Jorge Sanchez, Fernando Ortiz (Genera) Ginnell Torres (DCMC subcontractor) Miguel del Valle (S&L) Rafael Pabon (CDM Smith). Post meeting with Jesus Cintron and Joel Pantojas.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.25 | 184 | 46 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Proposal Clarifications call with Proponent and Maria Sanchez Bras, Jesus Cintron, Joel Pantojas, Joaquin Quinoy, Jorge Sanchez, Fernando Ortiz (Genera) Ginnell Torres (DCMC subcontractor) Miguel del Valle (S&L) Rafael Pabon (CDM Smith)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Preparation for Genera generation projects Self-Performed Work Meeting with Mark Merritt, Kelly George and Rick Patterson (DCMC).
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Begin drafting minutes for the Proposal Clarifications meetings held between Genera (María Sánchez Brás, Jesús Cintrón, Joel Pantojas, Jorge Sánchez, Fernando Ortiz. Miguel del Valle & Mike Kuckzynski S&L) Rafael Pabón CDM Smith) Ginnell Torres (DCMC subcontractor) Mitsubishi and RG Engineering on 02/10.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Discussion with Jesus Cintron (Genera) regarding multiple generation items such as New Generation Amendment and Self Performed Work.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Weekly Meeting preparation. Discussed weekly procurement processes updates and slides with Saul Falcon and Ginell Torres (DCMC). Reviewed Special Projects slide.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.75 | 184 | 138 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Maria Sanchez and Alejandro Maymi DCMC: Mark Merritt, D'Alexzander Gonzalez, Rafael Calderon, Victor Maldonado, Jose Ralat, Pedro Cabrera, Sheila Torres, Roberto Bosch, Marc Maceira and Shellsea Maysonet (independent contractor not DCMC).
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 184 | 138 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Weekly Status Meeting (10:00 AM - 10:45 AM) Participated in the weekly client status meeting with GeneraPR to review ongoing project statuses and critical items. Attendees: GeneraPR: Alejandro Maymi, Maria Sanchez DCMC: Mark Merritt, Roberto Bosch, D'Alexander Gonzalez, Sheyla Torres, Shellsea Maysonet, Ginel Torres, Marc Maceira, Esther Rohena, Jose Ralat, Rafael Calderon Integrum: Jorge Aponte, Carlos Gonzalez
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.25 | 184 | 46 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Core Applications Separation Daily Meeting (6:00 PM – 6:15 PM) Participated in the daily status meeting to review pending items and roadblocks related to the Core Applications Separation project. Discussions included updates from all stakeholders to ensure alignment on the project timeline and resolution of outstanding tasks. Attendees: GeneraPR: Maria Sanchez, Hector Vazquez, Yamaris Castro LUMA: Jim Seibert, Efrain Aguila, Manisha Shah Accenture: Andy Quanch, Chandra Sekhar DCMC: Marc Maceira
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Operations Data & Reporting Transition Meeting (4:00 PM – 5:00 PM) Held a meeting to discuss the required reports GeneraPR must generate to comply with the OMA (Operations & Maintenance Agreement). Key outcomes included plans to prepare an inventory of reports with their respective frequencies, deadlines, and responsible stakeholders. Attendees: GeneraPR: Hector Vazquez, Vladimir Scutt, Josue Sanchez, Jean Gonzalez, Michael Silva, Maria Sanchez, Hiram Medero DCMC: Marc Maceira
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Operations Data Reports Review (2:30 PM – 4:00 PM) Reviewed fuel data reports provided by GeneraPR to identify the required fields for preparing reports on fuel consumption and power generation by power plants. This will support compliance and operational reporting needs related to OMA.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Meeting (8:00 AM – 9:00 AM) Attended a status meeting with GeneraPR to review pending items and roadblocks for launching Genera Connect in their cloud environment. The client requested security certificate and domain information to the development team to move forward with the application setup. Attendees: GeneraPR: Jean Gonzalez, Elba Rodriguez, Michael Silva Integrum: Jorge Aponte, Carlos Gonzalez, Aldwin Pagan DCMC: Marc Maceira
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended call with Jack Darnall (Lemoine) and Mark Merritt (DCMC) to discuss the safety manual next steps and discuss the draft email that will be sent to Genera advising them on next steps to follow on revising the safety manual and updating the program.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR - Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Michael Merritt (DCMC) to discuss staffing and interview status. We went over the spreadsheet to select candidates for each of the positions, based on the interviews that have been held.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Drafted email to Ricardo Pallens (Genera) regarding our proposal for the construction safety manual program revision and support. The email included steps to follow and our proposal on creating a new program that follows PR law and Genera's culture and values.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in the Document Control weekly meeting for BESS and Peakers. The participants were Gabriel Perez (CDM Smith), Rafael Pabon (CDM Smith), Franklyn Colmenares (CSA), and Enrique Laya (CDM).
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Genera PM for the BESS and Peaker project. The participants were Gabriel Perez (CDM Smith), Rafael Pabon (CDM Smith) and German Ojeda (NFE).
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss staffing and interview update, as well as PMO update overall. The participants were Jack Darnall (Lemoine), Michael Merritt (DCMC), Lauren Wells (DCMC), AJ (DCMC).
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Call with Nyah Medina (DCMC) to discuss interviews and coordination regarding availability.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin reviewing COR3's findings regarding Genera's Federal Fundings Management SOPs
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with Jose Ralat and D'Alexzander Gonzalez (DCMC) re COR3 Monitoring of Genera's SOPs and FEMA's recent Project Amendment Obligations [671481 and 767305]
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Finalize reviewing COR3's findings regarding Genera's Federal Funding Management SOPs. Develop answers for the findings and send to Jose Ralat (DCMC).
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Timesheet Standup (3:30 PM – 4:00 PM) Participated in the Genera Connect Timesheet standup to review the latest updates on the system and provide feedback on functionalities and improvements. Discussions focused on user experience. Integrum: Jorge Aponte, Aldwin Pagan, Keyla Sierra DCMC: Marc Maceira, Eisha Mercader
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers meeting to discuss schedule and budget. The participants were Carlos Palomares (CDM Smith), Rafael Pabon (CDM Smith), German Ojeda (NFE), and Enrique Laya (CDM Smith).
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Prepare and draft meeting minutes for Grid Support Units RFP 205317. Share with Saul Falcon and Ginell Torres (DCMC) for input.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 3.5 | 184 | 644 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339' Continue reviewing Genera's FEMA Appeal package. Finalize analyzing Genera's Latent Damage Preliminary Assessment Report.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 184 | 184 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Drafted email to Ricardo Pallens (Genera) explaining the options and next steps for creating a security and safety program for Genera PR.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with Project Managers for BESS and Peaker project, Gabriel Perez (CDM Smith), and Rafael Pabon (CDM Smith).
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Review and comment on 739681 Power Generation EHP RFI Response as requested by Ricardo Pallens (Genera)
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 184 | 736 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Review, analyze and comment on Genera's PoP Extension Request, FEMA's Denial and begin reviewing Genera's Latent Damage Preliminary Assessment Report.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Financials Management Meeting (12:00 PM – 1:00 PM) Participated in the Procore Financials management meeting to discuss budget structure improvements aimed at enhancing financial tracking and reporting efficiency. Key discussion points included optimizing budget categories and streamlining financial workflows within Procore. Attendees: DCMC: Esther Rohena, Lauren Wells, Marc Maceira Procore: Breno Nasser
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Tesla BESS Risk Matrix Discussion (5:30 PM – 6:00 PM) Held a meeting with Jean Gonzalez from GeneraPR to review and discuss the risk matrix document related to Tesla BESS project documents. The discussion focused on identifying and mitigating potential risks associated with document access, security, and compliance. Attendees: GeneraPR: Jean Gonzalez DCMC: Marc Maceira
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss status in recruitment of candidates for the PMO team. We reviewed the staffing spreadsheet and updated it based on the interviews we have had. We also coordinated next steps on the program coordinator search. The participants were Mark Merritt, Michael Merritt, Barry Scanlon (DCMC), and Jack Darnall and Larry Hipsh (Lemoine).
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2 | 184 | 368 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended meeting with LUMA regarding interconnection studies for BESS and Peakers. The participants were Daniel Hernandez (Genera), Gabriel Perez (CDM Smith), Miguel del Valle (S&L), David Monasterios (LUMA), - David Monasterios (LUMA), Esther Serra (LUMA), Daniel Haughton (LUMA), Alfonso Baretty (LUMA), Zuleyka Perez (LUMA) and Rafael Pabon (CDM Smith).
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with Larry Hipsh (Lemoine) to compare notes on the interviews and make a decision regarding the positions and results of each interview.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Review and analyze FEMA appeal denial & FEMA RFI as requested by D'Alexzander Gonzalez (DCMC).
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Genera Generation Procurement alignment meeting with D'Alexzander Gonzalez, Saul Falcon (DCMC) Ginell Torres (DCMC subcontractor) and from Joel Pantojas, Eric Placencia and Ernesto Martinez (Genera)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Genera Generation Procurement alignment meeting with D'Alexzander Gonzalez, Saul Falcon and Ginell Torres (DCMC subcontractor).
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4.5 | 184 | 828 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Continue drafting RFC for Proponents.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Refinement of Risk Matrix for Tesla Document Access Process (BESS) (1:00 PM – 2:30 PM) Refined and expanded the risk matrix, ensuring that all potential risks, mitigation strategies, and access control measures were well-documented to align with GeneraPR's cybersecurity and compliance standards.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Development of Risk Matrix for Tesla Document Access Process (BESS) (9:30 AM – 11:00 AM) Worked on creating a risk matrix for the Tesla document access process related to Battery Energy Storage System (BESS) projects. The objective was to identify, categorize, and mitigate risks associated with data access and compliance requirements.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Core Apps Separation Executive Meeting (8:30 AM – 9:00 AM) Attended the executive status meeting to review updates on the Core Applications Separation project. Discussions included progress tracking, outstanding issues, and coordination between GeneraPR, Accenture, and DCMC. Attendees: GeneraPR: Hector Vazquez, Yamaris Castro, Maria Sanchez, Claudia Peña Accenture: Adrian Bazzini DCMC: Marc Maceira
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR -Deliverable 11 ¦ DR 4339 - Hurricane Maria - Review and analyze staffing and interview tracker.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Introductory meeting with Safety and Security Team from Genera, (Ricardo Pallens and Victor Rodriguez) and with Jack Darnall, Greg and Al Rocha (Lemoine). The meeting was coordinated to discuss the security and safety manual and how DCMC can support in cleaning up the manuals and updating them.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 184 | 92 | Yes | 25-144600 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with the BESS and Peaker project managers, Gabriel Perez (CDM Smith), Rafael Pabon (CDM Smith), Jesus Cintron (Genera), Joaquin Quinoy (Genera).
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.25 | 184 | 230 | Yes | 25-144600 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Attended Peakers Check In call to discuss schedule and status of the project. The participants were Rafael Pabon (CDM Smith), Miguel del Valle (S&L), Joaquin Quinoy (Genera) and German Ojeda (Genera).
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS Check In meeting with Joaquin Quinoy (Genera), Mike Sworoski (S&L), Gabriel Perez (CDM Smith), D Alexander Gonzalez (DCMC), Lauren wells (DCMC) and Larry Hipsh (DCMC).
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.75 | 184 | 322 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Begin drafting RFC for Proponents.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 3.5 | 184 | 644 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 205317 – Grid Support Units - Review RFP for evaluation criteria & weights and discuss with Jesus Cintron and Joaquin Quinoy (Genera). Review RFC sent by S&L; Follow up with Genera Legal re RFCs.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Maria Sanchez and Alejandro Maymi DCMC: Mark Merritt, Eisha Mercader, D'Alexzander Gonzalez, Rafael Calderon, Victor Maldonado, Jose Ralat, Pedro Cabrera, Sheila Torres, Roberto Bosch, Marc Maceira and Shellsea Maysonet (independent contractor not DCMC).
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 2 | 184 | 368 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Review 2 CFR 200.324, Genera's Procurement Manual regarding ICE. Review Black & Veatch MSA SOW. Develop and send correspondence to Jesus Cintron (Genera) regarding B&V SOW including the preparation of ICE.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2 | 184 | 368 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Tesla Document Access Diagram Development (2:00 PM – 4:00 PM) Began working on the Tesla documentation access request process to ensure compliance and data integrity for Battery Energy Storage System (BESS) projects. The diagram aims to provide a structured framework for controlling access and securing sensitive documentation related to Tesla BESS initiatives.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 184 | 184 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Weekly Status Meeting (10:00 AM – 11:00 AM) Participated in the weekly status meeting with GeneraPR and DCMC teams to discuss project updates, outstanding tasks, and upcoming deadlines. Attendees: GeneraPR: Maria Sanchez, Alejandro Maymi DCMC: Mark Merritt, D’Alexander Gonzalez, Roberto Bosch, Jose Ralat, Esther Rohena, Eisha Mercader, Shellsea Maysonet, Ginell Torres, Marc Maceira, Sheila Torres, Victor Maldonado Integrum: Jorge Aponte
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 184 | 276 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review Mock Cutover Status (8:30 AM – 10:00 AM) Reviewed the mock cutover to address pre-production issues for the February 28, 2025 production cutover. Focus areas included resolving missing vendor data, GL upload challenges due to accounting string issues and CVR violations, data cleansing delays, and patching overruns on the production server.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 5 of the Mitigation plan
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 167 | 167 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue work with CCL Tracker integrate the available information regarding Cost Estimate, Scope of Work, RFP, Contracts and Invoice of Critical Components. 4:00 pm - 5:00 pm
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue work with CCL Tracker integrate the available information regarding Cost Estimate, Scope of Work, RFP, Contracts and Invoice of Critical Components. 1:00 pm - 3:00 pm
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consultant Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process. 3:00 pm - 4:00 pm
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 4 | 167 | 668 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue work with CCL Tracker integrate the available information regarding Cost Estimate, Scope of Work, RFP, Contracts and Invoice of Critical Components. 8:00 am - 12:00 pm
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 5 of the Mitigation plan.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 4 of the Mitigation plan
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Contact Carlos Paez from Mitsubishi LTA to verify Cost Installation Cost of Critical Components GT Compressor Wash and GT Fully Bladed Rotor. 8:00 am - 8:30 am
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 167 | 250.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the weekly meeting with CPM, I focused on reviewing Critical Components priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion. 11: 00 am
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables. 1:00 pm - 1:30 pm
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 167 | 417.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Work with CCL Tracker integrate the available information regarding Cost Estimate, Scope of Work, RFP, Contracts and Invoice of Critical Components. 8:30 am - 11:00 am
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 3 | 167 | 501 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue work with CCL Tracker integrate the available information regarding Cost Estimate, Scope of Work, RFP, Contracts and Invoice of Critical Components. 8:30 am - 11:00 am
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 4 of the Mitigation plan.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 3 of the Mitigation plan
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Verify equipment acquired under PO 106028 and PO 102673. Because are component included into Critical Components Lists and need determine if additional RFP is necessary. 2:30 pm - 4:30 pm
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Coordinate a field visit with GENERA Jorge Sanchez to gather information regarding the necessary elements to complete the SOW for the installation of Overhead Crane. 1:00 pm - 1:30 pm
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Coordinate a field visit with GENERA Jorge Sanchez to gather information regarding the necessary elements to complete the SOW for the installation of 4kV Switch Gear. 8:30 am - 9:00 am
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Weekly meeting with participation from B&V: Tim Delaney, DCMC Pedro Cabrera. The discussion focused on reviewing fuel efficiency priorities, providing status updates, identifying next steps, metrics, challenges, and deadlines as part of the ongoing efforts to optimize performance and prepare for the next milestone. 12:00 pm - 12:30 pm
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the weekly meeting with B&V, I focused on reviewing fuel efficiency priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 167 | 417.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Updating this: Using the available information, such as the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components, I have developed a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA. 9:00 am - 11:30am
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Work on TO-01 for contract 107015 and share it with the provider SERPAGA for signature completion. 8:00 am - 8:30 am
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Critical Component meeting wirth DCMC Roberto Bosh and D'Alexzander Gonzáles to discuss the current status of the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components. Additionally, the meeting will cover the developed KPIs to determine the course of action regarding project amendments with FEMA. 1:30 PM - 2:30 PM
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 3 of the Mitigation plan.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 2 of the Mitigation plan
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 167 | 668 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Verify equipment acquired under contracts requisition 281156, 291464, 291252. Component is included into Critical Components List and determine if installation cost was included. 8:00 am - 12:00 pm
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 167 | 668 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Verify equipment acquired under contracts requisition 293150, 283220, 284592. Component was included into Critical Components List and need to determine if installation cost was included. 12:30 pm - 4:30 pm
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 2 of the Mitigation plan.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractor all day long, took pictures and generated my daily report
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue develop a PREB response regarding to Critical Components current status based of the response of the vendors and data avilable Asset Suite develop
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez Bras and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation. 10:00 am - 11:00 am
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 167 | 668 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Verify equipment acquired under contracts 106304 and 105992. Because are component included into Critical Components Lists and need determine if additional RFP is necessary. 12:30 pm - 4:30 pm
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1 | 167 | 167 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue develop a PREB response regarding to Critical Components current status based of the response of the vendors and data avilable Asset Suite develop 11:00 AM - 12:00 PM
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 6 | 167 | 1002 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report on Procore
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractor all day long, took pictures and generated my daily report
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Verify Milestone and Payments Schedule of contracts 102570 and 106735 to determine if necessary, contact the vendors.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.5 | 167 | 250.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Contact each vendors awarded contracts 104794, 104792, 104082 and verify the current status of the orders.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera Deliverable 11-DR 4339-Genera Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consultant Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process. 1:30 - 2:30 pm
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Based of the response of the vendors and data avilable Asset Suite develop PREB response regarding to Critical Components current status.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Contact each vendors awarded contract 106735 and verify the current status of the orders.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - CPM Jose Prado, Victor Aviles, Victor Alvarez DCMC Pedro Cabrera and GENERA Joaquin Quinoy. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables. 10:00 am - 11:00 am
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractor all day long, took pictures and generated my daily report
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Completed certifications required by Genera while working on the Procore application and completed Project Manager (Health and safety) certification. duration 2hr Project management and safety certification.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 4 | 167 | 668 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Verify that the CE develop by CPM contains the information according to the request before submitting it for detailed review by our Project Formulation team. Additionally, extract the proposed cost information from CPM for the following components. Hydrogen Cooler Turning Gear Assembly Generator Breaker 13kV Fill Shutoff Valves Trip Shutoff Valve Nozzle valve Leakage valve Generator Breaker 13kv EDI system 8:00 am - 12:00 am
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 3 | 167 | 501 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Contact each vendors awarded contracts 107015, 106280, and 104794 to verify the current status of the orders.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables. 1:00 pm - 1:30 pm
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1 | 167 | 167 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review RFP 221016 to determine if components qty are according to the actual requiered.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria /Traveled from the Genera Office in Hato Rey to Home in Guaynabo .
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 3 | 167 | 501 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / At the Genera Office went over the contract and Scope of work... as per project manager.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | 0.75 | 167 | 125.25 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Travel to Vega Baja Site for Genera PR Project
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.75 | 167 | 292.25 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Completed Site Survey Supervision with Sargent & Lundy.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ Travel from home in Guaynabo to Central San Juan for a Site Survey with Sargent & Lundy.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Traveled from Vega Baja Site to Genera Office Office in Hato Rey
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ Went over Procore Management Trainig 3.5 hours long
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 3.5 | 167 | 584.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components, develop a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Weekly meeting with participation from B&V: Tim Delaney, DCMC Pedro Cabrera. The discussion focused on reviewing fuel efficiency priorities, providing status updates, identifying next steps, metrics, challenges, and deadlines as part of the ongoing efforts to optimize performance and prepare for the next milestone. 12:00 pm - 12:30 pm
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the weekly meeting with B&V, I focused on reviewing fuel efficiency priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 3.5 | 167 | 584.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Work on Develop for requisition 297468 Evaluation criteria considering in the proposal evaluation Compliance with Required Services – Technical capacity to provide A&E services without gaps that could impact the project. Experience and Technical Capabilities – Experience in similar projects, certifications, and regulatory compliance. Approach and Methodology – Evaluation of the work plan, project management, and use of advanced tools (BIM, 3D, etc.). Cost and Efficiency – Competitiveness and transparency in the cost structure. Participation of Local and MWBE Businesses (6 pts) – Inclusion of women-owned and local businesses in Puerto Rico.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ Went over project coordination, team discussions, project Dismantling plan, Hazardous Material handling and disposal contract.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | 4.5 | 167 | 751.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Visited Genera facilities 12th floor Suite 1200. Introductory meeting with Gabriel Perez (Genera) for training purposes, Discussed and review the assigned tasks for Vega Baja substation.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 3.5 | 167 | 584.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Verify in Asset Suite the CPA created by end user for 106735 102570 106280 106777 106560 107789 105644 107315 106367 106333 100975 104732 to determine if GENERA end user complete the task, to determine whether the deliveries and payments have been completed 1:00 pm - 4:30 pm
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the plan proposed by CPM for delivering the pending SOWs for the critical components in order to identify possible delays. 8:00 am - 10:00 am
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez Bras and Alejandro Maymi Roda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation. 10:00 am - 11:00 am
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.5 | 167 | 250.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Verify in Asset Suite the CPA created by end user for 104792 107015 104794 104082 106805 to determine if GENERA end user complete the task, to determine whether the deliveries and payments have been completed 11:00 am - 12:30 pm
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4.5 | 167 | 751.5 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Went over training material, team building, meeting the team
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ travel from the Genera PR office in Hato Rey to Home in Guaynabo .
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 5 | 167 | 835 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ While I was at the Genera Office I met the team, downloaded information, went over the contracts deliveries
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ travel from Guaynabo Home to Genera Office in Hato Rey.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | 0.5 | 167 | 83.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11-¦ DR 4339 - Hurricane Maria- Took safety certification with Gustavo Vasquez (Genera) to enter the facilities for Vega Baja substation learning the requirements of the field.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera Deliverable 11-DR 4339-Genera Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consultant Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process. 10:00 am - 11:00 am
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 167 | 250.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Complete a Dashboard Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2 | 167 | 334 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components, develop a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA. 8:00 am - 10:00 am
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 167 | 250.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop response for NEPR-MI-2021-0014 based on Critical Components current status
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 4 | 167 | 668 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Work on Develop for requisition 297468, the following items. Requisition form Evaluation criteria Independent Cost Analysis (ICE) Attachment 4 Exhibit E – Price Proponent form.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Pedro Cabrera and Roberto Bosch. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables. 1:00 pm - 1:30 pm
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 4 | 167 | 668 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Critical Component - Contact each end user of each awarded contract 107989 104792/ 107015 PO 100975 104794 PO 106367 PO 106560 104082 102570 106633 107315 PO 105644 106805 106280 106735 107049 104732 107154 106777 to assist to complete Notice to Proceed for the awarded contract. 8:00 am - 12:00 pm
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11-DR 4339 Preparation for the weekly meeting with B&V, I focused on reviewing fuel efficiency priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 3 | 167 | 501 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Verify in Asset Suite the payments and delivery dates for PO 106650, 105644, 107315, and 106777 to inform the GENERA end user Herminio Arroyo, to determine whether the deliveries and payments have been completed 2:00 pm - 5:00 pm
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 3.5 | 167 | 584.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Continue complete a Dashboard Using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with FEMA. 8:00 pm 10:00 pm
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Identified the end user of each awared contract 107989 104792/ 107015 PO 100975 104794 PO 106367 PO 106560 104082 102570 106633 107315 PO 105644 106805 106280 106735 107049 104732 107154 106777 to verify if Notice To Proceded was completed. 1:00 pm - 5:00 pm
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Weekly meeting with participation from B&V: Tim Delaney, DCMC Pedro Cabrera. The discussion focused on reviewing fuel efficiency priorities, providing status updates, identifying next steps, metrics, challenges, and deadlines as part of the ongoing efforts to optimize performance and prepare for the next milestone. 12:00 pm - 12:30 pm
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Preparation for the weekly meeting with B&V, I focused on reviewing fuel efficiency priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components, develop a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA. 1:00 pm 5:00 pm
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 167 | 250.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Complete a Dashboard Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 - Identified NME Components actual status of scope of work (SOW) and CE purpose to request amendment to FEMA. Based on the actual status of the SOW and CE, the information to be added in the amendment request can be determined. 7:30 am - 12:00 pm
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 6 of the Mitigation plan
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Follow up on pending matters: P3A Contracts 16 Contracts under Review V&B RFI to Costa Azul Fuel Efficiency BFP TO 01 Serpaga Contract 107015 9:00 am - 10:00 am
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2 | 167 | 334 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Continue Reviewed and verify Contracts: 107963 107035 107032 107031 107030 106933 related to Critical Components 11:00 am - 1:00 pm
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Alejandro Maymi Roda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation. 10:00 am - 11:00 am
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 167 | 250.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Using the available information on NME and Critical Components, develop a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA. 8:30 am 10:00 am
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Reviewed and verify Contracts: 107963 107789 107777 107706 107701 107689 107291 107190 107127 related to Critical Components 1:00 pm - 5:00 pm
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2.5 | 167 | 417.5 | Yes | 25-144600 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 PROCORE working with Contract 107015 Aguirre Air Heater Basket possible strategies and approaches to efficiently generate, track, and manage contracts, including leveraging the OCR tool for automated data extraction, linking contracts with change orders, and ensuring compliance with project requirements 10:00 am -12:30pm
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 3 | 167 | 501 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Reviewed and validated overall status of NME and Critical Components focusing on tracking the Cost Estimates, Scope of Work,, as well as assessing the deliverables to ensure readiness for its. 9:00 am- 12:00 pm
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2.5 | 167 | 417.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Training session provide a comprehensive overview of the Task Order (TO) generation process. Genera: Carlos Negrón show me through the key steps, best practices, and system functionalities required to efficiently create, manage, and track TOs. 3:00 pm - 5:30 pm
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2.5 | 167 | 417.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Continue reviewed and validated overall status of NME and Critical Components focusing on tracking the Cost Estimates, Scope of Work,, as well as assessing the deliverables to ensure readiness for its. 12:30 pm - 3:00 PM
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 3 | 167 | 501 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Continue summarize the findings from the contract verification in the spreadsheet to discuss with Genera: Joaquin Quinoy.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1.5 | 167 | 250.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Reviewed and validated overall status of NME and Critical Components focusing on tracking the Cost Estimates, Scope of Work,, as well as assessing the deliverables to ensure readiness for its.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11-DR 4339 Weekly meeting with participation from B&V: Emilio Cabrera, Tim Delaney, DCMC Pedro Cabrera. The discussion focused on reviewing fuel efficiency priorities, providing status updates, identifying next steps, metrics, challenges, and deadlines as part of the ongoing efforts to optimize performance and prepare for the next milestone. 12:00 pm - 12:30 pm
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11-DR 4339 Preparation for the weekly meeting with B&V, I focused on reviewing fuel efficiency priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2.5 | 167 | 417.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Continue summarize the findings from the contract verification in the spreadsheet to discuss with Genera: Joaquin Quinoy.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2 | 167 | 334 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 - Identified NME Components actual status of SOW and CE purpose to request amendment to FEMA 8:00 am - 10:00 am
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 4 | 167 | 668 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Reviewed and verify Contracts: 106735 102570 106280 106777 106560 107789 related to Critical Components 1:00 pm - 5:00 pm
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1.5 | 167 | 250.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Summarize the findings from the contract verification in the spreadsheet to discuss with Genera: Joaquin Quinoy 5:00 pm - 6:30 pm
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2.5 | 167 | 417.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Reviewed and verify Contracts: 104792 107015 104794 104082 106805 related to Critical Components 10:00 am - 12:30 pm
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 167 | 83.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 - Identified Critical Components actual cost increment respect Project FEMA Version to share with Roberto Bosch DCMC. 12:00 pm - 12:30 pm
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1.5 | 167 | 250.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Continue Work on populating the tracker for NME, Critical Components, and Fuel Efficiency to insert the revisions made in the document "NME, Critical Component, Fuel Efficiency - GeneraPR - Projects to Formulate Discussion." 8:30 am - 10:00 am
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 - Collaborated with Roberto Bosch from DCMC, to discuss Critical Components and NME status regarding to SOW & CE. 11:00 am - 12:00 pm
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 167 | 167 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez Bras, Jesus Cintron and Alejandro Maymi Roda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation. 10:00 am - 11:00 am
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 2.5 | 167 | 417.5 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Continue Work on populating the tracker for NME, Critical Components, and Fuel Efficiency to insert the revisions made in the document "NME, Critical Component, Fuel Efficiency - GeneraPR - Projects to Formulate Discussion." 1:00 pm - 3:30 pm
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 2 | 167 | 334 | Yes | 25-144600 | PREPA Genera Deliverable 11 DR4339 Critical Component - Reviewed and validated overall status of NME and Critical Components focusing on tracking the Cost Estimates, Scope of Work, as well as assessing the deliverables to ensure readiness for its. 3:30 pm- 5:30 pm
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (4:00pm-4:30pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90217419 for TO#2 July 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-10:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (2h)
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (1:00pm-3:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761. Training portal Tesla compulsory curse completion. Completing and commenting on the available curses on Tesla Training Portal (Tesla Workforce Management). Title - Megapack 2 Operations: Service and Maintenance Awareness for System Owners (2nd of 6 required curses). Compulsory training in order to participate from upcoming site visits and to gain knowledge on how the system works and how to provide service to the system.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (3:00pm-4:00pm) (location: City View @ Guaynabo PR) Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting. Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team)
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 164 | 410 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (10:00am-12:30pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761. Invoice review from Milestone #1_PO of MVT for Aguirre, Cambalache, Costa Sur, Palo Seco, Vega Baja and Yabucoa. Working on Schedule 14A-1 based on contract requirements. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (4:30pm-6:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761. Training portal Tesla compulsory curse completion. Completing and commenting on the available curses on Tesla Training Portal (Tesla Workforce Management). Title - Megapack 2 Operations: Software Controls Awareness for System Owners (1srt of 6 required curses). Compulsory training in order to participate from upcoming site visits and to gain knowledge on how the system works and how to operate.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 3.5 | 164 | 574 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (12:30pm-4:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Schedule 14A-1 and schedules related to training material based on contract requirements. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 - Tesla Confidential Information- Meeting with the following participants: Franklyn Colmenares (CSA), Gabriel Sepúlveda(CDM), Fernando Ortiz (Genera), Rafael Calderón (DCMC) and Glorimel Torrado (DCMC). This meeting was to discuss requirements related to confidential information sharing and NDA procedures.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-9:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 3 | 164 | 492 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (9:00am-12:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761. Invoice review from Milestone #1_PO of MVT for Aguirre, Cambalache, Costa Sur, Palo Seco, Vega Baja and Yabucoa. Working on Schedule 14A-1 based on contract requirements. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (7:30am-8:30am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (3:00pm-4:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- Genera & Tesla Weekly project management meeting. Contract 106761. Project development based on deliverable schedule. Review pending action items. Meeting between Tesla team (Carlos Melendez, Jefferson Silver, Laura Miglietti, Keyur Javiya, Howen Lim and Qais Feroz) , CSA (Franklyn Colmenares), CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczinski, Vincent Skochdopole, Reinaldo Romero, Nelson Rosado.) and DCMC (Rafael Calderon).
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (4:00pm-5:00pm) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, Jaca & Sierra, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (1:00pm-3:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761. Invoice review from Milestone #1_PO of MVT for Aguirre, Cambalache, Costa Sur, Palo Seco, Vega Baja and Yabucoa. Working on Schedule 14A-1 based on contract requirements. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 4 | 164 | 656 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (8:30am-12:30pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90208243 for TO#2 March 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (3:30pm-5:30pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90217419 for TO#2 July 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (1:30pm-3:30pm) (location: City View @ Guaynabo PR)- Pre-Intervention Review RFI - Working with Black & Veatch Contract #217733_2024-G00207 and TO#5_Invoice# 6200582_ Dec 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Invoice Approved.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 4.5 | 164 | 738 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (8:30am-1:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- Siemens Kick-Off meeting with project management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Meeting between Siemens Energy team , CMD Smith PM team (Rafael Pabon, Juan Mendoza), Sargent & Lundy (Mike K., Miguel del Valle) Genera (Jesus Cintron, Joaquin Quinoy, Kevin Futch, Ricardo Pallens), CSA (Franklyn Colmenares) and DCMC (Rafael Calderon, Frances Vallejo).
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (3:30pm-5:30pm) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review in preparation to Kick-off Meeting for Peakers Costa Sur. Developing PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main Siemens Contract 106588, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (2:30pm-3:30pm) (location: City View @ Guaynabo PR) - Contract Management Activities- Peakers Check-In meeting with project management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Meeting between Siemens Energy team , CMD Smith PM team (Rafael Pabon, Juan Mendoza), Sargent & Lundy (Mike K., Miguel del Valle) Genera (Jesus Cintron, Kevin Futch, Ricardo Pallens), CSA (Franklyn Colmenares) and DCMC (Rafael Calderon, Frances Vallejo).
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (1:30pm-2:30pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team , CMD Smith PM team (Gabriel Sepulveda), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Frances Vallejo).
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-9:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 164 | 410 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 Pre-Intervention Review: Preparing RFI related to invoice format and pre-requirements for payment process.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting [In-person] Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team), For Genera Team (Alejandro Maymi, Maria Sanchez and Jesus Cintron)
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (9:00am-10:00am) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review in preparation to Kick-off Meeting for Peakers Costa Sur. Developing PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main Siemens Contract 106588, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 164 | 656 | Yes | 25-144600 | • Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (8:00am-12:00pm) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review in preparation to Kick-off Meeting for Peakers Costa Sur. Developing PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main Siemens Contract 106588, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 164 | 656 | Yes | 25-144600 | • Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (8:00am-12:00pm) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review in preparation to Kick-off Meeting for Peakers Costa Sur. Developing PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main Siemens Contract 106588, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (1:30pm-2:30pm) (location: City View @ Guaynabo PR) Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting. Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team)
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:30am-9:30am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (2:30pm-4:30pm) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review based on RFI submitted by Rafael Pabon requesting clarification on the official Share Website for all Siemens Submittals. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 3.5 | 164 | 574 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (9:30am-1:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Schedule 14A-1 and schedules related to training material based on contract requirements. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#10710 (5:30pm-6:30pm) (location: City View @ Guaynabo PR) Preparing email communication related to TESLA contract requirements to (Jefferson Silver and Elizabeth Arentsen from TESLA) answering questions related to pending delivery items, insurance contract requirements, Change orders and Specs clarification.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2.5 | 164 | 410 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (1:30pm-4:00pm) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review based on RFI submitted by Rafael Pabon (CDM) requesting clarification on the official Share Website for all Siemens Submittals. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (4:30pm-5:30pm) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:15am-9:15am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2.75 | 164 | 451 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (9:15am-12:00pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Schedule 14A-1 and schedules related to training material based on contract requirements. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 Weekly meeting with the following participants: Franklyn Colmenares (CSA), Elizabeth Arentsen (Tesla), Jefferson Silver (Tesla), Jorge Quintana, Carlos Palomares (CDM), Gabriel Sepúlveda(CDM), Rafael Calderón (DCMC) and Glorimel Torrado (DCMC). This meeting was to discuss deliverables for milestone 1, missing insurance documentation, change orders and invoice RFI.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (4:00pm-5:30pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Schedule 14A-1 and schedules related to training material based on contract requirements. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3 | 164 | 492 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (1:00pm-4:00pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90201791 for TO#1 Feb 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 4 | 164 | 656 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (8:30am-12:30pm) (location: City View @ Guaynabo PR)- Pre-Intervention Review RFI - Working with Black & Veatch Contract #217733_2024-G00207 and TO#7_Invoice# 6200524_ Sept 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Invoice Approved.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (7:30am-8:30am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 3.25 | 164 | 533 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PW#10710 (3:00pm-6:15pm) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review based on RFI submitted by Rafael Pabon requesting clarification on the official Share Website for all Siemens Submittals. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PW#10710 (1:00pm-3:0pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based on RFI submitted by Gabriel Perez (CDM) requesting clarification on training Schedules and suppliers responsibilities based on contract information (Milestone #1). Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.75 | 164 | 123 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (10:00am-10:45am) (location: City View @ Guaynabo PR) Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting [In-person] Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team) Genera (Maria Sanchez and Alejandro Maymi)
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-10:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (2h)
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.75 | 164 | 287 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (10:45am-12:30pm) (location: City View @ Guaynabo PR)- Pre-Intervention Review RFI - Working with Black & Veatch Contract #217733_2024-G00207 and TO#7_Invoice# 6200524_ Oct 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Invoice Approved.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#10710 (1:00 pm-3:00 pm) (location: City View @ Guaynabo PR) - Continue working with Siemens Energy Contract #00106588 and Deliverable Schedule review based on RFI submitted by Rafael Pabon (CDM Smith) requesting clarification on the official Share Website for all Siemens Submittals. Also clarifying information for Master Schedule updates to include updated NTP information. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PW#10710 (11:00am-12:30pm) (location: City View @ Guaynabo PR) - Siemens Energy Contract #00106588 and Deliverable Schedule review based on RFI submitted by Rafael Pabon (CDM Smith) requesting clarification on the official Share Website for all Siemens Submittals. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (10:00am-11:00am) (location: City View @ Guaynabo PR) Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting [In-person] Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team) (1h)
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-10:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (2h)
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PW#10710 (3:00pm-4:30pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA Contract 106761 and Deliverable Schedule review based on RFI submitted by Gabriel Perez (CDM) requesting clarification on training Schedules and suppliers' responsibilities based on contract information. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (3:00pm-4:00pm) (location: City View @ Guaynabo PR) Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2.5 | 164 | 410 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PW#10710 (12:00pm-2:30pm) (location: City View @ Guaynabo PR) - Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based on RFI submitted by Gabriel Perez (CDM) requesting clarification on training Schedules and suppliers responsibilities based on contract information. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2.25 | 164 | 369 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PW#10710 (8:15am-10:30am) (location: City View @ Guaynabo PR) - Contract Management Activities Siemens Energy Contract #00106588 and Deliverable Schedule review based on RFI submitted by Rafael Pabon (CDM Smith) requesting clarification on the official Share Website for all Siemens Submittals. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW10710 (4:00pm-4:30pm) (location: City View @ Guaynabo PR) Virtual meeting - with CSA Franklyn Colmenares. TESLA- Jorge Quintana and CDM - Gabriel Perez. Contract Management Meeting -Tesla First Payment Milestone - Discussing contractual schedules related to Deliverables #1 and Deliverable #2. Also developing strategies to maximize training material, Site visits to the Plants and system operators involvement .(.5h)
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (10:30am - 11:30am) Meeting in City View DCMC Office with Mike Kuczynski (Sargent & Lundy) and Glorimel Torrado (DCMC) to verify invoice progress and clarify information from Tesla contract.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (7:15am-8:15am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW10710 (2:30pm-3:00pm) (location: City View @ Guaynabo PR) Virtual meeting - with CSA Franklyn Colmenares. Contract Management Meeting - TESLA - Discussing pending RFI on invoice template provided by TESLA and Pos pending quantities clarification on MVT units. Also reviewing Training Schedules milestones as stablished by contract.(.5h)
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (3:00pm-4:00pm) (location: City View @ Guaynabo PR) Virtual meeting - Genera & Tesla Weekly Project Meeting. Discussing deliverables and action items related to contract execution and progress report. Participants (Tesla- Jorge Quintana, Qais Feroz, Carlos Melendez, Laura Miglietti) (Genera- Rafael Calderon , Sargent and Lundy - Mike Kuszynski, Nelson Rosado, Reinaldo Quinones) (CSA, Franklyn Colmenares) (1h)
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (4:30pm-5:30pm) (location: City View @ Guaynabo PR) Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (1:00pm-3:00pm) (location: City View @ Guaynabo PR) - TESLA_Contract 106761 deliveries review in preparation for upcoming invoices related to milestone#1. This delivery includes PO for MVT Equipment for all related sites. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2h)
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (10:30am-12:30pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90225874 for TO#11 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2h)
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (4:00pm-4:30pm) (location: City View @ Guaynabo PR) Virtual meeting - Genera PR: Tesla Operations & Controls Training Demo. Discussing deliverables related to training requirements, syllabus, schedules and clarifying general questions related to Training process . Participants (Tesla- Jorge Quintana, Qais Feroz, Carlos Melendez, Laura Miglietti) (Genera- Rafael Calderon , Sargent and Lundy - Mike K., Nelson Rosado, Reinaldo Quinones) (CSA, Franklyn Colmenares) (.5h)
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-9:30am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1.5h)
2025-02-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (9:30am-10:30am) (location: City View @ Guaynabo PR) Virtual meeting - CDM Invoice Review Status update. Discussing pending RFI on invoices related to PW9510 with Genera (Maria Sanchez, Jesus Cintron, Alejandro Maymi), DCMC (Rafael Calderon, Jose Ralat) and CDM (Jose Arsuaga) (1h)
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (5:00pm-5:30pm) (location: City View @ Guaynabo PR) Virtual meeting between Genera (Jesus Cintron) and DCMC (Rafael Calderon, Frances Vallejo) New Roll Guidance - Contract Manager BESS - Peakers. Discussing scope of work and responsibilities of new roll proposal for Rafael Calderón (DCMC) as Senior Contract Manager for Genera's federal contracts. (.5h)
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-10:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (2h)
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 4 | 164 | 656 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (1:00pm-5:00pm) (location: City View @ Guaynabo PR) - TESLA_Contract 106761 deliveries review in preparation for upcoming invoices related to milestone#1. This delivery includes PO for MVT Equipment for all related sites. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (4h)
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2.5 | 164 | 410 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 (10:00am-12:30pm) (location: City View @ Guaynabo PR) - Contract Management Review - Siemens Energy Contract #00106588 and Deliverable Schedule development. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2.5h)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW10615 (10:30am-12:30pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90225874 for TO#11 Jan 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2h)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW10615 (9:00am-10:00am) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90223791 for TO#11 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (1h)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-9:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3 | 164 | 492 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (2:30pm-5:30pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90217354 for TO#1 Jul 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Invoice was approved without pre-intervention and quantities need to be consolidated in future invoices. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (3h)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (1:30pm-2:30pm) (location: City View @ Guaynabo PR) BESS Check-In Meeting to discuss progress status, action items from all project areas and outstanding issues that need special attention from the team. Reviewing deliverables, schedules, certifications and general contract information in order to aligned all project efforts according to scope. (Meeting Participants - CDM Smith, Genera, CSA Group and DCMC. (1h)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (1:00pm-1:30pm) (location: City View @ Guaynabo PR) Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (.5h)
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (10:00am-10:30am) (location: City View @ Guaynabo PR) Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting [In-person] Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team) From Genera (Maria Sanchez and Alejandro Maymi) (.5h)
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3.25 | 164 | 533 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (1:45pm-5:00pm) (location: City View @ Guaynabo PR) - TESLA_Contract 106761 deliveries review in preparation for upcoming invoices related to milestone#1. This delivery includes PO for MVT Equipment for all related sites. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (3.25h)
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.25 | 164 | 41 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (1:30pm-1:45pm) (location: City View @ Guaynabo PR) Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting. Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team)
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3 | 164 | 492 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (10:00am-1:00pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90223791 for TO#11 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (3h)
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (8:00am-10:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (2h)
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (4:30pm-5:00pm) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting (.5h)
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (4:00pm-4:30pm) Pre-Intervention Meeting to review the contract requirements for invoicing under Tesla project. In this meeting participates Gabriel Pérez Sepúlveda (CDM Smith Project Manager), Jefferson Silver (Tesla Project Manager), Rafael Calderón (DCMC Contract Manager), Glorimel Torrado (Pre-Intervention Team) and Franklyn Colmenares (CSA Group BESS Project Coordinator). DCMC is going to facilitate the team an excel spreadsheet with deliverables and invoicing requirements as discussed in the meeting for better understanding of this project.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3 | 164 | 492 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (1:00pm-4:30pm) (location: City View @ Guaynabo PR) - TESLA_Contract 106761 deliveries review for Cambalache Site in preparation for upcoming invoices related to milestone#1. This delivery includes PO for MVT Equipment for all related sites. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (3h)
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (10:30am-12:30pm) (location: City View @ Guaynabo PR) - TESLA_Contract 106761 deliveries review in preparation for upcoming invoices related to milestone#1. This delivery includes PO for MVT Equipment for all related sites. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2h)
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (8:30am-10:30am) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90223791 for TO#11 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2h)
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (7:30am-8:30am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_ Hurricane Maria_PW#9510 (2:00pm-2:30pm) Meeting to discuss: "Siemens Deliverables Discussion (DCMC-CDM)" Reviewing Contract Schedules and Milestones with Project Manager from CDM - Rafael Pabon and from DCMC - Rafael Calderon and Glorimel Torrado.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_ Hurricane Maria_PW#9510 (900am-930am) Meeting to discuss CDM_TO#11 eligibility for management invoice. In this meeting: Rafael Calderón, Glorimel Torrado, José Ralat, Roberto Bosch and Esther Rohena. Review of invoice and Project worksheet. DCMC is going to request CDM to explain in detail the task related to management to verify if they are in accordance with FEMA's 90-91
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria (12:00pm-1:00pm) Meeting with Procore team and DCMC to discuss progress according to the needs of the company for the program and the expectations for Finance and Budgeting. In this meeting participate Lauren Kennedy, Breno Nasser (Procore), and Mark Merritt, Rafael Calderón, Glorimel Torrado, Esther Rohena, Marc Maceira and Lauren Wells (DCMC).
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (1:00pm-2:00pm) (location: City View @ Guaynabo PR) Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, Jaca & Sierra, Tesla and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (7:30am-9:00am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, Jaca & Sierra, Tesla and CAPTA. In preparation for Genera and DCMC Weekly meeting (1.5h)
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3 | 164 | 492 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (2:30pm-5:30pm) (location: City View @ Guaynabo PR) - TESLA_Contract 106761 deliveries review in preparation for upcoming invoices related to Milestone#1. This delivery includes PO for MVT Equipment for all related sites. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (3h)
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (10:00am-11:30am) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90206382 for TO#6 April 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Invoice was approved without pre-intervention and quantities need to be consolidated in future invoices. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (1.5h)
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (9:30am-10:00am) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90216215 for TO#1 Jun 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Invoice was approved without pre-intervention and quantities need to be consolidated in future invoices. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Invoice sent for approval (.5h)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#9510 (8:30am-10:00am) (location: City View @ Guaynabo PR) Compliance RFI Review - Sargent and Lundy Contract #2024-G00200 and TO#6_Invoice# 18300332_ Sept 2024. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (1.5h)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (7:30am-8:30am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, Jaca & Sierra, Tesla and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 164 | 328 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#9510 (10:30am-12:30pm) (location: City View @ Guaynabo PR) Compliance RFI Review - Sargent and Lundy Contract #2024-G00200 and TO#6_Invoice# 18300332_ Sept 2024. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2h)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (4:00pm-5:00pm) (location: City View @ Guaynabo PR) - TESLA_Contract 106761 deliveries review in preparation for upcoming invoices related to milestone#1. This delivery includes PO for MVT Equipment for all related sites. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (1h)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 164 | 410 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (1:00pm-3:30pm) (location: City View @ Guaynabo PR) - Compliance Review CDM Smith Invoice #90223791 for TO#11 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (2.5h)
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 164 | 82 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW#9510 (3:30pm-4:00pm) (location: City View @ Guaynabo PR) Internal DCMC Meeting (Teams) with Glorimel Torrado to discuss CDM TO#11 Eligibility Tasks based on Contract TO#11. (.5h)
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (7:30am-8:30am) (location: City View @ Guaynabo PR) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. In preparation for Genera and DCMC Weekly meeting (1h)
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 4 | 164 | 656 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (1:00pm-5:00pm) (location: City View @ Guaynabo PR) - Pre-Intervention Review CDM Smith Invoice #90224258 for TO#6 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Invoice was approved without pre-intervention and quantities need to be consolidated in future invoices. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (4h)
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (11:00am-12:30pm) (location: City View @ Guaynabo PR) - Pre-Intervention Review CDM Smith Invoice #90215469 for TO#6 Ago 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Invoice was approved without pre-intervention and quantities need to be consolidated in future invoices. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (1.5h)
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 164 | 164 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (10:00am-11:00am) (location: City View @ Guaynabo PR) Virtual meeting New- GENERA & DCMC- Weekly Status Pre-Meeting [In-person] Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team) From Genera (Maria Sanchez and Alejandro Maymi) (1h)
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 164 | 246 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria_PW9510 (8:30am-10:00am) (location: City View @ Guaynabo PR) - Pre-Intervention Review CDM Smith Invoice #90224258 for TO#6 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Invoice was approved without pre-intervention and quantities need to be consolidated in future invoices. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. (1.5h)
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.75 | 149 | 111.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María- Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and Marc Maceira from DCMC, and Shellsea Maysonet (MZC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Review Tesla Invoices for Palo Seco, Aguirre, Costa Sur, Cambalache, Vega Baja and Yabucoa. All of this invoices were review in a working session with Rafael Calderón (DCMC) to review quantities, all information provided, deliverable (PO and K-1) in compliance with contract and schedule.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_PW#9510 - Review invoices signed by Jesús Cintrón (Genera) and prepare final packages. Also, request CPA creation. This invoices corresponds to CDM TO2, Black and Veatch and Sargent and Lundy.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2.75 | 149 | 409.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA in preparation for Genera and DCMC Weekly meeting for today @3pm. Also, call with José Ralat (DCMC) and email requesting updates on payments for presentation and updates to Power Point presentation to be used in meeting.
2025-02-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.75 | 149 | 111.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#2, Invoice #18308442. RFI review. Verify all deliverables and responses to the RFI. Prepare final package and invoice for Jesús Cintrón (Genera) signature, request CPA and update excel Pre-Intervention tracker.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3.5 | 149 | 521.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO02_Inv90216344_June2024. Review formal RFI for this invoice, complete Pre-Intervention process on this invoice. Review narratives for administrative tasks. Final invoice was requested to CDM so it can be sent to Genera for Signature.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 149 | 298 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 Pre Intervention Review for Black & Veatch Puerto Rico, PSC., Contract #2024-G00207, TO#5, Invoice #6200523_September2024 . Preparing master excel to review the invoice and identify mistakes. Read contract and task order, also verify the invoice rates with the contract rates. Review task provided and identify missing information. Complete invoice review and send for Genera signature.
2025-02-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 149 | 298 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO02_Inv90201814. Complete Pre-Intervention process on this invoice. Review narratives for administrative tasks. Prepare invoice for genera signature. Send invoice on Adobe to Jesús Cintrón (Genera) for final approval.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Start Pre-Intervention Review for CDM Smith TO02_Feb2024_Inv90216337. Continue reviewing contract and Task Order. Review rates for employees in this invoice and verify narratives according to SOW.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María Internal Meeting with Rafael Calderón (DCMC) - Pre-intervention Tasks Update and Review. Reviewing pending action items from all vendors, Pending RFIs, Pending CPA and Email Follow-ups.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 149 | 298 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Continued Pre-Intervention Review for CDM Smith TO02_Feb2024_Inv90216337. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and verify narratives according to SOW.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Working session with Rafael Calderón (DCMC) to review and discuss Jaca y Sierra Change Orders, Main contract and Task Orders. This responds to change orders out of task order timeframe.
2025-02-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Start Pre-Intervention Review for CDM Smith TO02_Feb2024_Inv90216337. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and verify narratives according to SOW.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-RFI Development | Direct-PA | Development of RFI to client/applicant for initial or additional grant/financial documentation or information | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO02_June2024_Inv#90216344. Prepare formal RFI with all the missing information on this invoice. This email contains bullets with summarized information and excel document with entries marked in color and including comments that need attention and clarification.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 4 | 149 | 596 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO02_June2024_Inv#90216344. Continue pre intervention process, this invoice has hours that need to be split and is missing project and plant. I fill most of the information available on the missing parts. Also prepare the compliance sampling and cost by plant report.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 Pre Intervention Review for Black & Veatch Puerto Rico, PSC., Contract #2024-G00207, TO#5, Invoice #6200523. Invoice discussed with Rafael Calderón (DCMC), RFI review and request final invoice. Also, prepare last excel labor notes.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.25 | 149 | 37.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria Review Sargent and Lundy two invoices that labor notes were requested by José Ralat (DCMC) to prepare RFR's. I review the signed invoice and send José Ralat the attachments requested.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Meeting with Rafael Calderón (DCMC) to discuss pending action items on Siemens contract, we also review the RFI that I am preparing for CDM Invoice #90216344 and review Jaca y Sierra invoices. This was a working session on B&V_419955_Invoice 6200523_Sep24_RFI.
2025-02-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors and review all the pending invoices to be worked on today.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Start Pre-Intervention Review for CDM Smith TO02_June2024_Inv#90216344. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and identify discrepancies in numbers. Also, prepare email to request final invoice signed in PDF for this TO.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria - Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena and Glorimel Torrado. Also, Shellsea Maysonet (MZC); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Continue Pre-Intervention Review for CDM Smith TO01_July2024_Inv 06 contractor RFI response to continue validating narratives on this invoice. Also, in this invoice I identified all the narratives that corresponds to Administrative Expenses to be divided on RFR process reimbursement. Additionally, I prepare a response for CDM invoice email that request information for A&E and Administrative Tasks definitions.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Continue Pre-Intervention Review for CDM Smith TO01_July2024_Inv 06 contractor RFI response to continue validating narratives on this invoice. Also, in this invoice I identified all the narratives that corresponds to Administrative Expenses to be divided on RFR process reimbursement.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria - José Ralat DCMC request 7 invoices Labor Notes in excel from Sargent & Lundy. During this time, I review the invoice package and confirm quantities, identify the final document and send the documents by email. Also, I verify for José Ralat CPM Invoice #7187 for status update.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.25 | 149 | 335.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Continue Pre-Intervention Review for CDM Smith TO02_June2024_Inv#90216344. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and identify discrepancies in numbers. Also, prepare email to request final invoice signed in PDF for this TO.
2025-02-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.25 | 149 | 37.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Finished Pre-Intervention Review for CDM Smith TO01_July2024_Inv 06_90217354. Prepare final package, send invoice for Genera Signature and confirm this invoice with CDM.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Continue Pre-Intervention Review for CDM Smith TO01_July2024_Inv 06. Review contractor RFI response and start validating narratives on this invoice.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.25 | 149 | 37.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#1, Invoice #18308441_Oct2024. Review invoice signed by Genera and developed an email for CPA request to Franklyn Colmenares (CSA). Update Pre-Intervention tracker with this invoice completed.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 1.75 | 149 | 260.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. In preparation for Genera and DCMC Weekly meeting today and on Monday. This task includes requesting updates on payments to José Ralat (DCMC) and direct discussions with Rafael Calderón (DCMC) for updates on presentation and on tracker (invoicing),
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.25 | 149 | 37.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Continue Pre-Intervention Review for CDM Smith TO01_July2024_Inv 06 contractor RFI response to continue validating narratives on this invoice.
2025-02-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.75 | 149 | 111.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María- Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and Marc Maceira, and Shellsea Maysonet (MZC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Weekly meeting with the following participants: Franklyn Colmenares (CSA), Elizabeth Arentsen (Tesla), Jefferson Silver (Tesla), Jorge Quintana, Carlos Palomares (CDM), Gabriel Sepúlveda(CDM), Rafael Calderón (DCMC) and Glorimel Torrado (DCMC). This meeting was to discuss deliverables for milestone 1, missing insurance documentation, change orders and invoice RFI.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#1, Invoice #18308441_Oct2024. Continue with deliverables review to complete the compliance review. Prepare final package and invoice for Jesús Cintrón (Genera) signature. Send the invoice for signature and update excel Pre-Intervention tracker.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3 | 149 | 447 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Pre Intervention Review for CDM Smith TO01_April2024_Inv 3. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and identify discrepancies in numbers. Compliance report and cost per plant report. For this invoice I identify administrative expenses. I complete the pre intervention process and prepare invoice for signature.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, and B&V.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 Pre Intervention Review for Black & Veatch Puerto Rico, PSC., Contract #2024-G00207, TO#7, Invoice #6200477. Verify final backup information received and invoice. Prepare email with labor notes and final invoice signed for CPA creation. This was sent to Frances Adames Santiago (Genera).
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María Internal Meeting with Rafael Calderón (DCMC) - Pre-intervention Tasks Update and Review. Reviewing pending action items from all vendors, Pending RFIs, Pending CPA and Email Follow-ups. (.5h)
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 Pre Intervention Review for Black & Veatch Puerto Rico, PSC., Contract #2024-G00207, TO#7, Invoice #6200477. Reviewing deliverables for the Compliance Sampling tab, request final backup information to Emilio Cabrera and Irama Vargas (B&V).
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 4 | 149 | 596 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Start Pre-Intervention Review for CDM Smith TO01_June2024_Inv#90226117. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and identify discrepancies in numbers.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339- Hurricane María Update information for José Ralat (DCMC) with requests for status on pending invoices from Sargent & Lundy.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and Marc Maceira. Also, Shellsea Maysonet (MZC); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Start Review RFI response for CDM Smith TO01_July2024_Inv 06, I review their responses in excel spreadsheet and by email narrative. Call between Jose Arsuaga (CDM), Rafael Calderón and Glorimel Torrado (DCMC) to discuss findings and I prepare and email to reply for pending action items on this RFI.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 Review contract documentation to identify documents required for change orders and requirements. Discussion with Rafael Calderón (DCMC) to a previous formal response with all the information requested and to clarify the 3 pending action items on Siemens.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Review contract documentation to identify information to respond clarification request by Tesla regarding submittals and invoices.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 2 | 149 | 298 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to all the RFI's responses received in the weekend and new invoices updates in preparation for meeting. This task includes updating presentation with numbers provided by José Ralat (DCMC) of invoices already paid to vendors and DCMC invoicing.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 149 | 298 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (2:00pm-4:00pm) Start Pre-Intervention Review for CDM Smith TO01_July2024_Inv 06. Review contract and Task Order verifying expenses category. Continue pre intervention process for this invoice and submit RFI to CDM team.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. Review all information and RFI answers new from contractors. Also, update provided to Sargent and Lundy invoice pre intervention process.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1.25 | 149 | 186.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 (8:45am-10:00am) - Siemens Energy Contract #00106588 review and discussion with Rafael Calderón (DCMC) to answer Request for Information in order to provide guidance of platform to upload documents. This includes contract review to verify requirements to upload information. Platform to be used is Procore.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | 0.25 | 149 | 37.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria (10:45am-11:00am) Pre-Intervention Tracker Update - Editing presentation as requested in the meeting by Mark Merritt and D' Alexzander González (DCMC). Send the presentation updated to D' Alexzander to be used on final meeting on Tuesday with Genera client.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (8:15 am -8:45 am) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18315396_Nov2024. Review invoice signed and prepared package. Final package was sent to Franklyn Colmenares (CDM) for CPA.
2025-02-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.75 | 149 | 111.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María (10:00am - 10:45am) Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and Marc Maceira from DCMC, and Shellsea Maysonet (MZC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María (10:30am - 11:30am) Meeting in City View DCMC Office with Mike Kuczynski (Sargent & Lundy) and Rafael Calderón (DCMC) to verify invoice progress and clarify information from Tesla contract.
2025-02-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (2:00pm-4:30pm) Review important pending action items for today with Rafael Calderón and review Tesla contract to identify information needed for clarification emails. During this time review all the new information from contractors.
2025-02-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2 | 149 | 298 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (8:00am-10:00am) Review important pending action items for today with Rafael Calderón (DCMC) and review Tesla RFI responses. Read and discuss with Rafael Calderón the PW10710 assigned to this project and the amounts.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.75 | 149 | 260.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (10:45am -12:30pm) Pre-Intervention for Tesla, contract review and deliverables. Also, identify pending action items with Rafael Calderón (DCMC) for Siemens, CDM, Tesla, Jaca & Sierra, Sargent & Lundy and Critical components.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria (8:30am-10:00am) Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors and work with Rafael Calderón (DCMC) to include a new column that reflects invoices already paid by Genera additional to invoices approved in pre intervention, in preparation for Genera and DCMC Weekly meeting.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.75 | 149 | 111.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María (10:00am - 10:45am) Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and Marc Maceira. Also, Shellsea Maysonet (MZC); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3.5 | 149 | 521.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (1:30pm-5:00pm) Start Pre-Intervention Review for CDM Smith TO01_July2024_Inv 06. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and identify discrepancies in numbers.
2025-02-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (1:00pm-1:30pm) Pre-Intervention Review for CDM Smith review all invoice received by email (8) and identify one with correct format to be started.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (1pm -130pm) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18315396_Nov2024. Continue with deliverables review to complete the compliance review.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (9:30am -12:00pm) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18315396_Nov2024. Review RFI response for this Invoice. Review all deliverables provided to complete the compliance review.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 2.5 | 149 | 372.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (1:45pm-4:15pm) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18315396_Nov2024. Continue with deliverables review to complete the compliance review. Prepare final package and invoice for Jesús Cintrón (Genera) signature. Send the invoice for signature and update excel Pre-Intervention tracker. Also, review correspondence from Tesla projects, support Rafael Calderón (DCMC) with pre intervention invoice review Tesla and update pending action items for other invoices.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María (8:00am - 9:30am) Pre-intervention Tasks Update and Review. Reviewing pending action items from all vendors, Pending RFIs, Pending CPA and Email Follow-ups. Update tracker with invoices completed for meeting.
2025-02-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.25 | 149 | 37.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria (1:30pm - 1:45pm) Genera Pre-Meeting with participation from DCMC: Jose Ralat, Roberto Bosch, Rafael Calderon, Pedro Cabrera, Glorimel Torrado and Esther Rohena; to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client on next Monday.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#14, Invoice #18315397_November2024. This task consists in reviewing RFI responses from contractor, review notes and determine that this TO is nonfederal. I prepare an email referring this invoice to Joaquín Quinoy (Genera) to complete the evaluation.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_(4:00pm-4:30pm) Pre Intervention Meeting to review the contract requirements for invoicing under Tesla project. In this meeting participates Gabriel Pérez Sepúlveda (CDM Smith Project Manager), Jefferson Silver (Tesla Project Manager), Rafael Calderón (DCMC Contract Manager), Glorimel Torrado (Pre-Intervention Team) and Franklyn Colmenares (CSA Group BESS Project Coordinator). DCMC is going to facilitate the team an excel spreadsheet with deliverables and invoicing requirements as discussed in the meeting for better understanding of this project.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 4 | 149 | 596 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_ (8:00am-12:00pm) Pre-Intervention Continue contract Review for Tesla project. Reading contract document and preparing pre intervention notes for invoicing under Aguirre contract.
2025-02-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 3 | 149 | 447 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_(1230pm-330pm) Pre-Intervention Continue contract Review for Tesla project. Reading contract document and preparing pre intervention notes for invoicing under Aguirre contract. This task is in preparation for meeting with Tesla team.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.25 | 149 | 186.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (10:15am-11:30am) Pre-Intervention Review for CDM Smith Invoice #90206292_TO6_March2024 review of old invoice as requested. Read Task Order associated with invoice and line items that are in compliance with federal requirements and Scope of Work.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria (12:00pm-1:00pm) Meeting with Procore team and DCMC to discuss progress according to the needs of the company for the program and the expectations for Finance and Budgeting. In this meeting participate Lauren Kennedy, Breno Nasser (Procore), and Mark Merritt, Rafael Calderón, Glorimel Torrado, Esther Rohena, Marc Maceira and Lauren Wells (DCMC).
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (1pm-230pm) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#14, Invoice #18315397_November2024. Review deliverables for this invoice that were sent on RFI to contractor. Final review and prepare package for signature.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.25 | 149 | 186.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (7:45am -9:00am) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#4, Invoice #18315394_November2024. Review RFI response for this Invoice. Prepare final package and invoice for Jesús Cintrón (Genera) signature. Send the invoice for signature and update excel Pre-Intervention tracker.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (2:30pm-3:30pm) Meeting with Rafael Calderón (DCMC) and Rafael Pabón (Genera) to discuss Siemens contract and pending action items. Suppliers document registration list should be received on or before Feb 13 with detailed timeframes. Two invoices from Cambalache Dique were identified by Rafael Pabón that needs action from us to send Manuel Cortés (Genera) signature.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (900am-930am) Meeting to discuss CDM_TO#11 eligibility for management invoice. In this invoice participates DCMC Rafael Calderón, Glorimel Torrado, José Ralat, Roberto Bosch, D'Alexzander Gonzalez and Esther Rohena. In the meeting the team discussed the invoices review process for the contract # 102049 for vendor CDM Smith, pending to be submitted in an RFR under the Maria PW 9510. These invoices are related to A&E services provided by the vendor for the BESS and Peakers projects. Also, we discussed the invoices pre-intervention process, invoices pending to be approved, RFIs sent to the vendor and already paid.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.75 | 149 | 111.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (9:30am-10:15am) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#14, Invoice #18315397_November2024. This task consists in read Task Order, prepare master excel for pre intervention, review scope of work to confirm is aligned with TO and Compliance Sampling tab. Also, generate RFI for missing deliverable items.
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_ (3:30pm-4:30pm) Pre-Intervention Contract Review for Tesla project. Reading Attachment C (Payment Schedule) with milestones for Cambalache, Costa Sur, Vega Baja, Yabucoa, Aguirre and Palo Seco.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.25 | 149 | 186.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (3:45pm-5:00pm) Meeting with Rafael Calderón (DCMC) to discuss CDM TO11_December2024. In this meeting we review the Project Report (FEMA 90-91) and evaluate project management task that were included in invoice TO11 with allowable scope and costs according to FEMA obligation for Project 662947 PW10615.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.75 | 149 | 260.75 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (7:45am-9:30am) Continue Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#4, Invoice #18315394_November2024. Review pending scopes and prepare RFI for this invoice and submit request to contractor.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.25 | 149 | 186.25 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (10:30am-11:45am) Continue Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18315396_November2024. Prepare compliance sampling tab and Review scope of work for line items for RFI.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria (9:30am-10:30am) Pre-Intervention Tracker Review to identify pending RFI responses from Sargent and Lundy. Prepare report with invoice numbers and RFI sent date and send it to Mike Kuzinsky (Sargent and Lundy) by email.
2025-02-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 3.5 | 149 | 521.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (12:15pm-3:45pm) Continue Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18315396_November2024. Continue working with compliance sampling tab and Review scope of work for line items for RFI. Request for information was sent to request deliverables to complete compliance sampling review.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (11am -12pm) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#4, Invoice #18315394_November2024. Review RFI answers and start with employee rates review. The employee rates must match with Task Order positions rates for each employee.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | 1 | 149 | 149 | Yes | 25-144600 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María (10:00am - 11:00am) Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and Marc Maceira from DCMC, and Shellsea Maysonet (MZC); and María Sánchez (Genera) to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 0.5 | 149 | 74.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#4, Invoice #18315394_November2024. Review deliverables for this invoice. This consist of entering to each task identified and verify the submitted information to match what is detailed in the description. This completes the compliance review stage.
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 4 | 149 | 596 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (12:30 pm -4:30pm) Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#4, Invoice #18315394_November2024. Review RFI answers and start with employee rates review. Also request CPA for TO5_Nov2024 to Franklyn Colmenares (CDM).
2025-02-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | 1.5 | 149 | 223.5 | Yes | 25-144600 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 (8:30am-10am) Continue Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#5, Invoice #18315395_November2024. Review RFI answers and all deliverables. Prepare invoice for Genera (Jesús Cintrón) for signature.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 148 | 148 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - full day in San Juan for genera meetings and work
2025-02-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reports Specialist | Miller, Kylie | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | 1 | 122 | 122 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurricane Maria. Kylie Miller set up and executed a conference call with Jack Darnall of Lemoine and ExecHub to discuss excel help to better manage the task order $ breakdowns. Kylie Miller then shared documents and got an agreement in place with ExecHub.
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 111 | 111 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - travel day back to birmingham from San Juan
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 111 | 111 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - Travelled early AM from Birmingham to San Juan
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 32.21 | 32.21 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - uber from city view plaza to hotel
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 30.97 | 30.97 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - uber ride for jack darnall from work to dinner
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 26.39 | 26.39 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - Uber for jack darnalll to the office from the hotel
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 18.09 | 18.09 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria uber ride for jack darnall from hotel to work
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 14.04 | 14.04 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - uber for jack darnall to genera office from city view plaza
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 8.74 | 8.74 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - uber ride for jack darnall from the airport
2025-02-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 7.54 | 7.54 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - uber to the airport, Deducted the $7.81 reservation fee
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Project Executive | Darnall, Jack | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for |  | 6.98 | 6.98 | Yes | 25-144600 | Genera PR/Deliverable 11/Program Management/DR4339-Hurrican Maria - uber ride to the hotel after dinner
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management |  | Training Specialist | Ormonde, Heather | Project Management-Travel | Direct-PA | Travel necessary for project management |  | 860 | 860 | Yes | 25-144600 | The e-credit mentioned is from when we had originally planned the trip in Jan 2025 and was rescheduled. This is for the flight out to visit the Genera team.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management |  | Training Specialist | Ormonde, Heather | Project Management-Travel | Direct-PA | Travel necessary for project management |  | 292.51 | 292.51 | Yes | 25-144600 | I stayed in Courtyard Marriott Miriam San Juan while visiting the Genera team. Max lodging plus fee and tax $292.51 Billable; $77 Non-Billable.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management |  | Training Specialist | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities |  | 148 | 148 | Yes | 25-144600 | Travel from SJU Puerto Rico to OKC home of record. After a full day of meeting with the Genera team. Due to travel delay I did not arrive home until 130 AM on 2/20, Reason for Full day PerDiem.
2025-02-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management |  | Training Specialist | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities |  | 111 | 111 | Yes | 25-144600 | Travel from home of record to Puerto Rico Flight/Travel time OKC 430AM CST to SJU Arrived 530 PM UTC due to a Delay in flight and missed connection total Air travel time 11hrs.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management |  | Training Specialist | Ormonde, Heather | Project Management-Travel | Direct-PA | Travel necessary for project management |  | 13.93 | 13.93 | Yes | 25-144600 | Travel from from a Meal stop on the way to the Airport.
2025-02-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management |  | Training Specialist | Ormonde, Heather | Project Management-Travel | Direct-PA | Travel necessary for project management |  | 13.53 | 13.53 | Yes | 25-144600 | Travel from Genera office stopped for Meal on way to the airport. 250 Av Luis Munoz Rivera, San Juan, PR 00918, US 1248 PM Airport 5803 Calle Tartak, Carolina, PR 00979, US 104 PM
11387.25
[11 empty] | Construction mgmt cost= | 11387.25

## March
Entry Date | Client | Proj level1 | Proj level2 | Proj level3 | Client title | Asset | Task | Task Group | Task Description | Activity Type | Hours | Column1 | Activity Rate | Activity Extended | Billing Rate | Line Billable | Invoice Number | Narrative
2025-03-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 3 | 184 | 552 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Request documentation for the Trailers, installation quote, electrical, equipment, Personal Protection Equipment in the Vega Baja Project by Genera in Puerto Rico.
2025-03-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued task of managing Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 6 of the Mitigation plan
2025-03-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 6 of the Mitigation plan
2025-03-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Identification | Direct-PA | Activities necessary for project identification (i.e., meetings, coordination, documentation request/review) | Time | 1.25 | 1.25 | 184 | 230 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Contact the Dueñas Trailer, Rod Roaders and other companies for offices trailer and materials needs in Vega Baja Genera Project.
2025-03-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Identification | Direct-PA | Activities necessary for project identification (i.e., meetings, coordination, documentation request/review) | Time | 4 | 4 | 184 | 736 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Site inspection, meeting with Herbert Guilbe of Genera. We continued to discuss the Security and Safety Manual created by Genera. Call with Gabriel Perez (DCMC Smith) to discuss Vega Baja Site. Follow Up with Duenas Trailers.
2025-03-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 7 of the Mitigation plan
2025-03-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 7 of the Mitigation plan
2025-03-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3.5 | 3.5 | 184 | 644 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Site inspection. Walk Inspection in Vega Baja Site to assess, document and evaluate the Health & Safety issue in site. Make a report with findings and recommendation.
2025-03-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 8 of the Mitigation plan
2025-03-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project we are doing the mitigation, this mitigation will last about 12 days for Lead Contamination. Today is DAY 8 of the Mitigation plan. Today we concluded with the Mitigation and the results were in, we concluded the initial lead mitigation plan, the lead was removed from the house tiles from the back.
2025-03-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- One on One meeting with Gabriel Perez BESS Sr. Manager to discuss Cambalache and Vega Baja. 75 % was to provide current status, concerns and priority items on Vega Baja, mainly the current contractor Homeca.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1 | 1 | 184 | 184 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Continuing Evaluate the EHS issue in the Vega Baja Site. Development of document for request in the next contract of EHS and Security.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.25 | 3.25 | 184 | 598 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Site inspection, Review and evaluate the vulnerability plan for Vega Baja Site. Meeting with Franklyn Colmenares (CSA) and Gilberto Sucre (DCMC) to discuss the EHS and Security for the next RFP process and projects.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Scope of Work Development | Direct-PA | Activities necessary to develop/document project's scope of work (any level) | Time | 3.75 | 3.75 | 184 | 690 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Evaluate the EHS issue in the Vega Baja Site. Development of document for request in the next contract of EHS and Security.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we continued working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days, today is day 1 of this detail.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we started working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days, today is day 1 of this detail.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | ¿PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Visited site Vega Baja to identify everyone is wearing accurate Proper PPE, made various walkthrough to see that on every time during the walkthrough everyone kept their PPE all times Perform Safety Audits (e.g., inspecting equipment, reviewing protocols). performed On-site inspections to identify hazards. Equipment and machinery inspections. Site audits for regulatory compliance. Meetings with management or staff on safety concerns. Join Homeca to install the Loto tags while identifying some hazards on the way while assisted Genera electricians who visit the site to assist.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | ¿ PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, this mitigation will last about 12 days for Lead Contamination, Installed Loto Verified the employees and site for Quality.
2025-03-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Vega Baja update with Nelson Soler QA/QC site supervisor. Nelson provided update on activities to date and priority items to focus on. Agreed to hold meeting Monday AM with staff on site including Jean - Safety & Security.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3.5 | 3.5 | 184 | 644 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Site inspection, at the Vega Baja Site. Make reports of Vega Baja and Cambalache Site for Franklyn Colmenares of CSA. Evaluate the Genera BSS: State Design Fire prevention system. Meeting with Franklyn Colmenares to discuss Vega Baja Site EHS Issues.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.75 | 1.75 | 184 | 322 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Site inspection, the Vega Baja Site. Attended by DCMC Jaime Pesquera, Gilberto Soto, and Frances Vallejo. Discussed the EHS and Security Issue. Conference call with Herminio Arroyo (Genera ) regarding Co2 cylinder in Vega Baja Site.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we started working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days, today is day 2 of this detail.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we continued working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days, today is day 2 of this detail.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | ¿ PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, this mitigation will last about 12 days for Lead Contamination, Installed Loto Verified the employees and site for Quality.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | ¿PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Visited site Vega Baja to identify everyone is wearing accurate Proper PPE, made various walkthrough to see that on every time during the walkthrough everyone kept their PPE all times Perform Safety Audits (e.g., inspecting equipment, reviewing protocols). performed On-site inspections to identify hazards. Equipment and machinery inspections. Site audits for regulatory compliance. Meetings with management or staff on safety concerns.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 0.25 | 225 | 56.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Vega Baja Site operation Update with Jaime Pesquera - DCMC Construction Manager.
2025-03-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Correspondence reading of Vega Baja activities for next week.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1 | 1 | 184 | 184 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Meeting with Gilberto Sucre (DCMC), Gilberto Soto (DCMC), Nelson Soler (CDSMITH), Jaime Pesquera (DCMC) in site about Safety, Security, Contract issues in Vega Baja Site.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we resumed working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days. Today is day 3 of this detail.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we started working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days. Today is day 3 of this detail.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations for the project, took pictures of work performed and generated my daily report. In this stage of the project we are, today the welded scrap metal was cut and removed doing the mitigation. Supervised the employees and site for quality. Assisted Genera crew from Palo Seco and Cambalache with the items removed from site.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations for the project, took pictures of work performed and generated my daily report. In this stage of the project we are, today the welded scrap metal was cut and removed doing the mitigation. Supervised the employees and site for quality. Assisted Genera crew from Palo Seco and Cambalache with the items removed from site.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Reviewed project related item: Luma/Genera MOU to be able to disconnect power and relocate communications on site, Additional Diesel transfer to Vega Baja Change Order, Reviewed Homeca first invoice for Compliance with contract requirements. Participants: Franklin Colmenares, Enrique Laya, Manuely Concepcion (Genera) and Gilberto Sucre (DCMC)
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting to coordinate R & R and Site Access procedures, review of previous incidents not acceptable to the Program. Goals set and follow up meeting will be held to finalize on Tuesday 3/11. Attendees Franklin Colmenares - CDM Smith, Gabriel Perez - CDM Smith, Jean P. Menay - DCMC. First to be used for Vega Baja and later on to the Program through all sites.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Vega Baja weekly construction meeting with Homeca for Demolition Project, to get update on Safety, RFI's, Submittals, Change Orders & Progress. Attendees Carirma Sanchez - Homeca, Nelson Soler & Manuely Concepcion - CDM Smith, and from DCMC Gilberto Sucre, Gilberto Soto, Jose Lopez, Jaime Pesquera.
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 0.75 | 225 | 168.75 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Vega Baja Continued site visit from morning agenda including visiting Co Work Office to potentially be used due to the site space limitations. Attendees Jaime Pesquera, Gilberto Soto, Jean Pierre Menay, Jose Lopez & Gilberto Sucre (All - DCMC).
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Sucre, Gilberto | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 35.21 | 0.7 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Site visit to inspect project, meeting to meet team and get status. Attendees Jaime Pesquera CM, Nelson Soler QA/QC, Gilberto Soto EHS and Jean Pierre Menay
2025-03-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 1.75 | 184 | 322 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended weekly meeting with Vega Baja team to discuss lead abatement update, demolition and overall site status. Participants: Jaime Pesquera (DCMC), Gabriel Perez (CDM), Gilberto Sucre (DCMC), Carisma Rodriguez (Homeca).
2025-03-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Preparing materials takeoff for the equipment and materials needed on the Vega Baja office trailer. For the small compound project area, we need a small trailer, quoting all necessary equipment & materials, chairs, tables, printer, internet for Vega Baja office trailer. Coordination Metting with Jean Pierre Menay (DCMC) & Ada Diaz (DCMC).
2025-03-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Project Management coordination meeting necessary for project manager Jose Lopez (DCMC), Frances Vallejo (DCMC) and Jean Pierre Menay (DCMC). We work with the coordination of the construction compound area, discussing the area available to install an office trailer on Friday 3/14/2025. Coordinate the equipment & materials necessary to start using the trailer office at the beginning of next week. Additionally, we coordinate the safety needed to protect the trailer office on the Vega Baja project.
2025-03-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.75 | 1.75 | 184 | 322 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Collect the information for the PPE necessary in the site. Visit to Vega Baja Site, safety inspection in the project.
2025-03-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we continued working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days, today is day 4 of this detail.
2025-03-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures of work performed and generated my daily report. In this part of the project, we started working with the hot cutting of the scrap metal and taking it out from the site in metal container trucks, we will be in this stage for about 5 days, today is day 4 of this detail.
2025-03-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures of work performed and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assited Genera crew from Palo Seco and Cambalache with the items removed from site.
2025-03-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures of work performed and generated my daily report. In this part of the project we are, today they continued removing and cutting welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assited Genera crew from Palo Seco and Cambalache with the items removed from site.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 3.5 | 167 | 584.5 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Work on quoting for Vega Baja office trailer. Obtain quotes for all necessary equipment & materials, chairs, tables, printer, internet, and coordinate delivery dates with equipment suppliers.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 1.75 | 167 | 292.25 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Vega Baja Plant. Attendees, Frances Vallejo (DCMC), Jose Lopez (DCMC), Jaime Pesquera (DCMC), Jean Pierre Menay (DCMC), Gilberto Soto (EHS), Nelson Soler (DCMC), Harry Del Valle (DCMC). Topics discussed, walkthrough Project Site, discussed scope of works, project needs, demolition areas & construction compound areas. Measured areas. Additionally discussed the removal of the steel beams to remove, protection of the PREPA electric transformer to remain. Safety & Quality compliance on site.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 3 | 167 | 501 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera PR Vega Baja Job Site initial visit and DCMC staff introduction. Meet with Jean Pier Menay, Nelson Soler, Gilberto Soto and Jaime Pesquera from DCMC. Project Site introduction and ongoing Demolition activities and scope of work resume.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 3.75 | 3.75 | 184 | 690 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Collect the information for the PPE necessary in the site. Coordinate offices trailer, power connection, evaluate the site. Meeting with Gilberto Sucre (DCMC) about the Vega Baja and Palo Seco Site Status and resources operation needed.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 2.75 | 2.75 | 184 | 506 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Collect the information for the PPE necessary in the Vega Baja site. Site inspection in Vega Baja Site. Meeting with Harry del Valle (DCMC), Nelson Soler (CD SMITH), Jaime Pesquera (DCMC), Frances Vallejo (DCMC) and Jose Lopez (DCMC) about project status, EHS opportunity, and demolition status.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project, we are doing the site scrap clean up and hot cutting. Also, people from Genera-PR came in to help us get their stuff out of the site. This week and the rest of the week we worked on all submittals and all the RFI's that needed to be completed or updated or moved in the system that were not submitted by the contractor.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project, we are doing the site scrap clean up and hot cutting. Also, people from Genera-PR came in to help us get their stuff out of the site. This week and the rest of the week we worked on all submittals and all the RFI's that needed to be completed or updated or moved in the system that were not submitted by the contractor.
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assited Genera crew from Palo Seco and Cambalache with the items removed from site
2025-03-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assited Genera crew from Palo Seco and Cambalache with the items removed from site, supervised installation from trailers and electric connection
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Coordination & quoting office trailer needs, meet with Eng. Jaime Gago with JR Contractor to Trailer Anchors wok needs. Request Portable bathrooms quote to Portosan for Vega Baja Construction Site - Javier Aviles, (Portosan).
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 2.5 | 167 | 417.5 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting on the Vega Baja site with the Demolition subcontractor, Carirma Sanchez, and Eduardo Ramos with Homeca Recycling to discuss the actions required.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 | 4 | 184 | 736 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Collect the information for the PPE necessary in the site. Vega Baja Site visit, inspection. Meeting with Gilberto Soto (DCMC), Carirma Sanchez (HOMECA) and Eduardo Ramos (HOMECA) about the site issues including Cylinder, Diesel Tank, Trailer, House in the project and status the project. Conference call with Isha Encarnacion (Duenas Trailers).
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 1.5 | 1.5 | 184 | 276 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Collect the information for the PPE necessary in the site. Vega Baja Site, conference call with Kevin Gonzalez (GENERA). Conference call with Gilberto Sucre and Jaime Pesquera (DCMC) about the Vega Baja Project by Status and next works.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the site scrap clean up and hot cutting. Also people from Genera-PR came in to help us get their stuff out of the site. This week and the rest of the week we worked on the all submittals and all the RFI's that needed to be completed or updated or moved in the system that were not submitted by the contractor.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the site scrap clean up and hot cutting. Also people from Genera-PR came in to help us get their stuff out of the site. This week and the rest of the week we worked on the all submittals and all the RFI's that needed to be completed or updated or moved in the system that were not submitted by the contractor.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Continue to-assist Genera crew from Palo Seco and Cambalache with the items removed from site,Dumpster with of stainless steel louvers from Units 1-1 and 1-2 Intake/Filter Rooms were transported to Homeca Recycling in Caguas.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assited Genera crew from Palo Seco and Cambalache with the items removed from site,Dumpster with of stainless steel louvers from Units 1-1 and 1-2 Intake/Filter Rooms were transported to Homeca Recycling in Caguas.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.75 | 1.75 | 225 | 393.75 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Worked with Project Team Franklyn Colmenares (CSA Group)., Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Jaime Pesquera (DCMC) and Nelson Soler (CDM Smith) identifying list of issues affecting the project stoppage: * Telecom Relocation * CO2 Tanks removal * Electrical Line * Land Authorization * Transformer Study * Diesel Removal Change Order * Oil Barrels removal * Fire Extinguishers * Acetylene Tanks. After draft response was discussed a 2nd letter from Homeca was received in relation to the work stoppage it was decided to re-evaluate the response.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Gilberto Sucre led discussions and fact-finding requests from DCMC field project team Jaime Pesquera and Jose Lopez in reference to Homeca's Stoppage Letter received on 3/12.
2025-03-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 1.5 | 225 | 337.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Gilberto Sucre worked on response letter to Homeca's Stoppage Claim Letter.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Coordination & quoting office trailer needs, Coordination with Jean Pierre Menay (DCMC) trailer deliver on Vega Baja Site. Coordination for the Trailer Installation, Leveling trailer, power installation, stair installation, and anchoring installation on the trailer on Genera Vega Baja power plan project. Coordination with Ada Díaz (DCMC) for the purchase of materials and equipment necessary for the Genera project in Vega Baja.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4.5 | 4.5 | 167 | 751.5 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Coordination & quoting office trailer needs, Coordination with Jean Pierre Menay (DCMC) trailer deliver on Vega Baja Site.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 3.5 | 167 | 584.5 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 1.75 | 167 | 292.25 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  | 1 | 133.73 | 133.73 | 133.73 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Purchase of chairs from Costco for the Trailer Office in Vega Baja Site.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the site scrap clean up and hot cutting. Also people from Genera-PR came in to help us get their stuff out of the site. This week and the rest of the week we worked on the all submittals and all the RFI's that needed to be completed or updated or moved in the system that were not submitted by the contractor.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this part of the project we are doing the site scrap clean up and hot cutting. Also people from Genera-PR came in to help us get their stuff out of the site. This week and the rest of the week we worked on the all submittals and all the RFI's that needed to be completed or updated or moved in the system that were not submitted by the contractor.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted Genera crew from Palo Seco and Cambalache with the items removed from site
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted Genera crew from Palo Seco and Cambalache with the items removed from site, supervised installation from trailers and electric connection.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 1.5 | 225 | 337.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Got responses and approval to proceed with Draft letter response to Homeca's Project Stoppage Claim Letter. As instructed by Jesus Cintron (Genera) final draft was sent to Frances Vallejo (DCMC) for signature.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Telecom Relocation hosted by Gabriel Perez (CDM Smith). Attendees Gilberto Sucre (DCMC), Jean Gonzalez, Mohamad Salman (LUMA), Jose Torres, Franklyn Colmenares (CSA Group). The Project Coordination Meeting focused on the Telecom Relocation project at the Vega Baja site, discussing its two phases and the status of the Memorandum of Understanding (MOU), which has been sent for execution by Gabriel with the consortium team ready to take over. Key topics included the shared fiber among Luma, Panera, and Hub, with Mohamad tasked to review circuits to minimize downtime and ensure a swift mobilization of his team next week. Coordinated site visits were planned for Monday with Gilberto on-site, while document signing was scheduled for Tuesday, pending confirmation from Luis Monet regarding the MOU. Action items were assigned to team members, emphasizing the need for timely communication and movement to keep the project on track.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.75 | 1.75 | 225 | 393.75 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Reviewed Sargent & Lundy's response to Homeca's Submittals 29 Demolition and 35 Transformer Protection. Instructed to proceed and respond per their comments.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.25 | 2.25 | 225 | 506.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Completed Draft response to Homeca's Project stoppage Letter and distributed it for comments to Frances Vallejo (DCMC), Franklyn Colmenares (CSA Group). and Gabriel Perez (CDM Smith).
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Discussed with Project Team - Jaime Pesquera and Jose Lopez (DCMC) revised response to the latest letter received on 3/13.
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 2.5 | 184 | 460 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - Review Homeca's 03/12/25 letter to Genera, review Genera's draft response and edit response accordingly as requested by Frances Vallejo (DCMC) and Jesus Cintron (Genera).
2025-03-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 1 | 184 | 184 | 184 | Yes | 25-144810 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Revise and draft response letter to Homeca for Vega Baja site.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 3 | 167 | 501 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Vega Baja Job Site meeting with Jesus Cintron (Genera PR) to overview site conditions and contractor claim.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted Genera crew from Palo Seco and Cambalache with the items removed from site, supervised installation from trailers and electric connection. Assisted on installation of Duenas Trailers steps and tensor installation.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted Genera crew from Palo Seco and Cambalache with the items removed from site, supervised installation from trailers and electric connection.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Weekly Construction Meeting led by Jaime Pesquera DCMC attended by DCMC, CDM, CSA, Homeca. Review project status of Safety/ Submittals / RFI's / Change Orders / Response letter status on delay/ and Genera/Luma responsibilities.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 1.5 | 225 | 337.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja. "Response to Homeca Work Stoppage" focused on the status and responsibilities regarding the mobilization of temporary facilities by the contractor, which include lay down storage, trailers, potable water, sanitary facilities, and temporary electrical power. Key discussions included the contractor's obligations to supply, install, and maintain these facilities as outlined in the scope of work, alongside addressing the need for adequate scaffolding, lighting, and waste management. Additionally, participants reviewed necessary revisions to the site-specific health and safety plan, raising concerns about the documentation's accuracy. The meeting concluded with a status update on pending items, with action items assigned to the contractor for facility setup, the unassigned group for health and safety plan revisions, and Nelson Soler-Lugo tasked with following up on outstanding issues. Attendees Jose Lopez DCMC, Jaime Pesquera DCMC, Nelson Soler CDM Smith, Frances Vallejo DCMC & Gilberto Sucre DCMC.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 2.5 | 225 | 562.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Met with project team to get general update on project status. Visited and inspected site progress and general conditions including DCMC office trailer installation. Hosted visit of Jesus Cintron (Genera) who was interested in pending issues from Genera/Luma required for the continued progress of the execution as well as Homeca's Progress. Project Team participated of the walk thru. Jose Lopez (Sphera), Jaime Pesquera (DCMC), Nelson Soler (CDM Smith), Manuely Concepcion, (CDM Smith) and Gilberto Soto (DCMC).
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Check in Weekly Update main item discussed: Cambalache Contractor selection by 3/24 Community Meeting April 1st Status PUI for Vega Baja awaiting lead clearance Stoppage at Vega Baja and actions Items RACI is still pending Phase II bids Vega Baja due 3/24 - Costa Sur Civil 3/31 - Aguirre Civil 4/7 Attendees from Genera, CDM Smith, CSA Group, DCMC, Sargent Lundy
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 | 0.75 | 184 | 138 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - Resumed reviewing Homeca's MSA with Genera in order to address Homeca's letters to DCMC.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 1.5 | 184 | 276 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - Begin reviewing Homeca's MSA with Genera.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 0.5 | 184 | 92 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - Continue reviewing Homeca's MSA with Genera in order to address Homeca's letters to DCMC.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 | 0.25 | 184 | 46 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - meeting with Frances Vallejo and Gilberto Sucre (DCMC) regarding letter to Homeca.
2025-03-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 2 | 184 | 368 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - Finalize reviewing Genera and Homeca's MSA and edit draft letter accordingly.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 3 | 167 | 501 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project management and site coordination by overseeing daily tasks, coordinating activities, and ensuring milestones are met. Worked on asset management, task coordination, and progress monitoring for the Vega Baja site.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Continued assisting Genera and Luma to locate Fiber optic lines on the site, with Genera Ing Carrillo.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted Genera and Luma to locate Fiber optic lines on the site, with Genera Ing Carrillo.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 0.25 | 225 | 56.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Homeca Schedule of values evaluation vs. December inventory comparison and recommendation requested by Franklin Colmenares (CSA Group). and Enrique Laya (CDM Smith) by Friday 3/21
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Schedule of Values Homeca Contract Affectations Meeting Hosted by Fernando Ortiz (Genera) with Enrique Laya (CDM Smith), Gilberto Sucre (DCMC), Carlos Rivera , Franklyn Colmenares (CSA Group), Maria de L. Rivera. Discussion was to review Change order process and contract amendments required including need to register change orders at the controller office within 15 days from issuance. Diesel transfer change order initiated this discussion.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 1.25 | 225 | 281.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Reviewed Temporary Power Requirements for Project - Contract Section 3.13, Specification 011100, 011101 & Appendix A - DOR. Owner to provide 480-volt incoming power, Contractor responsible to install meter and set-down transformer for construction temporary power. Met with Jose Lopez (DCMC), Jaime Pesquera (DCMC), Nelson Soler (CDM Smith) and Franklyn Colmenares (CSA Group) the last 30 minutes to discuss findings and alignment.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Legal review of response letter to Homeca Stoppage Letter with Sheila Torres (DCMC). Sheila to redraft letter and consult with Jesus Cintron (Genera) strategy.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 | 0.25 | 225 | 56.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Cylinder Removals evaluation and recommendation. Quote was obtained by Jean Menay (DCMC) from Messer for $ 5,798. Not only included the CO2 tanks as well as the Acetylene tanks and testing of all prior to removal from site.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 1 | 184 | 184 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - In depth discussion with Gilberto Sucre (DCMC) related to ongoing issues with Homeca, including pending information and completion of the Site Specific Safety Plans, Demolition Plans and Transformer Protection Plans.
2025-03-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 1 | 184 | 184 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - Homeca contract affectation call with Enrique Laya, Franklyn Colmenares (CDM Smith) Maria Rivera de Jimenez (CNR), Gilberto Sucre (DCMC), Angelina Minier Gutierrez (Genera)
2025-03-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 2.75 | 1 | 184 | 184 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Meeting with Gabriel Perez (CDSMITH), Franklin Colmenares (CDSMITH) about the Vega Baja Project Site. Metting with Rafael Pabon (CDSMITH) about the Costa Sur project site.
2025-03-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted Axel Perez from Hub to find the optic fiber lines and identify areas.
2025-03-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Continued assisting Axel Perez from Hub to find the optic fiber lines and identify areas.
2025-03-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Finalized response to Homeca's Work Stoppage Letter and distributed.
2025-03-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 3 | 184 | 552 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Demolition at Vega Baja Power Plant - Develop Homeca Amendment Justification Memo and draft amendment. Send and discuss with Gabriel Perez Sepulveda, Franklyn Colmenares, Enrique Laya (CDM Smith), Jesus Cintron (Genera) Frances Vallejo and Gilberto Sucre (DCMC).
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Bess Project contract and Specs. Overview to ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution.
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4.5 | 4.5 | 167 | 751.5 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued Vega Baja Bess Project contract and Specs. Overview to ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution.
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted With Porto San deliveries and installation of bathrooms. Luma came to disconnect distribution line from site work done from the exterior of the site.
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality.
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Discussion of 1st Contract amendment for Homeca to include additional diesel transfer, cylinders deposition and spare amount or miscellaneous change for a total of $ 100k instead of $ 200k (Diesel was for the additional not total). Discussion between Enrique Laya (CDM Smith), Sheila Torres (DCMC), Gilberto Sucre (DCMC) and Fernando Ortiz (Genera)
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 1.5 | 225 | 337.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Meeting Update for Vega Baja - Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA Group).& Gilberto Sucre (DCMC) Review outstanding items for Project as well as others: * Safety, * Cylinders removal, * RACI, * Decommission, * Transformer test, * MOU, * Temporary power, Jean Menay (DCMC) permit for Vega Baja. For Cambalache re-evaluate New Transformer Location with Sargent & Lundy. Once contractor is selected CM Team to participate i final negotiations.
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja schedule follow up with Manuely Concepcion (CDM Smith) BESS Cost Tracking with Carlos Palomares (CDM Smith)
2025-03-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 0.5 | 225 | 112.5 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Beta Electric - Transformer Assessment Coordination Meeting hosted by Franklyn Colmenares (CSA Group). for the transformer assessment to be performed on site next Tuesday and Wednesday. Beta Electric, Jaime Pesquera, (DCMC) Jose Lopez (DCMC), Gilberto Soto (DCMC), Nelson Soler (CDM Smith) and Gilberto Sucre (DCMC) participated.
2025-03-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors all day long, took pictures and generated my daily report. In this week we participated in daily meetings with Genera-PR, Safety Meetings and read the Scope of work carious times back and forth to make sure we understand the project from the management standpoint, due to the fact that I still do not have a hot spot.
2025-03-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted With Porto San deliveries and installation of bathrooms. Assisted visit made by Luma Alexis Morales to create an estimate from the distribution lines, and Safety World Frank Santiago made a forklift trainer certification session refresher.
2025-03-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted With Porto San deliveries and installation of bathrooms. Assisted visit made by Luma from Alexis Morales to create an estimate from the distribution lines.
2025-03-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 | 0.25 | 225 | 56.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - evaluated and provided feedback to Amendment and Task order # 1 to Homeca's contract back to Sheila Torres (DCMC).
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3.25 | 3.25 | 184 | 598 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- - Security and Safety inspection Vega Baja Site with Gilberto Sucre (DCMC). Metting with Frances Vallejo (DCMC), Jaime Pesquera (DCMC), Jose Lopez (DCMC), Gilberto Soto (DCMC), Gabriel Perez (CDSMITH), Carirma Sanchez, Eduardo Ramos, Linnet Correa, Carlos Diaz (HOMECA).
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 3.75 | 3.75 | 184 | 690 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Review the Safety documents of Vega Baja Site. Meeting with Victor Rodriguez (GENERA) about the permission of Genera Safety Training. Call with Beta Electrics for visit site. Coordinate Tesla visitors' inspection tomorrow in Cambalache y Vega Baja Site. Coordinate utilities for Cambalache Site. Coordinate Sargent and Lundy visits.
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted meeting with Homeca and walk through from site.
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Continue to Assist meeting with Homeca and walk through from site.
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.25 | 3.25 | 225 | 731.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Preparatory work for formal meeting with Homeca. DCMC Team members 8 - 9 am Weekly Construction Meeting and response to Work Stoppage Action Items Particpants Homeca, CDM Smith, Genera, CSA Group & DCMC
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 2 | 184 | 368 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Vega Baja Demolition Project - Finalized review and markup of the Homeca contract; outlined Genera’s and Homeca respective responsibilities and identified a clear path forward as discussed with Gerardo Sucre (DCMC), Gabriel Perez (CDMSmith) and Jesus Cintron (Genera).
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 2 | 184 | 368 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Vega Baja Demolition Project - Kick off meeting with Franklyn Colmenares, Gabriel Perez, Gustavo Vazquez, Manuely Concepcion, Enrique Laya, Nelson Soler (CDMSmith), Carima Sanchez (HOMECA), Jose Lopez and Jesus Cintrón (Genera) and Jaime Pesquera, Gilberto Soto, and Gilberto Sucre (DCMC)
2025-03-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.75 | 2.75 | 184 | 506 | 184 | Yes | 25-144810 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting at the Vega Baja site with Homeca Recyclying to discuss the suspension of works and pending items required in the contract. Participants: Gilberto Sucre (DCMC), Jean Menay (DCMC), Gabriel Perez (CDM), Gilberto Soto (DCMC), Carirma Suarez (Homeca).
2025-03-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja RFP overview and evaluation. Demolition Phase PCO discussion with the VB Team and Franklin Colmenares from CDM Smith. Job Site Walkthrough with staff from Sargent and Lundy and CDM Smith Franklin Colmenares. Site walkthrough with Gabriel Perez. from CDM Smith.
2025-03-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted meeting with Suleyka Perez from Luma and walk through. Assisted Beta company with transformer grounding and testing.
2025-03-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted meeting with Luma and walk through. Assisted Beta company with transformer grounding and testing. Monitored Homeca electrician Hector Diaz while disconnected electric lines were removed from the site.
2025-03-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Meeting to update Vega Baja schedule noting the contractor was changing the contractual milestones mainly the PUI approval date of April 16th. Recovery discussion took place. Met with Carlos Palomares (CDM Smith) and Manuely Concepcion (MG Consulting).
2025-03-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 225 | 900 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Worked on multiple activities including generation of Minutes of meeting from previous day with Homeca and Genera; schelude update, Permitting, contractor change order and amendment to the contract # 1 to include additional diesel removal and transportation to Palo Seco, Removal and disposition of CO2 tanks, and removal of disconnected power line. Also, worked on the coordination of the transformer study to be performed by Beta Electric. Finalized selection of Designated Inspector for the PUI and Construction Works.
2025-03-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Demolition Phase I RFP and specification overview and evaluation. PCO Discussion with Franklin Colmenares (CDM Smith) and DCMC Vega Baja Team.
2025-03-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Resumed Demolition Phase I RFP and specification overview and evaluation. PCO Discussion with Franklin Colmenares (CDM Smith) and DCMC Vega Baja Team
2025-03-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted on inspection of the excavator that arrived today by Homeca, and assisted Beta Company with safety while working on the transformer.
2025-03-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted on inspection of the excavator that arrived today by Homeca, and assisted Beta Company with safety Protocol while working on the transformer With Arnaldo Negron From Beta
2025-03-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 1 | 184 | 184 | 184 | Yes | 25-144810 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Review and approve Vega Baja RFI received by Homeca in order to explain it to Vega Baja team by name and role.
2025-03-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted on inspection fence dismounting by Homeca, and assisted Beta Company with safety while working on the transformer.
2025-03-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted on inspection fence dismounting by Homeca, and assisted Beta Company with safety Protocol while working on the transformer.
2025-03-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 2 | 225 | 450 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Followed up on Vega Baja progress of ongoing activities including the Transformer Testing and now need to re-power with 480 Volt to complete the testing. Jose Lopez to coordinate with Bonilla. Discussed quotation received from Luma for the temporary power new meter required. Will required to get new quote as they included the traffic lights rework which belong to a separate budget.
2025-03-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted on inspection fence dismounting by Homeca on the west side and assisted Beta Company with safety Protocol while working on the transformer grounding.
2025-03-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Assisted on inspection fence dismounting by Homeca, and assisted Beta Company with safety while working on the transformer.
2025-03-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 1.25 | 225 | 281.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Followed up on Genera's progress of reconnecting 480 Volt to Transformer as well as completion of Beta Electric Testing of Transformer. Followed up with Luma for Telecom Disconnect Scheduled for Next Monday. Verified with Carlos Lopez PUI requirement for installation phase - New one will be required after Demolition PUI is properly closed by Homeca.
2025-03-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 1 | 225 | 225 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Review and Updated RACI for Demolition and Upcoming Installation Contract to be implemented. CDM Smith Franklyn Colmenares, Gabriel Perez, and DCMC Jose Lopez and Gilberto Sucre participated.
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 1 | 167 | 167 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning meeting with DCMC Vega Baja Job Site Team with Gilberto Sucre, Jaime Pesquera, Jean Pierre Menay (DCMC), and Nelson Soler (CDM Smith). to set objectives and discussed timelines and agendas
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 2 | 167 | 334 | 167 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Weekly project meeting with DCMC Vega Baja Job Site with Gilberto Sucre, Jaime Pesquera, Jean Pierre Menay, and Nelson Soler (CDM Smith). Carirma Sanchez and Eduardo Ramos from Homeca Recycling. Discussion over the RFIs and Submittals is pending.
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 2.5 | 2.5 | 184 | 460 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Meeting with Jaime Pesquera (DCMC), Jose Lopez (DCMC), Gilberto Sucre (DCMC) and Nelson Medina (Genera). Discussed Vega Baja Site, Safety Hazards and Operation Situation.
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 | 2 | 184 | 368 | 184 | Yes | 25-144810 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria- Evaluate the procure action in the sites. Evaluate with Gilberto Soto (DCMC) the workflow in Vega Baja Site.
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Meeting with Gilberto Sucre, and Jaime Pesquera (DCMC) and staff from Homeca.
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 4 | 167 | 668 | 167 | Yes | 25-144810 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Continue meeting Gilberto Sucre, and Jaime Pesquera (DCMC) and staff from Homeca. Uploaded information from site to ProCore
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 0.25 | 225 | 56.25 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Followed up on Updated Schedule status for Vega Baja - Demolition Project with Carlos Palomares (CDM Smith) and Manueli Concepcion (MG Consutling)
2025-03-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 0.75 | 225 | 168.75 | 225 | Yes | 25-144810 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Project Update with Homeca's Manager - Eduardo Ramos: Discussed transformer study completion and Grounding, Homeca to proceed with transformer protection plan. Discussed Signature of contract amendment for Homeca to proceed with preparation and execution of the removal of CO2 and Diesel removal and transfer to Palo Seco. Also discussed EHS submittal and approval process. Attendees: Jose Lopez, Jaime Pesquera, Gilberto Sucre, Jean Menay & Gilberto Sucre (DCMC) and Nelson Soler (CDM Smith)
78968.69
[13 empty] | Construction mgmt cost= | 78784.69

## April
Entry Date | Client | Proj level1 | Proj level2 | Proj level3 | Client title | Asset | Task | Task Group | Task Description | Activity Type | Hours | Column1 | Activity Rate | Activity Extended | Billing Rate | Line Billable | Invoice Number | Narrative
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 1226.5 | 1226.5 | 1226.5 | Yes | 25-145003 | Rod Rodder - attach a pigtail to the trailer - Arecibo
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 1000.72 | 1000.72 | 1000.72 | Yes | 25-145003 | Rod Rodder - attach a pigtail to the trailer - Vega Baja
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed payment milestones, cash flow milestones for the PEAKER projects costs for projects
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane participated in the weekly PMO meeting to discuss updates, hosted by CDM Smith Carlos Palomares. Items discussed RGE final costs, RFP for demolition, and cost reports outlines.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Office Trailers Update for Vega Baja & Cambalache with Frances Vallejo & Harry Del Valle (DCMC)
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Prepared Construction Weekly Report with DCMC Abraham Velazquez for week ending 3/29.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Project Update discussion with Jose Lopez - Site Manager. Luma Communication Pre-Work Homeca Update ESH Audit Response letter Progress Schedule Review.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting Participants: Sargent & Laundy, CDM Smith, DCMC Partners, and Genera. Provide status of drawings by disciplines. Also noted reminder of Yabucoa Site Presentation for Wednesday.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Update discussion with DCMC Jean Pierre Menay of EHS Communication Procedure between DCMC Partners and Genera.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Review Contractual EHS Obligations comparing Vega Baja vs. Cambalache contracts.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Finalized project schedule update to be discussed Project Team, met with Manuely Concepcion & Carlos Palomares (CDM Smith).
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Shared RGE's RFP response documents following contractor selection by Genera for General Contractor to execute the BESS installation in Arecibo. DCMC Luis Damudt, Luis Duque and Frances Vallejo participated in the meeting.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO EHS Safety Manual implementation update discussion with Jack Darnall (Lemoine). Genera is pending comments to Lemoine ESH Manual from Victor Rodriguez.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria _ Cambalache Introduction meeting with DCMC Carlos de Jesus, Scheduler Cost Engineer for Cambalache.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Scheduled update discussion with Jose Lopez, Manuely Concepcion & Carlos Palomares (CDM Smith) and Jaime Pesquera (DCMC) - Highlighted PUI approval being the critical path.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Weekly Reporting by Department DCMC Partners / CDM Smith / CSA Group * Construction * Critical Components * Inventory & Warehousing * Scheduling & Cost * Contracts * Procurement
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Update among Foster Veazey, Lauren Wells, Mike Merritt, Mark Merritt, Annelie Holton, Ada Diaz & Gilberto Sucre (Lemoine/ DCMC). Topics covered: * Staffing Update * Procore Training * Trailers Update * Bluebeam vs. Adobe * Safety Program * Lead * Budget Task * Organization Chart
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Weekly PMO Call with Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt (Lemoine/ DCMC)
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)worked on Procore SOP's for daily logs. Changes made as per project settings vs company level settings.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Frances Vallejo(DCMC) for introductions and overview of Procore assignment.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO Reporting with Frances Vallejo (DCMC), Jean Pierre Menay (DCMC), Rafel Calderon (DCMC), Gilberto Sucre (DCMC), Paul Brown (DCMC), Eduardo Jordan (DCMC), Foster Veazey (DCMC) .
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) Procore PM Specialist to discuss Procore.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on scheduling Procore meetings for introduction to Luis Roman with Key team members.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Abe Velazquez (DCMC) to discuss Procore meeting features.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Barry Scanlon (DCMC), GIlberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy and Tyler Scanlon (Procore), Esther Rohena (DCMC) to continue work on build out of financials tools.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) work on Procore financials and adding information to the 10710 budgets we have built.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)worked on adding new users to Procore, replying to Gabriel Perez (Genera) IT for helpdesk tickets.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR 4339. Teams call with Barry Scanlon, Mark Merritt, Frances Vallejo, Gilberto Sucre, DCMC and Jack Darnell, Lauren Wells, Foster Veazey, Lemoine. Discussed update on project, job offers, PROCORE training schedule, status of scheduler, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update and status of office space.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.25 |  | 184 | 598 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting by write the work process between DCMC and Genera about Health and Safety Security. This meeting with Osvaldo De Jesus Health and Safety Supervisor by Genera.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 184 | 46 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Continuum the meeting by write the work process between DCMC and Genera about Health and Safety Security. This meeting with Osvaldo De Jesus Health and Safety Supervisor by Genera.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting for PMO planning. Trailer Status Meeting with Frances Vallejo (DCMC), Harry del Valle (DCMC), Gilberto Sucre (DCMC). Conference call with Irving Babilonia by Health and Safety Genera about Luma work in Vega Baja.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Meeting by write the work process between DCMC and Genera about Health and Safety Security. This meeting with Osvaldo De Jesus Health and Safety Supervisor by Genera.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 184 | 138 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting to discuss site trailer update and coordination. Discuss equipment delivery at Cambalache. Participants: Harry del Valle (DCMC), Gilberto Sucre (DCMC) and Jean Pierre Menay (DCMC).
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Attended RFE update meeting to discuss Cambalache RFP status and next steps. Participants: Luis Damudt (DCMC), Luis Duque (DCMC), Gilberto Sucre (DCMC), Jorge Mercado (DCMC).
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 184 | 230 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Reporting call to discuss weekly reports from each support team member. Participants: Lauren Wells (DCMC), Carlos Palomares (CDM), Gilberto Sucre (DCMC), Sheila Torres (DCMC), Raissa Borges (DCMC), Paul Brown (DCMC) and Rafael Calderon (DCMC).
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Nyah Medina and Mike Merritt (DCMC) to discuss PMO staffing update and hiring status.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended PMO Catching call to discuss program status, Procore training, staffing update at each site, trailer installation and lean management coordination with Genera leadership. Participants: Mike Merritt (DCMC), Mark Merritt (DCMC), Barry Scanlon (DCMC), Anneilia Holton (DCMC), Lauren Wells (Lemoine), Gilberto Sucre (DCMC), Foster Veazey (Lemoine).
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Participated in a weekly update meeting with Jesús Cintrón (Genera) and Frances Vallejo (DCMC) to discuss ongoing activities and priorities related to the PMO. Reviewed the status of active initiatives, addressed any emerging issues, and aligned on next steps and deliverables. Provided input on workflow improvements, resource coordination, and upcoming deadlines to support effective project execution and cross-functional collaboration.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Began conducting a comprehensive review of all open solicitations related to the BESS, Peakers, Critical Components, and PMO initiatives currently posted on Power Advocate. Assessed the status of each bid, including submission deadlines, required documentation, and pending actions.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Finalized comprehensive review of all open solicitations related to the BESS, Peakers, Critical Components, and PMO initiatives currently posted on Power Advocate. Began developing a centralized tracking spreadsheet to monitor progress, key milestones, and responsible parties across all solicitations.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Contributed updates on assigned tasks, reviewed performance metrics, and participated in discussions aimed at streamlining reporting processes and enhancing cross-functional coordination. Collaborated with team members to identify action items and align on priorities for the upcoming reporting cycle. DCMC: Frances Vallejo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Engaged in a project update discussion with Winnie Irizarry, Jesus Cintron and Ricardo Pallens (Genera) regarding the progress of the BESS and Peakers initiatives. Provided status updates on key deliverables, addressed ongoing challenges, and reviewed upcoming milestones. Additionally, discussed the recent changes within the procurement team and explored strategies for adapting workflows and maintaining continuity in coordination and approvals moving forward. Ensured alignment on next steps to support project timelines and strategic objectives.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Participated in an introductory PMO meeting with Raissa Borges, the newly designated lead for reporting and Frances Vallejo (both DCMC). Discussed current reporting structures, key deliverables, and expectations moving forward.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Strategy Discussion on Data Reporting Discussed strategy with Jan Rodríguez and Josué Sánchez from Genera PR on data reporting for the Power Generation and Fuels Consumption monthly report, specifically targeting the March 2025 report to be provided in April 2025.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of March 2025 Power Plant Metrics Began reviewing the March 2025 power production and fuels consumption metrics for the report to be provided to LUMA, ensuring accuracy and completeness of the data.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Homeca brought materials required for tomorrow's task including delivery of a forklift. Continue to assisted Luma with Jose Bonilla for tomorrows task and uploaded information for ProCore.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS CWC project schedule update evaluation to ensure smooth project execution, optimize resource use, and help achieve goals on time.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Project Schedule Discussion with Gilberto Sucre, Jaime Pesquera (DCMC) to outline tasks, assign responsibilities to team members, and set deadlines.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Continued today's procedure. Lead & Asbestos Inspection and sampling collection to protect human health, ensure a safe environment, and comply with legal regulations. A Niton XLP analyzer equipment was used to analyze all painted areas. Attendees, Carlos Roman – EHSS, Frances Diaz - EHSS, Francisco Vazquez – Genera, Harry Del Valle - DCMC
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Non-Billable- Travel from Jobos Gas Turbine Plant to Home Office in Luquillo PR.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Began with today's procedure. Lead & Asbestos Inspection and sampling collection to protect human health, ensure a safe environment, and comply with legal regulations. A Niton XLP analyzer equipment was used to analyze all painted areas. Attendees, Carlos Roman – EHSS, Frances Diaz - EHSS, Francisco Vazquez – Genera, Harry Del Valle - DCMC
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Attendees, Gilberto Sucre – DCMC, Frances Vallejo - DCMC, Jean Pierre Menay - DCMC, Harry Del Valle - DCMC Discussed Sites Trailer Update
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RGE up-date meeting with Gilberto Sucre (DCMC) Frances Vallejo (DCMC) Luis Damudt (DCMC) and Luis Damudt (DCMC)
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Inspection work was carried out on work areas, daily work permits were generated for the tasks of the GEO company. The JSA was discussed with staff and supervisor Gabriel Martines (GEO). equipment inspection and site visits with Roseanne Perez (Genera).
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - the closure of daily work permits is generated, the work areas are visited at the end of the task with Roseanne Lopez (Genera)
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The daily report was generated in relation to the day's tasks. The areas of the condition of the zones were reported in the Informed after completing the tasks. the report is sent to the client Roseanne Lopez (GENERA) Frances Vallejo (DCMC) Gilberto (Sucre)
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC - Critical Components - Working on updating information regard of cost of project, delivery dates and liquidation damage cost per days for Condensing Circulating Water Pump RFP# 221003, this project was received by P3A and now was forward to FOMB, also reviewing the contract RFP. Received an email of Hector Moctezuma of Genera PS and inform that he will be working the installation date of PS CC equipment's after resolving some issue with U3 of PS. Send an follow-up email to Jose Hernandez of EPS for status of delivery date of PO# 106735 which is schedule to deliver on 4/21/25.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC and Lemoine: Abraham Velazquez, Frances Vallejo, Gilberto Sucre, Jean Pierre Menay, Lauren Wells, Paul Brown, Glorimel Toledo, Rafael Calderon, Frankly Colmenares, Raissa Borges and Carlos Palomares (CDM Smith), Meeting with DCMC to discuss PMO weekly project status reporting to Genera.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing of Asset Suite the PO 104413 for Condensing Circulating Water Pumps Vertical, this PO was canceled but appear to be still ongoing by Genera need to confirm with procurement for more information. Send an email to Gilberto Sucre of DCMC to verify with his team at Cambalache for the Leak Detection System issue with ACT and to take picture and look for drawing related to the Overhead Crane of Cambalache. Reviewing a request by D' Alexander Gonzalez of DCMC regard of comparing Critical Components with an NME table to provide what project are duplicate or are in a legacy LGA this was presented to Mark Merritt of DCMC and Joaquin Quinoy of Genera.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC - Critical Components - Working on updating the critical component tracker to review upcoming dates for delivery. Make correction on PO 104792 for unit cost per equipment the sum was incorrect. Send email to Hector Montezuma for follow up in regard of installation date for CC at Palo Seco plant. The Critical Componentes PREB tracker table was incorporated (4) graphic pivot table for presentation. Review RFP, proposal and contract award for a new event on Asset Suite of PO 105654 of Malnat, which replace the existing PO 107494 of Surpaga related to Air Heater Basket of Aguire U1 and U2, with this information was update the CCL tracker for delivery dates and cost.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at the warehouse Costa Sur, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at Costa Sur warehouse with Mr. Hernan Machado from DCMC, providing guidance on his first day regarding the cycle count process and the daily reports to be completed. The work plan for thye week was also establish, and inventory activities were initiated.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega of Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria weekly TEAMS meeting with Ms. Frances Vallejo PMO from DCMC and project managers to discuss projects progress and address any concerns that require attention.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop a report, requested by DCMC D'Alexzander Gonzales, detailing the delivery dates of the CPMs for the Cost Estimates and Scopes of Work, as they relate to the critical components list.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue updating CCL Tracker : Using the available information, such as the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components, I have developed a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Discuss 20241028-MI20210004-Resolution-and-Order with DCMC Mark Merrit, D'Alexzander Gonzales detailing in which LGA project was included the different components of the list.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review Contract 105654 for identify if is related to Critical Components.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop a report, requested by DCMC Mark Merrit of 20241028-MI20210004-Resolution-and-Order, detailing in which projects was LGA project was included.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review current status in Asset Suite of the following contracts: 107494, 108523, 105930, and 108527 they are supposed to be related to Critical Components.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Discuss a report of 20241028-MI20210004-Resolution-and-Order with DCMC mark Merrit, D'Alexzander Gonzales, Eduardo Rivera and GENERA-PR Jesus Cintron and Joaquin Quinoy
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS reviewed the email sent by Gilberto Sucre (DCMC) Request for information on construction project schedules near the entrance to the Cambalache Power Plant that may affect the project's construction work.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A.. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS review the Cambalache Document by email sending by Gilberto Sucre, VRFP-4826_RFC_(RGE_03-31-25), Value Engineering Steel Structure BESS Cambalache R7A.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS review the email sending by DCMC Gilberto Sucre, RG Engineering Inc. 24 Engineering Solutions and Recommendations Conceptual Drawings Cambalache Site Plan.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today in the afternoon I did the same stuff, I created RFI's and worked with RFI's that needed my attention, I also created submittals, I worked all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with contractor, and meetings with management of Genera-PR. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today in the morning I created RFI's and worked with RFI's that needed my attention, I also created submittals, I worked all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with contractor, and meetings with management of Genera-PR. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Homeca brought materials required for tomorrows task including delivery of a forklift.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria PMO Reporting Meeting - DCMC PMO staff meeting to discussed specific need of reporting based on project execution development per area. Working on PPT presentation template and review updates from BESS and Peakers project. Participants Frances Vallejo, Raissa Borges, Glorimel Torrado, Gilberto Sucre, Sheila Torres, Abraham Velazquez, Eduardo Rivera and Paul Brown.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Pre-Intervention Review - Working with Jaca & Sierra Contract #105165_2025-G00054 and TO#2_Invoice# 0054667_ Dec 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Invoice Approved.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Pre-Intervention Review - Working with Jaca & Sierra Contract #105165_2025-G00054 and TO#1_Invoice# 0054627_ Dec 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Invoice Approved.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Martinez Mendez, Felix | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 5 |  | 152 | 760 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse Palo Seco, conducting cycle counts, and recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory record. Today list number 00238 and 00239, location 041 to 054, inventory, recount, discrepancies, relocation and variance analysis.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, preparing a detail report outlining the work completed throughout which will be summitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.25 |  | 152 | 38 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA-001-000 to AA-009-000.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, conducting cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. The location worked on today were from AA-001 to AA-009.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Count value items cost; There were problems in the warehouse with asset suits.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Continued taking the price of inventory items from 03/17/25 to today
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Count value items cost; There were problems in the warehouse with asset suits.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Taking the price of inventory items from 03/17/25 to today
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, conducting Recounts List # 251 to verify inventory accuracy.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, conducting ABC Cycle Counts List # 250. In coordination with the Warehouse Supervisor of Genera PR Adan Silva.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, investigating any discrepancies in the list 251 to ensure proper stock control and alignment with inventory records. 10 Locations, 51 items and 435 pcs were worked on. This information was validated the employee in charge of Genera PR, . Finally, the daily progress report was prepared and submitted to the manager, DCMC.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the San Juan warehouse, preparing the lists #250 to begin the cycle counts.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Martinez Mendez, Felix | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 5 |  | 152 | 760 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse Palo Seco, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory record. Today list number 00238 and 00239, location 041 to 054, inventory, recount, discrepancies, relocation and variance analysis.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Lauren Wellss (Lemoine) to discuss Procore File Structure.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on Procore Certification (Procore Core Tools). Client requirement.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Walkthrough on the Procore Platform: review project costs projections, resources already on platform and development of execution plans to fully integrate contractors and users to the Procore experience.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 151 | 113.25 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Platform walkthrough with Lauren Wells (Lemoine) to overview platform projections.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 151 | 339.75 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Started Procore Certification: Procore Management Core Tools as the Owner. Certification for the main domain of Procore's Core Tools.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Create and review Standard Operating Procedures (SOP) for client and users of Procore Platform to help execute routine tasks consistently and effectively and reduces variability and minimizes the risk of errors.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Continue working on Pre-Intervention Review for CDM Smith TO02_Aug2024_Inv293566-9. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees, create pivot tables, analyze Task Order and identify expenses not allowed on this invoice.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO02_Aug2024_Inv293566-9. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and identify discrepancies in numbers.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 149 | 372.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Working session with Rafael Calderón (DCMC) to prepare new report for PMO weekly Meeting. This is the first time we fill the report to be presented today. For this report we prepared two slides one for Bess and one for Peakers related to Payment Milestone 2. The slides include potential risks, mitigation, next week to do items, milestones and important information related to.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - PMO Reporting weekly team meeting. On this meeting each team present their slides with the weekly updates. Raissa Borges will prepare one last report monthly for Genera. During this meeting with Frances Vallejo (DCMC) presented Gilberto Sucre (DCMC), Carlos Palomares (CDM Smith), Rafael Calderón (DCMC), Eduardo Rivera Jordán (DCMC), Lauren Wells (DCMC) and Sheila Torres in support to PMO legal area and procurement. Other participants Franklyn Colmenares (CSA) and from DCMC were Jean Pierre Menay, Abraham Velázquez and Paul Brown.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 149 | 37.25 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761 - Review total quantities for Tesla contract and send final numbers to José Ralat (DCMC). To complete this task, I review the Tesla tracker with all the payment milestones, contract document and Contralor (OCPR) web page.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.75 |  | 149 | 111.75 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. Reviewing pending invoices to organize invoices for today.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.75 |  | 149 | 111.75 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_PW9510 _ Review documents sent by Franklyn Colmenares to review Invoices from Jaca y Sierra. Prepare email requesting V2 RFP pricing or amendment to allow V3 RFP pricing to be used in the invoice review. For the email prepared I included Sheila Torres as a support in legal and procurement. Pending response to this RFI for Pre-Intervention Process on Jaca y Sierra.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Reviewed an email received from Chyenne Bliss DCMC regarding the Quick Dry Shirts. Send an email to Gilberto Soto, Gilberto Sucre, Harry Del Valle, Jaime Pesquera, Jean Pierre Menay, Jorge Mercado, Jose Lopez, Luis Damudt, Luis Duque, Paul Brown, Rafael Calderon, Sheila Torres-Sterling, Jack Darnall, and Foster Veazey (DCMC) regarding the quick-dry shirts. Check emails received with shirt size.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RGE update meeting with Frances Vallejo (DCMC), Gilberto Sucre (DCMC) and Luis Damudt (DCMC) for 4339_9510 BESS_Cambalache project.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the Value Engineering Steel Structure Bess Cambalache contract document of the 4339_9510 BESS_Cambalache project.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3)Continue review of the pre-contract and contract document of the project 4339_9510 BESS_Cambalache project.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review of pre-contract and contract document of the project 4339_9510 BESS_Cambalache project.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 122 | 366 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review of Critical Components, Procore, Program Controls – Schedule & Budgets, weekly report of PMO and performing a data analysis for the development of the monthly report.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 122 | 152.5 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review of RFPs tracker shared by Sheila Torres and performing a data analysis for the development of the monthly report.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 122 | 30.5 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal Teams Meeting with participation from DCMC members: Frances Vallejo and Sheila Torres. To getting familiar with projects legal and procurement process and reporting needs. We also discuss the RFPs tracker for monthly reporting.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 122 | 305 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review of Critical Components, Procore, Program Controls – Schedule & Budgets, weekly report of PMO and performing a data analysis for the development of the monthly report.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal Teams Meeting " PMO Reporting". The purpose of the meeting was for the members of the PMO team to discuss the weekly project status and updates. The meeting was organized by Frances Vallejo (DCMC).
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 108.5 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- travel directly from home to Costa Sur, round trip, to meet with Mr. Hernan Machado Inventory Supervisor from DCMC to review the progress made so far and provide onsite support throughout the day to address any questions regarding the process.
2025-04-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 112.7 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Harry Del Valle 4/01/2025 Travel from Home Office Luquillo to the Jobos Gas Turbine Plant (17.961105, -66.140130) to Home Office Luquillo. Purpose, Attendees, Carlos Roman – EHSS, Frances Dias - EHSS, Francisco Vazquez – Genera, Harry Del Valle - DCMC Procedure. Lead & Asbestos Inspection analyzer equipment was used to analyze all painted areas. Total Mileage 161 Miles
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 495.25 | 495.25 | 495.25 | Yes | 25-145003 | Safety Posters for Genera Project
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Discussions on outlining the scopes of work for the demolition portion of the projects. spoke with German Nunez Genera, Carlos Palomares CDM smith
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed demolition and site plans for Costa Sur
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Initial review of Installation bids submitted by AGR and RGE contractors.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Yabucoa Presentation - RFP231175: Genera PR: 40MW Battery Energy Storage System Civil-Structural Installation provided by Sargent & Lundy. In preparation for the RFP site visit the following day scope of work was presented by the Sargent & Lundy team. CDM Smith, CSA Group, DCMC Partners, Genera and Sargent & Lundy
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Presentation of Procore PM Specialist - Luis Roman to Abraham Velazquez and Gilberto Sucre (DCMC), Lauren Wells (Lemoine) hosted the meeting.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Genera & Tesla Weekly Project Meeting with Sargent & Lundy, Genera, Tesla, CDM Smith, DCMC Partners, and CSA Group,
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Morning call with Jose Lopez DCMC follow up project status
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Construction Execution process, and procedures review and implementation to be used for both BESS and Peakers Projects. Meeting was between Abraham Velazquez and Gilberto Sucre (DCMC). * EHS * Office Trailers * Communication Tools Bluebeam & i-pads, hot pots & copiers * Quality * Reporting * Coordination * Staff Sharing.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Formal Introduction with Carlos de Jesus DCMC presented Roles & Responsibilities for his role as Scheduler & Cost Control. Review Cambalache BESS Scope of Work, Schedule and selected contractor RGE Base Bid and Value Engineering proposal.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO EHS Procedure GENERA/DCMC Partners Discussion with Jean Pierre Menay DCMC. Goal established Safety & Enviornmental process and EHS Contractual Obligations.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Homeca contract discussion with contractor on potential change orders applicable or not. Jose Lopez (DCMC), Carirma Sanchez (HOMECA), & Eduardo Ramos (HOMECA).
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman(DCMC) and Gilberto Sucre (DCMC) for introduction and program overview.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on incorporating Procore Financial information into Procore based on the last meeting discussing cost items.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing contracts and invoices for Siemens contract 106588 for putting into Procore.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman(DCMC) to review Procore items and staffing structure.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore training to invite users to CPM training on 4/8.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence for Jorge Torres(DCMC) for permissions on inspections.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks in Teams planner for Luis Roman (DCMC) and Theresa Perez (DCMC).
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing documents to Luis Roman (DCMC) to help with his onboarding knowledge of Procore.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for Procore.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman(DCMC) to review Procore items and upcoming tasks.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing documents for Theresa Perez (DCMC) to onboard her for work in Procore.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy and Tyler Scanlon (Procore) to continue work on build out of financials tools in Procore.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.25 |  | 184 | 598 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Meeting with Abraham Velazquez (DCMC) about Peaker's Genera project. Meeting with Gilberto Sucre (DCMC) about Health, Safety and Secuity items in Vega Baja and Cambalache Project. Review all Local and Federal requirements about Genera Project.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Conference call with Osvaldo De Jesus (Genera) about Vega Baja project. Meeting with Harry del Valle (DCMC) about all sites DCMC managed by Genera. Discussed and review the Procore system action by Cambalache and Vega Baja sites. Meeting Carlos De Jesus (DCMC) about Costa Sur Site.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Meeting with Javier Centeno (Genera) Security Officer and Osvaldo De Jesus Genera (Safety Supervisor) about Palo Seco and Vega Baja site requirements. Review the Procore system actions. Complete the action day.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 184 | 230 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Meeting Continuing with Carlos De Jesus (DCMC) about Costa Sur Site.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Raissa Borges (DCMC) to discuss weekly reporting, BESS and Peakers construction reporting, discuss templates for power BI dashboard, discuss Pie charts format and next steps moving forward in regards to sharing the information with the team.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination with Carolyn Baez (DCMC) to arrange field equipment for the PMO team, Coordinate Tesla NDA signature from the new hires and trailer arrangement.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review and drafted response to Jesus Cintron (Genera) to include all the staff that has been hired up to date in the PMO.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS & Peakers - Followed up with Genera Procurement on the status of the Costa Sur demolition process as discussed during the BESS and Peakers weekly meeting. Requested and shared the current status of the related RFP with the team to ensure alignment and visibility on procurement progress. Circulated the draft demolition contract for internal review and feedback. Additionally, requested support from CDMSmith with the development of the ICE and SOW to advance the next phase of the contracting process.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Held a detailed discussion with Franklyn Colmenares (CDMSmith) and Fernando Ortiz (Genera Legal) regarding the Jaca and Sierra contract and associated task order issues. Addressed concerns related to Task Order Alignment with contract terms, and potential discrepancies impacting payment. Explored possible resolutions and next steps to ensure proper documentation and timely processing of the payment within the existing contractual framework. Responded to Glorimel Torrado's (DCMC) email related to this issue.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS & Peakers weekly catch up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya (CDM Smith) Miguel del Valle (S&L).
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - PW 107 10 - Reviewed and revised the draft letter requesting additional funding for the Equipment and Materials Project Worksheet (PW). Refined the language to strengthen the justification, clarify the basis for the funding request, and ensure alignment with FEMA guidelines and documentation standards. Ensured the updated version addressed prior feedback and included all necessary supporting details to facilitate approval. Shared with Jose Ralat (DCMC)
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Updated the BESS and Peakers project tracker in preparation for the upcoming weekly catch-up call. Incorporated the latest developments, including status updates, milestone progress, pending actions, and relevant correspondence. Ensured the tracker reflected accurate and up-to-date information to support effective discussion, coordination, and decision-making during the meeting.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Reviewed the Genera Connect documentation related to Time Entry to ensure consistency with the implemented processes, verifying alignment with system requirements. - Continued reviewing power plant performance metrics for March 2025, focusing on data accuracy and completeness for the upcoming report.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area, and assisted Omar Muniz and Jorge Diaz from Luma in disconnecting communications lines.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria—Review of GWC's daily scope of work with Carirma Sanchez from HOMECA. Following the daily activities and the status of the pending items in PROCORE. Held an Online meeting with Eduardo Ramos (HOMECA) to discuss the PCO's letter regarding scope of work omissions by HOMECA.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria—Review of GWC's daily scope of work with Carirma Sanchez from HOMECA. Following Daily activities and pending items status in PROCORE
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed and review Safety documents communication between Genera & DCMC. Gilberto Sucre - DCMC, Jean Pierre Menay - DCMC,
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Presentation - RFP231175: Genera PR: 40MW Battery Energy Storage System Civil-Structural Installation at Yabucoa Attendees, Eric M. Plasencia -Genera, Gilberto Sucre -DCMC, Enrique J. Laya -CD Smith, Mike J Kuczynski - Sargent Lundy - Franklyn Colmenares - CSA Group,
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Review of Hurricane Maria Quality Control Plan and Safety documents. We are developing this to see if we can establish them for the company. We reviewed the first draft and agreed to make certain modifications that are in line with the projects. Attendees, Gilberto Sucre (DCMC) & Harry Del Valle (DCMC)
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Request and Explain Portosan Safety Hazard Analisys necessary to Materials delivery. Jean Pierre Menay - DCMC, Javier Aviles - Portosan, Harry Del Valle - DCMC
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on QA/QC Forms and Checklists for the Vega Baja, Cambalache (Arecibo), & Yabucoa projects. Verifying specifications to create QA/QC Plan.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - FRC meeting whit RGE about value Engineering Proposal of the 433_9510_cambalache project
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visit to the Cambalache site. The area surrounding the Cambalache plant is explored, identifying nearby projects that may have an impact on the coordination of work on the site.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - A report is generated where the projects near the Cambalache site are documented and reported, this report is sent to Luis Damudt (DCMC)
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Informational meeting on projects near the Cambalache power plant with Luis Damudt (DCMC)
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Updated the Critical Components tracker with information provided by Hector Moctezuma of Genera for the equipment installation of PO#102570, 104082, 104794, 106735, 106805, 107989 and 107048.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing resolution provided by Genera in regard of resolution #20250210 and 20241028, the following NME listed on resolution will be included in the critical component's tracker. Reviewing LGA project 662947 PW 10615 and 662957 PW 10606 related to Critical Components. Reviewing LGA document for project 663383 PW 10607 to identify Critical Components.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing detail table sent by Jose Ralat of DCMC to see if we can identify from Asset Suit equipment components that has been charged by plant and if they can be identify as Critical Components.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Updating data entry for new NME projects entry to the Critical Components Lead tracker, the new list of NME was uploaded with item description and estimate cost by Genera.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Enter new data regard of new NME project at the Critical Components Tracker CCL for the following PO# 102073, 100239, 102348, 101296, 106561 and MR-871412.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at San Juan warehouse, assisting Mr. Felix Martinez DCMC on cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conference call with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse to meet with Inventory Supervisor Mr. Felix Martinez from DCMC. The purpose of the visit is to review the progress achieved so far and clarify any doubt regarding the process. During the visit, I will be performing quality control on the cycle count and assisting Mr. Martinez with the process.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega of Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4.5 |  | 167 | 751.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop a report, requested by DCMC D'Alexzander Gonzales of Critical Components to determine in which projects was included if was under Project 817248 or in one of the LGA Projects.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Coordination of meeting with CPM and GENERA-PR Cambalache Power Plant for discuss Over Head Crane
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review list of expesnses under account 100FG0109057 to verify current critical components already with expenses associated.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue updating CCL Tracker : Using the available information, such as the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components, I have developed a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, RFP-4826 RFC (RGE 3.15.25) Line #34 VE RI Drawings sent by Gilberto Sucre (DCMC).
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS review and practice of topics for the PROCORE platform; Add Markups to a Submittal PDF Attachment, Respond to a Submittal.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS call with Jorge Mercado, DCMC safety manager, to discuss the report on construction projects near Cambalache.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review of photos of construction projects near the Cambalache Plant that could affect construction.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS RG Engineering Presentation - RFP 4826 52 MW Battery Energy Storage System Installation at Cambalache.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today in the morning I created RFI's and worked with RFI's that needed my attention, I also created submittals, I worked all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with contractor, and meetings with management of Genera-PR. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. That is the stuff and chores I did for today, Wednesday in the morning.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today in the afternoon I created RFI's and worked with RFI's that needed my attention, I also created submittals, I worked all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with contractor, and meetings with management of Genera-PR. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. That is the stuff and chores I did for today, Wednesday in the afternoon.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, today they removed and cut welded the scrap metal, doing the mitigation, Verified the employees and site for Quality. Continue Homeca brought materials required for the scaffold inspected area, and assisted Omar Muniz and Jorge Diaz from Luma in disconnecting communications lines.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#6_Invoice# 18322772_Dec 2025. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 BESS Meeting: BESS project Status follow-up and review of contract schedules. Pre-Meeting preparation for next Thursday 4/3/2025 (DCMC-PMO) Workshop Meeting to discuss the following: Change order process and proposed change order package and Review upcoming Payment Milestones #2 Activities and possible issues with payments or contract timeline. DCMC Participants Rafael Calderon and Glorimel Torrado
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Invoice Workshop Meeting - Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Revision and development of Pre-Intervention process for demolition works (BESS-Peakers) - Case Study will be Homeca's 1st demolition invoice for BESS Project. DCMC Participants (Glorimel Torrado and Rafael Calderon)
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Continue working on Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#6_Invoice# 18322772_Dec 2025. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Martinez Mendez, Felix | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 5 |  | 152 | 760 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse 019 San Juan, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory record. Today list number 00253 and 00254, location AC 035 to AD 010, D001 and FT 053 inventory, recount, discrepancies, relocation and variance analysis.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, conducting cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. The location worked on today were from AD-001 to AD-016.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, preparing a detail report outlining the work completed throughout which will be summitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.75 |  | 152 | 570 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, resumed conducting cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. The location worked on today were from AD-001 to AD-016.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Inventory from CR 00 143 to CR 153, including recount, variants, highs and lows, and differential cost for this list.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse Aguirre, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records, Inventory, recount, variance, min & max, cost AA 001 to 010
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Inventory from CR 00 143 to CR 153, including recount, variants, highs and lows, and differential cost for this list.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting ABC Cycle Counts List # 255. In coordination with the Warehouse Supervisor of Genera PR Adan Silva.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Manager from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed. Preparing the lists #255 to begin the cycle counts.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse Palo Seco, conducting Recounts List # 261 to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. 16 Locations, 36 items and 751 pcs were worked on. This information was validated by the employee in charge of Genera PR.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Martinez Mendez, Felix | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 5 |  | 152 | 760 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse 019 San Juan, conducting cycle counts and recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory record. Today list number 00253 and 00254, location AC 035 to AD 010, D001 and FT 053 inventory, recount, discrepancies, relocation and variance analysis. Prepare daily report and sent to DCMC Manager and Genera.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call with Laurel Wells (Lemoine) to discuss daily activities and progress of assigned tasks.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reviewing the Daily Log SOP and editing the new Submittals SOP. SOP's created are for Procore Platform to ensure tasks are conducted uniformly and sustain high-quality outcomes.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue with Procore Certifcations process. Client requirement.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Lauren Wells (Lemoine) to go over Procore integration and program execution.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue SOP creation and review to ensure tasks are conducted uniformly and sustain high-quality outcomes.: Submittals on Procore Platform
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue working on Procore Certifications: Procore Financials.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Procore Platform Certification (Project Management Financials Certification).
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Lauren Wells (Lemoine) and Gilberto Sucre (DCMC) to go over Procore integration and program execution.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 149 | 521.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Pre Intevention for CDM Invoice #293566-7_To2_August2024. Continue reviewing notes and identifying what is part of the scope of work and what represent administrative expenses. Also, review amendment on TO2 and compare with the invoice to see if any adjustment is needed.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.25 |  | 149 | 335.25 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Review 1rst Invoice for Homeca, search on OCPR to download contract, read contract terms and invoicing requirements. Verify if Invoice #1 is in compliance with contract.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 149 | 372.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Working session with Rafael Calderón (DCMC) to discuss and review Pre-Intervention process for demolition works (BESS-Peakers) - Case Study will be Homeca's 1st demolition invoice for BESS Project. Also, in this working session we prepare for next Thursday 4/3/2025 (DCMC-PMO) Workshop Meeting to discuss the following: change order process and proposed change order package, align demolition & construction schedules with contract schedule for guaranteed delivery dates and installation of units, and review upcoming Payment Milestones #2 Activities and possible issues with payments or contract timeline.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Designing custom routes on Google Maps and adding directions for Gilberto Sucre DCMC, including the starting point and destination from UBS Financial Services to Luma Office in Vega Alta. The routes cover both directions for March 24 and 31. Review the maps and print them.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Reviewed an email received from Chyenne Bliss (DCMC) regarding the Quick Dry Shirts. Emailed Jaime Pesquera, Barry Scanlon, Mikie Merritt, Mark Merrit (DCMC), and Jarck Darnall (Lemoine) regarding the quick-dry shirts. Reading and answering email received by Chyenne Bliss regarding the names of the employees. Edited and printed the NDA for Genera, TESLA, preparing it for Carlos De Jesus (DCMC) to initial and sign as part of the work requirements.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue reviewing the Value Engineering Steel Structure Bess Cambalache contract document of the 4339_9510 Bess_Cambalache project.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR4339 work related on site Cambalache. Train in safety process with employee of DCMC Jean Pierre Menay- a safety requirement of Puerto Rico Electric Power Authority to obtain knowledge and skills to identify and minimize accidents, illnesses, and injuries that can cause project delays and affect productivity.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR4339 work related on site Cambalache create planning techniques, tables of documents and letters required to contractors for employee of DCMC Gilberto Sucre due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review the Value Engineering Steel Structure Bess Cambalache contract document of the 4339_9510 BESS_Cambalache project.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with RGE about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 122 | 427 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data gathering. Development of a Master Tracker for the monthly report that includes site weekly progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal Teams Meeting with Frances Vallejo, DCMC. The purpose of this meeting is to discuss project reports status and updates. The meeting was organized by Frances Vallejo (DCMC).
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 122 | 427 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data gathering. Development of a Master Tracker for the monthly report that includes site weekly progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 30 | 30 | 30 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. fuel for vehicle for site and travel
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 site visit to Vieques. Coordination meeting at Ceiba. Attendees: Genera Jesus Cintron, S&L engineers, Luma field personnel.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339 10710 site visit to inspect current field condition at the Vieques facility. Currently it has two generators to be replaced and an additional 3rd generator to be installed, same foundation to be used if possible.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Worked with Jose Lopez DCMC on EHS audit final response.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of installation bids from ARG and RGE contractors.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 225 | 675 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Tesla Contract Workshop - Review of contract Payment Milestone and deliveries hosted by Rafael Calderon and Glorimel Torrado (DCMC), Franklyn Colmenares (CDM Smith), Gilberto Sucre (DCMC), Carlos Palomares and Gabriel Perez (CDM Smiht) participated.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS/Peaker's Project Schedule & Budget Meeting hosted by Gabriel Perez attendees Genera, CDM Smith, CSA Group & DCMC Partners.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-¦ DR 4339 - Hurricane Maria- Coordination meeting with Joaquin Quinoy (Genera PR) discussing upcoming Lean training in support of lean tool implementation for the grant approval process.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-¦ DR 4339 - Hurricane Maria-Follow- up action items and planning from Coordination meeting with Joaquin Quinoy (Genera PR) discussing upcoming Lean training in support of lean tool implementation for the grant approval process. Sent email requesting meeting setup time to Carlos Negron (Genera), Frances Vallejo (DCMC), Joaquin Quinoy (Genera PR) and Jennifer Witeczek (Genera). As per request from Joaquin.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for Luis Roman (DCMC).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for the 10710 project. The PM tools are being turned off because we are only managing cost in this one.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) for Procore overview and Planner tasks.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training certification tracker updates.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating private folders in Procore for Franklyn Colmenares (CSA).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore project planning to ensure alignment with plans.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items for various users.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching different type financial configurations for Procore.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing meetings and scheduling them for next week with the Procore team (Luis Roman, DCMC and Theresa Perez, DCMC).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Franklyn Colmenares (CSA) for introduction and program overview on what Franklyn does.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore configurations for numbering. I am removing some unnecessary numbers from project names across the program.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 | 1 | 184 | 598 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Arrive to Yabucoa Site. Conference call with Harry del Valle (DCMC) about the Cambalache and Vega Site Administrative requirements. Review the Vega Baja Site action in the morning by LUMA and Homeca. Inspection to Yabucoa Site with construction contractors, Sargent & Lundy representatives. In the visit.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review the Procore action today. Call with Jose Lopez (DCMC) about Vega Baja Project. Review with Harry del Valle (DCMC) administrative items about Vega Baja and Cambalache site. Metting with Osvaldo de Jesus (GENERA) and Javier Centeno (GENERA) Local and Federal Requirements Laws in the site. Write the inspections reports in Yabucoa.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 184 | 138 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- On site visit with Harry del Valle (DCMC), Osvaldo de Jesus (GENERA) and Pedro Santiago (Genera). The objectives its review the space and requirements about construction.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Franklyn Colmenares (CSA) to discuss the PMO org chart. He requested the org chart with the latest staffing update. Worked on editing the PMO organizational chart to include new hires.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with BESS & Peakers Project Management team to discuss master scheduling and budget for both projects. Participants: Carlos Palomares (CDM), German Ojeda (Genera), Franklyn Colmenares (CSA), Gilberto Sucre (DCMC), Raissa Borges (DCMC).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Critical Components - Met with Pedro Cabrera DCMC to discuss the Critical Components tracking spreadsheet. Reviewed the current status of items and deliverables. Developed and discussed a plan to engage all relevant stakeholders and ensure comprehensive, up-to-date information is captured with Jesus Cintron and Ricardo Pallens (Genera).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Reviewed the Jaca and Sierra contract and Task Orders in detail, with a particular focus on the compensation structure and task order framework. Met with Fernando Ortiz to discuss the appropriate compensation method for past task orders, specifically evaluating the use of fixed-price versus rate-based approaches. Also assessed how the task order compensation method aligns with the overall contract terms, financial controls, and project delivery requirements. The discussion aimed to ensure clarity, compliance, and consistency in the execution of future work under the agreements and as a preparation for the upcoming call with Jaca and Sierra.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continued developing a centralized tracking spreadsheet to monitor progress, key milestones, and responsible parties across all solicitations. Coordinated follow up strategy for Critical Components with Pedro Cabrera (DCMC)
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Jan Rodríguez: Met with Jan Rodríguez from Genera PR to discuss the power plant performance metrics and fine-tune the master report, ensuring all data is accurate and mapped to the proper fields.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 30%, Assisted with safety protocol Luma employee Jorge Diaz with the disconnection of communication lines to complete work.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Held call with Gilberto Sucre (DCMC) to discuss the answer to the Genera EHS letter. Built a draft letter for discussion with Jean Pierre Menay (DCMC)
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Site walkthrough to verify HOMECA's daily progress with the MPT protection to help ensure that MPT plans are properly designed, implemented, inspected and maintained during construction, and that qualified individuals are employed at key positions
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on Yabucoa projects. Verifying specifications to create QA/QC Plan.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Walkthrough the Yabucoa BESS Site with Genera, Beta Electric, Sargent & Lundy, Lord, RG Engineering. Architects and Engineers explain scope of work to bidders. Explain projects steps & Construction procedures.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 |  | 167 | 542.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on QA/QC Forms and Checklists for the Vega Baja, Cambalache (Arecibo), & Yabucoa projects. Verifying specifications to create QA/QC Plan.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluation of the safety program notes for contractors prepared by Herbert Guilbe Marin (GENERA)
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS review and practice of topics for the PROCORE platform; Create Submittals.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS review and practice of topics for the PROCORE platform; Create Submittals.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS review and practice of topics for the PROCORE platform Import Submittals.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Meeting regard High Speed Control - Genera participant Herminio Arroyo, Kevynne Gonzalez, and Eliseo Martinez; CPM participant Luis Tapia and Victor Alvarez; DCPC participation from DCMC Pedro Cabrera and Eduardo Rivera - Meeting was discuss the Critical Component project for High Speed Control for (1) turbine, plant bring a concern if this project was for (2) unit due their need, it was inform to plant that this is (1) unit and (1) DCS, CPM had concern on how to generate a SOW and CE due to the information that they had receive does not include a vendor breakdown and price are just included in a lumpsum from GE. Herminio mention that Cambalache is also in conversation with another vendor regard to this project, we will discuss this concern with Joaquin Quinoy of Genera to validate what direction we will move regard to the project.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue on working on populating information for new added NME projects with Asset Suite and CCL tarcker for PO# 100239, 102570 and 101296.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - CPM Jose Prado, Luis Tapia, Carlos Castro, Diana Rivera and Victor Alvarez; DCMC Pedro Cabrera and Eduardo Rivera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, Discussion of Overhead Crane, Cambalache Leak Detection System and reviewing the deliverables.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Genera Procurement Sulinnette Perez; DCMC Saul Falcon, Pedro Cabrera, and Eduardo Rivera. Discuss Critical Components pending items status and follow up, FOMB status that has been submitted to FOMB pending respond by agency, Cooling Tower and Air Heater Basket is pending by Maria Sanchez of Genera for approval.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Review data from Critical components Table with data from Genera Project Status Table 8.07.24B to populate information of new added (24) NME projects with start and end dates, cost of project, PO number and procurement status of project.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working entering data of NTP, start, end, and project duration dates from Asset Suite to critical components tracker for project PO# 106561 regard of Costa Sur Cooling Tower Repair.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega of Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, assisting Mr. Vallejo on cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse to meet with Inventory Supervisor Mr. Juan Vallejo from DCMC. The purpose of the visit is to review the progress achieved so far and clarify any doubt regarding the process. During the visit, I will be performing quality control on the cycle count and assisting Mr. Vallejo with the process.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting held with DCMC HR representatives Mr. Mike Merrit and Ms. Nyah Medina to address a situation involving Mr. Felix Martinez at the Palo Seco warehouse. The purpose of the meeting was to review recent concerns related to workplace conduct and operational procedures.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Luis Tapia Victor Alvarez DCMC Eduardo Rivera, Roberto Bosch and Pedro Cabrera GENERA-PR Herminio Arroyo, Eliseo Martinez. Discuss Critical Components focused on Overhead Crane.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Prepare agenda for meeting of overall status of Critical Components with GENERA PROCUREMENT Sullinet Perez, DCMC Eduardo Rivera, Saul Falcon and Pedro Cabrera.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review narratives of Project 817248 to determine if all components was included.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Discuss of overall status of Critical Components with GENERA PROCUREMENT Sullinet Perez, DCMC Eduardo Rivera, Saul Falcon and Pedro Cabrera.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue review High Level CE of Project 817248 to determine total allocated by projects.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Eduardo Rivera, Roberto Bosch and Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue review narrative of Project 817248 to determine if all components was included.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, RFP-4826 RFC (RGE 3.15.25) Line #40 Fike sent by Gilberto Sucre (DCMC).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, RFP-4826 RFC (RGE 3.15.25) Line #40 Janus sent by Gilberto Sucre (DCMC).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS RG Engineering Presentation - RFP 4826 52 MW Battery Energy Storage System Installation at Cambalache.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, RFP-4826 RFC (RGE 3.15.25) Line #19 VE Structural Drawings, RFP-4826 RFC (RGE 3.15.25) Line #37 Schedule acceleration sent by Gilberto Sucre (DCMC).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today Thursday in the morning I created RFI's and worked with RFI's that needed my attention, I also created submittals, I worked all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with contractor, and meetings with management of Genera-PR. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. That is the stuff and chores I did for today, Thursday in the morning hours.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today Thursday in the afternoon, I created RFI's and worked with RFI's that needed my attention, I also created submittals, I worked all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with contractor, and meetings with management of Genera-PR. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. That is the stuff and the chores I did for today, Thursday in the afternoon hours.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 25%.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 Internal BESS Meeting: BESS project Change Orders Status follow-up and review of contract schedules. Participants from Tesla PMO Group, CSA (Franklyn Colmenares) CDM PM (Gabriel Sepulveda, Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC Contract Manager - (Rafael Calderon)
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 164 | 492 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 Meeting TESLA: Tesla Contract Workshop. Review Change Orders Packages, identify milestones and critical path from construction team. Reviewing Changes procedures and schedules delays. Participants from CSA (Franklyn Colmenares) CDM PM (Gabriel Sepulveda, Carlos Palomares) and DCMC Contract Manager - (Rafael Calderon, Glorimel Torrado, Gilberto Sucre)
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 Internal Meeting: BESS / Peaker's Project Schedule & Budget Meeting. Participants from CSA (Franklyn Colmenares) CDM PM (Gabriel Sepulveda, Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC Contract Manager - (Rafael Calderon)
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Martinez Mendez, Felix | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 5 |  | 152 | 760 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse 019 San Juan, continued conducting cycle counts and recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory record. Today list number 00273, location AD 011 to AD 020, D001 and AL 019 inventory, recount, discrepancies, relocation and variance analysis. Prepared daily report and send to DCMC Manager and Genera.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, conducting cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-017 to AD 025.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at Costa Sur Warehouse, receiving daily instructions on the work to be performed from my DCMC supervisor, Mr. Paul Brown, job briefing on safety and other work-related topics.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, preparing a detail report outlining the work completed throughout which will be submitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, conducting cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-017 to AD-025
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Inventory, recount, discrepancy, min, max cost list 272 AA 018 y 274 AA 023 to 0029
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Inventory, recount, discrepancy, min, max cost list 272 AA 018 y 274 AA 023 to 0029
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre completed conducting cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Inventory, recount, discrepancy, min, max cost list 272 AA 018 y 274 AA 023 to 0029
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | enera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed. Preparing the lists #275 to begin the cycle counts.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting ABC Cycle Counts List # 275. In coordination with the Warehouse Supervisor of Genera PR Adan Silva.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting Recount List # 280 to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. 15 Locations, 15 items and 264 pcs were worked on. This information was validated the employee in charge of Genera PR. Finally, the daily progress report was prepared and submitted to the DCMC manager.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Martinez Mendez, Felix | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 5 |  | 152 | 760 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse 019 San Juan, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory record. Today list number 00273, location AD 011 to AD 020, D001 and AL 019 inventory, recount, discrepancies, relocation and variance analysis.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Teams Meeting Startup with Lauren Wells (Lemoine) to discuss Procore overview and Planner tasks.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue working on Procore Certifications (Procore Financials)
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Creation of Emails Tool SOP documents for Procore Platform. Review existing SOP documentation.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on SOP creation and reviews. Suggestions for new document templates to guarantee operations are executed with precision and uniformity.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on Project Teams at the Genera Portfolio: editing and adding team members.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Coordination and presentation meeting with Franklyn Colmenares (CDM Smith) and Lauren Wells (Lemoine); brief Procore execution and upcoming workload discussion.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 149 | 447 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management - DR4339 Hurricane María - Tesla Project Workshop in DCMC Partners headquarters office at City View. In this hands on workshop participates from DCMC Glorimel Torrado, Gilberto Sucre and Rafael Calderón. From CDM participates Franklyn Colmenares, Carlos Palomares and Gabriel Sepúlveda. In this meeting we discuss pending action items important from field to be completed in order to comply with contract management. We review possible change orders to be presented, schedules of complietion for this project and how the changes can impact the contract to prevent additional fees.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management - DR4339 Hurricane Maria - Update invoices as requested by José Ralat (DCMC) for Sargent & Lundy. Also review invoices in RFI and request updates to vendor.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 149 | 372.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Pre Intevention for CDM Invoice #293566-7_To2_August2024. Continue reviewing notes and identifying what is part of the scope of work and what represent administrative expenses. Also, review amendment on TO2 and compare with the invoice to see if any adjustment is needed.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR4339 Hurricane María - Meeting with Keith Badger (Siemens) and from DCMC Rafael Calderón and Glorimel Torrado to discuss their request to change invoicing date for Milestone 2 and 3 up to October 2025. This is in response of their administrative needs and confirm all deliverables will be in time as contract stipulates. We request a formal notification for this request and share the information of this meeting with Genera.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 149 | 298 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761. Review contract and possible change orders identified, Review on tracker with deliverables key dates and milestones. Prepare for hands on meeting with CDM today at 2pm.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Reviewed emails received from DCMC Michael Merritt regarding the size request for long sleave, reviewed email from Raul Villanueva (DiSignXpress Inc.), and sent email regarding the DCMC Logo in PDF. Review the email from Lemoine Lauren Wells and send the Google Map with the PR Map Sites, including the names of the assigned staff.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Received a call from Harry del Valle (DCMC), who informed me that the hotspots were delivered to the office on Wednesday but were not functioning. I contacted T-Mobile, and Wanda Rodriguez from Customer Service explained that the SIM card must be inserted to activate the hotspot. I then called Harry del Valle to update him on the situation. Additionally, I sent an email to Franklin Colmenares (CS Group) with the Contact Log Per Site document attached. Later, I received a response from Mr. Colmenares indicating that some corrections were needed. Updated the Contact Log per Ste, the necessary adjustments were made, and the revised file was resent by email to Franklyn Colmenares (CSA Group).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: An email is sent to the employees of Cambalache and Vega Baja informing them that those who do not have an ID must report to the Genera office on Monday to obtain it. An email is also sent to Chyenne Blis (DCMC) with the final list for the purchase of shirts. A call is made to customer service (Wanda Rodriguez - T-Mobile) to inquire about the activation of the 12 hotspots. Ms. Rodriguez informs me that to activate the hotspots, Mr. Barry Scanlon (DCMC) must call with the order number and either activate the hotspots himself or authorize someone else to do so; otherwise, the hotspots cannot be used. I then proceeded to contact Frances Vallejo (DCMC) and inform her of the situation. I also resent an email to Mr. Raul Villanueva (DiSignXpress Inc) with the DCMC logo in PDF format.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue reviewing the project management document of the project 4339_9510 BESS_Cambalache project.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR4339 work related on site Cambalache. Review electrical activities from Procore project drawing file to send report data to DCMC Gilberto Sucre due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR4339 work related on site Cambalache. Review structural activities from Procore project drawing file to send report data to DCMC Gilberto Sucre due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of the project management document of the project 4339_9510 BESS_Cambalache project.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data gathering. Development of a Master Tracker for April monthly report that includes project site progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, contract management, critical components and inventory.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS / Peakers Schedule & Budget Meeting" The purpose of the meeting is to discuss projects finances and schedule status and updates. The meeting was organized by Gabriel Perez (CDM Smith). Meeting chair: Carlos Palomares (CDM Smith).
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data. Development of a Master Tracker for April monthly report that includes project site progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, contract management, critical components and inventory.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Fuel for travel to project sites
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 15 | 15 | 15 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. site visit to Vieques facility
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 62.3 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- travel directly from home to Aguirre, round trip, to meet with Mr. Juan Vallejo from DCMC to review the progress made so far and provide onsite support throughout the day to address any questions regarding the process.
2025-04-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 42.14 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Yabucoa Gas Turbine Plant - Genera to home office in Luquillo PR Harry Del Valle 4/03/2025 Travel from Home Office Luquillo to the Yabucoa Gas Turbine Plant (18.106216, -65.823685) to Home Office Luquillo Purpose, Walkthrough the Yabucoa BESS Site with Genera, Beta Electric, Sargent & Lundy, Lord, RG Engineering. Architects and Engineers explain scope of work Construction procedures. Total Mileage 60.2 Miles
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 held weekly PEAKER update and coordination meetings with the Peaker management team. German Nunez hosted, Carlos Palomares CDM Smith and Abraham Velazquez DCMC in attendance(myself)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 completed outline of RFP for demolition scope of work to be discussed at each Peaker site globally.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja MPT Protection meeting to discuss Main transformer protection details between Sargent & Lundy, Homeca and DCMC Team.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Procore - DCMC Financial Tools to discuss tracking of invoices and change orders for the program inclusive of equipment order and project subcontracts. Elizabeth Fronduto, Foster Veazey (Lemoine), Lauren Kennedy, Lauren Wells (Lemoine), Rafael Calderon and Gilberto Sucre (DCMC)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up - Bi-Weekly meeting to review * Staffing Update * IT access issues * Procore Training * Trailers Update * Safety Program * Lean * Projects development Attendees Mike Merritt, Mark Merritt, Foster Veazey, Lauren Wells, Frances Vallejo, Jack Darnall, Anneilia Holton and Gilberto Sucre ( Lemoine/DCMC)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting to discuss PMO Monthly Report format with Frances Vallejo, Raissa Borgess, and Gilberto Sucre (DCMC), and Carlos Palomares (CDM Smith)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed Vega Baja Proposal for Installation Phase, compared pricing and schedules.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Jean Pierre Menay (DCMC) to discuss EHS coordination process and EHS contractual obligation. Finalized response to Vega Baja Audit and discussed Cambalache Site Mobilization Conditions.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Weekly PMO Call with Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Jack Darnall, Barry Scanlon, Mark Merritt, and Mike Merritt (Lemoine/ DCMC)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding new users to Procore and emailing processes out about how to request a new user.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked creating permissions for CPM training lead for prep for 4/8.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to work through getting her PC setup and logging into Procore. Going over tasks items and next steps.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information and getting items in order based off the meeting today with Procore.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Barry Scanlon (DCMC), GIlberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating a document that shows the process for onboarding new users into Procore to share with Nyah Medina (DCMC).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of Procore training with CPM.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy and Tyler Scanlon (Procore, Gilberto Sucre (DCMC), Luis Roman (DCMC), Foster Veazey (Lemoine), Rafael Calderon (DCMC) and others to continue work on build out of financials tools.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing Procore Training Project for CPM to run training on 4/8.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss a task of Procore documents to prepare for training on 4/8 with CPM.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR 4339. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Gilberto Sucre, DCMC and Jack Darnell, Lauren Wells, Foster Veazey, Lemoine. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 184 | 322 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Carlos de Jesus (DCMC) by Procore system and action need by project. Meeting with Gilberto Soto (DCMC) about all projects by Genera.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- TSA (TWIC) process, call with Jose Lopez (DCMC) and Jaime Pesquera (DCMC) Vega Baja Project. Call Gilberto Soto (DCMC) Safety issue Vega Baja Site.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 184 | 138 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Call with Harry Del Valle (DCMC) and Javier Aviles (Portsan) Manager about services in Cambalache Site.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Gilberto Soto (DCMC) to discuss all projects by Genera. Work in Procore Vega Baja Project. Call with Osvaldo de Jesus (GENERA) about scheduled work for tomorrow March 5 2025.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss project status and next steps. We discussed Procore training at CPM on April 8th and staffing. Participants: Jack Darnall (Lemoine), Gilberto Sucre (DCMC), Anneilia Holton (DCMC), Mark Merritt (DCMC).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - In person meeting with Carlos Palomares (CDM) and Raissa Borges (DCMC) to discuss budget and scheduling reporting and organizing the data to include in the monthly report to the client.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Jesus Cintron (Genera) to discuss project status and RFP strategy.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Barry Scanlon (DCMC) and Carolyn Baez (DCMC) to discuss coordination with T Mobile to discuss hotspots activation for the 8 sites.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Carlos de Jesus (DCMC) to discuss PM Organizational chart, Administrative matters and Cambalache update.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Technical Support RFP - Finalized requisition form and requisition memo required for the upcoming Technical Support RFP.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Initiated the development of the requisition package for the upcoming Technical Support RFP, as requested by Jesús Cintrón (Genera). Began assembling key components of the package, including the requisition form and requisition memo. Reviewed relevant procurement guidelines to ensure compliance with internal requirements and alignment with the project's objectives. Coordinated with internal stakeholders to gather preliminary inputs and prepare for subsequent reviews and approvals.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 184 | 644 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Performance Metrics Reports: Continued reviewing the performance metrics reports from the power plants to generate the Power Production and Fuels Consumption report for March 2025. Discussed data entry issues with Jan Rodríguez from Genera PR to request corrections from the power plant managers.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 184 | 644 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Final Review of Performance Metrics Data: Continued reviewing the performance metrics data from the power plants with Jan Rodríguez from Genera PR in preparation to submit the final Power Production and Fuels Consumption report on April 7, 2025.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Weekly Meeting: Participated in the DCMC weekly meeting to discuss project statuses in preparation for the client's weekly status meeting. Participants from DCMC: Mark Merritt, D'Alexzander Gonzalez, Roberto Bosch, Saul Falcon, Eisha Mercader, Esther Rohena, Jose Ralat, Pedro Cabrera, Rafael Calderon, Victor Maldonado, Marc Maceira, and MSC Shellsea Maysonet.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 30% Day 2
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Gilberto Sucre DCMC to review the response letter for Genera PR regarding the EHS finding report by Gustavo Vázquez Vázquez. MS Team meeting with Sargent and Lundy Team. Enness Dean, THOMAS.K.CAVALCANTE@sargentlundy.com; "Cellentani, Eugene E" <EUGENE.E.CELLENTANI@Sargentlundy.com>;reinaldo.romeroquinones@sargentlundy.com,francisco.mathewslopez@sargentlundy.com.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria—Review of GWC's daily scope of work with Carirma Sanchez from HOMECA for the specific activities, deliverables, and outcomes of the project. Following Daily activities and pending items status in PROCORE.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Picking up material for the Cambalache office trailer.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Picking up material for the Cambalache office trailer.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Picking up additional material for the Cambalache office trailer.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Drop off Materials at Cambalache Office Trailer.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Site inspection in the overhead crane area, a report of the foundation and structure is generated as part of the work. An inspection is carried out in the area of the bridge located on Highway # 681 where the location of a double container pipe is documented.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continuation of work on the installation of DCMC temporary office with Harry Del Valle (DCMC)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with critical component tracker to upload information from Asset Suite. Meet with Sheila Torres of DCMC to provide information regard of Genera Legal Depart for RFP approval flow and also from P3A and FOMB, she will provide update of dates by next week. Provide assistance to Raissa Borges of DCMC in regard of critical components table to be used for PMO reporting, share CCL table for the most accurate information regard of CC projects.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Receive authorization by Jorge Sanchez of Genera to use Genera share point for access of Genera Projects Status Table 8.07.24B. Working with the critical component tracker to verify if new project added by NME can be identified an RFP# or PO# using the Genera Projects Status Table 8.07.24B.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working in correction on critical components tracker tab Installation Simple Table to fix error on formula, reviewing CCL tracker with RFP delivery dates for data entry.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing new table created for FEMA Cost Estimate Critical Components and NME, the table was created by PMO team, the table was found an error on the total sum of FEMA CC project and was required to be compare with the resolution 20241028, the table was fixed error found on formulas with correction an accurate data is provided on CC costs. Working PMO weekly report regard of critical components work activity completed action items and tracking upcoming activity. Contact Luis Danudt of DCMC he will provide picture in regard of Cambalache Overhead Crame and Leak Detection System located at a bridge near Cambalache.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Pre-Meeting with participation from DCMC: D' Alexzander Gonzalez, Rick Patterson, Rafael Calderon, Eisha Mercader, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Marc Maceira, Danny Martinez, Annelia Holton, Rick Patterson, Christian Cruz, Sheila Torres, Rafael Cordero, Sheila Torres and Roberto Bosch; Integrum Keylamerari Sierra, Jorge Aponte, Carlos Gonzalez, to discuss draft presentation priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process before presenting to Genera PR.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting with Ms. Maria Sanchez, CFO, and Mr. Anthony Vega from Genera to discuss the overall status of the warehouses, with a particular focus on the recent situation at the Palo Seco facility.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse to meet with Inventory Supervisor Mr. Giovanni Taffanelli from DCMC. The purpose of the visit is to review the progress achieved so far and clarify any doubt regarding the process.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting held with Mr. Jackson Cartagena, San Juan warehouse supervisor from Genera, to inform him of the decision made regarding Mr. Felix Martinez and to review the current progress of the warehouse cycle count.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Genera corporate office, preparing comprehensives report of all warehouses for Mr. Anthony Vega. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Once the report was completed, I reviewed it with Mr. Vega to ensure there were no outstanding questions or concern.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- TEAMS meeting held with Ms. Nyah Medina from DCMC HR to address the situation involving Mr. Felix Martinez, who was assigned to the Palo Seco warehouse.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria.Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consultant Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue updating CCL Tracker: Making adjustments to the logic and commands of the CCL Tracker to optimize its use and enhance its autonomous functionality, particularly in calculating key performance indicators such as costs and days of delay.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue updating CCL Tracker : Using the available information, such as the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components, I have developed a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review High Speed Control proposal form GE. Controls Upgrade to Mark VIe Upgrade (GT11 NM) Excitation Controls System Upgrade to EX2100e BOP Controller Upgrade Electrical Systems (budgetary).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review GT Fully Blade current status of possible that its components will be removed from Critical Components List.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue review High Level CE of Project 817248 to determine total allocated by projects.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS call with Carlos De Jesus, DCMC, to discuss about the most rencently construction schedule of Cambalache Power Plant.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS call with Gilberto Sucre, Harry del Valle DCMC, to discuss the toilet cabins, hotspot trailer office of projects near Cambalache.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, BESS& Peakers Milestone Schedule 4 Apr 25 - sent by Gilberto Sucre (DCMC).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Send submittal documentation of the Cambalache BESS Program, BESS & Peakers Milestone Schedule 4 Apr 25, Master Schedule/ COD Table Update 4Apr25 - to Carlos De Jesus (DCMC).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS contacted Carolyn Baez DCMC to confirm that Carlos De Jesus DCMC signed Genera PR, Tesla's NDA document.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS call with Frances Vallejo, DCMC, to discuss about the most rencently construction schedule of Cambalache Power Plant.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS call with Herminio Arroyo, Genera PR, to discuss about to privide the existing construction drawing underground area of Cambalache Power Plant .
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS call with Eduardo Rivera, DCMC, to discuss about the existing construction drawing underground area of Cambalache Power Plant .
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, BESS&Peakers - Master Schedule/ COD, Peakers - sent by Gilberto Sucre (DCMC).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- This morning, I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with the contractor and meetings with the management of Genera-PR. These were my chores for today, Friday 4th of April 2025.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- This afternoon I did the same stuff, I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. I also answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I also supervised the contractor Homeca, I handled meetings with the contractor and meetings with management of Genera-PR. These were my chores for today, Friday 4th of April 2025.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 35%. Day 2, inspected Excavator
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria_PW11855 Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Contract Management Meeting- Procore - DCMC Financials Tools. Reviewing Change Orders procedures and procore functionalities to manage changes on project contract and process of submittals and acceptance of the changes.. Participants (DCMC Rafael Calderon, Glorimel Torrado, Gilberto Sucre, Lauren Wells, HOMECA Elizabeth Fronduto)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #293410-11 for TO#1 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Pre-Meeting [In-person] Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team)
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting ABC Cycle Counts. In coordination with the Warehouse Manager of Genera PR.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. Meeting with my supervisor, Mr. Paul Browne of DCMC, to discuss the week's work, goals, and receive work instructions
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, conducting cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-026 to AD-043 manually, because Asset Suite is not working the Cycle Count informe.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, conducting cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-026 to AD-043 manually.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Extract the costs of items inventoried from March 18th to the present day, everything inventoried up to that day and prepare a weekly report.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Extract the costs of items inventoried from March 18th to the present day, everything inventoried up to that day and prepare a weekly report.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre completed conducting cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Extract the costs of items inventoried from March 18th to the present day, everything inventoried up to that day and prepare a weekly report.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed. Preparing the lists to begin the cycle counts.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting old Recounts List to verify inventory accuracy,
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Investigating any discrepancies to ensure proper stock control and alignment with inventory records. This information was validated the employee in charge of Genera PR,. Finally, the daily progress report was prepared and submitted to the manager, DCMC.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 4.5 |  | 151 | 679.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria IT Support/ Meeting with Lauren Wells (Lemoine) / Procore Zoom Meeting for Change Orders and Financial Contracts, Work through getting PC setup and logging into Procore.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore meeting and discussion for Change Orders integration with Lauren Kennedy (Procore), Foster Veazey (DCMC), Mac Tomlinson (Procore), Lauren Wells (Lemoine), Theresa Perez (DCMC), Glorimel Torrado (DCMC), Rafael Calderon (DCMC) and Gilberto Sucre (DCMC).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on creation and editing of Procore SOP documentation to streamline and coordinate team activities by setting clear process execution guidelines.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Project Teams Setup in Procore Platform for all BESS and Peakers projects with updated Program Staff Chart.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of BSEE and Peakers projects cost and budgets projections on Procore to help plan and manage budgets, allocate funds, evaluate alternatives, and control costs.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review SOP documentation for creation of new Procore platform tool's SOPs to optimize operations, promote uniformity, serve as a guide for sustaining quality and efficiency during operations, and achieve safety standards and superior performance levels.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Genera Pre-Meeting with participation from DCMC: José Ralat, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and Marc Maceira from DCMC, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable - Project Management - DR4339 Hurricane Maria - Prepare email requesting Asset Suite training for monday, review emails with new invoices pending. Also, update presentation for monday according to new correspondence.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339- Hurricane María - Meeting to discuss Procore process for change orders in contracts. In this meeting participates from DCMC Theresa Pérez, Luis Román, Rafael Calderón, Foster Veazey, Gilberto Sucre, Lauren Wells & Glorimel Torrado, and from ProCore Mac Tomlinson and Lauren Kennedy.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.75 |  | 149 | 558.75 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Pre Intevention for CDM Invoice #293566-7_To2_August2024. Finish reviewing invoice notes, compliance review of all deliverables for this invoice. Prepare formal RFI. Review master agreement contract for expenses in this invoice. Send RFI by email and update tracker with information for meeting today.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: I am on a call with Barry Scanlon to confirm that one of the 12 hotspots received in City View is working. Activated and configured 9 hotspots that will be used on the sites.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review of the project management document of the project 4339_9510 BESS_Cambalache project.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in create a time impact photo report and review project activities from project schedule to send report data to DCMC employee Luis Damudt due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 related on site Cambalache MS Teams meeting for review RFP documents on pending construction timing, submittals documents and value engineering status with DCMC Gilberto Sucre and Sargent & Lundy staff due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in review mechanical activities from Procore drawing file to send report data to DCMC employee Gilberto Sucre due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with RGE about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue reviewing the project management document of the project 4339_9510 BESS_Cambalache project.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 122 | 183 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. In person meeting at DCMC Office. The purpose of the meeting is to discuss projects finances and schedule status and updates for reporting purposes. Meeting participants: Frances Vallejo (DCMC) and Carlos Palomares (CDM Smith).
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 122 | 366 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data. Development of a Master Tracker for April monthly report that includes project site progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, contract management, critical components and inventory.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data. Development of a Master Tracker for April monthly report that includes project site progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, contract management, critical components and inventory.
2025-04-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data. Development of a Master Tracker for April monthly report that includes project site progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, contract management, critical components and inventory.
2025-04-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 40%. Day 3
2025-04-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued supervising daily activities performed by the GWC - HOMECA Recycling to reduce carbon emissions, conserve natural resources, minimize landfill waste, and reduce energy consumption.
2025-04-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Supervising daily activities performed by the GWC - HOMECA Recycling to reduce carbon emissions, conserve natural resources, minimize landfill waste, and reduce energy consumption.
2025-04-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 50%. Day 3
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 873.5 | 873.5 | 873.5 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Airfare (Basic Economy) for Foster Veazey's trip from Mobile, AL to San Juan, PR.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 765 | 765 | 765 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) travelled from BZN to SJN for meetings and Procore training in-person.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 284.49 | 284.49 | 284.49 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Hotel Lodging for Foster Veazey for 1 night in San Juan, PR ($244 lodging, $23.49 Taxes, $17 fees)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 261.6 | 261.6 | 261.6 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) lodging for 4/7 for meetings with Genera, DCMC and Lemoine for project planning.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 meeting on Peaker's weekly check in meeting with team, led by German Nunez Peaker's PC., and Rafael Pabon, Carlos Palomares CDM Smith. Discussed and reviewed possible lessons learned from Bess projects issues.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Reviewed and marked up with comments GENERA and S&L RFP and safety plans for demolition portion for Costa Sur facility / project.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence update - managed e-mail correspondence for PMO.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Weekly Update with DCMC Project Team Luis Damudt, Luis Duque, Carlos De Jesus & Jorge Mercado. reviewed activities for the current week.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Meeting with Jean Menay (DCMC) in preparation of afternoon meeting with Osvaldo de Jesus and Victor Rodriguez for EHS Procedures.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO EHS Permits Process and Procedures Implementation meeting between Victor Rodriguez, Osvaldo de Jesus, Jean Pierre Menay and Gilberto Sucre (DCMC)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache & Vega Baja Internal coordination Gabriel Perez & Franklyn Colmenares (CDM Smith) Update on Vega Baja weekend work, Temporary Transformer Protection & Phase 2 concerns. Cambalache review agenda for RFC with RGE meetings for the week.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja discussion with Jose Lopez (DCMC) & Mike Kuczynski (S&L) if the Temporary Protection for the transformer required or not a roof protection. It was decided not to provide.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check In - Weekly Update of Program led by Gabriel Perez CDM Smith with participation from CDM Smith, CSA Group, Sargent & Lundy, Genera & DCMC Partners.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 225 | 393.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting to discuss Auxiliary RFPs and equipment list. The purpose is to define auxiliary works that can be advanced to comply with CODs led by CDM Smith Carlos Palomares. attendees Abraham Velazquez (DCMC), Franklyn Colmenares, Gabriel Perez, Enrique Laya (CDM Smith) & Mike Kuczynski (S&L). Covered specifics for three sites: Cambalache, Costa Sur & Aguirre.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Andres Concepcion - DCMC Site Manager introduction & Project updates. BESS Program Schedule Budget Contractor Selection
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Nelson Rosado, Ricardo Pallens, Carlos Palomares, Joaquin Quinoy, Gabriel Perez, Mike Kuczynski, Franklyn Colmenares (Genera), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejando Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore settings with Theresa Perez (DCMC).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondence for Procore financials with Esther Rohena (DCMC), Rafael Calderon (DCMC), Gilberto Sucre (DCMC).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on reviewing documents structure proposed by Theresa Perez (DCMC) for Procore. She made recommendations for revamping the folder structure.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore Permissions for Theresa Perez (DCMC) and permissions for the AE role for publishing Drawings in Procore.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore training with CPM, who is conducting the training on 4/8.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review the Genera Manual of Health and Safety by employees. Meeting with Gilberto Sucre (DCMC), Victor Rodriguez (GENERA), Osvaldo de Jesus (Genera) about all project health and safety procedures.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-s). Meeting call with Osvaldo de Jesus (GENERA) to discuss Health and Safety issues.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Vega Baja site inspection work. Security Meeting with Homeca (Emanuel Santos and Issac Morales).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review the Health and Safety contractor Manual by Genera.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discussion with Gilberto Sucre DCMC regarding the staffing update and reorganization per site.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS Check In and Peakers check in meeting to discuss the projects status by site, RFP discussion and next steps. Participants: Giberto Sucre, Abraham Velazquez, Raissa Borges, Sheila Torres, Rafael Calderon (DCMC), Mike Shieiski (S&L), Gabriel Perez (CDM), Carlos Palomares (CDM), Franklyn Colmenares (CSA).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Inventory Management meeting with Paul Brown (DCMC) and Raissa Borges (DCMC) to discuss inventory reporting.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Researched, reviewed, and summarized Governor’s Executive Orders 2025-002, 2025-003, 2025-005, and 2025-015 to support the development of a formal letter and strategic approach aimed at amending a COR3 internal regulation. Drafted a formal letter requesting a policy adjustment to allow COR3 to issue additional working capital advances prior to the full expenditure of the existing advance shared with D'Alexzander González (DCMC) and Jesús Cintrón (Genera)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Resumed discussions regarding the Jaca & Sierra contract with Glorimel Tirado (DCMC) and Franklyn Colmenares (CDM Smith), focusing on contract management practices and their potential implications for federal reimbursement eligibility. Specifically analyzed how the fixed-price/lump-sum structure of the contract aligns with FEMA funding requirements, and whether the current administration of the contract could impact the reimbursement process. Subsequently engaged in follow-up discussions with D’Alexzander González (DCMC) and Fernando Ortiz (Genera Legal) to further evaluate compliance considerations, identify any risks, and explore possible strategies to ensure alignment with federal funding guidelines
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Peakers Weekly Check in with Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares (CDMSmith), Mike Kuczynski (S&L), D'Alexzander Gonzalez (DCMC) and Jesus Cintron (Genera)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Held an in-depth discussion with José Ralat (DCMC) regarding the Tesla, Siemens and GE contracts, with a focus on cash flow management and the project’s payment schedule. Reviewed current financial constraints stemming from COR3 regulations, specifically the limitation preventing the issuance of an additional advance until the existing advance has been fully expended. The conversation aimed to identify practical solutions that maintain project momentum while ensuring compliance with funding requirements.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Maria Sanchez Bras, and Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Marc Maceira, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: SM Consulting Shellsea Maysonet, and Johanna Díaz, Integrum Carlos González and MZL Ginnell Torres.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Held a discussion with Daniel Hernández (Genera) regarding his upcoming legislative hearing (04/09) and the specific federal funding information required for his presentation. He requested a clear and concise breakdown of the total amount of federal funds allocated to Genera, the amount already reimbursed, and the remaining balance pending reimbursement. Following this discussion, coordinated with José Ralat to review the relevant financial data and ensure accuracy and consistency in the figures to be presented. The objective was to support Daniel with precise, well-documented information for effective and transparent communication before the Legislature.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Performance Metrics: Collaborated with Jan Rodríguez, José del Río, José Carrasco, and Josué Sánchez from Genera PR to continue reviewing the performance metrics submitted by the power plants. During the reviews, discrepancies in fuel consumption at Palo Seco plants were identified and corrected, which were due to reporting errors. Additionally, the team recognized the need for a fuels consumption variance report to better track and manage future discrepancies.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Conducted testing in the Genera Connect Financial Tracker (v2) development environment from within the GeneraPR network, focusing on troubleshooting issues related to uploading financial report data. - Updated the GeneraPR status slide deck with the latest project information and milestones to reflect current progress and action items. - Participated in the weekly client meeting to provide project updates, address roadblocks, and align on upcoming deliverables. Attendees from GeneraPR: Maria Sanchez, Alejandro Maymi; from DCMC: Mark Merritt, D’Alexander Gonzalez, Rafael Calderon, Esther Rohena, Eisha Mercader, Saul Falcon, Marc Maceira; from Integrum: Carlos Gonzalez - Began reviewing the March 2025 Power Generation and Fuels Consumption report data to validate inputs and identify any issues.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 95%. Day 4
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - I called Carolyn Baez-Nieves (DCMC) regarding the hotspot and mentioned that my hotspot is not working on my phone. Mrs. Baez-Nieves called T-Mobile, and the service representative, Christopher Rodriguez, and Mrs. Baez-Nieves worked on resolving the connection issue with my phone. Mr. Rodriguez informed me that Mrs. Baez-Nieves needs to contact T-Mobile corporate to proceed with the connection, as the issue is with the SIM card not functioning.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working in progress weekly report and supervising the Daily activities, such as the fabrication of the Main Power Transformer protection by the GWC. (HOMECA Recycling).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 |  | 167 | 542.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Progress Report preparation to provide the project's current status, inform how things are progressing, indicate if the project is on track, and detail any challenges or risks emerged.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on QA/QC Forms and Checklists for the BESS Projects. Verifying specifications to create QA/QC Plan.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on QA/QC Forms and Checklists for the BESS Projects. Continued verifying specifications to create QA/QC Plan.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review Application Note: Elevated Megapack Installations sent by Mike J. Kuczynski Sargent & Lundy.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review the project management value engineering document for BESS cambalache project.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Weekly meeting of the Cambalache project with DCMC staff, Gilberto Sucre, Luis Damudt, Luis Duque.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review RG Engineering Presentation - RFP 4826 52 MW Battery Energy Storage System Installation at Cambalache.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera + Deliverable 11- DR4339 - Cambalache - Project scope of work documentation review for project management activities planning.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera PR +Deliverable 11 - DR4339 - Cambalache - Meeting with Frances Vallejo (DCMC) and Gilberto Sucre (DCMC) to discuss Site Manager role supervising construction site and managing project to ensure the company completes it on time, within budget and in compliance with regulations.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Send an email to Waldo Cordova of Genera requesting to provide information related to PI-DAS System, for this project was revised on Asset Suite to verify if they have an existing RFP. Updating the Critical Components Tracker for PO# 104413 with information provided by Roberto Bosh of DCMC regard of quantity of equipment.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing the Critical Component Lead Tracker for the new tab "FEMA/Cost Estimate/Crit. Comp." that summary the total cost of CC and NME project including equipment and installation per each project. Boiler Recirculating Pump PO# 107030 was reducing the quantity from (12) to (10), because (2) of the equipment will be purchase under a Legacy Project. Reviewing the SOW and CE send by Diana Rivera of CPM in regard of the SJ U5 Condenser Continues Cleaning System of PO#106758.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Review data from Critical components Table with data from Genera Project Status Table 8.07.24B. Working with weekly report for PMO related to Critical Components projects.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Review of project PI-DAS System of Mayaguez with existing RFP 00003185 which are similar project, but the one with RFP 00003185 is for PI-OPC Emission System, we are looking for project description to provide information to CPM. Send an email to Diana Rivera of CPM with picture of Overhead Crane and Leak Detection System.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, D' Alexzander Gonzalez, Paul Brown, Jose Ralat, Rafael Calderon, Esther Rohena, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Keylamerari Siera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez, Jesus Cintron and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Genera corporate office, preparing comprehensives report of all warehouses for Mr. Anthony Vega of Genera. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Once the report was completed, I reviewed it with Mr. Vega to ensure there were no outstanding questions or concern.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at DCMC office collecting the recently delivered safety equipment and organizing the necessary information for the scheduled TEAMS meeting with Genera, which takes place on Mondays at 10:00am
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting with Mr. Anthony Vega from Genera to return the computer previously assigned to former DCMC employee Mr. Felix Martinez. I also requested an update on the status of the Asset Suite program, which has been inoperative for several days.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-phone meeting with Mr. Anthony Vega from Genera to identify the issue we are experiencing with the Asset Suite program, as it currently not allowing any transactions related to the cycle count.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting with Ms. Frances Vallejo, PMO at DCMC, and Ms. Raissa Borges of DCMC to discuss the details of our upcoming meeting and establish the format for our weekly meetings.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Met at the DCMC office with Mrs. Carolyn Baez (DCMC), receiving the hotspots that will be delivered to the various PREPA/Genera warehouses.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- meeting held via TEAMS with Ms. Maria Sanchez of Genera, and staff of DCMC to discuss the weekly progress of the projects.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez Bras and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Updating CCL Tracker : Using the available information, such as the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components, I have developed a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop High Level CE of Project 817248.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue updating CCL Tracker : Using the available information, such as the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components, I have developed a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Review and communicate to DCMC responses provided by GENERA-PR regarding to GT Fully Blade.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR4339 - Meeting DCMC: D'Alexander Gonzalez, Pedro Cabrera and Roberto Bosch, review critical component tracker list, review duplicated item with legacy generation assets, identify critical components where can be mark as duplicates, but is not duplication is additional quantity and item that was eliminated on LGA in amendment.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, Asbetos and lead report cambalache sent by Gilberto Sucre (DCMC).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting with Carlos De Jesus DCMC Partners Possible impact and comments in schedules. Find attached information of possible impact from adjacent projects and a preliminary report of RFP vs Value Engineering Preliminary to use in schedule meeting of tomorrow. .
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today, I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca, I handled meetings with the contractor, and meetings with same people every week. Gabriel Perez, Franklyn Colmenares, Manuelly Concepcion CDM Smith. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. These were my chores for today.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today, I did the same stuff as in the morning, I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca, I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. These were my chores for the day.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 95%. Day 4 Received excavator from Homeca and uploaded information to ProCore.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 164 | 123 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Peakers Check-In meeting with project management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Meeting between Siemens Energy team , CMD Smith PM team (Carlos Palomares, Juan Mendoza), Sargent & Lundy (Mike K., Miguel del Valle) Genera (German Nunez) CSA (Franklyn Colmenares) and DCMC (Rafael Calderon, Frances Vallejo).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Continue working on Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Fed Funds Cash Flow - BESS & Peakers Payments. Meeting for Payment Milestones and Financial reconciliation opportunities review. DCMC participants (Jose Ralat, Mike Merritt, Esther Rohena, D'Alexander and Rafael Calderon). From Genera (Maria Sanchez, Jesus Cintron, Kevin Futch)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Pre-Meeting [In-person] Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team) from Genera (Alejandro Maymi, Maria Sanchez and Jesus Cintron).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #293566-8 for TO#2 Sept 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.25 |  | 164 | 205 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team , CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczinski.), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Frances Vallejo).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed. Preparing the lists to begin the cycle counts.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse, manually performing cycle counts by location while resuming reporting functionality in the system, then transferring the collected data to the report and continued entering it into the system and performing recounts to verify inventory accuracy and investigate any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-044 to AD-061 manually.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse, manually performing cycle counts by location while resuming reporting functionality in the system, then transferring the collected data to the report and entering it into the system and performing recounts to verify inventory accuracy and investigate any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-044 to AD-061 manually.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. inventory, recount, min & max, cost, and variances from AA 052 to AA 072
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Inventory, recount, min & max, cost, and variances from AA 072 to AA 082
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. inventory, recount, min & max, cost, and variances from AA 052 to AA 072
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, preparing a detailed report outlining the work completed throughout, which will be submitted to my supervisor from DCMC Paul Browne, to support the preparation of his report to Genera PR.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, conducting ABC Cycle Counts. In coordination with the Warehouse Supervisor of Genera PR Adan Silva. Consolidating count lists (Count List #76, 116 and Recount #78, 126 from warehouse A19 San Juan), attaching documentation in the new format.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, conducting ABC Cycle Counts. In coordination with the Warehouse Supervisor of Genera PR Adan Silva. Consolidating count lists (Count List #130 and Recount #131, 150 from warehouse A19 San Juan), attaching documentation in the new format.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore - Training Project Site / Creation of Project File Structure for Future Training Meetings
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Gather SOP reports for upload into Microsoft Teams channel folder (Submittals and Email's SOPs) to bring consistency across operations and ensure regulatory compliance and overall efficiency.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Procore Core Tools SOP for a dynamic platform that allows for instant updates, easy sharing, and seamless collaboration among teams.: Reviewed emails and RFI.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 151 | 37.75 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Started Procore Certifications (Engineer Certification)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 151 | 113.25 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Check-in meeting for the Peakers projects. Minute and meeting hosted by Carlos Palomares (CDM Smith). Also in the meeting: Francisco Santos, Abraham Velazquez, Raissa Borges, German Nunez, Rafael Calderon, Frances Vallejo, Sheila Torres.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 151 | 113.25 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Finish the Procore Financials certification.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.25 |  | 151 | 188.75 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on SOP reviews for Procore main Core Tools; review of team's organization chart to assembly Project Teams in Procore platform.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Check-in meeting for the BSEE projects. Minute and meeting hosted by Franklyn Colmenares (CDM Smith). Also online: Gilberto Sucre, Rafael Calderon, Frances Vallejo (DCMC)
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Obtaining Procore Certificacion (Procore Financials).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - Siemens Energy Contract #00106588 review contract for clarification on change orders and request for payment changes. Findings were discussed with Rafael Calderón (DCMC).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Meet with Gabriel Pérez Quiles (Genera) and Marc Maceira (DCMC) to configure Asset Suite Account. This process will allow me to verify CPA creations and final payment for invoice that were completed in Pre-Intervention process. This process was not finished, and a ticked requesting support was opened.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Discussion with Franklyn Colmenares (CDM Smith) and Sheila Torres (DCMC) about pending legal advice for Jaca y Sierra Invoice. This invoice has two issues: 1) lump sum contract and invoice are per item as described in proposal and 2) contract refers to price proposal revision 2 and invoice is based on price proposal 3. DCMC and Genera legal are working on this review and I was following up because the invoices are in RFI by now.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María ¦ Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and Marc Maceira. Also, Shellsea Maysonet (MZC); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Franklyn Colmenares (CDM Smith) request clarification on RFI sent for Homeca Invoice. We review the invoice and the request for information. After verifying all the items there are still missing item #6 and #13, Item #15 was clarified in this discussion.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 139 | 486.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Phone call with Manuely Concepcion, Nelson Soler (CDM Smith), and Franklyn Colmenares regarding assistance for the Procore Training in person at the CPM Office. Reading an email sent by Luis Roman and Abraham Velazquez (DCMC) regarding the PROCORE Training. I emailed Jose Lopez (DCMC) the Employee Equipment Form regarding the T-Mobile Hotspot and SIM card. Updating the NDA form for Andrés Concepción (DCMC), photocopying the NDA for his initials and signature. Ordering lunch and buying snacks for the PROCORE training at the CPM offices.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Activated and configured 3 hotspots that will be used on the sites. I had a call with Manuel Felix (T-Mobile) to activate the 12 SIM cards for the hotspots received in City View Plaza DCMC office and confirm they are working.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: I had a Phone call with Mr. Jose Lopez DCMC regarding the hotspot, during which he mentioned that his hotspot is not working on his phone. I called T-Mobile, and the service representative, Christopher Rodriguez, along with Mr. Jose Lopez, worked on resolving the connection issue with Mr. Lopez's phone. Mr. Rodriguez informed me that I should contact T-Mobile corporate to proceed with the connection, as the issue is with the SIM card not functioning. Phone call with Samaida Mojica (T-Mobile) to notify her that the SIM cards are not working in the hotspots. Mrs. Mojica proceeded to send a message to Mr. Manuel Félix (T-Mobile) asking him to contact me after 10 a.m. to resolve the issue with the SIM cards in the hotspots. Email sent to Naomi Ortiz (CPM) to coordinate the delivery of lunch boxes for the Procore Training at the CPM Office. Mrs. Ortiz (CPM) contacted me by phone to provide the delivery location and office details.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache project update meeting with Frances Vallejo (DCMC), Gilberto Sucre (DCMC) for 4339_9510 BESS_Cambalache project
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 related on site Cambalache coordination, review RFP documents, creating impact reports related to construction site, submittals documents reviews and value engineering review with Project Superintendent Luis Damudt DCMC due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 related on site Cambalache coordination, review RFP documents on pending construction timing, submittals documents reviews and value engineering review with Project Superintendent Luis Damudt DCMC due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue reviewing the project management Value Engineering proposal document of the 4339_9510 BESS_Cambalache project.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 134 | 469 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the project management Value Engineering proposal document of the 4339_9510 BESS_Cambalache project.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In". The purpose of the meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintron (Genera PR). Meeting chair: Carlos Palomares (CDM Smith).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal Teams Meeting with Frances Vallejo, DCMC and Paul Browne, DCMC. The purpose of this meeting was to discuss Inventory project status and updates.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In". The purpose of the meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintron (Genera PR). Meeting chair: Franklyn Colmenares (CDM Smith).
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Project master tracker and project progress dashboard development on Power BI platform for April monthly report.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 122 | 427 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Project master tracker and project progress dashboard development on Power BI platform for April monthly report.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from BZN>DEN>SJN for project management purposes.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 34.78 | 34.78 | 34.78 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from Airport to DCMC office for Foster Veazey.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 15.13 | 15.13 | 15.13 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from DCMC office to hotel for Foster Veazey.
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 21.56 | 0.7 | Yes | 25-145003 | Site Inspector- Luis O. Damudt Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Route- Calle # 6 B19 Urb. Isabel la Catolica Aguada PR00602 to El Mesón Sandwiches - Mayagüez Terrace Avenida Eugenio María De Hostos Mayagüez, 00682 (18.212567, -67.147476) Meeting with Carlos De Jesus Schedule for discussion the times scheduling task Power Plant Cambalache. Back to Home Calle # 6 B19 Urb. Isabel la Catolica Aguada PR00602. Date- April 7, 2025 Claiming Mileage for this route- Calle # 6 B19 Urb. Isabel la Catolica Aguada PR00602 to El Mesón Sandwiches - Mayagüez Terrace Avenida Eugenio María De Hostos Mayagüez, 00682 for iMeeting with Carlos De Jesus Schedule for discussion the times scheduling task Power Plant Cambalache Purpose- discussion the times scheduling task Power Plant Cambalache. Calle # 6 B19 Urb. Isabel la Catolica Aguada PR00602.. TOTAL MILEAGE- 30.8 miles
2025-04-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 6.16 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Mileage from Home to airport
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Merritt, Mark | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 589.68 | 589.68 | 589.68 | Yes | 25-145003 | Contruction Site Trailer Rental with Stairs for the Vega Baja site for the period of April 13-30. Credit card payment was combined with the Cambalache trailer and stairs.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 261.6 | 261.6 | 261.6 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) lodging for 4/8 for meetings with Genera, DCMC and Lemoine for project planning.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence and adding a new user to Procore.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 continued on my own to review the Costa Sur Demolition RFP with comments
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 held meeting to comment on Sargent & Lundy scope of work for Costa Sur demolition project. German Nunez (PEAKERS) Rafael Pabon (CDM Smith) Carlos Palomares (CDM Smith)
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Reviewed contract with RGE comments and responses from Genera.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Continuation Meeting with Andres Concepcion -DCMC Site Manager on Scope of Work, Project Status, Contractor Selection, BESS delivery dates, Project Team, and Project challenges but with DCMC Project Team Luis Damudt, Luis Duque, Jorge Mercado and Carlos de Jesus.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Meeting with Andres Concepcion -DCMC Site Manager on Scope of Work, Project Status, Contractor Selection, BESS delivery dates, Project Team, and Project challenges.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed Draft Quality Manual prepared by Harry Del Valle DCMC.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache RFC Meeting RGE continued evaluation of Value Engineering alternatives, schedule and design information exchange between RGE and Sargent & Lundy. Also discussed site access requirements. Present Sargent & Lundy, RGE, DCMC, CDM Smith, and GENERA.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Review update presentation for BESS and Peakers requested by Daniel Hernandez from Genera with Carlos Palomares from CDM Smith.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Project Status update discussion with Jose Lopez DCMC on 2nd Phase of Lead Abatement progress, anticipated completion, Lead Free Documentation, Demolition Plan approval plan and start date.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache. Internal Schedule review of RGE proposed value engineering schedule. Gilberto Sucre provided an overview of operations and introduced key concepts in value engineering, followed by CDM Smith Carlos Palomares’ aligned remarks. DCMC Carlos De Jesus led a discussion on stakeholder management, emphasizing the importance of effective communication and collaboration. The meeting highlighted team transitions, including the introduction of a new team member who will assume responsibilities for value engineering, alongside a brief mention of payment concerns. Finally, Gilberto confirmed project details and acknowledged the contributions of attendees before concluding the meeting. Action items were assigned to oversee the transition of responsibilities, follow up on the stakeholder management plan, and review engineering mini batch plantations.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 225 | 675 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) attending Procore training lead by CPM. We covered the following topics; Individual profiles, education, support, Home review, Document review, and drawings. Users attending were Frances Vallejo (DCMC), Abe Velaquez (DCMC), Luis Roman (DCMC), Jaime Pesquera (DCMC) and others.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on updating weekly update report for Procore items for Raissa Borges (DCMC) .
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 225 | 787.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) attending Procore training lead by CPM. We covered the following topics; RFI's, Submittals, Photos, Daily Logs, and Reporting. Users attending were Frances Vallejo (DCMC), Abe Velaquez (DCMC), Luis Roman (DCMC), Jaime Pesquera (DCMC) and others.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence and settings with Rafa Pabon (CDM Smith) and Franklyn Colmenares (CSA) for publishing drawing reviews for S&L.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondence for Procore items
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions and removing CPM from the VB project that we used to look at during their training today.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Merritt, Mark | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 196.56 | 196.56 | 196.56 | Yes | 25-145003 | Contruction Site Trailer Rental with Stairs for the Cambalache site for the period of April 25-30. Credit card payment was combined with the Vega Baja trailer and stairs.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Training offered by Marisel Espada and Yamil Cirino at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, Select a project, home, documents, Procore drive, drawing, RFI, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Continue training offered by Marisel Espada and Yamil Cirino at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, Select a project, home, documents, Procore drive, drawing, RFI, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Procore training session with CPM staffing (Yamil Cirino) and the PMO staff from CDM Smith (Gabriel Perez) and DCMC (Lauren Wells, Carolyn Baez, Harry del Valle). The topics were directed to the site data gathering information.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jesus Cintron (Genera) to discuss staffing update at Costa Sur and Aguirre sites
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Procore training session offered by Marisel Espada and Yamil Cirino at the CPM offices. Topics discussed: Individual profile, conversation, support & feedback, Select a project, home, documents, Procore drive, drawing, RFI, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Prepared legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed and formatted the questions received from proponents in connection with the Demolition at Palo Seco RFP. Engaged in a detailed discussion with Joaquín Quinoy (Genera) to verify the technical accuracy of the questions and identify any outstanding issues requiring clarification. Subsequently shared the draft with Mike Kuczinsky (S&L) to request additional input and information needed to finalize the Q&A document and move forward with its formal release on 04/10.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Updated the BESS and Peakers RFP tracker in preparation for the Wednesday weekly meeting. Incorporated the latest developments, including status updates, submission timelines, pending deliverables, and responsible parties for each active RFP. Ensured all information was current and clearly organized to support effective discussion, decision-making, and follow-up during the meeting.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Held a detailed discussion with José Ralat (DCMC) regarding the CDBG-DR cost share and its critical importance to Genera’s current financial position. Addressed the urgent cash flow challenges Genera is facing and emphasized how the timely disbursement of the cost share is essential to meeting contractual obligations and maintaining progress on federally funded projects. Explored potential pathways to expedite the cost share process and align with regulatory requirements and contractual obligations.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Drafted and shared with Ricardo Pallens (Genera) a brief memo summarizing the discussion regarding procurement award notice issues and related disputes faced by Genera. The memo outlined key challenges, proposed solutions, and immediate action items aimed at improving internal alignment and strengthening the procurement process. The objective was to provide clarity and support informed decision-making for next steps.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Discussed with Ricardo Palléns (Genera) ongoing issues and disputes Genera has encountered related to procurement award notices, including challenges in communication, transparency, and alignment with established procedures. We discussed possible causes and strategized potential solutions to improve the award notice process moving forward.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Performed tests on the Genera Connect Financial Tracker application and reviewed the reports to identify and troubleshoot the reasons behind the upload errors in some of the sheets. An issue identified was modified data structures inside of the used Excel sheets.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Connect Training Session: Conducted a training session with Keyla Sierra from Integrum and José Ralat and Victor Maldonado from DCMC to familiarize them with the platform's functionalities and operations.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 90%. Day 5
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria -I received an email from Franklin Colmenares from CSA to review and comment on the T&C for the BESS contract. After a morning review of the document, the comments were shared with the requestor and Gilberto Sucre (DCMC)
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Safety Tool Box Meeting with HOMECA Recycling and pre-coordination meeting of abatement activities for the day.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - In PROCORE training offered by Marisel Espada (CPM) and Yamil Cirino (CPM) at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, Select a project, home, documents, Procore drive, drawing, RFI, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - In PROCORE training offered by Marisel Espada (CPM) and Yamil Cirino (CPM) at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, Select a project, home, documents, Procore drive, drawing, RFI, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting with Herbert Gilbe (General) for discution contractor EHS manual note.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluation of the EHS document corresponding to the Cambalache and Vega Baja BESS projects on the Procore platform.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, RFP-4826 RFC (RGE 3.15.25) Line #34 VE RI Drawings sent by Gilberto Sucre (DCMC).
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluation of the EHS document corresponding to the Cambalache and Vega Baja BESS projects on the Procore platform.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, RFP-4826 RFC (RGE 3.15.25) Line #34 VE RI Drawings sent by Gilberto Sucre (DCMC).
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 - DR4339 - Cambalache - Reviewed project documents and specifications to ensure details are implemented during the construction management planning.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11- DR4339 - Cambalache - Reviewed request for proposal specified contractor responsibilities to coordinate contractor site requirements with local GeneraPR Facilities team and site conditions.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - DR4339- Meeting with CDM Smith (Franklyn Colmenares, Gabriel Perez), Sargent and Lundy (Mike Kuzcynski), DCMC Partners (Gilberto Sucre) to discuss ongoing action items to complete RG Engineering (contractor) proposal review and contract.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 - DR4339- Cambalache - Project RFC meeting with CDMSmith (Farnklyn Colmenares. Gabriel Perez), Sargent Lundy (Mike Kuzcynski) to discuss ongoing actions on the Contractor proposed Value Engineering and schedule impacts.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera PR - Deliverable 11 - DR4339- Cambalache - Met with DCMC Gilberto Sucre for onboarding and Cambalache site project insights and status to start coordination within the DCMC Cambalache site team.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 |  | 167 | 626.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with critical components table to enter data of installation cost including installation labor cost, general condition cost, heavy equipment cost, insurance cost, contingency and profit for all (69) critical components project and (24) NME projects.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Special assignment request by D' Alexander Gonzalez DCMC to complete cost estimate for NME projects, discuss with Pedro Cabrera of DCMC to generate a strategy to provide the report of cost estimate for (24) NME project that does not have a CE provided by CPM, we completed the cost estimate for a total of (24) NME and in addition of (7) MOR projects and tabulated CE in a excel table to be presented to FEMA. The cost estimate was included equipment, material installation, labor cost for installation, equipment rental, indirect cost for management, insurance, overhead, profit, and contingency. The report was sent by Pedro Cabrera of DCMC to D' Alexander of DCMC.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue with critical components table to enter data of installation cost including installation labor cost, general condition cost, heavy equipment cost, insurance cost, contingency and profit for all (69) critical components project and (24) NME projects. Creating new table for cost estimate for each plant site.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse with Mr. Hernan Machado from DCMC, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega of Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse to meet with Inventory Supervisor Mr. Hernan Machado from DCMC. The purpose of the visit is to review the progress achieved so far and clarify any doubt regarding the process. During the visit, I will be performing quality control on the cycle count and assisting Mr. Machado with the process.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue Develop DR4339_817248_Island Wide Plant Repairs and System Restoration_Cost Estimate after Genera Jesus Cintron input.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop DR4339_817248_Island Wide Plant Repairs and System Restoration_Cost Estimate.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue Develop DR4339_817248_Island Wide Plant Repairs and System Restoration_Cost Estimate after Genera D'Alexzander Gonzales input.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, Submittal #3.0 - Lead & Asbestos Reports for Cambalache sent by Gilberto Sucre (DCMC).
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Elevated_Megapack_Installations_AppNote_PRE-PRODUCTION-DRAFT.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Cambalache - RG Engineering Schedule with Gilberto Sucre, Carlos De Jesus DCMC, Franklyn CSAGroup, Reinaldo Romero-Quinones Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-Site - Evaluate possible impact and provide comments in schedules
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria A PROCORE training offered by Marisel Espada and Yamil Cirino at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, Select a project, home, documents, Procore drive, drawing, RFi's, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria A PROCORE training offered by Marisel Espada and Yamil Cirino at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, Select a project, home, documents, Procore drive, drawing, RFi's, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 90%. Day 5, Liferaft Company arrived to pick up CO2 cylinders With Mathew Lipuscek.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #293566-10 for TO#2 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Peakers meeting with Legal and contract management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Meeting between Siemens Energy team (Jim Matlock and Keith Badger) Genera (Kevin Futch) and DCMC (Rafael Calderon). Reviewing Payment Milestones #2 and #3 Payment terms change request and impact on contract schedules.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Review support for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Revision and development of excel editable Exhibit 1 for invoice financial tracker based on contract requirements. Developing excel document for construction team support. Demolition works (BESS-Peakers)
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #293566-8 for TO#2 Sept 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the San Juan warehouse, morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed. Preparing the lists to begin the cycle counts.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse, manually performing cycle counts by location while resuming reporting functionality in the system, then transferring the collected data to the report and entering it into the system and performing recounts to verify inventory accuracy and investigate any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-062 to AD-094 manually
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse, manually performing cycle counts by location while resuming reporting functionality in the system, then transferring the collected data to the report and entering it into the system and performing recounts to verify inventory accuracy and investigate any discrepancies to ensure proper stock control and alignment with inventory records. Working at location AD-062 to AD-094 manually. Asset Suite isn't working the cycle count inventory.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Items price recount list 115
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre completed conducting cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Items price recount list 115
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates any discrepancies to ensure proper stock control and alignment with inventory records. Items price recount list 115
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, conducting ABC Cycle Counts. In coordination with the Warehouse Supervisor of Genera PR, Adan Silva. Consolidating count lists (Count List #163, 164 and Recount #170, 175 and 174 from warehouse A19 San Juan), attaching documentation in the new format
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, conducting ABC Cycle Counts. In coordination with the Warehouse Supervisor of Genera PR Adan Silva. Consolidating count lists (Count List #217 and 218, Recount #221 and 220 from warehouse A19 San Juan), attaching documentation in the new format.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #19 San Juan, preparing a detailed report outlining the work completed throughout, which will be submitted to my supervisor, from DCMC, Paul Browne to support the preparation of his report to Genera PR.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore -Task Continue Procore Management Certification Training Modules per Lauren Wells (Lemoine)
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore -Task Procore Management Certification Training Modules per Lauren Wells (Lemoine)
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Project Management in PROCORE training offered by Marisel Espino and Yamil Cirino at the CPM offices. Topics (tools) discussed: Individual profile, Conversations, Support and Feedback, Select a Project, Home, Documents, Drawings.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Project Management in PROCORE training offered by Marisel Espino and Yamil Cirino at the CPM offices. Topics (tools) discussed: RFI, Submittals, Photos, Daily Log, Reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review Tesla Contract on Lithium Carbonate Adjustment. I was reviewing to gather more information on this adjustment in order to follow up on Genera on this request by Tesla. I discussed my findings with Rafael Calderón DCMC.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 148 | 148 | 148 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from BZN>DEN>SJN for project management purposes.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 139 | 486.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - DR 4339: Project Management: In PROCORE training offered by Marisel Espada and Yamil Cirino at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, select a project, home, documents, Procore drive, drawing, RFI, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4.5 |  | 139 | 625.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - DR 4339: Project Management In PROCORE training offered by Marisel Espada and Yamil Cirino at the CPM offices Topics discussed: Individual profile, conversation, support & feedback, select a project, home, documents, Procore drive, drawing, RFI, submittals, photos, daily log, and reports.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.75 |  | 134 | 234.5 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the Genera response of the project management Value Engineering proposal document of the 4339_9510 BESS_Cambalache project.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache. Review start and finish dates in mechanical activities from Procore project drawing file to send report data to DCMC employee Gilberto Sucre due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 134 | 100.5 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 related on site Cambalache. Attended MS Teams meeting for schedule update with DCMC employee Gilberto Sucre, Sargent & Lundy staff and other team members of project due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 134 | 167.5 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache. Worked on GENERA equipment's duration activities from project Procore project drawing file to send report data to DCMC employee Gilberto Sucre due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache. Study data from major electrical works in Procore project drawing file to send report data to DCMC employee Gilberto Sucre due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache. In building construction duration activities from Procore project drawing file to send report data to DCMC employee Gilberto Sucre due management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 related on site Cambalache MS Teams meeting for review RFP documents on pending construction timing, submittals documents and value engineering status with Construction Manager Gilberto Sucre DCMC, designer, contractor and other teams of project due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue the review of the Genera response to the project management Value Engineering proposal document for the 4339_9510 BESS_Cambalache project.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue reviewing the project management Value Engineering proposal document of the 4339_9510 BESS_Cambalache project.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 134 | 100.5 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RGE update meeting with Frances Vallejo (DCMC), Gilberto Sucre (DCMC) and Luis Damudt (DCMC) for 4339_9510 BESS_Cambalache project.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with RGE about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review the project management Value Engineering proposal document of the 4339_9510 BESS_Cambalache project.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. site visits fuel for vehicle
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 18.93 | 18.93 | 18.93 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from hotel to CPM Office for Procore training.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 17.9 | 17.9 | 17.9 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from hotel to DCMC office for Foster Veazey.
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 14.44 | 14.44 | 14.44 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -OFFICE TRAILER CONSUMABLES. PAD LOCKS
2025-04-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 110.67 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- travel directly from home to Costa Sur, round trip, to meet with Mr. Hernan Machado Inventory Supervisor from DCMC to review the progress made so far and provide onsite support throughout the day to address any questions regarding the process.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 261.6 | 261.6 | 261.6 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) lodging for 4/9 for meetings with Genera, DCMC and Lemoine for project planning.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 reviewed and marked up revised Costa Sur demolition scope of work from Sargent & Lundy.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Participated in meetings with German Nunez (PEAKERS) Rafael Pabon (CDM Smith) Carlos Palomares (CDM Smith). Reviewed the RFP for Costa Sur demolition scope of work.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Prepare Weekly Construction Reports for Vega Baja, Cambalache, Costa Sur & Aguirre.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Weekly Reporting Meeting -Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Program Genera & Tesla Weekly Project Meeting - Attended the weekly meeting to review the status of design, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Attendees: Tesla, Sargent & Lundy, CDM Smith, Genera, CSA Group & DCMC.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence catch-up of daily incoming e-mails and responses.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Procore DCMC Financials tools 2nd Meeting hosted by Elizabeth Fronduto (Procore) - Discussed and walked thru the preparation of Commitments Change Orders and Vendor Change Orders. Attendees: Foster Veazey, Esther Rohena, Rafael Calderon, Glorimel Torrado, Lauren Wells (Lemoine/DCMC), Lauren Kennedy, Tyler Scanlan (Procore) & Gilberto Sucre.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up Meeting. In the recent PMO Team Catch Up meeting. key updates were shared across various topics. Staffing updates highlighted Paola Arroyo's upcoming role as the community engagement liaison and ongoing recruitment efforts for several positions, including a warehouse supervisor and site managers. The ProCore training was discussed, noting positive feedback but suggesting a reduction in session length for future trainings. Infrastructure updates revealed that trailers were installed at Cambalache and plans for Aguirre and Costa Sur were in place. The team addressed safety plans, with revisions needed for Lemoine's manual. Lean management initiatives and the status of the budget task order were examined, along with ongoing PMO reporting efforts and an upcoming monthly dashboard report. Scheduling updates included the expected Governor's visit and hiring process refinements, while further follow-ups on inventory needs and candidate qualifications were necessary. The meeting concluded with a detailed list of action items assigned to specific team members to ensure accountability and progress. Attendees Jack Darnell, Foster Veazey, Frances Vallejo, Gilberto Sucre, Michael Merritt, Annelia Holton, Lauren Wells ( Lemoine/ DCMC)
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache RFC Meeting RGE continued from yesterday's meeting and discussed action items between RGE, Sargent & Lundy and Genera. DCMC and CDM also participated of the meeting.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore files setup discussion on Construction Execution with Lauren Wells and Luis Roman (DCMC).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Execution Alignment discussion with Jack Darnall and Foster Veazey (Lemoine) for improvement.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Weekly PMO Call with Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Jack Darnall, Barry Scanlon, Mark Merritt, and Mike Merritt (all Lemoine/ DCMC)
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - PMO Reporting Call with Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Raissa Borges, Lauren Wells to discuss overall program goals.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Meeting between Gilberto Sucre (DCMC), Jack Darnall, and Foster Veazey (Lemoine) to discuss streamlined communication for the Project.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on gathering information to prepare for Procore Financial call with Lauren Kennedy (Procore ) later today.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Rafael Calderon (DCMC) to discuss Procore financials for entering in cost codes and change management forms.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore financial items to follow up from previous Procore call.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training write up for Anneilia AJ Williams (DCMC) for purpose of publishing.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Procore (Lauren Kennedy, Tyler Scanlon), Gilberto Sucre (DCMC), Rafael Calderon (DCMC) to discuss Change Event with Correspondence and making decisions on Change Orders.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), GIlberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Gilberto Sucre (DCMC), Luis Roman (DCMC) to discuss Procore locations and how we want to structure those. Sucre says we don’t need to use them.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on email correspondence for Procore items for Daily Logs and other items.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss Procore open items; adding users, inactivating users, permissions changes.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Raissa Borges (DCMC) and Frances Vallejo (DCMC) to discuss Procore Analytics and Power BI.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching Procore settings for submittals for Franklyn Colmenares (CSA).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: . Review the safety procedure. Review procore jobs.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Inspection site, review the Homeca job. Meeting with Jaime Lopez (DCMC), Nelson Soler (CDSMITH) in site about Vega Project. Workflow Vega Baja Project. Review the safety and security aspect in Vega Baja Site. Review the workflow in Procore about all Genera Projects.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Homeca Teams about safety and security aspects. Site inspection before start job.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PRDeliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jorge Bracero (Genera) to discuss Paola Arroyo (DCMC) Community Engagement Plan at Vega Baja.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss PMO status, staffing update, Procore training, Safety plan, Lean Management coordination visit, and Governor's visit to Vega Baja site. Participants: Gilberto Sucre (DCMC), Mike Merritt (DCMC), Lauren Wells (DCMC), Anneilia Holton (DCMC) and Jack Darnall (Lemoine).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Lauren Wells (DCMC) and Raissa Borges (DCMC) to discuss Power BI access, Procore analytics and monthly reporting.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Harry del Valle DCMC to discuss trailer update at Costa Sur and Aguirre.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Continued development of the requisition package for the upcoming Technical Support RFP, as requested by Jesús Cintrón (Genera). Finalized drafting the SOW. Ensured alignment with project goals and Genera’s operational needs.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Drafted a formal letter to the Puerto Rico Department of Housing (Vivienda) regarding the CDBG-DR cost share, emphasizing its critical role in supporting Genera’s cash flow and ability to fulfill its obligations under federally funded projects. The letter outlined the urgency of the situation, explained the financial constraints currently impacting Genera, and requested expedited consideration of the cost share disbursement. Ensured the tone and content aligned with regulatory expectations and communicated the importance of timely collaboration.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Continued the development of the requisition package for the upcoming Technical Support RFP, as requested by Jesús Cintrón (Genera). Initiated the development of the Independent Cost Estimate (ICE). Began gathering relevant data, historical cost information, and past proposals to establish a well-supported pricing framework. Structured the initial components of the estimate to align with the draft SOW and ensure consistency with federal and internal procurement standards.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Contributed updates on assigned tasks, reviewed performance metrics, and participated in discussions aimed at streamlining reporting processes and enhancing cross-functional coordination. Collaborated with team members to identify action items and align on priorities for the upcoming reporting cycle. DCMC: Frances Vallejo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Browne, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Continued development of the requisition package for the upcoming Technical Support RFP, as requested by Jesús Cintrón (Genera). Began drafting and refining the Scope of Work to clearly define the objectives, deliverables, and required qualifications. Ensured alignment with project goals and Genera’s operational needs.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS & Peakers weekly catch up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya (CDM Smith) Miguel del Valle (S&L).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Asset Suite Training and Discussion on Financial and Time Trackers: Supported coordination for the Asset Suite training for the cycle counting DCMC team that will be deployed at the power plant inventory storages. The training will be provided by Hiram Medero from Genera PR. Additionally, discussed the status of the Genera Connect Financial Tracker and Time Tracker with Carlos González and Jorge Aponte from Integrum.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Power Plant Performance Reports: Reviewed power plant performance reports with Jan Rodríguez, José del Río, Vladimir Scutt, and Josue Sánchez from Genera PR to discuss further standardization of reporting metrics. Identified and corrected duplicate report data of fuel consumption from the Trailer Mounted (TM) power generators. Provided the fuels consumption report in MMBtu to Jan Rodríguez for submission to the environmental department.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Preparation of Fuels Consumption Report: Worked on the fuel's consumption report in MMBtu units to provide it to Jan Rodríguez from Genera PR.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Concepcion, Andres | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 178.4 | 178.4 | 178.4 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Cambalache BESS -, Safety equipment for site safety (Safety Boots, Safety glasses and Hard hat chintrap).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Verify Submittals and RFI for approvals on ProCore.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Abatement Activities field supervision and coordination. Meeting with Carirma Sanchez (HOMECA ) to discuss the weekend work schedule.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Safety Tool Box Morning meeting with HOMECA workers in preparation for today's lead removal activities to deliver relevant and timely safety messages to the entire work crew.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued working with projects documents for the Yabucoa Project, reviewing drawings specifications, scope of work, soil studies.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working with projects documents for the Yabucoa Project, reviewing drawings specifications, scope of work, soil studies.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Verification and analysis of EHS documents and procedures related to lead and asbestos removal on the Procore platform
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Notes are generated for Genera contractor safety program.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RFC Meeting RGE Cambalache whit Jose Robles (EGE) Gilberto Sucre (DCMC) Luis Duque (DCMC)
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Safety meeting whit Jan Pierre (DCMC) and Gilberto Soto (DCMC) to discuss contractors' work processes.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Notes are generated for Genera contractor safety program.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera PR - Deliverable 11 - DR4339 - Cambalache - Project Scope of Work Planning and documentation review for Cambalache construction start date.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - DR4339- Cambalache - Assisted GeneraPR HQ to meet with Digno Cartagena (Genera) to generate site access badge as contractor. Met Gabriel Perez (CDM Smith) for introduction as Site Manager. Met with Carlos De Jesus (DCMC) to went over Cambalache project schedule.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - DR4339- Cambalache - Construction Management planning for initial contractor coordination and schedule to clarify responsibilities, identify potential issues, and plan for a successful project.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing total components from PREB resolution and compare with critical components tracker, reviewing the indirect cost and direct cost of the CE for each NME and MOR project. Review email send by Pedro Cabrera of DCMC in regard of Genera cancelation of PO# 107015 of Surpaga vendor. Making correction of Cost Estimate template for O&H and Profit.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working in preparation of a Cost Estimate template. Reviewing the cost of DR4339-817248-Power Plant Repairs and System Restoration PW-108115.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC and Lemoine: Abraham Velazquez, Frances Vallejo, Gilberto Sucre, Jean Pierre Menay, Lauren Wells, Rafael Pabon, Glorimel Toledo, Rafael Calderon, Frankly Colmenares, Raissa Borge, Sheila Torres and Carlos Palomares (CDM Smith), Meeting with DCMC to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Cambalache Meeting - meeting to discuss the issue of Overhead Crane and Leak Detection System, participant Herminio Arroyo of Genera, DCMC - Pedro Cabrera and Eduardo Rivera.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Meet with Joaquin Quinoy (Genera) to discuss the action item from the meeting of Cambalache Overhead Crane and Leak Detection System, he requested to see if we can request a proposal for a A&E to design the requirements for the new crane, also for the leak detection system he mention that ACT should be responsible to install a temporary leak detection when line is relocated and then reinstall when bridge is relocated for us then install the leak detection system, issue is that ACT has not inform when this project will be executed.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with minutes meeting of meeting with Hermino Arroyo of Genera and Pedro Cabrera of DCMC. Continue reviewing of DR4339-817248-Power Plant Repairs and System Restoration PW-108115 there was some error in the sum of some data entry that was corrected.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting with Mr. Anthony Vega from Genera to discuss the details of the Asset Suite training that was provided to my team.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting with Anthony Vega from Genera to confirm that today's training is still scheduled and to ensure that all necessary resources are available.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participating in Asset Suite training with Mr. Medero from Genera PR.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participating in Asset Suite training with Mr. Medero from Genera PR.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conference call with my team to ensure everyone is clear about the training we will be attending today at Genera, and to address any questions or concern they may have.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Develop a delegation plan for colleagues Eduardo Rivera and Roberto Bosch DCMC as part of the work plan, in preparation for my scheduled vacation.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting - With participation from DCMC: Eduardo Rivera; from Genera Herminio Arroyo, to discuss project overhead crane and leak detection system.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop an allocation report based on PW-10710, PW-10815 & PW's LGA.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Adjust DR4339_817248_Island Wide Plant Repairs and System Restoration_Cost Estimate
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop an allocation report based on PW-10710, PW-10815 & PW's LGA.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, Minimum Design Loads for Buildings and Other Structures sent by Mike J. Kuczynski Sargent & Lundy.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Minimum Design Loads for Buildings and Other Structures sent by Mike J. Kuczynski Sargent & Lundy.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review submittal documentation of the Cambalache BESS Program, RFP-4826 RFC (RGE 3.15.25) Line #34 VE RI Drawings sent by Gilberto Sucre (DCMC).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Application Note: Elevated Megapack Installations, Forklift Live Loading sent by Mike J. Kuczynski Sargent & Lundy.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 2 | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I went to the Genera_PR Building to get my badge done. Then at the site I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca, I handled meetings with the contractor. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. These were my chores for today.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca.I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. These were my chores for today.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Homeca brought materials required for the scaffold inspected area. Continue Scaffold inspection for transformer protection, Scaffold progress 100%. Day 5 meeting on teams with DCMC Jean Pierre Menay and Jorge Mercado.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Pro-Core Meeting: Procore - DCMC Financials Tools - review new ProCore functionalities to process and document change request and formal Change Orders based on contracts requirements. This tool will facilitate and centralized all change order request for all Genera projects including BESS and Peakers. Participants from DCMC - (Rafael Calderon, Lauren Wells, Lauren Kennedy, Gilberto Sucre, Tyler Scandal, Glorimel Torrado)
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 164 | 574 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Genera & Tesla Weekly project management meeting. Contract 106761. Project development based on deliverable schedule. Meeting between Tesla team (Carlos Melendez, Jefferson Silver, Laura Miglietti, Keyur Javiya, Howen Lim and Qais Feroz) , CSA (Franklyn Colmenares), CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczinski, Vincent Skochdopole, Reinaldo Romero, Nelson Rosado.) and DCMC (Rafael Calderon).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria PMO Reporting Meeting - DCMC PMO staff meeting to discussed specific need of reporting based on project execution development per area. Working on PPT presentation template and review updates from BESS and Peakers project. Participants Frances Vallejo, Raissa Borges, Glorimel Torrado, Gilberto Sucre, Sheila Torres, Abraham Velazquez, Eduardo Rivera and Paul Brown.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Pro-Core Meeting: Procore Financial Discussion - review new ProCore functionalities to process and document change request and formal Change Orders based on contracts requirements. Reviewing Contract Change Orders Forms. This tool will facilitate and centralized all change order request for all Genera projects including BESS and Peakers. Participants from DCMC - (Rafael Calderon and Lauren Wells)
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Change Orders Review based on mutual agreement between Genera and Tesla. Aligning financial information with project cost adjustments in order to request next working capital advance. Change Order relates to Payment Milestone #2 and #3. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel to Genera office to meet with Genera leaders regarding a training session that will be provided to inventory team.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Meeting with Mr. Paul Browne DCMC to discuss the details of working with the new feature in Asset Suite.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participating in Asset Suite training with Mr. Medero from Genera PR.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participating in Asset Suite training with Mr. Hiram Medero in Genera PR.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria; Travel from Genera corporate office to home from a training session meeting with Genera Mr. Anthony Vega and Mr. Hiram Medero.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria; Continued training session/ inventory team with DCMC Mr. Anthony Vega and Mr. Hiram Medero /will be provided with a training session Asset suit.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria; training session/ inventory team with DCMC Mr. Anthony Vega and Mr.Hiram Medero /will be provided with a training session Asset suit.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria; Travel from home to Genera corporate office. To meet Mr. Anthony Vega and Mr. Medero, the inventory team will be provided with a training session.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participating in Asset Suite training IT Manager from Genera PR.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participating in Asset Suite training with IT Manager from Genera PR.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Certification per Lauren Wells / Management Procore Discussions Meeting with Lauren Wells
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Discussion meeting with Lauren Wells (Lemoine) and Gilberto Sucre (DCMC) for the inclusion of locations in Procore projects. Discussed project needs per core tools and the complexity of full platform introduction.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review project structure suggestions and work on additional documentation that must be considered for backup on the Documents Tool (contracts, bid phase amendments, and others)
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Obtain Contractor ID Card from Genera. While in the process: review inclusions for locations for Procore projects.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Procore Core Tools SOP's and Project Teams to ensure access to the latest guidelines, promoting uniformity in operations across the organization.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Document's Suggested Structure Draft for the Documents Tool on Procore; to perform document control of documentation without a Procore Core Tool established to do so, in addition to Contractual Documents.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - PROCORE meeting to discuss pre intervention and financial process in the plataform. In this meeting participates Lauren Kennedy from Procore, Gilberto Sucre, Rafael Calderón, Lauren Wells and Glorimel Torrado from DCMC.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC participants: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado and Lauren Wells. CDM Smith participants: Franklyn Colmenares, Rafael Pabon and Carlos Palomares.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - PROCORE meeting to discuss how change orders will be reflected in Procore platform. In this meeting participates Tyler Scanlan and Lauren Kennedy from Procore, Gilberto Sucre, Rafael Calderón, Esther Rohena, Lauren Wells and Glorimel Torrado from DCMC. Pending action: send change order forms to the team.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 148 | 148 | 148 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from BZN>DEN>SJN for project management purposes.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Edited the NDA for Genera and TESLA for Juan Vallejo, Hernan Machado, and Giovanni Taffanelli (DCMC) for them to initial and sign as part of their work requirements and sent it by email. Updated the DCMC-TESLA NDA Status Excel spreadsheet. Revised the Hotspots Employee Equipment Checkout and Hand Receipt Form for Giovanni Taffanelli, Paul Brown, Juan Vallejo, Hernan Machado, Jose Lopez Linares, Andres Concepcion, and Harry del Valle (DCMC). Emailed Franklyn Colmenares (CSA Group) the NDA for Andres Concepcion and Carlos De Jesus (DCMC). Updated the Contact Log Per Site Excel spreadsheet.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Meeting with Anneilia Holton-Williams and Connie Wright (DCMC) in a call to discuss the collaboration on a new task related to supporting staff with Tempest Time and the narratives of the PMO staff at Genera. This task aims to make it easier for the staff to complete their daily entries and manage their expenses.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Continue review of the Genera response to the project management Value Engineering proposal document for the 4339_9510 BESS_Cambalache project.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 related on site Cambalache- in GENERA Headquarters office to obtain ID batch with DCMC employee Andrés Concepción due management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache review civil works on Procore drawing file to send report data to DCMC employee Andres Concepcion due management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in review contractor electrical activities from Procore project drawing file to send report data to DCMC employee Gilberto Sucre due management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of the Genera response to the project management Value Engineering submittal document for the 4339_9510 BESS_Cambalache project.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review of the Genera response to the project management Value Engineering proposal document for the 4339_9510 BESS_Cambalache project.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with RGE about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. "Power Bi Access" teams meeting with Frances Vallejo, DCMC and Lauren Wells, Lemoine. The purpose of this meeting is to discuss Procore projects reports. The meeting was organized by Carolyn Baez (DCMC).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data gathering. Development of a Master Tracker for the monthly report that includes site weekly progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data gathering. Continued developing a Master Tracker for the monthly report that includes site weekly progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 122 | 305 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Visiting Genera Offices for ID contractor's batch.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 122 | 183 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Weekly reports compilation and teams meeting " PMO Reporting". The purpose of the meeting was for the members of the PMO team to discuss the weekly project status and updates. The meeting was organized by Frances Vallejo (DCMC).
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 15.98 | 15.98 | 15.98 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from Genera office to hotel.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 12.93 | 12.93 | 12.93 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from hotel to DCMC office.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 9.93 | 9.93 | 9.93 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from DCMC Office to Genera Office.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 7.71 | 7.71 | 7.71 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from hotel to dinner.
2025-04-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 6.96 | 6.96 | 6.96 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from dinner to hotel.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 1779.59 | 1779.59 | 1779.59 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. rental of vehicle for travel and site visits last rental
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 held internal meeting with Foster Veazey DCMC VP operations Frances Vallejo Rosich DCMC Deputy program manager to discuss project.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 met with Genera asset manager, Vladimir Scutt, to discuss the best way to work on sites with little to no interruption.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Program Execution Alignment discussion with Jack Darnall and Foster Veazey (Lemoine).
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peakers reviewed and update EHS Procedures, Approvals and Site Entry Requirements to be used on all project sites..
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Project Schedule & Budget Meeting The BESS / Peaker's Project Schedule & Budget Meeting, led by Carlos Palomares (CDM Smith) , focused on crucial aspects of the project's timeline, documentation, and joint venture arrangements. Key discussions included expected delivery timelines, the differentiation between 'issue for bid' and 'issue for construction' documentation, as well as the necessary formal documentation for project delivery and construction processes. The team also addressed joint venture visibility and contractual obligations, notably surrounding notice of award procedures. Additionally, commissioning planning was reviewed, emphasizing coordination and the need for specific documentation regarding foreign involvement. Action items assigned included the preparation and finalization of key documents related to construction and commissioning, along with follow-ups on joint venture arrangements.- Attendees from Genera, CDM Smith, CSA Group, DCMC,
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFP 4898, Phase I Evaluation - Vega Baja, and RFC's & RFP 4899 Evaluation Kickoff Meeting - Costa Sur. Evaluation team from Genera, Sargent & Lundy, CDM Smith, CSA Group, and DCMC Partners reviewed commercial and technical proposal from ARG and RGE companies for the preparation of RFC's to both companies for Vega Baja Installation Phase. Introduction of Costa Sur contractors' bids were mentioned three in total.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued evaluation of Vega Baja Phase II Installation - commercial and schedule of ARG proposal.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Reporting coordination meeting to review construction slides with Abraham Velazquez, Frances Vallejo, Raissa Borges and Gilberto Sucre (DCMC).
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Agenda preparation for mobilization site security, Environmental Health & Safety meeting for Jean Pierre Menay, Osvaldo de Jesus y Nelson Medina (DCMC)
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Weekly BESS / Peakers Permitting Discussion focused on key updates regarding permitting and project timelines in light of a newly announced executive order from the Puerto Rico governor, which exempts Prepa, Genera, and Luma from certain local permitting obligations for electrical system repairs, although federal requirements remain in place. Participants discussed the status of Tetra Tech’s pending emissions tables essential for FEMA scope compliance, with a proposal expected for approval soon. The team reviewed permitting requirements post-executive order, noting the need for floodplain elevation certificates and the approach for submitting permits in Vega Baja despite the changes. Updates on project timelines included estimates for the completion of demolition at Vega Baja by late May and the ongoing asbestos testing across several sites. Action items were assigned to follow up on emissions table scheduling, floodplain certification, and the completion of various reports. Participants Genera, CDM Smith, Sargent & Lundy, CSA Group, DCMC, and Tetra Tech
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Assessment of overall Program Execution and improvements. Evaluation made after six weeks of my participation of the PMO Program.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)Worked on correspondence for Procore items for directory questions for Franklyn Colmenares (CSA). Also worked on Procore permission settings.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore equipment list for Daily logs in order to get a list populated for users.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) to discuss Procore documents tool structure for the program. Theresa proposed a new structure and we went through each item to vote yes or no to incorporate.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items for assigning tasks to Luis Roman (DCMC) and Theresa Perez (DCMC).
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Theresa Perez (DCMC) and Gabriel Perez (CDM Smith) for an intro call so Theresa can understand Gabriel's role and how he will help with information as we restructure the folders in Documents.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Inspection site, review the Homeca job. Meeting with Nelson Medina, Osvaldo de Jesus, Herminio Arroyo, Clara Padovani Roseanne Perez by (Genera) about Cambalache Project. Items included Security, Safety, Emergency Managment, Enviromental and Site Manager.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Inspection site, review the Homeca job. Metting with Osvaldo de Jesus (Genera) Health and Safety Supervisor about Cambalache Project.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jesus Cintron (Genera PR) to discuss Gabriel Morales candidate for Yabucoa site, CDM Smith contract for the staffing positions, and project update.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Visited Cambalache site for a trailer installation inspection
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended BESS and Peakers site reporting discussion with Abraham Velazquez, Gilberto Sucre and Raissa Borges (DCMC)
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Finalized the ICE for the upcoming Technical Support RFP, ensuring accuracy, completeness, and alignment with the SOW. Incorporated relevant cost data and historical benchmarks to support a well-founded estimate. Verified compliance with applicable procurement guidelines and internal standards to facilitate the next steps in the requisition and approval process. Sent the SOW and ICE to Jesus Cintron (Genera) for review and sign-off.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed and reformatted the SOW and Pricing Schedule for the Costa Sur Demolition RFP to ensure clarity, consistency, and alignment with procurement requirements. Reformatted the Pricing Schedule to clearly present cost breakdowns and facilitate evaluation, while ensuring both documents met internal standards and were ready for inclusion in the final solicitation package.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS - Discussed the Tetra Tech Task Order and proposed amendment with Jesús Cintrón (Genera), focusing on scope adjustments, budget considerations, and alignment with ongoing project needs. Following the conversation, relayed key points and next steps to Rafa Pabón (CDM Smith) and requested a draft of the revised Task Order for internal review and further processing.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Daily Scope of work supervision and monitoring.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Daily Scope of work supervision and monitoring. Team meeting with Genera RFP Review board to discuss the Vega Baja Phase II bidders' documentation. There were 19 participants. Carlos A. Negrón Genera was the meeting organizer from Genera PR.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning Meeting with the GWC HOMECA representative, Carirma Sanchez, to review the pending submission approvals.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Daily Scope of work supervision and monitoring. Meeting with Thessy Perez (DCMC)to discuss the PROCORE SOP_ and the Vega Baja projects' needs.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued working with projects documents for the Yabucoa Project, reviewing drawings specifications, scope of work, soil studies.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working with projects documents for the Yabucoa Project, reviewing drawings specifications, scope of work, soil studies.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Management ¦ DR 4339 – Hurricane Maria Inspection walks the project site with the DCMC work team, Luis Damudt and Andrés Concepción (DCMC).
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - meeting to discuss the safety manual and notes taken with Victor Rodriguez (GENERA) and Helberet Guilde (GENERA)
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Inspection Walk to the swapping site with the DCMC work team, Luis Damudt and Andres Concepcion (DCMC).
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Inspection Walk to the swapping site with the DCMC work team, Luis Damudt and Andres Concepcion (DCMC).
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - DR4339 - Cambalache - Meeting with Jean Pierre Menay (DCMC) for site safety initial coordination needed to ensure rules are followed according to the best practices for construction safety to minimize workplace incidents.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - 4339DR - Walkthrough to assess project site conditions with DCMC Construction Manager (Luis Damudt) to support construction initiation planning.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - 4339DR - Evaluated site office conditions to plan on pending equipment for construction monitoring and management. Generated action items and activities list.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - DR4339 - Cambalache - Site walkthrough to assess site coordination efforts to identify potential hazards, address safety concerns, and create a secure work environment.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - 4339DR - Project Meetings with Facility general manager (Herminio Arroyo - GeneraPR) & Jean Pierre Menay (DCMC) for site mobilization coordination on BESS project.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewed of DI numbers corresponding to the duplicate items that were removed from the installation project and, eventually, from the “Equipment and Materials” component, as they were already included in Legacy projects regard of the critical components and NME mapping.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 |  | 167 | 626.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working to add MOR projects to critical components lead tracker. Reviewing email send by Pedro Cabrera DCMC in regard of Fuel Efficiency new list Projects for Genera., this list replaces the previous version. Review of Costa Sur clarification question made by Black & Vetch still pending response by Genera.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - CPM Jose Prado, Luis Tapia, Carlos Castro, Diana Rivera and Victor Alvarez; DCMC Pedro Cabrera and Eduardo Rivera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, Discussion of Overhead Crane, Cambalache Leak Detection System and reviewing the deliverables.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue reviewing the BV-Genera Fuel Efficiency Action Item List tracker for critical components project that was included in PREB resolution, the allocation related to PW-10710 (Equipment and Materials), PW-108115 (Power Plant Repairs & System Restoration), and the LGA PWs after adjustment requested by GENERA-PR will be shared with FEMA and COR3. They are (49) Critical Components – PW-10710 & PW-108115, (20) Critical Components – LGA PWs, (18) NME – PW-108115, (6) NME – LGA PWs and (7) MOR – PW-108115.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing BV-Genera Fuel Efficiency Action Item List for critical components project that was included in PREB resolution.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-at Palo Seco warehouse to work with Mr. Giovanni Taffanelli from DCMC. The objective of this visit is to provide guidance on the ABC cycle count process and to walk through the procedure to ensure a clear and comprehensive understanding.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- preparing a detailed report on the daily cycle count across all three Genera PR warehouses for Mr. Anthony Vega and Maria Sanchez CFO from Genera PR.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- on site at the Palo Seco warehouse with Inventory Supervisor from DCMC Giovanni Taffanelli to assess the progress achieved to date and to review the installation of the new profiles on computer from Genera PR, ensuring proper access to the Asset Suite system. Also, will be assisting Mr. Taffanelli on the Cycle count process.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Eduardo Rivera, Roberto Bosch and Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Adjust DR4339_817248_Island Wide Plant Repairs and System Restoration Cost Estimate per GENERA-PR request after review by GENERA-PR.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Develop a mapping of Critical Components & NME included int LGA's projects.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Adjust DR4339_817248_Island Wide Plant Repairs and System Restoration_Cost Estimate after GENERA-PR review.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Project Management planning & support for BESS project with Andres Concepcion, Jorge Alexis Mercado DCMC.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Site walkthrough to assess potential site coordination efforts with Andres Concepcion, Jorge Alexis Mercado DCMC, Herminio Arroyo Genera PR.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Note: RFP-4826_RFC_(RGE_04-07-25) (S&L 04-08-25) 228198 GENERAPR RFP 4826 52 MW BESS Cambalache sent by Mike J. Kuczynski Sargent & Lundy.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Project Management planning & support for BESS project with Andres Concepcion, Jorge Alexis Mercado DCMC.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache Facility general manager Herminio Arroyo – Genera PR & Jean Pierre Menay DCMC about the site movilization coordination on BESS project.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Continue to supervise Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Electrician Geraldo Diaz arrived to correct power outage.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761 Internal Meeting: BESS / Peaker's Project Schedule & Budget Meeting. Discussed new change order requests and impact to the contract schedule. Participants from CSA (Franklyn Colmenares) CDM PM (Gabriel Sepulveda, Carlos Palomares), and DCMC Contract Manager - (Rafael Calderon)
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 Meeting. Review deliverable Schedule based on project development and new change order request. Contract review and documentation to identify allowable task, scope and impact to contract schedules. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Participants CDM - Rafael Pabon and DCMC - Rafael Calderon
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Continue working on Compliance Review CDM Smith Invoice #90231395 for TO#2 Sept 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #90231395 for TO#2 Sept 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting ABC Cycle Counts List # 285 in the AC024 - AC032 Locations. In coordination with the Warehouse Supervisor of Genera PR, Adan Silva.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. System reporting functionality was restored, and we continued manually processing inventory on Friday, April 4. Locations AD 026 through AD 043 for a total of 18 locations, 63 catalog IDs, and a count of 4,719 units. Cycle counts and recounts were performed to verify inventory accuracy, and we investigated any discrepancies to ensure proper inventory control and alignment with inventory records.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. System reporting functionality was restored, and we began manually processing inventory on Friday, April 4. Locations AD 026 through AD 043 for a total of 18 locations, 63 catalog IDs, and a count of 4,719 units. Cycle counts and recounts were performed to verify inventory accuracy, and we investigated any discrepancies to ensure proper inventory control and alignment with inventory records.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, preparing a detail report outlining¿ the work completed throughout wich will be sunmitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. First day to operate Asset Suit from CR 00 072 000 to CR 01 042 000, inventory, recount, min & max, variances, and item cost
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. First day to operate Asset Suit from CR 00 072 000 to CR 01 042 000, inventory, recount, min & max, variances, and item cost
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre completed conducting cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. First day to operate Asset Suit from CR 00 072 000 to CR 01 042 000, inventory, recount, min & max, variances, and item cost
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 152 | 494 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting Recounts List # 285 to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. 9 Locations, 29 items and 316 pcs were worked on. This information was validated the employee in charge of Genera PR.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, preparing a detailed report outlining the work completed throughout, which will be submitted to my supervisor, from DCMC Paul Browne, to support the preparation of his report to Genera PR.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed. Preparing the lists to begin the cycle counts.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Working Session with Lauren Wells (Lemoine) & Luis Roman (DCMC) regarding Project File Structures for Genera Projects in Procore/ Workshop for Onboarding & Offboarding users in Procore
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Team Workshop with Jose Lopez, Nelson Soler & Gilberto Soto (Vega Baja) Equipment Tools for Daily Reporting/ Teams Workshop Vega Baja Location Tools to be Implemented in Procore for Genera
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Project Equipments for Vega Baja site; review of project team the main tasks to underline equipment being used or projected to be in use. Also, review Core Tools SOP for Daily Logs.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Project Locations for Vega Baja site; review of project drawings to oversee impacted site locations in the civil/structure/architectural works stage.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) and Theresa Perez (DCMC) to discuss the proposed File Structures for the Document Tool on Procore.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Project Locations for Vega Baja site; review of project drawings to oversee impacted site locations in the civil/structure/architectural works stage.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 139 | 243.25 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Three calls with Abraham Velazquez and five calls with Jorge Alexis Mercado to explain how to generate the PREPA and DCMC time reports and submit them again. Updating the Contact Log Per Site Excel Spreadsheet.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Reviewing the emails received from Hernand Machado, Juan Vallejo, and Giovanni Taffanelli (DCMC) about the NDA between Tesla and Genera. Sent an email to Franklyn Colmenares (CSA Group) that the NDA employees received today. Updated the DCMC - TESLA NDA Status Excel Spreadsheet. Call Abraham Velazquez and Jorge Alexis Mercado to explain how to generate and submit the Payroll reports.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the RFC Value Engineering submittal document for the 4339_9510 BESS_Cambalache project.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in demolition and site drawings from Procore file to send report data to DCMC employee Andres Concepcion due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in review design drawing status from Procore file to send report data to DCMC employee Andres Concepcion due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue reviewing the RFC Value Engineering submittal document for the 4339_9510 BESS_Cambalache project.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 122 | 427 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data gathering. Continued developing Master Tracker and Power Bi dashboard for the monthly report that includes site weekly progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review projects information and data gathering. Developing Master Tracker and Power Bi dashboard for the monthly report that includes site weekly progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. In person and teams meeting with Frances Vallejo, Gilberto Sucre and Abraham Velazquez from DCMC. To discuss project weekly reports template updates.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from BZN>DEN>SJN for project management purposes.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 60 | 60 | 60 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) parking from 4/7-4/10.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 27.86 | 27.86 | 27.86 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. N95 Personal Protective Equipment. (Particulate Respirator)
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 14.11 | 14.11 | 14.11 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from Genera office to Airport.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 11.96 | 11.96 | 11.96 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Uber from hotel to Genera Office.
2025-04-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 6.37 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) milage from airport to home.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 reviewed RFP for contractor pricing incorporated comments Prepared for final revision of Costa Sur demolition.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Prepared for final revision of Costa Sur demolition.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up Meeting. Key updates were shared across various topics. Staffing updates of ongoing recruitment efforts for several positions, including a warehouse supervisor and site managers. The ProCore training was discussed. Infrastructure updates revealed that trailers were installed at Cambalache and plans for Aguirre and Costa Sur were in place. The team addressed safety plans, with revisions needed for Lemoine's manual. Lean management initiatives and the status of the budget task order were examined, along with ongoing PMO reporting efforts and an upcoming monthly dashboard report. Attendees Jack Darnall, Foster Veazey, Frances Vallejo, Gilberto Sucre, Michael Merritt, Annelia Holton (DCMC)
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO BESS Reviewed progress & milestones for the during the week and prepared checklist for the following week Vega Baja - Phase I & II, Cambalache, Costa Sur & PMO Support.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO * Reviewed and responded to e-mail correspondence. * Requested NDA's for RFP 4899 Aguirre & 4900 Yabucoa to be able to participate on Demolition, Civil & Structural Packages bid evaluations. * Met with Carolyn Baez to coordinate staffing NDA's for their assignments. * Navigated on Procore to audit RFP's documentation for Vega Baja, Cambalache, Costa Sur, and Yabucoa.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Met with Frances Vallejo (DCMC) to evaluate staffing requirements and potential relocation of project personnel to other sites including start dates.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Evaluated Site mobilizations options and site restrictions to be implemented during the BESS project to be executed by RGE.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache RFC Meeting with RGE Contractor, Sargent & Lundy, CDM Smith, DCMC and Genera. The Meeting focused on crucial project aspects such as security, document management, fire protection, building requirements, and site logistics. Gilberto Sucre highlighted ongoing security measures, while Xiomara was appointed as the lead document controller, tasked with gathering certifications and uploading critical documentation to Procore. The team discussed the need for additional geotechnical borings, confirmed the warehouse loading specifications, and explored various design considerations for the fire protection system. Deliberations on hurricane protection methods emphasized the importance of resilience against severe weather, particularly regarding building standards during Hurricane Maria. Site logistics were addressed, particularly concerning worker parking and laydown areas, with attention to delivery coordination of the Tesla mega pack. The meeting concluded with a clear action item list aimed at advancing project tasks, including the finalization of specifications and scheduling timely follow-ups, with a completion target set for the following Friday.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed PMO performance feedback & updates from DCMC Jose Lopez - Site Manager, DCMC Harry del Valle - Construction Manager, DCMC Abraham Velazquez - Sr. Construction Manager and CDM Smith Carlos Palomares - Project Controls.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Weekly PMO Call with DCMC Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Jack Darnall, Barry Scanlon, Mark Merritt, and Mike Merritt to discuss program staffing and overall program goals.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Gilberto Sucre (DCMC) on adding users to Procore for RGE since we don't have a signed contract, but they need access to RFIs and Submittals only.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing Procore equipment settings in order to support Luis Roman (DCMC) in setting up equipment list for Vega Baja.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Site Inspection and Metting with Carirma Sanchez (Homeca), Osvaldo de Jesus (GENERA), Jaime Pesquera (DCMC) and Gilberto Soto (DCMC) about Vega Baja Site in specific Health and Safety issues. Review the site and procedure with Osvaldo de Jesus (GENERA).
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 184 | 46 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review the SOP between DCMC and Genera to help execute routine tasks consistently and effectively.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Gabriel Perez (CDSIMITH), Osvaldo De Jesus (GENERA) Ricardo Pallens (GENERA) about Genera process and Vega Baja Site Demolition Jobs. Review the SOP between DCMC and Genera.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call with Mike Merritt (DCMC), Anneilia Holton (DCMC), Gilberto Sucre (DCMC) and Lauren Wells (DCMC) to discuss staffing update, Procore training, lean management schedule.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Jesus Cintron (Genera), and Mark Merritt and Mike Merritt (DCMC) to discuss staffing rearrangement and next steps.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Ivan Baez (Genera) and Jorge Bracero (Genera) to discuss community engagement liaison lead work plan, discuss site mapping, stakeholders, and meetings, in preparation of the new candidate starting on Monday (Paola Arroyo).
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS -Continued preparing the amendment package for the Tetra Tech contract. Drafted the Non-Competitive Procurement Worksheet to support the request.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in the weekly DCMC coordination meeting to prepare the client briefing for Genera. The team discussed and aligned on key topics, including grant management, cash flow status, procurement activities, technology initiatives, and other ongoing projects. Contributed updates and insights on ongoing BESS and Peakers projects to support a cohesive and well-informed presentation to the client. DCMC Team: Mark Merritt, D'Alexzander González, Roberto Bosch, Marc Maceira, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: MZL Shellsea Maysonet, Johanna Díaz, and Integrum Carlos González and Ginnell Torres
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS -Continued preparing the amendment package for the Tetra Tech contract. Finalized the Amendment Justification Memo
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS - Began preparing the amendment package for the Tetra Tech contract. Discussed with Fernando Ortiz (Genera Legal) certain compliance requirements related to the required documentation and justification criteria. Reviewed Genera’s Procurement Manual to ensure alignment with applicable policies and federal requirements. Began drafting the Amendment Justification Memo.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Continue day 2
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Preparatory meeting with HOMECA representatives, Isac Morales (HOMECA) Emanuel Santos (HOMECA).
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Abatement progress supervision and inspections.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with Manueli Concepcion (CDMSmith) to discuss the master project schedule regarding the abatement process by HOMECA
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Attendees, Carlos Roman – EHSS, Frances Dias - EHSS, Harry Del Valle - DCMC Procedure. Lead & Asbestos Inspection and sampling collection. A Niton XLP analyzer equipment was used to analyze all painted areas.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordination Meeting with Gilberto Sucre -DCMC. Topic discussed, RFP Yabucoa projects BESS & Peaker's. DCMC Quality Control Plan, Site visits for next week. Lead & Asbestos test performed today in Yabucoa Gas Turbine.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Attendees, Carlos Roman – EHSS, Frances Dias - EHSS, Harry Del Valle - DCMC Procedure. Continued Lead & Asbestos Inspection and sampling collection. A Niton XLP analyzer equipment was used to analyze all painted areas.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Project Walk with the contractor and its representatives, Alberto Borrely (RGE) Erminio Arroyo (GENERA) Jorge Carreras (Promix) Roseanne Perez (Genera) Andres Concepcion (DCMC)
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Inspection walks the project site with the DCMC work team, Luis Damudt , Andrés Concepción and Luis Duque (DCMC)
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - 4339DR - Prepared action items and site visit meeting agenda for discussion with contractors, designers and Genera PR facilities management.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - 4339DR - Project Management planning & support for BESS project. Development of internal Construction Management plan.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - 4339DR - Project Management planning & support for BESS project. Development of project action items and meeting minutes.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | PREPA Genera Deliverable 11 Cambalache - 4339DR - Coordination Meeting with Potential Contractor RG Engineering (Alberto Borrelli), Sargent & Lundy (Francisco. Mathews), ProMix (Jorge Carreras) GeneraPR Facilities (Herminio Arroyo) and DCMC Team (Luis Damudt, Luis Duque, Jorge Mercado, Carlos DeJesus) for onsite concrete plant evaluation, electrical connection points assessment and site logistics during construction.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing critical components and fuel efficiencies project with Master PowerBI - MAP for critical and NME to confirm how much funding are still available on the DI for the project. Meet with Joaquin Quinoy of Genera to discuss Cambalache Overhead Crane project he refers to Carlos Negron of Genera and inform that they are in the such with a contractor that installed the foundation of this overhead crane, to obtain the drawings. Reviewing PO 106560 and 105644 on Asset Suit to verify if the awarded contract was included liquidation and damage cost.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing the cost for critical components projects versus legacy projects and with the Master Power BI MAP for CC & NME to identify which project is low in budget and will be required to be amendment. Working on generating the weekly report for PMO which include the activity accomplish during this week. Reviewing in Asset Suite the contract status of PO 95750 for project# 669233 to confirm if project was fully completed and invoiced.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue reviewing PO 106560 and 105644 on Asset Suit to verify if the awarded contract was included liquidation and damage cost. Send an email to Saul Falcon of DCMC Procurement to verify if they had additional information regard of the contract award for these two PO because on arriba the information was not found.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Pre-Meeting with participation from DCMC: D' Alexzander Gonzalez, Rick Patterson, Rafael Calderon, Eisha Mercader, Victor Maldonado, Glorimel Torrado, Marc Maceira, Danny Martinez, Annelia Holton, Rick Patterson, Christian Cruz, Sheila Torres, Rafael Cordero, Sheila Torres and Roberto Bosch; Integrum Keylamerari Sierra, Jorge Aponte, Carlos Gonzalez, to discuss draft presentation priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process before presenting to Genera PR.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega of Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, assisting Mr. Juan Vallejo DCMC on cycle counts, recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse to meet with Inventory Supervisor Mr. Juan Vallejo from DCMC. The purpose of the visit is to review the progress achieved so far and clarify any doubt regarding the process. During the visit, I will be performing quality control on the cycle count and assisting Mr. Vallejo with the process
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Meeting Cambalache Facilties for desing and site logisticc Coordination with Potencial Contractor RG Engineering representative Alberto Borrelli, Juan Lopez, Jorge Carreras Promix, Herminio Arroyo – Genera PR & Andres Concepcion, Jorge Alexis Mercado, Luis Duque, Carlos De Jesus DCMC.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Project Management planning & support for BESS project with Andres Concepcion, Jorge Alexis Mercado, Luis Duque and Carlos De Jesus DCMC.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Project Management planning & support for BESS project development of internal construction management plan with Andres Concepcion, Jorge Alexis Mercado, Carlos De Jesus and Luis Duque DCMC.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- 4339_9510 BESS Project Management planning & support for BESS project with Andres Concepcion, Jorge Alexis Mercado, Carlos De Jesus and Luii Duque DCMC.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I walkd the site, handled all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca.I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Used and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca, I handled meetings with the contractor, and meetings with the management of Genera-PR. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Continued supervising and inspecting Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Day 2
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Change Orders Review based on mutual agreement between Genera and Tesla. Aligning financial information with project cost adjustments in order to request next working capital advance. Change Order relates to Payment Milestone #2 and #3. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #90226153 for TO#11 Jan 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team)
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Continue working on Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Change Orders Review based on mutual agreement between Genera and Tesla. Aligning financial information with project cost adjustments in order to request next working capital advance. Change Order relates to Payment Milestone #2 and #3. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting Recounts List # 306 to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. 6 Locations, 14 items and 389 pcs were worked on. This information was validated the employee in charge of Genera PR.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 152 | 38 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. Meeting with my supervisor, Mr. Paul Browne of DCMC, to discuss the week's work, goals, and receive work instructions.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, preparing a detail report outlining¿ the work completed throughout wich will be summitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. System reporting functionality was restored, and we resumed manually processing inventory on Monday, April 7. Locations AD 044 through AD 066 for a total of 22 locations, 43 catalog IDs, and a count of 12,422 units. Cycle counts and recounts were performed to verify inventory accuracy, and we investigated any discrepancies to ensure proper inventory control and alignment with inventory records.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. System reporting functionality was restored, and we began manually processing inventory on Monday, April 7. Locations AD 044 through AD 066 for a total of 22 locations, 43 catalog IDs, and a count of 12,422 units. Cycle counts and recounts were performed to verify inventory accuracy, and we investigated any discrepancies to ensure proper inventory control and alignment with inventory records.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Team Meeting Asset Suit, inventory, recount, cost, variance, min. & Max CR 01 040 to CR 01 50
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Team Meeting Asset Suit, inventory, recount, cost, variance, min. & Max CR 01 040 to CR 01 50
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre completed conducting cycle counts, recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records. Team Meeting Asset Suit, inventory, recount, cost, variance, min. & Max CR 01 040 to CR 01 50
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting ABC Cycle Counts List # 300. In coordination with the Warehouse Supervisor of Genera PR Adan Silva,
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, preparing a detailed report outlining the work completed throughout, which will be submitted to my supervisor, from DCMC Paul Browne, to support the preparation of his report to Genera PR.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, morning job briefing with Manager from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed. Preparing the lists to begin the cycle counts.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Revise approved Procore proposed file structure/ uploaded for review and final approval by client/ Processed documentation for Vega Baja / Costa Sur/ Aguirre /Yabucoa per CDM Smith
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Procore Certification: Project Management as Owner Representative.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continuation of Project Equipment uploading for Vega Baja Project at Procore to improve project efficiency, allocation of resources, and maximize productivity.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continuation of Project Equipment uploading for Vega Baja Project at Procore to minimize equipment delays, misplaced materials, or inaccurate inventory.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Procore Certification: Project Management as Owner Representative.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón DCMC to review Siemens Payment Milestones. After discussion he prepare an email with information about this contract.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María - Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Sheila Torres-Sterling, Eisha Mercader and Marc Maceira from DCMC, and Shellsea Maysonet (MZC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare CPM Invoice for Genera signature PRIN0008220 Jan2025, this invoice was signed and sent for CPA by email to Frances Adames. Also, pre intervention tracker was updated.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Closeout RFI Response | Direct-PA | Development, validation, or submission of RFI response for closeout | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review on RFI pending invoice from CDM, CPM, S&L. I verify on the financial tracker all my invoices in RFI and send an email following up on pending clarifications.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO01_October2024_Inv#293410-9. Start reviewing RFI 594 lines to verify. This task will be finished on Monday.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Phone call with Andrew Rohena (CPM) regarding my email following up on pending RFI's. I helped him clarifying some questions about the information we request. He asked me to send in one email all pending RFI's for CPM. After the call I review the tracker and send all the pending RFI's (4 invoices) in excel format by email with explanation of tabs that he should verify.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María Working session with Rafael Calderón (DCMC) to update tracker for internal DCMC Meeting today. We also update power point presentation and share it with the team.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | General PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Reviewed Frances Vallejo’s email regarding the list of office supplies for the sites. Responded with an additional list of items to be purchased. Sent an email to Jean P. Menay (DCMC), with a copy to Gilberto Sucre and Frances Vallejo (DCMC), regarding his attendance at City View on April 14, 2025.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review the RFC Value Engineering submittal document for the 4339_9510 BESS_Cambalache project.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 related on site Cambalache in meeting in site with RG Engineering staff, GENERA staff, Promix staff, DCMC employees Luis Duque, Luis Damudt, Jorge Mercado, Andrés Concepción for talks related to temporary connection and inspect space for temporary concrete batch in plant due managements site meetings requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was created a report due to meeting related to temporary connection and inspect space for temporary concrete batch in plant with DCMC employees, Luis Duque, Luis Damudt, Jorge Mercado, Andrés Concepción due managements requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue reviewing the RFC Value Engineering submittal document for the 4339_9510 BESS_Cambalache project.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting and site walkthrough with Genera PR, RGE, Sargent and Lunder about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Updating master tracker and continue with the development of Power Bi dashboard for the monthly report that includes project progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continued updating master tracker and continue with the development of Power Bi dashboard for the monthly report that includes project progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 68.18 | 0.7 | Yes | 25-145003 | Date (4/11/2025) Site Inspector Luis Duque Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Route Guaynabo to Arecibo, round-trip to Guaynabo. Drive 97.4 miles, 1 hr 57 min Claiming Mileage for this route Travel from Guaynabo (18.392607 -66.123698) roundtrip to Cambalache Power Plant, Arecibo (18.471729, -66.700701) back to Guaynabo (18.392607 -66.123698) Purpose meeting and walkthrough site with Genera, RGE, Sagent and Lunder for 4339 9510 BESS Cambalache project. TOTAL MILEAGE 97.4 miles
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 46.9 | 0.7 | Yes | 25-145003 | Harry Del Valle 4/11/2025 Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to the Yabucoa Gas Turbine Plant (17.961105, -66.140130) to CPV Guaynabo. Purpose, Asbestos & Lead Tests. Procedure. Lead & Asbestos Inspection analyzer equipment was used to analyze all painted areas. Attendees, Carlos Román – EHSS, Frances Diaz - EHSS, Francisco Vázquez – Genera, Harry Del Valle - DCMC Total Mileage 67 Miles
2025-04-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 62.3 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- travel directly from home to Aguirre, round trip, to meet with Mr. Juan Vallejo from DCMC to review the progress made so far and provide onsite support throughout the day to address any questions regarding the process.
2025-04-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Day 3 Homeca dispached containers with lead base paint items
2025-04-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. Also, I continued supervising the contractor Homeca, I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. Also, I continued supervising the contractor Homeca, I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Today we had to wrok overtime and I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. also supervised the contractor Homeca. I walked the site regularly during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week.
2025-04-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site.Continue Day 3 Homeca continued to dispatch containers with lead and steel to their recycling facility.
2025-04-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Day 4 Homeca continue to work on the same mitigation status cleaning the area with posible lead base paint.
2025-04-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Supervising HOMECA daily Activities and loading Daily Log into Procore platform. Abatement Activities, Dismantling Activities, Lead Transfer Activities. General Cleaning.
2025-04-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Following Morning meeting with Gilberto Soto (DCMC), Emanuel Santa (HOMECA); inspect and provide an overview of daily abatement activities to prioritize the health and safety of workers, comply with regulations, codes, and standards and mitigate risks associated with activities.
2025-04-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning meeting with Gilberto Soto (DCMC), Emanuel Santa (HOMECA) to discuss daily abatement activities to prevent or mitigate potential problems.
2025-04-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Day 4 Homeca continued to clean areas with lead dust.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 reviewed and discussed Demolition RFP for costa sur project reviewed comment with team, German Nunez, Rafael Pabon, Carlos Palomares (CDM Smith).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Weekly Update review of activities including worked performed during the weekend to advance Phase II of Lead Abatement, PUI Permit Status, Frame 5 components responsibility for execution Genera or Homeca. One to one meeting with DCMC Jose Lopez - Site Manager
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS EHS Roles & Responsibilities discussion with Jean Pierre Menay (DCMC). Review upcoming tasks required for Cambalache and Vega Baja Phase II for EHS implementation on both sides.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Preparation for Cambalache weekly update with project team. RFP status and pending pre-mobilization activities.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Internal Project Site Team led by Jose Lopez DCMC to review performance to date, roles & responsibilities by each member, client interactions, and upcoming activities for the completion of the Demolition Phase and the Phase II Installation. Attendees: Jaime Pesquera, Gilberto Soto, Jean Pierre Menay, Gilberto Sucre (DCMC)
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Team Update meeting provided a comprehensive review of the project's current status across several key areas. Gilberto initiated the discussion with an overview of the value engineering cycle for the final proposal, emphasizing the importance of integrating the RGE schedule into the review process and examining the project's financial aspects. Jorge highlighted specific components of the design development process, noting that the project is nearing its final phase while technical development progress was discussed. The team then addressed the environmental impact review, where Gilberto pointed out the need for a ground check and comparisons of environmental impacts between the original and revised bid sets. Brief discussions on furniture and equipment considerations wrapped up the meeting. Action items were assigned, with Gilberto tasked to complete the value engineering review, Jorge responsible for core personnel updates and equipment specifications, and Luis to review the environmental impact assessment documentation. Attendees: Andres Concepcion, Luis Duque, Luis Damudt, Carlos de Jesus, Jorge Mercado, Gilberto Sucre (DCMC)
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja PUI Application clarification for Proyectista / Agent Role pertains to Homeca and not Genera. Discussion with Gabriel Perez (CDM Smith).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Weekly Coordination PM/CM Coordination between Franklyn Colmenares (CDM Smith) and Gilberto Sucre. * Vega Baja - Update, PUI, Demolition Ground-Breaking Activities Coordination, Turbine Component Disassembly, Phase II bid documents. * Cambalache - Procore for RFI & Submittals, Current project drawings, field inspection report form 4/11.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence review and development.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Planning for weeks activities and deliverables for BESS Program.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Check In - Weekly Update of Program led by Gabriel Perez with participation from CDM Smith, CSA Group, Sargent & Lundy, Genera & DCMC Partners. Topics: * Cambalache/Vega Baja/Costa Sur RFP status * Vega Baja Permits/Demolition/Telecom Removal/RACI * Costa Sur/Cambalache/Aguirre IT/OT Rooms * Palo Seco Pre-Demolition Activities * Costa Sur Rule 141 * Aguirre Phase Approach * Global - Design Status/Procore/Transformer Studies/Decommissioning Plan/Unit Retirement/Interconnection Studies/Future RFP's
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache. Internal Meeting for the PM and CM teams focused on aligning project status, schedules, and budgets ahead of Friday's deadline, emphasizing technical clarifications with RGE. Key updates included confirmation that value engineering feedback was submitted, yet pricing breakdowns remained pending, with concerns over RGE using outdated transformer drawings addressed by Mike Kuczynski (CDM Smith). The design timeline was reviewed, with critical switch gear and civil drawings anticipated in the coming weeks, ensuring no delays on long-lead items. Technical discussions involved finalizing fire protection specifications and addressing rigid inclusion budgets. Logistics were also discussed, particularly space constraints for the concrete batch plant, leading to alternative options being explored. Action items were assigned to multiple team members, including follow-ups on EHS documentation uploads and communication with RGE regarding steel drawings and batch plant arrangements. Sargent & Lundy, CDM Smith, CSA Group & DCMC Partners.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Nelson Rosado, Ricardo Pallens, Carlos Palomares, Joaquin Quinoy, Gabriel Perez, Mike Kuczynski, Franklyn Colmenares (Genera), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejando Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Ada Diaz (DCMC) and Frances Vallejo (DCMC) to discuss P6 software and use for Procore.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) weekly meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) to discuss open items with Procore and current tasks list.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Peakers Check-In with Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Jesus Citron (Genera), Mike Kuczynski (Sargent & Lundy), Franklyn Colmenares (CSA) and others My part was to update on Procore items.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondence for adding users to Procore. Getting an understanding of what access is needed per the request.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Teams planner for tracking Procore tasks with the team.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondence/support tasks for Procore for permissions and gaining access to the scheduling tool for Cambalache.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore configurations for setting up documents folder structure.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondence for Procore items for Siemens distribution lists, coordinating setup of meetings for 4/15.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore research for financial module.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Homeca Teams about safety and security aspects. Site inspection before start job. Review the safety procedure. Review Procore jobs. Meeting call with Osvaldo de Jesus (HOMECA).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: . Meeting with Jose Lopez (DCMC), Jaime Pesquera (DCMC), Carirma Sanchez (HOMECA), Gabriel Lopez (CDSMITH), Franklyn Colmenares (CDSMITH) about Vega Baja Site status.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Gilberto Soto (DCMC), Jaime Pesquera (DCMC), Gilberto Sucre (DCMC), Jose Lopez (DCMC) about procedure and jobs in Vega Baja Site.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Development the trainning Health and Safety to DCMC.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Job in Procore systems about Cambalache and Vega Site. Review the requirements entrance to Cambalache Site. Meeting with Andres Concepcion (DCMC) about Cambalache Site.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Ada Diaz and Lauren Wells (DCMC) to discuss P6/Primavera licenses for the PMO team
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Genera Project Managers for BESS and Peaker project (Gabriel Perez, CDM, and German Ojeda, Genera). We discussed the status and pending items of both projects.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR - Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS Check In and Peakers Check in meetings to discuss update on RFPs, Procore status, Trainings, and Veg Baja update. Participants: German, Ojeda, Gabriel Perez, Jesus Cintron (Genera), Carlos Palomares, Gilberto Sucre (DCMC), Rafael Clderon (DCMC), Sheila Torres (DCMC)
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Cambalache update meeting to discuss RGE contract status Participants: Gilberto Sucre, Andres Concepcion, Jorge Mercado (DCMC).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS & Peakers - Began updating the RFP tracker to reflect the latest developments related to RFP 4898. Incorporated new information on submission status, key dates, outstanding documentation, and assigned responsibilities. Ensured the tracker remains accurate and up to date to support effective coordination, internal visibility, and timely follow-up across all stakeholders involved in the procurement process.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczinski.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Followed up with Jesús Cintrón (Genera) on several pending items, including the finalization of the Tetra Tech Task Order, progress on the Beta Task Order, and outstanding documentation and deliverables related to S&L. Confirmed current status, clarified next steps, and reinforced timelines to ensure continued momentum across all workstreams. Coordinated action items to support timely execution and alignment with project priorities.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS & Peakers - Continued updating the RFP tracker to reflect the latest developments related to RFP 4899, 4900, 231160 and the pending Demolition for Costa Sur RFP. Incorporated new information on submission status, key dates, outstanding documentation, and assigned responsibilities. Ensured the tracker remains accurate and up to date to support effective coordination, internal visibility, and timely follow-up across all stakeholders involved in the procurement process.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Maria Sanchez Bras, and Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Marc Maceira, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Carlos González and Ginnell Torres
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS - Reviewed and edited the Tetra Tech Task Order based on comments and feedback provided by D’Alexzander González (DCMC). Made targeted adjustments to ensure clarity, accuracy, and alignment with the intended scope and budget. After finalizing the revisions, submitted the updated draft to Jesús Cintrón (Genera) for review and approval.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.75 |  | 184 | 506 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussion on Opralog Capabilities and Weekly Status Meeting: - Discussed with Vladimir Scutt from Genera PR the validation of Opralog's capability to add NERC codes and subcodes for reporting power plant events, such as outages. This enhancement aims to improve performance metrics by better identifying the usual causes of events. - Participated in the weekly status meeting with Genera PR to discuss project status updates. Participants from Genera PR included María Sánchez and Alejandro Maymi; from DCMC: Esther Rohena, José Ralat, Rafael Calderon, Saúl Falcón, Christian Cruz, Eisha Mercader, Mark Merritt, and Marc Maceira, and MSC Shellsea Maysonet,
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Fuels Consumption Discrepancy: Reviewed the fuels consumption discrepancy reported for the Trailer Mounted (TM) power generators with José del Río and Jan Rodríguez from Genera PR. Identified a missing "regas" (credit) for Ecoeléctrica. The report was amended and sent to Cristina Ribas from Genera PR.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Vega Baja Bess meeting at DCMC CVP office with Jaime Pesquera, Jose Lopez, Jean Pierre Menay and Gilberto Sucre (DCMC) to discuss management and Procedures for the site. and upload information to Procore app daily log photos and JHA.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning daily job site overview and walk through the project surroundings to ensure quality control, worker safety, and productivity. Inspection to document the conditions of the project we are working on and find deficiencies - if any. Review the weekly report.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Weekly progress meeting with Carirma Sanchez (HOMECA) Jaime Pesquera, Gilberto Soto, (DCMC), Franklin Colmenares, Gabriel Perez, (CDM Smith). Overview of project status and pending items from last week's meeting.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - DCMC Team Meeting to review and discuss the Team responsibility matrix for the Vega Baja BESS project. The team was instructed on how to work with the PROCORE's Daily Logs inputs. Meeting with Jaime Pesquera, Gilberto Soto, Gilberto Sucre, Jean Pier Menay.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Lead abatement daily activities overview.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 5 |  | 167 | 835 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on drawings for Yabucoa Gas Turbine projects BESS & Peaker's. Preparing report for Lead & Asbestos test performed today in Central San Juan - Genera.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Attendees, Carlos Roman – EHSS, Frances Dias - EHSS, Harry Del Valle - DCMC Procedure. Lead & Asbestos Inspection and sampling collection. A Niton XLP analyzer equipment was used to analyze all painted areas.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / DCMC - Review of construction documents for the Cambalache site 4339 _9510 BEES review Genera cambalache schedule – preliminary projection of possible design & built April 12 2025 BESS program send by Carlos de Jesus DCMC
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - 04339 _9510 BEES Review Report Status in Drawing RFP, Submittals and Submission & track table, send by Carlos de Jesus from DCMC
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - 4339_9510 Review Genera Cambalache BESS RFP 4826 send by Sargent & Lundy
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Luis Damudt and Luis Duque DCMC Partners Cambalache power plan team.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed correspondence regarding project Drawings (Bid Addendum) and generated correspondence to share project site photos to Sargent & Lundy's Mike Kuczynski,
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project Management planning & support for BESS project. Correspondence review regarding Value Engineering proposal.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project meeting with Program and Design Managers (CDM Smith Gabriel Perez, Reinaldo Romero, Franklyn Colmenares; Sargent & Lundy, Mike Kuczynski, DCMC Gilberto Sucre- to coordinate action and pending items to complete construction contract and contractor (RG Engineering) Value Engineering proposal review.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project meeting with Program and Design Managers (Gabriel Perez CDM Smith, Mike Kuczynski Sargent & Lundy, Gilberto Sucre DCMC) to coordinate action and pending items to complete value engineering and construction contract.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project Management planning & support for BESS project. Evaluated Procore tools status and information and confirmed drawings sets to start documenting and monitoring construction
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Generated email and followed up with last Friday site visit meeting action items for contractor (RG Engineering) to complete construction proposal.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project Management planning & support for BESS project. Redacted RFI correspondence to GeneraPR.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Attended DCMC Site Team (Luis Damudt, Luis Duque, Carlos De Jesus, Jorge Mercado, Gilberto Sucre) weekly meeting for Cambalache project status, updates and action items.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Coordinated with (Carlos Palomares CDM Smith and Luis Roman DCMC), requested correspondence regarding project schedule to start Procore scheduling tool implementation.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, D' Alexzander Gonzalez, Paul Brown, Jose Ralat, Rafael Calderon, Esther Rohena, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Keylamerari Siera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez, Jesus Cintron and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working on legacy cost project review with Master Power BI mapping to compare cost has exceeded FEMA budget for (44) legacy project of critical components projects. Working in provide information on CC tracker table and reviewing project with FEMA project number and Asset Suite. Send an email to Shellsea Maysonet of DCMC to verify on the Sabana Master table project cost.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working in identify LGA project that can be duplicated with the critical component for then presented to Joaquin Quinoy of Genera, the surch is at FEMA project number narrative, Asset Suite, Master Power BI table (La Sabana) and critical component tracker table.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing legacy cost project with Master Power BI mapping to compare if cost has exceeded FEMA budget for (44) legacy project of critical components. Working in provide information on CC tracker table.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- on site at the Palo Seco warehouse with Inventory Supervisor from DCMC Giovanni Taffanelli to assess the progress achieved and will be assisting Mr. Taffanelli on the Cycle count process.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-weekly TEAMS meeting with Ms. Maria Sanchez, CFO of Genera, to discuss the progress made during the past week.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting with Mr. Anthony Vega from Genera to discuss the arrangements made for the new team member to obtain the ID and assigned computer.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- preparing a detailed report on the daily cycle count across all three Genera PR warehouses for Mr. Anthony Vega and Maria Sanchez CFO from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Once the report was completed, I reviewed it with Mr. Vega to ensure there were no outstanding questions or concern
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Genera office with Mr. Milton Flores from DCMC and Mr. Anthony Vega from Genera, coordinating the issuance of Mr. Flores ID and computer. The computer must be configured and the user profile set up with the IT group to enable its use at the San Juan warehouse.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review GENERA Cambalache Schedule - Began working on preliminary Projection of possible Design & Built April/12/2025 BESS Program, sent by Carlos De Jesus (DCMC).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review GENERA Cambalache Schedule - Resumed working on Preliminary Projection of possible Design & Built April/12/2025 BESS Program, sent by Carlos De Jesus (DCMC).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Genera Cambalache BESS RFP 4826 - RE: RFC Meeting, sent by Mike J. Kuczynski Sargent & Lundy.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Action: Report status RFI, Submittals & Drawings BESS Program, sent by Carlos De Jesus (DCMC).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I supervised the contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I conducted a meeting with the contractor and participated in meetings with same people every week. Gabriel Perez, Franklyn Colmenares, Manuelly Concepcion CDM Smith. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting at DCMC Headquarters conducted by Jose Linares (Site Manager), project overview and responsibilities duties as a team.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I did the same chores preety much as in the morning, So here we go, I supervised the contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Homeca Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Day 5
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, continued to take pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Continued inspecting Homeca Lead Base paint protocols were being followed according to DRNA, for mitigation stage on site. Day 5
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Peakers Check-In meeting with project management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Meeting between Siemens Energy team , CMD Smith PM team (Carlos Palomares, Juan Mendoza), Sargent & Lundy (Mike K., Miguel del Valle) Genera (German Nunez) CSA (Franklyn Colmenares) and DCMC (Rafael Calderon, Frances Vallejo).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Pre-Intervention Review RFI - Working with Black & Veatch Contract #217733_2024-G00207 and TO#5_Invoice# pending_ Feb 2025 Status Update Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team , CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike K.), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Frances Vallejo).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Change Orders Review based on mutual agreement between Genera and Tesla. Aligning financial information with project cost adjustments in order to request next working capital advance. Change Order relates to Payment Milestone #2 and #3. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.75 |  | 152 | 570 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Genera office with Mr. Anthony Vega Genera receiving my ID and the computer that will be used at the San Juan warehouse.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, working on the recount of the discrepancies found from Locations AD 067 through AD 098.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. System reporting functionality was restored, and we began manually processing inventory on Tuesday, April 8. Locations AD 067 through AD 098 for a total of 31 locations, 77 catalog IDs, and a count of 1,004 units. Cycle counts and recounts were performed to verify inventory accuracy, and we investigated any discrepancies to ensure proper inventory control and alignment with inventory records.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, preparing a detail report outlining¿ the work completed throughout wich will be summitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Costa Sur warehouse. System reporting functionality was restored, and we continued manually processing inventory on Tuesday, April 8. Locations AD 067 through AD 098 for a total of 31 locations, 77 catalog IDs, and a count of 1,004 units. Cycle counts and recounts were performed to verify inventory accuracy, and we investigated any discrepancies to ensure proper inventory control and alignment with inventory records.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre completed conducting cycle counts, conducts recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records—Cr 150 to 180 inventory, recount, variance, min, max cost.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre continued conducting cycle counts, conducts recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records—Cr 150 to 180 inventory, recount, variance, min, max cost.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre conducts cycle counts, conducts recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records—Cr 150 to 180 inventory, recount, variance, min, max cost.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria. At the warehouse, Aguirre resumed conducting cycle counts, conducts recounts to verify inventory accuracy, and investigates discrepancies to ensure proper stock control and alignment with inventory records—Cr 150 to 180 inventory, recount, variance, min, max cost.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists # 314 to begin the cycle counts.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, preparing a detailed report outlining the work completed throughout, which will be submitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera PR.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting ABC Cycle Counts List # 314. In coordination with the Warehouse Supervisor of Genera PR, Adan Silva.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting Recounts List to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. 12 Locations, 41 items and 850 pcs were worked on. This information was validated the employee in charge of Genera PR, Adan Silva.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Workshop with Lauren Wells (Lemoine) & Luis Roman (DCMC) review of Tasks/Teams Workshop with Franklyn Colmenares (CDM Smith) & Rafael Pabon (CSA) for COIs & File Structure/Setup users for Procore
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RG Engr for Cambalache Project/Teams Workshop with CSA Rafael Pabon & CDM Smith Franklyn Colmenares for incorporation of RFP Permissions for various projects /Team Workshop with Lauren Wells (Lemoine) & Luis Roman (DCMC) for File Structure Review & Comments for incorporation into various projects
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform last review on proposed file structure for Procore Documents tool.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Weekly check-in meeting for the Peakers project hosted by Carlos Palomares (CDM Smith)
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) to discuss progress on ongoing PMO tasks such as SOP and Procore Tools assignments.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Weekly check-in meeting for the BESS project hosted by Gabriel Perez (CDM Smith)
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Documents Tool on Vega Baja and Cambalache projects for Contractual Document review and adjustments on projects data for cost and time.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review SOP documentation for Photos, RFI and Emails to verify it provide a step-by-step set of instructions that guides team members to perform tasks in a consistent manner.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.25 |  | 149 | 37.25 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO06_Feb2025_Inv#90229562. Final invoice was received, reviewed and prepared for Genera Signature (Jesús Cintrón).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO06_Feb2025_Inv#90229562. Review RFI information provided for the compliance sampling. Document was verified and final invoice was requested to CDM to complete pre intervention process.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María ¦Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, Roberto Bosch, Rafael Calderón, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and Marc Maceira. Also, Shellsea Maysonet (MZC); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. Make corrections in formulas that were not working correctly.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.25 |  | 149 | 37.25 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 Continue Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#2, Invoice #18334031_Jan2025. RFI was responded by Sargent and Lundy clarifying plant and narratives. This allows me to start Pre-Intervention for this invoice. Prepare master excel and start verifying employee rates.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.75 |  | 149 | 260.75 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Continue Pre-Intervention Review for CDM Smith TO01_October2024_Inv#293410-9. Compliance review for this invoice and send CDM an email requesting final version to finish pre-Intervention for this Invoice. All information was reviewed and approved.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.75 |  | 149 | 111.75 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO02_August2024_Inv#293566-7. Review RFI information, complete compliance sampling for this invoice and proceed to request official Invoice # and PDF version. Also, on this invoice CDM has to incorporate the corrections to this RFI in their narrative and include employee timesheets.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#3, Invoice #18322769. Review RFI responses and compliance review. Prepare final package and invoice for Jesús Cintrón (Genera) signature. Send the invoice for signature and update excel Pre-Intervention tracker.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Finished Pre-Intervention Review for CDM Smith TO01_October2024_Inv#90231861. This invoice number is new but corresponds to preliminary invoice293410-9. Final invoice was received and sent to RFI requesting timesheets. Final invoice was updated by CDM and I prepare signature request for Genera-Jesús Cintrón. Final package was created, issues with size of the document.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams with DCMC, Genera, Lemoine, and CDM Smith personnel: Jesus M. Cintron Rivera; Mike Kuczynski; D'Alexzander Gonzalez; Franklyn Colmenares; Nelson Rosado; Frances Vallejo Rosich; Joaquin A Quinoy; Gabriel A. Perez Sepulveda; Ricardo Pallens Cruz; Carlos Palomares; Maria Sanchez Bras Fernando Ortiz Melendez; Rafael Calderon; Gilberto Sucre; Mark Merritt; Kevin D. Futch; Francisco Santos Rivera; Raissa Borges Almodovar; Lauren Wells; Foster Veazey and Jorge Bracero. The project was about BEES with Genera. Jorge L. Bracero Nieves talk about the need to coordinate and checked in with the Governor, Jenniffer Gonzalez for a viable groundbreaking date, he confirmed demolition kickoff with the contractor and scheduled a site visit for Wednesday. Gabriel A. Perez Sepulveda request formal confirmation from OPG and DNR regarding the consultation submitted and Jesus Cintron receive formal confirmation regarding the submitted consultation and sign a formal request to confirm no issues with payment disbursement from FEMA.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria review regulatory requirements and BESS project milestones. I review and focus on the materials Jorge Bracero (Genera) sent me to get to know the Vega Baja Community Relations Plan and the Communication Plan. I review the budget and the funding timetables, site location map in Vega Baja, demographics for the Vega Baja Municipality, role and responsibilities for the plan. I review the BESS and Peakers Milestone and the document about the BESS project needs.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams Meeting with DCMC, Genera, and CDM Smith personnel: Jesus M. Cintron Rivera; Juan Mendoza; Rafael Pabon; Kevin Futch; Franklyn Colmenares; Miguel Del Valle; Carlos Palomares; Ricardo Pallens; Alexzander Gonzalez; Frances Vallejo Rosich; Francisco Santos Rivera; Alejandro Maymi Ronda; Warehouse; Mark Merritt; Sarahi Medina Nieves. The meeting was call Peakers Check In.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Sent an email with the NDA to be initial and signed to D'Alexzander Gonzalez (DCMC). Reviewing the NDA received by email from D'Alexzander Gonzalez. Read the email sent by Raul Villanueva (Design Express) regarding the logo to be used in the banner for the sites. I replied to Mr. Villanueva and informed the logo was updated. Contact Chyenne Bliss (DCMC) to send the new logo in PDF format. Sent an email to Franklyn Colmenares (CSA Group) with the signed D'Alexzander Gonzalez NDA.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Continue reviewing the RFC Value Engineering submittal document for the 4339_9510 BESS_Cambalache project.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was created, a report status of Procore RFI, Submittals and Drawings file sent to Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in call meeting with employee Luis Damudt DCMC. Explained a review in construction start related to Procore documents file as requirement due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in Teams meeting with employee Gilberto Sucre (DCMC) to explain status of finish design, submittals reports, construction start and Tuic ID due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache review of Procore Schedule training due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the RFI, submittal and drawings documents for the 4339_9510 BESS_Cambalache project.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache project update meeting with Frances Vallejo (DCMC), Gilberto Sucre (DCMC) for 4339_9510 BESS_Cambalache project
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review the RFC Value Engineering submittal document for the 4339_9510 BESS_Cambalache project.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Completed review of the RFI, submittal and drawings documents for the 4339_9510 BESS_Cambalache project.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue reviewing the RFI, submittal and drawings documents for the 4339_9510 BESS_Cambalache project.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with Genera PR, RGE, Sargent and Lunder about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Jesus M. Cintron (Genera); D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Frances Vallejo (DCMC); Franklyn Colmenares (CDM Smith); Ricardo Pallens (Genera); Lauren Wells, Foster Veazey (Lemoine), among others.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Updating master tracker and continue with the development of Power Bi dashboard for the monthly report that includes project progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Jesus M. Cintron (Genera); D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Frances Vallejo (DCMC); Franklyn Colmenares (CDM Smith); Ricardo Pallens (Genera); Lauren Wells, Foster Veazey (Lemoine), among others.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 122 | 366 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with the development of Power Bi dashboard for the monthly report that includes project progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with the development of Power Bi dashboard for the monthly report that includes project progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 7.98 | 7.98 | 7.98 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - OFFICE TRAILER CONSUMABLES (water).
2025-04-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 45.92 | 0.7 | Yes | 25-145003 | Harry Del Valle 4/14/2025 Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to the Central San Juan (18.427720, -66.105067) to Home Office Luquillo. Purpose, Asbestos & Lead Tests. Procedure. Lead & Asbestos Inspection analyzer equipment was used to analyze all painted areas. Attendees, Carlos A Román – EHSS, Frances Diaz - EHSS, Victor Ortiz – Genera, Harry Del Valle - DCMC Total Mileage 65.6 Miles
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Gilberto Sucre, Jack Darnell, Lauren Wells, Foster Veazey, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 updated daily reports and reviewed comments for upcoming meeting on RFP demolition scope of work
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 held another review session with team members to draw down on site specific details on RFP for demolition contracts at the Costa Sur facility
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache RFC Meeting with RGE Contractor, Sargent & Lundy, CDM Smith, DCMC and Genera. Recurrent Meeting focused on the remaining RFC's responses, Contract comments, schedule and final pricing with the goal to complete the evaluation process by the end of this week. Sargent & Lundy stated a Fire Protection Meeting was taking place in the mainland at the same time with RGE.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L / CDM Smith Weekly BESS Drawings Meeting Reviewed design drawing status for Cambalache and Vega Baja: * None have been issued for Construction * Compared IFC scheduled dates vs. construction activities - Civil dates will need to be improved. * Audited Procore files to assure the latest issues are loaded. * Identified drawing revision numbers to be corrected. * Sargent & Lundy to issue drawing list status next week by project. Participants Sargent & Lundy, CDM Smith, CSA Group, and DCMC Partners.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria * Vega Baja - followed up Frame 5 transfer to location if Palo Seco or Jobos. Genera instructed to be delivered Central San Juan. * Spoke to Jose Lopez to consult inspection requirements for Lead Abatement if any to assure Clean Bill. * Followed up on approval status of Homeca's application # 1 & # 2. * Coordinate location for Ground-Breaking Ceremony Location & Aerial Photos
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Completed Review of EHS Manual to be implemented and issue to upload in Procore. Completed Cambalache Contractor Site Access Requirements
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Tesla Preferred Equipment Delivery Dates for Cambalache, Vega Baja & Costa Sur. Compared Tesla Delivery dates with current installation dates for Cambalache and Vega Baja on both deliveries are 5 months ahead. Will need to notify Tesla to delay the shipment. This will require a change order as the current PO allows for a notification 60 days prior to contractual date + internal Genera change order approval process. During the next two weeks will need formally start the notification process. Coordination with Tesla Installation Supervisor to be scheduled. Meeting Participants Carlos Palomares, Gabriel Perez, Franklyn Colmenares (CDM Smith), and Gilberto Sucre (DCMC).
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Designated Inspector Contract resolution was discussed for the PUI and Construction Inspections and Monthly Reports. Decommissioning Permit - Quarterly Report details were reviewed and submission dates identified. Field Team will take the lead to complete.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | *Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up - Mark Merritt, Michael Meritt, Anneilia Holton, Lauren Wells, Foster Veazey, Jack Darnall, Frances Vallejo, Ada Diaz, and Gilberto Sucre (DCMC) Key Updates Shared Across various topics: * Staffing Update, upcoming interviews, and relocation of personnel * ProCore Financial Training Update * Monthly Reporting * Community Engagement - Paola Arroyo * Tempest Audit * Ground-Breaking @ Vega Baja. * EHS Safety Plan Implementation * Centralized Project Site Support. * Office Space * Site Office Trailers for Costa Sur & Aguirre.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Updated action Items list for tomorrow and remainder of the week.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Weekly Execution Update with Jack Darnall, Foster Veazey and Gilberto Sucre (DCMC) Main topics discussed: * Program Execution * Staffing Updates * Procurement and Pre-Construction Participation * Monthly Report * Concerns and Risk Identification * Internal Roles & Responsibilities
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Weekly PMO Call with DCMC Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Jack Darnall, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Procore (Lauren Kennedy) to prepare for Friday's meeting for Financial discussions.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on configurations for Procore meeting minutes.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence for setting up Procore meetings with Procore, replying back to users that request have been completed.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on updating Procore permissions so that the pervious CDM Smith template doesn't allow admin for drawings.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on entering in change order forms to Procore.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore configurations for the scheduling tool for all BESS projects. This was requested by Carlos DeJesus (DCMC).
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Theresa Perez (DCMC) to discuss open Procore items.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondence for Procore with Theresa Perez (DCMC)
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore user onboarding and training materials. Also worked on Procore support to confirm that we cannot change a meeting minute number once it has been assigned, so that Jose Lopez (DCMC) can move to the next task.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Call with Osvaldo de Jesus (GENERA) about safety and security issue en Cambalache Site. Train in health and safety Claudio Cabral (INNOVATE COPR).
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Make a form for incidents reports by DCMC in site. Train Jorge L Aponte (ALTOL) and Jaime Rodriguez (ALTOL) about Genera Health and Safety Training. Job in Procore Vega Baja jobs. Inspections jobs in Vega Baja Site. Conference call with Osvaldo de Jesus (GENERA) about Costa Sur Site. Prepeare and train Elvin Lugo by Altol in Health and Safety Training Genera. Conference call Clara Padovani about Emergency Plans Genera Sites.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: . Make visit plan SOP for DCMC. Make a health and safety training for DCMC contractors.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Make a form for incidents reports by DCMC in site. Train Jorge L Aponte (ALTOL) and Jaime Rodriguez (ALTOL) about Genera Health and Safety Training. Job in Procore Vega Baja jobs. Inspections jobs in Vega Baja Site.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jorge Bracero (Genera) and Paola Arroyo (DCMC) to discuss community engagement workplan and site visit schedule.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch Up call to discuss staffing update, Lean Managemement Luncheon, Procore financials and next steps. Participants: Foster Veazy (Lemoine), Mark Merritt, Mike Merritt, Annelia Holton, Gilberto Sucre and Lauren Wells (DCMC).
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Drafted in excel the Community Engagement Work Plan for Paola Arroyo (DCMC), new employee. The plan includes all deliverables required for the position.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Carolyn Baez, DCMC, to discuss administrative PMO matters and shirt purchase.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR - Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Nyah Medina and Mike Merritt (DCMC) to discuss staffing update in preparation for the PMO update call with DCMC leadership.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Followed up with Jesús Cintrón (Genera) on several key pending items requiring coordination and next steps. Topics included the status of the PUI application for the Vega Baja BESS Project, the approval process for a pending RFR, and updates related to the Sargent & Lundy Task Order and a the pending FOMB RFI.The objective was to ensure continued momentum on critical project activities and alignment across procurement, funding, and contract execution processes.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Peakers - Began reviewing comments provided by Abraham Velázquez (DCMC) on the draft SOW for the Costa Sur Demolition RFP. Assessed the suggested revisions for clarity, accuracy, and alignment with the project’s objectives and procurement requirements. Identified sections requiring further refinement or discussion, and prepared to incorporate applicable feedback into the next version of the document.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Peakers - Finished reviewing comments provided by Abraham Velázquez (DCMC) on the draft SOW for the Costa Sur Demolition RFP. Assessed the suggested revisions for clarity, accuracy, and alignment with the project’s objectives and procurement requirements. Identified sections requiring further refinement or discussion, and prepared to incorporate applicable feedback into the next version of the document.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS - Engaged in a Conflict of Interest (COI) discussion with Ada Díaz, Frances Vallejo, and Gerardo Sucre (DCMC) to ensure alignment with Genera’s Procurement Manual and internal compliance protocols. Reviewed the current COI procedures and clarified requirements for proper documentation and certification. Additionally, consulted with Franklyn Colmenares (CDM Smith) to understand how other contractors typically complete the COI documentation, with the goal of standardizing expectations and ensuring consistency across all submissions.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Reviewed FOMBs RFI related to the S&L contract amendment. Drafted a detailed response addressing the questions and concerns outlined in the RFI, sent to Jesús Cintrón (Genera) for review and sign off.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS & Peakers - Reviewed BETA Electric Task Order #3 for accuracy, completeness, and alignment with the associated scope and contractual terms. After confirming all details, forwarded the finalized document to Jesús Cintrón (Genera) for signature and further processing.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -BESS - Participated in a feedback session related to the BESS RFPs, where we discussed the issue of low participation in recent procurements. Contributed to a strategic conversation on potential ways to increase market engagement, including the development of a targeted RFQ for the upcoming Aguirre-Yabucoa and Costa Sur procurement processes. The discussion focused on refining the approach to vendor outreach and qualification to ensure broader competition and alignment with project timelines and objectives. Genera: Christian Torres and Fernando Ortiz CDM Smith Franklyn Colmenares, Enrique Laya, Gabriel Sepulveda, Carlos Palomares. S&L Mike Kuczynski
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussion on Security Certificate and Implementation of Security Changes: - Discussed with Jean Gonzalez and Elba Rodriguez from Genera PR the requirements for the security certificate needed for deploying Genera Connect Financial Tracker and Time Tracker within Genera PR. - Began reviewing security changes requested by Michael Silva from Genera PR and collaborated with Aldwin Pagán from Integrum to start implementing these changes in the Genera Connect environment on the Azure cloud.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 184 | 644 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Financial Tracker Report and Application Testing: - Reviewed the financial tracker report sent by José Ralat from DCMC to identify issues for uploading to Genera Connect Financial Tracker. - Continued testing the Genera Connect Financial Tracker application to ensure all modules are functioning as intended.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Continue to Inspect Homeca Lead Base paint protocols were inspected mitigation and scrap steel transportation were conducted. Innovate conducted lead inspection supervised the inspection with Claudio Cabral on antenna trailer and field.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning MST Call with Luis Roman and Thessy Pérez (DCMC) to review Project SOP for Procore.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning briefing with VB DCMC's Vega Baja Jobsite management staff to review contractor daily activities.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Phone call with Lic.—Carlos W. Freites from CW Legal regarding the BVB jobsite CEST Plan Monthly Inspections.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project overview and scope of work monitoring for today's contractor's activities on the project to include deliverables, timelines, milestones and reports.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Central Aguirre Plant. Attendees, Miguel Beauchamp (Genera), & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work, project needs, construction compound areas. Measured areas.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Travel from Central Aguirre (17.951690, -66.229675) to Central Costa Sur (18.000463, -66.753480).
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Central Aguirre Plant. Attendees, Alexis Cruz (Genera), Francisco Mari (Genera) & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work, project needs, construction compound areas. Measured areas.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria 4339_ 9510 BESS Review status in drawnings, RFI, submittals & track table send by Carlos De Jesus from DCMC
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria 4339_ 9510 BESS Review cambalache power plant independent engineering report, send by Gilberto Sucre (DCMC)
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Exhibit K RFP-4826 document review for the installation of the 52 MW battery energy storage system in Cambalache
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project meeting with Program and Design Managers (Gabriel Perez, Franklyn Colmenares (CDM Smith), Mike Kuczynski (Sargent & Lundy), Gilberto Sucre (DCMC) to coordinate Request for Clarifications actions and pending items to complete value engineering and construction contract.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Generated correspondence related to RFI to GeneraPR to coordinate Warehouse inventory and temporary relocation prior facility demolition.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed project specifications for initial activities coordination.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Phone call and meeting with Sargent & Lundy (Francisco Mathews) for follow up of pending action item for the Request for Clarifications document evaluation.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Generated request to Program Managers for the required assets for PMO site office operation and construction monitoring.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Program meeting with Program and Design Managers (Franklyn Colmenares, Gabriel Perez, Enrique Laya (CDM Smith), Vincent Skochdopole (Sargent & Lundy), Gilberto Sucre (DCMC) to review project design drawings progress and pending items.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Contacted and met via Phone the manager (Jose Feliciano-Arecibo Speedway) for land/lot next to project site to ask for use of space for Construction staging. Developed correspondence for this request.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Organized and reviewed project documentation (uploaded by CDM Smith Franklyn Colmenares) in Procore for coordination with team purposes.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed Demolition specifications to provide comments on pending information to start Demolition activities.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with new Master Power BI send by Shellsea Maysonet of MZL for all LGA project. Start compare what are the project number with the DI number to confirm total cost of project. Made correction on DI 1229677 on CC tracker table with the total amount assigned to this project PW# 672950.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working in identify LGA project that can be duplicated with the critical component and reviewing the cost associated to the DI project versus Critical Component and LGA, such is at FEMA project number narrative, Asset Suite, Master Power BI table (La Sabana) and critical component tracker table. Created a table to include the total cost found on the LGA project reports, still pending information by Shellsea Maysonet of MZL regard of cost verification of all DI projects.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working in identify LGA project that can be duplicated with the critical component and reviewing the cost associated to the DI project versus Critical Component and LGA, such is at FEMA project number narrative, Asset Suite, Master Power BI table (La Sabana) and critical component tracker table.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working in identify LGA project that can be duplicated with the critical component and reviewing the cost associated to the DI project versus Critical Component and LGA, also searching at FEMA Grant project number narrative, Asset Suite, Master Power BI table (La Sabana) and critical component tracker table to evaluate information and compare cost.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Central San Juan warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega of Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Central San Juan warehouse to meet with Inventory Supervisor Mr. Milton Flores from DCMC. The purpose of the visit is to review the progress achieved so far and clarify any doubt regarding the process. During the visit, I will be performing quality control on the cycle count and assisting Mr. Flores with the process.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse finalizing the investigation of all discrepancies. This step is essential to ensure the accuracy of inventory records and to identify any necessary corrective actions to mantain proper stock control and data integrity.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-we continue at San Juan warehouse identifying discrepancies and investigating variances to ensure proper inventory control. This process helps maintain accuracy in stock levels, supports operational efficiency, and allows for timely corrective actions when inconsistencies are found.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Central San Juan warehouse, assisting Mr. Flores on cycle counts, recounts, to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Report status in Drawings, RFI, Submittals & Track table, sent by Carlos De Jesus from DCMC.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Review Cambalache Power Plant Independent Engineering Report, sent by DCMC Gilberto Sucre.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS call with Carlos De Jesus, DCMC, to discuss about the status schedule task.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Schedule an appointment for TWIC Card evidence.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS call with Andres Concepcion DCMC, to discuss about the status in Drawings update, RFI, Submittals & Track table and coordination a meeting with Herminio Arroyo from Genera PR.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review 20250221-MI20210002-Motion to Request Approval for Rehabilitation Projects, sent by DCMC Gilberto Sucre.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Homeca recycling company started some part of the demolition, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created and read some submittals.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I supervised the same contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, I continued to work on all the submittals that needed my attention for today.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I supervised the contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Bess, uploaded documentation and photos to Procore app on daily log including mitigation documents, assistance and equipment.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Homeca Lead Base paint protocols were inspected mitigation and scrap steel transportation were conducted. Innovate conducted lead inspection supervised the inspection with Claudio Cabral on antenna trailer and field. Day 2 assisted on conducting diesel test on tanks.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Change Orders Review based on mutual agreement between Genera and Tesla. Aligning financial information with project cost adjustments in order to request next working capital advance. Change Order relates to Payment Milestone #2 and #3. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 164 | 656 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria_PW11855 Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting Recounts List # 321 to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. 10 Locations AC051-AC060, 41 items and 492 pcs were worked on. This information was validated the employee in charge of Genera PR, Adan Silva.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AD022 to AD 029.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from location AD022 to AD 029.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to the Inventory Manager, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum levels from location AD022 to AD 029.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse San Juan, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. Location AD022 to AD 029.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, working on the recount of the discrepancies found on Locations AD-01-000 to AD-01-039.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and continued investigating discrepancies from locations AD-01-000 to AD-01-039.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD-01-000 to AD-01-039.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AD-01-000 to AD-01-039
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists # 321 to begin the cycle counts.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, conducting ABC Cycle Counts List # 321. In coordination with the Warehouse Supervisor of Genera PR, Adan Silva.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. At the warehouse #16 Palo Seco, Toa Baja, preparing a detailed report outlining the work completed throughout, which will be submitted to my supervisor, Mr. Paul Browne from DCMC, to support the preparation of his report to Genera PR.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Worked on Vega Baja Documents / Data Entry for Permitting/Financials
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Workshop with Lauren Wells (Lemoine) regarding Meeting Module in Procore/ Procore Workshop with Jose Lopez DCMC of Meeting Module in Procore/Procore Coordination w Xiomara Perez & Vernadee Ortiz RG Engr
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Certification: Project Management
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Core Tools review/audit: Project Teams, Administrative Information of Cost and Time, file naming structure and more.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – SOP for Procore Tools: Schedule, Photos and RFI. Also, reviewing SOP for Vendor's Submittals to establish procedures for assessing and qualifying suppliers to ensure compliance with quality standards and regulatory requirements.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 149 | 447 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 Continue Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#2, Invoice #18334031_Jan2025. Continue reviewing invoice, read and verify narratives in compliance with PA. This invoice has discrepancies with employees, after reviewing I open a full RFI for January invoices since I noticed that all excels has different invoice number and totals from the pdf invoice version. Also, I send a message to S&L by teams about the email with the RFI to clarify any question.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 149 | 521.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Finish Pre-Intervention on CDM Invoice #90231898, all documents were reviewed and confirmed deliverables. I proceed to prepare file for Genera Signature. Issues with sizing was presented, invoice need to be splitted from backup documentation and temporary resolved. Also, I confirmed to CDM that this invoice complete Pre-Intervention process and that was sent to Genera for Signature.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 Start Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#2, Invoice #18334031_Jan2025. Review invoice and prepare RFI since there are discrepancies in narrative and plants that does not permit to continue pre intervention process. This RFI was sent to Sargent and Lundy for clarification.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Look for excel invoices for Sargent and Lundy: Inv. #18315396, 18293398, 18293399, 18293396, 18315395, 18315393 and 18300330 and share them with José Ralat DCMC so the team can prepare the RFR's corresponding to these invoices.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting with the Genera PR team to schedule 'next steps' of pending projects, update and update the work agenda for the next few days
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams Meeting with DCMC Team: Frances Vallejo Rosich, D'Alexzander Gonzalez and Mark Merritt. In the meeting was the Genera Team: Jesus Cintron, Kevin Futch, Francisco Santos, German Nunez, Alejandro Maymi and Sarahi Medina Nieves. In the meeting was the CDM Smith: Juan Mendoza, Rafael Pabon and Calos Palomares. The meeting was about Peakers Check In.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting with Jorge Bracero from Genera at the City View offices related to the Community Engagement Work Plan. In this meeting we have Frances Vallejo, DCMC. We discuss about the BESS site visit; Peakers site visits; Community Engagement Plan; Stakeholder mapping and the program expectations.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I was reviewing of the SharePoint file like send by Jorge Bracero for Genera, to my email. Create an account in Procore. Review the flowchart COMMS Plan Vega Baja, Genera bulletin and the Kroma draft Plan de Communication for Vega Baja because one of the functions discussed will be the update of these plans.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria review of Cambalache Community Relations Plan send by Jorge Bracero Nieves from Genera via email to start understanding the Cambalache project in order to begin implementing a community outreach plan.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I work on the coordination meeting with Jorge Bracero (Genera) in City View Plaza for the BEES project. Coordinate a new time since the client was going to be delayed due to logistical issues.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Reviewed email from Andres Concepción (DCMC) regarding the equipment list for the Cambalache site. Reviewed an email from Gilberto Sucre (DCMC) to Jean Pierre Menay (DCMC) concerning TWIC card requirements. Jean P. Menay provided a link for the TWIC application, which was forwarded to Andres Concepción, Luis Duque, Luis Damudt, Jorge Mercado, and Carlos de Jesús (DCMC). Updated the NDA for Paola Arroyo (DCMC), printed documents for her initials and signature. Sent the signed NDA to Franklyn Colmenares (CSA Group).
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with Genera PR, RGE, Sargent and Lundy about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was review documents to generate status report of Procore RFI, Submittals and Drawings. File was sent to Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was creating a report status of Procore RFI, Submittals and Drawings file sent to Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 134 | 335 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue reviewing the RFI, submittal and drawings documents for the 4339_9510 BESS_Cambalache project.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the updated submittal documents for the 4339_9510 BESS_Cambalache project.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review the RFI, submittal and drawings documents for the 4339_9510 BESS_Cambalache project.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue reviewing the updated submittal documents for the 4339_9510 BESS_Cambalache project.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Proceed with the development of the Power BI dashboard for the monthly report, focusing on Critical Components data and updates.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue working on the monthly report, focusing on Inventory Management status and updates.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with the development of Power Bi dashboard for the monthly report that includes project progress, project control - budget, project control - schedule, project control - key milestone, RFPs, staffing, Procore trainings, critical components and inventory.
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 10.64 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- travel directly from home to Central San Juan, round trip, to meet with Mr. Milton Flores from DCMC to review the progress made so far and provide onsite support throughout the day to address any questions regarding the process
2025-04-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 161 | 0.7 | Yes | 25-145003 | Harry Del Valle 4/15/2025 Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Central Aguirre (17.951690, -66.229675) to Central Costa Sur (18.000463, -66.753480) to home Office Luquillo Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Central Aguirre Plant. Attendees, Alexis Cruz (Genera), Francisco Mari (Genera) & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work, project needs, construction compound areas. Measured areas. Meeting & Coordination for Central Costa Sur. Attendees, Miguel Beauchamp (Genera), & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work, project needs, construction compound areas. Measured areas. Total Mileage 230 Miles
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 384.8 | 384.8 | 384.8 | Yes | 25-145003 | Portosan - Portable Toilet Rental - Vega Baja
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 prepared for upcoming meeting on Costa Sur scope of work and PMO meeting late this week.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 working on final revision of Costa Sur demolition.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed Lemoine's Incident report form to be implemented and discussed with Jean Pierre Menay (DCMC).
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria e-mail correspondence review, response and organized agenda for the day.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The Project Coordination Meeting for the RFC Meeting RGE Cambalache focused on several key topics including updates to the RFC documentation, project status, foundation design, stormwater retention requirements, and fire protection system design. Mike confirmed the posting of the new RFC in the Ignite folder and emphasized the importance of using this folder for document version control. The team discussed upcoming design concepts and the need for updated seismic calculations from Maurice Shea, as well as issues related to the steel drawings. Foundation elevation options were analyzed, with recommendations to either maintain or slightly reduce the current height to improve water retention. The team clarified stormwater retention requirements in light of FEMA regulations and discussed a need for AutoCAD site survey versions to explore potential solutions. Gary reported on the fire protection system design, highlighting the absence of internal fire suppression in Tesla containers and the need for MODBUS communication. Action items were assigned to team members, including sending relevant drawings and documents, facilitating insurance discussions, and scheduling follow-up meetings to ensure project continuity. The meeting concluded with a need to adjust future schedules due to travel commitments.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Update discussion with Jose Lopez of daily activities and the EHS Incident occurred the day before.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre. Harry del Valle (DCMC) presented the site options to locate the project temporary facilities. Golf cart will be required to move along the site.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - `DCMC - Zoom meeting with Foster Veazey, Lauren Wells, Frances Vallejo, Abraham Velazquez, Connie Wright, Gilberto Sucre, Paul Browne, Glorimel Torrado, Anneilia Holton-Williams, and Lygia Irizarry Nieves (DCMC) for the Tempest Discussion (PMO Leadership) to explain that the narrative must be completed daily and to provide guidance on how to do so. Topics included daily time allocation, the rejected narrative, and the observation that some individuals are performing the same tasks every day, which presents an opportunity to create a different narrative. The workday should be divided into two 4-hour blocks, with no more than 5 consecutive hours of work, as everyone is required to take a break after 5 hours. Additionally, narratives should avoid referencing specific positions.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre - Continued discussion with Harry del Valle (DCMC) on the temporary site facilities and construction staging.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Daily evaluation and updating action items list
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Weekly Meeting - Review and Progress Status of BESS Program by site. Sargent & Lundy, Tesla, Genera, CDM Smith, CSA Group, & DCMC Partners participated.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed Vega Baja Decommissioning Quarterly Report with Project Team Jose Lopez (DCMC), Manuely Concepcion (CDM Smith), Jaime Pesquera, and Gabriel Perez (CDM Smith). Draft to be issued to Genera on Monday for their comments.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluation of PMO Monthly Report Dashboard prepared by Raissa Borges DCMC, as well as data validation.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Cambalache mobilization, Value Engineering, and Reviewing RGE RFC's and Sargent & Lundy recommendations.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Continued reviewing Decommissioning Quarterly Report.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adjusting Procore permissions for Andres Concepcion (DCMC) for access to submittals and RFI's for Admin access to have oversight for the project site.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on process improvement tweaks for capturing everyday tasks and alignment.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore training schedule to share with Luis Roman (DCMC) to plan for future training sessions.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence for photo module and deleting of a mistaken photo. Also discussed responsibility of this task going forward should be on Luis Roman (DCMC).
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for Procore questions.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing Submittal SOP's from Luis Roman (DCMC) for us to publish to users.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Procore research for Quality tools and new updates to the system.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued worked on reviewing Submittal SOP's from Luis Roman (DCMC).
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) updating Procore Tools tracker and milestones.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Correspondence field set for use in Financial Management.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) to discuss Procore open items. We discussed scheduling tool, permissions and training schedule items.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | PREPA Genera Deliverable 11 DR 4339. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Gilberto Sucre, Jack Darnell, Lauren Wells, Foster Veazey, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Flores, Milton | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 186.58 | 186.58 | 186.58 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Boots, helmet and glove for counting inventory in San Juan warehouse. (receipt date 4.12.25)
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria, Conference call with Osvaldo de Jesus (GENERA) about Health and Safety incident in Vega Baja Site. Conference call with Carirma Sanchez (HOMECA) about Health and Safety incident in Vega Baja. Working with Gilberto Soto (DCMC) this incident. Work in Procore about all Genera Sites.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 184 | 414 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur inspection site with Richie Correa, Luis Torres, Osvaldo de Jesus and Clara Padovani by Genera. Metting with Luis Torres, Richie Correa and Osvaldo de Jesus about Health and Safety, Security and Emergency Managment ares in Costa Sur Site. Conference call about safety incidentes in Vega Baja. Create at safety requirements for Costa Sur site.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur inspection site with Richie Correa, Luis Torres, Osvaldo de Jesus and Clara Padovani by Genera. Meeting with Luis Torres, Richie Correa and Osvaldo de Jesus about Health and Safety, Security and Emergency Managment areas in Costa Sur Site.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 184 | 138 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Continuum Metting with Gabriel Perez (CDSIMITH), Osvaldo De Jesus (GENERA) Ricardo Pallens (GENERA) about Genera process and Vega Baja Site Demolition Jobs. Review the SOP between DCMC and Genera.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur inspection site with Richie Correa, Luis Torres, Osvaldo de Jesus and Clara Padovani by Genera. Metting with Luis Torres, Richie Correa and Osvaldo de Jesus about Health and Safety, Security and Emergency Managment ares in Costa Sur Site.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Gilberto Sucre (DCMC) to discuss staffing rearrangement and incident that occurred in Vega Baja site.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11¦ DR 4339 - Hurricane Maria - Meeting with Paola Arroyo (DCMC) to discuss work plan, site visit and Governors Visit at the Vega Baja plant.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Raissa Borges (DCMC) to discuss monthly report dashboard to the client. We discussed budget, employees hired and other report formats that need to be changed.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Prepared for the weekly BESS and Peakers catch-up call by reviewing and updating the project tracking spreadsheet. Incorporated feedback and updates received on 04/15 from the Genera procurement team, including changes to documentation status, and contractor communications. Ensured the tracker reflected accurate, real-time information to support productive discussion, alignment across teams, and timely follow-up during the coordination meeting.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -BESS -Engaged in a detailed conversation with Ricardo Pallens and Jesús Cintrón (Genera) regarding the Tetra Tech contract amendment and the proposed approach for moving it forward. Discussed compliance considerations and alignment with project funding requirements. Identified next steps for finalizing documentation and advancing internal approvals.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- BESS -Continued preparing the amendment package for the Tetra Tech contract. Reviewed and reformatted the Federally Funded contract clauses to ensure alignment with the MSA.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS -Continued preparing the amendment package for the Tetra Tech contract. Drafted the Second Amendment to support the request.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - BESS & Peakers weekly catch up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site File an incident report for an Homeca employee.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PROJECT MANAGEMENT ACTIVITIES.Activity and resource planning Organizing and motivating a project team Controlling time management Cost estimating and developing the budget Ensuring customer satisfaction Analyzing and managing project risk Monitoring progress Managing reports and necessary documentation Project managers manage people, tasks, schedules, and resources through the project lifecycle.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued working with projects documents for the Central Aguirre Project, reviewing drawings specifications, scope of work, soil studies. Looking for possibles discrepancies & measures. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for Office Trailer.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working with projects documents for the Central Aguirre Project, reviewing drawings specifications, scope of work, soil studies. Looking for possibles discrepancies & measures. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for Office Trailer.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Completed working with projects documents for the Central Aguirre Project, reviewing drawings specifications, scope of work, soil studies. Looking for possibles discrepancies & measures. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for Office Trailer.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria An inspection was carried out in the area of the warehouse of Roseanne López (Genera) Andrés Concepción (DCMC) as part of the demolition, in addition to the possible areas for the temporary warehouse
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Exhibit K RFP-4826 document review for the installation of the 52 MW battery energy storage system in Cambalache
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria An inspection was carried out in the area of the warehouse of Roseanne López (Genera) Andrés Concepción (DCMC) as part of the demolition, in addition to the possible areas for the temporary warehouse
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria coordination meeting with Luis Damudt (DCMC) Andrés Concepción (DCMC) on site prior to the walk with the client Genera
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordination meeting for the demolition part of the warehouse with the client where Erminio Roseanne Pérez (Genera) Luis Damudt (DCMC) Andrés Concepción (DCMC) participated
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed project Technical Specification for contractor RG Engineering mobilization coordination.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Organized Warehouse temporary relocation meeting notes to distribute to team and contractor (RG Engineering) to be considered during activity.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Meeting with Cambalache Facilities Genera management team (Herminio Arroyo, Roseanne Perez, Kevynne Gonzalez) to discuss warehouse temporary relocation considerations based on current warehouse layout, inventory, flow of goods, accessibility of storage areas, and utilization of space.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR -Defined temporary storage coordination action items and developed meeting agenda to meet with Genera PR Facilities team in Cambalache.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed a temporary stormwater management plan to minimize impacts during civil activities regarding the flow and quality of stormwater during project’s construction,
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Received email from Rafael Torres of Malnat that Air Basket Heater for Palo Seco will arrive on 21-25 of April. Send an email to Jose Hernandez of EPS to provide status in regard of delivery of PO 106735 schedule to arrive on April 21. Received email from Maria Hernandez of EPS to inform that PO 106735 was pick on April 2 by WEB PRO with WW1167462 and will contact them to confirm the ETA. Continue working with the identification of the LGA project that may be duplicate with CC equipment cost.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with new table for LGA vs CC projects, to identify the project that has cost on critical components and Legacy to presented to Joaquin Quinoy of Genera to then evaluate on a meeting next week to go by each item to verify if item is a purchase of an equipment or labor for installation with this exercise we can identify duplicity of purchase of equipment.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Send an email to Joaquin Quinoy of Genera to verify total cost of Critical Components versus Legacy (LGA) projects. Joaquin Quinoy of Genera requested to verify delivery of Air Heater Basket (Hot and Cold) for Costa Sur. Contacted Juan Maldonado of Malnat to verify delivery status of the Air Heater Basket of CS and are in schedule for May 2025, this information was provided to Joaquin of Genera. Continue reviewing the Master Power BI Mapping to confirm cost of NME project that may be duplicate with Critical Components.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working in identify LGA project that can be duplicated with the critical component and reviewing the cost associated to the DI project versus Critical Component and LGA, such is at FEMA project number narrative, Asset Suite, Master Power BI table (La Sabana) and critical component tracker table. Completed the new table with information used by the Master Power BI - Mapping.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at the Palo Seco warehouse, continuing with the cycle count and assisting Mr. Giovanni Taffanelli DCMC with the inventory process to ensure materials and equipment are available when needed, reducing delays and cost overruns for the project.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 |  | 167 | 459.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse assisting Mr. Giovanni Taffanelli DCMC investigating any discrepancies to ensure proper stock control and alignment with inventory records to streamline operations, reduce costs, and improve project outcomes. Today we work on locations AC061 TO AC066.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse, assisting Mr. Giovanni Taffanelli from DCMC on recounts, to verify inventory accuracy. and investigating any discrepancies to ensure proper stock control and alignment with inventory records. Today we work on locations AC061 TO AC066.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse with Inventory Supervisor Mr. Giovanni Taffanelli from DCMC. The purpose of the visit is to review the progress achieved so far and clarify any doubt regarding the process. During the visit, I will be performing quality control on the cycle count and assisting Mr. Taffanelli with the process.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were AC061 to AC066, AD01039 to AD01066, AD030 to AD040.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Site walkthrough to assess potential site coordination efforts with Andres Concepcion, Jorge Alexis Mercado DCMC, Kevin Gonzalez, Rosseanne Perez Genera PR.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- 4339_9510 BESS Review Report Attachment status in Drawings, RFI, Submittals & Track table, sent by Andres Concepcion from DCMC.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Review Action: Report status in Drawings, RFI, Submittals & Track table updated April 16, 2025, sent by Carlos De Jesus from DCMC.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Review Report Attachment E Federal Contracting Clause, sent by Andres Concepcion from DCMC.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Meeting Cambalache facilities about the coordination works plan with Herminio Arroyo, Kevin Gonzalez Genera PR, Andres Concepcion, Jorge A. Mercado and Luis O. Damudt DCMC Partners.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Supervised the contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I conducted a meeting with the contractor Homeca. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals and read them.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I worked alongside the contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I conducted a meeting with the contractor HOMECA. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed attention, I also created submittals, worked on all the submittals that needed my attention for today.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I walked the site all day long with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Homeca Lead Base paint protocols were inspected mitigation and scrap steel transportation were conducted. Innovate conducted lead inspection supervised the inspection with Claudio Cabral on antenna trailer and field. Continues assisting on conducting diesel test on tanks.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety guidelines and regulations, took pictures and generated my daily report. In this part of the project we are, Verified the employees and site for Quality. Inspected Homeca Lead Base paint protocols were inspected mitigation and scrap steel transportation were conducted. Innovate conducted lead inspection supervised the inspection with Claudio Cabral on antenna trailer and field.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Change Orders Review based on mutual agreement between Genera and Tesla. Aligning financial information with project cost adjustments in order to request next working capital advance. Change Order relates to Payment Milestone #2 and #3. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Genera & Tesla Weekly project management meeting. Contract 106761. Project development based on deliverable schedule. Meeting between Tesla team (Carlos Melendez, Jefferson Silver, Laura Miglietti, Keyur Javiya, Howen Lim and Qais Feroz) , CSA (Franklyn Colmenares), CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczinski, Vincent Skochdopole, Reinaldo Romero, Nelson Rosado.) and DCMC (Rafael Calderon).
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria_PW11855 Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-02 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #293566-10 for TO#2 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC061 to AC066.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report. Location from AD30 to AD40.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AD30 to AD40.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse San Juan, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. Location from AD30 to AD40.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria At the warehouse San Juan, conducting cycle counts, conducting recounts to verify inventory accuracy, and investigating any discrepancies to ensure proper stock control and alignment with inventory records. From location AD30 to AD40.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to the Inventory Manager, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum levels.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria at Costa Sur warehouse, working on the recount of the discrepancies found from locations AD 01 039 00 to AD 01 066 00.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AD 01 039 00 TO AD 01 066 00
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AD 01 039 00 to AD 01 066 00
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD 01 039 00 to AD 01 066 00
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC061 to AC066.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC061-AC066.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists # 323 to begin the cycle counts.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued working on Projects Data Management in Procore for Cambalache to plan, regulate, and control the project and identify and manage risks.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Worked on Projects Data Management in Procore for Aguirre_Vega Baja to plan, regulate, and control the project and identify and manage risks.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review with Project Teams the requirements for Documents back-up at the Document Tool.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) for current assignments updates: Schedule and Inspection tools implementation.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Implementation of Schedule Tool for projects; perform schedule update on Training Project to develop proper Schedule SOPs.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform Procore platform review on Documents Tool on active construction projects.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Project Schedules in order to provide proper guidance on uploading and monthly updating schedules.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 149 | 372.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#9, Invoice #18334036. Verifying the invoice rates with the contract rates and the new invoice provided in RFI by contractor. Organizing and formatting excel document.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. Principal purpose is to verify pending invoices to be attended today. Also, I verify Sargent and Lundy response sending updated invoices information. I update the files in sharepoint and update the Tracker with correct quantities for January invoices.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón DCMC to update tracker and prepare presentation for Internal Meeting on Thursday. During this meeting we review all invoices worked during this week and confirm tracker formulas. Also, we discuss findings on invoices that are important pending issues for this week. The preliminary Power Point presentation was sent to Shellsea Maysonet (contractor) and D'Alexander Gónzalez (DCMC). I also coordinate for tomorrow work on DCMC invoices payment report.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#9, Invoice #18334036_Jan2025. Prepare formal RFI requesting compliance sampling documents for this invoice. Complete review and send email to Vendor.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 149 | 447 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#1, Invoice #18334031. Verifying the invoice rates with the contract rates and the new invoice provided in RFI by contractor. Organizing and formatting excel document.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 139 | 556 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Identify local NGO's to partner with in site locations in Vega Baja for the BESS Project. A dynamic and interactive list was created for the benefit of the client. The chart includes all the names, number, location and important information according to the NGO's. Carry out the same procedure with the public housing units of Arecibo and Vega Baja. A table was made in the same way that includes names, telephone number and address
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Work on a community engagement work plan focused on DCMC's role in the Bess project in Vega Baja using the documents that Jorge Bracero, from Genera, has been sending as support The document focuses on my tactics to be more efficient and have a draft that we can work with as the project progresses with a focus on the specific needs of the client. The document is for internal use and does not alter Jorge's work plan but seeks to align us with the client at the level of communications with the identified audiences.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 prepare for a meeting that will be held tomorrow by Teams with the Genera team related to the BESS project in Vega Baja. The meeting is about groundbreaking event of Vega Baja in coordination with Fortaleza will be scheduled for Thursday, April 24. The meeting is being coordinated by Jorge Bracero, Community Relations Manager for tomorrow, April 17 at 11:00 a.m. Create an agenda, search for related materials and immerse myself in the topic
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue reviewing the floor plan drawings for the 4339_9510 BESS_Cambalache project.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was to send a document using a contractor scope proposal of project with review and comments to Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was created a report status of Procore RFI, Submittals and Drawings file sent to Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was to send a document in a week summary report using a Procore RFI, Submittal and Drawing status, schedules reports, contractor scope proposal, review of value engineering, recommended notes and letter of project with review and comments to Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue reviewing the updated submittal documents for the 4339_9510 BESS_Cambalache project.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the floor plan drawings for the 4339_9510 BESS_Cambalache project.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review the updated submittal documents for the 4339_9510 BESS_Cambalache project.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with Genera PR, RGE, Sargent and Lunder about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal Teams Meeting with Frances Vallejo, DCMC. The purpose of this meeting is to discuss project reports status and updates. The meeting was organized by Frances Vallejo (DCMC).
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue collecting data for the Inventory Management project to support the development of the monthly report.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 122 | 366 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing data from the projects schedule and budget to support the development of the monthly report.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue updating master tracker and to support the Power Bi monthly report.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.35 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-after completing the meeting at the Palo Seco warehouse with Mr. Giovanni Taffanelli from DCMC, drove back home to Guaynabo. The purpose of the visit was to review the progress achieved so far and clarify any doubts regarding the process. Also, we assist Mr. Taffanelli with the process.
2025-04-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 7.84 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel from home in Guaynabo to Palo Seco, the purpose of the visit is to review the progress so far and clarify any doubt regarding the process of cycle count.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 participated in a BESS&PEAKERS check in meeting, discussed current status on individual projects brief overviews. CDM Smith Franklyn Colmenares, Rafael Pabon, Genera Jesus Cintron, DCMC Sheila T. Sterling.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 resumed working on final revision of Costa Sur demolition.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Dashboard Review & Comments. Gilberto Sucre and Raissa Borges (DCMC) met to review draft Dashboard provide recommendations and data to be validated. Agreed to issue draft next week for comments to formally issued April's Monthly Report the 2nd week of May.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Internal Meeting PM / CM Team. Purpose of meeting is to be aligned with RGE final scope items pending to be submitted, budget and schedule to complete the post bid exercise to achieve Notice to Proceed. there will be a follow up meeting with RGE on Friday, and next week Tuesday and Thursday. From there will transfer to a construction meeting led by the DCMC Field team. Gabriel Perez, Enrique Laya, Franklyn Colmenares (CDM Smith), Mike Kucynski (S&L), Reinaldo Romero and Gilberto Sucre participated.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Project & Budget Meeting
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Internal coordination with Frances Vallejo (DCMC) of April's Monthly Dash-Board draft to be issued next week, staffing draft on BESS projects and incident investigation status for Vega Baja,
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Ground-Breaking Ceremony Coordination Meeting to be held on April 24th 10-11 AM.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Coordination between Gabriel Perez (CDM Smith) and Gilberto Sucre of daily tasks upcoming meetings agendas and Vega Baja Incident Status.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Homeca's Incident review notifications, correspondence, management, and meeting with DCMC Jose Lopez, Jean Pierre Menay and Gilberto Soto related to employee's hand injury the prior day.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO EHS Incident reporting process implementation to be established for BESS/Peakers Program.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting RGE Cambalache, continued evaluation of RFC's, Value Engineering, and finalization of poet bid process. Sargent & Lundy, RGE, CDM Smith, CSA Group & DCMC Partners.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Update of action items list.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on review of Safety Plan that Gilberto Sucre (DCMC) provided for guidance on how/what we use Procore for. Worked on Procore safety topic outline for discussion with Jean Pierre Menay (DCMC)
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financials.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tools table for all open items.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Meeting coordination for safety and Procore discussion today.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Jean Pierre Menay (DCMC) and Luis Roman (DCMC) for discussion of safety plan and use of Procore.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore configurations for permissions templates and trying to find out why Theresa Perez (DCMC) can't see some of them even though permissions are correct.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 225 | 450 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore financial implementation plan and open items to deliver to leadership on where the finish line is for completing this.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on correspondence for Procore items for Jose Lopez (DCMC) and Luis Roman (DCMC)
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Training Paola Arroyo (DCMC) in Genera Health and Safety Training. Call with Franklin Colmenares and Gabriel Perez CDSMITH about Genera Projects. Call with Osvaldo de Jesus (GENERA) about the Genera Vega Baja Site. Meeting with Gilberto Sucre (DCMC) about the Vega Baja Incident. Call about Yabucoa Site Viste with Angel Rivera (LUMA) and Gabriel Perez (CDSMITH). Coordinate the Yabucoa Site Inspection.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 184 | 322 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Call with Gilberto Soto (DCMC) and Carirma Sanchez (HOMECA) about H&S incident in Vega Baja. Call with Osvaldo de Jesus (GENERA) about all sites and activities Genera.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review the ERAP by Costa Sur Plant. Metting with Lauren Wells (Lemoine) about Safety section in Procore.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 1 | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review the ERAP by Costa Sur Plant. Review the documentation for incidente H&S in Vega Baja Site. Work in Procore Vega Baja incident.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Vega Baja Ground Breaking Event Prep Meeting with Genera's communication team to prepare for the Governor's visit at Vega Baja plant. Participants: Paola Arroyo (DCMC), Jorge Bracero (Genera), Gilberto Sucre (DCMC), Rafael Rodriguez (Genera), Franklyn Colmenares (CSA).
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Genera Project Management team for BESS and Peaker projects to discuss the projects schedule and budget status. Participants: Carlos Palomares (CDM), Gilberto Sucre (DCMC), Raissa Borges (DCMC), Abrham Velazquez DCMC.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Gilberto Sucre and Raissa Borges (DCMC) to discuss dashboard, review first draft and discuss comments.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - RFP 4826 – BESS Installation at Cambalache: Reviewed and organized the RFP procurement file in response to questions raised by Franklyn Colmenares (CDM Smith). Ensured all relevant documents were clearly named, properly filed, and aligned with procurement standards. Provided specific references and explanations for each of the 14 items he inquired about to facilitate clarity, traceability, and efficient follow-up. Provided such information to CDM Smith, S&L and Genera Team.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Grid Support Units (Peakers) Began reviewing the selection summary and award analysis documentation as requested by Joel Pantojas (Genera). Assessed the existing content for completeness, consistency, and alignment with procurement requirements. Initiated the drafting of an updated version, incorporating relevant scoring rationale, and supporting justifications to ensure transparency and compliance with internal and federal procurement standards.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Implementation of Changes and Security Certificate Review - Continued working with Aldwin Pagán from Integrum to incorporate changes into the production and development environments of Genera Connect, addressing observations made by Michael Silva from Genera PR. - Reviewed compliance of the security certificate provided by Aldwin Pagán from Integrum to proceed with purchasing the security certificates for Genera Connect.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.75 |  | 184 | 506 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Scheduling Software Requirements and Discussion on Certificates - Reviewed requirements to enable scheduling software in Procore to improve scheduling for critical components projects. - Discussed certificate requirements with Michael Silva from Genera PR and Aldwin Pagán from Integrum for the Genera Connect Financial Tracker and Time Tracker components.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety. Make sure they comply with the safety protocols and measures while conducted lead base abatement clearance by Homeca.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 |  | 167 | 459.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Incident report documentation submitted by contractor HOMECA reviewed and discussed with Gilberto Soto (DCMC) and Gilberto Sucre (DCMC).
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning call with Gilberto Sucre (DCMC ) to review yesterday's project occurrence. VEGA BAJA BESS PROJECT.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Status report draft review with the Vega Baja PM Team. Gilberto Soto and Jaime Pesquera.(DCMC)
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - working with the Status Report based on meeting with Gilberto Sucre (DCMC) for the project regarding yesterday's occurrence.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working with projects documents for the Central Costa Sur Project, reviewing drawings specifications, scope of work, soil studies. Looking for possibles discrepancies & measures. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for Office Trailer.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Completed working with projects documents for the Central Costa Sur Project, reviewing drawings specifications, scope of work, soil studies. Looking for possibles discrepancies & measures. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for Office Trailer.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued working with projects documents for the Central Costa Sur Project, reviewing drawings specifications, scope of work, soil studies. Looking for possibles discrepancies & measures. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for Office Trailer.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Exhibit K RFP-4826 continued document review for the installation of the 52 MW battery energy storage system in Cambalache
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - 04339 _9510 BEES Review Report Status in Drawing RFP, Submittals and Submission & track table, send by Carlos de Jesus from DCMC
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of the RGE contractor's safety plan.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed correspondence to communicate to DCMC Sr. Construction Manager (Gilberto Sucre) the Temporary Warehouse considerations that RG Engineering may considered. This is to be shared with Program Manager (Carlos Perez-CDM Smith) for contract discussion.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed Cambalache team scheduler (Carlos De Jesus) weekly report regarding impacts to project timeline and ensure corrective actions.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed correspondence to direct Cambalache site team to begin reviewing project demolition specification to prepare ahead the initial coordination of this activity.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed Cambalache contractor (RG Engineering) cost proposal and schedule. Evaluated proposal comparing with RFP requirements and project specifications define project controls.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewing and assesing all project information that is tracked in Procore such as RFIs and Submittals.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Review and evaluation of project technical specifications to ensure they are complied by General Contractor during construction of BESS project.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Generated Entries in Procore platform to document 4/16/2025 site visits photos and meeting notes.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Cambalache RFC meeting with CDMSmith (Gabriel Perez), Sargent & Lundy (Rob Molner), RG Engineering (Jose Robles) and MorrisandShea (Bill Shea, Peter Deming) for foundation design discussion regarding technical considerations to complete the design proposal and pricing of rigid inclusions structure.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue reviewing LGA project table to identify duplicate project with Critical Component tracker table, reviewing using Asset Suite, FEMA Project Reporte and Master Power BI Mapping to identify the project description on the DI to confirm item with critical component resolution agreement. Updated start and end date for Cambalache Diesel Tank #2 Rehabilitation.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing critical components lead tracker table installation simple table tab to fix formula that was giving an error. Reviewing project cost of DI 1231434 to confirm cost with our critical component's tracker table has not a wrong data entry. Made correction on critical component tracker table for Costa Sur and Aguirre Boiler Feed Pump DI number regard of project # 669233 and 672950. Working on generating weekly report for PMO presentation of progress work related to Critical Components. Meet with Joaquin Quinoy of Genera to inform that CPM recommend a Design and Build for the Leak Detection System of Cambalache due to the route is different from the drawing and to evaluate the equipment need for this project.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Pre-Meeting with participation from DCMC: Rick Patterson, Rafael Calderon, Eisha Mercader, Victor Maldonado, Glorimel Torrado, Mark Merritt, Marc Maceira, Danny Martinez, Ginnell Torres, Rick Patterson, Christian Cruz, Sheila Torres, Paul Brown, Rafael Cordero, Sheila Torres and Roberto Bosch; to discuss draft presentation priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process before presenting to Genera PR.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - CPM Jose Prado, Luis Tapia, Carlos Castro, Diana Rivera and Victor Alvarez; DCMC Eduardo Rivera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, Discussion of Cambalache Leak Detection System, and reviewing the deliverables for SOW & CE.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working with verification of LGA project table that may be duplicate with Critical Component projects table, reviewing each project at Asset Suite and FEMA Project Reporte to identify the project description DI with the Master Power BI Mapping table.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Meet with Miguel Del Valle of Sargent and Lundy to discuss if they need any additional information regard of proposal for Fire Protection System at Cambalache Plant, all scope was discussed, and they will provide no later than next week a proposal that will be send to Joaquin Quinoy of Genera to evaluate and provide a Task Order.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with verification of LGA project table that may be duplicate with Critical Component projects table, reviewing each project at Asset Suite and FEMA Project Reporte to identify the project description DI with the Master Power BI Mapping table, made correction on DI1222398 and DI1229685 for project cost with Master Power BI Mapping information, this project may require to confirm equipment if is related to BFP.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria continued warehouse inventory review with Hernan Machado from DCMC, performing targeted recounts to validate previously identified discrepancies. Investigated root causes through cross-checking inventory movement records, analyzing stock logs, and engaging warehouse staff for clarification. Documented inconsistencies and proposed adjustments to ensure full alignment between physical inventory and system records, reinforcing inventory control and traceability.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-at Palo Seco warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were AD01067 to AD01091, AD 003 to AD 004, AD 001 to AD 002, AC 067 to AC 071.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria participated in on-site inventory verification efforts at the Costa Sur warehouse alongside Hernan Machado from DCMC. Initiated detailed cycle count procedures by reviewing existing inventory logs, organizing warehouse zones, and conducting physical counts to validate stock quantities. Efforts focused on ensuring accuracy of recorded inventory levels and identifying any initial discrepancies between system data and actual stock.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with DCMC Inventory Supervisors to discuss any issues or challenge encountered the previous day and to establish the work plan moving forward.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Review Warehouse Temporary Storage Notes – 4/16/2025 meeting with GeneraPR Facilities Team, sent by Andres Concepcion from DCMC.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- 4339_9510 BESS Review after meeting report status in Drawings, RFI, sent by Carlos De Jesus from DCMC.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS, RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria-4339_9510 BESS Review Action: RFP Genera Request for Proposal - DCMC comments for attention to RGE documents in schedules, sent by Carlos De Jesus from DCMC. Action: RFP Genera Request for Proposal - DCMC comments for attention to RGE documents in schedules
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- 4339_9510 BESS Review Attachment Federal Contracting Clauses, sent by Andres Concepcion from DCMC.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I read and created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I conducted a meeting with Homeca the contractor.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I supervised the contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. These were my chores for today,
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I supervised the contractor Homeca, I walked the site regularly with them and our safety personnel, during the day and made sure they were all in compliance under safety, made sure they were doing what we discussed about what their task is for today or for this week. I conducted a meeting with the contractor and participated in meetings with the management of Genera-PR. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site created an incident report related to an affected employee from Homeca send emails and meeting with Jean Pierre Menay and Jaime Pesquera DCMC including Nelson Soler from CDM Smith. Completed report
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site created an incident report related to a affected employee from Homeca send emails and meeting with Jean Pier Menay and Jaime Pesquera including Nelson Soler from CDM Smith.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Meeting Siemens Energy Contract #00106588 and Deliverable Schedule review Peakers Costa Sur. Genera/ Siemens Costa Sur Peakers weekly status meeting. Participants from CDM - Rafael Pabon, from Genera German Nunez, from DCMC Rafael Calderon. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 164 | 123 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team)
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4.25 |  | 164 | 697 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Change Orders Review based on mutual agreement between Genera and Tesla. Aligning financial information with project cost adjustments in order to request next working capital advance. Change Order relates to Payment Milestone #2 and #3. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists # 329 to begin the cycle counts.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report for locations AD01 to AD04 in Palo Seco.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AD01 to AD04 in Palo Seco.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AD01 to AD04 in Palo Seco.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AD01 to AD04 in Palo Seco
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD01 to AD04 in Palo Seco
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD01 to AD04 in Palo Seco
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AD 01 067 000 to AD 01 091 000 in list #325 and recount 332. In addition, i work the recount list #334 for the 04.16.2025 job.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD 01 067 000 to AD 01 091 000 in list # 325
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AD 01 067 00 to AD 01 091 000
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC067 - AC071.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC067-AC071.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC067 - AC071 from recount list # 330.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Vega Baja Coordination of Incident Reports/ Costa Sur (Peakers) Project_Siemens_Follow up on Proposed File Structure for Approval & Review/Data Implementation Task for Procore SOP(s)
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Procore Tools SOPs to submit for review: Schedule, emails, photos and RFI.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review submittals uploading process on the Training Project; review requirements for contractors to submit equipment and devices specs.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Observations and Inspections Tool; review forms to be uploaded (Toolbox Meetings, JHA, among others) in order to start creating Inspections through Procore.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Lauren Wells (Lemoine) and Jean Menay (DCMC) to discuss the implementation of Inspection and Observation tools to cover Project Safety issues.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on Procore tools implementation (Schedule tool); review users permissions for submittals creation with draft status.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - I worked on the Pre Intervention tracker to update formulas preparing to include DCMC update on invoices. Then I called Victor Maldonado (DCMC) who helped me providing information from Asset Suite to update the payments and invoice from DCMC to Genera. This information was updated in the tracker and in the Power Point presentation for today's meeting. Sent by email to Shellsea Maysonet (contractor) and D'Alexander González (DCMC)
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Grant Management ¦ DR 4339- Hurricane María- Genera Pre-Meeting with participation from DCMC: José Ralat, Esther Rohena, Roberto Bosch, Rafael Calderón, Eisha Mercader and Marc Maceira from DCMC, and Shellsea Maysonet (MZC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 149 | 521.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - TESLA_Contract 106761 Reviewing invoices corresponding to Payment Milestone #2. During this time, I review the invoices for Palo Seco, Vega Baja and Aguirre. Also, provide grants team invoices numbers and total for all the plants.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Carry out a thorough review of the BESS and Peakers pages on the Genera PR website to confirm that both the text (copy) and images are up to date and aligned with the most recent information.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Activity related to going to the Safety Zone store at San Francisco Dental, 87 Avenida de Diego, San Juan in which they sell the safety equipment for the site visit program as part of the BESS project together with Jean Pierre Menay of DCMC. Equipment Purchase and Safety-Related Management
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting in Teams with GENERA, DCMC and CDM Smith staff Jorge Bracero, Iván Báez Santiago, Gabriel Pérez Sepúlveda, Jesús Cintrón Rivera, Rafael A Rodríguez Ema, Gilberto Sucre Franklyn Colmenares and Victoria Flores to outline the strategy and tactics for the Ground Breaking Event Prep Meeting of the BEES project in Vega Baja, in which the governor of Puerto Rico Jenniffer González is invited. During the meeting, Gilberto Sucre (DCMC) reported that after seizing the PLO equipment, the final laboratory results and confirmation that the environment is clear are expected to be received on Monday. They also indicated that the PUI can be submitted even though we are still in process; the intention is to proceed with the demolition as soon as possible. They mentioned that a letter is anticipated on Monday that will allow the immediate start of the down breaking (demolition). Logistics topics were discussed, as well as coordinating efforts with the community post-event. The event is proposed for next Thursday (April 24).
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 -Translate to English the community engagement work plan focused on DCMC's role in the Bess project in Vega Baja using the documents that Jorge Bracero, from Genera, has been sending as support The document focuses on my tactics to be more efficient and have a draft that we can work with as the project progresses with a focus on the specific needs of the client. The document is for internal use and does not alter Jorge's work plan but seeks to align us with the client at the level of communications with the identified audiences.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Create a table in excel with 14 fields to define tasks for the community outreach project. The table contains information about the person or team responsible, hearings, key message, communication channels, frequencies and indicators of success. This will facilitate task execution.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339: Reading and answering email sent by Lygia Irizarry-Nieves (DCMC), regarding the meeting yesterday 4-16-2025, to review who's the client to charge it. Read an email sent by Connie Wright (DCMC) about Jose Lopez( DCMC) about the expense he didn't submit. Called Jose Lopez and explain how he had to submit the expense and confirm he submitted it. Call Raissa Borges (DCMC) about the expenses and she share her Tempest screenshot and explain where she has to submitted the report. Send email back to Connie Wright and confirm the expenses is done. .
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the warehouse demolition specifications of 4339_9510 BESS_Cambalache project.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 134 | 201 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was evaluating a document 8._Appendix_D.3-_Demolition_Specifications of Procore with scheduling notes and sent evaluation to employee Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache was evaluating a document RFP Genera Request for Proposal of Procore with scheduling notes and sent to employee Andrés Concepción (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on schedule update and sent to employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur continued working on a status report of PROCORE documents file of RFI, Drawings and submittals and sent to employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with Genera PR, RGE, Sargent and Lunder about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue reviewing the floor plan drawings for the 4339_9510 BESS_Cambalache project.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review the floor plan drawings for the 4339_9510 BESS_Cambalache project.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue reviewing the warehouse demolition specifications of 4339_9510 BESS_Cambalache project.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4.25 |  | 122 | 518.5 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue reviewing data from the projects schedule and budget to support the development of the monthly report.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 122 | 91.5 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. In person meeting with Gilberto Sucre (DCMC) to review and discuss program dashboard report.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue reviewing data from the projects schedule and budget to support the development of the monthly report.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez, Gilberto Sucre CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares, Enrique Laya Genera: German Nunez
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 122 | 427 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Gathering and organizing information needed to support reporting processes focusing on project key milestone.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.23 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-after completing the meeting at the Costa Sur warehouse with Mr. Hernan Machado from DCMC, drove back home to Guaynabo. The purpose of the visit was to review the progress achieved so far and clarify any doubts regarding the process. Also, we assist Mr. Machado with the process.
2025-04-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.3 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel directly from home in Guaynabo to Costa Sur, to meet with Mr. Hernan Machado from DCMC. The objective of this visit is to provide guidance on the ABC cycle count process and to walk through the procedure to ensure a clear and comprehensive understanding.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks plans for meeting Monday with Luis Roman (DCMC) and Theresa Perez (DCMC).
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 reviewed weeks notes, reviewed final comments on Costa Sur RFP demolition SOW
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 reviewed submittals and RFI's for the Peakers projects
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Procore Files for Cambalache Project.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Review and evaluation of contractors bid for Civil & Structural Bid from AGR, GRE and Second Base.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Cambalache RGE, RGE never made it to the meeting but Sargent & Lundy, CDM Smith and DCMC Partners discussed remaining activities and pending items to complete post bid evaluation and final scope selection
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weeks' evaluation of BESS Program Status per site pre-construction and/or construction stage assigned staff.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Procore (Lauren Kennedy and Tyler Scanlon) to discuss project plan, next steps and Change Order forms for Correspondence module.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations tasks list.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information for implementation.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Incidents module for Jean Pierre Menay (DCMC).
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of SOP procedures for Schedule, RFI and Inspections Tools to guide project teams in creating, managing, and updating the project schedule and determining the roles and responsibilities, and the necessary checkpoints for assessing progress.
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Certification: Project Management as Owner Representative
2025-04-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on Procore implementation for Inspections and other safety tools; formulation of JHA and Inspection forms to be used by the PMO.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 2115.5 | 2115.5 | 2115.5 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Airfare (Basic Economy) for Foster Veazey's trip from Mobile, AL to San Juan, PR.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 407.5 | 407.5 | 407.5 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel expenses to meet with Genera team onsite to support Grant Management process improvement. Claiming SW airfare from Oklahoma City OK to San Juan PR for $407.50.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 286.39 | 286.39 | 286.39 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Hotel Lodging for Foster Veazey for 1 night in San Juan, PR ($245 lodging, $24.39 Taxes, $17 fees).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710, Peakers Project management update meetings and coordination with Sargent & Lundy Representatives, Chris Mateo, Lemuel Nieves and Miguel Del Valle. Reviewed for final release to GENERA all components of the contract and scope of work.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 final comments/ revision of the Costa Sur Demolition RFP with team German Nunez,( PEAKERS sr. manager ) Rafael Pabon, CDM Smith Carlos Palomares CDM Smith
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess Tesla Site Inspections Coordination with Franklyn Colmenares - CSA Group for Cambalache, Vega Baja, Costa Sur y Yabucao.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Internal Weekly Meeting evaluating remaining action items pending between Sargent & Lundy and RGE in order for contractor to submit their final proposal. Participants Sargent & Lundy, CDM Smith, CSA Group and DCMC Partners.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Resume's evaluation project vacancies to be filled.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Staffing Planning with Frances Vallejo - DCMC Partners
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Monthly Reporting Dash-Board Review and Data Validation., for the PMO.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Governor's Visit - Ground- Breaking Ceremony Coordination. Provide preparation required from DCMC's Site Team in preparation of the activity.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - RFP 4898 Responses submitted by Contractors RGE and ARG. Evaluation of Technical Response, Commercial and Schedule for Phase II Installation.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM Weekly Meeting Update with Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group and Gilberto Sucre DCMC Partners. Topics: Inspector Contract, RFC's Documentation, Bids vs. Budgets, Procore, Cambalache & Vega Baja - Decommissioning Quarterly Report.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Navigated in Procore to drawings, specification, RFP's and contractor's bids for Vega Baja, Cambalache, Costa Sur, Aguirre & Yabucoa. Lots of documentation is missing.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluated relocation of current staffing to projects closer to their home town.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - I developed and distributed Pre-training materials and resource content in support of project planning activities for the 4339 Hurricane Maria FEMA grant initiatives, The team training was on effective meetings. Materials included a structured agenda, team-specific training resources to ensure the content focused on supporting all upcoming grant-funded projects. I distributed all prework and relevant information to meeting participants in advance to support productive and informed discussion. Participants of the training included. Joaquin A Quinoy Ortiz (Genera), Ivan Baez Santiago (Genera), Maria Sanchez Bras (Genera), Carlos A Negron Alfonso (Genera), Jennifer Witeczek (Genera), Kevin D. Futch (Genera), Vladimir Scutt (Genera), Ricardo Pallens Cruz (Genera), Hector Vazquez Figueroa (Genera), Jose Del Rio Velez (Genera), Winnie Irizarry (Genera), Jeanniffer Gonzalez Diaz (Genera). This communication was sent digitally and presented in person to the team.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - I developed and distributed pre-meeting materials and resource content in support of project planning activities for the 4339 Hurricane Maria FEMA grant initiative, planning one-on-one meetings with each department leader. Materials included structured agendas, company knowledge assessment to determine current understanding of content, participant guidance, and background documentation to ensure alignment with project goals. I distributed all prework and relevant information to meeting participants in advance to support productive and informed discussion. Participants of the meetings included. Joaquin A Quinoy Ortiz (Genera), Ivan Baez Santiago (Genera), Maria Sanchez Bras (Genera), Carlos A Negron Alfonso (Genera), Jennifer Witeczek (Genera), Kevin D. Futch (Genera), Vladimir Scutt (Genera), Ricardo Pallens Cruz (Genera), Hector Vazquez Figueroa (Genera), Jose Del Rio Velez (Genera), Winnie Irizarry (Genera), Jenniffer Gonzalez Diaz (Genera). This communication was sent digitally.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting presentation development
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore financial information plan provided by Liz Fronduto (Procore).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) for Procore weekly check-in items.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Quality Inspection forms conversation with Andres Concepcion (DCMC).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore Financial items timeline to present to leadership.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore Reports PPT for Raissa Borges (DCMC) for monthly reporting.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore Team tasks items to prepare for team meeting. This helps us align efforts for the week on Procore tasks.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)worked on correspondence for Procore meetings with Liz Fronduto (Procore) to keep working on Financial Management Implementation.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for Luis Roman (DCMC) to allow ability to create inspections as he is working with Jean Pierre Menay (DCMC) on safety inspections.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)worked on Procore configurations for permissions for Incidents module per Jean Pierre Menay (DCMC), requests.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 186.6 | 186.6 | 186.6 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I stayed at Airbnb at 7 Calle Cervantes, San Juan, PR 00907-1315, US while visiting the Genera team. The nightly cost was $186.60 per night.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Confirm with Homeca job in Vega Baja. Coordinate Costa Sur, Aguirre, Cambalache and Vega Baja Genera site visit. Review the Cambalache ERA Plan.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Call with Jaime Pesquera (DCMC) about Vega Project contractor. Meeting with Gilberto Sucre (DCMC) about Vega Baja Project.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Take a FEMA training ICS 700 An Introduction to the National Incident Management System.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Conference call with Gustavo Perez (Genera) about Yabucoa site planning and visit. Call with Franklin Colmenares (CDM Smith) about Tesla Representatives Visit to Costa Sur, Yabucoa, Vega Baja and Cambalache Genera sites. Review the Cambalache and Vega Baja site project. Train in the Genera Health and Safety training with Javier Oyola, Felix Oyola, Saul Santiago, and Carlos Villamil by Villamil Group.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Coordinated with Carolyn Baez (DCMC) Genera T shirts for the PMO team and also coordinated office supply purchase with vendors. Sent emails regarding the needs for the PMO team to Carolyn and Harry del Valle (DCMC).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Meeting with Project Management leads for BESS and Peakers projects. Participants: Gabriel Perez and German Ojeda (Genera).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Call with Carolynn Baez to coordinate the Lean Management Luncheon meeting with Genera leadership and send email to Frances Adames (Genera) to coordinate 1x1 meetings with Genera leadership staff.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Cambalache update call with Gilberto Sucre (DCMC) and Andres Concepcion (DCMC) to discuss RFP status.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Meeting with Jesus Cintron (Genera) and Sheila Torres (DCMC) to discuss RFP status and next steps on BESS project.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review and analyze the Vega Baja community engagement plan.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS -Finalized preparing the amendment package for the Tetra Tech contract and sent to Jesus Cintron (Genera) for sign-off.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS - RFP 231175 - Worked on the development of the Q&A responses and Addendum No. 3 for the active procurement process. Reviewed and finalized clarifications to bidder inquiries to ensure accuracy, consistency, and alignment with the solicitation documents. Additionally, created Attachment G to incorporate new information related to project management. Ensured all documents were properly formatted and coordinated for internal review prior to formal issuance.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Maria Sanchez Bras, and Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Marc Maceira, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Carlos González and Ginnell Torres
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS - Updated the amendment package for the Tetra Tech contract pursuant to conversation with Jesús Cintrón and Ricardo Palléns (Genera). Sent documents for review and sign-off.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jesús Cintrón (Genera) and Frances Vallejo (DCMC) to discuss the status of multiple ongoing PMO projects, including key initiatives such as the BESS and Peakers projects. Reviewed project progress, outstanding action items, and upcoming deliverables. Identified potential challenges, discussed resource coordination, and aligned on next steps to maintain project momentum and ensure continued compliance with internal timelines and objectives.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Financial Tracker Changes and Strategy Discussion: -Began validating recent fixes in the Genera Connect Financial Tracker by reviewing changes to the report import process. - Discussed the rollout strategy for the Genera Connect timesheets tracker with Eisha Mercader from DCMC, focusing on user adoption, system functionality, and transitioning from the current process.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.75 |  | 184 | 506 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Validation and Packaging of Fuel Consumption Reports: Validated and packaged the January 2025, February 2025, and March 2025 fuel consumption reports and provided them to Jose del Río from Genera PR's fuels department.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Testing of Financial Tracker: Continued testing the Genera Connect Financial Tracker and encountered issues uploading reports. WCA reports are being processed properly. Tested uploading the Invoice Register and Reimbursement sheets from the Financial Tracker report but experienced intermittent issues.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site Attended PortoSan arrival to install bathrooms trays, and second arrival of PortoSan Truck Driver Ruben Nieves for bathroom maintenance.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Dismantling, Decommissioning and demolition works planning for phase II. Homeca Recycling should submit an LED abatement removal certification to ensure they can safely handle and remove lead hazards, protecting workers and staff from lead exposure.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria—Weekly look-ahead schedule review and discussion with the DCMC team, Gilberto Soto, Jaime Pesquera, and Gilberto Sucre: Coordination and logistics for the Governor's site visit. Working with the procurement process for a subcontractor to clean the site.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Resumed working on Procore, reviewing drawings, Scheduling & Contract Documents for the Aguirre, Costa Sur & Jobos projects. Verify and corroborate possibles discrepancies & measures. Continued preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing drawings, Scheduling & Contract Documents for the Aguirre, Costa Sur & Jobos projects. Looking for possibles discrepancies & measures. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of RFP 4826 Exhibit L (Pipe Relocation) and exhibit M (Electrical Engineering & Design)
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of RFP 4826 Annex K Civil and Structural.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Weekly Internal Meeting with Andres Concepcion (DCMC) to discuss project issues, goals, timelines, and progress
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed Procore Platform data and tasks to ensure that project pending actions (RFI, Submittals) are bien addressed.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Cambalache site coordination meeting with DCMC Gilberto Sucre to align weekly action items and project status.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Continued Procore platform project management training to ensure efficient coordination trough project tools.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR -Developed and drafted Cambalache site project responsibility matrix to set coordination and identify accountability of project activities.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed and drafted initial construction kick-off meeting agenda and topics to be implemented prior construction start with contractor RG Engineering.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project meeting with Program and Design Managers (Gabriel Perez, Franklyn Colmenares (CDM Smith), Mike Kuczynski, Robert Molner (Sargent & Lundy), Gilberto Sucre (DCMC) to coordinate internal Cambalache ongoing project actions and project update.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR -Reviewed team internal construction management processes (Safety , Quality Control) to identify improvement areas and pending actions to set up a complete process.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Continued Procore platform project management training to ensure efficient coordination trough project tools.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR -Phone call with DCMC Jorge Mercado to discuss expected safety protocol for construction start preparation to help minimize risks and create a safer work environment.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, D' Alexzander Gonzalez, Paul Brown, Jose Ralat, Rafael Calderon, Esther Rohena, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Keylamerari Siera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing critical components lead tracker table installation with LGA project to review any duplicate projects. Meet with Pedro Cabrera of DCMC to inform the finding of projects that may not be duplicate with the LGA list, he will review FEMA Grant Portal for the project SOW.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Critical Components - Participant Anthony Vega of Genera, Pedro Cabrera and Eduardo Rivera DCMC - Kickoff Meeting to create a new strategy to provide follow up on critical components tracking delivery by each plant and Genera will provide support by warehouse of receiving of equipment and when will be deliver to plant for installation.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue in review of critical components lead tracker table installation with LGA projects. Meet with Anthony Vega of Genera he will revise the delivery dates with DCMC to create an installation plan of each generation plant; the meeting will be at 2PM.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical components - Pedro Cabrera and Eduardo Rivera DCMC working to identify (37) equipment on NME with the cost provided on Master Power BI Mapping Table with our critical component's tracker.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Send email to Anthony Vega of Genera in regard of Critical Components pending to be paid by Genera, also notifying vendor has received 92 acid pumps for PS and forward email that was sent to Mayaguez, Cambalache and Palo Seco SP in regard of request for CC equipment receiving and installation dates. Working with (37) NME components that need to confirm cost, some of the components are not at the Master Power BI Mapping Table. Creating new table for Pending FY2025 NME projects due to lack of fundings.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- meeting held via TEAMS with Ms. Maria Sanchez of Genera, and staff of DCMC to discuss the weekly progress of the projects.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with Hernan Machado, Milton Flores (DCMC) and other personnel from warehouses to discuss the issues encountered last week and to establish the work pace for the current week. Administrative matters were also addressed, including the proper format for submitting recorded work hours.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participated in on-site inventory verification efforts at the Aguirre warehouse. Initiated detailed cycle count procedures by reviewing existing inventory logs, organizing warehouse zones, and conducting physical counts to validate stock quantities. Efforts focused on ensuring accuracy of recorded inventory levels and identifying any initial discrepancies between system data and actual stock.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were CR 0181 to CR 0185, AD005 to AD 011, AD 041 to AD 044 and AE 001 to AE 038.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-continued warehouse inventory review, performing targeted recounts to validate previously identified discrepancies. Investigated root causes through cross-checking inventory movement records, analyzing stock logs, and engaging warehouse staff for clarification. Documented inconsistencies and proposed adjustments to ensure full alignment between physical inventory and system records, reinforcing inventory control and traceability. Today I work locations CR0181 to CR 0185.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez Bras and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Modifying after discussion with D'Alexzander Gonzalez DCMC a report for NME identify under FY2025 NME Projects Due to Lack of Funding list. Provide the current FEMA project and actual cost included in those projects.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Develop of a report for NME identify under FY2025 NME Projects Due to Lack of Funding list. Provide the current FEMA project and actual cost included in those projects.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Review of Critical Components duplicates in LGA projects. Based on review of FEMA Actual Version and Data shared by GENERA-PR.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components continue review of Critical Components duplicates in LGA projects. Based on review of FEMA Actual Version and Data shared by GENERA-PR.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Status meeting with participation from DCMC: Pedro Cabrera, and Eduardo Rivera; from Genera-PR Anthony Vega, to discuss priorities and deliverables, status updates, identify next steps for critical components.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Preliminary Drawing BATTERY ENERGY SUPPORT SYSTEM FOUNDATION KEY PLAN BESS CONCRETE SUPPORTS, BATTERY ENERGY STORAGE SYSTEM RIGID INCLUSION PLAN CABOO-SF-BYS-0002, FOUNDATION PLAN CAB00-SF-BYS-0003.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Preliminary Drawing BATTERY ENERGY SUPPORT SYSTEM FOUNDATION PLAN CAB00-SF-BYS-0003, BATTERY ENERGY STORAGE SYSTEM RIGID INCLUSION SECTION CAB00-SF-BYS-0007
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | General Deliverable PR 11 - Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS received COMMENTS from DCMC on April 17, 2025. 8. Appendix D.3 - Demolition Specifications submitted by Andrés Concepción, DCMC. Review of the preliminary document was initiated, which includes the general planning of the demolition work, the methods to be used to demolish the structure, the necessary equipment and measures to be taken to carry out the work safely and to make comments on floor demolition drawings and missing electric water and diesel lines.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Tesla Delivery date and schedule data prior to the Wednesday meeting, sent by Carlos De Jesus from DCMC.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria- I participated in a morning meeting with our supervisors and the management of Genera-PR. Attended the meeting: Carirma Sanchez, from Homeca, Eduardo Ramos-Homeca, Nelson Soler, CDM Smith, Enrique Laya CDM Smith, Franklyn Colmenares CSA Group, Gabriel Perez Sepulveda CSA Group, Manuelli Concepcion CDM Smith, Jose Lopez Linares, DCMC, Gilberto Sucre DCMC, Gilberto Soto, Jean Menay, DCMC). I read submittals, that needed my attention for today #66. I answered and read multiple emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria- Homeca did not make it to the site today at all, we do not have the lead and or asbestos results from the laboratory in yet. I created RFI's and worked with RFI's that needed my attention, I worked on all the submittals that needed my attention for today#63,#65,#66. I participated in a morning meeting with our supervisors and the management of Genera-PR (attended the meeting: Carirma Sanchez, from Homeca, Eduardo Ramos-Homeca, Nelson Soler, CDM Smith, Enrique Laya CDM Smith, Franklyn Colmenares CSA Group, Gabriel Perez Sepulveda CSA Group, Manuelli Concepcion CDM Smith, Jose Lopez Linares, DCMC, Gilberto Sucre DCMC, Gilberto Soto, Jean Menay, DCMC). I also went over all the documentation that Homeca owed us and answered emails on Procore.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Homeca did not make it to the site today at all, we do not have the lead and or asbestos results from the laboratory in yet. I created RFI's and worked with RFI's that needed my attention, I also created submittals, worked on all the submittals that needed my attention for today. I participated in a morning meeting with our supervisors and the management of Genera-PR (attended the meeting: Carirma Sanchez, from Homeca, Eduardo Ramos-Homeca, Nelson Soler, CDM Smith, Enrique Laya CDM Smith, Franklyn Colmenares CSA Group, Gabriel Perez Sepulveda CSA Group, Manuelli Concepcion CDM Smith, Jose Lopez Linares, DCMC, Gilberto Sucre DCMC, Gilberto Soto, Jean Menay, DCMC). I answered and read emails I needed to in order to keep up with all the communications and worked with Procore constantly throughout the day.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site attended RodRogers to verify Homecas Trailer Holding Tank that was reported leaking. Uploaded related documentation to ProCore app.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team), From Genera: Maria Sanchez and Alejandro Maymi).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Continue working on Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 164 | 656 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Pre-Intervention - TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on invoice review for Payment Milestone #2 for all Plants. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations From AD 41 to AD44 San Juan
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations. AD41 TO AD44 San Juan.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AD41 to AD44 San Juan
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at Costa Sur warehouse, working on the recount of the discrepancies for locations AE 00 001 000 to AE 00 038 000.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE 00 001 000 to AE 00 038 000.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE 00 001 000 to AE 00 038 000.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE 00 001 000 to AE 00 038 000
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD005 to AD011 to begin the cycle counts.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AD005 to AD011.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies in Recount Lists #345, 346, and 347 from locations AD005 to AD011. The recount was validated by Genera personnel, Wandimar Jimenez.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD005 to AD011 Cycle Count List # 342.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordination of Weekly Tasks with Lauren Wells (Lemoine) & Luis Roman (DCMC)
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - SOP for Procore File Structure - Task Management Tool
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review document uploading process for the new file structures on the Documents Tool of the Procore platform.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Implementation of new core tools for project execution (Incidents and Forms). Performing SOP for these new core tools as user guidance on the platform.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue Procore Certification: Project Management as an Owner Representative.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review SOP final draft for Schedule and RFI; perform QA/QC of other SOPs drafts (Incidents, Observations)
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) as a weekly catch-up to discuss Procore Execution: new tools that will be enabled and potential workload with these new tools.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue Procore Certification (Project Management as an Owner Representative).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review new created forms to be uploaded as Fillable PDF forms to Inspections and Forms Core Tools.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Franklyn Colmenares, Gabriel Pérez and Carlos Palomares from CDM, Rafael Calderón and Glorimel Torrado from DCMC. This is a recurrent meeting to discuss payment milestone #2, progress, possible change orders, important due dates with Project Management team. In this meeting also participates Mike Kuczinsky from Sargent & Lundy.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Working session with Rafael Calderón (DCMC) reviewing Homeca contract and requirements prior processing invoice #1. Also, go over Homeca invoice #1 and review missing information that needs to be included in documents. Missing DI's associated with Invoice.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 - Siemens Energy Contract #00106588 and Deliverable Schedule, verifying on change orders information required. Siemens section 6 axD-9, A.2.7.2 Product receiving, storage and landing. Also review point A.2.7.1 and attachment B key delivery dates, research on DCS 9.29. Share information with Rafael Calderón (DCMC).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - TESLA_Contract 106761 - Review conditions precedent for payment on Tesla Contract. I was verifying pending documents from Tesla to process Invoice for Milestone #2. Reading the contract and identifying important information as parent guarantee and insurance requirements. Send the information to Rafael Calderón (DCMC).
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 ¦ Genera and DCMC Weekly Meeting with participation from DCMC: D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and Marc Maceira. Also, Shellsea Maysonet (MZC); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare Tesla Milestone #2 Invoices for Genera signature (Jesús Cintrón). I prepare invoices from Yabucoa, Vega Baja and Palo Seco. Review final invoice and submit on Adobe Sign. When signed, I prepare Tesla invoices for final step. I create final files and send to Franklyn Colmenares (CDM) for CPA. I send the request for Palo Seco, Vega Baja, Yabucoa, Costa Sur, Aguirre and Cambalache.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria At Genera office, Hato Rey participated in 1:1 with Lymaris Otero, external consultant, and Genera Jorge Bracero, Community Relations Manager to talk about the communication plan for the week.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA - Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Genera Teams: Jorge Bracero; Rafael A Rodríguez Ema e Iván Báez with the team of the communications agency Kroma Amarilys Torres, Victoria Flores, Bernardo Medina and Miriam Seda to discuss this week's communications tactics and efforts in relation to the Bess project, particularly groundbreaking in Vega Baja, which is scheduled for Thursday, March 24, but Governor Jenniffer González has not yet confirmed her participation. The meeting outlined the communication pieces that must be delivered related to community communications efforts.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create the work plan on the fact sheet that would be used at each site as part of the BESS project, which would be distributed when the community meetings are over. The "Fact sheets" are about the progress of the project in order to keep the community, local authorities, stakeholders and public of interest updated on the progress of the project. The work plan was sent so that the Genera communications team, Jorge Bracero, Rafael Rodríguez Ema and Iván Báez -can verify it in order to execute it
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 139 | 417 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria first day at the GENERA Puerto Rico offices starting with the inductions of the day with Genera Jorge Bracero, Community Relations Manager. Present the community relations plan to you, complete the registration process in Genera' office in Hato Rey. Meeting with Jorge Bracero Nieves, Community Relations Manager, Rafael Rodriguez Ema and Ivan Baez Santiago, from the Genera's communication team to talk about de recap for the week.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR-Deliverable 11 - Project Management ¦ DR 4339: Reading email received from Anneilia Holton-Williams regarding follow up to Paola Arroyo, Milton Flores and Frances Vallejo (DCMC) about the entries in Tempest that have not sent the email to Connie Wright. Called Paola Arroyo and Milton Flores and explain the process and the email they need to send at the end of each paid period. Receive call from Frances Vallejo and she informed that she would finish the entries today. Call Marimar Bracero (DiSignXpress Inc.), regarding the banners we need for the Vega Baja site on Thursday.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review the warehouse demolition specifications of 4339_9510 BESS_Cambalache project to verify labor, materials, and equipment required for the demolition, and/or disposal of all structures, building materials, and equipment to be removed.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule BESS Tesla data and sent a table for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule BESS data and planned a table for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procore Quality and Safety inspection best practices training course for 4339_9510 BESS_Cambalache project.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Updating project financial and budget data on project report.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Enhance and develop project risks and mitigation strategies for reporting purposes.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 111 | 111 | 111 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from home of record to Puerto Rico
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 53.92 | 53.92 | 53.92 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from airport to the hotel.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 38.44 | 38.44 | 38.44 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from airport to DCMC office for Foster Veazey. Tip adjusted to $5.00 ($27.55 trip fare, $5.00 tip, $2.14 booking fee, $3.75 airport fee)
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 23.01 | 23.01 | 23.01 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from DCMC office to Hotel for Foster Veazey. Reimbursement is for a tip of $3.00 ($17.72 subtotal + $2.29 booking fee + $3.00 tip)
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 8.05 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Mileage to drive from office to airport for an onsite meeting with Genera team.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel from home in Guaynabo to Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane -Maria -travel back home in Guaynabo from Aguirre, the purpose of the visit was to support warehouse operations during Mr. Juan Vallejo medical leave
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 384.8 | 384.8 | 384.8 | Yes | 25-145003 | Portosan - Containment Tray Rental - Vega Baja
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710, completed consolidating various project specific documentation for tracking and scheduling purposes
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Working on internal spread sheet to start to capture all the various documents and prioritize based on order of importance, for the Costa Sur demolition portion of the project
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Risk Management Meeting for LUMA Operation led by Luis Munet - LUMA discussed Risk Register for BESS and Peakers. Other participants besides LUMA, CDM Smith, CSA Group, DCMC Partners, Sargent & Lundy.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Daily Progress Update discussion with Jose Lopez, Andres Concepcion and Harry del Valle DCMC Site Managers and Construction Manager for Vega Baja, Cambalache and Yabucoa respectively. Plus e-mail correspondence reading.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Sargent & Lundy / CDM Smith / DCMC Partners Weekly Coordination and Design Status support of Construction Execution.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 225 | 506.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Performance Evaluation with Foster Veazey DCMC Partners. Topics covered: EHS Implementation, Manual and Incident Reporting Org Chart Resolution, P-6, Procore, Monthly reporting Dash-Board, PMO Deliveries, Staff Evaluations.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Update with Gabriel Perez - CDM Smith on Ground-Breaking Ceremony, LUMA Property Line Resolution, Diesel Transfer, Frame 5 dismantle, site visit by Jesus Cintron and Winnie Irizarry- GENERA.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Procore Financial Implementation. - Continued discussion for Change Management processes Led by Elizabeth Fronduto - ProCore, Lauren Kennedy & Tyler Scanlan - ProCore and from DCMC - Esther Rohena, Foster Veazey, Rafael Calderon, Lauren Wells and Gilberto Sucre.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache The RFC Meeting for the RGE Cambalache project, led by Rob Mulner in Mike's absence, covered several key points related to project status and coordination. Key discussions included confirmations on project pricing, with José Robles indicating that pricing without seismic conditions would be provided that day, followed by a complete package within 1-2 days using RGE's preferred pricing format. The team emphasized the urgency for information regarding the Vega Baja project, along with technical drawings to address engineering options. The meeting addressed the integration of the riser diagram and required lists of equipment and permits, highlighted site design considerations focusing on earth movement issues, and stressed the need for effective stakeholder communication, especially with PREPA. Action items were assigned, including uploading contract comments to Power Advocate, beginning submittals in Procore, and coordinating necessary permits for the contract. A follow-up meeting was scheduled for Thursday to review the pricing information. Companies participating RG Engineering, Sargent & Lundy, Genera, CDM Smith, CSA Group and DCMC Partners.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Joaquin A Quinoy Ortiz (Genera) - Meeting follow up and reschedule one-on-One with Danny Hernandez (Genera) due to team conflict.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria José del Río (Genera) alignment discussion for deliverables and proposal. We discussed Grant approval process challenges and Lean processes to improve and reduce the Approval process around scheduling & communication processes for current projects. All participants were in person at the Genera office.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria During the meeting with Maria Sanchez (Genera), CFO of procurement and warehouse, we discussed critical technology challenges in financial systems, specifically the transition to Oracle Fusion and the need for automated invoice processing to streamline grant-related documentation. The conversation highlighted the manual nature of current invoice entry processes and the desire to implement vendor-direct invoice uploads, which would significantly improve tracking and reporting capabilities crucial for FEMA Grant project transparency and compliance. By exploring more efficient technological solutions, the organization aims to enhance financial management, reduce manual data entry, and create more robust documentation systems that can better support federal grant reporting requirements. All participants were in person at the Genera office.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Hector Vazquez - IT (Genera) Team Leadership, Strategy and Alignment discussion for software applications acceptable that will meet Genera IT standards for Grant projects, to include challenges and Lean processes to improve processes around scheduling & communication processes for current projects. All participants were in person at the Genera office.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review notes from one-on-one meetings with Maria Sanchez Bras, Jose Del Rio, Hector Vazquez and Joaquin Quinoy (Genera) to develop next step action plans and implementation for upcoming Grant projects which includes approval process, challenges around scheduling & communication processes for current projects. All participants were in person at the Genera office.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Joaquin Quinoy (Genera) - Team Leadership, Strategy and Alignment discussion for deliverables and proposal for Grant approval process, challenges and Lean processes to improve process around scheduling & communication processes for current projects. All participants were in person at the Genera office.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Review and coordination of current Programmatic Action Items with Gilberto Sucre DCMC.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting to review the Procore financial tools module for implementation on the Program. Attendees were the Procore Staff (Elizabeth Fronduto, Lauren Kennedy, and Tyler Scanlan), Foster Veazey (LEMOINE), Lauren Wells (LEMOINE), Esther Rohena (DCMC), Gilberto Sucre (DCMC), and Rafael Calderon (DCMC).
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Weekly PMO Call with DCMC Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Overview of Procore Needs and Reporting structure for the program with Gilberto Sucre (DCMC).
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of SOP for documents tool for Theresa Perez (DCMC) to complete once structure is setup.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Safety plan review. Found JSA and communicated to Luis Roman (DCMC) that he should work on this with Jean Menay (DCMC) and then incorporate into Procore inspections.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on exporting list of all users in Procore and cleaning up list to send email out to users for documents update.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence for publishing drawings, folder structure comments.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information. Created new project for 9510 information and gather info for 10710.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore user session reporting to show volume of users using the system.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information based on information from earlier call with Procore.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of documents tool restructure for final draft for Theresa Perez (DCMC).
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on correspondence for Procore documents to send to all users to inform them of documents folders structure update.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)worked on updating monthly Procore report for PMO team.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) to discuss Procore forms vs Inspections for safety forms.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Procore (Lauren Kennedy), Foster Veazey (Lemoine), Rafael Calderon (DCMC) to review the Procore financial tools module for implementation on the Program.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for permissions.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 186.6 | 186.6 | 186.6 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I stayed at Airbnb at 7 Calle Cervantes, San Juan, PR 00907-1315, US while visiting the Genera team. The nightly cost was $186.60 per night.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Jobs and Site inspection. Review the projects documents. Final review the site after jobs. Make the report to Genera Health and Safety Departments and Security Departments.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria-Site inspection, meeting with Carima Sanchez by Homeca about health and safety. Meeting with Jose Lopez, Jaime Pesquera from DCMC on site to discuss about the same.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 |  | 184 | 690 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria Site inspection before start jobs. Health and Safety Meeting, with Homeca Recycling staff to review the site jobs.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended First community engagement meeting at Arecibo with the communications team and project management team for the BESS project. The meeting consisted in offering a presentation to the Arecibo community to explain and provide update on the Cambalache BESS project. Participants" Jorge Bracero (Genera), Jesus Cintron(Genera), Paola Arroyo (DCMC) and Rafael Rodriguez (Genera) and Gabriel Perez (CDM).
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Paola Arroyo (DCMC), Gilberto Sucre and Abraham Velazquez (DCMC) to discuss BESS project and Peakers project, provide a high level briefing on construction and discuss important points the community could ask in the meeting at Arecibo.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS - RFP 4826 52 MW Battery Energy Storage System Installation at Cambalache - Reviewed and completed four appendices received from Ernesto Martínez Baco (Genera) in connection with ongoing procurement and compliance documentation. Carefully analyzed the requirements for each appendix to ensure accuracy, consistency, and alignment with project and regulatory standards. Prepared the finalized documents for internal review and further processing as part of the supporting package.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Began developing Pricing Schedule and updating ICE accordingly as requested by Jesús Cintrón (Genera). Updated positions 1 through 6 with 3 comparables (GSA or past proposals) for each.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Preparation of Genera Connect Timetracker Presentation: Prepared a comprehensive presentation on the current state of the Genera Connect Timetracker project to present to the Genera PR IT team. The presentation included detailed project updates, key functionalities, and strategic approaches for employee onboarding.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting on Genera Timesheets Module Development: Participated in a collaborative meeting with Genera’s IT department (Jean Gonzalez, Hiram Medero), Integrum (Jorge Aponte, Carlos Gonzalez), and DCMC (Eisha Mercader) to discuss the development and implementation of the Genera timesheets module. The discussion focused on critical aspects such as system functionality, data integration, user requirements, and next steps. The goal was to ensure a smooth rollout and adoption of the module across the organization, addressing any potential challenges proactively.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Strategy Discussion on Security Improvements: - Engaged in a strategic discussion with Jean Gonzalez (Genera) on enhancing the security of the Genera Connect applications to ensure compliance with existing Genera PR policies. This involved reviewing current security measures and identifying necessary improvements from the application side. - Based on the discussion with Jean Gonzalez, began reviewing the current architecture of the Genera Connect application to identify any gaps in order to be able to implement the requested modifications.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and continued supervising contractors for their safety to protect workers from hazards, prevent accidents, and ensure compliance with regulations while conducting Demolition and clean the areas by Homeca.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Job Site Visit walk-through with Jesus Cintron (Genera PR) and Winnie Irrizarry (CEO, Genera PR). Discussed project status and project schedule issues.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Continued Oversight and supervision of dismantling, decommissioning and demolition works by HOMECA to ensure hazardous materials are properly disposed of or recycled.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Carolyn Baez-Nieves (DCMC) called regarding issues with the hotspot located at the Vega Alta site. Mr. Manuel Félix from T-Mobile and Carolyn Baez-Nieves participated in a three-way call. I provided the SIM card number for verification, and the hotspot was turned off and on again to ensure it was functioning properly.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Oversight and supervision of dismantling, decommissioning and demolition works by HOMECA to ensure observance of environmental protection, regulatory compliance, and worker safety.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Yabucoa Gas Turbine Plant. Attendees, Franklin Colmenares (Genera), Juancarlos Cruz (Röhlig Logistics), Wayne Jepson (Röhlig Logistics), Danny Rosario (Transporte Rosario) & Harry Del Valle (DCMC). Topics discussed - Verify the areas as part of the logistics for the delivery of Tesla batteries. The company Röhlig Logistics was hired by Tesla is in Puerto Rico, they are responsible of the delivery coordination with the transportation company.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Travel from Central Costa Sur (18.000463, -66.753480) to Yabucoa Gas Turbine Plant (18.106216, -65.823685) for a meeting to discuss logistics for the delivery of Tesla batteries. .
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Central Costa Sur. Attendees, Franklin Colmenares (Genera), Juancarlos Cruz (Röhlig Logistics), Wayne Jepson (Röhlig Logistics), Danny Rosario (Transporte Rosario) & Harry Del Valle (DCMC). Topics discussed - Verify the areas as part of the logistics for the delivery of Tesla batteries. The company Röhlig Logistics was hired by Tesla is in Puerto Rico, they are responsible of the delivery coordination with the transportation company.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination and installation of a temporary office for DCMC staff at the Cambalache to provide a comfortable and functional environment to facilitate coordination, decision-making, and management.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PUERTO RICO REVIEW THE THERMAL GENERATION FACILITIES OPERATION AND MAINTENANCE AGREEMENT.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Weekly Internal Meeting with Gilberto Sucre (DCMC) Andres Concepcion (DCMC) to review project development, workload, equipment requirements, and subcontractor performance.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued coordination and installation of a temporary office for DCMC staff at the Cambalache site to provide a comfortable and functional environment to facilitate coordination, decision-making, and management.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - BESS Drawings meeting with Sargent Lundy (Robert Molner, Vincent Skochdopole) CDM Smith (Gabriel Perez) and DCMC (Jose Lopez) for weekly follow up on project drawings progress.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project meeting with Program and Design Managers (Gabriel Perez, Franklyn Colmenares (CDM Smith), Mike Kuczynski, Robert Molner (Sargent & Lundy), Gilberto Sucre (DCMC), contractor (RG Engineering, Jose Robles) to discuss ongoing action items to complete Cambalache construction contract.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed and replied to emails to Gilberto Sucre, Luis Damudt, Luis Duque, Carlos De Jesus - DCMC Partners) regarding Cambalache project coordination and action items follow up during the week.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Drafted and developed request for information (RFI) for TESLA team regarding questions/concerns during the battery install that will be discussed in a future meeting.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Cambalache project drawing set review for quality assurance and comments for Sargent & Lundy corrections.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Weekly internal meeting with Cambalache DCMC team (Luis Damudt, Lus Duque, Carlos De Jesus, Jorge Mercado and Gilberto Sucre) to discuss updates and provide direction and assignments for site coordination pending actions.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Drafted a Cambalache project submittal responsibility matrix for submittal and project coordination.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing table of NME Status for Federal Side Reconciliation of GENERA PR Pending items for FY2025 in regard of NME status projects due to lack of federal funding. Reviewing resolution MI20210004-Resolution-and-Order- NME and MI20210002 Resolution and Order 23 SOW- NME. Generate equipment inventory list in regard of equipment used for Genera PR job site.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working request by Anthony Vega of Genera to provide what has been paid of all critical components and NME projects, this was done using Asset Suite for does project that have a PO number assigned for a total of (26) project that was verify with payment and pending balance to vendor. We created a new table to populate the critical components and NME projects that has been paid and have pending balance to a table and shared to Anthony Vega of Genera as requested.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing new PMO Power BI Dashboard presentation send by Raissa Borges of DCMC for Critical Components and providing comments to fix some segment of the presentation, this presentation will be presented to Genera PR. Meet with Miguel Del Valle of S&L to follow up on cost estimate for Cambalache Fire Protection System, the proposal is still pending to be submitted by S&L.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were CR 0186 to CR 0191, AE 039 to AE 056,
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Aguirre warehouse performing cycle counts and recounts to ensure the inventory aligns accurately with the system records. During the day, locations CR 0186 to CR 0191 were counted.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-continuing with the recount of discrepancies to validate the previous inventory count. Additionally, any variances identified are being documented and investigated to ensure accuracy and alignment with system records.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse conducting a job briefing with Giovanni Taffanelli, Milton Flores (DCMC) and other warehouses personnel to provide guidance on the new report that must be included in the daily report and address any issues that may have occurred the previous day.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Develop of a report for GENERA-PR regulatory with the current cases in FOMB revision.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Develop of a report for GENERA-PR Anthony Vega of delivered critical components with details of disbursement by GENERA-PR to the vendors.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Continue develop of a report for GENERA-PR Anthony Vega of delivered critical components with details of disbursement by GENERA-PR to the vendors.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Federal Projects Revision Status meeting with participation from DCMC: Pedro Cabrera, and D'Alexzander Gonzaléz and Roberto Bosch; from Genera-PR Joaquin Quinoy, to discuss priorities and deliverables, status updates, identify next steps for projects under Federal Grant.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Preliminary Drawings update, RFI, Submittals.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Genera Cambalache BESS: RFP-4826 Construction Schedule + RGE Pricing sent by Carlos De Jesus from DCMC.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | General Deliverable PR 11 - Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS received COMMENTS from DCMC on April 17, 2025. 8. Appendix D.3 - Demolition Specifications submitted by Andrés Concepción, DCMC. Initiated reviewing the preliminary document, which includes the general planning of the demolition work, the methods to be used to demolish the structure, the necessary equipment and measures to be taken to carry out the work safely and to make comments on floor demolition drawings and missing electric water and diesel lines.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria We continued for another hour, once the contractor did not make it to the site today again and no lead and or asbestos results came in from the laboratory. Contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project discussed with our safety crew Gilberto Soto DCMC then we called it for the day.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Homeca did not make it to the site today again and no lead and or asbestos results from the laboratory. Contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project discussed with our safety crew Gilberto Soto DCMC
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Daily project coordination on the field and project management with contractor Homeca Recyclers. Project Documents Overview and analyzing documents status in the Procore platform and updates to discuss the current project Phase situation with the Demo Contractor (with Nelson Soler CDM Smith, Jose Lopez Linares DCMC. Homeca crew did not make it to the site today again and no lead and or asbestos results from the laboratory.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to protect workers from hazards, prevent accidents, and ensure compliance with regulations while conducting Demolition and clean the areas by Homeca.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293410-10 for TO#1 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Procore - DCMC Financials Tools. Internal Zoom Meeting with Pro-Core team to discuss new change order tools available on Procore to capture changes relates to federal projects. Reviewing workflow, contract requirements, analyzing standard Change Order forms and collaborating to streamline the change process based on Contractual needs. Participants: Foster Veazey, Lauren Wells, (Lemoine) Lauren Kennedy, Tyler Scanlan (Procore) and Rafael Calderon (DCMC).
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293410-8 for TO#1 Sept 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory report for maximum and minimum stock levels from locations AD012 to AD020.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK001 to AK 005
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AK001 to AK005
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AK001 to AK005
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE 00 039 000 to AE 00 056 000.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE 00 039 000 to AE 00 056 000.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE 00 039 000 to AE 00 056 000
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies in Recount Lists #364, 365, and 366 from locations AD012 to AD020 for a total of 4,154 pcs.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD012 to AD020 Cycle Count List # 350.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD012 to AD020 to begin the cycle counts.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Data Management - Data Review and Process to help improve efficiency, reduce costs, enhance decision-making, and boost overall project outcomes.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) to overview the introduction of forms creations vs inspection templates for Procore Platform.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform data analysis for information to be included in Fillable PDF forms being uploaded to Procore at Inspections and Forms core tools.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review previously created SOPs for Contractor and Vendors on Submittals and RFI.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) for a second overview and feedback on the introduction of forms creations vs inspection templates for Procore Platform.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review progress of Procore new core tools implementation such as Incidents, Inspections and Forms.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 149 | 596 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on invoice for Sargent and Lundy TO01_January 2025 - this invoice was reviewed ell employee rates, compliance sampling, prepared for final package and sent for Genera Signature.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Receive email from Sargent and Lundy with response on RFI for compliance sampling on TO9_18334036_January2025. Complete compliance sampling was completed and invoice sent for Genera signature.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - PROCORE meeting to view process live about change orders. In this meeting participates Foster Veazey, Glorimel Torrado and Rafael Calderón from DCMC, Lauren Wells from Lemoine and Lauren Kennedy from PROCORE.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 148 | 148 | 148 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Full Day PerDiem
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting with Abraham Velazquez of DCMC Partners about the Peaker project, the operational phases of the project, budget and address doubts.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 139 | 486.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria First meeting with the community in Cambalache related to the Bess project in Arecibo. The meeting seeks to answer questions and communicate important information about the project to the community. Jorge Bracero, Genera; Rafael A Rodriguez Ema, Genera; Frances Vallejo, DCMC Partners; Jesus Cintron, Genera; Gabriel Perez, BESS Manager were available at the meeting.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting with Gilberto Sucre, DCMC Partners and Jorge Bracero, Genera about the BESS project, the operational phases of the project, budget and address doubts related to the protection of Bess in Vega Baja, Arecibo, Yabucoa, Costa Azul, Palo Seco, Aguirre.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create communication materials for the first meeting with the community in Arecibo related to the BESS project.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA - Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Jorge Bracero, Rafael A Rodríguez Ema, Iván Báez, Genera PR, and the team of the communications agency Kroma Amarilys Torres, Victoria Flores, Bernardo Medina and Miriam Seda to discuss this week's communications tactics and efforts in relation to the Bess project, particularly groundbreaking in Vega Baja, which is scheduled for Thursday, March 24, but Governor Jenniffer González has not yet confirmed her participation. The meeting outlined the communication pieces that must be delivered related to community communications efforts.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2 |  | 139 | 278 | 139 | Yes | 25-145003 | PREPA - Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 visit the Cambalache plant in Arecibo of Genera PR together with Jorge Bracero, Genera PR, and Frances Vallejo Rosich, DCMC Partners, to learn about the different operations of Genera PR plants due to the new works related to the community.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR-Deliverable 11 - Project Management ¦ DR 4339: I received a call from Marimar Bracero (DiSignXpress Inc.), informing me that the banners are being prepared and can be picked up tomorrow. Grommets will be placed every 24 inches. I proceeded to write to Chyenne Bliss (DCMC) to inform them about the grommets and received a response to proceed with them. Call from Marimar Bracero. A phone call was made to T-Mobile regarding issues with the hotspot located in Vega Alta. I contacted Mr. Manuel Félix from T-Mobile and had a three-way call with José Lopez (DCMC). José provided the SIM card number for verification, and the hotspot was turned off and on again to ensure it was functioning properly.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue Procore Quality and Safety inspection best practices training course for 4339_9510 BESS_Cambalache project.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache participate in team in weekly internal meeting discussing strategies for a meeting with designer Sargent & Lundy, timings for possibles starting project of contractor RGE contractor and news related to team responsibilities with employees Jorge Mercado, Luis Duque, Luis Damudt, Gilberto Sucre, Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create project schedule with data of RFP contractor proposal and send a report to employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create project schedule with data of RFP contractor proposal for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Completed Procore Quality and Safety inspection best practices training course for 4339_9510 BESS_Cambalache project.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continued Procore Quality and Safety inspection best practices training course for 4339_9510 BESS_Cambalache project.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with Genera PR, RGE, Sargent & Lundy about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache project update meeting with Frances Vallejo (DCMC), Gilberto Sucre (DCMC) for 4339_9510 BESS_Cambalache project.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Updating Critical Components spreadsheet data as request for proposal progress, vendors, units cost, and actual cost for reporting purposes.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Integrating comments arise from previous meeting regarding April program monthly report. Updating Contract Management and Risks table and information.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. In person meeting with Foster Veazey (Lemoine), Gilberto Sucre (DCMC) and Rafael Calderon (DCMC) to review and discuss program monthly report.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with the data entry for Critical Components project monthly report.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 26.73 | 26.73 | 26.73 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Airbnb to Genera's office. Tip adjusted to $3.65, wait time deducted.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 24.17 | 24.17 | 24.17 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from DCMC office to airport for Foster Veazey. Tip adjusted to $3.00 ($19.15 Trip Fare, $2.02 Booking Fare, $3.00 tip)
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 20.08 | 20.08 | 20.08 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from hotel to DCMC office for Foster Veazey.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 10.96 | 10.96 | 10.96 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Genera's office to Airbnb. Tip adjusted to $2.00
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 41.44 | 0.7 | Yes | 25-145003 | Jean Menay 04/22/2025 Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site inspections job in the site. Meeting with Carirma Sanchez (Homeca) Total Distance 59.2 miles
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 158.9 | 0.7 | Yes | 25-145003 | Harry Del Valle Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Central Costa Sur (18.000463, -66.753480) to Yabucoa Gas Turbine Plant (17.961105, -66.140130) to Home Office Luquillo. Meeting & Coordination for Central Costa Sur and Yabucoa Gas Turbine Plants. Attendees, Franklin Colmenares (Genera), Juancarlos Cruz (Röhlig Logistics), Wayne Jepson (Röhlig Logistics), Danny Rosario (Transporte Rosario) & Harry Del Topics discussed - Verify the areas as part of the logistics for the delivery of Tesla batteries. The company Röhlig Logistics was hired by Tesla is in Puerto Rico, coordination with the transportation company. Total Mileage 227 Miles
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel from home in Guaynabo to Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel back home in Guaynabo from Aguirre, the purpose of the visit was to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in meeting review of comments to the contract with Francisco Feliu Attended an additional meeting the Peakers weekly pm review, we discussed and reviewed recent drawings and comments with Sargent & Lundy representatives as the EOR of the project; Mike Kuczynski– S&L Chris Mateo , Gino Sambolin, William Crespo Lemuel Nieves, Reinaldo Romero, Miguel Del Valle Rafael Pabon CDM Smith and Carlos Palomares CDM Smith,
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in Peakers meeting update with team members, Items discussed the procurement of equipment, the team individual reviews of the Demolition RFP and scope of works, reviewing schedule and projections. Mike Kuczynski– S&L Chris Mateo S&L Gino Sambolin S&L German Nunez, Genera Rafael Pabon,( CDM smith Carlos Palomares (CDM Smith,
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS - Genera & Tesla Weekly Project Meeting Attendees from Genera, Sargent & Lundy, Tesla, CDM Smith, CSA Group & DCMC Partners. Reviewed Payment status, deliveries, delivery subcontractors visit to 4 sites, New Contract Management Meeting to be set for Fridays starting this week. Review RFI's mainly for Cambalache & Vega Baja.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 225 | 506.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS management overview and assessment of: * Procore implementation * BESS budget and Project Site Specifics * Vega Baja Pending action List * Decommissioning Quarterly Review * Monthly Report Dashboard.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Internal meeting with Carlos Lopez - Site Manager & Jaime Pesquera -Construction Manager from DCMC Partners to discussed path forward activities and action items to maintain project on time.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Tesla upcoming meetings coordination with Franklyn Colmenares - CSA Group.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Ground-Breaking Event-Last Checkup with Jorge Bracero & Rafael Rodriguez Ema from Genera, Victoria Flores -Kroma Idea, and Paola Arroyo and Frances Vallejo - DCMC. Discussed preparatory items for reschedule of event.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up. The PMO Team Catch Up meeting focused on several critical aspects of project management, including project status updates, staffing discussions, and upcoming activities. Gilberto Sucre DCMC confirmed the completion of grass cutting at Vega Baja and highlighted financial progress led by Lauren Wells - DCMC, who is advocating for more meetings to accelerate processes. The team reviewed the staffing spreadsheet and discussed potential personnel transitions, with Eduardo Rivera DCMC seeking a move to site management and various candidates considered for open positions across several sites. They also addressed critical components management, with Carlos Lopez potential hire emerging as a front runner for Eduardo Rivera's current role and further deliberated on training sessions for Procore financial management. Upcoming activities included the rescheduling of the Governor's visit and preparations for a PMO RFP, with specific action items assigned to team members to ensure progress on personnel decisions and resource allocations.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Evaluated and discussed draft Decommission Report with Gabriel Garcia CDM Smith.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Weekly Construction Meeting led by Jaime Pesquera DCMC with Homeca, DCMC Partners, and CDM Smith representatives. Review outstanding submittals including Rigging, Plan, PUI Submission, Diesel Transfer Plan to Palo Seco, and Temporary Power Installation. After meeting had individual assessment with Jose Lopez,DCMC.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFQ Feedback for BESS RFP Meeting to discuss comments to RFQ Questions and agree on a Final Version. Participants from CDM Smith, CSA Group, Sargent & Lundy, Genera, DCMC Partners.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.75 |  | 225 | 393.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 -I met with Vladimar Scutt (Genera). We discussed team development for upcoming grant projects and coaching the new teams. We also discussed setting up KPI's to measure efficiency of units, run times and EAF(Event forced outage rates). we also discussed the grant approvals process, time tracker, and tracking closure of work orders. All participants were in person at the Genera office.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 -Meeting prep time to finalize Team meeting lunch N Learn training. Reviewed training with Joaquin Quinoy. (Genera) and Jennifer Witeczek (Genera) to ensure the content meets the needs and expectations of the team. All participants were in person at the Genera office.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 -Meeting with Jennifer Witeczek (Genera) We discussed Grant approval process challenges, processes to improve and reduce the Approval process and scheduling and communication processes for current grant projects. we also developed a plan to capture lessons learned and how to apply lessons learned to ensure alignment of Grant projects and establish standard meeting rules. We also determined to proceed with getting all leaders to take the Gallup strengths assessment to ensure we are leveraging the team's strengths for upcoming grant projects. All participants were in person at the Genera office.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 2.75 |  | 225 | 618.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 -Lunch training - Lean Management Program on effective meetings and Lessons learned from the recent outage event. We also developed new standard meeting ground rules to improve the effectiveness of meetings. Participants of the meeting included. Joaquin A Quinoy Ortiz (Genera), Ivan Baez Santiago (Genera), Maria Sanchez Bras (Genera), Carlos A Negron Alfonso (Genera), Jennifer Witeczek (Genera), Kevin D. Futch (Genera), Vladimir Scutt (Genera), Ricardo Pallens Cruz (Genera), Hector Vazquez Figueroa (Genera), Jose Del Rio Velez (Genera), Winnie Irizarry (Genera), Jeanniffer Gonzalez Diaz (Genera). All participants were in person at the Genera office.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 -I met with Ricardo Pallens (Genera), We discussed the recent outage event and developed a plan to capture lessons learned and how to apply lessons learned to ensure alignment of future grant projects. All participants were in person at the Genera office.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Check in with Joaquin Quinoy (Genera) to confirm meetings scheduled for the day, finalize agendas. We also discussed the previous day's one-on-one meetings and action items identified. We also discussed the recent outage event and developed a plan to capture lessons learned and how to apply lessons learned to ensure alignment of Grant projects. All participants were in person at the Genera office.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 -I met with Kevin Futch(Genera). We discussed the Grant approval process challenges and procurement process as it relates to writing the contracts. We also discussed how to develop standards for the MSA contracts to reduce processing time. All participants were in person at the Genera office.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Admin settings for project names and how they are ordered in the system per BESS and Peakers.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks lists for review with Theresa Perez (DCMC) and Luis Roman (DCMC).
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Procore (Liz Fronduto) for setting up next meetings for Services Hours discussion and meetings for the team on configurations.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for follow up to Procore Financial meeting on 4/22. I sent out screenshots and questions to the team for decisions in how Potential Change Order forms should work.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of SOP's for Procore Submittals to give feedback to Luis Roman (DCMC).
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), GIlberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items with Theresa Perez (DCMC) and Luis Roman (DCMC).
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore Financial information for implementation.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on setting up Incidents tool in Vega Baja for specific users with permissions. This should be limited to has access to enter in an incident.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on email correspondence for Procore document structure items to respond to users.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore settings for turning on certain tools that were not active before.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks list for each tools and preparing training materials for financial modules.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Lauren Wells, Foster Veazey, Barry Scanlon, Jack Darnall, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 186.6 | 186.6 | 186.6 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I stayed at Airbnb at 7 Calle Cervantes, San Juan, PR 00907-1315, US while visiting the Genera team. The nightly cost was $186.60 per night.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.75 |  | 184 | 690 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Gabriel Perez (CDMSMITH) about Genera Site in Vega Baja. Conference call with Franklyn Colmenares (CDMSMITH) about batteries route. Review the Vega Baja resume by job day. Coordinate Yabucoa Visit. Review the Genera findings
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria Hurricane Maria: Review documentation for Homeca. Weekly Meeting about Vega Baja Project with Carirma Sanchez (Homeca), Jaime Pesquera (DCMC), Gilberto Sucre (DCMC), Gabriel Perez (CDSMITH). Work in Procore actions for all projects by Genera.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 184 | 138 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Call with Carirma Sanchez by Homeca about Vega Baja Project. Review documentation by Vega Baja Project.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review and add comments to the Community engagement plan for Vega Baja and Cambalache site.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended staffing update meeting with Nyah Medina (DCMC) to discuss staffing offers, interview feedback and next steps.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended call with Jorge Bracero (Genera) to discuss feedback on the Arecibo meeting with the community.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss PMO status on staffing, offers that are pending, trailer installation, Procore status and other related matters. Participants: Mike Merritt, Mark Merritt, Ada Diaz, Gilberto Sucre, Anneilia Holton (DCMC), Lauren Wells.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Raissa Borges (DCMC) to discuss draft dashboard that we will send to the client regarding PMO update.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Attended meeting with Paola Arroyo (DCMC) to discuss feedback and observations from the community engagement meeting at Arecibo. Also discussed next steps on the community engagement plan.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Continued updating ICE (positions 7 through 17 with 3 comparables (GSA or past proposals) for each.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -BESS -Participated in a follow-up feedback session focused on the BESS RFPs, specifically addressing the issue of low vendor participation in recent procurements. Engaged in a strategic discussion on the proposed Request for Qualifications (RFQ) approach, including how to frame the qualifications criteria, the type of questions to be included, and strategies to increase market engagement. Also reviewed the anticipated timeline and key steps in the requisition and solicitation process to ensure alignment across procurement, technical, and legal teams. Genera: Christian Torres and Fernando Ortiz CDM Smith Franklyn Colmenares, Enrique Laya, Gabriel Sepulveda, Carlos Palomares. S&L Mike Kuczynski
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Updated legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Prepared for the weekly BESS and Peakers catch-up call by reviewing and updating the project tracking spreadsheet. Incorporated feedback and updates received on 04/21 from the Genera procurement team, including changes to documentation status, and contractor communications. Ensured the tracker reflected accurate, real-time information to support productive discussion, alignment across teams, and timely follow-up during the coordination meeting.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria User Adoption Strategies and Security Implementation: - Discussed Genera Connect Time Tracker user adoption strategies with Alex Valdés from Genera PR's IT team, focusing on effective methods to encourage user engagement and smooth integration of the new system. - Provided Jean González from Genera PR's cyber team with a status update on alternatives for implementing the required security measures into the Genera Connect applications. - Collaborated with Aldwin Pagán from Integrum to implement the remediation for Michael Silva's security observation using the documented approach, ensuring the system meets the necessary security standards.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.75 |  | 184 | 506 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Security Observation Resolution: Addressed the pending security observation provided by Michael Silva from Genera PR's cyber team. Conducted tests in a controlled environment to validate the necessary changes and documented the configuration approach to ensure it can be replicated within the Genera Connect system.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and continued supervising contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca brought a truck to transport metals to their recycling facility.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Issue for Bid drawings 4339_9510. Report for discussion with Gilberto Sucfre, DCMC Partners, to discuss missing information.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Revision of issue for bid 43339-_9510 drawings set and evaluation of missing information.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Costa Sur & Yabucoa projects. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Costa Sur & Yabucoa projects. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project coordination walks to ensure the project meet standards, adhere to regulations, and maintain safety. Delivery and work with Tesla staff and the DCMC team are evaluated.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RGE Contractor Safety Plan Evaluation.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting on site with DCMC Luis Damudt, Andres Concepcion and Luis Duque team to discuss project management issues and contract documents.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Coordinated Site Office required equipment and drawings sets to facilitate construction meetings and coordination.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Generated project meeting agenda and gathered information for site visit with Röhlig Logistics to evaluate site conditions for batteries delivery logistics.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Meeting with Cambalache Facilities personnel to discuss movement of existing assets to open space for the construction. Met Luis Damudt (DCMC) and Kevynne Gonzalez (GeneraPR)
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Generated meeting minute notes to communicate Gilberto Sucre (DCMC Partners), Franklyn Colmenares (CDM Smith) and Mike Kuscynski (Sargent & Lundy) regarding the TESLA logistics subcontractor site visit and survey.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR -Site visit and meeting with Juancarlos Cruz , Wayne Jepson, Daniel Rosario – Röhlig Logistics Herminio Arroyo , Eliseo Martinez - Genera PR Andres, Concepcion, Luis Damudt, Carlos De Jesus, Luis Duque, Jorge Mercado, (DCMC Partners) to do a walktrough to evaluate site for BESS equipment delivery.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Performed review of project specifications and project drawings for constructability comments to be provided to project designer (Robert Molner - Sargent & Lundy) and Gabriel Perez (CDM Smith) for corrections or clarifications.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with Critical Component Tracker table to include new column to separate actual cost with PO from pending actual cost without PO. Updated the procurement column with procurement status update related to all projects. Review actual cost for each project that has PO on Asset Suite. Reviewing status on Asset Suite of the PO 107190 that is still pending to be awarded to vendor update procurement status column.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with Genera Resolution at "Negociado de Energia" MI-2021-0004 portal to verify all Genera resolution for NME projects, they are a total of 26 resolutions to verify information related to NME projects.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Meet with Pedro Cabrera of DCMC to discuss the new table with NME project and what are the founding related to cost of all these (23) projects, some has cost difference and also one project was not found on this list in compared to the critical component's tracker.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working in data entry for new table related to NME FY2025 activities in related to critical components (CC) tracker. The table was populated with information but (3) was not able to be match with CC tracker. The are difference in cost estimate assigned to these NME in compare with the one on Master Power BI Mapping and CC tracker.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Aguirre warehouse performing cycle counts and recounts to ensure the inventory aligns accurately with the system records. During the day, locations CR 0192 to CR 0196 were counted.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-we continue identifying discrepancies and investigating variances to ensure proper inventory control. This process helps maintain accuracy in stock levels, supports operational efficiency, and allows for timely corrective actions when inconsistencies are found.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-continuing with the cycle count and recounts to ensure that the inventory accurately matches the records in the system. Additionally, any discrepancies identified are being reviewed and validated to maintain data integrity and support accurate reporting.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were CR 0192 to CR 0196, AE 057 TOAE 074, AD 021 TO AD 026, AK 006 TO AK 012.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Develop a list based on NEPR resolution for NME identify under FY2025 NME Projects.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC-Reporting Meeting with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz; SM Consultant: Shellsea Maysonet and Johanna Diaz to discuss Dashboard to present to GENERA-PR.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Review in NEPR all resolution for NME identify under FY2025 NME Projects.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the notes before meeting and walk tour with Andres Concepcion, Jorge Alexis Mercado DCMC.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting and Site walkthrough to assess potential site coordination efforts delivery coordination and technical aspects of work areas on the bridge and types of cranes with Jean Carlos Cruz from Rohlig team for deliveries of Tesla Mega Packs with Andres Concepcion, Jorge Alexis Mercado DCMC, Herminio Arroyo Genera PR.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100- Drawings which serve as record of the project to be used for maintenance, repairs, renovations, or any other modifications.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Contractor Supervision (Homeca Recyclers) for Abatement Activities field supervision and coordination all around the site. Meeting with Carirma Sanchez (HOMECA ) Jose Lopez Linarez DCMC to discuss the weekend work schedule. Field supervision activities briefing with Gilberto Soto from DCMC.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Continued Vega Baja Contractor Homeca Recyclers field supervision with Gilberto Soto. Overview to and frequent briefings ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution and with safety in mind.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca making hot cuts on the metal beams to dismantle area.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Revision and development of editable Exhibit 1 for invoice financial tracker based on contract requirements. Developing excel document for construction team support. Pre-Intervention process for demolition works (BESS-Peakers). Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Technical Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla Technical reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda, Carlos Palomares), Sargent & Lundy (Mike Kuczynski), and DCMC (Rafael Calderon, Gilberto Sucre)
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón (DCMC) to update presentation for PMO. This include go over the contracts and update template with risks and change orders information critical for projects.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 Invoice Workshop Meeting - Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Revision and development of Pre-Intervention process for demolition works (BESS-Peakers) - Case Study will be Homeca's 1st demolition invoice for BESS Project. DCMC Participants (Glorimel Torrado and Rafael Calderon)
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Revision and development of editable Exhibit 1 for invoice financial tracker based on contract requirements. Developing excel document for construction team support. Pre-Intervention process for demolition works (BESS-Peakers). Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AK006 to AK012
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK006 to AK012
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AK006 to AK012
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE 00 057 000 to AE 00 074 000.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE 00 057 000 to AE 00 074 000.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE 00 057 000 to AE 00 074 000
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD021 to AD026 Cycle Count List # 372.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #379, 380, and 381 from locations AD021 to AD026 for a total of 6,244 pcs.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 379, 380, 381.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD021 to AD026 to begin the cycle counts.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 151 | 528.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Mgmt for Costa Sur BESS/Costa Sur PEAKERS/Cambalache BESS
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Finalization of Document Data & Users for New File Structure - Procore Data Management for Vega Baja BESS/Costa Sur BESS
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Forms creation for implementation on Procore recently enabled Core Tools.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review draft SOPs for Procore Core Tools (Inspections, Observations, Incidents).
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review project scheduling progress to maximize Schedule core tool (to be used as construction progress tracking and supporting documentation/evidence for contractor's payment certifications).
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón (DCMC) to update presentation for PMO. This include go over the contracts and update template with risks and change orders information critical for projects. When the working session finished, I review the document to familiarize with the new format previous to our team meeting tomorrow.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 149 | 298 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, Homeca, CPM, B&V, Siemens Energy and CAPTA. Also, I update the entries with the invoices that I completed during the week and identify invoices with past due dates.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Invoice Workshop with Rafael Calderón (DCMC) - Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-01 Revision and development of Pre-Intervention process for demolition works (BESS-Peakers) We did an overview on Invoice #1 with the RFI response and prepare for final process on this invoice. Invoice #2 is pending for review.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 148 | 148 | 148 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Full Day PerDiem
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA - Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting Vega Baja Groundbreaking Event-Last Checkup. Logistical details for the inauguration event in Vega Baja were reviewed, including the coordination of materials and catering. The meeting was with the Genera team: Jorge L. Bracero Nieves, and Rafael A. Rodríguez Ema.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Begin preparing the fact sheets on the first community meeting held yesterday, Tuesday, in Arecibo with the purpose of keeping the community, local authorities, and stakeholders updated on the progress of the project.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Call with Jorge Bracero from Genera PR to begin addressing the next steps, best practices, learnings from the BESS project in Cambalache of community relations after the first community meeting with leaders from the Arecibo sector.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria create a list of the people who attended the first community meeting in Vega Baja was created yesterday, Tuesday, with the purpose of meeting the needs of the community relations project. The document allows us to continue community relations and, in turn, feed our current database. The list of people includes the people we must keep neutralized. Similarly, the people who can be connectors with our target audiences were identified. The list was sent to Jorge Bracero from Genera PR to integrate them as part of the project.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create a detailed minute summarizing the first meeting with the community in which it is offered: the topics that were discussed, the stages of the project, impact and benefit of the BESS project and the number of participants who attended the event as well as the next steps we will be implementing in the community meetings. The letter was sent to Jorge Bracero Nieves from Genera PR.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR-Deliverable 11 - Project Management ¦ DR 4339: Called Marimar Bracero from (DiSignXpress Inc.), regarding the Banners for the eight Sites, coordinating the delivery to City View Plaza today. Sent an email Chyenne Bliss (DCMC) requesting another long sleeve shirt. Called Office Depot to verify the printing of plans and requesting prices for it.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the Bid addendum drawings of 4339_9510 BESS_Cambalache for changes, modifications, or clarifications.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create project comments report using RFP drawings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create project schedule with Genera Power plant data for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache participate in site meeting with visit with TESLA's logistics contractor Röhlig Logistics with employee Mr. Arroyo, and Mr. Wein, to assess site conditions and readiness for the TESLA battery's delivery coordination with DCMC Jorge Mercado, Luis Duque, Luis Damudt and Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting and site walkthrough with Genera PR, TESLA's logistics contractor Röhlig Logistics about Tesla Battery installation Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with Critical Components data updates. Pending Actuals Cost Without PO column was added and RFPs Procurement Status were changed.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with the data entry of pending actuals cost without purchase order and defining columns meaning with Tooltips feature for Critical Components project on dashboard report.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 25.6 | 25.6 | 25.6 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Airbnb to Genera's Office. Wait time deducted. 7 Calle Cervantes, San Juan, PR 00907-1315, US to 250 Av Luis Munoz Rivera, San Juan, PR 00918, US
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 14.7 | 14.7 | 14.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Genera's office to Airbnb ¦ 250 Av Luis Munoz Rivera, San Juan, PR 00918, US to DCMC Office. Tip adjusted to $2.50. ¦ 7 Calle Cervantes, San Juan, PR 00907-1315, US
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 68.18 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Site Inspector Luis Duque Route Guaynabo to Arecibo, round-trip to Guaynabo. Drive 97.4 miles, 1 hr 57 min Claiming Mileage for this route Travel from Guaynabo (18.392607 -66.123698) roundtrip to Cambalache Power Plant, Arecibo (18.471729, -66.700701) back to Guaynabo (18.392607 -66.123698) Purpose meeting and walkthrough site with Genera, RGE, Sagent and Lunder for 4339 9510 BESS Cambalache project. TOTAL MILEAGE 97.4 miles
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.2 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel back home in Guaynabo from Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel from home in Guaynabo to Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 332.5 | 332.5 | 332.5 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel expenses to meet with Genera team. Original flight cancelled and rescheduled due to Genera team availability. Due to needing to change my return flight, I had to change airlines to accommodate the adjusted schedule. Note on flight charges Original flight $605.00 Flight change to week 4/21 fare difference $90.00 SW Credit for 2nd flight change credit ($287.50) Flight change to Thursday to accommodate adjusted schedule - had to cancel SW flight and book American flight $332.50.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence with Theresa Perez (DCMC) for document structure questions from users.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended Bi-monthly PMO reporting meeting, items discussed was the outline of the power point presentation dashboard, the information break down and access to different items/ reports via the dashboard, group open session. Gilberto Sucre DCMC Rafael Pabon, CDM Smith Carlos Palomares CDM Smith, Frances Vallejo Rosich DCMC Foster Veazey DCMC Jean Pierre Menay DCMC Sheila Torres-Sterling DCMC Francisco Feliu Genera Jean Pierre Menay DCMC Paul Browne DCMC Lauren Wells DCMC Paola Arroyo DCMC Colmenares, Franklyn CSA Group
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in weekly BESS/ PEAKERS permitting discussions. Items discussed were the current status of Demolition and any ancillary permits that are applicable to each project if at all. discussed the areas of responsibility on the general contractor to pull permits when and as needed on a project-by-project basis Harry Del Valle DCMC Gilberto Sucre DCMC Rafael Pabon, CDM Smith Carlos Palomares CDM Smith, Frances Vallejo Rosich DCMC Foster Veazey DCMC Jean Pierre Menay DCMC Sheila Torres-Sterling DCMC
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Reporting Monthly Report Review Update among DCMC Partners, CDM Smith, GENERA and CSA Group
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 225 | 393.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly PMO Program Action Items from Staffing, Execution, EHS, Construction Updates, RFP's evaluations for Vega Baja, Costa Sur and Cambalache Final Proposal Expectations.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Internal Meeting Weekly Design Update and PM/CM needs. Sargent & Lundy, CDM Smith, CSA Group and DCMC Partners participants.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS One on One Meeting with Gabriel Perez CDM - Smith Evaluating Program Organizational Chart, Roles & Responsibilities, and transition roles from PM Design Stage to Construction Stage.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - evaluated Schedule Key Dates adjustments due to actual Permit for Demolition actual date of 4/22. Discussed key points on response to Homeca's delay and additional days claim letter with Jose Lopez - DCMC
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Miscellaneous calls/discussions with DCMC employees Jose Lopez, Harry del Valle, Jean Pierre Menay and Andres Concepcion.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja obtained legal advice from Sheila Torres DCMC Partners for correspondence response to Homeca's request for additional days.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting RGE - Follow up meeting on remaining items to finalized evaluation process prior contract signature. CDM Smith, RGE, Sargent & Lundy, DCMC Partners participated.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria EHS Implementation and Manual for Genera - Discuss details with Jack Darnell - Lemoine.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Joaquin Quinoy (Genera) to review the past 2 days of meetings and develop a plan moving forward for the implementation plan for Team Leadership, Strategy and Alignment discussion for deliverables and proposal for upcoming Grant projects. All participants were in person at the Genera office.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Strategic Planning Session with Maria Sanchez CFO (Genera) and Mark Merritt (DCMC) to review the past 2 days of meeting and develop a plan moving forward for the implementation plan for Team Leadership, Strategy and Alignment discussion for deliverables and proposal for upcoming Grant projects. All participants were in person at the Genera office.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up meetings for Procore items with users and Procore team.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of SOP items for Procore.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items, answering questions for users.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for SOP document generation.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence with RGE and Sargent and Lundy for documents.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) PMO reporting meeting with Raissa Borges (DCMC), Frances Vallejo(DCMC), Glorimel Torrado (DCMC), Paul Browne(DCMC), Abraham Velazquez (DCMC) and others to review master dashboard for showing risks, activities and other items.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting update for leadership for PMO Reporting.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on Procore Financial information for creating 9510 the same setup as 10710.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for Theresa Perez (DCMC) for RGE setup in Procore.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on training list for Procore to update to show who has been trained and who else needs training so that we can start to schedule our next session. Will pass this task on to Theresa Perez (DCMC) on 4/25/25 as one of her tasks to update.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on training list for Procore to update to show who has been trained and who else needs training so that we can start to schedule our next session.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reports from the system to show volume of users and what tools are being utilized.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review documentation for Homeca, Diesel Transfer from Vega Baja Site (GENERA) to Palo Seco Site GENERA. Work projects in Procore.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria : Review documentation for Homeca about Vega Baja Site Diesel Transfer. Emergency Management training. Conference call with Jaime Pesquera and Gilberto Soto (DCMC) about Vega Baja Site. Diesel Transfer from Vega Baja Site (GENERA) to Palo Seco Site GENERA.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 1 | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review documentation for Homeca about Vega Baja Site Diesel Transfer. Meeting with Clara Padovani by (Genera) about the Vega Baja Activity and Diesel route. PMO Meeting about projects Status and development discussion of measurement tools. Conference call with Franklin Colmenares (CDMSMITH) about Palo Seco Project. Meeting with Andres Concepcion (DCMC) about Cambalache Site. Review the Health and Safety DCMC presentation.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Reporting call with PMO supporting team. In this call we all reviewed the monthly report that we will send to the client by the end of month which includes all areas under the PMO structure. Participants: Raissa Borges, Lauren Wells, Sheila Torres, Jean Menay, Gilberto Sucre, Abraham Velazquez (DCMC), Franklyn Colmenares (CSA).
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Sent email to Jesus Cintron (Genera PR) regarding staffing update.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Communications team at Genera and project management team to discuss feedback and recommendations for the next community engagement meetings at the site. Participants: Jorge Bracero, Ivan Baez, (Genera), Gabriel Perez (CDM) and Jesus Cintron (Genera), Paola Arroyo (DCMC).
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Contributed updates on assigned tasks, reviewed performance metrics, and participated in discussions aimed at streamlining reporting processes and enhancing cross-functional coordination. Collaborated with team members to identify action items and align on priorities for the upcoming reporting cycle. DCMC: Frances Vallejo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Browne, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Finalized updating ICE (positions 18 through 30 with 3 comparables (GSA or past proposals) for each.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Finalized the update and reformatting of Attachments D, E, and F for the upcoming RFP, ensuring alignment with current project requirements and adherence to procurement standards. In parallel, began revising the applicable Exhibits—specifically Exhibits A and B—by updating content, layout, and formatting to enhance clarity, consistency, and ease of use for prospective respondents. These updates are intended to support a more transparent and user-friendly solicitation package.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Began updating and reformatting the attachments for the upcoming RFP to ensure consistency with current project requirements and procurement standards. Focused on revising Attachment A, B and C, updating content, formatting, and structure to improve clarity and usability for prospective respondents.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued making hot cuts on the metal beams to dismantle area, Homeca continue cutting using acetylene to demolish 1-1 generator metal Beams Day 2 Continuation
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria—Weekly Project meeting at the Vega Baja job site with HOMECA Recycling representative Carirma Sanchez to discuss daily project activities and progress and follow- pending up submittals and pending RFI's.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Contract (24112-P3A)- review for discussion with Eduardo Ramos from Homeca Recycling. Verified the terms, and conditions governing the contract, including schedule, responsibilities, and liabilities.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued on Procore, reviewing RFPs documents for the Yabucoa Gas Turbine project. Looking for possibles discrepancies and/or any information missing Working with spreadsheets for inventory of materials in the trailers office. Quoting materials for new Offices Trailer.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing RFPs documents for the Yabucoa Gas Turbine project. Looking for possibles discrepancies and/or any information missing Working with spreadsheets for inventory of materials in the trailers office. Quoting materials for new Offices Trailer.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation and preparation of the presentation that is being implemented for the entry of new contractors for the Cambalache site.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review of RFP 4826 Attachment A – Administrative Requirements Attachment B, Intent to Bid and Q&A Form, Attachment C – Master Services Contract & attachments.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of RFP 4826 Attachment A – Administrative Requirements Attachment B, Intent to Bid and Q&A Form, Attachment
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review of RFP 4826 Attachment A – Administrative Requirements Attachment B, Intent to Bid and Q&A Form, Attachment C – Master Services Contract & attachments.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed Procore documents that were uploaded during the day.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Meeting with Jean Pierre Menay (DCMC Partners) to review safety orientation presentation that will be implemented in project.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed project general specifications to consolidate submittal requirements to be followed during construction.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed and developed comments to the contractor (RG Engineering) accelerated project construction schedule and ensure it aligns with delivery plan.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed design drawings for quality control and documented comments to be sent to Robert Molner (Sargent and Lundy) and Gabriel Perez (CDMSmith) for clarifications and corrections.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Project meeting with Program and Design Managers (Gabriel Perez, Franklyn Colmenares (CDM Smith), Mike Kuczynski, Robert Molner (Sargent & Lundy), Gilberto Sucre (DCMC), contractor (RG Engineering, Jose Robles) to discuss ongoing action items to complete Cambalache construction contract.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed design drawings for quality control and documented comments to be sent to project designer CDM Smith for clarifications and corrections.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC and Lemoine: Abraham Velazquez, Frances Vallejo, Jean Pierre Menay, Lauren Wells, Rafael Pabon, Glorimel Toledo, Rafael Calderon, Frankly Colmenares, Raissa Borge, Sheila Torres, and Paola Arroyo. Meeting with DCMC to review the status of active projects, discuss progress against key milestones, presenting new Dashboard for PMO and address any issues impacting timelines or deliverables.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing PO# 104413 that was canceled for CCWP of CS & AG was found that the PO recently was uploaded a transmittal document for the review and approval of submittal related to the CCWP's. This information was sent as an email to Sulinnette Perez of Genera Procurement to confirm if the PO is still open so we can update the CC tracker table from Cancel to Pending Awarded. Continue review in the CC tracker all project that has a Cancel status to confirm if they remain the same status or has changed.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with updating the critical component tracker for procurement status for all projects, confirming status of procurement using Asset Suite. Provide feedback to Raissa Borges of DCMC on the new PMO Power BI presentation was made changes on procurement status and project cost.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Review the status in Asset Suite of the requisition # 285665, 286708, 287688, 287173, 287797, and 285838.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were CR 0197 to CR 0203, AE 075 to AE 0105, AD 027 to AD 033, AK 013 to AK 022
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at Aguirre warehouse identifying discrepancies and investigating variances to ensure proper inventory control. This process helps maintain accuracy in stock levels, supports operational efficiency, and allows for timely corrective actions when inconsistencies are found. Today we work with locations CR 0197 to CR 0203
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -TEAMS meeting with Frances Vallejo and DCMC personnel to review the dashboard created with the latest updates on the work completed. The purpose of the meeting is to ensure alignment on progress, address any pending isuues, and gather feedback for further improvement.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at Aguirre warehouse performing recounts to ensure that inventory has been recorded accurately. This step is essential to validate the initial counts, correct any discrepancies, and maintain the integrity of the inventory data.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Aguirre warehouse continuing with the cycle count to ensure that the inventory accurately matches the records in the system.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Aguirre warehouse performing cycle counts and recounts to ensure the inventory aligns accurately with the system records. During the day, locations CR 0197 to CR 0203 were counted
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Review the list created from NEPR resolution for NME identify under FY2025 NME Projects.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Develop of a report for GENERA-PR PMO with the current cases cancel and pending of award.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Using the available information in Asset Suite to update CCL Tracker.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100- Drawings to ensure access to the most up-to-date drawings and revisions.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Genera Cambalache BESS: RFP-4826 Construction Schedule + RGE Pricing.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | General Deliverable PR 11 - Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS received COMMENTS from DCMC on April 17, 2025. 8. Appendix D.3 - Demolition Specifications submitted by Andrés Concepción, DCMC. Continued reviewing the preliminary document, which includes the general planning of the demolition work, the methods to be used to demolish the structure, the necessary equipment and measures to be taken to carry out the work safely and to make comments on floor demolition drawings and missing electric water and diesel lines.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria I continued to supervise the contractor Homeca , went over daily's activities overview progress of the tasks and walked the site, to make sure they are all doing what they are supposed to safely and on target for this week.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11 Project Management¦ DR 4339 Hurricane Maria- I supervised the morning crew and noticed that Homeca Recycler did not started to work at 6:45 am and stated that they start work at 6am...I created some emails to reopen gate #1 because it was closed by mistake, contractor worked on the allowed demolition to do specific areas only, before we start for good. Worked with Procore and all the emails I needed to work with.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca making hot cuts on the metal beams to dismantle area, Homeca continue cutting using acetylene to demolish 1-1 generator metal Beams Day 2
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.75 |  | 164 | 287 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#2_Invoice# 18322768_Dec 2024. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#6_Invoice# 18322772_Dec 2024. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 164 | 123 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria PMO Reporting Meeting - DCMC PMO staff meeting to discuss specific need of reporting based on project execution development per area. Working on PPT presentation template and review updates from BESS and Peakers project. Participants Frances Vallejo, Raissa Borges, Glorimel Torrado, Gilberto Sucre, Sheila Torres, Abraham Velazquez, Eduardo Rivera and Paul Brown.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#3_Invoice# 18334033_Jan 2025. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, HOMECA, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #401 from locations AD027 to AD033 for a total of 1,707 pcs.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK 013 to AK 022
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AK013 to AK 022
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AK013 to AK022
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE 00 075 000 to AE 01 015 000.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE 00 075 000 to AE 01 015 000
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE 00 075 000 to AE 01 015 000
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD027 to AD033 to begin the cycle counts.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 401.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AD027 to AD033 Cycle Count List # 388.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, resumed working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 401.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control-File Structure/ Coordination Efforts w CM Teams for Cambalache BESS Data Mgmt for Vega Baja/Costa Sur BESS & PEAKERS/Coordination with CM Team and Permissions for Data Distribution/Document Control-File Structure for Aguirre
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control-File Structure Cambalache BESS/Costa Sur BESS & PEAKERS/Coordination with CM Team and Permissions for Data Control
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Gather Vega Baja contractual files to maximize Procore output efficiency by reflecting actual project established time and metrics.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review File Structure uploading scheme on active construction projects (Vega Baja)
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Procore online trainings to establish proper guidance on the SOPs for Core Tools use.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Finishing review and audit Vega Baja project's Submittal Log to identify items not to be uploaded as submittals (results from testing,
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria PMO Reporting Meeting - Working on PPT presentation template and review updates from BESS and Peakers project. We go over updates from Wednesday and include new information from Tesla. Also, during this time I update the pre intervention tracker with invoices signed.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, Homeca, CPM, B&V, Siemens Energy and CAPTA. Updates to start preparing for Friday internal discussion.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 149 | 111.75 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria PMO Reporting Meeting - DCMC PMO staff meeting to discuss specific need of reporting based on project execution development per area. Participants from DCMC: Frances Vallejo, Raissa Borges, Glorimel Torrado, Gilberto Sucre, Sheila Torres, Abraham Velazquez, Eduardo Rivera and Paul Brown.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 148 | 148 | 148 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from SJU Puerto Rico to OKC home of record. My first meeting with the Genera team was at 8.30 am, I had meetings until my flight at 3.30pm. Due to my flight not landing until after 23.00 and I did not arrive home until after midnight on 4/25/25. due to flight delays from weather.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.25 |  | 139 | 451.75 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Begin Finalize and delivere the fact sheets on the first community meeting held yesterday, Tuesday, in Arecibo with the purpose of keeping the community, local authorities, stakeholders and stakeholders updated on the progress of the project. The work was handed over to the Genera PR team Jorge Bracero and Rafael Rodríguez.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.25 |  | 139 | 312.75 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create a summary for Genera Jorge Bracero Nieves, of the strategic planning of the community meetings related to the BESS project in Cambalache, integrating both logistical and key communicational elements to ensure effective, clear and respectful participation.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Internal meeting with the DCMC Reporting team to perform PMO Reporting to observe a key function in project management.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review project to build relationships with the community to bring community efforts to schools to educate students from the generation system. Review an educational package for the community that is sought to be incorporated into the local schools of the communities we visit.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting to discuss the April 22 community meeting event in Arecibo. In the meeting we discussed the lessons and feedback from the event. Francés Vallejo from DCMC, Iván Báez Santiago, Jorge Bracero Nieves, Gabriel Pérez Sepúlveda, Jesús Cintrón and Rafael Rodriguez Ema from Genera PR were at the meeting.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Resumed reviewing the Bid addendum drawings of 4339_9510 BESS_Cambalache project for changes, modifications, or clarifications.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports with comments in necessary requirements included by proponent in RFP considering technical specifications for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports with comments in necessary requirements included by proponent in RFP considering exhibits and scheduling specifications for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continued reviewing the Bid addendum drawings of 4339_9510 BESS_Cambalache project for changes, modifications, or clarifications.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 124 | 124 | 124 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -A TWIC Card is required for work site entrance.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Franklyn Colmenares, CDM Smith to discuss Request for Proposal kanban board method to be implemented on project report to help teams manage workflow by visualizing tasks and their progress.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.25 |  | 122 | 30.5 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Overseeing the management, enhancement, and modification of relationships between tables in Power BI to ensure the timely delivery of the final report.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 122 | 91.5 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 122 | 366 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Overseeing the management, enhancement, and modification of relationships between tables in Power BI to ensure the timely delivery of the final report.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 122 | 427 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with Inventory Management data updates and defining columns with Tooltips feature on project dashboard report.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 60 | 60 | 60 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Airport Parking
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 weekly site and office visits as requiered
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 21.96 | 21.96 | 21.96 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from DCMC Office ¦ Carr 165 Km 1.2, Guaynabo, PR 00965, US to International Airport ¦ Av Aeropuerto, Carolina, PR 00937, US
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 17.26 | 17.26 | 17.26 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria'. PPE is required for work in the site area-hat and earplugs. Receipt dated 3.13.25.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 14.24 | 14.24 | 14.24 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Genera's office ¦ 250 Av Luis Munoz Rivera, San Juan, PR 00918, US to DCMC Office Carr 165 Km 1.2, Guaynabo, PR 00965, US
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 10.3 | 10.3 | 10.3 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Airbnb ¦ 7 Calle Cervantes, San Juan, PR 00907-1315, US to Genera's office ¦ 250 Av Luis Munoz Rivera, San Juan, PR 00918, US
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 8.05 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Mileage to drive from airport to office for an onsite meeting with Genera team.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel back home in Guaynabo from Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel from home in Guaynabo to Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal reviewing of weeks meeting notes, and action plans. Reviewed recent final release of the demolition contract for release for pricing comments have been incorperated. Internal data entry's from the week notes
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in the weekly PEAKERS projects management team weekly update Reviewed the roles and responsibilities flow chart, reviewed the week's meetings and notations, discussed the release of the final version of the RFP for demolition. German Nunez, Rafael Pabon, CDM Smith Carlos Palomares CDM Smith
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Weekly PMO Call with DCMC Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Paola Arroyo (DCMC) Frances Vallejo (DCMC) and Theresa Perez (DCMC) to discuss using Procore documents for Community Engagement files.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial information for implementation.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore research for setting up funding for Financials.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks list for Luis Roman (DCMC) and Theresa Perez (DCMC).
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Analytics permissions and support setup to prepare for meeting with Raissa Borges (DCMC) for the monthly dashboard.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore worked meeting minutes module.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up meetings for next week to discuss Procore open items with the internal team.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Annelia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Lauren Wells, Foster Veazey, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the Safety Training with Gilberto Soto and Jorge Mercado by (DCMC). Meeting with Raissa Borges (DCMC) review the Genera Dashboard. Make the report to Victor Rodriguez (GENERA).
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review and Inspection of trailers in Dueñas Trailer yard with Harry del Valle (DCMC) and Daniel Dueñas, (Dueñas Trailers).
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Train in Health and Safety Genera programs to Rafael Pabon and Eugene Cellentani CDMSMITH. Coordinate Costa Sur Power Plant jobs to Sargent & Lundy Construction Team.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting to discuss Procore Project weekly discussion. Participants: Gabriel Perez (CDM), Lauren Wells (DCMC), Frankyln Colmenares (CSA).
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Genera Project Management team for BESS and Peaker project. Participants: Carlos Palomares (CDM), Gabriel Perez (CDM)
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO catch up call to discuss PMO management status, lean management training, Procore financials status, Tempest. Participants: Mark Merritt, Mike Merritt, Anneilia Holton, Gilberto Sucre, Lauren Wells, Ada Diaz (DCMC).
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting to discuss Procore folder and subfolder add ons for the project divided by site specifically to include the community engagement documents. Participants: Lauren Wells and Paola Arroyo (DCMC).
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Participated in a meeting focused on the RFP scoring methodology and evaluation criteria. Engaged in a detailed discussion on how to structure the evaluation framework to ensure fairness, transparency, and alignment with procurement best practices. Reviewed scoring ranges, weighting of technical versus cost components, and approaches to evaluating qualifications, experience, and value. Genera: Ernesto Martinez and Jesús Cintrón. CDMSmith: Rafa Pabón. DCMC: Saúl Falcón
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in the weekly DCMC coordination meeting to prepare the client briefing for Genera. The team discussed and aligned on key topics, including grant management, cash flow status, procurement activities, technology initiatives, and other ongoing projects. Contributed updates and insights on ongoing BESS and Peakers projects to support a cohesive and well-informed presentation to the client. DCMC Team: Mark Merritt, D'Alexzander González, Roberto Bosch, Marc Maceira, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: MZL Shellsea Maysonet, Johanna Díaz, and Integrum Carlos González and Ginnell Torres
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP -Completed the revision of the RFP Exhibits, specifically Exhibits G, H, and I, by updating the content, layout, and formatting to enhance clarity, consistency, and usability for prospective respondents. Additionally, conducted a thorough review and edit of the full RFP package to ensure all dates, references, and cross-referenced sections were accurate and aligned with the final solicitation requirements.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Prepared Attachment 4 for the BESS Installation at Cambalache procurement. Developed and formatted the document to align with the Scope of Work, project requirements, and procurement standards. Ensured clarity, consistency, and accuracy to facilitate bidder understanding and compliance. Shared with Franklyn Colmenares (CDMSmith), Joel Pantojas, Ernesto Martinez (Genera) and Saul Falcon (DCMC)
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Continued revising the RFP Exhibits, specifically Exhibits C, D, and F, by updating content, layout, and formatting to enhance clarity, consistency, and ease of use for prospective respondents. These updates are intended to support a more transparent and user-friendly solicitation package.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Costa Sur Demolition RFP - Continued revising the RFP Exhibits, specifically Exhibits E, E.1 and E.2 by updating content, layout, and formatting to enhance clarity, consistency, and ease of use for prospective respondents. These updates are intended to support a more transparent and user-friendly solicitation package.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.25 |  | 184 | 414 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Testing and Error Identification in Financial Tracker: Continued rigorous testing of the Genera Connect Financial Tracker, with a particular focus on the Financial Tracker report. Through continuous testing and detailed review of errors, identified specific line entries that were interrupting the import process. This step is crucial for ensuring the accuracy and reliability of the financial data within the system.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordination for Financial Tracker Demonstration: Coordinated a meeting to demonstrate the Genera Connect Financial Tracker to Jose Roque and Dimaries Gonzalez from Genera PR's financial team. The demonstration aims to showcase the tracker’s functionalities and address any questions or concerns from the financial team.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly DCMC Pre-Meeting: Participated in the weekly DCMC pre-meeting to discuss status updates of various projects in preparation for the weekly client meeting. Attendees from DCMC included Mark Merritt, D'Alexander Gonzalez, Victor Maldonado, Shellsea Maysonet, Esther Rohena, Rafael Calderon, Pedro Cabrera, Eisha Mercader, Saul Falcon, Ginell Torres, and Marc Maceira. Representatives from Integrum were Carlos Gonzalez and Keyla Sierra.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field house keeping and move materials to continue dismantling areas Day 3
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Manuely Concepcion (CDMSmith) to review the project progress schedule which outlines the tasks, and resources required to complete it. Jobsite Visit with Gabriel Pérez (CDMSmith) to evaluate the project progress and issues to ensure that it is progressing as planned.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Carirma Sanchez (HOMECA) to review the pending project RFI's and discuss project progress schedule tasks, sequences, and resources. Preparing a letter in response to a Time Extension letter requested by HOMECA.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Danny Duenas (Duenas Trailer Owner), Jean Pierre Menay (DCMC) & Harry Del Valle (DCMC). Topics discussed - Verify the amounts & Size of Office Trailers available for next projects.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued on Procore, reviewing RFPs documents for the Yabucoa Gas Turbine project. Looking for possibles discrepancies and/or any information missing Working with spreadsheets for inventory of materials in the trailers office. Quoting materials for new Offices Trailer.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of documents submitted by the RGE contractor, related to safety manual.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation and preparation of the presentation that is being implemented for the entry requirements of new contractors to the Cambalache site.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -meeting with Jean Pierre Menay (DCMC) where the safety talk for the contractor is discussed.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review of RFP 4826 Attachment A – Administrative Requirements Attachment B, Intent to Bid and Q&A Form, Attachment C – Master Services Contract & attachments.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Continued developing and drafting project and submittal process responsibility matrix to determine responsible on each task for effective coordination.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed and followed up Procore documentation and updates for the Cambalache project.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Continued Procore construction management platform project tools trainings and learning to ensure all project documentation and workflow is managed properly with contractors.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed a draft for weekly report format to apply for project weekly reporting and document important information.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed project electrical drawing set to quantify scope of work and materials.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Pre-Meeting with participation from DCMC: D' Alexzander Gonzalez, Rick Patterson, Rafael Calderon, Eisha Mercader, Victor Maldonado, Glorimel Torrado, Marc Maceira, Danny Martinez, Annelia Holton, Rick Patterson, Christian Cruz, Rafael Cordero, Sheila Torres and Roberto Bosch; Integrum Keylamerari Sierra, Jorge Aponte, Carlos Gonzalez, to discuss draft presentation priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process before presenting to Genera PR.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing the documents related to Black and Veatch Fuel Efficiency List for Genera Efficiency Projects table with comments.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with critical component tracker table, made correction of MOR cost that was not aligned to estimate cost that will be presented to FEMA. Verify in Asset Suite if the following requisition has been assigned a PO# for requisition # 285665, 286708, 287688, 287173, 287797, and 285838. Reviewing email send by Sulinnette Perez of Genera in regard of process RFP 220904 that was canceled but in Asset Suite was found a submittal transmittal of this RFP with the PO# 104413, Genera procurement needs to confirm if this RFP is canceled or is pending award. Reviewing projects that has been purchase with a PO if was awarded with an NTP.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with critical component tracker in updating vendor information on table and delivery dates. Working with Pedro Cabrera of DCMC to verify resolution of PREB for (66) that should be included as NME but only 24 was identify as part of NME and 3 are not part of DCMC contract.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were CR 0204 to CR 0227, AE 01 016 to AE 01 050, AD 034 to AD 038, AK 023 to AK 037.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Aguirre warehouse analyzing and preparing the count sheets that will be used for inventory.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with Milton Flores, Hernan Machado (DCMC) and warehouses personnel to discuss any issue identified the previous day and to emphasize the importance of accurately entering data into the TEMPEST system. Additionally, best practices and corrective actions were reviewed to ensure consistent and reliable data management moving forward.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦DR 4339 – Hurricane – Maria- at Aguirre warehouse identifying discrepancies and investigating variances to ensure proper inventory control. This process helps maintain accuracy in stock levels, supports operational efficiency, and allows for timely corrective actions when inconsistencies are found. Today we work with locations CR 0204 to CR 0227.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse performing recounts to ensure that the inventory has been recorded accurately. This step is essential to validate the initial counts, correct any discrepancies, and maintain the integrity of the inventory data.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducting cycle counts for the designated locations schedule for today. This process is part of our ongoing effort to maintain accurate inventory records and ensure alignment with the system data.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Continue develop a Matrix of NEPR resolution for NME identify under FY2025 NME Projects to determine in witch FEMA projects was included.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria.Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consultant Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Continue develop a Matrix of NEPR resolution for NME identify under FY2025 NME Projects to determine in witch FEMA projects was included.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Develop a Matrix of NEPR resolution for NME identify under FY2025 NME Projects to determine in witch FEMA projects was included.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - 4339_9510 BESS Review document Procore Folder 100- Drawings that manage and archive project drawings and revisions to ensure that team members always have access to the most current drawing set.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Genera Cambalache BESS: RFP-4826 Construction Schedule created to mitigate the projects risks, ensure on time delivery and maintain the highest standards of quality and safety.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11- DR 4339 - Hurricane Maria. 4339_9510 BESS Design of attendance sheet format for meetings to be used for documentation, tracking progress, and ensuring accountability.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-DR 4339 - Hurricane Maria. 4339_9510 BESS Design of site inspection sheet format to ensure consistent documentation, and record key findings from a visual inspection of a job site.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and move materials to continue dismantling areas, Homeca fixed the mesh on the storm water drain Day 3
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #90232782 for TO#1 Sept 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, HOMECA, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293410-11 for TO#1 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, HOMECA, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Continue working with Compliance Review CDM Smith Invoice #293410-11 for TO#1 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team)
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Contractual high-level Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla contract reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes and client's financial needs. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczynski.), and DCMC (Rafael Calderon)
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD034 to AD038 to begin the cycle counts.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK023 to AK 037
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AK023 to AK 037
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AK023 to AK 037
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AK023 to AK037
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE 01 016 000 TO AE 01 050 000
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE 01 016 000 to AE 01 050 000
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE 01 016 000 TO AE 01 050 00.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 416 and 417.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #416, and 417 from locations AD034 to AD038 for a total of 5,555 pcs.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AD034 to AD038 Cycle Count List # 409.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continuation of BESS Projects Data Management/Jobos/Vega Baja/Palo Seco/Yabucoa. Coordination with Paola Arroyo, Frances Vallejo, and Lauren Wells (DCMC) for Community Outreach to build trust, mitigate negative impacts, and reap long-term benefits for the client and the communities they serve.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control Data Management for BESS Jobos Project File Structure. Coordination and Setup Data for community outreach with DCMC's Paola Arroyo/Lauren Wells/Frances Vallejo to foster goodwill, reduce project delays, and achieve overall success.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue Procore Certification (Project Management as an Owner Representative). Part of the main certifications required by our client.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of recently created Fillable PDF files for field inspections and job safety analysis, among others.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Verify document uploading into new File Structure for Vega Baja project: review of main core tools items to be kept inside the tools.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of final SOP drafts for Schedule, RFI, Inspections and Observations Core Tools at Procore.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Creating forms' drafts to incorporate in Procore Inspection Core Tool as Fillable PDF to be populated by contractors and field management staff.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine), Franklyn Colmenares (CSA), Gabriel Perez, German Nunez and Sheila Torres (DCMC) to overview this week's progress on BESS and Peakers; ongoing pending tasks and upcoming scheduled training for Procore users.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339- Prepare excel spreadsheet with Invoice #, Contract #, Vendor information, Amount and CPA. This report was shared with Christian Cruz (Genera) requesting updates with payments for DCMC internal presentation today.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339- Genera Weekly Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and Marc Maceira from DCMC, and Shellsea Maysonet (MZC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review invoices that were cancelled in Adobe pro because Jesús Cintrón was not able to sign. Apparently, Adobe Sign is having issues with the sent for signature feature. Invoices for Sargent & Lundy were prepared for resubmission looking for different ways to edit the document for a better process. Prepare final package for Jesús Cintrón (Genera) signature.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339- Working session with Rafael Calderón (DCMC) to update Pre-intervention tracker for presentation. We also update Power Point presentation with information provided by Christian Cruz (DCMC) about payment.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 |  | 139 | 486.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria create a 2025 annual community outreach plan in Excel. The plan contains the tactics, budget, and KPIs of the project.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Finalize and deliver the document along with the next steps related to optimizing community meetings. The document includes the notes related to the post-community feedback meeting we held yesterday, Thursday. Similarly, some revisions were made to the document that was delivered to Genera Jorge Bracero.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting for the introduction to Procore with DCMC Lauren Wells, Frances Vallejo Rosich and Theresa Perez. Discussed the use of Procore documents for Community Engagement files.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports considering baseline and update scheduling of BESS procurement for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports with comments in necessary requirements included by proponent in RFP considering technical specifications for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Implementing projects safety and security status and updates to the monthly report to help safeguard the well-being of personnel and add to the project’s overall success, sustainability, and successful completion.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Review and gathering information from "BESS & Peakers Weekly Update Call" presentation for reporting purposes.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel from home in Guaynabo to Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria -travel back home in Guaynabo from Aguirre, the purpose of the visit is to support warehouse operations during Mr. Juan Vallejo medical leave.
2025-04-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Making adjustments to the dashboard and share it with Mark Merritt (DCMC) for review and comments.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal review of revised demolition scope of work and reviewed procurement dates for arrive dates of equipment.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed micro grid scope of work for Vieques and Culebra facilities
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM weekly update meeting with Franklyn Colmenares - CSA Group * Vega Baja Diesel Transfer & Frame 5 turbogenerator * Tesla Deliveries advance GSU's & Delays on Batteries - need updated schedule. * RGE Legal review with Francisco Feliu - Genera @ 2pm. * ARG selected for Vega Baja Phase II Installation
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed contractors latest schedule to be compared with Teslas GSU and Batteries delivery in other to prepare for delivery change orders by sites - with Carlos Palomares - CDM Smith.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Drawings Discussion to make a final decision on what role will be responsible for publishing drawings in Procore once they are ready for review. Scheduler/Invoice person? Quality? Site Manager? Attendees German Nunez - Genera, Franklin Colemares - CSA Group, Rafael Pabon CDM Smith, and Lauren Wells & Gilberto Sucre DCMC Partners. In Summary decision is still pending as SME should approve and release drawings for IFC, once that is the case Sargent & Lundy should upload directly to ProCore then Quality person should review accordingly.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Worked on response to Homeca's Schedule Extension Claim, and met with Jose Lopez DCMC on project progress update.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluated RFP bid sets for Vega Baja & Costa Sur identified drawings not pertaining to Project Scopes.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed and navigated on project files setup and document transfer after setup for Vega Baja, Cambalache and Costa Sur. Identified missing information or incomplete transfer of files.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Consulted with Sheila Torres - DCMC response letter to Homeca's Time extension request.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Weekly Check-In Meeting Program Update led by Frankly Colmenares - CSA Group with attendees from GENERA, Sargent & Lundy, and DCMC Partners.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Final review of contract language comments from RGE with Jose Robles - RGE, Francisco Feliu - Genera, Franklyn Colmenares - CSA Group and Gilberto Sucre - DCMC. Review and discussed final comments. Francisco Feliu will contact Jose Robles on Wednesday morning to finalized. Expect contract agreement by this Friday.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly Peakers Project Coordination meeting. Meeting attendees were Jesus Cintron, Juan Mendoza (Genera), Rafael Pabon, Kevin Futch (Genera), Franklyn Colmenares. (CDM Smith) and Abraham Velazquez (DCMC)
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Nelson Rosado, Ricardo Pallens, Carlos Palomares, Joaquin Quinoy, Gabriel Perez, Mike Kuczynski, Franklyn Colmenares (Genera), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejando Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Analytics for purpose of sharing with Luis Roman (DCMC) and Theresa Perez(DCMC).
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on drawings review with Luis Roman (DCMC). Discussing how Procore process works.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Gilberto Sucre (DCMC), German Nunez (Genera), Rafa Pabon (CDM Smith), Franklyn Colmenares (CSA) and Luis Roman (DCMC) to discuss how drawings are reviewed and published by who
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) for review of weekly Procore tasks items and to collaborate on any open items.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Liz Fronduto (Procore) for setting up meetings and agendas.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore safety inspections settings.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Peakers Check-In with Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Jesus Cintron (Genera), Mike Kuczynski (Sargent & Lundy), Franklyn Colmenares (CSA) and others. My part was to update on Procore items.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Franklyn Colmenares (CSA) to discuss Procore drawings and settings.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for RFI's to create a quick look for usage and overdue items.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items for submittals for Vega Baja.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks in Teams for our Procore team to discuss.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Make Emergency Management Guidelines for contractor. Review the special condition for site. Continuing meeting with Frances Vallejo, Andres Concepcion, Jose Lopez and Harry del Valle (DCMC) about all trailer's equipment in all Genera Sites.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Make Emergency Management Guidelines for contractor. Review the special condition for site. Meeting with Frances Vallejo, Andres Concepcion, Jose Lopez and Harry del Valle (DCMC) about all trailer's equipment in all Genera Sites.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Call with Osvaldo de Jesus (GENERA) about all projects. Meeting and Review Palo Seco Site, about Vega Baja Site and Palo Seco site with Javier Centeno and Osvaldo de Jesus (GENERA). Make the Safety and Security Presentation by Vega Baja and Cambalache Site.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Cambalache update meeting with Andres Concepcion and Gilberto Sucre (DCMC)
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended BESS and Peakers Check In meetings with the PMO Team to discuss overall update for the projects. Participants: Gabriel Perez (CDM), German Ojeda (Genera), Jesus Cintron (Genera), Lauren Wells (DCMC), Abraham Velazquez (DCMC), Rafael Calderon (DCMC), Franklyn Colmenares (CSA), Gilberto Sucre (DCMC)
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Ivan Baez (Genera) to discuss community engagement strategy, Paola Arroyo (DCMC) feedback and next steps.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Maria Sanchez Bras, and Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Marc Maceira, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Carlos González and Ginnell Torres
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - RFP 231175 - Worked on the development of the second round of Q&A responses for the active procurement process. Reviewed and organized the questions submitted by bidders, ensuring clarity and proper categorization. Formatted the inquiries to align with internal response protocols and shared them with the appropriate technical teams for input (S&L and CDM Smith).
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed the draft letter sent by Gerardo Sucre (DCMC) for accuracy, clarity, and compliance with the terms of the Homeca Master Services Agreement. Revised the letter to ensure alignment with contractual requirements, proper referencing of applicable provisions, and consistency with Genera’s internal standards. After completing the necessary edits, returned the revised version to Gerardo Sucre for finalization.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczinski.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Engaged in a detailed conversation with Winnie Irizarry (Genera) regarding the roadblocks Genera has been encountering with COR3 and Vivienda. Discussed how delays, regulatory constraints, and administrative hurdles are impacting Genera’s projects, cash flow, and overall ability to meet project milestones.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed the letter received from PREPA regarding the ER1 Cost Share Program to assess its implications for Genera’s funding strategy and project execution. Subsequently discussed the proposed approach and response strategy with Jesús Cintrón (Genera) to confirm alignment on messaging, next steps, and coordination with broader cost share and reimbursement efforts.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Preparation of Weekly Status Report: Prepared the weekly status report for the Genera PR client meeting, detailing the latest updates and progress on the Genera Connect Financial Tracker and Time Tracker projects. This report aimed to provide a clear and concise overview of the current status and any significant developments.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and move materials to continue dismantling areas Day 4 Homeca removed Lead Container to dispose on Ponce PR.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja project documentation evaluation. Homeca Recycling submitted all the manifests for the ACM and Lead, and we need to check compliance with the General's environmental program.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - meeting with Harry Del Valle, Jean Pierre Menay, Frances Vallejo, and Andres Concepcion (DCMC Partners) to discuss and go over the job site office trailer consumables list.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Morning meeting with Thessy Perez (DCMC), PROCORE document control, to establish document QC/QA for the Vega Baja project. Morning call with Gilberto Sucre (DCMC) for project manpower status discussion and course of action.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Cambalache project. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for standardize Office Trailers Materials Attendees, Frances Vallejo (DCMC), Jose M Lopez (DCMC), Andres Concepcion (DCMC) & Harry Del Valle (DCMC). Topics discussed - Standardize supplies material & equipment for Office Trailers. Stablished procedures & amounts to orders materials.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 |  | 167 | 459.25 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Cambalache project. Preparing spreadsheets for inventory of materials in the trailers office. Resumed quoting materials for sites Office Trailer.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of RFP No. 4736 (ATTACHMENT A)
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RGE Contractor Safety Plan Evaluation.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of RFP 4826 Exhibit L (Pipe Relocation) and exhibit M (Electrical Engineering & Design)
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of RFP 4826 Annex K Civil and Structural.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed RFI items in spreadsheet for designer (Robert Molner - Sargent and Lundy) evaluation and comments regarding design progress (Bid Addendum) set DCMC questions.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Review of Testing procedures on Technical Specifications for planning and coordination of future material testing activities.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed contractor responsibilities and scope of work in the project draft contract MSA (Master Services Agreement) for RG Engineering.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Review of Cambalache project Technical Specifications documents for site coordination and contractor management purposes.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Review of Technical Specifications Quality Control section for planning and coordination of inspection activities.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed the Contractor (RG Engineering) draft Master Service Agreement (MSA) Task Order Schedule section to organize scheduling requirements in project by contract.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Internal Meeting with Harry Del Valle, Jose Lopez, Jean Pierre Menay and Frances Vallejo (DCMC Partners) for site office trailers equipment and supplies coordination.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Review of PREB funding approved versus Federal funding for NME projects, send email to Rafael Torres of Malnat for status of Air Heater Basket of Palo Seco, in response the delivery is schedule to be received during this week. Send email to Anthony Vega of Genera informing the delivery of this critical components that will be received during this week.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing the NME projects versus Federal project they are a total of (39) project approved by the PREB which (3) does not have budget for FY2025 and they are (26) Federal Funding Project which (1) is already at the Peaker project and was found that (1) project that still need to be determe for a total of (66) projects.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, D' Alexzander Gonzalez, Paul Brown, Jose Ralat, Rafael Calderon, Esther Rohena, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Keylamerari Siera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing RFP 4302 with Contract #104413 that is still open with a vendor that recently submitted a submittal for review in regard of HP Vertical Motors for CCWP and Bearing for Costa Sur and Aguirre plant. Searching for a Fuel leak detection system that can be integrated wireless for Cambalache fuel system. Contacted Freddie Gongalez of Emerson to verify for a model or recommendation of a system that is wireless, and it can detect hydrocarbon in a double containment fuel pipe, he will send a model of an equipment that can be recommended for the Cambalache Fuel Detection System. Pedro Cabrera of DCMC send an email related to Overhead Crane where Jorge Sanchez of Genera recommend replacing the crane with a same capacity, but this is good idea, but it may bring issue with a company that will replace the crane because they will not sell a crane that will use at 100% capacity it may require a more capacity crane but this affect the foundation.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- meeting held via TEAMS with Ms. Maria Sanchez of Genera, and staff of DCMC to discuss the weekly progress of the projects.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦DR 4339 – Hurricane – Maria- at Aguirre warehouse identifying discrepancies and investigating variances to ensure proper inventory control. This process helps maintain accuracy in stock levels, supports operational efficiency, and allows for timely corrective actions when inconsistencies are found. Today we work with locations CR 0228 to CR 0251.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report on all warehouses for Mr. Anthony Vega from Genera PR. This report includes the number of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. Locations that were worked on across the different warehouse were CR 0228 to CR 0251, A01 051 to A01 086, AD 039 to AD 044, AK 038 to AK 045
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse performing recounts to ensure that the inventory has been recorded accurately. This step is essential to validate the initial counts, correct any discrepancies, and maintain the integrity of the inventory data.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducting cycle counts for the designated locations schedule for today. This process is part of our ongoing effort to maintain accurate inventory records and ensure alignment with the system data. Today locations are CR 0228 to CR 0215.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Aguirre warehouse analyzing and preparing the count sheets that will be used for inventory.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with Hernan Machado, Milton Flores and other warehouse personnel from DCMC to discuss any issue identified the previous week and to emphasize the importance of accurately entering data into the TEMPEST system. We also discussed the importance of recording all maximum and minimum stock levels for the daily report.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continuing with the cycle count of locations CR 0228 to Cr 0251.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Continue develop a Matrix of NEPR resolution for NME identify under FY2025 NME Projects to determine in witch FEMA projects was included. Found components included in project 662957.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez Bras,, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Continue develop a Matrix of NEPR resolution for NME identify under FY2025 NME Projects to determine in witch FEMA projects was included. . Found components included in project 669815.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting to discuss NME project under FY-2025 from DCMC: Pedro Cabrera and Genera Jorge Sanchez to discuss data shared by GENERA-PR regarding to NME projects.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Made adjustment to the report of NME PREB Resolution after Mark Merritt (DCMC) input.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Develop a report of current actual cost of Critical Components to amendment FEMA project purpose.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100- 6. Appendix D.1- Design Drawings Architectural plans.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100-8._Appendix_D.3-_Demolition_Specifications
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Project Review Reporting send by Andres Concepcion from DCMC.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Revised GENERA CAMBALACHE RECOMMENDED PLANNING ACTIVITIES send by Carlos De Jesus from DCMC.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 4 Homeca remove steal 20 CY container and bought a clean one.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #902329030 for TO#1 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Continue working with Compliance Review CDM Smith Invoice #902329030 for TO#1 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (All DCMC Genera Team), From Genera: Maria Sanchez and Alejandro Maymi).
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 427 and 428.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK038 to AK045
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AK038 to AK045
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AK038 to AK 045
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AK038 to AK045
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AK038 to AK045
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE 01 051 000 to AE 01 086 000.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE 01 051 000 to AE 01 086 000
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE 01 051 000 to AE 01 086 000.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD039 to AD044 to begin the cycle counts.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AD039 to AD044 Cycle Count List # 426.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #427 and 428 from locations AD039 to AD044 for a total of 10,491pcs.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - BESS Yabucoa/Palo Seco Data Management File Structure for PEAKERS Daguao Project to provide an organized view of all of the project's documents.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 151 | 528.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control -Data Management Coordination with Vega Baja Field Personnel/Data Management File Structure BESS Projects San Juan/Yabucoa/Palo Seco/Vega Baja/Procore Data Coordination of Project Submittals with Lauren Wells (DCMC)/Luis Roman (DCMC)
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Check-in Meeting with Lauren Wells (Lemoine) to discuss weekly progress of ongoing tasks: SOPs for Procore Users, Training set-up and platform issues with users.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Finish SOP drafts for Drawing and Inspections Tools on Procore Platform; guidance for users on creating inspections and uploading drawings.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Lauren Wells (Lemoine), Franklyn Colmenares (CSA), Gilberto Sucre (DCMC), Rafael Pabon (CDM Smith) and German Nunez (Genera PR) to discuss the Drawings Publishing process, persons in charge and QC of other Procore documentation procedures.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Finish SOP draft for Observations Tool on Procore Platform: users guidance to create Observations and the different types of forms available.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – BESS Check-in Meeting hosted by Gabriel Perez (CDM Smith). Discussed project site issues, Procore Onboarding and SOP status, drawings and design-related topics and more.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform QC of available Fillable PDF forms on Procore and configuring new forms to be uploaded for users.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Peakers Check-in Meeting hosted by Carlos Palomares (CDM Smith). Discussed the minute from last meeting including project site issues, contracting status and others.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.75 |  | 149 | 111.75 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 ¦ Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, Mark Merritt, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado. Also, Shellsea Maysonet (MZC); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.25 |  | 149 | 186.25 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#2, Invoice #18334032_Jan2025. Continue with deliverables review to complete the compliance review. Prepare final package and invoice for Jesús Cintrón (Genera) signature. Send the invoice for signature and update excel Pre-Intervention tracker.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Update Pre Intervention tracker for meeting at Genera. I change Tesla slide with payment quantities that were updated on Friday. Also, I change deltas on the presentation and create the final Power Point. This was shared with Rafael Calderón (DCMC) for final review.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#2, Invoice #18334032_Jan2025. Start deliverables review for compliance review. Contractor sent a link with documents, I started reviewing documents that matches with invoice TO2.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.25 |  | 149 | 37.25 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare final package for CPA, Sargent and Lundy_TO1_Inv18334031_Jan2025. Backup documentation and signed invoice was sent to Franklyn Colmenares and Manuely Concepción (CDM). Also, I prepare an email to contractor to share final invoice signed.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Finish working on the annual Community Outreach Plan detailed by site. Also, prepare to present it at the meeting with the Public Affairs team
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Work on the Fact Sheet for Genera PR of the BESS project focused on the Cambalache, Arecibo site.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Corporate Affairs Meeting with Genera’s Team: Ivan Baez, Jorge Bracero and Rafael Rodríguez Ema
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams Meeting with DCMC, Genera, and CDM Smith personnel: Jesus M. Cintron Rivera; Juan Mendoza; Rafael Pabon; Kevin Futch; Franklyn Colmenares; Miguel Del Valle; Carlos Palomares; Ricardo Pallens; Francisco Santos Rivera; Alejandro Maymi Ronda; Warehouse; Mark Merritt, Alexzander Gonzalez; Frances Vallejo Rosich (DCMC); Sarahi Medina Nieves. The meeting was call Peakers Check In.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Work on the Fact Sheet for Genera PR of the BESS project focused on the Cambalache, Arecibo site.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting about the Website BESS Peakers with the Genera Team: Alex Valdes Diaz and Jorge Bracero.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Work and deliver the Fact Sheet for Genera PR of the BESS project focused on the Cambalache, Arecibo site.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Kroma and Genera Weekly Meeting in the meeting was the Genera's PR Team: Ivan Baez, Jorge Bracero and Rafael Rodriguez. In the meeting was the Kroma team: Amarilys Torres and Victoria Flores
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams with DCMC Frances Vallejo, Rafael Calderon, Luis Roman, D'Alexzander Gonzalez, Sheila Torres Sargent & Lundy: Miguel Del Valle, Vincent Skochdopole Genera: Jorge Bracero CDM Smith: Carlos Palomares, Franklyn Colmenares, Rafael Pabon Lemoine: Lauren Wells. The project was about BEES with Genera.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports with comments considering specifications of RFP contract baseline and update scheduling for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create planning reports with comments in necessary requirements RFP considering technical specifications and drawings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: DCMC: Abraham Velazquez, Paola Arroyo, Frances Vallejo, Rafael Calderon, Sheila Torres, Luis Roman, D'Alexzander Gonzalez S&L: Miguel Del Valle Genera: German Nunez, CDM Smith: Enrique Laya, Carlos Palomares, Rafael Pabon Lemoine: Lauren Wells, Foster Veazey
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Carlos Palomares from CDM Smith to discuss the status and budget of active projects, discuss progress and update finance on monthly report.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue overseeing the management and modification of relationships between tables in Power BI to ensure the timely delivery of the final report.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Grant Management team from DCMC (D'Alexander Gonzalez, Esther Rohena and Jose Ralat) and DCMC Frances Vallejo for dashboard report review, comments and feedback from Grant Management perspective.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 122 | 183 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing projects budget and schedule for reporting purposes.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check in Project Needs" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: DCMC: Paola Arroyo, Frances Vallejo, Rafael Calderon, Luis Roman, D'Alexzander Gonzalez, Sheila Torres Sargent & Lundy: Miguel Del Valle, Vincent Skochdopole Genera: Jorge Bracero CDM Smith: Carlos Palomares, Franklyn Colmenares, Rafael Pabon Lemoine: Lauren Wells
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 regular various site and office visits through the week
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel from home in Guaynabo to Aguirre, the purpose of the visit is to support warehouse operation during Mr. Juan Vallejo medical leave.
2025-04-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.2 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel back home in Guaynabo from Aguirre, the purpose of the visit was to support warehouse operation during Mr. Juan Vallejo medical leave.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 prepared construction PM roles and responsibilities chart, and field sequencing plan
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended meeting to review Peakers documents and RFP German Nunez, Rafael Pabon, Carlos Palomares (CDM Smith)
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up staffing updates highlighted Carlos de Jesus's transition to DCMC and consideration of Sylvia Franco for the Cambalache scheduler position, emphasizing her scheduling strengths. Project staffing timelines revealed ongoing recruitment efforts, notably for Carlos Lopez’s critical components manager role. Training initiatives included the development of SOPs for scheduling and a RACI matrix to clarify roles. Budget discussions underscored overruns for the initial BESS projects, prompting a need for better funding management and proactive alignment with grant management reporting. Attendees from DCMC Mark Merritt, Mike Merritt, Frances Vallejo, Lauren Wells, Ada Diaz, Gilberto Sucre and Foster Veazey.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L, CDM Smith / DCMC Partners Weekly Coordination Meeting. Main topic was the IFC Drawing status for Vega Baja & Cambalache as well as owner's approval process to release IFC. Participants from CDM Smith, Sargent & Lundy and DCMC Partners.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cost vs. Budgets discussions and Schedule updates from contractors vs. Tesla delivery dates coordination - Discussions with Carlos Palomares CDM Smith.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Worked on Quality Assurance Implementation for the Program.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache The RFC Meeting for RGE Cambalache centered on the comprehensive review of the revised value engineering proposal presented by Jose Robles' team, focusing on significant cost savings of $8 million through various engineering adjustments, including redesigns and material changes. The meeting also explored options for schedule acceleration, with investments assessed for reducing project timelines effectively, while highlighting the importance of a detailed 15.2-month schedule for justifying these costs. Additional technical alternatives, including structural options and fire protection systems, were discussed, with a clear emphasis on further evaluations by the Sargent & Lundy, Genera, PM and CM Team. Participants Sargent & Lundy, Genera, CDM Smith & DCMC Partners
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Project Pre-Con activities in preparation to get started and RGE revised proposal review with Andres Concepcion DCMC .
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Review and approval response to Homeca's request for time extension.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Temporary Facilities Status and Requirements for Vega Baja, Cambalache and Costa Sur. Discussions with Harry del Valle DCMC Construction Manager.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Discuss Quality Program Development and Implementation discussion with Harry del Valle DCMC Construction Manager.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Daily Update discussion with Jose Lopez - DCMC
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Internal Progress meeting with the DCMC - Andres Concepcion, Luis Damudt, Luis Duque, Jorge Mercado, Carlos de Jesus & Gilberto Sucre.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Review and evaluation of the Value Engineering Revised Scope, Pricing and Schedule for BESS Installation from RG Engineering Inc.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - PMO Proposal prep meeting to discuss the requirements and action items necessary for the upcoming Program Management RFP. Attendees were Foster Veazey, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Ada Diaz (DCMC).
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with DCMC Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt. Discussed update on project, PROCORE training, trailer set-up, schedule for locations, and program management plan update.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)Worked on reviewing SOPs for Procore photo tools that Luis Roman (DCMC) created.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore role matrix.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Luis Roman (DCMC) in regards to review of SOP's for Procore and the process we want to use.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Observation settings to present in next meeting with Andres Concepcion (DCMC).
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to talk about Procore training tracker.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on adding users to a new Procore project for the purpose of having Tesla on the meeting minutes that came from that project, which is a combined BESS & Peakers updates.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences. Reviewing emails from Theresa Perez (DCMC) and Jose Lopez (DCMC).
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financials for project settings for implementation.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)worked on Procore Tools RACI matrix to help define what Roles are using which tools, per Andres Concepcion (DCMC).
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Andres Concepcion (DCMC) to discuss Quality observations in Procore.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore RFI reports for tracking overdue items.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 25-145003 | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Lauren Wells, Foster Veazey, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site jobs make by Homeca Recycling. Manage the Health and Safety issues in site to safeguard the well-being of workers, protect the environment, and ensure safe operations.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Call with Osvaldo de Jesus (GENERA) about all projects. Continued site Inspection in Vega Baja Site to identify and mitigate risks to prevent accidents, injuries, and illnesses identifying and mitigating risks before they can cause harm.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria : Call with Osvaldo de Jesus (GENERA) about all projects. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended staffing call with Mike Merritt and Nyah Medina (DCMC) to discuss staffing update for the PMO.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch Up call with Mark Merritt, Mike Merritt, Anneilia Holton, Gilberto Sucre, Foster Veazey and Lauren Wells (DCMC). Discussed project update, job offers, PROCORE training, trailer set-up, and program management plan update.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jesus Cintron (Genera) to discuss PMO update.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria -Prepared for the weekly BESS and Peakers catch-up call by reviewing and updating the project tracking spreadsheet. Incorporated feedback and updates received on 04/28 from the Genera procurement team, including changes to documentation status, and contractor communications. Ensured the tracker reflected accurate, real-time information to support productive discussion, alignment across teams, and timely follow-up during the coordination meeting.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Held discussions with Ricardo Pallens and Cristina Ribas (Genera) regarding the FOMB RFP packages, focusing on content, compliance considerations, and ensuring the completeness of documentation from the Procurement team. Subsequently met with Angelina Minier (Genera) to review and align on the P3A RFP packages, with the same objective of confirming all required materials were properly addressed and ready for submission. These conversations aimed to support the strategic development and timely release of both sets of procurement documents while maintaining consistency and adherence to internal standards.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed the FOMB Coordination SOP shared by Cristina Ribas (Genera) to ensure understanding of updated coordination requirements and compliance expectations. Additionally, reviewed the FOMB and P3A Contract Review Spreadsheet provided by Angelina Minier (Genera), identifying key updates and requirements. Based on these reviews, updated the BESS and Peakers RFP documents to incorporate necessary revisions, ensuring alignment with oversight processes and contractual standards.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Discussed the letter received from PREPA regarding the ER1 Cost Share Program with Jose Ralat (DCMC) Developed a draft response addressing the key points raised, ensuring alignment with contractual obligations and program requirements. Shared the draft with Jose Ralat, D'Alexzander Gonzalez (DCMC) for finalization.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Created and completed Attachment 4 for RFP 4898 BESS Installation at Vega Baja and RFP 4826 BESS Installation at Cambalache ensuring that the content aligned with project requirements, solicitation guidelines, and internal standards. Carefully formatted and reviewed the document for accuracy and consistency before circulating it to Jesús Cintrón (Genera) for review and signature.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Discussed the requirements for preparing Justification Memos to support the time extensions needed for the EHSS, Jaca & Sierra, and Javier Bidot contracts associated with the BESS and Peakers projects.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Deployment Strategy Discussion and Testing Preparation: - Discussed with Aldwin Pagán from Integrum the deployment strategy for making the Genera Connect Financial Tracker and Time Tracker applications available to Genera PR employees. This included planning the rollout process and ensuring all necessary steps are in place for a smooth transition. - Prepared additional testing scenarios to ensure the Genera Connect Time Tracker application can handle the expected load from Genera PR employee usage. This will involve emulating typical usage patterns to validate the application's performance and reliability under real-world conditions.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and move materials to continue dismantling areas Day 5 acetylene works are being completed on generator 1.1
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Meeting with S&L, Kuczynski, Mike, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDMSmith), Andres Concepcion, Gilberto Sucre from DCMC Partners to discuss the BESS IFC design delivery status.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Prepared the Agenda for the weekly progress meeting for the Vega Baja Site to help discuss project issues and improve communication across the site team.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Weekly project meeting with HOMECA representatives Carirma Sanchez and Eduardo Ramos. Project Schedule and progress discussion to mitigate risks, optimize resource allocation, and achieve project objectives effectively.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Meeting minutes built, revised, and distributed to Gilberto Sucre, Jaime Pesquera (DCMC Partners) & Noel Soler (CDM Smith).
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Cambalache project. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for discussed standardization on Office Trailers Materials Request Attendees, Gilberto Sucre (DCMC), & Harry Del Valle (DCMC). Topics discussed - Report agreement between projects managers to Standardize the request for supplies material & equipment for Office Trailers.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue Working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Cambalache project. Preparing spreadsheets for inventory of materials in the trailers office. Resumed quoting materials for sites Office Trailer.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Safety issues are coordinated prior to the start of the project with Andres Concepcion (DCMC) regarding compliance requirements by the contractor.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued evaluation of RGE Contractor Safety Plan.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of evacuation plans and confirmation and management of contacts in case of emergency.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Weekly Internal Meeting with DCMC teams Gilberto Sucre, Andres Concepcion, Luis Damudt , Luis Duque and Carlos de Jesus to discuss plans, identify potential issues, and keep the project on track.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of RFP No. 4736 (ATTACHMENT A)
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Reviewed Cambalache contractor (RG Engineering) revised pricing proposal as part of pre contract activities.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Developed a pre-mobilization plan for Cambalache project to begin initial discussions with contractor (RG Engineering)
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Design drawings QA/QC meeting with Sargent Lundy (Mike Kuczynski, Robert Molner), CDM Smith (Gabriel Perez, Enrique Laya), CSA (Franklyn Colmenares), RG Engineering (Jose Robles) to discuss design management and design progress.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Cambalache Site DCMC Team update meeting with Gilberto Sucre, Carlos De Jesus, Luis Damudt and Luis Duque for project updates and concurrence follow up on project actions.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Cambalache RFC meeting with Sargent Lundy (Mike Kucsynski, Robert Molner), CDM Smith (Gabriel Perez), CSA (Franklyn Colmenares), RG Engineering (Jose Robles) for pricing proposal discussion as part of pre contract.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Meeting at post office to process TSA's TWIC credentials to obtain security clearance to work on Cambalache power plant.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - meeting with DCMC Procore Team (Lauren Wells and Luis Roman) to discuss the observation tools application during the construction.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR -Cambalache contractor (RG Engineering) project pricing proposal and acceleration schedule review to generate comments as part of the pre contract process.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Provide feedback to new PMO dashboard, meet with Raissa Torres of DCMC in regard of new PMO dashboard recommendation for Genera presentation.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue with Federal Funding project NME that was assigned to Genera evaluating cost assigned to each project, email was send to Sulinnette Perez of Genera to identify the procurement stage of (24) Federal funding project. These projects will be under an NME project for execution but they are (26) additional project that are not assigned to DCMC.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with the verification of PREB NME projects versus Fedeal Funding projects by resolution, using a SharePoint table send by Jorge Sanchez of Genera to review status of federal project that has a status of procurement, planning, awarded, issued, execution, or closed and using Asset Suite to verify if projects has been awarded a PO#, with this information we be reviewing our critical components tracker to evaluate if status required to be updated with information provided by Jorge.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing DI 1229682 and PW 10702 for Bifurcate Boiler Tubes for unit 5 for cost verification.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continuing with the cycle count of designated inventory locations, covering CR 0252 to CR 0265. This task supports the verification and reconciliation of physical inventory against system records to ensure accuracy and compliance.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria - at Aguirre warehouse, identifying discrepancies and investigating variances to ensure effective inventory control. This process supports inventory accuracy, operational efficiency, and timely corrective action when inconsistencies are detected. Today's work focused on locations CR 0252 to CR 0265.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-job briefing with Giovanni Taffanelli, Hernan Machado and other warehouse personnel from DCMC to discuss any issue identified the previous day and the importance of recording all maximum and minimum stock levels for the daily report.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducting recount at the Aguirre warehouse to ensure inventory accuracy. This step is critical for validating initial counts, addressing discrepancies, and preserving the integrity of the inventory records.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, preparing comprehensives report covering all warehouses for Mr. Anthony Vega from Genera PR. The report includes data on the numbers of catalogs, locations, units counted, cost, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each warehouse. The locations worked on across the various warehouses include CR 0252 to CR 0265, AD 045 to AD 050, AA 0008 to AA 0025, AK 046 to AK 053.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performing cycle counts for the scheduled locations assigned for today. Today locations are from CR 0252 to CR 0265. This effort supports the ongoing initiative to maintain accurate inventory records and ensure consistency with system data.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducting analysis and preparing inventory counts sheets at the Aguirre warehouse.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Updating CCL Tracker : Using the available information, such as the Cost Estimate, Scope of Work, RFP, Contracts, and Invoices for NME and Critical Components, I have developed a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Discus with GENERA-PR Joaquin Quinoy NME Projects that will be funded by Federal Funds.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Revision Proyectos Federales Status meeting with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz, and Roberto Bosch; from MZC Shellsea Maysonet; from Genera-PR Joaquin Quinoy, to discuss priorities and deliverables, status updates, identify next steps for projects under Federal Grant.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Reviewing priorities, deliverables, and the status of projects under federal funding for the meeting with GENERA-PR Joaquin Quinoy.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Procedure to obtain the Qualifying Transportation Worker Identification Credential(TWIC) for entry to the Cambalache Project Site.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100- Preliminary Drawings.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- I Supervised the Contractor Homeca. I created RFI's and worked with RFI's that needed my attention, I also read multiple submittals, I kept up the submittals that needed my attention for today or were due today. I received various phone calls from the project personnel (from Jean Menay DCMC, Gilberto Soto DCMC & Jose Lopez Linares DCMC). I also answered multiple emails, read multiple emails I needed to in order to keep up with all the communications and updated throughout the day.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Weekly meeting with contractor Homeca (attended the meeting: Carirma Sanchez, from Homeca, Eduardo Ramos-Homeca, Nelson Soler, CDM Smith, Enrique Laya CDM Smith, Franklyn Colmenares CSA Group, Gabriel Perez Sepulveda CSA Group, Manuelli Concepcion CDM Smith, Jose Lopez Linares, DCMC, Gilberto Sucre DCMC, Gilberto Soto, Jean Menay, DCMC). Supervised the Contractor Homeca. I created RFI's and worked with RFI's that needed my attention, I also read multiple submittals, I worked the submittals that needed my attention for today. I read & answered emails I needed to in order to keep up with all the communications and updated throughout the day.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 5 acetylene works are being completed on generator 1.1
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 164 | 656 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA virtual meeting with project management Sargent and Lundy Team. Contract 106761 and Deliverable Schedule review based contract development. Reviewing change order tracker and justification narrative for Genera final determination. Meeting between Sargent & Lundy (Vincent Skochdopole) and DCMC (Rafael Calderon).
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK046 to AK053
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AK046 to AK053
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AK046 to AK053
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AK 046 to AK053
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AK046 to AK053
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 00 008 000 to AA 00 025 000
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 00 008 000 to AA 00 025 000.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 00 008 000 to AA 00 025 000
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 436, 437 and 438.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #436, 437 and 438 from locations AD045 to AD050 for a total of 10,769 pcs.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AD045 to AD050 Cycle Count List # 431.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD045 to AD050 to begin the cycle counts.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control/Data Management File Structure Setup PEAKERS Jobos/San Juan/Yabucoa to provide an organized view of all of the project's documents.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control/Data Management File Structure Setup PEAKERS Daguao/Jobos to provide an organized view of all of the project's documents.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 151 | 604 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the implementation of Observations Tool for different project sites and verify staff domain of Procore platform.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on new Internal SOPs for PMO users on Procore Platform due to different roles and procedures on documentation and tasks.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Documents Tool for Contractual Documents related to project scope, time and cost, and other contractual requirements per project site.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) and site manager Andres Concepcion (DCMC) to overview the integration of core tools at full capability for the Cambalache Project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review change orders sent by Lauren Wells (Lemoine) that were developed in Procore platform using contract model. Corrections were made on the document suggesting our idea of how it should look according to the original form.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 - Pre Intervention Review for Black & Veatch Puerto Rico, PSC., Contract #2024-G00207, TO#7, Invoice #1. Continue Pre Intervention invoice, prepare Compliance Sampling tab to request deliverables. organize and review RFI, send request by email and update Pre Intervention tracker.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review Sargent and Lundy invoices to update José Ralat (DCMC) report and share with him new information. For this report there are two new invoices pending for Genera signature (Inv. 18322772 and 18334036) and still 3 invoices pending for Pre Intervention (18334033, 18334034, 18334035). Invoices information was sent by email.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339_ Hurricane Maria_PW#9510 - Start Pre-Intervention Review for CDM Smith TO02_Oct24_Inv 09. Prepare pre intervention excel document. Review contract and Task Order. Review rates for employees in this invoice and identify discrepancies in numbers.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 149 | 149 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Verify Pre Intervention Tracker and filter for my pending invoices. Create a excel spreadsheet that includes 15 pending invoices that needs my attention. Some are already assigned to me, others are still unassigned but are due. There are a lot of RFI pending for answer, I will follow up on this. During this time, I verify dates, notes, and create a plan to address invoices.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Grant Management ¦ DR 4339 - Hurricane Maria_pw#9510 - Pre Intervention Review for Black & Veatch Puerto Rico, PSC., Contract #2024-G00207, TO#7, Invoice #1. Start reviewing invoice, filling missing information, developing RFI.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare final packages for invoices signed by Jesús Cintrón (Genera). Invoices signed: CDM_TO1_Oct2024_90231861 and S&L_TO2_18334032_January2025. For CDM invoice I requested Kathleen Anderson (CDM) excel backup information that was missing from the final package. For S&L invoice I prepare package and request CPA creation to Franklyn Colmenares (CDM) and Manuely Concepción (CDM). Also review Pre Intervention tracker and update CPA invoice number for S&L_TO1_18334031 and process for CDM_TO1_Oct and S&L_TO2_Jan.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 139 | 556 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Update list with data on community leaders in the general matrix. Enter and update the Google Earth map of Arecibo's community leader data.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Osvaldo Rojas, external consultant LGAStrategies and Jorge Bracero, from Genera PR to discuss the strategies that we will be implementing in order to organize relations with the community and the municipalities.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria prepare for a meeting with Jorge Bracero, from Genera PR and Osvaldo Rojas, external consultant.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Complete revisions related to all Google Earth maps of communities. Call with Jorge Bracero from the Genera' s Team to clarify doubts related to the Google Earth maps project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting in Teams with Jorge Bracero from the Genera PR to discuss the work on the entry of data from community leaders in Arecibo.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR-Deliverable 11 - Project Management ¦ DR 4339: Received a call from Mr. Nelvick Santiago López (Ricoh PR) regarding the request for a quotation for photocopiers to be deployed across multiple sites. Mr. Santiago explained that to prepare an accurate quotation, it is necessary to: Verify the existing network connectivity and infrastructure at each site. Identify the specific requirements for each location (e.g., volume of printing, color vs. black-and-white needs, multifunction capabilities). Determine whether the client prefers a purchase or leasing option, based on the expected duration of the project. Include service and maintenance agreements in the proposal, tailored to the chosen equipment and usage levels. Awaiting further internal coordination to schedule a site visit and finalize the necessary specifications for the quotation.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | Genera PR-Deliverable 11 - Project Management ¦ DR 4339: Reviewed email correspondence from Harry del Valle (DCMC) to Mr. Piñero (ACGIPR) regarding a request for a quote on photocopiers that can support 11 x 17 paper for installation across multiple sites. Additionally, reviewed an email sent to Mrs. Lopez (Dorado Ice Water Plant) to inquire about a quote for the delivery of 5-gallon water bottles and coolers. Contacted Mr. Brian Padró (Aguas Alcalinas Le Marie) to discuss distribution details for 5-gallon water bottles and coolers; Mr. Padró requested an email outlining specific requirements to proceed with providing a quotation. Lastly, reached out to Kate Flores from Ricoh Puerto Rico to request comprehensive information about their photocopier solutions, including machine specifications, maintenance services, and installation availability across multiple operational sites. Awaiting her response to assess the compatibility of their offerings with project requirements.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache project update meeting with Andres Concepcion (DCMC), Gilberto Sucre (DCMC) for 4339_9510 BESS_Cambalache project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports with comments considering contractual milestones guides to proponent proposal RFP for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache participate in team in weekly internal meeting discussing strategies to a meeting with designer Sargent & Lundy, timings for possibles starting project of contractor RGE contractor and news related to team responsibilities with employees Jorge Mercado, Luis Duque, Luis Damudt, Gilberto Sucre, and Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports with comments considering with baseline and update scheduling guides of proponent proposal RFP for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Completed Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Continue Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with Genera PR, RGE, Sargent & Lundy about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 134 | 67 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3)(PART 2) Continue Procore Inspections and Observations: How to Involve Trade Partners training course for 4339_9510 BESS_Cambalache project.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 124 | 124 | 124 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procedure to obtain the Qualifying Transportation Worker Identification Credential (TWIC) for entry to the Cambalache Project Site
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Concepcion, Andres | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 124 | 124 | 124 | Yes | 25-145003 | PREPA Genera - Deliverable 11 Cambalache BESS - 4339DR - Payment to obtain TSA's TWIC security credential required to work on Cambalache site.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Ensuring updates to the master tracker and continuing the refinement of the Power BI dashboard for the monthly report.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Maintaining the master tracker and proceeding with the enhancement of the monthly report.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Damudt, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 81.9 | 0.7 | Yes | 25-145003 | Date April 29, 2025 Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Claiming Mileage for this route Calle # 6 B19 Urb. Isabel la Catolica Aguada PR00602 to Todo Licenias, Parque industrial Tuque, PR-591 edif #3091 suite 104, Ponce, 00728 for Procedure to obtain the Qualifying Transportation Worker Identification Credential (TWIC) for entry to the Cambalache Project Site
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.2 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel back home to Guaynabo from Aguirre, the purpose was to support warehouse operation and maintain workflow during Mr. Juan Vallejo medical leave.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel directly from home in Guaynabo to Aguirre to support warehouse operations and maintain workflow during Mr. Juan Vallejo medical leave.
2025-04-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 44.73 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site inspections job in the site. Meeting with Carirma Sanchez (Homeca) Total Distance 63.9 miles
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 continued on site walkthrough to review the demolition plan and scope of work. We also performed an inventory of existing buildings designated to be removed of all materials and equipment inside each structure. Abraham Velázquez – DCMC Partners - Rafael Pabón – CDM Smith - Nieves Diaz, Lemuel SARGENT &LUNDY
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 performed an onsite walkthrough with S&L reps. to review the demolition plan and scope of work Abraham Velázquez – DCMC Partners - Rafael Pabón – CDM Smith - Del Valle, Miguel A -SARGENT&LUNDY - Cristóbal Mateo. SARGENT&LUNDY - Romero Quiñones, Reinaldo; SARGENT&LUNDY - Nieves Diaz, Lemuel SARGENT &LUNDY
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Daily Progress Update with Jose Lopez - DCMC Partners Site Manager
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Reporting - Meeting with Abraham Velazquez DCMC Partners to get update from the Peakers Pre-Con activities.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Weekly Project Meeting - Update of Design status of the BESS Program including RFI and submittal status. Participants of CDM Smith, Genera, DCMC Partners, CSA Group and Sargent & Lundy.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria TESLA contract review to understand delivery commitments, options to delay delivery to site, liquidated damages.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence reading, evaluation and update of actions items of PMO Construction.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO EHS Management Alignment and Implementation with Corporate. Participants Jack Darnell and Al Rocha from Lemoine and Foster Veazey & Gilberto Sucre - DCMC Partners.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Diesel to be transported to Palo Seco will require additional testing for COA, evaluated options to execute them and the fastest ways to test them in order not to delay the activity nor project end date. Enrique Laya - CDM Smith, Jose Lopez and Gilberto Sucre DCMC Partners.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting to contemplate when Change Orders need to be issued and what kind of delay for the first three projects. Gabriel Perez - CDM Smith, Rafael Calderon and Gilberto Sucre from DCMC Partners, Concentrated to the first the facilities
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache -Continue evaluating RG Engineering VE Revised Proposal including review Construction Project Team comments.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Compared Tesla Batteries Deliveries dates vs. contractors best offered schedules to start installation. All average a six-month delay. Contractors scheduled need to be finalized for Cambalache, Vega Baja & Costa Sur.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR – Deliverable 11: Project Management ¦ DR 4339. Meeting follow- up develop action items and plan for implementation and next steps to meet Joaquin Quinoy (Genera) request and expectations that were discussed during the weekly alignment meeting.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR – Deliverable 11: Project Management ¦ DR 4339. Meeting with Joaquin Quinoy (Genera), weekly alignment meeting to discuss process improvement implementation and strategy for grant projects.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 225 | 675 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Data formulation and information gathering that is needed for the upcoming Program Management RFP. This includes revisions to the DCMC org chart, development of a rate schedule that corresponds with the overall Org Chart, review of resumes and experience, compiling scope of work templates, and outlining the overall Program Approach.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore role matrix.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks updates for the Procore team.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Submittal Workflow from Franklyn Colmenares (CSA) for purpose of building it out in Procore.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for Analytics. This is in preparation for working with Raissa Borges (DCMC) on using data tables from Procore for creating dashboard.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financials for implementation.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating the tool tracker task sheet for leadership.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on the Procore role matrix (RACI).
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore SOP's review and working to find a place to "publish" the final versions for teams to use/see.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financials for implementation.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on downloading Power BI files to share with Raissa Borges (DCMC) in the upcoming meetings. These will be used for the PMO reporting dashboard.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore configurations for permissions.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Raissa Borges (DCMC) to discuss Procore Analytics for purpose of PMO reporting.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing the Site Inspection and liquid extraction in the Generator #1. Evaluate the Health and Safety process.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conversation with Gilberto Soto (DCMC) about before Vega Baja Start Job in Site. Site inspection in Vega Baja. Meeting with Gilberto Soto, Emmanuel Santos (HOMECA), Nelson Soler (CDMSMITH) about the jobs in projects. Inspection the liquid extraction in the Generator #1.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Evaluate documentation receive by Franklyn Colmenares and Nelson Soler (CDMSMITH) about Vega Baja and Costa Sur (GENERA) projects.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers Contract Amendments - Discussed amendment justification memos with Franklyn Colmenares (CDM Smith), focusing on the documentation required to support contract extensions and modifications. As part of the process, reviewed and confirmed the relevant contract details for the following vendors: Javier E. Bidot & Associates, PSC; CAPTA PSC; Geo-Engineering, LLC; Jaca & Sierra Engineering, PSC; and Environmental Health Safety Services (EHSS).
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers Contract Amendments - Verified the financial account number associated with each contract to ensure accuracy and proper alignment with procurement records and reporting requirements (Javier E. Bidot & Associates, PSC; CAPTA PSC; Geo-Engineering, LLC; Jaca & Sierra Engineering, PSC; and Environmental Health Safety Services (EHSS). Verified the financial account number associated with each contract to ensure accuracy and proper alignment with procurement records and reporting requirements.)
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers Contract Amendments - Drafted the contract amendment justification memo for Javier E. Bidot & Associates, PSC to reflect the necessary updates related to the contract term. Ensured that the memo language was consistent with the original contract terms and aligned with applicable procurement and compliance standards.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers Contract Amendments - Drafted the contract amendment justification memo for CAPTA PSC, Geo-Engineering LLC, Jaca & Sierra Engineering PSC and Environmental Health Safety Services to reflect the necessary updates related to the contract term. Ensured that the memo language was consistent with the original contract terms and aligned with applicable procurement and compliance standards. Send drafts for review and approval to Franklyn Colmenares (CDM Smith) and Jesús Cintrón (Genera)
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya, Carlos Palomares (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Support for Power Generation and Fuels Consumption Reports: Collaborated with Jan Rodríguez from Genera PR to prepare the Power Generation and Fuels Consumption reports for April 2025. This involved structuring the data requests to be sent to power plant managers, covering both baseload units and peaker units. The goal was to ensure comprehensive and accurate data collection for the monthly reports.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 7 acetylene works are being completed on generator 1.1 and clean around the generator
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Dismanteling and Demolition process daily activities overview.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Gilberto Sucre (DCMC) and Enrique Laya (CDMSmith) to discuss work plan for the additional diesel test required by Genera PR. - Communication with the Homeca representative to go over the daily activities plan.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting & Coordination - LUMA will conduct a visit to the Yabucoa site in order to verify the area and gather the necessary details to carry out the relocation of the telecommunications system (telecom). Walkthrough & Measured areas. Attendees - Samuel Gonzalez (LUMA), Ángel Rivera (LUMA), Franklin Colmenares (Genera), Axel Rivera (Genera) & Harry del Valle (DCMC)
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue Working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Cambalache project. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is underway on a safety presentation for new contractors, seeking to educate staff on the risks associated with the scope of the project as part of DCMC's contractual requirements.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the CONTRACTOR'S MANUAL OCCUPATIONAL HEALTH & SAFETY REV 1 of Genera.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is underway on a safety presentation for new contractors, seeking to educate staff on the risks associated with the scope of the project as part of DCMC's contractual requirements.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination with the Genera team (Rosseane Perez) to establish an evacuation plan at the Cambalache site.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Evaluated Procore Observation tool implementation and developed recommendations for Lemoine's Lauren Wells process standarization.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed RG Engineering (contractor) pricing proposal and developed comments as part of the pre contract considerations. Developed comments list and provided to DCMC Partners - Gilberto Sucre.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Cambalache site team meeting to discuss Design Drawings review and comments provided to Sargent and Lundy (Designer). Met with DCMC Partners site team: Carlos De Jesus, Luis Damudt and Luis Duque.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and evaluated Procore program responsibility matrix (by Lauren Wells - Lemoine) to determine the use of responsibility of the tools depending on the site role and position.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Phone call meeting with Jorge Mercado - DCMC for site specific safety plan development coordination.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed RG Engineering (contractor) pricing proposal and developed comments as part of the pre contract considerations.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued design drawings QA/QC review and comments to be provided to designer (Sargent and Lundy) and ensure high quality project information in final drawing set.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with the critical component's tracker to update vendor status and information. Send email to Juan Pascual of Control Associates in regard of PO 107049 for delivery of equipment, Mr. Pascual informs that they had not yet received this PO, send email to Sulinnette Perez of Genera for the status of this PO, she sends information of Asset Suite that PO is on an Issued status, but I inform that the vendor still has not received this PO we are pending for Genera to advise. Meet with D' Alexander Gonzalez of DCMC to discuss NME and Federal Funding project that may be duplicate. Send email to Jonny Martinez of Genera for coordination related to Multimedia Filter Skid Water Treatment Plant of PS.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with Genara Project Status Table to identify the PO requisition assigned to each of the (24) Federa Funding projects that should be included as NME. Send email to Joaquin Quinoy of Genera related to alternative solution in regard of Cambalache Leak Detection System.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Meet with Anthony Vega of Genera to inform status of delivery for Air Heater Basket (Hot and Cold) of Palo Seco, also send an email to Anthony Vega of Genera with all equipment delivery schedule from April thru June for logistic coordination at the warehouse. Send an email to Jorge Ramos of Alonso and Carus requesting progress status update related to PS New Fixed Screen and Demi Water Tank #2 construction, in the case of Fixed Screen also requested if delivery date is still in schedule for 5/6/25. Send an email to Jose Mestres of EPS to provide delivery status of PO 101296 in regard of New Multimedia Filter Skid Water Treatment Plant.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with critical component tracker table in updating information and data entry for delivery updates of equipment. Genera IT installed a desktop at my office for Asset Suite. Updating the weekly status report for PMO presentation with recently information related od delivery of equipment.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed recount at the Aguirre warehouse to ensure inventory accuracy. This process is essential for validating initial counts, resolving discrepancies, and maintaining the integrity of inventory records.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted variance analysis by identifying discrepancies and investigating inventory inconsistencies to support effective inventory control. This activity promotes accuracy, operational efficiency, and timely corrective actions. Today's efforts focused on locations CR 066 through CR 0269.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory data analysis and prepared count sheets for the schedule cycle count at the Aguirre warehouse. Task included validating item locations, reviewing stock accuracy, and organizing materials to ensure a smooth and efficient inventory process.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued cycle counting of designated inventory locations, specifically from CR 0266 to CR 0269. This activity supports the verification and reconciliation of physical inventory with system data to ensure accuracy and regulatory compliance.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Aguirre warehouse, prepared a comprehensive report for Mr. Anthony Vega from Genera PR, consolidating data across all warehouses. The report includes catalog counts, locations details, unit counted, item costs, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each facility. Locations reviewed include CR 066 to CR 069, AA 026 to AA 043, AD 051 to AD 056, AE 001 to AE 010.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a job briefing with Hernan Machado, Milton Flores and other warehouse personnel from DCMC to review any issues identified the previous day and reinforced proper data entry procedures to ensure inventory accuracy.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle counts for the schedule inventory locations assigned for the day, specifically from CR 0266 to CR 0269. This task supports the ongoing effort to ensure inventory accuracy and alignment with the system records.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Continue adding to the Matrix of NEPR resolution for NME identify under FY2025 NME Projects to current GENERA-PR contracts for these activities.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components Add to the Matrix of NEPR resolution for NME identify under FY2025 NME Projects to current GENERA-PR contracts for these activities.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100- 6. Appendix D.1- Design Drawings Structural plans.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100- 6. Appendix D.1- Design Drawings Electrical plans.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Folder 100- 8._Appendix_D.3-_Demolition_Specifications.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Specific Health, Safety and Physical Security Requirements for Cambalache Requirements for the Contractor before the start of work, PAGE 1-5 send by Jean Pierre Menay from DCMC.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document different discipline Demolition, Architectural, Structural, Electrical, Site, Arc Procore Folder 100- 6. Appendix D.1- Design Drawings.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 25-145003 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache - Drawing Review with Andres Concepcion, Luis O. Damudt, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant Magnagement team.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- I Supervised the Contractor Homeca, this week they are removing and cutting of all metal material from turbine UVB 1-1 and turbine UVB 1-2. I also answered multiple emails, read multiple emails I needed to in order to keep up with all the communications and updated throughout the day.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- I worked with RFI's that needed my attention for today, added and updated the information on multiple RFI's (ex. RFI # 39 & RFI #23). I also read some submittals to keep up with the movement of things from the project. I Supervised the Contractor Homeca Recycling, this week they are removing and cutting of all metal material from turbine UVB 1-1 and turbine UVB 1-2.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 5 acetylene works are being completed on generator 1.1 Martinez Oil Collector company arrived to drain the turbines 1.1 1.2
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#5_Invoice# 18334034_Jan 2025. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- TESLA_Contract 106761. DCMC and CDM BESS Meeting: BESS project Change Orders Status follow-up and review of contract schedules. Delivery date delay notice logistic discussion. Participants from CDM PM (Gabriel Sepulveda) and DCMC - (Rafael Calderon and Gilberto Sucre)
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 456 and 457.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AE001 to AE010
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE001 to AE010
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE001 to AE010
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AE001 to AE010
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 00 026 000 to AA 00 043 000.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 00 026 000 to AA 00 043 000.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 00 026 000 to AA 00 043 000
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #379, 380, and 381 from locations AD051 to AD056 for a total of 20,114 pcs.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD051 to AD056 to begin the cycle counts.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 152 | 494 | 152 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AD051 to AD056 Cycle Count List # 446.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Procore File Structure PEAKERS Yabucoa/Costa Sur Document Control - Data Management - Verification of Vega Baja BESS Existing Data & Documents in Procore
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja (BESS)/Costa Sur (PEAKERS)/Cambalache (BESS) to ensure documents and data are created, reviewed, distributed, tracked, stored and archived in an organized and controlled manner.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review and Audit the Meetings and Submittals (2nd audit) Tools on Cambalache Procore Project to verify and classify items corresponding to their proper locations.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 151 | 528.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Determine preliminary configuration of SOPs to be presented on Procore Home Page directly from associated links; configure and classify SOP as internal and externals.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review and Audit the Meetings and Submittals (2nd audit) Tools on Vega Baja Procore Project to verify and classify items corresponding to their proper locations.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 149 | 447 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761 and Deliverable Schedule review based on information requesting GS unit delivery before contract date. Review contract documentation to identify allowable task and scope. Identify and mitigate contractual risks.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 149 | 596 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 -PW#9510 - Continue Pre-Intervention Review for CDM Smith TO02_Oct24_Inv 09. Review narratives and prepare RFI requesting clarification on missing entries. During the complete review I also identify administrative narratives. RFI was sent to contractor and Pre Intervention tracker was updated for this invoice.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 25-145003 | Genera PR ¦ Deliverable 11 ¦ DR4339 - Generate final packages to request CPA for the following invoices: CDM_TO1_Oct24_90231861, CDM_TO6_Feb25_90229562, CDM_TO2_Aug24_90231898. Also, for S&L_TO9_Jan25_18334036. All invoices were sent by email to Franklyn Colmenares and Manuely Concepción (CDM) for CPA creation. This email includes PDF signed by Genera invoice and Excel version with Labor Notes. Update was sent also to José Ralat (DCMC) and I updated all the information in the Pre Intervention tracker. Email sent to Mike Kucynski (S&L) with copy of signed pdf invoice as requested.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.25 |  | 139 | 451.75 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create Community Relations Program Diagram¿ to organize and structure project tactics for Genera's Team.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence development for Jorge Bracero from the Genera team to clarify doubts about the content and scope of the community relations program
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create a document with the details, status of projects and dates related to the communication outreach liaison project. The report was sent to Jorge Bracero and Ivan Beaz Santiago from the Genera PR team.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review and induction on the community project to rehabilitate and create alliances with the community of Cataño – Toa Baja. The information was provided by Jorge Bracero from the Genera team with the aim of starting to create relationships with the community linked to the Bess and Peakers project.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Begin the process of entering data related to the mapping in Google Earth of Vega Baja of the community leaders.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR – Deliverable 11 – Project Management ¦ DR4339: Received a call from Mr. Nelvick Santiago López (Ricoh PR) regarding a meeting request at CVP to discuss a quotation for the deployment of photocopiers across multiple sites. Scheduled a presentation on Ricoh equipment for May 2, 2025, at 10:30 a.m., and sent calendar invitations to Harry del Valle, Frances Vallejo, and Gilberto Sucre (DCMC).
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 25-145003 | Genera PR – Deliverable 11 – Project Management ¦ DR4339: Received an email from Brian Padró (Agua Alcalina Le Marie) outlining a proposal for the delivery of bottled water to multiple project sites. The proposal includes options for quantities, delivery schedules, and pricing. The information was forwarded to Harry Del Valle (DCMC) for his review and further evaluation. In addition, began reviewing an email from Ada Díaz (DCMC) regarding the list of cleaning materials required for operations across various sites. The request includes specific items and quantities,
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Bid-Addendum Documents for 4339_9510 BESS_Cambalache project.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create inspection reports summarized in excel with comments using drawings worked by company Sargent & Lundy in Procore for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache participated in drawing of Procore internal TEAMS meeting discussing strategies to inspection of drawings with comments creation to designer Sargent & Lundy with employees Luis Duque, Luis Damudt and Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create inspection reports with comments in project designed drawings considering technical project specifications for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 25-145003 | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create inspection reports with comments in drawings required by RFP considering technical project guides for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review of Bid-Addendum Documents for 4339_9510 BESS_Cambalache project.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review updated Bid-Addendum Drawings for 4339_9510 BESS_Cambalache project.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache project drawing review meeting with Andres Concepcion (DCMC) for 4339_9510 BESS_Cambalache project.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 122 | 427 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Gathering and organizing information needed to support reporting processes focusing on project key milestone.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Revising the master tracker and further developing the Power BI dashboard to support the monthly reporting process.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 25-145003 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Lauren Wells from Lemoine to discuss Procore Analytics feature for Dashboard report.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 44.73 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site inspections job in the site. Meeting with Emmanuel Santos (Homeca) and Gilberto Soto (DCMC) and Inspection the liquid extraction on the Site. Total Distance 63.9 miles
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.2 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled from Aguirre back home to Guaynabo. The purpose of the trip was to support warehouse operations and ensure workflow continuity during Mr. Juan Vallejo medical leave.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from residence in Guaynabo to the Aguirre warehouse to support ongoing operation and ensure workflow continuity during Mr. Juan Vallejo medical leave.
2025-04-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 42.07 | 0.7 | Yes | 25-145003 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from Home Office Luquillo to Yabucoa Gas Turbine Plant (18.106216, -65.823685) to Home Office Luquillo. Purpose Meeting & Coordination - LUMA will conduct a visit to the Yabucoa site to verify the area and gather the necessary details to carry out the relocation of the telecommunications system (telecom). Walkthrough & Measured areas. Attendees - Samuel Gonzalez (LUMA), Ángel Rivera (LUMA), Franklin Colmenares (Genera), Axel Rivera (Genera) & Harry del Valle (DCMC) Total Mileage 60.1 Miles
96191.5
[13 empty] | Construction mgmt= | 93481
[13 empty] | Community | 2710.5
96191.5

## May1
Entry Date | Client | Proj level1 | Proj level2 | Proj level3 | Client title | Asset | Task | Task Group | Task Description | Activity Type | Hours | Column1 | Activity Rate | Activity Extended | Billing Rate | Line Billable | Invoice Number | Work Site | Narrative
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 696.12 | 696.12 | 696.12 | Yes |  |  | T-Mobile for Business. April charges for hotspots and cellphones for Genera Deliverable 11 project.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Procore (Elizabeth Fronduto, Delia Garcia, Marisa Young, Kenna Crouse) to discuss SOP services, training, etc.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended a Peaker's strategy meetings discussed GC roles and division of work and site access. Attendees: German Nunez, Rafael Pabon, Carlos Palomares (CDM Smith)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed site visit plans, worked on revised demolition plan and site plan with notes in order to mitigate risks, keep costs under control, and ensure that the project is completed on time and in compliance with all relevant laws and regulations.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Best Peaker's Schedule & Budget Meeting Weekly Review of both programs schedule & cost. Rafael Pabon- CDM Smith, German Nunez - Genera, Carlos Palomares - CDM Smith, Franklyn Colmenares - CSA Group, Gabriel Perez - CDM Smith and Gilberto Sucre - DCMC.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting ARG Ceres / Vega Baja Site Phase II - Kick-off meeting for the Installation Phase to be executed by AGR Ceres. Each team presented themselves GENERA, CDM Smith, Sargent & Lundy, and DCMC. Early start date June 1, 2025
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur RFP 4899 RFC Discussion Two proposals were evaluated for this RFP. One from ARG-CERES and the second from RG Engineering. A third proposal was received but it was not evaluated since it was incomplete. Carlos Negron - Genera led the meeting attended by Genera, CDM Smith, CSA Group, Sargent & Lundy and DCMC. RGE is the recommended Contractor for Costa Sur.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Email correspondence review and BESS Schedule review.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Internal Meeting PM/CM Team the purpose of this meeting is to be align with RGE final scope, budget and schedule for the Cambalache site. Participants Sargent & Lundy, CDM Smith, CSA Group and DCMC.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Reviewed letter from Homeca on their response to DCMC rejection of time extension as requested.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore DCMC. Continued Financial Model implementation of change order process. Elizabeth Fronduto - ProCore, Lauren Wells, Esther Rohena, Rafael Calderon, Gilberto Sucre and Glorimel Torrado from DCMC Partners, and Foster Veazey - Lemoine.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Project update discussion with Jose Lopez - DCMC
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - BESS and Peaker's Project Schedule and Overall Project Budget Meeting. Attendees were Gabriel Perez (CDM Smith), Foster Veazey, Gilberto Sucre, Abraham Velazquez,(DCMC) Carlos Palomares, Franklyn Colmenares, and Jesus Cintron (Genera).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on RACI items role matrix with Andres Concepcion (DCMC).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss Procore documents tool and SOP's.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Correspondence for Procore items.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Gilberto Sucre (DCMC), Glorimel Torrado (DCMC), Rafael Calderon (DCMC) to discuss items for Procore Financial implementation.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Rafael Pabon (CDM Smith), German Nunez (Genera), Franklyn Colmenares (CSA) and Theresa Perez (DCMC) to discuss Procore Document Control.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating the Procore correspondence based on Feedback from Glorimel Torrado (DCMC) and Rafael Calderon (DCMC).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on setting up meetings for PDF fillable forms with Theresa Perez (DCMC) for use in Procore.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on updating Observation fields in Procore for Andres Concepcion (DCMC).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Observation fields in Procore for Andres Concepcion (DCMC).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the Health and Safety Equipment need in the offices. Review, evaluate and comment the rigging plan sent by Homeca the Vega Baja Site. This plan needs extense revision.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 | 2 | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the emails received for all Genera Projects. Conference call with Harry del Valle (DCMC) about Costa Sur project. Review the Health and Safety Equipment need in the offices. Review, evaluate and comment the diesel transfer plan sent by Homeca the Vega Baja Site to Palo Seco Site Genera.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 0.75 |  | 184 | 138 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review with Andres Concepcion (DCMC) the Cambalache (Genera Site) Status.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Participated in a PMO reporting alignment call with Raissa Borges (DCMC) and Franklyn Colmenares (CDM Smith) to review and align on the content of the Procurement slide. Discussed key updates, formatting, and messaging to ensure consistency with overall reporting objectives and accurate representation of procurement activities for the upcoming PMO report.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 4826 - BESS Installation at Cambalache - Compiled the responses provided by S&L to bidder inquiries, ensuring clarity, consistency, and alignment with the original questions. Formatted the responses in accordance with Genera’s standards and submitted the finalized Q&A document to Ginnell Torres (subcontractor), Saúl Falcón (DCMC) and the Genera Procurement team for publication.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed the FOMB Contract Policy to ensure understanding of applicable requirements and alignment with upcoming procurement efforts. Analyzed the required appendices associated with contract submissions and created editable versions (Appendix A-C and Funds Certification form) to streamline the preparation of upcoming procurement packages. Ensured all templates were formatted in accordance with FOMB standards to support compliance and facilitate timely completion.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 4826 - BESS Installation at Cambalache - Began assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 15 supporting documents. Initiated the process of completing the mandatory appendices, beginning with Appendix A. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in a meeting to demonstrate the Genera Connect Financial Tracker, focusing on the available data cards and the overall reporting process. Attendees included Gerardo Sanchez, Lilliam Ortiz, Jose Roque, Claudia Peña, and Dimaries Rodriguez from Genera PR; José Ralat from DCMC; and Keylamerari Sierra from Integrum. The session facilitated alignment across teams on financial tracking capabilities and reporting workflows.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 6 acetylene works are being completed on generator 1.1 and continued cleaning around the generator.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued Vega Baja Bess Project contract and Specification overview to ensure all project participants clearly understand the expectations and requirements, and their participation in the project’s execution.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Morning meeting with Thessy Perez and Luis Roman (DCMC), PROCORE document control, to establish document QC/QA for the Vega Baja project. Morning call with Gilberto Sucre (DCMC) for project manpower status discussion and course of action.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting & Coordination - Sargent & Lundy scan the Water Tanks area on the northwest of the site of the Plant to verify the space available in this area to install a new water storage tank, document potential connection points to the existing system, and walkthrough the piping routes from this area to the new power block area. Document the pressure, temperatures, flow rates, nameplate information of the existing system. Walk through some of the preliminary piping routes for the other plant systems that we have planned in our 3D model. Gather additional information about the existing interface (e.g. fire protection flanges) Attendees; Christopher Mateo (Sargent & Lundy), Gino Sambolin (Sargent & Lundy), Jose Rivera (Sargent & Lundy), Deldrick Lozada (Sargent & Lundy), Roberto Santana (Sargent & Lundy), Ramón Quinones (Genera), Harry Del Valle (DCMC)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review the Alternative Rigid Inclusion Foundation Design BESS System and New Warehouse Foundations Genera PR
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The crane lifting plans for the Tesla batteries being shipped by the contractor RGE are being reviewed. They are reviewed based on existing site conditions.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The contractor's general safety plans are being reviewed, and work continues on the design and development of the safety briefing for new project entrants to support risk mitigation, promote consistent safety practices, and enhance operational readiness.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Ongoing review of contractor general safety plans to ensure alignment with project safety requirements and applicable regulations. In parallel, work is being conducted on the development of a standardized safety briefing program for onboarding new personnel entering the BESS Cambalache Project. These efforts support risk mitigation, promote consistent safety practices, and enhance operational readiness.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and commented design drawings for designer (Sargent & Lundy) corrections to be incorporated in final design set.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Completed Procore Observations tool review and comments for team implementation to ensure project observations are donde regularly during the project to document important project situations. Comments sent to Lemoine's Lauren Wells.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received and reviewed Procore Responsibility Matrix from Lemoine's Lauren Wells. Provided comments on how each site personnel role would use the platform.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and provided comments to documents ( pre-submittals) received from contractor (RG Engineering) regarding accelerated construction schedule, Rigging Plan, Fire protection and Rigid Inclusions preliminary design.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued developing Cambalache site project reporting format and process. Reviewed Procore reporting tool to align information and formats.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Xiomara Perez of RG Engineering provided new delivery date for PO 105644 and 106560 that was delay new date delivery date 05/09/25 due to port congestion issue. Reviewing drawing send by Diana Rivera of CPM related to the leak detection system route at Cambalache plant. Continue reviewing drawing related to existing leak detection system of Cambalache.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue with critical component tracker reviewing requisition if is aligned with project description, some project descriptions are similar but not the same.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with critical component tracker reviewing requisition if is aligned with project description, some project descriptions are similar but not the same. Send email to Freddie Gonzalez of Emerson to confirm the recommended wireless transmitter will be replace batieres after 10 years of use, this instrument has been sent to Joaquin Quinoy of Genera as a recommendation for the Leal Detection System of Cambalache.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - CPM Jose Prado, Luis Tapia, Carlos Castro, Diana Rivera and Victor Alvarez; DCMC Pedro Cabrera and Eduardo Rivera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, Discussion of Cambalache Leak Detection System, Overhead crane, fire system and reviewing the deliverables for SOW & CE.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working with critical component data entry for update and review. Send email to Rafael Torres of Malnat for status of delivery date for Air Heater Basket (Hot and Cold) for Aguirre power plant. Sulinnette Perez of Genera procurement sent the contract PO to Control Associate for the purchase of Boiler and Burner Recirculating Valve.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue review of critical component tracker table updates. Pedro Cabrera of DCMC provide information of (3) projects that will be cancel Boiler feed water pumps, Clutch Removal and Air Heater Basket of Aguirre. In case of Air Heater Basket of Aguirre this will be cancel to a vendor and new RFP will be run for another vendor. Diana Rivera of CPM send picture related to Cambalache Leak Detection System; I request to CPM to send me drawing that was obtain during planta site visit.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a recount at the San Juan warehouse with Mr. Milton Flores from DCMC to ensure inventory accuracy. This effort was critical for validating initial counts, addressing discrepancies, and upholding the integrity of inventory records.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed variance analysis by identifying discrepancies and investigating inventory inconsistencies to support effective inventory control. This activity enhances accuracy, operational efficiency, and enables timely corrective actions. Today's efforts focused on inventory locations AE 011 to AE 020.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued cycle counting of designated inventory locations, specifically from AE 011 to AE 020. This task supports the verification and reconciliation of physical inventory against system records to ensure accuracy and compliance with regulatory standards.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the San Juan warehouse, prepared a comprehensive report for Mr. Anthony Vega of Genera PR, consolidating data across all warehouses. The report included catalog counts, location details, unit counted, items costs, discrepancies, maximum and minimum stock levels, and percentage indicators reflecting the current status of each facility. Locations reviewed included CR 001 to CR 005, AA044 to AA 061, AD 057 to AD 062, AE 011 to AE 020.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed inventory data analysis and prepare cycle count sheets for schedule activities at the San Juan warehouse, supporting Mr. Milton Flores of DCMC. Responsibilities included validating item locations, reviewing stock accuracy, and organizing materials to ensure an efficient and streamlined inventory process.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a job briefing with Giovanni Taffanelli, Milton Flores and key warehouse staff from DCMC to address discrepancies identified during the prior day activities and to emphasize adherence to accurate data entry protocols for improved inventory integrity.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed cycle counts for the schedule inventory locations assigned for the day, specifically covering AE 011 to AE 020. This effort supports ongoing initiatives to maintain inventory accuracy and ensure alignment with system records.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Prepare agenda for meeting of overall status of Critical Components with GENERA PROCUREMENT Sullinet Perez, DCMC Eduardo Rivera, Saul Falcon and Pedro Cabrera.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components & Fuel Efficiency & NME Identified in Actual FEMA VERSION according PREB resolution.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Eduardo Rivera, and Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Worked on the Reconstruction Progress Request spreadsheet requested by FEMA. Task included gathering and inputting updated project data, reviewing timelines and milestones, and ensuring consistency with field documentation. This spreadsheet helps demonstrate ongoing progress across recovery projects.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary document Genera Cambalache BESS: Existing U1 MPT Foundation y Piling Drawings.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Generate PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary document Proposed schedule, Rigging Plan, Structural Preliminary Rigid Inclusions and Fire Protection.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary document Cambalache Alternative Foundation Description_042925_rev7 and Pending Submitals for Cambalache BESS.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Revised Value Engineering Offer and Optional Prices BESS Cambalache.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria- Supervised the Contractor Homeca Recyclers, this week they are removing and cutting of all metal material from turbine UVB 1-1 and turbine UVB 1-2. (this is what they are doing, a repeat of the same tasks for a few days sometimes for it is a large site with metal scraps and it takes a lot of time to do burn cutting...)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- I Supervised the Contractor Homeca, this week they are removing and cutting of all metal material from turbine UVB 1-1 and turbine UVB 1-2. I also answered multiple emails, read multiple emails I needed to in order to keep up with all the communications and updated throughout the day.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 6 acetylene works are being completed on generator 1.1 and clean around the generator.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review process implementation in Procore for Change Orders. Collaborating session with Glorimel Torrado (DCMC) to review Lauren Wells (Lemoine) email with links to access PDF new versions for change orders and screenshot from platform. In order to comment on this, we review contract requirements and generate a document providing feedback.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens / Genera Peakers biweekly meeting with project management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Reviewing status of project execution including upcoming Change Orders and Logistic in preparation for the Delivery Dates. Meeting between Siemens Energy team , CMD Smith PM team (Rafael Pabon, Carlos Palomares), Sargent & Lundy (Miguel del Valle, Mateo Agosto and Gino Sambolin) Genera (German Nunez), and DCMC (Rafael Calderon).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Miguel del Valle (Sargent and Lundy), Rafael Pabón (CDM) and from DCMC Rafael Calderón & Glorimel Torrado. This meeting was to discuss with the Project Managers about the DCS delivery. They indicate that is a small system that can be storage in a secured and low humidity place. We requested a clear communication indicating that this change will not affect milestones for this contract.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- Procore - DCMC Financials Tools. Reviewing Change Orders procedures and Pro-Core functionalities to manage changes on projects contract and process of submittals and acceptance of the changes. Participants (Rafael Calderon, Glorimel Torrado, Gilberto Sucre, Foster Veazey, Lauren Wells, and Tyler Scanlan)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Collaboration with Glorimel Torrado (DCMC) in working session reviewing Siemens contract. This is in preparation for formal meeting at 5pm. Siemens is requesting to send DCS system with the turbines. This will need Genera to provide storage for the system until is time to program the DCS. DCS is the System Control (hardware and software). During this time, we identified responsibilities and important questions to be discussed in formal meeting.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 152 | 494 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AD057 to AD062 Cycle Count List # 461.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE011 to AE020
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE011 to AE020
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AE011 to AE020
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE011 to AE 020.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AE011 to AE020
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 00 044 000 to AA 00 061 000
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 00 044 000 to AA 00 061 00
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 00 044 000 to AA 00 061 000
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts 460, 468,469,470.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 001 and CR 002 using Cycle Count List #372.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 001 and CR 002 at the Aguirre warehouse to start the cycle counts.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location CR 001 and CR 002.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD057 to AD062 to begin the cycle counts.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 152 | 342 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 474 and 475.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #379, 380, and 381 from locations AD057 to AD062 for a total of 7050 pcs.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Vega Baja BESS Data Management/Preparation of Draft SOPs for all GENERA projects for publishing to ensure routine operations are conducted safely, consistently, and effectively.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Costa Sur (PEAKERS)/Coordination of Directory Permissions Costa Sur (PEAKERS) with Rafael Pabon (CDM)/ Document Control Vega Baja BESS Data Management/Coordination of Documentation Process for all GENERA projects with Lauren Wells (DCMC), Rafael Pabon (CDM), Franklyn Colmenares (CSA), German Nunez (GENERA), Gabriel Perez (CDM)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Vega Baja Submittal Log to identify potential submittals to be included in a Safety Submittals Package, due to wrong location of items and files.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue working on Procore Certification: Project Management as an Owner Representative (client requirement).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 151 | 453 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Vega Baja's Submittal Log: upload new submittals and new submittal attachments due to contractor's issues with the Submittal Tool. Discussing with Team Members Rigging Plan attachments and revision (Submittal 61.1 and 61.2).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 151 | 453 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the implementation of Procore Observation Tool with DCMC Team Members to discuss their feedback on the enabled tools and items; Discuss the users' input of documentation regarding correct classification and location.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Financials Tools Procore Meeting. Recurrent meeting to discuss Procore changes for change order tools. In this meeting participates Rafael Calderón (DCMC), Gilberto Sucre (DCMC), Lauren Wells (Lemoine), Lauren Kennedy and JC Willard from Procore and Glorimel Torrado (DCMC).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, Homeca, CPM, B&V, Siemens Energy and CAPTA. I review if any vendor responds to RFI and update tracker with invoices attended. This is in preparation for Friday internal meeting.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR4339 - Review Lauren Wells (Lemoine) email and Esther Rohena (DCMC) follow up on pending action for this email. Start reading and preparing for working session about the review requested on Change Orders inside Procore system.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Siemens Energy Contract #00106588 and Deliverable Schedule review based on RFI submitted by Rafael Pabon (CDM). I started reviewing my notes and searching on contract for DCS information. They are requesting to send the DCS with the turbines. Working session will be held today afternoon to discuss this topic.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Miguel del Valle (Sargent and Lundy), Rafael Pabón (CDM) and from DCMC Rafael Calderón & Glorimel Torrado. This meeting was to discuss with the Project Managers about the DCS delivery. They indicate that is a small system that can be stored in a secured and low humidity place. We requested a clear communication indicating that this change will not affect milestones for this contract.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Collaboration with Rafael Calderón (DCMC) in working session reviewing Siemens contract. This is in preparation for formal meeting at 5pm. Siemens is requesting to send DCS system with the turbines. This will need Genera to provide storage for the system until is time to program the DCS. DCS is the System Control (hardware and software). During this time, we identified responsibilities and important questions to be discussed in formal meeting.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 149 | 223.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review process implementation in Procore for Change Orders. Collaborating session with Rafael Calderón (DCMC) to review Lauren Wells (Lemoine) email with links to access PDF new versions for change orders and screenshot from platform. In order to comment on this, we review contract requirements and generate a document providing feedback.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Prepare for a meeting in Teams with Jorge Bracero from Genera PR to explain the automation process. Meeting with Jorge Bracero from Genera PR to explain the process of automating site mapping.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Data entry related to stakeholder mapping on Google Earth (community engagement for Vega Baja site)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria work on the process automation related to stakeholder mapping on Google Earth (community engagement for Vega Baja site)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue the Data entry related to stakeholder mapping on Google Earth (community engagement for Vega Baja site)
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management ¦ DR4339: Following the email received from Gilberto Sucre (DCMC) regarding the EHS Contractor Manual, I have initiated the review process in preparation for drafting the updated version of the document. This initial review phase focuses on identifying key areas requiring revision to ensure alignment with the current manual structure, internal procedures, and applicable Environmental, Health, and Safety (EHS) standards.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management ¦ DR4339: I contacted Mr. Kevin Huerta from Grainger Puerto Rico to receive guidance on the different options available for creating an account with the company, in order to purchase office and cleaning supplies for the various sites that will be worked on. He explained the different types of account registration they currently offer. He also mentioned that merchandise delivery involves an additional cost. I received the Account Opening document and the Tax Exemption document from the Department of the Treasury. I sent emails to Ada Díaz (DCMC) to explain the process with Grainger and to forward the documents for her review.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review of Bid-Addendum design drawings Warehouse erosion floor plan Documents for 4339_9510 BESS_Cambalache project.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create report with comments considering specifications and Procore drawings using a third version schedule of contractor RGE for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on updated reports in excel with comments with incomplete or misinformation using Procore file for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review of Bid-Addendum design drawings Warehouse erosion floor plan Documents for 4339_9510 BESS Cambalache project.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 122 | 427 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Adjusting financial records for the April final report covering Genera projects Peakers and BESS.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting "PMO Reporting Alignment Chat" with Sheila Torres (DCMC) and Franklyn Colmenares (CDM Smith) to discuss projects Request for Proposal status and updates for reporting purposes.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Revising financial information for Genera projects Peakers and Bess received from Carlos Palomares from CDM Smith.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.97 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-after concluding at the San Juan warehouse with Mr. Milton Flores from DCMC, returned to Guaynabo. The purpose of the visit was to review progress to date, address any outstanding questions, and provide continued support to Mr. Flores throughout the process.
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 153.3 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Costa Sur Power Plant to Home Office Luquillo. Hurricane Maria Meeting & Coordination - Sargent & Lundy scan the Water Tanks area on the northwest of the site of the Plant to verify the space available in this area to install a new water storage tank, document potential connection points to the existing system, and walk through the piping routes from this area to the new power block area. Document the pressure, temperatures, flow rates, nameplate information of the existing system. Walk through some of the preliminary piping routes for the other plant systems that we have planned in our 3D model. Gather additional information about the existing interface (e.g. fire protection flanges) Attendees; Christopher Mateo (Sargent & Lundy), Gino Sambolin (Sargent & Lundy), Jose Rivera (Sargent & Lundy), Deldrick Lozada (Sargent & Lundy), Roberto Santana (Sargent & Lundy), Ramón Quinones (Genera), Harry Del Valle (DCMC).
2025-05-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 5.32 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from Guaynabo to Central San Juan to meet with Mr Milton Flores from DCMC. The purpose of the visit is to provide support and walk through the procedures to ensure a clear understanding of the process.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 worked on revised scope of work for Costa Sur projects for milestones, deadlines, deliverables, and expectations, reviewed plans and marked up site photos.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 completed entries to logs and updates specs reviewed Procore submittals
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Update weekly construction progress tracker with Raissa Borges (DCMC)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in a call with Gilberto Sucre, José López, Sheila Torres-Sterling (DCMC), and Gabriel Pérez Sepúlveda (CDMSmith) to review and discuss Homeca’s response in detail. Addressed specific provisions of the MSA that appear to be unmet, including instances of potential non-compliance with procedural and contractual requirements. Following the call, debriefed with Joaquín Quinoy (Genera) to evaluate the implications of the discussion and align on next steps for addressing the identified issues and ensuring adherence to the contract.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria The PMO Team Catch Up meeting focused on key updates regarding staffing, resource management, infrastructure and operations, and project reporting. The team discussed ongoing interviews for site and construction managers, deciding on candidates and potential role adjustments, while emphasizing the need to fill several critical positions. Resource management challenges were addressed, including feedback on candidates and performance concerns related to existing team members. Infrastructure updates included work on SOPs, trailer installations, and administrative processes, with action items assigned to various team members to finalize client reports, coordinate resources, and address pending amendments. Overall, the meeting aimed to ensure clarity in roles, improve resource allocation, and streamline project operations. Mike Merritt, Mark Merritt, Jack Darnall - Lemoine, Frances Vallejo, Lauren Wells, Anneilia Holton, Ada Diaz and Gilberto Sucre - DCMC.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Prepared weekly action-items check list for following week.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Reporting and Update discussion between Gabriel Perez - CDM Smith, Gilberto Sucre -DCMC, and Jesus Cintron - Genera.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache RGE Construction Contract, Schedule and Pre-Mobilization discussions with Jose Robles - RGE, Jesus Cintron - Genera, Gabriel Perez - CDM Smith and Gilberto Sucre - DCMC
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Reviewed Legal Comments provided by Francisco Feliu - Genera on AGR Ceres Contract.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Further discussions on Homeca's performance. Agreed with Jose Lopez DCMC to continue providing execution coaching to Carirma Sanchez - Homeca.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Distribute meeting notes and action items determined during 4/23/25 in-person meeting with the Genera Team. Deliverables include meeting notes summary, draft Meeting ground rules document and next steps for the team.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with DCMC Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for Observations types.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence and meeting setups.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Andres Concepcion (DCMC) to discuss Procore reporting and Meeting minutes template.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) to discuss Procore Observation setup and SOPs.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Configurations.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence forms for Financials.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore team tasks for Luis Roman (DCMC) and Theresa Perez (DCMC).
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating Procore Meeting template for Contractor meetings on Camabalace.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Coordinate site visit to Costa Sur for Abraham Velazquez, Gilberto Sucre and Harry del Valle (DCMC) for preinpection the site. Review the document submit for Homeca about the Diesel Transport Vega Baja to Palo Seco (SITE).
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2.75 |  | 184 | 506 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the emails received for all Genera Projects. Conference call with Osvaldo de Jesus (GENERA) about Vega Baja Site. Meeting with Jorge Mercado and Gilberto Soto (DCMC) about Vega Baja and Cambalache Health and Safety.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR – Deliverable 11: Project Management ¦ DR 4339 Meeting with Nelvick Santiago (Ricoh PR), Harry del Valle, Jean Pierre Menay, Andres Concepción (DCMC).Mr. Nelvick Santiago, representative of Ricoh Puerto Rico, visited the CVP offices to present information regarding the acquisition of printing equipment through leasing for various sites. It was discussed that equipment specifications must include monthly rental, delivery, toner, parts, services, 11x17 printing capability, and both black & white and color printing functionality. He was informed that the projects may last over a year and that the equipment must be capable of being relocated as needed. Mr. Del Valle noted the need for two technicians per region, each trained in safety protocols and equipped with the appropriate personal protective equipment (PPE). Mr. Santiago confirmed that he will work on the proposal and send it later today.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Jose Lopez (DCMC) about the rigging Plan and Transport Diesel from Vega Baja Site (GENERA) to Palo Seco SITE (GENERA). Conference call with Gabriel Perez (CDMSMITH) about Vega Baja Project status and special jobs inside and transport the "IGLESIA" special part. Answer the question in email for Genera Site.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss BESS and Peaker project status and pending items. Participants: Mark Merritt, Michael Merritt, Gilberto sucre and Lauren Wells (DCMC)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 4826 - BESS Installation at Cambalache - Continued assembling the FOMB Request for Approval package, focusing on organizing and gathering the required information for Appendix A. Ensured that all supporting details were accurately compiled and aligned with FOMB’s submission requirements to facilitate a complete and compliant approval process.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - BESS Vega Baja Demolition - Participated in a call with Gilberto Sucre, José López (DCMC), and Gabriel Pérez Sepúlveda (CDM Smith) to review and discuss Homeca’s response in detail. Addressed specific provisions of the Master Services Agreement (MSA) that appear to be unmet, including instances of potential non-compliance with procedural and contractual requirements. Following the call, debriefed with Joaquín Quinoy (Genera) to evaluate the implications of the discussion and align on next steps for addressing the identified issues and ensuring adherence to the contract.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - BESS Vega Baja Demolition - Reviewed Homeca’s response in detail and cross-referenced it with the terms and conditions outlined in the MSA in preparation for the 8:30 am call. Identified specific provisions of the MSA that are not being followed, including potential non-compliance with procedural requirements and contractual obligations. Prepared key discussion points to ensure a clear and well-supported position during the meeting, aimed at resolving discrepancies and reinforcing adherence to the agreement.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 231161 Demolition at Costa Sur - Discussed the Intent to Bid deadline with Saul Falcón (DCMC) and Ginnell Torres (DCMC subcontractor) to assess the need for an extension based on vendors that were invited after publication of the RFP. Subsequently drafted Addendum No. 1 to formally extend the Intent to Bid deadline. Ensured the addendum was consistent with the original solicitation and included all necessary updates. Sent the finalized document to Saúl Falcón and the Genera Procurement team for review and publication.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 231161 Demolition at Costa Sur - Discussed the publication and outreach strategy with Rafa Pabón (CDM Smith) and Rafa Rodríguez Ema (Genera) to increase visibility and attract a broader pool of bidders. As part of the effort, drafted a targeted social media post designed to promote the procurement opportunity and encourage vendor participation, aligning messaging with the overall communication strategy.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Held a discussion with Jean Gonzalez, Mario Gomez, Michael Silva, and Elba Rodriguez from Genera PR to review and address pending items related to Genera Connect. Participated in the kickoff FortiNAC meeting with the same group, initiating efforts to establish secure access protocols for internal financial and asset management applications, including Asset Suite, Oracle Fusion, and Genera Connect. Additionally, modified Financial Tracker reports provided by Jose Ralat from DCMC to meet system requirements and successfully uploaded them into the Genera Connect Financial Tracker for review.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed outstanding items related to the Genera Connect Financial Tracker and Timesheets to assess current progress and identify next steps. Collaborated with Michael Silva from Genera PR to install a purchased domain validation SSL certificate for the Genera Connect Azure environment.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 7 acetylene works are being completed on generator 1.1 and clean around the generator. Received excavator for demolition phase.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform. I called Gilberto Sucre (DCMC) and Jaime Pesquera (DCMC) to discuss the current project phase situation with the Demo Contractor. (Homeca Recycling).
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in a call with Gilberto Sucre, José López, Sheila Torres-Sterling (DCMC), and Gabriel Pérez Sepúlveda (CDMSmith) to review and discuss Homeca’s response in detail. Addressed specific provisions of the MSA that appear in the document, including instances of potential non-compliance with procedural and contractual requirements. Following the call, I debriefed with Joaquín Quinoy (Genera) to evaluate the implications of the discussion and align on next steps for addressing the identified issues and ensuring adherence to the contract.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the PROCORE platform.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform. I called Gilberto Sucre (DCMC) and Jaime Pesquera (DCMC) to discuss the current project phase situation with the Demo Contractor. (Homeca Recycling).
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Continue working on Procore to review contract documents, project drawings, and scope of work for the BESS installations at Costa Sur and Central Aguirre. Assessed potential discrepancies and site-specific requirements. Initiated vendor outreach to obtain quotes for materials, potable water delivery, and office trailer printers.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR – Deliverable 11: Project Management ¦ DR 4339 Meeting with Nelvick Santiago (Ricoh PR), Carolyn Baez, Jean Pierre Menay, Andres Concepción and Harry Del Valle (DCMC). Mr. Nelvick Santiago, representative of Ricoh Puerto Rico, visited the CVP offices to present information regarding the acquisition of printing equipment through leasing for various sites. It was discussed that equipment specifications must include monthly rental, delivery, toner, parts, services, 11x17 printing capability, and both black & white and color printing functionality. He was informed that the projects may last over a year and that the equipment must be capable of being relocated as needed. Mr. Del Valle noted the need for two technicians per region, each trained in safety protocols and equipped with the appropriate personal protective equipment (PPE). Mr. Santiago confirmed that he will work on the proposal and send it later today.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on preparing logistic report for BESS System delivery, Scheduling & Contract Documents for the Yabucoa project. Preparing spreadsheets for inventory of materials in the trailers office. Quoting materials for sites Office Trailer.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of documents (RFP 4826 attachment A, terms and condition article 3.1 contractor responsibilities.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RGE's proposed crane lifting plan with a 350-ton crane is evaluated. Missing information and details in the document are identified, and notes are made for further changes and revisions.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Weekly project meeting where specific safety issues are discussed with Jean Pierre Menay (DCMC) to protect workers, equipment, and the environment on construction site.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of documents submitted by the RGE contractor, (RFP 4826 Exhibit J)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - A safety manual for the RGE contractor is being prepared to identify the emergency management plan (section 6.1). Comments are being made on the document for evaluation.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR – Deliverable 11: Project Management ¦ DR 4339 Meeting with Nelvick Santiago (representative of Ricoh PR), Harry del Valle, Jean Pierre Menay, Carolyn Baez (DCMC). Mr. Nelvick Santiago visited the CVP offices to present information regarding the acquisition of printing equipment through leasing for various sites. Cambalache site was coordinated.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Consolidated and developed project contractor submittals regarding the pre contract negotiation (schedules, foundation design and rigging plan). Sent comments to DCMC Partners - Gilberto Sucre.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Drafted templates in Procore for meetings. This meetings templates will be used regularly within the site team to manage communication with contractor (RG Engineering)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - reviewed proposed project reporting format and compared with Procore tools for alignment. Cooridnated a meeting with Procore team (Lemoine's - Lauren Wells) for support on generating a reporting template.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed and prepared Pre-Mobilization pending actions to contractor be able to start construction activities. This items will be discussed in a cordinated meeting with contractor (RG Engineering) on May 7th.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Consolidated site team drawings comments for design set improvements and corrections and sent to Robert Molner (Sargent and Lundy)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Procore Team (Lauren Wells & Luis Roman) for Procore Reporting & Meetings tools. Discussion to generate templates to facilitate this regular processes during the project.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Cambalache site team for project drawing review to provide comments to designer (Sargent & Lundy) as part of a quality control and corrective measures to complete de final construction drawing set.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing the RFP 4928 in regard of Boiler Feeds Pumps Breakers Palo Seco Unit 4, this RFP is not related to a critical component the item is similar to one requested for Palo Seco but is not for the BFP.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue review of RFP list of progress projects, send a email request to Saul Falcon of DCMC for the RFP #230902 of Boiler Feeds Pumps Breakers Palo Seco Unit# 4, this project is similar to a project in our tracker, and we need to identify if is different or same.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Pre-Meeting with participation from DCMC: Rick Patterson, Rafael Calderon, Eisha Mercader, Victor Maldonado, Glorimel Torrado, Mark Merritt, Danny Martinez, Ginnell Torres, Rick Patterson, Saul Falcon, Christian Cruz, Sheila Torres, Paul Brown, Carlos Gonzalez, Rafael Cordero, Jorge Aponte, Sheila Torres and Roberto Bosch; and Marc Maceira (HONRA LLC) to discuss draft presentation priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process before presenting to Genera PR.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with critical component tracker updating information. Rafael Torres of Malnat confirm that the PO# 105654 for Aguirre Air Heater Basket (Hot and Cold) may be received by June or July, this delivery is scheduled for August to be deliver. Juan Pascual from Control Associate has confirm that finally they have received the PO #107049 on 5/31/25 for the procurement of Boiler and Burner Recirculation Valve, they will confirm the delivery date for the equipment.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Verifying a list of projects sent by D' Alexander Gonzalez of DCMC for review of (40) FEMA project with our tracker to identify if the FEMA number is correct with our critical component tracker table and to see if they are RFP available for all projects.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Genera Procurement Sulinnette Perez; DCMC Saul Falcon, Pedro Cabrera, and Eduardo Rivera. Discuss Critical Components pending for Air Heater Basket status, Clutch Removal, Boiler Feed Water Pumps, Condensing Circulating Water pumps and NME Funding Projects.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Based on the description of the (40) projects we found (1) they with an RFP available for the projects, they are (23) projects that are aligned with our tracker and FEMA number are the same but the remaining (17) are not in our project list. Send revised list to Pedro Cabrera of DCMC for review and comments.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a recount at the Aguirre warehouse alongside Mr. Juan Vallejo from DCMC to support inventory accuracy. This activity was essential for validating previous counts, resolving discrepancies, and ensuring the reliability and integrity of inventory records.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conductedvariance analysis by identifying discrepancies and investigating inventory inconsistencies to support effective inventory control. This activity contributes to improved accuracy, operational efficiency, and timely corrective actions. Today's efforts centered on validating critical inventory areas.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed cycle counts for the schedule inventory areas assigned for the day. This effort supports ongoing initiatives to improve inventory accuracy between physical stock and system records.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory data analysis and prepare cycle count sheets to support schedule activities at the Aguirre warehouse, assisting Mr. Juan Vallejo of DCMC in his reintegration. Task included validating item locations, verifying stock accuracy, and organizing materials to facilitate a streamlined and efficient inventory process.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a job briefing with Juan Vallejo, and Hernan Machado of DCMC and key warehouse and key warehouse personnel to support Mr. Juan Vallejo reintegration following medical leave. The meting focused on addressing discrepancies identified during the previous inventory activities and reinforcing proper data entry protocols to maintain accuracy and integrity in the cycle count process.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued cycle counting of assigned inventory areas. This task supports the verification and reconciliation of physical stock with system records to ensure accuracy and compliance with regulatory standars.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while stationed at the Aguirre warehouse, prepared a comprehensive inventory report for Mr. Anthony Vega of Genera PR, consolidating data across all warehouse's locations. The report included catalog counts, items details, unit quantities, cost analysis, discrepancies, maximum and minimum stock thresholds, along with percentage indicators reflecting the current status of each facility. Locations reviewed included CR 007 to CR020, AA 062 to AA 079, AD 063 to AD 071, AE 021 to AE 031.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Prepare presentation to GENERA PR respect to PREB resolution projects.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue develop summary to GENERA PR respect to PREB resolution projects.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Discuss of overall status of Critical Components with GENERA PROCUREMENT Sullinet Perez, DCMC Eduardo Rivera, Saul Falcon and Pedro Cabrera.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with DCMC Roberto Bosch, review list of Critical Component and review Legacy Generacion Asset project, identify critical component included on Power Restoration and Critical included on Legacy for Project 817248 Plant repair and System restoration
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria.Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consultant Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Components review project 817248 to determine current RFP already completed.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop summary to GENERA PR respect to PREB resolution projects.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Document DCMC Comments on GENERA Cambalache Schedule - Preliminary Projection of possible Design & Built April/12/2025 send by Carlos De Jesus (DCMC).
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Document Preliminary Drawings Cambalache Gas Storage Enclousure.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings Cambalache BESS Warehouse Building.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache - Drawing Review Andres Concepcion, Carlos De Jesus, Luis Duque and Luis O. Damudt DCMC Partners Cambalache Power Plant team.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and move materials to continue dismantling areas Day 7 acetylene works are being completed on generator 1.1 and clean around the generator. Received clean container for metal disposal.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Internal DCMC contract management meeting with Frances Vallejo, Rafael Calderón and Glorimel Torrado to discuss progress and pending important issues on Siemens, Jaca y Sierra, Homeca and Tesla contracts.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens Energy Contract #00106588 / Siemens Peakers Costa Sur Contract RFI. Working on RFI answers related to CDM / Siemens questions about proper justification to be included for change requests that have no impact on any of the Change Criterias. Preparing email communication to CDM, DCMC and Genera Team. Reviewing status of project execution including upcoming Change Orders and Logistic in preparation for the Delivery Dates.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#5_Invoice# 18334034_Jan 2025. Compliance Review- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PW#9510 Pre-Intervention Review Workshop - Working with CPM Contract #2024-G00142 and TO#10_Invoice# PRIN0008450_Feb 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #502, 503, 504 and 505 from locations AD063 to AD071 for a total of 3,667 pcs.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE021 TO AE031
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AE021 TO AE031
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE021 TO AE031
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE021 TO AE031
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AE021 TO AE031
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 00 062 00 to AA 00 079 000
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 00 062 000 to AA 00 079 000
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 00 062 000 to AA 00 079 000
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 007 and CR 010 using Cycle Count List #372.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 007 to CR 010 at the Aguirre warehouse to start the cycle counts.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location CR 007 and CR 010.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AD063 to AD071 to begin the cycle counts.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AD063 to AD071 Cycle Count List # 481 and 490.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 152 | 342 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 502, 503, 504 and 505.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja BESS Project - All Folders so important information is organized, accurately transmitted and readily accessible.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 151 | 528.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja BESS - Process Project Documents Document Control - Data Management Cambalache BESS - Process Project Documents
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review last SOPs drafts for Observations, Inspections, Drawings and Submittals; dividing SOP between Internal (PMO, Owner, Inspection) and External (Contractor, Vendor, Supplier) including critical items to be considered.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 151 | 453 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform implementation of Locations, Observation Tool new fields, forms inclusion and other deliverables related to the Observations and Documents Tool in the Procore Platform; testing forms for Cambalache Project.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) and Andres Concepcion (DCMC) to discuss the integration of weekly reports and new meeting minutes templates for the Documents and Meetings Tools at Procore.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting hosted by Franklyn Colmenares (CSA) to discuss the team progress at the Procore Platform: SOPs status, integration of new tools, and submittals and rfi workflows.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) to discuss the implementation of Observations Tool in the Procore Platform for the Cambalache Project Site: inclusion of locations, new trades and observations to current form.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of project data such as Contractual Documents (SOW, contractual agreement, standard specifications) to maximize owner input at the Procore Platform, projecting correct time and cost on the Admin tool.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Genera Pre-Meeting with participation from DCMC: Victor Maldonado, D'Alexzander González, Mark Merritt, Esther Rohena, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Glorimel Torrado, Eisha Mercader from DCMC, and Shellsea Maysonet (SMC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Internal DCMC contract management meeting with Frances Vallejo, Rafael Calderón and Glorimel Torrado to discuss progress and pending important issues on Siemens, Jaca y Sierra, Homeca and Tesla contracts.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Review notes with Rafael Calderón (DCMC) in preparation to Contract Management Meeting with Frances Vallejo (DCMC). We go over important points to be discussed from Tesla and Siemens. Also, I review an email from Kevin Futch (Genera) regarding possible changes on tariffs due to Trump policies.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Pre-Intervention Tracker Update - Review week updates on Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, Homeca, CPM, B&V, Siemens Energy and CAPTA.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO09_June2024_Inv#293566-9. Review RFI response from CDM with final invoice. New invoice #90233446. Final document was sent to Jesús Cintrón (Genera) for signature. Final package was created on sharepoint and Pre Intervention Tracker was updated.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review for CDM Smith TO09_June2024_Inv#293566-9. Review RFI response from CDM and complete compliance review verifying deliverables. An email was sent requesting final invoice to complete pre intervention process.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Data entry related to stakeholder mapping on Google Earth (community engagement for Arecibo site)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue the Data entry related to stakeholder mapping on Google Earth (community engagement for Arecibo site)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria work on the process automation related to stakeholder mapping on Google Earth (community engagement for all the sites)
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | Genera PR – Deliverable 11: Project Management ¦ DR 4339 Meeting with Nelvick Santiago (Ricoh PR), Harry del Valle, Jean Pierre Menay, Andres Concepción (DCMC).Mr. Nelvick Santiago, representative of Ricoh Puerto Rico, visited the CVP offices to present information regarding the acquisition of printing equipment through leasing for various sites. It was discussed that equipment specifications must include monthly rental, delivery, toner, parts, services, 11x17 printing capability, and both black & white and color printing functionality. He was informed that the projects may last over a year and that the equipment must be capable of being relocated as needed. Mr. Del Valle noted the need for two technicians per region, each trained in safety protocols and equipped with the appropriate personal protective equipment (PPE). Mr. Santiago confirmed that he will work on the proposal and send it later today.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of Bid-Addendum design drawings stormwater pond culvert and pump inlet plan documents for 4339_9510 BESS_Cambalache project.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on inspections and creates comments in Procore grading plan in BESS site area drawings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on inspections and creates comments in Procore pipping relocation area drawings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache participated in drawing of Procore internal TEAMS meeting discussing status of start project and updates of new drawings of designer Sargent & Lundy with employees Luis Duque, Luis Damudt and Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on inspections and creates comments in Procore new parking area drawings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache project Drawings review meeting with Andres Concepcion (DCMC) for 4339_9510 BESS_Cambalache project.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Completed review of Bid-Addendum design drawings stormwater pond culvert and pump inlet plan documents for 4339_9510 BESS_Cambalache project.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review of Bid-Addendum design drawings stormwater pond culvert and pump inlet plan documents for 4339_9510 BESS_Cambalache project.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Completing the financial data update for the April report on Genera projects Peakers and Bess.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Updating project sites progress spreadsheet and making final adjustments to the April dashboard report on Genera projects, Peakers, BESS, Critical Components and Inventory Management.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 45 | 45 | 45 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for rental car site visits, costa sur, Yabucoa
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel directly from home in Guaynabo to Aguirre to meet with Mr. Juan Vallejo from DCMC. The objective of this visit is to provide support in the reintegration following medical leave.
2025-05-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-after completing the meeting at the Aguirre warehouse with Mr. Juan Vallejo from DCMC, returned to Guaynabo. The visit focused on the reintegration of Mr. Vallejo following medical leave
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 945.12 | 945.12 | 945.12 | Yes |  |  | Home Depot - purchase of cleaning supplies for the trailers being used on the Genera project Deliverable 11
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Costa Sur. Attended Peakers permitting meeting. Items discussed: which permits have been secured and which permits will be part of the General contractor's scope to ensure safety, compliance, and successful construction. German Nunez (Genera); Gilberto Sucre, Frances Vallejo, Jean Pierre Menay, and Sheila Torres-Sterling (DCMC); Carlos Palomares and Rafael Pabon (CDM Smith)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Costa Sur. Attended meeting to discuss open items and needs for the Peakers projects. Items discussed: what Genera needs to do to facilitate the site plan and demolition portion of the project to come to ensure safety and efficiency. Attendees: Rafael Pabon, and Carlos Palomares (CDM Smith); German Nunez, and Jesus Cintron (Genera)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check-In Weekly meeting led by Gabriel Perez - CDM Smith. Topic covered BESS sites RFP's with the Exception of Palo Seco, Vega Baja - Demolition Status, Palo Seco - Decommissioning, Costa Sur - Rule 141 Addendum, Aguirre Phase Approach, & Global Topics. Participants from CDM Smith, CSA Group, Sargent & Lundy, Genera, and DCMC Partners
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Project Needs Weekly Meeting. Gabriel Perez CDM Smith requested support from Jesus Cintron - GENERA for Bess Projects and German Nunez & Rafael Pabon - Genera did the same for Peakers Projects. Action Items Sargent & Lundy - Late Deliverables List, PreCon Activities List for BESS and Peakers and Staffing Requirements at Costa Sur and Yabucoa. Other participants in the meeting Franklyn Colmenares - CSA Group, Abraham Vazquez & Gilberto Sucre - DCMC Partners.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Internal Meeting PM/CM with Sargent & Lundy. Planned weekly activities to achieve final alignment with RGE Final scope, Budget & Schedule for Cambalache, and with ARG Ceres for Vega Baja Installation. Gabriel Perez - CDM Smith, Franklyn Colmenares -CSA Group, Enrique Laya - CDM Smith, Mike Kuczynski and Robert Molner - Sargent & Lundy, and Gilberto Sucre DCMC Partners.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Evaluation of Lead Paint Study in BESS and Peakers Areas.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria EHS Manual Revision and Translation for Genera to implement. Review status with Carolyn Baez DCMC Partners.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur & Aguirre. Met with Harry Del Valle DCMC Partners, to review site mobilization plans for both sites in preparation for Tuesday's Site Visits.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Coordinated Meeting and Agenda for Wednesday's Meeting with Homeca and Genera to discuss time extension request with Jose Lopez - DCMC Partners.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review Legal Comments from RGA Ceres for Vega Baja Installation Project with Francisco Feliu - Genera.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM Weekly Meeting with Gabriel Perez - DCMC and Franklyn Colmenares - CSA Group. BESS Update and prepared for meeting with Jesus Cintron - Genera.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Reviewed with Jose Lopez - DCMC Homeca's status, four week look ahead, Frame 5 coordination with Central San Juan and agenda for meeting with Genera & Homeca.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly Peakers Project Coordination meeting. Meeting attendees were Jesus Cintron (Genera), Abraham Velazquez (DCMC), Juan Mendoza (Genera), Rafael Pabon (CDM Smith), Kevin Futch (Genera), Franklyn Colmenares (CDM Smith).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting to ensure that all stakeholders are informed and aligned on project goals, timelines, and progress. Meeting attendees were from Genera: Jesús Cintrón, Nelson Rosado, Ricardo Palléns, Joaquín Quinoy, Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez; CDM Franklyn Colmenares, Gabriel Pérez; from Sargent and Lundy Mike Kuczynski; DCMC: Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre and others.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Gabriel Perez (CDM Smith), Frances Vellajo (DCMC), Franklyn Colmaneras (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked setting up several Procore meetings for various topics and various teams for weekly updates.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss Adobe PDF Fillable forms for Procore use.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked meeting template and weekly status reports for Andres Concepcion (DCMC).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Procore (Kenna Crouse, Delia Garcia) to discuss Summary of Services SOW that they proposed to finish Financial implementation.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial tools for configurations.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked reviewing and redlining Procore Summary of Services for Financial Implementation.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked Procore correspondence.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) for review of weekly Procore tasks items and to collaborate on any open items.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)continued working on review of Procore SOP's to send drafts to users for review and feedback.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked Procore permissions.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review and finalize SOP for Procore Documents. Sent out to several users to review and provide Feedback before we post the final version for users.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Kermith Calvo by Neptune Internet Services for all Genera Site have construction. Conference call with Harry del Valle (DCMC) about special needs in (Genera) sites. Meeting and Inspection site with Nelson Soler (CDMSMITH), Gilberto Soto (DCMC) and Jaime Lopez (DCMC) about Vega Baja site, includes inclement weather, status de project, Health and Safety Issues, Riggins plan and tranportation plan.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Pick up material for Vega Baja and Cambalache (GENERA) sites in Home Depot Bayamon.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.75 |  | 184 | 322 | 184 | Yes |  | Site | Genera PR – Deliverable 11: Project Management ¦ DR 4339 Meeting with Kermith Calvo (NEPTUNO) and Harry del Valle (DCMC). Mr. Calvo its a representative of NEPTUNO Puerto Rico, that visited the CVP offices to present information regarding the acquisition of internet equipment and service to provide these services in all Genera Sites. Meeting with Gilberto Sucre (DCMC) about the Genera site visits coordination.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Victor Sanchez Manager (NMEAD) Puerto Rico Emergency Management Vega Baja Zone and Osvaldo de Jesus (GENERA) Supervisor about Diesel Transport from Vega Baja to Palo Seco. Training to Xavier Ortiz Pagan by (Sphera) inspector about Health and Safety (Genera).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jesus Cintron (Genera PR) to discuss BESS and Peakers Project needs. Participants: Gabriel Perez (CDM), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peaker Check In meetings to discuss project status, RFPs in process, Procore financials, demolition phase at Vega Baja, contract management for TESLA and Siemens and deliverables. Participants: Gabriel Perez (CDM), Carlos Palomares (CDM), Jesus Cintron (Genera), Rafael Calderon (DCMC), Gilberto Sucre, Abraham Velazquez, Sheila Torres, Raissa Borges (DCMC) and Franklyn Colmenares (CSA)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Peakers project management team to discuss staffing spreadsheet and starting dates for new employees. Participants: German Nunez (Genera), Rafael Pabon (CDM), Abraham Velazquez (DCMC), Carlos Palomares (CDM).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, and Glorimel Torrado, and Marc Maceira (HONRA LLC). Subcontractors: Shellsea Maysonet, Johanna Díaz (SM Consulting), Carlos González and Ginnell Torres ( Integrum)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 4826 - BESS Installation at Cambalache - Continued assembling the FOMB Request for Approval package, focusing on organizing and gathering the required information for Appendix B and C. Ensured that all supporting details were accurately compiled and aligned with FOMB’s submission requirements to facilitate a complete and compliant approval process.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed the third draft of the response letter to PREPA regarding the ER1 Cost Share Program. Shared edits with Jose Ralat, D'Alexzander Gonzalez and Esther Rohena (DCMC) for finalization.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Provided support to Jan Rodriguez, Josue Sanchez, and Jose del Rio from Genera PR in preparing the monthly Power Production and Fuels Consumption report, including discussions on methodologies for calculating accumulated generation, heat rate, and equivalent availability across power plants. Also reviewed and validated fuels consumption data with Jan Rodriguez and Jose del Rio to ensure consistency and accuracy. Continued evaluating the underlying data within the reports to confirm correctness and alignment with reporting standards.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Initiated development of the communications plan for the Genera Connect Financial Tracker and Timesheets in preparation for the upcoming initial go-live. Delivered a project status update during the weekly Genera PR client meeting, with participation from Alejandro Maymi (Genera PR) and DCMC team members D'Alexander Gonzalez, Saul Falcon, Rafael Calderon, Jose Ralat, Victor Maldonado, Esther Rohena, Eisha Mercader, and Mark Merritt. Additionally, held discussions with Hiram Medero and Josue Sanchez of Genera to explore approaches for collecting financial reporting data, specifically targeting actual versus budgeted project costs to support operational cost tracking.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 8 acetylene works are being completed on generator 1.1 and clean around the generator. Assisted Jose Oquendo with Genera Training, and received Porto San with bathroom cleaning
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Weekly look-ahead schedule review and discussion with Gilberto Soto, Gilberto Sucre (DCMC), and Nelson Soler (CDMSmith). The staff intends to help Homeca Recycling with the weekly work plan presented and compare the intended plan with the project progress schedule.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Supervising dismantling, Decommissioning and demolition works planning for phase II. Homeca Recycling should submit an LED abatement removal certification to safely handle and remove lead hazards, protecting workers and staff from lead exposure.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue Working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Yabucoa BESS Project. Looking for possibles discrepancies & measures for efficient resource allocation. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Yabucoa BESS Project. Looking for possibles discrepancies & measures. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the safety documents sent by the contractor Jose Segarra (RGE). The safety plans for the mobilization of personnel are evaluated.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the CONTRACTOR'S MANUAL OCCUPATIONAL HEALTH & SAFETY REV 1 of Genera. (Cutting and welding work procedure)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on a safety presentation for new contractors, seeking to educate staff on the risks associated with the scope of the project as part of DCMC's contractual requirements.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the CONTRACTOR'S MANUAL OCCUPATIONAL HEALTH & SAFETY REV 1 of Genera. (Requisition for hot work)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Compilated and organized action items and information required for Tuesday 5/6/2025 meeting with Genera Facilities Manager (Herminio Arroyo).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Phone calls and meetings with DCMC Partners -Gilberto Sucre to review action and pending items to prepare for contractor mobilization. Phone call with Luis Damudt (DCMC Partners) to review and follow up regarding Cambalache existing warehouse inventory pending tasks.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Monitored and reviewed construction management web platform (Procore) for any documents submitted by contractor. No documents were submitted and pending items were placed as action tasks to follow up with RG Engineering (contractor).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed the Procore Submittal workflow created by Franklyn Colmenares (CDM Smith) to start applying into submittal process. Discussed with Gilberto Sucre (DCMC Partners) and distributed information to DCMC Cambalache Site Team.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed construction initial meeting agenda and discussion topics draft. Meeting will be held May, 7, 2025 to start coordinating contractor (RG Engineering) mobilization to site.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed the Project Scope of Work presentations (Exhibits K, L, M, N) (Civil, Mechanical, Electrical, Architectural) to validate the included tasks that the contractor will be performing in contract.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working with reviewing a list of projects send by D' Alexander Gonzalez (DCMC) in regard of QPR list of projects that need to be verify with critical components and NME projects. Meet with D' Alexander in regard of the Liquidation Damage of each PO contract award that must be review due to procurement meeting with Genera Sulinnette Perez of Genera mention that is the responsibility of each plant site to implement the LD to the vendor that does not deliver on time.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with bi-weekly report status update for critical components projects. Reviewing a list of projects send by D' Alexander Gonzalez (DCMC) in regard of QPR list of projects that need to be verify with critical components and NME projects.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue working with reviewing a list of projects send by D' Alexander Gonzalez (DCMC) in regard of QPR list of projects that need to be verify with critical components and NME projects. Reviewing PO95750 and 107032 for BFWP of Costa Sur/Aguirre if was included the inner barrel with the pump, also the RFP 225916 if it was included the pump and inner barrel.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: Mark Merritt, D' Alexzander Gonzalez, Paul Browne, Jose Ralat, Rafael Calderon, Esther Rohena, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Keylamerari Sierra, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Maria Sanchez and Alejandro Maymi Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed inventory data analysis and prepare cycle count sheets for schedule activities at the Palo Seco warehouse, supporting DCMC Mr. Giovanni Taffanelli. Responsibilities included validating item locations, reviewing stock accuracy, and organizing materials to ensure an efficient and streamlined inventory process.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while stationed at the Palo Seco warehouse, prepared a consolidated inventory report for Mr. Anthony Vega of Genera PR, incorporating data from all warehouse locations. The report included catalog counts, items details, unit quantities, cost analysis, discrepancies, maximum and minimum stock thresholds, along with percentage indicators to reflect the current inventory status of each facility. Locations reviewed included AA 080 to AA 088, AE 000 to AE 006, CR 020 to CR 037, AE 032 to AE 041.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle counts for the scheduled inventory locations assigned for the day, specifically covering AE 000 to AE 006. This activity is part of the ongoing efforts to enhance inventory accuracy and ensure data alignment with system records.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a recount at the San Juan warehouse alongside Mr. Giovanni Taffanelli from DCMC to verify inventory accuracy. This task was essential for validating previous counts, resolving discrepancies, and ensuring the reliability and integrity of the inventory records.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted variance analysis by identifying discrepancies and examining inventory inconsistencies to support effective inventory control. This effort contributes to enhanced accuracy, operational efficiency, and timely corrective actions. Today's focus was on validating high-priority inventory areas to ensure alignment with system data.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a job briefing with Juan Vallejo, Milton Flores and key DCMC warehouse personnel to review discrepancies identified during the prior week activities. Emphasis was placed on reinforcing accurate data entry protocols to enhance inventory integrity and ensure procedural compliance.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review current list of Fuel Efficiency list to verify if components of Cambalache was included in LGA 663383 project.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review presentation to GENERA PR respect to PREB resolution projects.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Discuss with GENERA PR- Alejandro Maymi and DCMC; D'Alexzander Gonzalez PREB resolution projects actual status.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Alejandro Maymi, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of the CCL Tracker to identify cases with discrepancies in purchase orders or contract information. The CCL Tracker was reviewed to determine which cases have issued purchase orders or executed contracts that present inconsistencies or conflicting information in the documented records.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Verify RFP 225916 reason cancellation. Need confirmation from the End User GENERA-PR Miguel Beauchamp.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary BESS Cambalache VE Accelerated Schedule
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Cambalache Alternative Foundation Description_042925_rev7
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Control House and Switchgear Clean Agent Calculations
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Cambalache BESS INSTALLATION LAYOUTS.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document different discipline Demolition, Architectural, Structural, Electrical, Site, Arc Procore Folder 100- 6. Appendix D.1- Design Electrical.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 8 acetylene works are being completed on generator 1.1 and clean around the generator. Received Guard trailer station and inspected the same.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Continue working on Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team, CDM Smith PM team (Gabriel Sepulveda), Sargent & Lundy ( (Mike Kuczynski) Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Lemoine Procore (Lauren Wells).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Continue working on Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC Participants: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and others. From Genera: Maria Sanchez and Alejandro Maymi).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review. Siemens Chek-In Meeting: Peakers Costa Sur project Status follow-up and review of contract schedules. Participants from Genera (Jesus Cintron, German Nunez), CSA (Franklyn Colmenares) CDM PM (Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC Contract Manager - (Rafael Calderon, Abraham Velazquez, D'Alexander González and Sheila Torres).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AE000 to AE006 to begin the cycle counts.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AE032 to AE 041
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AE032 to AE 041
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE032 to AE 041
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AE032 to AE 041
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AE032 to AE 041
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 00 080 000 to AA 00 088 000
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels and recount from locations AA 00 080 000 to AA 00 088 000
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse, investigated discrepancies between locations AA 00 080 000 and AA 00 088 000 and other locations are being checked for missing material.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 00 080 00 to AA 00 088 000
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts by locations CR 020 and CR 037
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 020 and CR 037 using Cycle Count List # 511,512,513.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations CR 020 and CR 037.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 020 and CR 037 at the Aguirre warehouse to start the cycle counts.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE000 to AE006.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AE000 to AE006 Cycle Count List # 514.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies with Wandimar Jimenez from Genera PR in Recount Lists #522 and 523 from locations AE000 to AE006 for a total of 3670 pcs.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 522 and 523 from locations AE000 to AE006.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 151 | 528.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Cambalache BESS Documents_Coordination with Lauren Wells (DCMC) for SOPs/Vega Baja BESS Document Data Mgmt
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Cambalache BESS Documents Data Mgmt /Coordination with Lauren Wells (DCMC) & Luis Roman (DCMC) Tasks_Submittals_RFI/Vega Baja BESS Document Data Management/Costa Sur PEAKERS Data Management
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) and Theresa Perez (DCMC) to go over Procore weekly check-in: Discussed the Documents Tool implementation process and output, activation of new tools for project staff, SOP reviews status and upcoming work load.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 151 | 113.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting for BESS Projects Check-in hosted by Franklyn Colmenares (CSA). Also in call: Gabriel Perez (CDM Smith), Lauren Wells (Lemoine), Gilberto Sucre (DCMC), Discussed upcoming construction kick-offs for BESS Projects, different RFP's status, Procore execution, and contractor's mobilizations, among others.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting for Peakers Projects Check-in hosted by Franklyn Colmenares (CSA). Also in call: Rafael Pabon (DCMC), Lauren Wells (Lemoine). Discussed upcoming workload for Peakers Project, different RFP's status, and Procore execution, among others.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review final SOP versions prior to publishing for external users: Submittals, RFI, Emails, Photos. Also; review for internal users SOPs
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 151 | 37.75 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Jean Pierre Menay (DCMC) to take on the Genera Safety Training prior to any site visit (client requirement).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 151 | 528.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Collaborated directly with DCMC field staff at Vega Baja and Cambalache with testing on platform tools prior to begin providing input for record; review users permissions and workflow templates.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - _pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18334035_Jan2025. Continue reviewing invoice. This invoice has 8,505 excel lines with information to be reviewed. Review invoice notes, identify duplicates, start working on individual entries that does not need corrections.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - _pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18334035_Jan2025. Continue reviewing invoice. This invoice has 8,505 excel lines with information to be reviewed. I started with the 120 Employee rates review.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 -Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, and Glorimel Torrado; and Marc Maceira (HONRA LLC). Also, Shellsea Maysonet (SM Consulting); and from Genera: Alejandro Maymí Ronda, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - _pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18334035_Jan2025. Preparing master excel to review the invoice and identify mistakes. Read contract and task order, also verify the invoice rates with the contract rates.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 -Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, CPM, Tesla, Homeca, B&V, Siemens and CAPTA. Verify pending invoices for this week, find discrepancies on CDM pending invoice number and request verification. Also, send report for CPM invoices to José Ralat (DCMC) pending for payment and RFI invoices.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting via Teams with Genera Team, Jorge Bracero and External Consultant Lymaris Otero to discuss the weekly community relations plan.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Data entry related to stakeholder mapping on Google Earth (community engagement for Vieques site)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Corporate Affairs Meeting with Genera’s Team: Ivan Baez, Jorge Bracero and Rafael Rodríguez Ema to facilitate communication, enable project teams to exchange information, address concerns, and coordinate efforts.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams Meeting with DCMC Team: Frances Vallejo Rosich, D'Alexzander Gonzalez and Mark Merritt. In the meeting was the Genera Team: Jesus Cintron, Kevin Futch, Francisco Santos, German Nunez, Alejandro Maymi and Sarahi Medina Nieves. In the meeting was the CDM Smith: Juan Mendoza, Rafael Pabon and Carlos Palomares. The meeting was about Peakers Check In.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey. In the meeting was the Genera PR Team: Jorge Bracero, Jesus Cintron, Joaquin A Quinoy, Ricardo Pallens, Maria Sanchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczinsky and Nelson Rosado. The meeting was about the Bess Project.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Data entry related to stakeholder mapping on Google Earth (community engagement for Toa Baja and Salinas Site)
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Workshop to receive input on how Genera works with content distribution channels with their communities. The meeting was attended by the Genera PR team: Ivan Baez Santiago and Jorge Bracero
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | Genera PR – Deliverable 11 –Project Management -DR4339: Start the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. I am currently drafting the document using the correct format, following the structure and style of the original English version to ensure consistency, technical accuracy, and compliance with established standards. This draft will include appropriate terminology and linguistic adaptations that preserve the clarity and original intent of the content while maintaining formal sections, headings, numbering, and references. The manual contains 360 pages.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management ¦ DR4339: I contacted Mr. Nelvick Santiago (Ricoh PR) by phone regarding the proposal for the rental of copiers for the project sites. Mr. Santiago informed me that he had sent the proposal on Friday afternoon. I told him I had not received it, and he proceeded to resend the document, as he had used the wrong email address. Once I received the document, I forwarded it to Ada Díaz, Harry del Valle, Jean P. Menay, Frances Vallejo, and Gilberto Sucre (DCMC).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management - DR4339: I am in the process of contacting and searching for cleaning companies that offer their services island-wide for the different sites. I have reached out to Mrs. Rivera, a representative of Mangual Office Cleaning Services in San Juan, and Mr. Torres from Cleaning Puerto Rico. I have requested a proposal from them, provided they meet the required safety standards. I indicated that the personnel responsible for office cleaning must have the following training and knowledge,
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 –Project Management -DR4339: Resumed the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. I am currently drafting the document using the appropriate format and closely following the structure and style of the original English version to ensure consistency, technical accuracy, and compliance with established standards. This draft incorporates precise terminology and linguistic adaptations that preserve the clarity and original intent of the content while maintaining formal sections, headings, numbering, and references. The manual comprises a total of 360 pages.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management - DR4339: Continued translating the Safety, Health, and Environment (SHE) Manual from English to Spanish. Currently, I am drafting the document in the appropriate format, meticulously following the structure and style of the original English version to ensure consistency, technical accuracy, and adherence to established standards. This draft incorporates precise terminology and linguistic adaptations that maintain the clarity and original intent of the content while preserving formal sections, headings, numbering, and references. The manual consists of a total of 360 pages.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of Bid-Addendum design drawings of Battery Energy support system foundation plan documents for 4339_9510 BESS_Cambalache project.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on inspections of documents creates comments in Procore drawings status report and BESS arrangement plan for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on inspections of documents creates comments in Procore RFP Schedule of proponent RGE for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on inspections of documents creates comments in Procore demolition drawings for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review of Bid-Addendum design drawings of Battery Energy support system foundation plan documents for 4339_9510 BESS_Cambalache project.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 124 | 124 | 124 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Required background check and certification ID to enter restricted facilities while performing duties required of my position Twic ID
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Getting familiar with Procore Analytics to provides a detailed report with insights and visualizations related to the progress and performance of action plans, ensuring that project teams can effectively manage tasks and meet their project goals.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue navigated and gathering data from Procore Analytics to provides a detailed report related to the progress and performance of the project and project teams.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Rafael Pabon (CDM Smith), Luis Roman (DCMC), Paola Arroyo (Genera), Jorge Bracero (Genera), Lauren Wells (Lemoine), Foster Veazey (Lemoine), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Franklyn Colmenares (CDM Smith), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Sheila Torres (DCMC).
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 43.61 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection from home offices San Juan to Vega Baja Site (18.446230, -66.392561) from V Management Zone Vega Baja meeting with Manager Victor Sanchez. From (Vega Baja Site) 18.446230, -66.392561) to Projects. From Bayamon to Metro Offices Park. Metro Offices Park to cll Hidalgo San Juan. Purpose Site inspection, meeting with Emergency Management, Genera Supervisor and pick up material for the pro Total Distance 62.3 miles
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.42 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the purpose of the visit was to review the progress achieved and assist Mr. Giovanni Taffanelli from DCMC.
2025-05-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.35 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the purpose of the visit is to review the progress achieved so far and assist Mr. Giovanni Taffanelli from DCMC.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore summary of services along budget/billed hours for work complete.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Costa Sur, Site visit to take inventory of existing tools and materials to enhance productivity, reduce costs, and maintain operational efficiency. Also, note and record locations of potential laydown and staging areas for the project. Attendees: Lemuel Nieves, Reinaldo Romero, and Miguel Del Valle (Sargent & Lundy)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Site visit to Costa Sur, with team members. Items reviewed: the onsite conditions, new plan layout and field conditions to assess quality, safety and compliance with regulations. Attendees: Lemuel Nieves, Reinaldo Romero, and Miguel Del Valle (Sargent & Lundy).
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 225 | 281.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre - Site Inspection Met Genera - Alexis Cruz and Harry del Valle - DCMC, visited the site to evaluate access roads, parking, staging, and temporary facilities.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Site Inspection to evaluate contractor temporary facilities, laydown and parking facilities. Met with Genera Plant Manager - Miguel Beauchamp, Lemuel Nieves - Sargent & Lundy, and Abraham Velazquez, Carlos de Jesus and Gilberto Sucre - DCMC.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Tesla Warranty - Project Management and Technical Review Meeting focused on critical aspects of battery warranty, site visit observations, and delivery timelines. Concerns were raised about battery warranty timelines, emphasizing that warranties commence when batteries become operational and detailing restrictions on storage duration. Rafael Calderon DCMC shared comprehensive warranty documentation while discussing installation responsibilities and the risks tied to exceeding warranty periods due to project delays. The team also outlined change orders and noted a projected 6-8 month delay for Megapacks, planning to finalize a change order package for presentation to Genera. Meeting participants DCMC Rafael Calderon, Frances Vallejo, Gilberto Sucre, Foster Veazey.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L / CDM Smith Weekly BESS Drawings Meeting led by Gabriel Perez - CDM Smith Reviewed scheduled Sargent & Lundy IFC dates vs. Construction Project needs for Cambalache and Vega Baja in general dates are late to support construction. Participants Sargent & Lundy, CDM Smith & DCMC Partners.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting to discuss the contractual verbiage for the warranty of the Tesla batteries, the schedule, and how potential storage prior to installation could negatively impact the warranty for the client. DCMC attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Glorimel Torrado, Rafael Calderon, and Sheila Torres.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence for setting up teams on home page, document control and other items.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore reporting for Andres Concepcion (DCMC).
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for Andres Concepcion (DCMC).
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)worked on Procore configurations.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on SOP's review and updating tools tracker.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks tracker.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks updates for our internal Procore team.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on organization and review of current SOP's.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Inspection new equipment in site and review its documentation. Health and Safety site inspection about the job in Vega Baja Site to prevent accidents, injuries, and other incidents or hazards.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2.75 |  | 184 | 506 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria : Call with Osvaldo de Jesus (GENERA) about all projects. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Identification | Direct-PA | Activities necessary for project identification (i.e., meetings, coordination, documentation request/review) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Safety Meeting before job starts in Vega Baja Site. Site inspection. Meeting with Homeca (Carirma Sanchez and Eduardo Ramos), DCMC Jaime Lopez, Jose Pesquera, CDSMITH (Eduardo Laya, Nelson Soler and Manuelli Concepcion) about Vega Baja Project.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Health and Safety Inspection of the jobs in the site. Review the procedure on Vega Baja Genera Site to identify potential hazards that could lead to accidents or injuries, ensure compliance with legal standards, and enhance overall productivity.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call. We discussed sites, staffing update per site, Procore Financials status, Trailer update and Governors visit to Vega Baja. Participants: Mike Merritt, Mark Merritt, Lauren Wells, Barry Scanlon (DCMC).
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR-¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and prepare new slides dividing by sites for BESS and Peaker project using Vizio application in order to update employees per site and their information.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting to discuss battery warranty discussion. We discussed the terms of the Tesla contract regarding warranty and deliverables. Participants: Foster Veazey (Lemoine), Rafael Calderon (DCMC), Sheila Torres (DCMC) and Gilberto Sucre (DCMC)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11 ¦ DR 4339 - Hurricane Maria - Meeting with Paola Arroyo (DCMC) to discuss Vega Baja and Cambalache community plans, discuss talking points for Tesla presentation.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with BESS and Peaker Project management team to provide a project update to DCMC Paola Arroyo, new community engagement liaison. Participants: Paola Arroyo (DCMC), Gabriel Perez, Rafael Pabon (CDM)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 4826 - BESS Installation at Cambalache - Continued assembling the FOMB Request for Approval package, with a focus on organizing, gathering, and renaming files to ensure clarity and ease of reference. Concentrated on the RFP documentation, downloading, reviewing and formatting the remaining 13 required documents. Ensured that all supporting materials were accurately compiled and aligned with FOMB’s submission requirements to support a complete, well-structured, and compliant approval package.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - TESLA Battery warranty discussion with Frances Vallejo, Foster Veazey, Rafael Calderon and Gilberto Sucre (DCMC)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Participated in a strategic alignment meeting focused on federal projects to review ongoing initiatives, funding streams, and compliance requirements. Discussed key priorities, potential challenges, and coordination efforts to ensure alignment with federal guidelines, program objectives, and reporting standards. The discussion also addressed timelines, resource needs, and next steps to support the successful execution of federally funded projects. with Jesus Cintron, Joaquin Quinoy, Jorge Sanchez and Carlos Negron (Genera) D'Alexzander Gonzalez, Roberto Bosch, Pedro Cabrera, (DCMC) and Shellsea Maysonnet and Joanna Torres (subcontractors).
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed the fourth draft of the response letter to PREPA regarding the ER1 Cost Share Program. Integrated reference materials, including letters from PREPA and Vivienda provided by Jesús Cintrón (Genera), to ensure accuracy and contextual alignment. Formatted all three appendices to meet internal standards and improve clarity. Shared the final version of the response letter and appendices with D’Alexzander González and Esther Rohena (DCMC) to proceed with routing for signature and formal submission.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - RFP 4826 - BESS Installation at Cambalache - Continued assembling the FOMB Request for Approval package, with a focus on organizing, gathering, and renaming files to ensure clarity and ease of reference. Concentrated on the RFP documentation, downloading, reviewing and formatting 10 of the 23 required documents. Ensured that all supporting materials were accurately compiled and aligned with FOMB’s submission requirements to support a complete, well-structured, and compliant approval package.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued populating data for the fiscal year heat rate calculation of the power plants and supported Jan Rodriguez from Genera PR with validation of the heat rate figures. Reviewed the monthly Power Production and Fuels Consumption report to ensure data accuracy ahead of its submission to Cristina Ribas from Genera PR's compliance team. Additionally, resolved broken reference issues within the master report to maintain integrity and functionality of the reporting framework.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Initiated the development of a report to calculate plant heat rate for the current fiscal year (July 2024 through June 2025), in response to a request from Josue Sanchez and Jan Rodriguez of Genera PR. This effort involved defining the data parameters and methodology required to support accurate and comprehensive reporting aligned with operational and performance tracking needs.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria I supervised the Contractor Homeca Recyclers. I also read multiple submittals, I kept up the submittals that needed my attention for today or were due today. I received various phone calls from the project personnel (from Jean Menay DCMC, & Manuely Concepcion from CDM Smith). I also worked or updated RFI #23. Answered multiple emails, read multiple emails I needed to in order to keep up with all the communications (regarding the movement of the Diesel Transport to San Juan & the crane operators' certification for the use of heavy lifting weights.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Meeting minutes built, revised, and distributed to Gilberto Sucre, Jaime Pesquera (DCMC Partners), Noel Soler (CDM Smith), Carirma Sanchez, and Eduardo Ramos (HOMECA Recycling)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Prepared the Agenda for the weekly progress meeting for the Vega Baja Site to help discuss project issues and improve communication across the site team. Weekly project meeting with HOMECA representatives Carirma Sanchez and Eduardo Ramos. Project Schedule and progress discussion to mitigate risks, optimize resource allocation, and achieve project objectives effectively.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Meeting minutes built, revised, and distributed to Gilberto Sucre, Jaime Pesquera (DCMC Partners) & Noel Soler (CDM Smith).
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Meeting with S&L, Mike Kuczynski, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDMSmith), Andres Concepcion, and Gilberto Sucre from DCMC Partners to discuss the BESS IFC design delivery status.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Central Aguirre. Attendees, Alexis Cruz (Genera), Gilberto Sucre (DCMC), Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work of the BESS Projects, reviewing drawings on site, verified possible routes for BESS Delivery, the existing infrastructure, project needs, looking for construction compound areas. Measured areas.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 167 | 292.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Central Costa Sur. Attendees, Miguel Beauchamp (Genera), Lemuel Nieves (Sargent & Lundy), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos De Jesus (DCMC) & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work of the BESS & Peakers Projects, reviewing drawings on site, verified all existing infrastructure, project needs, review demolition areas, looking for construction compound areas. Measured areas.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on evaluation of RFP No. 4736 (ATTACHMENT J AND K)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project meeting with the client Herminio Arroyo (Genera) for the planning of work and monitoring of environmental concerns as part of the decision-making process, to provide comprehensive insights into the potential ecological consequences of the project.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria - Cambalache - Meeting with Facilities Team where issues related to the start of the project and coordination were discussed according to the previous meeting with Herminio Arroyo (Genera)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Cambalache DCMC site team (Luis Damudt, Carlos De Jesus, Luis Duque, Jorge Mercado) for recurrent construction management coordination to keep project on track by making sure team knows what to do, deadlines are met, and issues are addressed.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared materials and visuals (drawings) for project SOW discussion with Genera facilities team regarding site logistics.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Site Meeting and walktrough with Genera secutiry and facilities management (Nelson Jimenez, Herminio Arroyo) for facility security and access process and plan discussion.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Design Management meeting with Sargent & Lundy (Robert Molner) CDM Smith (Gabriel Perez) DCMC Partners (Gilberto Sucre) for weekly updates regarding design progress of project.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with GeneraPR Facilities Team (Herminio Arroyo, Roseanne Perez) and DCMC Partners (Jorge Mercado & Luis Damudt) for coordination and discussion of site logistics during the construction for scheduling, safety measures, and sustainable practices to minimize risks and maximize productivity.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated daily schedule and organized action items and meeting agenda for meetings for the day. Received Luis Roman (DCMC Partners) on site for Procore orientation.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Luis Roman (DCMC Partners) on site to discuss Procore process and use on the field.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Meet with Pedro Cabrera, D' Alexander Gonzalez, Roberto Bosch and Eduardo Rivera of DCMC in regard of the Fuel efficiency project to understand what has been consider in our critical component tracker, NME and Legacy project, also to revise if new amendment will be required to be included in CE of some of the Fuel Efficiency Projects.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working on update of delivery of equipment on critical component tracker. Review in Asset Suite the PO 100975 that was deliver to Mayaguez plant. Working with fuel efficiency table of project that will be included as part of our critical component tracker we are pending respond by Joaquin Quinoy and Jesus Cintron of Genera if will be included. Reviewing DI 1238150 in regard of cost.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Verify the cost for the project 663383 to provide information to Genera. Send an email to Joaquin Quinoy of Genera related to the project 663383 of GT11N1 that is for unit 1 and funding for unit 2 and 3 of cambalache is a more reduce SOW that does not required rehabilitation or replace for new GT, send also the requested funding for the 663383.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working in reviewing the critical component tracker. Send follow up to Vendor Rafael Torres of Malnat to provide updated status for delivery date of Palo Seco and Costa Sur Air Heater Basket. Send email to vendor Jose Camuy of Allied Power Technologies for follow up on Aguirre 13kV breaker.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing the project# 663383 to confirm on resolution that the Fuel Efficiency project integrated for the Remove and install new Convert to GT11NM. The upgrade configuration from GT11N to 11NM which includes new blades and turbine blades, heat shield segments, blade carrier and exhaust shroud, after the review we had consider that project is the same under DR4339-663383 but for Unit 1 Rehabilitation of Cambalache, it does not include unit 2 or 3.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed variance analysis by identifying discrepancies and evaluating inventory inconsistencies to strengthen inventory control measures. This initiative supports improved accuracy, operational efficiency, and timely corrective actions.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a job briefing with Hernan Machado, Giovanni Taffanelli and key DCMC warehouse personnel to align on upcoming operational priorities and ensure clarity on assigned task. This session focused on improving coordination, reinforcing accountability, and preparing for the week inventory activities.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while based at the Costa Sur warehouse, developed and submitted a consolidated inventory report for Mr. Anthony Vega of Genera PR, encompassing data from all warehouse sites. The report provided a strategic overview of catalog records, unit quantities, cost assessments, inventory discrepancies, and stock level thresholds, including maximum and minimums. It also featured key indicators to reflect current inventory health. Locations assessed included AA 089 to AA 095, CR 037 to CR 065, AE007 to AE 012, AL 001 to AL 012.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed cycle counts for the designated inventory locations scheduled for the day, specifically covering AA 089 to AA 095. The activity was carried out as part of ongoing activities to improve inventory accuracy and ensure alignment between physical stock and system records. Additional efforts included identifying discrepancies, validating bin locations, and documenting observations for follow up actions.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC to confirm inventory accuracy. This effort was critical for validating prior counts, addressing discrepancies, and ensuring the reliability and integrity of the inventory records.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory data analysis and prepare cycle count sheets for schedule activities at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC. Key responsibilities included validating item locations, verifying stock accuracy and organizing materials to support an efficient and structured inventory process.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue searching motions and resolutions issued by PREB and GENERA regarding to Equipment and Material Project 673691.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Revision Proyectos Federales Status meeting with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz, and Roberto Bosch; from SMC Shellsea Maysonet;, to discuss priorities and deliverables, status updates, identify next steps for projects under Federal Grant.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Searching motions and resolutions issued by PREB and GENERA regarding to Equipment and Material Project 673691.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Discuss of PREB resolution regarding to Equipment and Material Project 673691 with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz, and Roberto Bosch and Eduardo Rivera.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Prepare a report of each motions and resolutions issued by PREB and GENERA regarding to Equipment and Material Project 673691 with conent included in each one.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document "Requerimientos particulares sobre Salud, Seguridad y Seguridad física para Cambalache" and send to discution an evaluation with Jorge Alexis Mercado DCMC
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache Facilities Coordination, Herminio Arroyo Genera PR, Andres Concepcion, Luis O. Damudt DCMC Partners Cambalache Power Plant team.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Comments on BESS Cambalache VE Accelerated Schedule send by Carlos de Jesus DCMC
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore Submittals Workflow send by Andres Concepcion DCMC.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Continue to Review document Comments on BESS Cambalache VE Accelerated Schedule send by Carlos de Jesus DCMC
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache Security Coordination, Herminio Arroyo Genera PR Nelson Medina FSO Genera PR, Andres Concepcion, Luis O. Damudt and Jorge Mercado DCMC Partners Cambalache Power Plant team.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Weekly meeting with contractor Homeca (attended the meeting: Carirma Sanchez, from Homeca, Eduardo Ramos-Homeca, Nelson Soler, CDM Smith, Enrique Laya CDM Smith, Franklyn Colmenares CSA Group, Gabriel Perez Sepulveda CSA Group, Manuelli Concepcion CDM Smith, Jose Linares, DCMC, Gilberto Sucre DCMC, Gilberto Soto, Jean Menay, DCMC). Supervised the Contractor Homeca. I created RFI's and worked with RFI's that needed my attention (#39 & Meeting Certification payment), I also read and close (#68 for example) submittals, I worked the submittals that needed my attention for today. I read & answered emails I needed to in order to keep up with all the communications and updated throughout the day.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Continue working on Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Preparing email communication to DCMC Team and CDM project management team with updates and schedules revision for Tesla deliveries. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 164 | 410 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Continue working on Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, Mega Packs and tariffs for all plants. Meeting participants CSA (Franklyn Colmenares), CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczynski) Vincent Skochdopole), and DCMC (Rafael Calderon)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Battery Warranties Internal Meeting) Meeting with project management Team. Contract 106761 - Reviewing current contract requirements for warranties based on equipment component and specific vendor. Meeting participants DCMC (Rafael Calderon, Frances Vallejo, Gilberto Sucre, Foster Veazey)
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #550 and 551 from locations AE007 to AE012.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AL001 to AL012
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations Al001 to AL012
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AL001 to AL012
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations Al001 to AL012
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AL001 to AL012
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 00 089 000 to AA 00 095 000
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 00 089 000 to AA 00 095 000
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 00 089 000 to AA 00 095 000
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations CR 037 to CR 065
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 037 to CR 065 at the Aguirre warehouse to start the cycle counts.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts 539/540/541/544 locations CR 037 to CR 065
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 037 to CR 065 using Cycle Count List.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations AE007 to AE012 to start the cycle counts.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AE007 to AE012 Cycle Count List # 538.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #550 and 551 from locations AE007 to AE012 for a total of 2,031 pcs.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AE007 to AE012.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Cambalache BESS to ensure documents are created, reviewed, distributed, tracked, stored and archived in an organized and controlled manner.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Cambalache BESS Procore addition of GENERA Safety Personnel/Yabucoa BESS Data Management/Vega Baja_Cambalache BESS Procore addition of DCMC Safety Personnel for a successful safety staffing framework.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Meetings Tool for the implementation of different Agenda and Minutes templates to be used at Cambalache Power Plant. Also, modify existing forms for Inspections for QA/QC of items available.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Walkthrough on Cambalache Project Site; Review documentation regarding Procore users feedback and new tools implementation.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 |  | 151 | 113.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the progress of Observation Tools implementation by discussing its features with DCMC Construction Manager (Luis Damudt) and Safety Officer (Jorge Mercado) at Cambalache Site.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 151 | 113.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Site Operations staff Herminio Arroyo and Roseanne Perez (Genera PR), in addition to Andres Concepcion, Luis Damudt and Jorge Mercado (all DCMC); internal discussion for upcoming construction kick-off on Cambalache site; GeneraPR concerns about site usage, designated construction areas, and environmental regulations compliance.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Update CPAs on Pre Intervention Tracker. Also, update started invoice for S&L. 3 CPA's were updated on tracker according to report (90233446, pending; 18322767 approved and 18334031 approved. This update is in preparation for Friday internal meeting.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Continue with contract review documentation to identify important information about equipment warranty. Provide guidance and support to project managers and other stakeholders on contractual matters. After Change order meetings, to this review we include reading on System Mega Packs differences between contracts. Also, reviewing about safety and pre delivery activities on site.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Change orders meeting with the following participants: Franklyn Colmenares (CSA), Gabriel Sepúlveda(CDM), Rafael Calderón (DCMC) and Glorimel Torrado (DCMC). This meeting was to follow up on pending information regarding Change Orders. Sargent & Lundy is supposed to finish justifications tomorrow and Tesla will work over that information. As soon as the change orders are submitted, we will request final approval from Genera. Also, an internal meeting with Genera and DCMC financial teams needs to be coordinated after change order information is submitted to evaluate the impact on milestone payments. In this meeting we discuss all pending actions to complete the change orders for Tesla.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 |  | 149 | 409.75 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Contract review documentation to identify important information about equipment warranty. Provide guidance and support to project managers and other stakeholders on contractual matters. This is in preparation for meeting today @330pm.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 149 | 372.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Continue with contract review documentation to identify important information about equipment warranty. Provide guidance and support to project managers and other stakeholders on contractual matters. Work with shared document with Rafael Calderón (DCMC) to include important aspects of the contract about the warranties. This document will be shared with the team. We also gather together in a working session to review our notes on today's research previous to the meeting.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 149 | 37.25 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Battery Warranty internal meeting with DCMC Foster Veazy, Gilberto Sucre, Glorimel Torrado and Rafael Calderón. This meeting was to discuss about the Tesla equipment warranty and the established per contract time frames that warranty starts or any liquidated damages that can apply. This meeting was until 4 but I participate until 345pm.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Finish and delivered the document with the talking points and create a Speakers Bio’s to highlight as part of the BESS project for Jesus Cintron from Genera's Team how is participating in the Caribbean Renewable Energy Forum tomorrow.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting in Meets about BESS & Peaker update with: DCMC Partners Team: Frances Vallejo Genera's PR Team: Jorge Bracero CDM Smith Team: Rafael Pabon and Gabriel Perez Sepulveda.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.75 |  | 139 | 521.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Work and finally deliver the Fact Sheet for Genera PR of the BESS project focused on the Cambalache, Arecibo site. The Fact Sheet was deliver to Genera Team: Jorge Bracero, Ivan Baez Santiago and Rafael Rodriguez.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.75 |  | 139 | 382.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Create talking points and create a Speakers Bio’s to highlight as part of the BESS project for Jesus Cintron from Genera's Team how is participating in the Caribbean Renewable Energy Forum tomorrow.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management - DR4339: I continue translating the Safety, Health, and Environment (SHE) Manual from English to Spanish. I am currently editing the document to match the appropriate format, correcting terminology and language errors, and closely following the structure and style of the original English version to ensure consistency, technical accuracy, and compliance with established standards. Completed the review and correction of 20 pages of the manual.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management - DR4339: Continued editing the Spanish translation of the Safety, Health, and Environment (SHE) Manual. Focused on refining terminology, correcting language issues, and aligning the format with the original English version. Reviewed and revised 12 pages out of 360.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management - DR4339: I am continuing the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. My current focus is on editing the translated content to align with the required formatting, correcting terminology and language usage, and ensuring adherence to the original English version’s structure and style. This process guarantees consistency, technical precision, and compliance with established standards. Completed the review and revision of 15 pages of the manual.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of Bid-Addendum design drawings of Battery Energy support system control room details documents for 4339_9510 BESS_Cambalache project.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on creates comments in Procore related to relocation and not included items in design drawings for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on creates considering Procore design drawings for office distribution of laydown for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 134 | 335 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur participate in site meeting with visit with Sargent and Lundy with employee Lemuel Nieves Diaz, to review demolition in site and laydown area with DCMC Harry Del Valle, Gilberto Sucre and Abraham Velazquez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache participated in drawing of Procore internal TEAMS meeting discussing Procore document, about the first contractor meeting and special point to start project communication with employees Luis Duque, Jorge Mercado and Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 134 | 201 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on update of documents creates comments in Procore demolition drawings for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review of Bid-Addendum design drawings of Battery Energy support system control room details documents for 4339_9510 BESS_Cambalache project.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache project update meeting with Andres Concepcion (DCMC), Gilberto Sucre (DCMC) for 4339_9510 BESS_Cambalache project.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Initiating the process of connecting Procore Analytics to Power BI in order to develop a detailed report of the project progress and project team performance.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Procore projects data migration to Power BI for reporting purposes to ensure data integrity, streamlined operations, and real-time data access.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 30.5 | 30.5 | 30.5 | Yes |  |  | Generates PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Receipt, copies of the key to the trailer office of the Cambalache power plant project.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 27.5 | 27.5 | 27.5 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits with rental vehicle, costa sur site walkthrough
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 44.73 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection from home offices San Juan to Vega Baja Site (18.446230, -66.392561). From Purpose Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure Total Distance 63.9 miles
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 161 | 0.7 | Yes |  |  | Harry Del Valle 5/6/2025 Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Costa Sur Power Plant to Central Aguirre to Home Office Luquillo. Meeting & Coordination for Central Costa Sur. Attendees, Miguel Beauchamp (Genera), Lemuel Nieves (Sargent & Lundy), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos De Jesus (DCMC) & Harry Del Valle (DCMC). Total Mileage 230 miles
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.3 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-travel directly from home in Guaynabo to Costa Sur to meet with Mr. Hernan Machado from DCMC. The purpose of the visit is to provide on-site support for inventory validation tasks and ensure alignment with operational objectives.
2025-05-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.37 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled back home to Guaynabo from Costa Sur. The purpose of the visit was to provide on-site support for inventory validation tasks and ensure alignment with operational objectives.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOP's for Emails to finalize and publish into documents folder.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710.Costa Sur. Work on marking up site plans, site pictures with Bluebeam to review, and compare the drawing sets all within one file, and questions in regard when materials will be relocated.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Costa Sur. Attended meeting to discuss revisions to the RFP for demolition for the Costa Sur site. An addendum is to be issued by Sargent & Lundy. Attendees: German Nunez, (Genera); Rafael Pabon, and Carlos Palomares (CDM Smith).
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Establishing Construction Offices Equipment & Supplies Requirements for BESS & Peakers Facilities
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review & Coordinated Temporary Project Facilities for Costa Sur and Aguirre from site visit made on Tuesday May 6th.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Meeting with Homeca, Genera, CDM Smith and DCMC Partners representatives to discuss extension time claim and path forward.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache - Reviewed RGE 12 month accelerated schedule provided by RGE.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Assessment and Strategy Discussion in Preparation of for Time extension request meeting with Homeca, CDM Smith, Genera, and DCMC Partners representatives.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache initial construction coordination meeting to start team introductions and initial coordination items for the start of the construction, led by Andres Concepcion - DCMC Partners, RGE Team Members, Sargent & Lundy, CDM Smith, CSA Group, and DCMC Partners.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache RGE Meeting discussion with Jose Robles - RGE of final pending items to be completed in order to sign contract for project. Other Participants - Francisco Feliu - Genera, Gabriel Perez - CDM Smith, Mike Kuczynski - Sargent & Lundy, Gilberto Sucre - DCMC Partners.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Update Project Discussion with Jose Lopez - DCMC.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache discussed project update and feedback with Andres Concepcion DCMC from meeting with Herminio Arroyo- Genera with Project Scope affecting daily plant operations.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Internal Meeting to discuss RGE (S & L, CM, PM) Gilberto Sucre, Andres Concepcion, Jorge A. Mercado, and Luis Duque from DCMC.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prep for meeting with Joaquin Quinoy (Genera) to discuss the development of internal training programs focused on Lean tools, including Kaizen, 5Y analysis, PDCA cycle, WAIST categories, and Value Stream Mapping (VSM). Explored current knowledge gaps, training objectives, and potential rollout strategies.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial review.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore documents tool structure to ensure correctness.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore submittal workflow templates for BESS projects.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meetings for Procore calls.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences, answering questions about Procore settings.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Photos SOP's document.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence for Summary of Services.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Mark Merritt (DCMC) to discuss Procore Summary of Services for Financial Implementation.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued reviewing work on Procore SOP's for Photos to finalize and publish into documents folder.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on meeting cooridnation for Monica Ybarra (Sargent and Lundy) and Ivette Rios (Sargenty and Lundy) to discuss Procore documents.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore Drawings tool SOP questions.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences to answer questions.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tools tracker update to present in meeting this afternoon.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Cambalache Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 3.25 |  | 184 | 598 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Nelson Medina (GENERA), Osvaldo de Jesus (GENERA) Andres Concepcion (DCMC) and Jorge Mercado (DCMC) in Cambalache Site (GENERA) about Emergency Managment, Health and Safety and Security Issues in this site. Discuss the eventually construction. Meeting between RGA team (Jose Robles, Jose Segarra) and DCMC (Andres Concepcion, Gilberto Sucre, Luis Duque, Luis Damudt, Jorge Mercado) Team about construction process in Cambalache Site.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continue Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Review on site jobs. Review the documents in Procore.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2.25 |  | 184 | 414 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continue Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Review the Procore progress and documents about this project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR - Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - draft talking points regarding BESS project as requested from Jesus Cintron (Genera). Also reasearch bios for speakers participating in renewable energy conference.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Procore courses for the folder and subfolder session, interconnection with Power BI and for the procore financials session.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - BESS Installation at Multiple sites RFI - Began drafting an RFI for the installation of BESS across multiple sites. Focused on outlining the preliminary scope and key questions to engage qualified vendors and gather market intelligence to inform the upcoming procurement strategy.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - BESS Installation at Multiple sites RFI - Finalized the draft of the RFI for the installation of BESS across multiple sites. Prepared and formatted the relevant attachments to ensure clarity, consistency, and alignment with the RFI content. Conducted a thorough review for completeness and compliance, and shared the full draft with the broader group for feedback and input before finalization.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 |  | 184 | 598 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Continued assisting Jan Rodriguez from Genera PR with finalizing the monthly Power Production and Fuels Consumption reports for submission to Cristina Ribas from Genera, ensuring data accuracy and completeness. Additionally, initiated weekly working sessions with Mario Gomez and Michael Silva from Genera PR’s ITOT Infrastructure and Cybersecurity team to configure FortiNAC. This configuration effort is part of a broader strategy to strengthen compliance with internal network controls for secure access to key internal applications, including Oracle Fusion, Asset Suite, and Genera Connect.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued configuration efforts for FortiNAC during the weekly session with Mario Gomez and Michael Silva from Genera PR, as part of the initiative to enforce internal network access controls for critical applications used to report and track federal funds usage. Additionally, met with Jan Rodriguez and Jose del Rio (Genera) to validate that natural gas fuel purchase data aligns with consumption figures for power production at the plants, ensuring consistency and accuracy in the report being prepared for submission to Cristina Ribas from Genera PR's compliance team.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 9 acetylene works are being completed on generator 1.1 and clean around the generator. Received Jorge Sanchez Homeca for disposal of heavy metals 20CY bin two trips.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Abatement Activities field supervision and coordination. Meeting with Carirma Sanchez (HOMECA ) to discuss the weekend work schedule.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - HOMECA Recycling daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Preparing Office trailers Layout for Costa Sur, Aguirre y Yabucoa projects. Quoting materials necessaries for trailers office. Continue review projects documents.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing drawing to ensure accuracy, regulatory compliance, and construction feasibility, Scope of Work, Scheduling & Contract Documents for the Yabucoa BESS Project. Looking for possibles discrepancies & measures. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with FSO Nelson Medina (Genera) and Jean Menay (DCMC) staff at the Cambalache site regarding access and project coordination issues.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Verification of safety procedures for confined spaces and verification of hazardous energy control procedures
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache - Initial Construction Coordination meeting with Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team Jose Segarra, Alberto Borelli, Javier Reyes from RGE to serve as a platform for collaboration and align teams towards a common goal for the project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting agenda development and closing prior Cambalache initial coordination meeting with RG Engineering, DCMC Partners & Sargent & Lundy.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received Cambalache accelerated schedule from RG Engineering and performed QA/QC review to validate activities, sequences and durations.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Cambalache initial construction meeting (kick-off) with Contractor (RG Engineering staff, Jose Robles, Jose Segarra), DCMC Partners (Gilberto Sucre, Luis Damudt, Luis Duque, Carlos De Jesus), CDM Smith for project team introduction and initial coordination.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Generated Cambalache Initial Coordination Meeting minute in Procore and distributed to project team (RG Engineering, Sargent & Lundy & DCMC Partners.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated via phone calls with Franklyn Colmenares (CSAGroup) regarding Cambalache TESLA scope of work. Phone call with Gilberto Sucre (DCMC Partners) to touchbase in project pending items.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with GeneraPR (Nelson Medina) DCMC (Jean Pierre Menay, Jorge Mercado) for site security and access coordination.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 167 | 41.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Conversation with Rolando Avila of Ensysa Energy related to the delivery of the Feed Water Heater & Boiler Valve Actuator for Palo Seco site, we discuss the delivery date for the equipment, Rolando informs that equipment may arrive early than schedule date 6/30/25.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing email sent by Pedro Cabrera of DCMC related to Fuel Efficiency Projects. Reviewing Critical components tracker list for updating information related to project and verify the percentage progress report for SOW and CE submitted by CPM.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 167 | 292.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing document sent by Pedro Cabrera of DCMC in regard of B&V clarification list for Costa Sur Fuel Efficiency projects, this list of RFI required a plant maintenance technician department to answer some of the question that B&V are requesting. Pedro Cabrera of DCMC share a share point folder of Black & Vetch related to specification of Fuel Efficiency projects.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a recount at the San Juan warehouse with Mr. Milton Flores from DCMC to verify inventory accuracy. This task was essential for confirming initial count results, resolving discrepancies, and reinforcing the reliability and consistency of inventory records.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executedcycle counts for the designated inventory locations scheduled for the day, focusing on areas AL 013 to AL 023. This initiative supports ongoing efforts to uphold inventory accuracy and ensure consistency with system data.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted variance analysis by identifying discrepancies and investigating inventory inconsistencies to strengthen overall inventory control. This effort supports improved accuracy, enhances operational efficiency, and facilitates timely corrective measures. Today's work specifically targeted inventory locations AL 013 to AL 023.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued cycle counting activities for assigned inventory locations, specifically from AL 013 to AL 023. The objective was to verify and reconcile physical inventory with system records, ensuring accuracy, consistency, and compliance with regulatory and operational standards.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-assisted with inventory data review and the preparation of cycle count documentation to support scheduled operations at the San Juan warehouse, in collaboration with Mr. Milton Flores of DCMC. Duties included confirming item location accuracy, verifying stock levels, and coordinating materials to enhance the efficiency and flow of inventory procedures.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a job briefing with Hernan Machado, Juan Vallejo and key DCMC warehouse personnel to review discrepancies identified during the previous day's activities and to reinforce proper data entry protocols aimed at enhancing inventory accuracy and control.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the San Juan warehouse, compile and submitted a comprehensive inventory report for Mr. Anthony Vega of Genera PR, integrating data from all warehouse sites. The report covered catalog inventories, location-specific details, unit counts, cost summaries, identified discrepancies, stock level threshold (maximum/minimum), and performance indicators to reflect each facility's current status. The analysis focused on inventory locations ranging from AL 013 to AL 023, CR 065 to CR 085, AA 096 to AA 109, AE 013 to AE 020.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the meeting with B&V, I focused on reviewing fuel efficiency priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Working to get data for develop answer to Reconstruction Progress Request By FEMA Spreadsheet
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop response to Reconstruction Progress Request By FEMA related to GENERA-PR projects.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Weekly meeting with participation from B&V: Tim Delaney, DCMC Pedro Cabrera. The discussion focused on reviewing fuel efficiency priorities, providing status updates, identifying next steps, metrics, challenges, and deadlines as part of the ongoing efforts to optimize performance and prepare for the next milestone.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of Fuel Efficiency, develop a KPI to share with the team. This KPI will help determine the course of action regarding project amendments with FEMA.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache - Initial Construction Coordination Gilberto Sucre, Andres Concepcion, Jorge A. Mercado, and Luis Duque from DCMC, Alberto Borrelli, Jose Segarra, Angel Cruz, Javier Reyes from RGE, Mike J. Kuczynski S & L
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Discussion with Andres Concepcion, Jorge Mercado, and Jean Pierre Menay DCMC on contractor mobilization, safety, and environmental regulations, as well as coordination of the contractor's visit to the Cambalache site.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Comments on BESS Cambalache VE Accelerated Schedule DCMC Comments on GENERA Cambalache Schedule - Preliminary Projection before the Meeting Cambalache - Initial Construction Coordination 10:30am
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache - Initial Environmental Coordination, Andres Concepcion, Luis O. Damudt from DCMC, Roseanne Perez from Genera PR.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Supervising work from Homeca Recycling. Labor personnel keeps dismantling (turbine housing base #1 & turbine housing base #2), Decommissioning and demolition works and planning for phase II.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Abatement Activities field supervision and coordination. Meeting with project manager Carirma Sanchez (HOMECA ) to go over the projected weekend work schedule. (we went over decommissioning, and demolition works and planning for Turbine housing base floor #1 & turbine housing base floor #2 where to locate the man lift on which side and where to spray water for the wind not to carry away the smoke away to far out).
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 9 acetylene works are being completed on generator 1.1 and clean around the generator. Assisted oil energy system with oil separator maintenance
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW11855 Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-02_Mar2025 Revision and development of editable Exhibit 1 for invoice financial tracker based on contract requirements. Developing excel document for construction team support. Pre-Intervention process for demolition works (Vega Baja). Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW9510 Pre-Intervention Review - Working with ENVIRONMENTAL HEALTH SAFETY SERVICES INC. Contract #103750_2024-G00512 and TO#7_Invoice# 11835_ Apr 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla Technical reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda, Carlos Palomares), Sargent & Lundy Mike Kuczynski.), and DCMC (Rafael Calderon, Gilberto Sucre)
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AE013 TO AE020 to begin the cycle counts.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AL013 to AL023
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AL013 to AL023
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AL013 to AL023
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AL013 to AL023
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AL013 to AL023
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 00 096 000 to AA 01 009 000
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 00 096 000 to AA 01 009 000
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 00 096 000 to AA 01 009 000
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 065 to CR 085 at the Aguirre warehouse to start the cycle counts.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 065 and CR 085 using Cycle Count List #583/584/585/574/579
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location CR 065 to CR 085
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 563/70/71 locations CR 065 to CR 085
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AE013 to AE020 Cycle Count List # 567.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #568 AND 569 from locations AE013 TO AE020 for a total of 3,516 pcs.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #568 and 569 from locations AE013 TO AE020.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels from locations AE013 TO AE020.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management on Costa Sur BESS Jobos BESS_Vega Baja BESS_Palo Seco BESS_/San Juan BESS_Yabucoa BESS to ensure documents are created, reviewed, distributed, tracked, stored and archived in an organized and controlled manner.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja BESS/Cambalache BESS/Costa Sur BESS/Costa Sur PEAKERS to ensure documents are created, reviewed, distributed, tracked, stored and archived in an organized and controlled manner.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Initial Construction Coordination Meeting for Cambalache Project hosted by Site Manager Andres Concepcion (DCMC) with contractor staff (RG Engineering; Alberto Borelli, Jose Segarra, Jose Robles, Xiomara Perez and Admin Staff), Gilberto Sucre and Luis Damudt (DCMC), and Dean Ennes (Sargent & Lundy); discussion for existing pre-construction concerns, bid award evaluation and status, and Procore set-up, among others.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review working progress for users on recently enabled tools such as Observations and Incidents. Review with field staff proper workflows and assignees depending on the tool and user's permissions.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work directly with the Procore 24/7 Help Assistance Live Chat Team to report troubleshooting with the Drawings Tool on unpublished drawings. Review drawings requirements and drawing areas set up.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams call with Franklyn Colmenares (CSA) to discuss troubleshooting with the Drawings Tool as drawings go unpublished due to repeated drawing titles and no drawing areas identified.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review SOP final deliverables for Internal Staff on Procore main Core Tools; Submittals, Inspections, and Observations. Adapting team feedback and commentaries to final versions.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 149 | 596 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - PW#9510 Pre Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6_Invoice #18334035. Continue reviewing invoice. During this time I review 350 lines.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review José Ralat (DCMC) email and update table for Sargent and Lundy Pre Intervention Process. For this update I review the Pre Intervention Tracker and Sharepoint files for invoice stages. There are two pending invoices from January and from February there are invoices still pending to be sent by vendor to start review.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Public Affairs Council’s May 7th Webinar: Employee Engagement in Social Impact.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR 4339 - Development of the newsletter for the Bess and Peakers particularly at the Arecibo site, Cambalache. These tasks included working particularly with the graph related to the progress report to the community for the purpose of providing community information and build trust and credibility.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Locate in Canva the creative elements to support the creation of the Bess and Peakers Newsletter, particularly the project in Cambalache. These tasks included searching for the timeline in Canva, selecting internal photos of the Arecibo site, editing the text and writing to keep the community informed and engaged with the project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Development in Canva of the newsletter for the Bess and Peakers, create copy, header, image selection, and graphics to summarize the progress of the project in Cambalache, Arecibo. These tasks included editing the written material and corroborating data to promote and early and transparent communication with the community, address concerns, and build public support.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339- Work on the Newsletter section related to the benefits of the BESS and Peakers project for the Arecibo, Cambalache site. These tasks included writing information related to the progressive improvements of the network, direct employment opportunities and increase in the amount of demand for goods and services for the municipality.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Frances Vallejo from DCMC Partners about the Bess and Peakers project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management - DR4339: Continued with the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. My current focus is on editing the translated content to align with the required formatting, correcting terminology and language usage, and ensuring adherence to the original English version’s structure and style. This process guarantees consistency, technical precision, and compliance with established standards.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Phone call to Peter Lampon (Innovative Clean) to request a quote for the cleaning services they offer. This request is based on the need to find personnel to visit the sites biweekly and clean the trailers. Mr. Lampon informed me that he would get back to me to send the quote for the requested services.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review of Bid-Addendum design drawings of Battery Energy support system control room details documents for 4339_9510 BESS_Cambalache project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on formatting schedule agenda with special information using schedule safety and enviromental activities as informative considering Procore format for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on formatting schedule agenda with special information using schedule critical activities as informative considering Procore format for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on inspections and creates schedule agenda using schedule activities as informative, schedule team, schedule duration and milestones considering Procore format for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache Teams meeting with Sargent and Lundy with employee Dean A. Ennes, RGE contractor employee Luis Robles, Jose Segarra, Xiomara Perez, CD Smith employee Gabriel Perez to review initial and pending steps for construction start with DCMC Andres Concepción, Gilberto Sucre, Luis Damudt, Jorge Mercado and Luis Duque due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC Initial Construction coordination meeting within DCMC Partners (Owners Representative and RG Engineering Team for the 4339_9510 BESS_Cambalache. Harry Velazques, Angel Cruz, Alberto Borrelli, Jose Segarra (RGE), Andres Concepcion, Luis Damudt, Jorge Mercado, Carlos De Jesus (DCMC Partners)
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 134 | 201 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review of Bid-Addendum design drawings of Battery Energy support system control room details documents for 4339_9510 BESS_Cambalache project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) (Part 2) Continue review of Bid-Addendum design drawings of Battery Energy support system control room details documents for 4339_9510 BESS_Cambalache project.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Managing data from Procore's project management software to generate visualizations, metrics, and key performance indicators (KPIs) that help monitor and analyze the projects.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue gathering data from Procore's project management software to generate visualizations, metrics, and key performance indicators that help monitor and analyze the projects.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 52 | 52 | 52 | Yes |  |  | Portsan - Containment tray rental for portable toilets for Genera project Deliverable 11
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 68.18 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Claiming Mileage for this route Travel from Guaynabo (18.392607 -66.123698) roundtrip to Cambalache Power Plant, Arecibo (18.471729, -66.700701) back to Guaynabo (18.392607 -66.123698) Purpose project meeting with Genera, RGE, Sagent and Lunder for 4339 9510 BESS Cambalache project. TOTAL MILEAGE 97.4 miles
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 5.25 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-fallowing the meeting at the San Juan warehouse with Mr. Milton Flores from DCMC, returned back to Guaynabo. The visit focused on evaluating the progress of ongoing inventory control initiatives and discussing strategies to enhance data accuracy and reporting consistency with the ABC cycle count process.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 5.95 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from Guaynabo to Central San Juan to meet with Mr. Milton Flores from DCMC. The objective of the visit is to assess progress on current inventory control initiatives and to discuss improvements to data accuracy and reporting consistency within the ABC cycle count progress.
2025-05-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 74.2 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection from home offices San Juan to Cambalache and Vega Baja Genera Site (18.47 Purpose Genera PR - Metting with Osvaldo de Jesus, Nelson Medina (GENERA) and Andres Concepcion, (DCMC), in Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they me Total Distance 106 miles
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for documentation of items in Procore documents tool
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Worked remote offsite on internal reports and document cleanup to enhance strategic project management, improve communication, ensure compliance, and reduce risks.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Worked remotely on schedule review and internal documents to enable construction managers to visualize the scope of work, foresee potential challenges, and streamline operations.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache. Andres Concepcion DCMC provided update of Pre Con Activities.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly BESS / Peakers Permitting Update Discussion led by Anna Rausch Sargent & Lundy. Presented Permitting Status across all sites and programs. CDM Smith, CSA Group, Sargent & Lundy, Genera and DCMC partners participated.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 225 | 562.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja In Person Meeting ARG Ceres / Sargent & Lundy / PM Team / CM Team to discuss Rigging Inclusion for Project Site, held at Sargent & Lundy's office in Santurce. Also discussed next steps in RFC process for ARG Ceres Final Proposal. CDM Smith, CSA Group and DCMC Partners representatives also participated in the meeting.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Update discussion of project with Jose Lopez DCMC Partners.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Staffing Candidates selection among BESS and Peakers Site meeting with Frances Vallejo - DCMC.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Office Trailers Selection for Bess and Peakers Sites with Harry del Valle DCMC.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Project Schedule & Budget Weekly Meeting Update led by Carlos Palomares CDM Smith., Rafael Pabon and Gabriel Perez CDM Smith, Franklyn Colmenares CSA Group and Gilberto Sucre DCMC Partners.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Worked on overall program update, project progress, RFC status for Cambalache, Vega Baja and Costa Sur. Special attention review of Homeca's progress update and remaining activities.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence Reading and evaluation of project emails.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Meeting to discuss the overall Project Schedule & Budget as it relates to both the Peakers and the BESS programs. Attendees were Perez Sepulveda (CDM), Foster Veazey (DCMC), Abraham Velazquez (DCMC), Alejandro Maymi (Genera), and Franklyn Colmenares (CSA).
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial review.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on PowerPoint slides for Cambalache kick-off meeting for Procore with the team.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore Analytics dashboard in Power BI.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences to track, record, receive, and distribute all formal project communications.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for Andres Concepcion (DCMC).
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks for Theresa Perez (DCMC) and Luis Roman (DCMC).
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore RACI sheet for Andres Concepcion (DCMC).
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Raissa Borges (DCMC) to discuss Procore analytics
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items to turn Observation tool on.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks for Procore team.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore schedule tool to see how it works in the training project.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Give training to Eduardo Rivera (DCMC) about (GENERA) Health and Safety Program. Make the PowerPoint presentation about the Health and Safety for Cambalache Genera Site to maintain the well-being of workers, protect the environment, and ensure safe operations.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Worked on the Vega Baja Report and sent it to Osvaldo de Jesus (GENERA). Review the Homeca (CONTRACTOR) documents, equipment logs and activity procedure.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Andres Concepcion (DCMC) about site inspection by RGE and Health and Safety themes. Conference call with Jose Lopez (DCMC) about the Vega Baja jobs status and progress. Conference call with Gilberto Sucre (DCMC) about Genera projects. Meeting with Harry del Valle (DCMC) about the Genera projects and needs.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended call with Project Management team for BESS and Peaker project to discuss budget and schedule. Participants: Carlos Palomares (CDM), Franklyn Colmenares (CSA), Gilberto Sucre (DCMC), German Nunez (Genera).
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Gilberto Sucre (DCMC) to discuss staffing tracker, coordinate locations and strategic planning.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended call with Raissa Borges (DCMC) and Marc Maceira (HONRA LLC) to discuss PowerBI platform, access to the link to send to Genera and coordinate with Lemoine IT team to provide access.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 184 | 46 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Held a meeting with Rafa Calderón (DCMC) regarding the TESLA contract and several Change Orders prepared by S&L. Reviewed the scope and justification and aligned on next steps to ensure consistency with contractual terms and project objectives.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Peakers - Drafted four amendment justification memos for the one-year extension of the EHSS, Geo-Engineering, Jaca & Sierra, and Javier E. Bidot contracts. Ensured that each memo clearly outlined the rationale for the extension, aligned with procurement requirements, and supported continued project execution. Confirmed account number for each with Jose Ralat (DCMC). Formatted the documents for consistency and clarity, and submitted them to Jesús Cintrón for review and sign-off.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 184 | 322 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Peakers - Drafted amendment justification memos for the one-year extension of the CAPTA, contract. Ensured that each memo clearly outlined the rationale for the extension, aligned with procurement requirements, and supported continued project execution.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria /Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and move materials to continue dismantling areas Day 10 acetylene works are being completed on generator 1.1 and clean around the generator. Homeca continued disposal of heavy metals 80CY bin second trip.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting on the Vega Baja site with the Demolition subcontractor, Carirma Sanchez, and Eduardo Ramos from Homeca Recycling to discuss the actions required to accelerate the progress of the dismantling activities. HOMECA will work on Saturdays to pick up the pace.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued Vega Baja Bess Project Specs. An overview of HOMECA's performance is needed to ensure all project participants clearly understand the expectations and requirements and their participation in the project’s execution and progress and to ensure the guaranteed completion date.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing drawings, verified Scope of Work to ensure that contractors, clients, and project managers are on the same page, Scheduling & Contract Documents for the Yabucoa BESS Project. Looking for possibles discrepancies & measures. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue Working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Yabucoa BESS Project. Looking for possibles discrepancies & measures. Working on office trailers needs for each project, preparing spreadsheet list for each project and standardize the procedure for requesting materials.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting in Duenas Trailers Company - Topic Discussed, we discuss the different office alternatives for the Costa Sur, Aguirre and Yabucoa projects, size, availability and price. Layouts were also discussed. Attendees, Danny Duenas (Duenas Trailers) & Harry Del Valle (DCMC)
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - A coordinated walk-thru was conducted at the Cambalache site with the construction team from the RGE (Jose Segarra) (Alberto Borelli) (Javier Reyes) and the DCMC (team Andres Concepcion) (Carlos De Jesus) and (Luis Duque) construction team,
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work related to the alarm system and evacuation of the Cambalache site is being coordinated with Eliceo Martinez (GENERA).
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The documentation regarding contractual compliance for safety sent by the contractor is evaluated. The work plans and safety controls for the Cambalache site are verified.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the eviction plan according to the existing plans for the Cambalache site of Genera received from Osvaldo De Jesus (Genera).
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Site Meeting with contractor (RG Engineering) (Jose Segarra, Alberto Borrelli) team and Genera PR (Herminio Arroyo) and DCMC (Luis Duque, Jorge Mercado, Luis Damudt, Carlos De Jesus). Initial coordination items were discussed and walkthrough the facility to survey the site plan.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Drafted and coordinated meetings for Team Cambalache Procore alignment and generated agenda. This meeting will align team on the use of the Procore platform during project.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed project site visit notes and meeting minutes and distributed to DCMC Team and RG Engineering Team via Procore.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project scheduling for Cambalache and provided comments and notes to RG Engineering PM (Jose Segarra)
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - meeting with DCMC Jean Pierre Menay for Genera Safety Introductory Training. This training will allow me entrance to Genera Power Plant Site and for Vega Baja.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working in review of documents send by Emilio Cabrera of Black and Vetch related to Fuel Efficiency projects, review the list of projects send by B&V that area (4) project that are not assigned and (2) that was deleted form the list. Reviewing email send by Waldo Cordova of Genera in regard of information requested for DCS and PI-DAS of Cambalache site. Contact Frances Vallejo of DCMC to provide information related to BESS project of Vega Baja.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - CPM Jose Prado, Luis Tapia, Carlos Castro, Diana Rivera and Victor Alvarez; DCMC Pedro Cabrera and Eduardo Rivera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, Discussion of Cambalache Leak Detection System, Overhead crane, fire system, Cambalache static frecuency transformer and reviewing the deliverables for SOW & CE.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing specification for Atomatic Tube Cleaning System of Aguirre 1 and 2. Send email to Jean Pierre Menay of DCMC to coordinate safety training for entry of Genera Vega Baja Site.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Reviewing information send by Jose Molina of Genera in regard of GRF system, the information is related to past SOW and CE, this information may be useful to CPM develop a new SOW and CE for the acquisition of Recirculating fan duct and GRF system.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - Continue working with the verification of Fuel Efficiency projects list 673691 with the Black & Vetch Fuel Efficiency project specification task table to review if project was included in their SOW. Send email to Sulinnette Perez of Genera in regard of information of procurement status for the Static Frequency Converter Transformer of Cambalache. Send email to Jose Lopez of DCMC to provide guidance related to Vega Baja BESS project that I will be in a transition phase of project manager Jose Lopez to me, and requested information related to site visit as part of the transition. Send email to Herminio Arroyo of Genera to see if plant can provide any information or specification related to the Static Frequency Converter Transformer of Cambalache. Joaquin Quinoy of Genera requested an update for the GPR-PREB-NEPRMI20210014-20240226 #4 related to critical components procurement stage of varios projects.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a a coordination meeting with Juan Vallejo and Hernan Machado of DCMC, along with key warehouse personnel. The focus was to align upcoming inventory tasks, clarify team responsibilities, and ensure all personnel are following standardized procedures to support the continuity and accuracy of the cycle count process.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a targeted inventory recount at the Aguirre warehouse in collaboration with Mr. Juan Vallejo from DCMC to improve data fidelity. The activity focused on validating prior cycle counts, identifying and reconciling variances, and reinforcing the accuracy and traceability of inventory records in alignment with asset management protocols.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued cycle counting of designated inventory areas. This task supports the verification and reconciliation of physical inventory with system records to ensure accuracy.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a variance analysis at the Aguirre warehouse, identifying inventory discrepancies and investigating inconsistencies to enhance inventory control measures. This task directly supports data accuracy, operational efficiency, and the implementation of timely corrective actions.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed cycle counts for the schedule inventory areas assigned for the day. This activity supports ongoing efforts to enhance inventory accuracy by reconciling physical stock with system records. Today's locations are from CR 086 to CR 100.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed inventory data analysis and prepare cycle count sheets to support schedule activities at the Aguirre warehouse, in coordination Mr. Juan Vallejo of DCMC. Task included validating item locations, confirming stock accuracy, and organizing materials to ensure a streamlined and efficient inventory process
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the Aguirre warehouse, a consolidated inventory report was prepared for Mr. Anthony Vega of Genera PR. consolidating data across all warehouse's locations. The report integrated data across all warehouse locations and included catalog items counts, unit quantities, cost analysis, identified discrepancies, and stock thresholds. It also featured percentage-base indicators to reflect the operational status of each site. The reviewed inventory locations range from CR 086 to CR 115, AA 101 to AA 115, AE 021 to AE 026, AL 024 to AL 036.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue Develop response to Reconstruction Progress Request By FEMA related to GENERA-PR projects.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Rewrite and review important notes during Cambalache Meeting Walk-tour 9:00am-12:30pm RG Engineering and Genera PR.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Issue for construction comments before 9:00am-12:30pm RG Engineering and Genera PR Meeting - RFP 4826 52 MW Battery Energy Storage System Installation at Cambalache with Andres Concepcion, Luis O. Damudt, Jorge A. Mercado, Carlos De Jesus, Luis Duque DCMC.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Meeting Walk-tour Coordination with RGE and Genera PR Cambalache Power Plant with Andres Concepción, Luis O. Damudt, Jorge A. Mercado, Carlos De Jesus, Luis Duque DCMC, Alberto Borelli, Jose Segarra, Angel Cruz, Harry Velazquez from RGE, Herminio Arroyo Genera PR.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Discussion Construction Project Issue Scope after walk tour 9:00am-12:30pm Meeting Walk-tour Coordination with RGE and Genera PR with Andres Concepcion, Luis O. Damudt, Jorge A. Mercado, Carlos De Jesus, Luis Duque DCMC.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Dismantling, Decommissioning and demolition works planning for phase II. Homeca Recycling (the contractor) should submit an LED abatement removal certification to ensure they can safely handle and remove lead hazards, protecting workers and staff from lead exposure. Worked with the dismantling of cutting away turbine unit 2 & turbine unit 1.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview (specifications versus contract) and analyzing documents status in the Procore platform. Met with Gilberto Soto (DCMC) to discuss the current Safety project Phase situation with the Demo Contractor and all de safety factors in detail.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria /Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 10 acetylene works are being completed on generator 1.1 and clean around the generator. Received Javier Baez Homeca for disposal of heavy metals 80CY bin for two trips.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW9510 Pre-Intervention Review and finance validation CDM Smith Invoice #90232903 for TO#1 Nov 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#9510 Pre-Intervention Review - Sargent and Lundy Contract #2024-G00200 and TO#5_Invoice# 18334034_Jan 2025. Compliance RFI Answers- Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW9510 Pre-Intervention Review- Working with Black & Veatch Contract #217733_2024-G00207 and TO#5_Invoice# 6200867_ Feb 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AE021 to AE026
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AL024 to AL036
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AL024 to AL036
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AL024 to AL036
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AL024 to AL036
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AL024 to AL036
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 010 000 to AA 01 015 000
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 010 000 to AA 01 015 000
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 010 000 to AA 01 015 000
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 86 and CR 115 using Cycle Count List #574/579/585/583/584
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations CR 086 to CR115.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 086 to CR115 at the Aguirre warehouse to start the cycle counts.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 578/579/590/589 locations CR 86 and CR 115.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AE021 to AE026 to begin the cycle counts.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 586 locations AE021 to AE026.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #586 from locations AE021 to AE026 for a total of 2,480 pcs.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AE021 to AE026 Cycle Count List # 577.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Daguao Peakers to ensure information is properly organized, accurately transmitted and readily accessible for the project team. Coordination with Rafael Pabon (CDM) Costa Sur Peakers Project Submittals. Data Management for Jobos Peakers/Costa Sur Peakers/Cambalache BESS.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Projects Daguao (Peakers) to ensure documents are created, reviewed, distributed, tracked, stored and archived in an organized and controlled manner.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review existing SOPs including user permissions intention and requirements per project management standards; implementation of tools workflows and requirements.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continued reviewing Cambalache Drawings status and the implementation of Drawing Areas at the Drawings Tool for better classification on multiple sheet drawings.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Cambalache Drawings status and the implementation of Drawing Areas at the Drawings Tool for better classification on multiple sheet drawings.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review troubleshooting on Drawings Tool for unpublished drawings due to repeated drawing titles. Work directly with Procore 24/7 help assistance on live chat.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Work in the newsletter for the Bess and Peakers project to build public support and promote communication with the community. Create an insight, draft, write all the text and create a template in Canva.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with the team of Genera Jorge Bracero, Iván Báez and Rafael Rodríguez Ema related to the community relations projects of May
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting with Jorge Bracero of the Genera PR team on an update on the pending projects related to the BESS and Peakers project.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.75 |  | 139 | 382.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Work on the sections of the fact sheet in Canva about the BESS project. These tasks included editing the section on 'What is the project about?' and the timeline of the work completed as part of the BESS project in Arecibo, Cambalache. These tasks included editing the text, drafting and including information about the estimated connection, and providing a statement about the start of operations for all units in operation.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Creation of an Excel spreadsheet with the list of trailer equipment, office supplies, and cleaning materials to be purchased and distributed across the different sites. An email was sent to the employees informing them that all requests for equipment, office supplies, and cleaning products must be sent to Gilberto Sucre and Frances Vallejo (DCMC), who will be responsible for reviewing and authorizing each request before processing.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management - DR4339: Continued with the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. My current focus is on editing the translated content to align with the required formatting, correcting terminology and language usage, and ensuring adherence to the original English version’s structure and style. This process guarantees consistency, technical precision, and compliance with established standards.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review of Bid-Addendum design drawings of Battery Energy support system control room details documents for 4339_9510 BESS_Cambalache project.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in extract Procore data for inspection of entrance in project area, inspection of new access ramp for LUMA company for DCMC Andres Concepción due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache in site visit meeting with RGE contractor employees Jose Borreli and Jose Segarra, an initial meeting for inspection entrance in project area, identify obstructions to traffic, inspection of new access ramp for LUMA company and for inspection of flood site in project with DCMC Andres Concepción, Luis Damudt, Jorge Mercado and Luis Duque due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on inspection review with comments considering specifications and Procore documents in contractor RFP schedule a fourth for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC Initial Construction coordination meeting A site walkthrough to identify project scope of work location and construction operations needs due reduced space with Harry Velazques, Angel Cruz, Alberto Borrelli, Jose Segarra (RGE) Herminio Arroyo (Genera), Andres Concepcion, Luis Damudt, Jorge Mercado, Carlos De Jesus (DCMC Partners) for the 4339_9510 BESS_Cambalache project.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 124 | 124 | 124 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. US Government Id require for entrance to Genera Site with ports. (TWIC card receipt date 3.25.25)
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue developing new reporting templates and processes for our PMO Reporting Bi-weekly meeting.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Introducing updated reporting templates and streamlined processes enabling the PMO team to efficiently monitor project statuses and updates.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS / Peakers Schedule & Budget Meeting" The purpose of the meeting is to discuss projects finances and schedule status and updates. The meeting was organized by Gabriel Perez (CDM Smith). Meeting chair: Carlos Palomares (CDM Smith). DCMC: Frances Vallejo, Gilberto Sucre CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares, Enrique Laya
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Lauren Wells from Lemoine to discuss updates from Procore Analytics feature for dashboard report.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 122 | 305 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Implementing new reporting templates and processes for our PMO Reporting Bi-weekly meeting.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 76.99 | 76.99 | 76.99 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane PPE necesary for the Genera Projects (Receipt date 4.29.25; 5 hard hats)
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 68.18 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Claiming Mileage for this route Travel from Guaynabo (18.392607 -66.123698) roundtrip to Cambalache Power Plant, Arecibo (18.471729, -66.700701) back to Guaynabo (18.392607 -66.123698) Purpose project meeting and site walkthrough to identify project scope of work location and construction operations needs due reduced space with Genera, RGE, Sagent and Lunder for 4339 9510 BESS Cambalache project. TOTAL MILEAGE 97.4 miles
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from home in Guaynabo to Aguirre to meet with Mr. Juan Vallejo from DCMC. The purpose of the visit is to oversee inventory operations, provide on-site coordination, and ensure alignment with the project objectives.
2025-05-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-after completing the meeting at the Aguirre warehouse with Mr. Juan Vallejo from DCMC, returned back home in Guaynabo. The purpose of the visit was to oversee inventory operations, provide on-site coordination, and ensure alignment with the project objectives.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Expense |  |  | 364 | 364 | 364 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Risk assessor and Lead abatement training to be able to enter the facilities and works being performed with lead base paint.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 off site remote, reviewed folder structure to enable the project to achieve its objectives effectively and efficiently while fostering collaboration, transparency, and successful project outcomes. Review internal data entry of project documents
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 off site remote, document controls, and internal review of project sequencing to ensure tasks are completed in a specific order, and project has a clear chronology that enables a quality final product.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Evaluation and discussions of the 2 safety incidents which took place in one hour at the project site. Jean Pierre Menay & Jose Lopez from DCMC.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC with RG Engineering call with Jose Robles RGE, Mike Kuczynski - Sargent & Lundy, Gabriel Perez CDM Smith and Gilberto Sucre - DCMC Partners to expedite remaining scope, schedule and commercials to finalize contract for Cambalache.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genra & Tesla Management Project Meeting - Review Contract Payment Status, Change orders and upcoming new Change orders due to battery deliveries dates change from 2025 to 2026 tariffs, future tariffs, new equipment and advanced GSU deliveries. Genera, CDM Smith, Sargent & Lundy, CSA Group and DCMC Partners Participated.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache RFC Cambalache RGE Technical review of outstanding items was rescheduled for 10 am as Sargent & Lundy main Participants had an emergency call. RGE, CDM Smith, Sargent & Lundy and DCMC Partners.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Team exchange discussions of incidents which occurred, incident causes, future preventive measures, work stoppage and CDM Smith handling of events. Multiple calls took place between Jose Lopez, Jean Pierre Menay and Gilberto Sucre DCMC Partners.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Reinitiated RFC Technical review of RGE proposal mainly Value Engineering and alternate proposal pricing. Alignment was reached with few exceptions between participants CDM Smith, CSA Group, Sargent & Lundy, RG Engineering and DCMC Partners.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed Procore Documentation Upload across all BESS project sites concentrating on Drawings, Specifications, RFP's, Contractor bids, RFC's
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with DCMC Program Management team. Attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3.75 |  | 184 | 690 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2.25 |  | 184 | 414 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Conference call with Jose Lopez and Gilberto Sucre (DCMC) about EHS incident in Vega Baja Site. Conference call with Gilberto Soto (DCMC) about potential hazards in Vega Baja Site. (GENERA)
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Conference call with Gabriel Perez (CDMSMITH), Osvaldo de Jesus, Victor Rodriguez (GENERA), Carirma Sanchez and Emmanuel Santos (HOMECA) about the EHS incident on Site.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3.25 |  | 184 | 598 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards and meet Safety and Health Emergency.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Peakers - Drafted Genera’s formal response to a second RFI concerning the Grid Support Units RFP. Coordinated with Mike Kucsinsky and Miguel del Valle (S&L), Genera’s Legal team (Kevin Futch, Christian Torres and Angelina Minier) to review the draft, and ensure consistency with contractual and regulatory requirements. Integrated feedback from all parties to finalize a comprehensive and accurate response, supporting Genera’s position and ensuring alignment with the RFP’s objectives.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Peakers - Drafted Genera’s formal response to a RFI concerning the Grid Support Units RFP. Coordinated with Mike Kucsinsky and Miguel del Valle (S&L), Genera’s Legal team (Kevin Futch, Christian Torres and Angelina Minier), and Jorge Sanchez (Genera PMO) to review the draft, verify technical accuracy, and ensure consistency with contractual and regulatory requirements. Integrated feedback from all parties to finalize a comprehensive and accurate response, supporting Genera’s position and ensuring alignment with the RFP’s objectives.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Provided an update to key IT stakeholders Jean Gonzalez and Hector Vazquez from Genera PR regarding the readiness of the Genera Connect platform for production deployment, emphasizing the need for their support to finalize internal network access from Genera PR HQ. Continued troubleshooting report upload issues in the Genera Connect Financial Tracker; after comparison with the template provided by Keylamerari Sierra from Integrum, identified that missing hidden columns were causing the issue. These columns will be temporarily added to the reports as a workaround while a permanent resolution is implemented at the application level.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.75 |  | 184 | 690 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Conducted initial testing of the financial tracker report uploads to the Genera Connect Financial Tracker and identified issues with uploading the payment complete report. Also initiated testing on the Genera Connect Timesheet module, where a data retrieval issue for the logged-in user was detected. Consolidated the Oracle Fusion Standard Operating Procedures into a single, indexed document and shared it with Alejandro Maymi from Genera PR to support operational consistency. Additionally, prepared the draft presentation for the upcoming weekly DCMC preparation meeting.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 11 acetylene works are being completed on generator 1.1 and clean around the generator. Received Javier Baez Homeca for disposal of heavy metals 80CY bin two trips.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform.Hurricane Maria. MST met with Gilberto Sucre (DCMC) and Jaime Pesquera (DCMC) to discuss the current project Phase situation with the Demo Contractor.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - I had several phone calls with the HOMECA project manager, Carirma Sanchez, and the company administrator, Eduardo Ramos, to discuss the project contract requirements and progress of activities.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Analyzed contract documentation and project scope for Costa Sur and Aguirre BESS projects in Procore. Focused on identifying areas for clarification and cost tracking. Gathered vendor estimates for required field trailer items such as potable water delivery and multifunctional printers.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with Gilberto Sucre, Carolyn Baez-Nieves and Harry del Valle (DCMC) to discuss the equipment and materials needed at the sites, as well as the minimum equipment required for employees to carry out their work safely and efficiently. During the discussion, we identified key categories of supplies, including tools and essential site materials. We also emphasized the importance of maintaining an updated inventory to track the availability and condition of all equipment, ensuring timely replacements or repairs when needed. Action items were established, including the assignment of responsibilities for monitoring inventory levels, verifying deliveries, and coordinating future supply needs across all sites.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Performed in-depth review of Costa Sur and Central Aguirre BESS project deliverables using Procore, verifying alignment between drawings, schedules, and scope of work. Researched potential discrepancies and initiated quote requests for on-site essentials including drinking water and office printers.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 167 | 375.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Reviewed Costa Sur and Central Aguirre BESS project materials in Procore, focusing on drawings, schedule, and contract alignment. Searched for gaps or potential issues and requested quotes for support items like potable water and printers for the site offices.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue working on Procore, reviewing drawings, review Scope of Work to ensure it includes details on the deliverables, timeline, milestones, and reports. and verify Scheduling & Contract Documents for the Yabucoa BESS Project. Looking for possibles discrepancies & measures.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on a safety presentation for new contractors. Purpose is to educate staff on the risks associated with the scope of the project as part of DCMC's contractual requirements.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The agenda and minutes of the important points for knowledge and discussion with the contractor management RGE are being worked on.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project coordination via email and phone calls to discuss safety and environmental concerns. Dates are established for a meeting with the staff from Genera Osvaldo De Jesus, Andres Concepcion DCMC team, and the contractor RGE.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Evaluation of safety documents related to the mobilization of the contractor RGE. Risk assessments related to the contractor's daily tasks are evaluated according to the work plans and Genera's health and safety manual for contractors.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Evaluation of the safety documents related to the mobilization of the contractor RGE. The credentials and competencies of the personnel are evaluated, as well as the occupational risk analyses presented by José Sarraga of (RGE).
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed RFI #18 in Procore. Verified information and responsibles were properly assigned in the platform to ensure satisfactory review of information.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Organized Cambalache pre contract RFC meeting action items for follow up with contractor (RG Engineering).
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated a Safety Meeting for May 13, 2025 and generated agenda and invititations to contractor RG Engineering (Javier Reyes) and GeneraPR Facilities Team (Osvaldo De Jesus).
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - QA/QC review and document observation on construction schedule to address pending information to define project timeline and milestones in contract.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued drafting agenda of topics to be discussed in the team Procore Alignment meeting on 5/14/2025
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Cambalache pre contract RFC Meeting with Mike Kuczinski (Sargent & Lundy) Gabriel Perez (CDMSmith) Jose Lopez (DCMC) and team (RG Engineering) to go over technical pending items to close construction contract.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with DCMC- Gilberto Sucre to discuss Cambalache site logistics items in order to define final mobilization plan in contract.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Contact by phone Edgard Santana of CPM that is working at Costa Sur Power Plant to see if he can provide information related to the Fan ID and FD of Costa Sur so we can provide the information to B&V for the development of specification. Send an email to Edgard Santana of CMP with the B&V clarification word sheet in regard of FD and ID fans of CS. Continue reviewing in Procore the project information related to Vega Baja BESS.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with new assigned project BESS Vega Baja Power Plant on Procore to review project status, activity, submittal, RFI and daily log. Working with the update requested by Joaquin Quinoy of Genera in regard of procurement status for critical components projects.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with new assigned project BESS Vega Baja Power Plant on Procore to review project RFI. Working with Pedro Cabrera of DCMC for the update requested by Joaquin Quinoy of Genera in regard of procurement status for critical components projects.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Continue with new assigned project BESS Vega Baja Power Plant on Procore to review project RFI and Submittals. Send email to Joaquin Quinoy of Genera in regard of procurement status for critical components projects, status was sent to Joaquin for his review or comments. Meet with Gilberto Sucre of DCMC to provide feedback in regard of RFP for phase 2 of Vega Baja BESS project in Procore but we realize that I do not have access to the RFP, Gilberto will request that access to phase 2 RFP.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Critical Components - Working with PREP tracker presentation to integrate a Pivot Table for closed RFP and Open RFP. Continue reviewing in Procore the RFI, drawing and Submittal of Vega Baja BESS projects, they are still pending access for RFP review.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Genera Pre-Meeting with participation from DCMC: Rick Patterson, Rafael Calderon, Eisha Mercader, Victor Maldonado, Glorimel Torrado, Mark Merritt, Danny Martinez, Ginnell Torres, Rick Patterson, Saul Falcon, Christian Cruz, Sheila Torres, Paul Browne, Carlos Gonzalez, Rafael Cordero, Jorge Aponte, Sheila Torres and Roberto Bosch; and Marc Maceira (HONRA LLC) to discuss draft presentation priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process before presenting to Genera PR.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle counts for the assigned inventory locations scheduled for the day, specifically covering AA 116 to AA 118. The task was part of ongoing efforts to enhance inventory accuracy and ensure consistency between physical stock and system data. Key activities included identifying discrepancies, verifying bin locations, and recording observations to support necessary follow-uop actions
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted variance analysis by identifying discrepancies and assessing inventory inconsistencies to enhance control measure. This effort aimed to improved data accuracy, boost operational efficiency, and enable prompt corrective actions.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed cycle count sheets to support scheduled activities at the Costa Sur warehouse, in coordination with Mr. Hernan Machado from DCMC. His key responsibilities included validating item locations, confirm stock accuracy and organizing materials to facilitate and structured inventory process.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a job briefing with Juan Vallejo, Giovanni Taffanelli and key DCMC warehouse personnel to align on upcoming operational priorities and clarify task assignment. This session emphasized enhancing coordination and strengthening accountability.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC to verify inventory accuracy. This activity was essential for validating previous counts, resolving discrepancies, and ensuring the consistency and integrity of inventory records.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while stationed at the Costa Sur warehouse, compiled and submitted a comprehensive inventory report to Mr. Anthony Vega of Genera PR, incorporating data from all warehouse locations. The report offered a strategic summary of catalog records, unit quantities, cost evaluations, discrepancies and stock level parameters, including maximum and minimums. It also included key performance indicators to reflect the current state of inventory. Locations reviewed included AA 116 to AA 118, CR 115 to CR 140, AE 027 to AE 033, AL 037 to AL 052.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Collect data of QPR Summary Q2 2025 to illustrate project delivering on expectations and areas of needed improvement.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria.Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consultant Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop response to Puerto Rico Energy Bureau of request related to Critical Components status.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue Develop response to Reconstruction Progress Request By FEMA related to GENERA-PR projects and validated data with QPR Summary Q2 2025
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Procore RFI #18 - Discrepancies between drawing CAB99-JN-BSS-0003 (Rev 0) and CAB99-JN-BSS-0003 (Rev 0.1)
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review VE prop Rev4 (3.14.25) Steel Structure (HVP)_Detallado_230425_Comparativa, CAMBALACHE BESS - VALUED ENG ACC SCH_230425_Proy.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document , Site, Arc Procore Folder 100- 6. Appendix D.1- Design Drawings.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review DCMC Comments on GENERA Cambalache Schedule - Preliminary Projection of possible Design & Built April/12/2025, DCMC Comments on Cambalache third version RFP schedule send by Carlos De Jesus (DCMC).
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervising work for daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform. Project documentation is instrumental in setting and defining clear project goals, ensuring everyone, from the project manager to the stakeholders, shares the exact expectations.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Activities field supervision and coordination. Field walks through the day (HOMECA) to discuss the today's tasks and area of work turbine 1 & turbine 2. Today we had two tanks' incidents, one tank briefly caught on fire and the other one fell off and went off shooting gas on the floor.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca resumed cleaning the field housekeeping and move materials to continue dismantling areas Day 11 acetylene works are being completed on generator 1.1 and clean around the generator. Homeca continued for disposal of heavy metals 80CY bin two trips. Report incidents to ProCore app
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 11 acetylene works are being completed on generator 1.1 and clean around the generator. Received Javier Baez Homeca for disposal of heavy metals 80CY bin two trips. Upload information and sent emails about incidents from Homeca Recycling to Procore.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW9510 Pre-Intervention Review CDM Smith Invoice #293410-15 for TO#1 Apr 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339- Hurricane Maria Pre-Intervention Tracker Update - Continue working on Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Contractual high-level Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla contract reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes and client's financial needs. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczynski), and DCMC (Rafael Calderon)
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339- Hurricane Maria New- DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC Participants: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and others.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations AE027 to AE033 to start the cycle counts.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AL037 to AL052
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AL037 to AL052
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AL037 to AL052
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AL037 to AL052
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AL037 to AL052
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 016 000 to AA 01 018 000
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 016 000 to AA 01 018 000
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 115 and CR 140 using Cycle Count List 597/98/99/607/608/609
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 115 to CR140 at the Aguirre warehouse to start the cycle counts.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 602/603/604/607/611/612 for locations CR 115 to CR140.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location. CR 115 to CR 140
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #605 and 606 locations AE027 to AE033
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations AE027 to AE033 using Cycle Count List #600.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #605 and 606 for locations AE027 to AE033, totaling 4,063 pieces.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes |  | Remote | Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera PR Document Control - Data Management - Procore Additional Users for Aguirre BESS/Vega Baja BESS/Cambalache BESS/ Yabucoa BESS & Peakers. Users are assigned to the project and can perform actions based on their permissions. Documentation for Cambalache BESS
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Remote | Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera PR ¦ Document Control - Data Management Cambalache BESS RG Documents to ensure documents are created, reviewed, distributed, tracked, stored and archived in an organized and controlled manner.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Resumed reviewing Cambalache Drawings status and the implementation of Drawing Areas at the Drawings Tool for better classification on multiple sheet drawings.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform documents review for SOP final publising on external users; working on internal users SOP on critical tools.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on Procore Certification: Project Management for Owner's Representative.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Cambalache Drawings status and the implementation of Drawing Areas at the Drawings Tool for better classification on multiple sheet drawings.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, and Eisha Mercader from DCMC, and Shellsea Maysonet (SM Consulting); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Update Pre Intervention Tracker and QA/QC team presentation. All data should match with our tracker. This data review was in preparation for weekly team meeting held today at 1:30 pm.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Design and work on the graphics related to the security plan in Cambalache that are included in the Fact Sheet in Canva that will be distributed to the community as part of community relations. Work with the data, copywriting, and creative elements that will be included in the Fact Sheet.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Work on the visual graphics of the Fact Sheet in Canva related to the important data of the BESS project regarding the Cambalache project in Arecibo. These tasks included copywriting, editing, photo selection, and following the guidelines related to the brand kit of the Genera PR brand.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with the Genera Team: Jorge Bracero, Digno Cartagena, Lucy Gonzalez, Jose del Rio, Lorena Torres, Walter Pomales, Anthony Vega, Jean C Gonzalez, Maria Sanchez, Ricardo Pallens, Rafael Rodriguez, Winnie Irizarry, Indira Mohip Colon, Vladimir Scutt, Alexis Cruz Figueroa and Victor Rodriguez Cruz. The meeting was about a drill preparation for an explosive exercise in Aguirre.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued working on the translation of the Safety Manual from English to Spanish. Focused on reviewing translated sections for consistency, technical accuracy, and correct use of terminology. Worked on aligning formatting and structure to match the original document, ensuring the final Spanish version meets established standards and is clear for Spanish-speaking staff.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11- DR4339: Meeting with Gilberto Sucre and Harry del Valle (DCMC) to discuss the equipment and materials needed at the sites, as well as the minimum equipment required for employees to carry out their work safely and efficiently. During the discussion, we identified key categories of supplies, including tools and essential site materials. We also emphasized the importance of maintaining an updated inventory to track the availability and condition of all equipment, ensuring timely replacements or repairs when needed. Action items were established, including the assignment of responsibilities for monitoring inventory levels, verifying deliveries, and coordinating future supply needs across all sites.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue RFI New feature and best practices training for 4339_9510 BESS_Cambalache project.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create comments report on RFP schedule Cambalache third and fourth version file of contractor named Sch VE prop Rev4 (3.14.25) Steel Structure (HVP)_Detallado_230425_Comparativa, CAMBALACHE BESS and VALUED ENG ACC SCH_230425_Proy for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on formatting scheduling agenda considering contractor baseline, schedule critical activities, logical construction, task order in contract and scheduling control documentation using project files in Procore for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on create agenda draft report considering contractor baseline, schedule critical activities, logical construction, task order in contract and scheduling control documentation using project files in Procore for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC meeting with Genera PR, RGE, Sargent & Lundy about Value Engineering Proposal of the 4339_9510 BESS_Cambalache project. Harry Velazques, Angel Cruz, Alberto Borrelli, Jose Segarra (RGE) Herminio Arroyo (Genera), Andres Concepcion, Luis Damudt, Jorge Mercado, Carlos De Jesus (DCMC Partners) and Sargent & Lundy representatives.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFI New feature and best practices training for 4339_9510 BESS_Cambalache project.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Completed RFI New feature and best practices training for 4339_9510 BESS_Cambalache project.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 122 | 274.5 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Evaluated project performance metrics to support the preparation of management reports. The purpose was to synthesize findings into clear summaries that reflect project progress and flag potential issues.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting with Marc Maceira (Honra LLC) to discuss technical issues with dashboard report and possibles solutions.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Collecting and structuring data for monthly insights to ensure that the information gathered is accurate and reliable and identify inconsistencies and errors, which can be corrected and refined.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 |  | 122 | 396.5 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Collecting and structuring data for monthly insight to identify areas of improvement, optimize processes, and develop effective solutions.
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 41.16 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home offices. Purpose Site inspection jobs. To meet Health and Safety Situation. Total Distance 58.8 miles
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.23 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Maria- traveled from to Costa Sur back home in Guaynabo. The purpose of the visit was to evaluate current inventory control measures and provide assistant in implementing improvements, Additionally, support was provided to Mr. Machado throughout the cycle count progress
2025-05-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.3 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -traveled directly from home in Guaynabo to Costa Sur to coordinate operational support with Mr. Hernan Machado from DCMC. The purpose of the visit is to evaluate current inventory control measures and provide assistant in implementing improvements, Additionally, support will be provided to Mr. Machado throughout the cycle count progress.
2025-05-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluated Jose Robles RGE response to S&L issued Value Engineering Revised Scope Evaluation that addresses their approvals, rejections, comments and conditions for the value engineering and optional prices. In the table RGE included their comments, clarifications and confirmations. On the bottom of the table a summarized of the adders and deducts to come up with the final contract price. Confirmation of these were evaluated for the final contract cost for a delivery term of 12 months.
2025-05-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Gilberto Sucre (DCMC) about incident in Vega Baja Site. Conference call with Jaime Pesquera (DCMC) about Homeca procedures. Make a report to Osvaldo de Jesus (GENERA) about incident in Vega Baja Site May 9, 2025. Call with Gilberto Soto (DCMC) about jobs in site Vega Baja today.
2025-05-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 12 Preparing cuts for dismantling the exhaust on GT1 2.
2025-05-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition activities field supervision and coordination. Met with Homeca Recyclers field guys supervisors (Issac Morales & Emanuel Santos) to discuss the daily activities. Cutting the turbine #2 exhaust today and catting scrap metal from turbine housing base.
2025-05-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Continued with demolition Activities field supervision and coordination. Met with Homeca Recyclers supervisors (Issac Morales & Emanuel Santos) field guys to discuss the daily activities. Continued cutting & dismantling the turbine #2 exhaust today. Cutting of the scrap metal from turbine #1
2025-05-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca resumed cleaning the field housekeeping and move materials to continue dismantling areas Day 12 Homeca make cuts on the steel chimney to prepare for rigging plan. Homeca used excavator to break concrete to make way for the rigging plan truck.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended Peakers meeting with project team status updates. Items discussed project management structure, safety review of protocols and updated schedule start of construction activities German Nunez, GENERA; Harry Del Valle, Gilberto Sucre, Frances Vallejo, and Foster Veazey DCMC and Rafael Pabon, Carlos Palomares (CDM Smith_
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended meetings to review Peakers project schedules Discussed impact to schedule based on procurement and delivery dates of equipment Rafael Pabon, CDM Smith Carlos Palomares CDM Smith German Nunez, GENERA.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS program status preparation and coordination for Weekly BESS PM/CM Meeting.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly BESS & Peaker's Project Needs with Jesus Cintron - Genera. Rafael Pabon CDM Smith presented Peakers needs and Gabriel Perez CDM Smith Presented BESS needs to Jesus Cintron for GENERA's support for both programs. Other Participants Franklyn Colmenares - CSA Group, Abraham Velaquez and Gilberto Sucre DCMC Partners.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS CHECK IN Weekly led by Gabriel Perez - CDM Smith. Provided update on BESS sites RFP's, Vega Baja - Demolition Status, Palo Seco - Decommissioning, Costa Sur - Rule 141 Addendum, Aguirre Phase Approach, & Global Topics. Participants from CDM Smith, CSA Group, Sargent & Lundy, Genera, and DCMC Partners
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Update discussion with Andres Concepcion - DCMC
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Site Assessment Request for BESS & Peakers led by Jesus Cintron - Genera. DCMC to prepare for each site Genera's obligations to clear up areas prior to Contractors' Mobilization. Frances Vallejo, Abraham Velazquez and Gilberto Sucre - DCMC, and Gabriel Perez - CDM Smith.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS PM/CM meeting weekly update reviewing Cambalache, Vega Baja, Costa Sur, and Aguirre status and pending items to complete post bid activities to final contract signature with Gabriel Perez - CDM Smith and Franklin Colmenares - CSA Group.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Meeting Luis Reyes and Luis Moctezuma - DCMC to bring them up to date on the Project Status.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja project update discussion with Jose Lopez - DCMC
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Construction Technical Internal Meeting PM / CM Team with Sargent & Lundy, CDM Smith, CSA Group and DCMC to be align with final scope, budget and schedule to negotiate contracts for Cambalache, Vega Baja, Costa Sur and Aguirre.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting to identify potential issues and keep the project on track. Meeting attendees were Jesus Cintron, Nelson Rosado, Ricardo Pallens, Carlos Palomares, Joaquin Quinoy, Gabriel Perez, Mike Kuczynski, Franklyn Colmenares (Genera), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on answering questions for Theresa Perez (DCMC) for Procore documents.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked information gathering to present for Procore Kick-off meeting for Andres Concepcion (DCMC) for Cambalache project.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing a PowerPoint for the Camabalache Procore kick-off meeting. This will include roles and responsibilities, tools to be used, SOP's and more.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOW and wrote summary to leadership to review and approve.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Power BI reporting review.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on PMO Monthly reporting for Raissa Borges (DCMC).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP's for publishing final versions.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked Procore correspondence to templatize and formalize communications.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Conference call with Luis Moctezuma (DCMC) about EHS department includes the Aguire Genera Site.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.75 |  | 184 | 322 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Meeting with Carirma Sanchez, Emanuel Santos (HOMECA), Eduardo Rivera, Gilberto Soto and Jaime Pesquera (DCMC) Osvaldo de Jesus (GENERA) about EHS incidents on site.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Continue Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Review the documents by jobs on site.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2.25 |  | 184 | 414 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Review the site pre-work. Review the emails about all Genera projects.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 184 | 230 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting to discuss BESS and Peakers project needs with Jesus Cintron (DCMC), Gabriel Perez (CDM), Gilberto Sucre and Abraham Velazquez (DCMC).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting to discuss site assessments for BESS and Peakers projects. The client requested outliens for both projects for all sites. Participants: Jesus Cintron (Genera), Abraham Velazquez (DCMC), Gilberto Sucre (DCMC), Gabriel Perez (CDM).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS check in call to discuss project overall status. Participants: Gabriel Perez (CDM), Sheila Torres (DCMC), Gilberto Sucre (DCMC), Rafael Calderon (DCMC), Foster Veazey (DCMC), Lauren Wells (DCMC), Carlos Palomares (CDM)
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with DCMC new hires, Luis Reyes and Luis Moctezuma (Scheduler and safety officer at Aguirre site). We gave them an onboarding presentation and discussed organizational chart, RFP and BESS project status. Participants: Gilberto Sucre (DCMC)
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado; and Marc Maceira (HONRA LLC) Subcontractors: Shellsea Maysonet, Johanna Díaz (SM Consulting), Carlos González and Ginnell Torres (Integrum)
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 -Completed the FOMB Contract Approval Request package for RFP 4826 – BESS Installation at Cambalache. Ensured that all 50+ required documents were properly compiled, organized, and accounted for in accordance with the FOMB Contract Review Checklist. Verified that each document aligned with the specific requirements outlined in FOMB’s Contract Review Policy and contributed to a clear, easy-to-navigate submission. The final package was structured to provide FOMB with a comprehensive and compliant roadmap for efficient review and approval.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PMO meeting preparation - Updated legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Initiated and executed performance testing on the Genera Connect Timesheets application, simulating real-world usage scenarios with approximately 20% of users concurrently submitting time entries. The tests confirmed that the current resource allocation is sufficient to support the expected user load while also identifying opportunities to optimize system performance and reduce IT infrastructure costs through more efficient resource utilization.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed outstanding items related to the Genera Connect Financial Tracker and Timesheets to assess readiness for upcoming milestones. Updated the communications plan for the launch of Genera Connect Timesheets to incorporate training materials developed by Keylamerari Sierra from Integrum, enhancing user onboarding support. Additionally, held discussions with Michael Silva from Genera PR to define requirements for executing performance tests on Genera Connect Timesheets resources, ensuring system stability and responsiveness ahead of deployment.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 13 Preparing cuts for dismantling the exhaust on GT1 2. received Man Lift arriving to replace the existing one.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT: Dismanteling and Demolition Activities field supervision and coordination. Meeting with Carirma Sanchez (HOMECA ) to discuss the weekend work schedule.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -BESS VEGA BAJA - Weekly look-ahead schedule review and discussion with the DCMC team, Gilberto Soto, Jaime Pesquera, and Gilberto Sucre: Coordination and logistics for Homeca's week work plan.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Dismantling, Decommissioning, and demolition works planning for phase II. Homeca Recycling should submit the weekly plan for the week. Carirma Sanchez (Homeca) was instructed that all manifests of recycling material removal should be certified based on the scope of work requirements. The morning safety talk included protecting workers and staff from lead exposure, which requires safely handling and removing lead hazards.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue Working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Yabucoa BESS Project. Looking for possibles discrepancies & measures. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Project review tasks in Procore related to BESS Costa Sur and Central Aguirre. Analyzed SOW, contract terms, and design documents to check for inconsistencies. Coordinated vendor quotes for water services and equipment for the site trailers, including printers and basic supplies.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Evaluation of the Megapack 2 XL Design and Installation Manual, Revision 2.7, point 1.2.1 Site Designer and 1.2.2 Installation Contractor
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Developing a safety plan for project and contractor personnel to prevent injuries, improve regulatory compliance, and build a better safety culture, The plan will establish minimum safety requirements for excavation and heavy equipment.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Evaluation of the Design and Installation Manual for Megapack 2 XL, Revision 2.7, Appendix B: Delivery Checklist and Process Flow.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Gilberto Sucre (DCMC Partners) to discuss Cambalache project pending items and submittals received during the weekend by contractor (RG Engineering) regarding site logistics and value engineering.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received and reviewed information received from contractor (RG Engineering) regarding Cambalache Value Engineering Revised Scope Evaluation and site staging areas. Evaluated and generated comments to support GeneraPR with negotiations to close construction contract.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed contractor (RG Enginering) and subcontractor (Morris-Shea) submitted documentation by email (Jose Robles) regarding BESS Rigid Inclusion Foundation Design progress.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed scope of work proposed by contractor (RG Engineering - Jose Segarra) regarding Levee access route in Cambalache site.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received RFI response from project designer Sargent & Lundy via Procore and reviewed information regarding electrical components needed to be purchased.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with review of submittal related of Dust Control, Disposal of demolition material, and RFP proposal of Homeca Contractor. The contractor still has not completed the demolition of both GT, still pending Diesel tank to be demolish and removal of folk lift.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting with Carirma Sanchez of Homeca in regard of a safety meeting regard of a safety incident during las week. Reviewing the RFP contract of Homeca to evaluation project contract agreement with Genera PR.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with reviewing the Homeca contract and cost proposal, Reviewing submittal in of Dust Control Plan for demolition of concrete slab.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working on site of Vega Baja BESS project for the transition of the project with Site Manager Jose Lopez of DCMC during this site visit we are in a transition of all pending work overview. Meet with Construction Manager Jaime Pesquera of DCMC to understand work progress at project site.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- participated in a virtual meeting via Microsoft Teams with Ms. Maria Sanchez from Genera PR, and DCMC staff to review and discuss the weekly progress of ongoing project activities.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed cycle counts for scheduled inventory locations, specifically covering areas GB 001 to GB 015. This task supports ongoing initiative to ensure alignment between physical stock and system data.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued cycle counting activities for assigned inventory locations, specifically from GB 001 to GB 015. The objective was to verify and reconcile physical inventory against system records, to ensure accuracy, consistency, and compliance with both regulatory and operational standards
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed variance analysis by identifying discrepancies and investigating inventory inconsistencies to enhance overall inventory control. This effort contributed to greater accuracy, improved operational efficiency, and enable timely corrective actions. The activity focused specially on inventory locations GB 001 to GB 015.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a recount at the San Juan warehouse alongside Mr. Milton Flores from DCMC to validate inventory accuracy. This effort was critical for confirming initial cycle count results, addressing discrepancies, and strengthening the reliability and consistency of inventory records
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-supported inventory data validation and the preparation of cycle count documentation in coordination with Mr. Milton Flores of DCMC to facilitate upcoming operations at the San Juan warehouse. Responsibilities included verifying item locations, confirming stock levels, and coordinating materials to improve procedural efficiency and inventory flow.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the San Juan warehouse, prepared and submitted a detailed inventory analysis report for Mr. Anthony Vega of Genera PR, consolidating information from all warehouse locations. The report encompassed catalog listing, item quantities, valuation summaries, discrepancy findings, threshold levels (min/max), and performance metrics to accurately represent each site's inventory status. The review specifically addresses inventory locations from GB 001 to GB 015, CR 140 to CR 165, DM 001 to DM 050, BR 001 to BR 008, HL 001 to HL 007.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a job briefing with Giovanni Taffanelli, Juan Vallejo and key DCMC warehouse personnel to address discrepancies identified during the previous week operation and to review data entry protocols aimed at improving inventory accuracy and control.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Discuss project 817248 of possible findings of duplication with DCMC D'Alexzander Gónzalez and Roberto Bosch.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Project Funding Identification | Direct-PA | Review and determination of most appropriate funding vehicle for client/applicant's funding needs | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Discuss the finding of the review of the Project 817248 with DCMC D'Alexzander Gonzalez to determine course of action with CE.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Project Funding Identification | Direct-PA | Review and determination of most appropriate funding vehicle for client/applicant's funding needs | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Based on the review the SOW of Project 817248 modifies the CE.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Continue work with CCL Tracker integrate the available information regarding Cost Estimate, Scope of Work, RFP, Contracts and Invoice of Critical Components.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Alejandro Maymi, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Project Funding Identification | Direct-PA | Review and determination of most appropriate funding vehicle for client/applicant's funding needs | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Reviewed Project CE 817248 under the Critical Components category to identify elements potentially excluded during the duplication of benefits (DOB) analysis. The task involved cross-referencing component lists with FEMA and insurance documentation to ensure no eligible scope was incorrectly omitted. This review supports the accurate validation of project costs and helps uphold compliance with FEMA PA program requirements, contributing to the integrity of the funding request.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Document Comments related to providing temporary access to substation and possible alternatives submitted by Carlos de Jesús (DCMC)
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document different discipline Site, Arc Procore Folder 100- 6. Appendix D.1- Design Drawings.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document different discipline Architectural and Structural, Arc Procore Folder 100- 6. Appendix D.1- Design Drawings.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Document, Construction Schedule Template Meeting Document, Tasks and Dates submitted by Carlos De Jesus (DCMC).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Continued to dismantle, decommissioning and demolition works and planning for phase II, for turbine #1 base steel frame & turbine #2 base steel frame (discussed how to and dead ends with them) with supervisors Issac Morales & Emmanuel Santos from Homeca recyclers.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES. Had a Safety Meeting & discussion of an Incident/Accident Report with the DCMC team, Gilberto Soto DCMC, Eduardo Rivera DCMC, Jean Menay DCMC, and Homeca Recyclers Team Carirma Sanchez & Manuelli Santos. Homeca Recycling keeps dismantling, Decommissioning and demolition works and planning for phase II.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 13 Homeca make cuts on the steel chimney to prepare for rigging plan.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Pre-Intervention Review - Working with ENVIRONMENTAL HEALTH SAFETY SERVICES INC. Contract #103750_2024-G00512 and TO#6_Invoice# 11826_ Apr 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Invoice Approved.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Continue working on Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- GENERA & DCMC- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC Participants: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and others.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review. Siemens Chek-In Meeting: Peakers Costa Sur project Status follow-up and review of contract schedules. Participants from Genera (Jesus Cintron, German Nunez), CSA (Franklyn Colmenares) CDM PM (Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC Contract Manager - (Rafael Calderon, Abraham Velazquez , D'Alexander González and Sheila Torres).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team , CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuczynski, Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Pro-Core (Lauren Wells).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GB001 to GB015
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GB001 to GB015
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GB001 to GB015
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GB001 to GB015
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GB001 to GB015
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BR 00 001 000 to BU 00 008 000.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BR 00 001 000 to BU 00 008 000
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BR 00 001 000 to BU 00 008 000
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations CR 135 to CR160
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 135 to CR160 and DM 001 to DM 050 using Cycle Count List # 620/21/24/632/33/34
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 135 to CR160 and DM 001 to DM 050 at the Aguirre warehouse to start the cycle counts.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 628/631/635 locations CR 135 to CR160
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #622 and 623 locations HL001 to HL007
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #622 and 623 for locations HL001 to HL007, totaling 61 units.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations HL001 to HL007 using Cycle Count List #614 locations HL001 to HL007
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations HL001 to HL007
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations HL001 to HL007 to start the cycle counts.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera PR ¦ Document Control - Data Management Vega Baja BESS/ Cambalache BESS/Aguirre BESS/Daguao Peakers/Jobos Peakers San Juan Peakers/Costa Sur Peakers to ensure documents are created, reviewed, distributed, stored and archived in an organized and controlled manner.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera PR ¦ Document Control - Data Management Vega Baja BESS/ Cambalache BESS to ensure information is organized, accurately transmitted and readily accessible for the project team.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Manage Observations tool to review Ball in Court assignation on the Procore Platform, permission issues and review of core tools main distribution items.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Cambalache Drawings status and the implementation of Drawing Areas at the Drawings Tool for better classification on multiple sheet drawings.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Peakers Project Check-in Call hosted by Franklyn Colmenares (CDM Smith). Discussed current open RFP status, Procore progress on active users, determination on current pending agreements and others.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Vega Baja and Cambalache directory staff; addition of Genera PR new users and review of internal user's permissions on specific core tools such as Observations.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review team efforts on Observations Tool for Vega Baja; analyzing current observations workflows, issues with assigning tasks to a contractor's representative, and run testings for the tool with the field staff.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review internal users (DCMC) permissions on Observations to assign non-compliance tasks and incident reports. Review projects scope of work to determine expected safety documents and submissions within a submittal log.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Peakers Project Check-in Call hosted by Gabriel Perez (CDM Smith). Discussed current open RFP status, Procore progress on active users, determination on current pending agreements and others.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, and Glorimel Torrado. Also, Shellsea Maysonet (SM Consulting) and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 149 | 372.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - _pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18334035_Jan2025. Final review on the pending narratives, prepare RFI and send information by email requesting clarification. This invoice has 8,505 excel lines with information to be reviewed.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, CDM Constructors, CPM, EHSS, Homeca, Tesla, B&V, Siemens Energy and CAPTA. Review CPA status with Rafael Calderón (DCMC) for updates on tracker for meeting. Also, verify for any new payment made on Friday that can change our presentation to Genera. Prepare delta for Power Point presentation.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create communication pieces to inform the community of Aguirre that on Thursday, May 15, the Aguirre center will participate in a drill involving a suspicious device. Due to the nature and complexity of the event, there will be questions from community members who may have concerns about their safety and disruptions to their usual routine.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey. In the meeting was the Genera PR Team: Jesus Cintron, Joaquin A Quinoy, Ricardo Pallens, Maria Sanchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczinsky and Nelson Rosado. The meeting was about the Bess Project.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams Meeting with DCMC Team: Frances Vallejo Rosich, D'Alexzander Gonzalez and Mark Merritt. In the meeting was the Genera Team: Jesus Cintron, Kevin Futch, Francisco Santos, German Nunez, Alejandro Maymi and Sarahi Medina Nieves. In the meeting was the CDM Smith: Juan Mendoza, Rafael Pabon and Carlos Palomares. The meeting was about Peakers Check In.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Communicate with all the community leaders and stakeholders of Aguirre and Jobos and give them the communication pieces to inform the Aguirre community that on Thursday, May 15, the Aguirre power plant will participate in a drill for a suspicious device. The exercise will be conducted live by making calls to 9-1-1 and responders will move from their respective municipalities. Due to the nature and complexity of the event, there will be questions from the communities and concerns regarding their safety and disruption of their usual routine.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Work and finish at Canva on the design of the fact sheet for the communities related to the Bess and Peakers project.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 –Project Management -DR4339: Continuing to draft the Safety, Health, and Environment (SHE) Manual, it is essential to adhere to the correct format, ensuring consistency, technical accuracy, and compliance with established standards. This document should follow the structure and style of the original English version, incorporating appropriate terminology and linguistic adaptations that preserve the clarity and original intent of the content. Formal sections, headings, numbering, and references must be maintained to ensure the manual is comprehensive and easy to navigate. By doing so, we can guarantee that the SHE Manual effectively communicates vital information and guidelines, promoting a safe and healthy work environment.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 139 | 451.75 | 139 | Yes |  | Site | Genera PR – Deliverable 11 –Project Management -DR4339: Continuing the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. I am currently drafting the document using the correct format, carefully following the structure and style of the original English version to ensure consistency, technical accuracy, and compliance with established standards. This draft will include precise terminology and linguistic adaptations that preserve the clarity and intent of the original content while maintaining formal sections, headings, numbering, and references.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 –Project Management -DR4339: Continue translating the Safety, Health, and Environment (SHE) Manual from English to Spanish. I am currently drafting the document using the correct format, following the structure and style of the original English version to ensure consistency, technical accuracy, and compliance with established standards. This draft will include appropriate terminology and linguistic adaptations that preserve the clarity and original intent of the content while maintaining formal sections, headings, numbering, and references.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 134 | 469 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Continued technical review of the BESS Erosion and Sediment Control Plan for the 4339_9510 BESS Cambalache project. Assessed whether the proposed measures meet environmental compliance requirements and documented key findings for coordination with the design and permitting teams.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create comments about temporary access ramp in project for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create comments about master schedule milestone update for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 134 | 167.5 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Kick off meeting with Gilberto Sucre and Frances Vallejo DCMC to make introduction of the BASS Aguirre Genera projects.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Reviewed the BESS Erosion and Sediment Control Plan for the 4339_9510 BESS Cambalache project. The review focused on assessing the adequacy of proposed sediment barriers, drainage flow paths, and erosion prevention measures in accordance with environmental compliance standards. Documented observations and recommendations to align the plan with FEMA and local permitting requirements, supporting implementation readiness for site preparation activities.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 |  | 122 | 457.5 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Processing Peakers and BESS projects data for bi-weekly and monthly report generation.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Rafel Pabon (CDM Smith), Luis Roman (DCMC), Paola Arroyo (Genera), Jorge Bracero (Genera), Lauren Wells (Lemoine), Foster Veazey (Lemoine), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Franklyn Colmenares (CDM Smith), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Sheila Torres (DCMC).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 122 | 274.5 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Organizing and reviewing Peakers and BESS projects data for reporting purposes.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC).
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices Purpose Site inspection. Meeting with Carirma Sanchez, Emmanuel Santos (HOMECA), Osvaldo de Jesus (GENERA) (DCMCD) about EHS incident. Total Distance 64.0 miles
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.97 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-following the meeting at the San Juan warehouse with Mr. Milton Flores from DCMC, returned back home in Guaynabo. The purpose of the visit was to discuss strategies for enhancing data accuracy and ensuring consistent reporting withing the ABC cycle count process and also assist Mr. Flores with the process.
2025-05-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 5.32 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from home in Guaynabo to Central San Juan to meet with Mr. Milton Flores from DCMC. The purpose of the visit is to review the status ongoing inventory control efforts and discuss strategies for enhancing data accuracy and ensuring consistent reporting withing the ABC cycle count process.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Remote | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Foster Veazey, Barry Scanlon, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Site visit to Costa Sur, marked up all structures to be demolished as per revised RFP, documented items via pics& blue beam mark ups all files loaded up on PROCORE for team review
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Second part of agenda with ref. to the onsite visit to Costa Sur facility. Took inventory of materials and equipment currently on site to be designated for relocation and removal of current locations. All files with mark ups have been uploaded to PROCORE for team reviews.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L / CDM Smith Weekly BESS Drawings Meeting. Reviewed upcoming scheduled dates for issuing IFC drawings to support construction for Vega Baja, Cambalache, Costa Sur & Aguirre. Sargent & Lundy, CDM Smith, CSA Group and DCMC Partners representatives.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO ReportingThe Project Status Update meeting focused on several key areas, including the planning for the Demolition Project, coordination of the contractor walkthrough, and updates on budget and financial items. Abraham is finalizing a detailed report on materials to be moved at Costasur, with demolition expected to begin by mid to late August. A contractor walkthrough is scheduled for Monday, involving important team members and selected contractors, ensuring clarity in the invitation process. The financial discussion included change order packages and the current status of the project budget. Additionally, updates on Procore implementation highlighted significant progress on safety inspections and document organization, while training opportunities were offered for team members needing immediate assistance. Action items were assigned to various team members to address specific tasks and further advance project goals. CDM Smith, CSA Group, and DCMC Partners
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Correspondence update review and daily coordination of meetings and action items.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur discussed the need to get direction and approval from Genera General Manager for location of Emergency Generator to be relocated and DCMC office trailer location. Alternate options were evaluated with Harry del Valle DCMC Partners.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up meeting focused on key updates regarding staffing, operational matters, facilities, and safety protocols. Shared staffing updates, highlighting new hires and ongoing evaluations for various positions within the team, while also noting the need for increased manpower due to changes in project demands. Operational updates included plans for improved utilization of Procore software, with a scheduled presentation to address cooperation issues. The team discussed the arrival of new trailers and the need for additional trailer space at various sites. Safety remained a top priority, with planned meetings to tackle concerns and ensure compliance. Participants: Mark Merritt, Michael Merritt, Laura Wells, Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia Holton - DCMC and Jack Darnall Lemoine.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja ARG Ceres presented their Value Engineering Alternative of using Pre-Cast Concrete Solution for the Cast in Place walls and platform. ARG Ceres requested final information to run their model and commercial evaluation. Sargent & Lundy, CDM Smith, and DCMC Partners representatives participated.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Weekly Construction Meeting Topics discussed Safety, Demolition Progress, work plan for week, Diesel transfer, and Temporary Power Installation. Scheduled a Progress and Safety Walk thru on Friday at 9 am. Participants from Homeca, CDM Smith, and DCMC Partners.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting RGE / Costa Sur Site The Project Coordination and Technical Review Meeting for the RFC concerning the RGE/Costa Sur Site commenced with congratulations to RGE for securing the Costa Sewer Civil Structural Project. Key items discussed included the review of pending Requests for Clarification (RFCs), the need for specific documentation, and the current project schedule. RGE was tasked with providing updated pricing and necessary documentation, including a demolition breakdown and a redacted proposal. Concerns about lead paint discovered on site were raised, necessitating a quote for remediation while ensuring the schedule accommodates this work. Technical specifications and site layout were also addressed, with plans to upload relevant documents for RGE's review. The contract was deemed generally acceptable, and a follow-up meeting was scheduled to address outstanding items and coordinate next steps. Action items from the meeting were assigned to team members to ensure progress and alignment moving forward. RGE, CDM Smith, CSA Group, Genera, Sargent & Lundy and DCMC Partners Participated.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Daily Update and Aguirre Kickoff Coordination with Jose Lopez - DCMC
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on meeting agenda items for Cambalache procore kick off call.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) to discuss submittal workflows for Vega Baja.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked SOP schedule and publishing of finished ones.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences to capture business processes and send custom communications created through a template to subcontractors, contractors, and clients.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) to discuss Procore items.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks items for DCMC Procore team.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO reporting with Raissa Borges (DCMC), Frances Vallejo (DCMC), Gilberto Sucre, and others.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for Submittals at the company level.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on meeting agenda items for Cambalache procore kick off call.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on scheduling of meetings for Procore items.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on PMO reporting details for Raissa Borges (DCMC).
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 1.25 |  | 184 | 230 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Training to Rafael Navarro (Rafy Cool Services) by Homeca.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Meeting with Javier Almodovar, Alberto Borreli (ARG) (about Cambalache Project) Health and Safety themes.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Project Formulation | Direct-PA | Activities necessary for project formulation (i.e., meetings, coordination, documentation request/review) | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection, review the Vega Baja transport Diesel Plan.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Review the Vega Baja Diesel Plan to Palo Seco Genera Site.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2.75 |  | 184 | 506 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Training in Genera EHS program to Adrian Iglesias and Arturo Iglesias (Technical Fire), Jorge Parra, Pedro Marrero, Ludgardo Gonzalez and Carlos Hernandez ARG-ceresjv. Metting with Eduardo Ramos, Carirma Sanchez (HOMECA), Gilberto Sucre, Jose Lopez, Jaime Pesquera, Gilberto Soto (DCMC) and Gabriel Perez (CDMSMITH) about Vega Baja Project.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and analyze the community engagement work plan for 2025.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- call with Jaime Pesquera (DCMC) to discuss Vega Baja incidents and how it was resolved.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss program status, Procore, staffing update, Trailers, safety plan. Participants: Mark Merritt, Mike Merritt, Lauren Wells, Gilberto Sucre, Foster Veazey (DCMC).
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended trailer update meeting with Harry del Valle and Gilberto Sucre (DCMC) to discuss trailer coordination for Aguirre and Costa Sur.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Prepared for PMO reporting weekly meeting by reviewing and updating the project tracking spreadsheet. Incorporated feedback and updates received from the Genera procurement team, including changes to documentation status, and contractor communications. Ensured the tracker reflected accurate, real-time information to support productive discussion, alignment across teams, and timely follow-up during the coordination meeting.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Developed detailed checklists in support of federally funded contract approval submissions, in accordance with the FOMB Contract Review Policy and Genera's Procurement Manual. Ensured that each checklist clearly outlined the required documentation, aligned with policy provisions, and served as an organized reference tool to facilitate a streamlined and compliant review process. The checklists were tailored to the specific contracts being submitted and designed to enhance transparency, traceability, and ease of evaluation for the reviewing authorities. Shared these checklists with Axel Velez, Ricardo Palléns and Jesús Cintrón (Genera) for review and sign-off.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Peakers Developed the draft of Addendum No. 3 for RFP 231161, related to the Costa Sur Demolition project. The addendum was prepared to formally amend and substitute the following components of the solicitation: (a) Section 5.1, Milestone 3 – Site Visit and Engineering Presentations with Proponents; (b) Attachment D – Scope of Services; (c) Exhibit E – Price Proposal Forms; and (d) Exhibit E.2 – Division of Responsibility. Formatted and updated the accompanying exhibits to ensure consistency with the revised content and compliance with procurement standards. The addendum was structured to provide clarity and support an orderly continuation of the RFP process. Sent to the CDM Smith and Genera teams for review and approval, and for subsequent publication on the Power Advocate platform.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 14 Homeca make cuts on the steel chimney to prepare for rigging plan. Received visit from Carlos Hernandez next step contractor, and Vieques Enviro inc. to drain Oily water separator. Dismantled two pieces of structure from the G 1 2 exhausted to transport to Homeca Recycling center in Caguas.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Weekly project meeting with HOMECA representatives Carirma Sanchez and Eduardo Ramos. Project schedule and progress discussion to mitigate risks, optimize resource allocation, and achieve project objectives effectively, as well as pending submittals and pending items.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Meeting minutes built, revised, and distributed to Gilberto Sucre, Jaime Pesquera (DCMC Partners) & Noel Soler (CDM Smith).
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Vega Baja BESS- Prepared the Agenda for the weekly progress meeting for the Vega Baja Site to help discuss project issues and improve communication across the site team.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue Working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Yabucoa and Costa Sur BESS Projects. Coordinate trailer's location in Costa Sur BESS Project Looking for possibles discrepancies & measures in drawings and contract documents. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Worked in Procore platform verifying Scope of Work, drawings, and schedule documentation for the BESS efforts at Costa Sur and Central Aguirre. Investigated potential issues or missing elements in contract deliverables. Gathered pricing information for potable water, printers, and site trailer materials.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-The initial meeting of the BEES project was handled at the Cambalache site on safety issues with the contractor EGE staff (Alberto Borrely) (Jose Segarra) and (Javier Reyes). The DCMC work team also attended (Andres Concepcion) (Luis Damudt) (Luis Duque) and (Carlos de Jesus) on behalf of the client Genera (Osvaldo de Jesus).
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Safe work procedures submitted by the EHS department, cutting and welding, and daily work permits are verified.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with the client Genera Heminio Arroyo and Nelson Colon with the purpose of discussing access control to the facilities and the personnel responsible for project security.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed activities and sequences for latest construction schedule. Drafted comments to support negotiations on contract agreement.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Phone call with RG Engineering Project Manager Jose Segarra to discuss regarding project schedule pending actions and to coordinate a meeting for geotechnical designers as part of the foundation submittals and design.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - (1) Reviewed pending action items to follow up on contract execution. (2) Met with Cambalache site team to align on daily activties (3). Reviewed Safety meeting agenda with Jorge Mercado (DCMC) to discuss safety procedures with contractor (RG Engineering - Jose Segarra).
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting regarding Cambalache Safety processes with RG Engineering (Contractor - Javier Reyes, Alberto Borrelli) and DCMC Partners (Jorge Mercado, Jean Pierre Menay). initial discussion on construction safety procedures
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting in Cambalache Facility with GeneraPR (Herminio Arroyo and Nelson Medina) and DCMC (Jean Pierre Menay) to discuss security and access control during the construction planning.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing contract RFP and Cost Estimate of contractor ARG/Ceres for the installation of Vega Baja BESS. Continue reviewing submittal and RFI for Vega Baja Demolition Project.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation of Abraham Velazquez, Frances Vallejo, Gilberto Sucre, Lauren Wells, Rafael Calderon, Pedro Cabrera, Raissa Borges, Sheila Torres, Paola Arroyo, Paul Browne from DCMC and Lemoine; and Franklyn Colmenares, and Carlos Palomares (CDM Smith), Meeting with DCMC to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing incident report in Procore in regard of Homeca Contractor working at Vega Baja GT demolition work.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing document send by Gilberto Sucre of DCMC in regard of BESS Tesla installation & design manual, Transportation & Storage & Lifting manual, and Operation & Maintenance manual.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue reviewing documents in Procore in regard of contract RFP, Management Plan, Schedule and Cost Estimate of contractor ARG/Ceres for the installation of Vega Baja BESS.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a compliance-driven inventory recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC. This effort was undertaken to ensure alignment with regulatory standards, validate previous inventory counts, resolve discrepancies, and uphold the integrity and accuracy of inventory records as required by project and audit protocols.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a job briefing with Juan Vallejo, Milton Flores and key DCMC warehouse personnel to review discrepancies identified during the prior day activities. The session focused on reinforcing accurate data entry practices to strengthen inventory integrity and ensure adherence to procedural standards.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory data analysis and prepare cycle count sheets to support schedule activities at the Palo Seco warehouse, in coordination with DCMC Mr. Giovanni Taffanelli. Task included validating item locations, verifying stock accuracy, and organizing materials to support a streamlined and efficient inventory process.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed cycle counts for the designated inventory locations assigned for the day, specifically from AG 001 to AG 007. This effort supports ongoing initiatives to improve inventory accuracy and ensure alignment between physical stock and system records.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed variance analysis to identifying discrepancies and evaluate inventory inconsistencies in support of accurate inventory control. The objective was to improve data integrity, operational efficiency, and ensure timely corrective actions. Today's efforts were focused on reviewing high priority inventory locations to confirm alignment with systems records.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while stationed at the Palo Seco warehouse, developed a consolidated inventory report for Mr. Anthony Vega of Genera PR, integrating data from all warehouse locations. The report encompassed catalog counts, items details, unit quantities, cost analysis, discrepancies, and maximum/minimum stock thresholds, along with percentage indicators to reflect the current inventory status of each facility. Locations reviewed included AG 001 to AG 007, GB 016 to GB 021, BN 001 to BN 005, DM 002 to DM 040.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Discuss work plan action regarding to Federal Projects DCMC: Pedro Cabrera, GENERA-PR Joaquin Quinoy.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Complete Bi-Weekly Report Template for PMO Reporting Meeting
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Project Funding Identification | Direct-PA | Review and determination of most appropriate funding vehicle for client/applicant's funding needs | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Continued revising Cost Estimate CE 817248 related to Critical Components under the FEMA Public Assistance (PA) Program. This task included reviewing scope alignment with eligible damages, refining quantities and unit costs, and ensuring compliance with FEMA cost reasonableness guidelines. The objective is to support accurate and justifiable funding requests, contributing to proper documentation and audit readiness as part of the DR 4339 recovery efforts.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review PREB Resolutions regarding to Regulatory Approvals and Installation Timeline for Emergency Peaking Units and BESS Projects under Project 164988.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Revision Proyectos Federales Status meeting with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz, and Roberto Bosch; from MZC Shellsea Maysonet;, from GENERA-PR Joaquin Quinoy and Jorge Sanchez to discuss priorities and deliverables, status updates, identify next steps for projects under Federal Grant.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC and Lemoine: Abraham Velazquez, Frances Vallejo, Gilberto Sucre, Lauren Wells, Rafael Calderon, Pedro Cabrera, Sheila Torres, Raissa Borges, Paola Arroyo, Paul Browne and (CDM Smith), Carlos Palomares, and Franklyn Colmenares, Meeting with DCMC to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Project Funding Identification | Direct-PA | Review and determination of most appropriate funding vehicle for client/applicant's funding needs | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Modify CE 817248 after review of DCMC D'Alexzander Gónzalez and incorporate recommendations.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache - Initial Safety Meeting Work procedures, General/RGE work permits, RGE emergency plan, Risk assessment with Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team Jose Segarra, Alberto Borelli, Javier Reyes from RGE.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Practice with the PROCORE platform tutorial videos on the Daily Logs topic.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache - Review the Issue and topics before Initial Safety Meeting 10:00am 12:00pm with Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache Weekly Internal Meeting Jorge A. Mercado, Andres Concepcion, Luis O. Damudt, Luis Duque DCMC Partners Cambalache Power Plant and Herminio Arroyo, Nelson Medina, and Osvaldo De Jesus from Genera PR
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Rewrite and review important notes during Cambalache Meeting Walk-tour 9:00am-12:30pm RG Engineering and Genera PR.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Safety briefing conducted by Homeca and Gilberto Soto DCMC was present. Had Meeting with Carirma Sanchez (HOMECA) to discuss the weekly & weekend work schedule.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervising works at the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform so everyone on the team can work in the proper context and achieve tasks efficiently.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 14 Homeca make cuts on the steel chimney to prepare for rigging plan. Received visit from Carlos Hernandez next step contractor, and Vieques Enviro inc. to drain Oily water separator
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Pre-Intervention Review - Working with ENVIRONMENTAL HEALTH SAFETY SERVICES INC. Contract #103750_2024-G00512 and TO#7_Invoice# 11835_ Apr 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 164 | 656 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Pre-Intervention Review - Working with ENVIRONMENTAL HEALTH SAFETY SERVICES INC. Contract #103750_2024-G00512 and TO#6_Invoice# 11826_ Apr 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria PMO Reporting Meeting - DCMC PMO staff meeting to be discussed specific need of reporting based on project execution development per area. Working on PPT presentation template and review updates from BESS and Peakers project. DCMC Participants Frances Vallejo, Raissa Borges, Glorimel Torrado, Gilberto Sucre, Sheila Torres, Abraham Velazquez, Eduardo Rivera and Paul Brown.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations AG001 to AG007 using Cycle Count List #645.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GB016 to GB021
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GB016 to GB021
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GB016 to GB021
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GB016 to GB021
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GB016 to GB021
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BN 00 001 000 to BQ 00 005 000
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BN 00 001 000 to BQ 00 005 000
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BN 00 001 000 to BQ 00 005 000
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations CR 160 to CR 199 and DM 010 to Dm 040
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 646/51/56 locations CR 160 to CR 199 and DM 010 to Dm 040
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 160 to CR 199 and DM 010 to Dm 040 at the Aguirre warehouse to start the cycle counts.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #657 and 658 for locations AG001 to AG007, totaling 166 pieces.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations AG001 to AG007 to start the cycle counts.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #657 and 658 locations AG001 to AG007
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Costa Sur Peakers/ Vega Baja BESS - Submittals Data to ensure documents are created, reviewed, distributed, tracked, stored and archived in an organized and controlled manner.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Vega Baja BESS to provide accurate and timely information, leading to better execution of project plans and specifications.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) to discuss the Submittals Workflow Templates for the Cambalache Power Plant project.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Workflow Templates implementation for the Cambalache Power Plant Project: creating approval workflows on Submittals Tool depending on submission category.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of unpublished drawings at the Cambalache project in order to fix troubleshoot on multiple sheet drawings: communication with the Procore System Team for guidance on new drawing features creation.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Financial Tool implementation regarding the connection of Schedule Tool for reports and other output information required to link both tools.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 151 | 453 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the final publishing of tools SOP including new information regarding permissions and potential tasks users will be able to do. These are External SOPs to ensure consistency and quality which help minimize errors and ensure regulatory adherence.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.75 |  | 149 | 409.75 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Pre Intervention for ENVIRONMENTAL HEALTH SAFETY SERVICES INC. Task Order #8 and Task Order #9 invoices. These two invoices were reviewed and edited since there was missing information on the document. Compliance information was reviewed (reports for lead and asbestos and formal documents). A formal RFI was sent to Manuely Concepción (CDM Smith) with invoices missing signature and information.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Pre Intervention for ENVIRONMENTAL HEALTH SAFETY SERVICES INC. Continue reviewing Task Order #8 invoice. Start verifying deliverables for this invoice and making notes on pending items.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 149 | 111.75 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - PMO Reporting meeting - Recurrent meeting to discuss project management for Bess and Peakers. In this meeting participated DCMC Frances Vallejo, Rafael Calderón, Glorimel Torrado, Paul Brown, Pedro Cabrera, Gilberto Sucre, Eduardo Rivera Jordán, Raissa Borges, Lauren Wells and others.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 149 | 447 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review contract for ENVIRONMENTAL HEALTH SAFETY SERVICES INC. This is a new vendor in Pre Intervention, I started reviewing all contract information and Task Orders document. I prepare my folder with contract important information regarding invoicing and start reviewing first invoice.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón (DCMC) to prepare PMO presentation for today. On this session we discuss pending action items on Siemens and Tesla and past two week updates for this two contracts and add the information on the shared folder.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ Hurricane Maria_PW#9510 - Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6, Invoice #18334035_Jan2025. Continue with review, verify RFI response on clarification request and review all deliverables requested to complete the compliance review. Prepare final package and invoice for Jesús Cintrón (Genera) signature. Send the invoice for signature and update excel Pre-Intervention tracker.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create and send email update with Digno Cartagena of the Genera PR team regarding the coordination and follow-up efforts with community leaders in the Salinas area to inform them about the drill at the Genera Aguirre Complex. Additionally, information was provided regarding follow-up to communications sent to the municipalities regarding the drill. A meeting or call was requested with Digno Cartagena to discuss logistical details regarding participation in the drill.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued to organize all the visual and textual elements into a clear, orderly, and attractive structure in Canva particularly related to the project in Arecibo. Start a search for international information related to Bess and Peakers, focusing on their initiatives and collaborations.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Reporting Meeting with DCMC Partners Team: Frances Vallejo Rosich, Eduardo Rivera Jordan, Jean Pierre Menay, Lauren Wells, Rafael Calderon, Gilberto Sucre, Paul Browne, Foster Veazey, Sheila Torres Sterling, Raissa Borges Almodovar, Abraham Velazquez, Glorimel Torrado and Pedro Cabrera. In the meeting was the CDM Smith team: Carlos Palomares.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria After conducting research on international information related to the BESS and Peakers project, I started to edit and adapt this information for the newsletter in Canva in order to strengthen relationships with the community and continue the Genera Newsletter project. These tasks included editing the information, adjusting in the Canva, and ensuring the aesthetics of the project.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue designing and editing informative graphics for the Newsletter on the Canva platform (such as statistics on the impact of the BESS project in Arecibo and events held), using Canva's design tools. These tasks included searching for graphics, adjusting the format to the branding of the Genera brand and copy writing
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordinate meeting with Sandra Miranda, the director of the childcare center in Toa Baja Choo Choo Train Day Care and Learning Center with the purpose of organizing educational talks in the summer during camps and informing the preschool community about the Bess and Peakers project.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create an email to follow up with municipalities regarding the drill involving a suspicious device in Aguirre. The goal is to ensure communities have all the information related to the event.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translating the Safety Manual from English to Spanish. Focused on reviewing translated sections for consistency, technical accuracy, and appropriate terminology. Worked on aligning formatting and structure to mirror the original document, ensuring the final Spanish version meets quality standards and is clear and accessible for Spanish-speaking personnel.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – (Day 2) Continued review of the Erosion and Sediment Control Plan for the 4339_9510 BESS Cambalache Project. Focused on analyzing the proposed best management practices (BMPs) to ensure compliance with environmental regulations and FEMA guidelines.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create comments about RFP proponent schedule in file Sch VE prop Rev4 (5.11.25) Steel Structure (HVP)_Det-SE_120525 and Sch VE prop Rev4 (5.11.25) Steel Structure (HVP)_Det-SE_120525_Critical for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on inspection and create comments of not related drawings using Design drawings uploaded in PROCORE for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue Revision of project documentation (Genera BESS State of Design and Milestone Schedule) BESS Genera Aguirre projects to help track progress, communicate and coordinate with the team, identify risks, and ensure accountability.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Revise project documentation (Genera BESS State of Design and Milestone Schedule) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Continue working on the erosion control measures proposed for the BESS Cambalache site under project 4339_9510. Recommended improvements and documented review outcomes.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC Safety coordination meeting with Andres Concepcion (DCMC) and Genera PR Cambalache site manager Herminio Arroyo (Genera PR) for the 4339_9510 BESS_Cambalache project.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 –Reviewed technical specifications and cross-sections included in the BESS Erosion and Sediment Control Plan for the 4339_9510 Cambalache project. Provided comments for design adjustments to better align with local environmental permitting standards.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 128.05 | 128.05 | 128.05 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 supplies needed so high light revised demolition scope of work at costa sur site in preparation for general contractors walkthrough
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Preparing excels sheets to be filled by the PMO team on the reporting meeting where we discuss Critical Components, Inventory, Peakers and BESS projects progress, key milestones and address any issues impacting timelines or deliverables.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue compiling and analyzing Peakers and BESS projects status information and documentation.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 122 | 305 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Analyzing and structuring Genera projects (Critical Components, Inventory, Peakers and BESS) information discussed on the PMO team meeting.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Glorimel Torrado, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 68.18 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route Travel from Guaynabo (18.392607 -66.123698) roundtrip to Cambalache Power Plant, Arecibo (18.471729, -66.700701) back to Guaynabo (18.392607 -66.123698) Purpose project meeting and site walkthrough for initial safety coordination with Genera and RGE for 4339 9510 BESS Cambalache project. TOTAL MILEAGE 97.4 miles
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.35 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- traveled directly from Guaynabo to Central Palo Seco to meet with Mr. Giovanni Taffanelli from DCMC. The purpose of the visit is to provide on-site oversight of warehouse operations, evaluate current inventory control measure, and collaborate with Mr. Taffanelli on improving process efficiency. The visit also focused on identifying potential gaps in execution and aligning efforts with project deliverables
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.42 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria following the visit at the San Juan warehouse with Mr. Giovanni Taffanelli from DCMC, returned to Guaynabo. The purpose of the visit was to provide on-site oversight of warehouse operations, evaluate current inventory control measure, and collaborate with Mr. Taffanelli on improving process efficiency. The visit also focused on identifying potential gaps in execution and aligning efforts with project deliverables.
2025-05-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 74.2 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection from home offices San Juan to Cambalache to Vega Baja Genera Site to Home Offices San Juan (18.47 Purpose Genera PR - Metting with Osvaldo de Jesus, Nelson Medina (GENERA) and Andres Concepcion, (DCMC), in Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they me Total Distance 106 miles
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 384.8 | 384.8 | 384.8 | Yes |  |  | Portsan - Rental of portable toilets for Genera project Deliverable 11
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financials
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended meetings on Peakers drawing review with S&L discussed reversed RFP for Costa Sur site and when new detailed drawings will be published, need for full scaled drawings. Chris Mateo, Gino Sambolin, William Crespo, Lemuel Nieves, Reinaldo Romero, and Lemuel Nieves (Sargent & Lundy) Miguel Del Valle (Engr Mgr)
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 - Participated in BESS&PEAKERS 2025 RFP meeting. Items discussed was the current status of RFP for demolition at costa sur, the coordination of onsite activities when scheduling the contractor walk and review of scope for the demolition portion only. Jesus. Cintron Genera Franklyn Colmenares, CSA Group German Nunez, (Genera) Harry Del Valle and Gilberto Sucre (DCMC); Rafael Pabon, and Carlos Palomares (CDM Smith); Chris Mateo, and Lemuel Nieves (Sargent & Lundy)
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Weekly Project Meeting Design Progress Meeting Reviewed design status between Sargent & Lundy and Tesla. Other participants CDM Smith, CSA Group and DCMC Partners.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre DCMC Partners Project Team kickoff meeting with Jose Lopez, Luis Reyes, Luis Moctezuma. Review Design, Contractor Selection, Temporary Facilities, Construction Mobilization and Project Schedule Milestone Status Review.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Sr. Project Management Alignment Meeting between Abraham Velazquez for Peakers Program and Gilberto Sucre BESS Program
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja RFC Meeting with ARG Ceres. Update alignment meeting to review and evaluate remaining items to achieve Final Contract Award. CDM Smith, CSA Group, Sargent & Lundy, RGE and DCMC Partners Participation.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Duties transition coordination between Demolition Phase and Installation Phase from Jose Lopez to Eduardo Rivera from DCMC Partners.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting for team alignment on Procore tools that will be used in Cambalache. Discuss, roles, responsibilities, assignees, Managers, tools to be used. Lauren Wells, Andres Concepcion, Luis Damudt, Luis Duque, Luis Roman, Carlos De Jesus, Jose Lopez, Harry Del Valle, Eduardo Rivera, Jorge Mercado and Gilberto Sucre from DCMC Partners.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Follow-up meeting action items documented and distributed from the following referenced meeting with Joaquin Quinoy (Genera) to discuss the development of internal training programs focused on Lean tools, including Kaizen, 5Y analysis, PDCA cycle, WAIST categories, and Value Stream Mapping (VSM). Explored current knowledge gaps, training objectives, and potential rollout strategies.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Met with Joaquin Quinoy (Genera) to discuss the development of internal training programs focused on Lean tools, including Kaizen, 5Y analysis, PDCA cycle, WAIST categories, and Value Stream Mapping (VSM). Explored current knowledge gaps, training objectives, and potential rollout strategies.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence with Procore team for new SOW contract.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Power BI Reports review.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) resumed working on presentation for Procore kick-off call with Cambalache team
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Andres Concepcion, Luis Damudt, Luis Roman, Giblerto Sucre, Jose Lopez, Harry De Valle (DCMC) and others for a Procore kick off for the Cambalache team.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordinating meeting with Theresa Perez (DCMO) and Ivette Rios, Monica Ybarra (Sargent & Lundy).
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on presentation for Procore kick-off call with Cambalache team
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked presentation for Procore kick-off call with Cambalache team.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Pedro Alvalle (Maralen) about Vega Baja Genera project and training in Genera EHS. Start review of documentation about Vega Baja- next steps in the project. Review Vega Baja projects status in Procore.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Javier Almodovar by (ARG) about Vega Baja Genera project. Training in Genera EHS with DCMC Luis Moctezuma. Start review documentation about Vega Baja next steps for the project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Jose Lopez (DCMC) about the transfer diesel from Vega Baja to Palo Seco Genera Site. Review the Transfer Diesel Plan from Vega Baja to Palo Seco submit by Homeca.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Paul Browne (DCMC) to discuss status of the inventory management project and discuss needs for the warehouse.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting withn Raissa Borges (DCMC) to discuss PowerBI issue and access with Genera IT, and discuss data for the next monthly report.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya, Carlos Palomares (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Drafted a follow-up letter to PREPA regarding the ER1 Cost Share Program, informing them that FEMA has approved the second Request for Reimbursement (RFR) related to the BESS project. The letter was prepared to keep PREPA formally informed of the funding milestone and to support ongoing coordination efforts. Shared the draft with José Ralat and Esther Rohena (DCMC) for review and further action.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Prepared for the weekly BESS and Peakers catch-up call by reviewing and updating the project tracking spreadsheet. Incorporated feedback and updates received on 05/13 from the Genera procurement team, including changes to documentation status, and contractor communications. Ensured the tracker reflected accurate, real-time information to support productive discussion, alignment across teams, and timely follow-up during the coordination meeting.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Developed the full set of requisition documents for the 228MW BESS Installation RFP. This included drafting the justification memo, completing Attachment 4, filling out the requisition form, and formatting the Independent Cost Estimate (ICE) to ensure clarity and compliance with procurement standards. Coordinated with Jesús Cintrón to secure signatures on all required documents. Once finalized, uploaded the complete package to SharePoint to enable Franklyn Colmenares (CDM Smith) to initiate the formal requisition process.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Prepared a requirements gathering document in advance of a meeting with Sulinnette Pérez from Genera PR to ensure comprehensive information capture for the development of a sourcing integration Scope of Work. During the meeting, engaged in detailed discussions with Sulinnette Pérez to understand the functional and technical requirements needed to begin drafting the Scope of Work, aligning on initial priorities and integration objectives.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 |  | 184 | 598 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued the weekly FortiNAC configuration session with Mario Gomez and Michael Silva from Genera PR, focusing on enhancing secure connectivity to key internal platforms including Asset Suite, Oracle Fusion, and Genera Connect. Additionally, followed up with Michael Silva regarding the pending request to route network communications from Genera PR headquarters to the Genera Connect Azure environment, a necessary step to enable application access and ensure proper integration within the network infrastructure.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.75 |  | 184 | 506 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Began reviewing the latest fixes implemented in the Genera Connect Financial Tracker and Timesheets modules, as communicated by Keylamerari Sierra and Aldwin Pagan from Integrum, to validate issue resolution and system functionality. Also continued the weekly FortiNAC configuration session with Mario Gomez and Michael Silva from Genera PR, focusing on securing connectivity to critical internal applications including Asset Suite, Oracle Fusion, and Genera Connect.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 15 Homeca make cuts on the steel chimney to prepare for exhaust dismantled and last trip.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable11¦ DR 4339 - Hurricane Maria Using Procore to learn information at the project related to the Aguirre works zones, safety, construction and data entry
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Continue the training videos at Procore and learning documentation related at Aguirre Project provided by Jose Lopez (DCMC)
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria I take the training at Genera PR Occupational Health and Safety Induction was coordinated by Jean Pierre Menay (DCMC)
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Aguirre Kick off meeting organized by Gilberto Sucre DCMC in which they participated Jose Lopez, Luis Reyes (DCMC) to discuss project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT: Dismanteling and Demolition Activities field supervision and coordination. Meeting with Carirma Sanchez (HOMECA ) to discuss the weekend work schedule.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Vega Baja BESS project Teams Meeting with the PROCORE Specialist from DCMC, Lauren Wells, Luis Roman, and site managers Andres Concepcion, Gilberto Sucre, Jaime Pesquera, Harry Del Valle, and Eduardo Rivera. The standard operating procedures to be used with PROCORE at all BESS Sites were shown in the meeting. The discussion included RFIs, submittals, and general guidelines for the PROCORE platform to be used to standardize its use in all BESS sites.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre BESS, kick off meeting at City View Plaza, DCMC Offices, with the Aguirre Management Team Gilberto Sucre, Luis Moctezuma, and Luis Perez from DCMC. Gilberto Sucre (DCMC) explained the scope of work of the Aguirre BESS project and provides a summary of the team's responsibilities. Gilberto Sucre presents the project Summary and Site location, and discusses the project milestones and completion dates expected by Genera PR.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache BESS - 4339DR - Cambalache Procore Kickoff/Team alignment meeting to discuss the processes and tools to be applied in Procore platform to ensure construction management and administrative tasks are performed efficiently. Meeting with DCMC Partners - Lauren Wells, Luis Roman, Gilberto Sucre, Jorge Mercado, Luis Duque, Luis Damudt, Jose Lopez, Carlos de Jesus, Harry Del Valle.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Costa Sur BESS Projects. Looking for possibles discrepancies & measures to ensure efficient resource allocation and track contractor performance. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Meeting & Coordination for Central Costa Sur. Attendees, Miguel Beauchamp (Genera), Roberto Camacho (Genera) & Harry Del Valle (DCMC). Topics discussed, walk through BESS Project Site, discussed Office trailer location, Final Location of Existing Generator to be relocated, project needs. Measured areas.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Evaluation of document Revision 2.7 of the Megapack 2 XL Design and Installation Manual for safe installation and transportation according to Tesla manufacturer standards. Made a note corresponding to section ,6.2.1 Craning (RIGGING CONFIGURATION)
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Developing a safety plan in accordance with the contractor's manual, which describes the meeting points and emergency exit routes related to the Cambalache BESS project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- We attend a meeting scheduled by Andres Concepcion (DCMC) via the Teams platform for the purpose of using and managing the PROCORE platform for project management.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Evaluation of document Revision 2.7 of the Megapack 2 XL Design and Installation Manual for safe installation and transportation according to Tesla manufacturer standards.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Cambalache Procore Kickoff/Team alignment meeting to discuss the processes and tools to be applied in Procore platform to ensure construction management and administrative tasks are performed efficiently. Meeting with DCMC Partners - Lauren Wells, Luis Roman, Gilberto Sucre, Jorge Mercado, Luis Duque, Luis Damudt, Jose Lopez, Carlos de Jesus, Harry Del Valle.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Revised Procore RFI # 18 and modified assignees and information workflow to ensure contractor (RG Engineering) questions are addressed by the project designer Sargent & Lundy.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Monitored and reviewed Procore platform project correspondence and pending actions for follow up with designer Sargent & Lundy and contractor RG Engineering.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated Site Readiness requirements report for the Cambalache site pending items for Construction Start activities. The document will be distributed to Genera PR to ensure items are addressed.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Cambalache Procore RFI #19. Noted errors in the workflow and documented for follow up and corrections.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Completed coordination to organize a Cambalache DesignTechnical meeting for foundations and seismic considerations. Meeting is coordinated for Thursday May 15, 2025 with Sargent & Lundy, Morris-Shea, RG Engineering and DCMC Partners teams.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Procore kickoff meeting agenda and developed questions to cover the Cambalache team specific communication to be managed with contractor (RG Enginering - Jose Segarra).
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue reviewing the Mega Pack documents sent by Tesla in regard of Vega Baja BESS project, also reviewing before meeting the RFC document sent by Gilberto Sucre of DCMC related to second phase of BESS project for Vega Baja.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - The meeting was conducted by Gilberto Sucre of DCMC with Jose Lopez and Eduardo Rivera of DCMC - Meeting was to discuss project overview of Vega Baja demolition and for new project with ARG for the BESS installation.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 1 | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working at Vega Baja site reviewing project progress and field site visit. Two segment of the GT 1 stack has been removed. Gilberto Sucre of DCMC send a revised RFC of ARG/Ceres in regard of Vega Baja site.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS -Meeting with Gabriel Perez and Enrique Laya of CDM, Juan Perez of CERES, Gilberto Sucre of DCMC, and Wilfredo Sierra of S&L. Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS -Attended Procore Alignment Meeting with organizer Lauren Wells and Andres Concepcion of DCMC and participants Carlos De Jesus, Harry Del Valle, Jaime Pesquera, Jorge Mercado, Jose Lopez, Luis Damudt, Luis Duque, and Luis Roman of DCMC and Nelson Soler of CDM Smith. Meeting was to discuss the functionality of Procore for the BESS projects of Genera.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing email related to Vega Baja BESS project and preparing for meeting with Gilberto Sucre of DCMC in regard of Vega Baja BESS project turnover. Reviewing the Mega pack technical documents sent by Tesla.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing documents RFI related to BESS foundation Geopier Lateral Resistance Load, this information was sent by contractor Ida Ramirez of ARG/Ceres.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-provided support with inventory data verification and development of cycle count documentation in collaboration with Mr. Milton Flores of DCMC. We focused on preparing for daily operations such as validating locations, stock level confirmation, and coordination of material to enhance procedural efficiency and inventory management.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a recount at the San Juan warehouse in collaboration with Mr. Milton Flores from DCMC to validate inventory data. The objective was to confirm preliminary cycle count results, resolve identified discrepancies, and enhance the reliability and consistency of inventory records.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the San Juan warehouse, compiled and submitted a comprehensive inventory analysis report for Mr. Anthony Vega of Genera PR. The report consolidated data from all warehouse locations included catalog listing, item quantities, valuation summaries, discrepancy findings, threshold levels (min/max), and performance indicators to provide an accurate overview of each site. This review specifically focused on inventory locations GB 022 to GB 025, CR 200 to CR 269, AA01 019 to AA 01031, AG 008 to AG 014.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a variance analysis to identifying discrepancies and investigating inventory inconsistencies to enhance overall inventory control. The effort supported improved accuracy, enhance operational efficiency, and the implementation of timely corrective actions. The activity focused specially on inventory locations GB 022 to GB 025
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-facilitated an early morning meeting with Hernan Machado, Milton Flores and key DCMC warehouse staff to address operational discrepancies identified during the prior day. The session focused on implementing corrective actions and reinforcing proper data entry procedures to strengthen inventory control and improve overall reporting accuracy.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle counts for designated inventory areas, specifically locations GB 022 to GB 025. This effort is part of the ongoing initiative to align physical inventory with system records and ensure data integrity across operational process.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Complete Template for Aguirre Status Budget for leadership purpose.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Complete Template for Palo Seco Status Budget for leadership purpose.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Developed a standardized template for tracking project budget performance to support executive reporting and decision-making. The template consolidates key financial and operational metrics—such as obligated amounts, expenditures, and work progress. This tool enhances visibility for leadership, facilitates compliance monitoring, and ensures alignment with Public Assistance program expectations for financial oversight.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Construction Work Schedule send by RGE.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Practice with the PROCORE platform tutorial videos on the Daily Logs topic for the meeting "Cambalache" - Procore Alignment by Lauren Wells DCMC.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Write a list of questions and concerns about using PROCORE software tools and permissions for the meeting "Cambalache" - Procore Alignment by Lauren Wells DCMC
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting "Cambalache" - Procore Alignment by Lauren Wells, Andres Concepcion, Gilberto Sucre, Frances Vallejo, Jorge A. Mercado, Harry Del Valle, Carlos De Jesus, Luis Roman, Thereza Perez and Luis Duque from DCMC
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BESS. Supervising work of Homeca Recycling. Contractor keeps dismantling, decommissioning and demolition works and planning for phase II. Turbine 2 base and the crane started dismantling the exhaust stack for number 1 turbine.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BESS- Supervising work from contractor HOMECA. Contractor continued dismantling took out and carried away two huge exhaust stacks from turbine #2 in a long flatbed truck out of the site. Decommissioning and demolition work continued on turbine base #1 and scrap metal was cut out.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 15 Homeca make cuts on the steel chimney to prepare for rigging plan. Homeca truck driver Joseph Perez removed 12 filters from site towards Homeca Recycling Center.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review based on project development. Contract review and documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla Technical reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda, Carlos Palomares), Sargent & Lundy (Mike Kuczynski), and DCMC (Rafael Calderon, Gilberto Sucre)
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Pre-Intervention Compliance Review - Working with ENVIRONMENTAL HEALTH SAFETY SERVICES INC. Contract #103750_2024-G00512 and TO#7_Invoice# 11835_ Apr 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 164 | 410 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations AG008 to AG014 to start the cycle counts.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GB022 to GB025
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GB022 to GB025
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GB022 to GB025
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GB022 to GB025
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GB022 to GB025
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 019 000 to AA 01 031 000
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 019 000 to AA 01 031 000
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 019 000 to AA 01 031 000
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 666/676/672 localization CR 200 to CR 269
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location. CR 200 to CR 269
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day. We set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations CR 200 to CR 269 using Cycle Count List # 664/655/667/668/669/671/672/673/678/679/680
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations CR 200 to CR269 at the Aguirre warehouse to start the cycle counts.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #681 and 682 locations AG008 to AG014
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations AG008 to AG014 using Cycle Count List #670.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #681 and 682 for locations AG008 to AG014, totaling 124 pieces.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AG008 to AG014
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja BESS / Cambalache BESS/ Addl Management for Personnel for all Peakers Projects/ to help track changes and clearly communicate and implement any updates.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache BESS Procore Coordination for Module Setup & Access w Lauren Wells (DCMC)_Andres Concepcion (DCMC)_Luis Roman (DCMC)_Gilberto Sucre (DCMC)_Luis Reyes (DCMC) Continued Document Control - Data Management Cambalache BESS/Vega Baja BESS Addl Users Update
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Call with Carlos De Jesus (DCMC) to discuss the potential inclusion of new information columns at the Schedule Tool to maximize output efficiency.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with the Cambalache Power Plant Project Team. Hosted by Andres Concepcion (DCMC), the Designer (Sargent & Lundy w./ Ivette Miranda and Monica Ybarra) and Internal Team (DCMC with Gilberto Sucre, Luis Duque, Luis Damudt, Lauren Wells from Lemoine) discussed the implementation of Procore Platform and the correct procedures for the upcoming Construction Phase.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Resumed reviewing unpublished drawings at the Cambalache project in order to fix troubleshoot on multiple sheet drawings.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of unpublished drawings at the Cambalache project in order to fix troubleshoot on multiple sheet drawings. Creating Drawing Areas based on construction impact at project site.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of unpublished drawings at the Cambalache project in order to fix troubleshoot on multiple sheet drawings.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continued review of unpublished drawings at the Cambalache project in order to fix troubleshoot on multiple sheet drawings.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón (DCMC) to discuss Tesla important changes prior meeting with Jesús Cintrón (Genera). In this session we work on the Tesla schedule tracker and combine our data with Tesla, Sargent and Lundy, and Franklyn Colmenares (CDM) documents.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 |  | 149 | 521.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761 Contract documentation review to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reading and review in preparation for working session.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Send a reminder communication to community leaders and stakeholders of Aguirre and Jobos and provide them with the communication pieces to inform the Aguirre community that on Thursday, May 15, the Aguirre power plant will participate in a drill for a suspicious device.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create an email update to Jorge Bracero from the Genera team regarding the meeting with Sandra Miranda, the director of a care center in Toa Baja. The communication discusses what was addressed in the meeting, specifically the educational project, particularly the BESS and Peakers efforts.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue editing the BESS and Peakers Newsletter for Genera PR by integrating and editing information related to the first community meeting we had with the Cambalache community in Arecibo. This information includes meeting dates, important information about community participation, and what it means for the community in Arecibo. These tasks included searching for photos from the meeting to include, and aesthetic editing of the visual elements of the Newsletter.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Frances Vallejo from DCMC Partners about the status of Bess and Peakers project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create a document with the initiatives that we would be discussing next week with Sandra Miranda, the director of the childcare center in Toa Baja Choo Choo Train Day Care and Learning Center. These initiatives will be discussed on Monday with the Genera PR team, Jorge Bracero.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Prepare a Standby statement for the Genera PR Drill at the Aguirre Generating Complex, Salinas, in case any member of the community calls on the day of the event notifying any questions related to the drill. The Standby statement for the Genera PR Drill was sent to the Genera PR team Rafael Rodriguez Ema.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translating the Safety Manual from English to Spanish. Focused on reviewing translated sections for consistency, technical accuracy, and appropriate terminology. Worked on aligning the formatting and structure to reflect the original document, ensuring the final Spanish version adheres to quality standards and remains clear and accessible for Spanish-speaking personnel.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | Genera PR-Deliverable 11-Project Management-DR4339: I received an email from Nyah Medina (DCMC) requesting an update to an Excel spreadsheet related to the Verification of DCMC Employees' Work Schedule -Genera PMO. The update includes clock-in/out times and weekly work location. I began working on the update and, once completed, sent the revised table to Nyah Medina via email.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review Bess Elevation drawings for 4339_9510 BESS_Cambalache project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule of RFP setting P6 file and configuration in PROCORE for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on PROCORE alignment in scheduling PMO functions for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule of RFP review and inspection in PROCORE for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on teams meeting related to a PROCORE Alignment and PowerPoint presentation with important functions in PMO service with DCMC employees Andres Concepcion, Lauren Wells, Gilberto Sucre, Luis Roman, Luis Damudt, Luis Duque, Harry Del Valle, Jose Lopez, Jaime Pesquera, due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - attend meeting regarding new BESS Aguirre Genera Projects. Discussing duties, roles and responsibilities of every crew member. Project attendants Gilberto Sucre, Luis M. Reyes, Jose Lopez and Luis Moctezuma (DCMC)
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Revise project documentation (Milestone Schedule and RFP-4900_BESS_Aguirre_Schedule_Rev 1) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue with revising project documentation (Milestone Schedule and RFP-4900_BESS_Aguirre_Schedule_Rev 1) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Bess Elevation drawings for 4339_9510 BESS_Cambalache project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procore Alignment meeting with Andres Concepcion (DCMC) and Lauren Wells (DCMC) for 4339_9510 BESS_Cambalache project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue (PART 2) review Bess Elevation drawings for 4339_9510 BESS_Cambalache project.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Organizing and reviewing Peakers and BESS project updates to facilitate reporting.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. One on One meeting with Frances Vallejo (DCMC) to discuss projects reporting status and progress.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue compiling and organizing project status data on power bi for monthly report.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 122 | 183 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Compiling and organizing Peakers and BESS project status on power bi for monthly report.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 fuel for traveling to costa sur site and Yabucoa sites
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 5.32 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from home in Guaynabo to Central San Juan to meet with Mr. Milton Flores from DCMC. The purpose of the visit is to review the status of ongoing inventory control efforts, assist Mr. Flores during the schedule visit from Ms. Maria Sanchez from Genera PR.
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 134.4 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Claiming Mileage for this route, Travel from CPV Guaynabo to Costa Sur Power Plant (18.000463, -66.753480) to Home Office Luquillo. Purpose, Costa Sur Power Plant - Walk through BESS Project Site, discussed Office trailer location, Final Location of Existing Generator to be relocated, project needs. Measured areas. Attendees, Miguel Beauchamp (Genera), Roberto Camacho (Genera) & Harry Del Valle (DCMC). TOTAL MILEAGE 192 miles
2025-05-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.97 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled back home in Guaynabo from Central San Juan after meeting with Mr. Milton Flores from DCMC. Although the scheduled visit from Ms. Maria Sanchez of Genera PR did not take place; support was still provided to Mr. Flores in reviewing the status of ongoing inventory control efforts.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 worked on internal files, updating documents, house cleaning of desktop files and updating PROCORE uploading recent documents to minimize delays, reduces errors, and improves overall project efficiency.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in meetings Peakers schedule update and budget meeting. Discussed the updating of the project schedules for all project in general based on procurement. Budget review of all projects general discussion globally on procuring accurate numbers for budgetary purposes. Foster Veazey, Lauren Wells (Lemoine), Jean Pierre Menay, Sheila Torres-Sterling, Paul Browne, and Paola Arroyo (DCMC); Jesus Cintron and Francisco Feliu (Genera) Colmenares, Franklyn CSA Group.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 225 | 675 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Project Inspection of Demolition Phase to evaluate remaining activities, execution mode and durations in order to meet the project completion date of May 31, 2025. Participants Homeca Recycling, CDM Smith and DCMC Partners. After the inspection the DCMC Team met to start coordination for the Installation Phase to be executed by another Contractor.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Coordination Meeting with Jose Lopez DCMC in preparation for the Project Inspection in the afternoon and alignment procedure on the diesel transfer to Palo Seco.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peakers Weekly Project Schedule and Budget Review Meeting led by Carlos Palomares CDM Smith. Participants CDM Smith, CSA Group, Genera, and DCMC Partners.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Final Legal Review of Subcontract agreement with RG Engineering for the BESS execution with Francisco Feliu - Genera and Gabriel Perez CDM Smith.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore - DCMC Financials Tools - Direct Cost/Funding. Alignment Meeting for use of this model across the Program. Attendees Lauren Wells, Glorimel Torrado, Rafael Calderon, Gilberto Sucre, Esther Rohena - DCMC Partners, Lauren Kennedy and Elizabeth Fronduto - Procore,
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Reviewed BESS - Site Readiness Plan prepared by Andres Concepcion DCMC Partners.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Evaluated Execution Alternatives for the next demolition phase from project continuity and commercial aspect if awarding to current contractor vs. the Installation Phase with ARG Ceres.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja DCMC Safety Meeting - Gilberto Sucre (DCMC) met with Mark Merritt (DCMC) to discuss events leading to the work stoppage on site after the two near misses on Friday Morning, and the response from CDM Smith and Genera to renew work.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja RFC Meeting ARG Ceres / Vega Baja Site continuation meeting with Carlos Hernandez - ARG, Sargent & Lundy, CDM Smith, CSA Group to review remaining action items to finalize the contract award for the installation phase of the project.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Meeting with DCMC and Procore teams to discuss the integration of financial tools and how the modules should be established. Attendees were Foster Veazey, Lauren Wells (Lemoine) and Gilberto Sucre (DCMC).
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - BESS / Peaker's Schedule and budget meeting. Attendees were Gabriel Perez, and Jesus Cintron (Genera) Foster Veazey (Lemoine), Gilberto Sucre, Abraham Velazquez (DCMC),
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued worked on Financial correspondence for Change orders for suppliers form.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Seimens Change Order forms for Procore.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Daily Log types for Cambalache.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) to discuss Procore items, document control and other items.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing financial spreadsheet from Rafael Calderon (DCMC).
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating mock-up of 10710 and 9510 file structure in Procore to send to group from earlier meeting.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with D'Alexander Gonzalez, Pedro Cabrera, Rafael Calderon (DCMC), and Johanna Diaz, Shellsea Maysonet (SM Consulting) to discuss committed cost.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for sending Procore certification information to DCMC team.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) call with Andres Concepcion (DCMC) and Luis Roman (DCMC) to discuss RFI status and moving forward with Overdue items.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial structure.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Financial correspondence for Change orders for suppliers form.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon, Gilberto Sucre, Esther Rohena, Glorimel Torrado (DCMC), Ginnell Torres (Integrum) and others to discuss Procore direct cost and Funding.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the Procore action about day job in all Genera Site. Discuss with Jose Lopez (DCMC) and Gilberto Sucre (DCMC) Vega Baja Diesel Task.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting in Arecibo "Junta Regional de Respuesta a Emergencias del Norte". This is an Emergency Response Teams in North side of the Island with Carmen Fuster Ramos, "Department of Natural Resources", Yadira Caban (Thermo King), Osvaldo de Jesus (GENERA), Alberto Maysonet (AVARA) about Emergency Plan in North Side.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Juan Carlos Santos director Zone North Emergency Management Agency and Osvaldo de Jesus EHS Supervisor about Cambalache start jobs.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers schedule and budget meeting. Participants: Carlos Palomares (CDM), Gilberto Sucre (DCMC), Gabriel Perez (CDM)
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting to discuss committed cost tracking in regards to the contracts and grant management for the BESS and Peaker project. also discuss the monthly report and align on the financial data. Participants: D Alexander Gonzalez (DCMC), Rafael Calderon, Raissa Borges, Jose Ralat (DCMC)
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Jesus Cintron (Genera) to discuss staffing update and Vega Baja incident.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Attended the meeting with the emergency local committee at Cambalache plant in Arecibo. The meeting was with pharmaceutical organization to discuss emergency drill in regard to the project. Participants: Paola Arroyo (DCMC), Jean Pierre Menay (DCMC)
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4899 Civil and Structural Works for 30MW BESS at Costa Sur – Reviewed the Award Memo. Then, proceeded to review individual scores submitted by all four voting members of the evaluation committee. Calculated the average scores and applied the appropriate weighting based on the established evaluation criteria. Updated the evaluation memorandum to reflect the final scoring results and ensure alignment with the procurement process and documentation standards.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Addressed a network configuration issue identified by Mario Gomez from Genera PR, involving conflicting address spaces between the Genera Connect Azure environment and internally reserved ranges. Began analyzing the scope and size of the existing address space to develop a recommendation for reorganization, aiming to resolve conflicts and ensure seamless network connectivity and integration across environments.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Transitions the virtual machines and database instances for the Genera Connect Financial Tracker and Timesheets applications to a newly defined address space, addressing the network conflict identified by Mario Gomez from Genera PR. Additionally, collaborated with Mario Gomez to review and validate the routing configuration from Genera PR headquarters to the Genera Connect Azure environment, ensuring proper connectivity and access to the applications following the address space reconfiguration.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed documentation provided by Sulinnette Perez from Genera PR outlining current procurement processes, as part of the initial analysis for developing a sourcing integration Scope of Work. Additionally, coordinated with Mario Gomez from Genera PR to plan and oversee the deployment of the Genera Connect Financial Tracker and Genera Connect Timesheets, ensuring alignment with technical requirements and deployment timelines.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 16 Homeca make cuts on the steel chimney to prepare for rigging plan. Vieques Enviro inc. to drain Oily water separator Day 2
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS PROJECT - Continued Vega Baja Bess Project contract and Specs. An overview to ensure all project participants clearly understand the expectations and requirements, and their participation in the project’s execution.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS project, participate in a walk-through of the Vega Baja Site with Gilberto Sucre, Gilberto Soto, Jaime Pesquera, Eduardo Rivera (DCMC staff), and Nelson Soler, Enrique Laya, Gabriel Perez (CDM Smith), to go over the progress performance and percent of completion of Homeca Recycling represented by Eduardo Ramos. The completion activities done as of today were discussed to decide on the time extension requested by HOMECA Recycling as granted by Genera PR in a previous meeting.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | -Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting on the Vega Baja BESS site with the DCMC Team, Jaime Pesquera, Eduardo Rivera, to review Homeca's scope of work performance and discuss the recovery plan to avoid delays of the project critical path.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS - Contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting on the Vega Baja BESS site with the Demolition subcontractor, Carirma Sanchez, with Homeca Recycling to discuss the actions required for other daily activities.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Conducted review of drawings, schedules, and scopes of work for BESS Projects at Costa Sur and Aguirre through Procore. Focused on identifying possible inconsistencies and logistical gaps. Requested pricing for supplies, water service, and necessary equipment for the field office trailers.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing drawings, verify Scope of Work to ensure it outlines the specific tasks, responsibilities, and deliverables required for the successful completion of the project, Scheduling & Contract Documents for the Costa Sur BESS Projects. Looking for possibles discrepancies & measures. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Evaluation of document Revision 2.7 of the Megapack 2 XL Design and Installation Manual for safe installation and transportation according to Tesla manufacturer standards. A note corresponding to section 4.1.5, Consideration of the ground surface, is included.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Continued developing the contractor's safety plan to design training for confine space control and process related to the BESS Cambalache project. Training is essential to equip workers with the knowledge and skills they need to stay safe.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Evaluation of document Revision 2.7 of the Megapack 2 XL Design and Installation Manual for safe installation and transportation according to Tesla manufacturer standards. Made a note corresponding to 3.6 Safety Certification and Hazard Mitigation
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Developing the contractor's safety plan to design training for confine space control and process related to the BESS Cambalache project. Training is essential for ensuring the safety and preparedness of employees.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meetings and Phone Call with RG Engineering (contractor) Project Manager Jose Segarra for the discussion of project General Conditions and logistics.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Attended meeting to discuss design technical details for the seismic and geotechnical considerations. Sargent & Lundy (Robert Molner) Morris Shea (Bill Shea), RG Engineering (Jose Segarra).
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Lauren Wells and Luis Roman (DCMC) to solve a Procore RFI (RFI #19) issue. Move forward to do corrections in Procore platform.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed TESLA Design, Operation and Transportation manuals shared by Franklyn Colmenares (CDM Smith) for the application and management of the TESLA scope of work in the project.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Distributed and shared project information to Cambalache team (Luis Damudt, Carlos de Jesus, Jorge Mercado, Luis Duque) regarding Submittal Management and TESLA Megapacks Design Manuals.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Procore Drawings tool publish issues to coordinate a meeting with Luis Roman (DCMC) and Vincent Skochdopole ( Sargent & Lundy) correct drawings numbering.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Completed Cambalache site readiness report to guide Genera PR to solve action items prior construction start. Distributed information to Gilberto Sucre (DCMC) for review.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Drafted and generated an Procore SOP (procedure) that will applied in the project with the contractor (RG Engineering).
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Meeting with Gabriel Perez and Enrique Laya of CDM, Carlos Rodriguez of ARG, Jose Lopez, Gilberto Sucre and Eduardo Rivera of DCMC, and Wilfredo Sierra, Gary Jasutis, Margolis Jordan, Robert Molner, and Vicent Skochdpole of S&L. Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing RFI and contract RFP of ARG for Vega Baja BESS project, perform walkdown at VB site to view project progress work at GT stack 2.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue reviewing ARG project management plan to understand the contractor key players and also revieing the contract RFP in regard of ARF/CERES contractor.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - Field walkdown at Vega Baja Site with Gilberto Sucre, Jose Lopez, Jaime Pesquera, Gilberto Soto and Eduardo Rivera of DCMC, Eduardo Ramos of Homeca, Nelson Soler, Enrique Laya, Gabriel Perz and Manuely Concepcion of CDM. Meeting to review all pending work asóciate to the demolition of the GT of Vega Baja.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Homeca contractor on the removal of tow segment of GT #2 stack to a platform with a Crane.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting - CPM Jose Prado, Luis Tapia, Carlos Castro, Diana Rivera and Victor Alvarez; DCMC Pedro Cabrera and Eduardo Rivera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, Sarting Frecuency Transformer of Cambalache, DCS and PI DAS system of Mayaguez and request information of FDF and IDF of Costa Sur and reviewing the deliverables for SOW & CE.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working in Vega Baja BESS project. Continue turnover transition with Jose Lopez of DCMC in regard of Vega Baja project. Brainstorm to review all pending item by contractor Homeca in regard of demolition works.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing ARG project management plan to understand the contractor key players and also revieing the contract RFP regard of ARF/CERES contractor, this contract has not yet been signed by ARG but is under negotiation with GENERA. HOMECA continue the demolition of GT #2 still a lot of demolition work pending to be completed by this contractor.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-assisted with the preparation of cycle count sheets to support scheduled inventory activities at the Costa Sur warehouse, in coordination with Mr. Hernan Machado from DCMC. Task included validating item locations, verifying stock accuracy and organizing materials to ensure a structured and efficient inventory process.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-perfromed cycle counts for the designated inventory locations scheduled for the day, specifically covering AA 01 032 to AA 01 040. This effort was part of ongoing initiatives to improve inventory accuracy and ensure alignment between physical stock and system records.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a job briefing with Juan Vallejo, Giovanni Taffanelli and key DCMC warehouse staff to review current inventory challenges and implement corrective actions. The focus of the session was on identifying bottlenecks, improving data accuracy, and reinforcing inventory management procedures.. This session emphasized enhancing coordination and strengthening accountability.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while stationed at the Costa Sur warehouse, compiled and submitted a detailed inventory report to Mr. Anthony Vega of Genera PR, incorporating data from all warehouse locations. The report included a strategic summary of catalog records, unit counts, cost assessment, noted discrepancies, and stock level thresholds (max/min). It also highlighted key performance indicators to reflect the current inventory status. Review locations spanned from AA 01 032 to AA 01 040, AA 020 to AA 145, AG 015 to AG 024, GC 001 to GC 006.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC to verify inventory accuracy. This effort focused on validating previous counts, resolving discrepancies, and ensuring the consistency and reliability of inventory records.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed variance analysis by identifying discrepancies and evaluating inventory inconsistencies to strengthen control measure. This initiative focused on enhancing data accuracy, improving operational efficiency, and enabling timely corrective actions.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the weekly meeting with CPM, I focused on reviewing Critical Components priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Template for Power Plant Status Budget to determine if adjustments are necessary.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Eduardo Rivera, and Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Prepare a report of NME Projects Included in Federal Projects for Regulatory purpose.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Committed Cost- Tracking- With participation from DCMC: DAlexzander Gónzalez, Jose Ralat, Rafael Calderon, Pedro Cabrera, Sheila Torres, and Glorimel Torrado to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue Complete Template for Aguirre Status Budget for leadership purpose.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Prepare agenda for meeting of overall status of Critical Components with GENERA PROCUREMENT.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop agenda for Procurement Meeting of Critical Components with, DCMC & GENERA.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, TESLA Manuals Megapack 2 XL Design and Installation Manual 8 Installing Megapack send by Andres Concepcion from DCMC.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, TESLA Manuals Megapack 2 XL Design and Installation Manual Topic 1 Megapack System Overview send by Andres Concepcion from DCMC.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Discussion Meeting and comments via DCMC Teams chat with Carlos De Jesus, Andres Concepcion, and Jorge Alexis Mercado on the topics of 4.1.5 Ground Surface Design Consideration, 4.5.1.1 Foundation Installation Requirements, 4.2.1.2.1. Additional Consideration for Concrete
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, TESLA Manuals Megapack 2 XL Design and Installation Manual Topic 6 Transporting Megapack send by Andres Concepcion from DCMC.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS S & Cambalache BESS- S&L/MRCE/MS - Technical Meeting to discuss technical details regarding Cambalache BESS foundation design with Gilberto Sucre, Andres Concepcion, Luis O. Damudt, Jorge A. Mercado, Carlos De Jesus, Luis Duque DCMC, Alberto Borelli, Jose Segarra, Angel Cruz, Harry Velazquez from RGE, Angel J. Alicea Rodriguez, David E. Nielson Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BESS Supervising work from contractor Homeca Recycling. Contractor keeps dismantling, Decommissioning and demolition works and planning for phase II to ensure environmental protection, regulatory compliance, and worker safety.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Project Meeting walk through site with Emanuel Ramos from Homeca, Gilberto Sucre DCMC, Jaime Pesquera (DCMC Partners) & Noel Soler (CDM Smith), Jose L Linares DCMC, Emmanueli Concepcion (CDM Smith), Gabriel Perez (CDM Smith),Enrique Laya (CDM Smith) .took notes, minutes built, revised, and distributed to Gilberto Sucre, Jaime Pesquera (DCMC Partners), Noel Soler (CDM Smith), Eduardo Rivera (DCMC). We discussed the punch items list with the expected new completion date.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Supervising contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project essential for maintaining a healthy environment, complying with regulations, and promoting sustainability.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 16 Homeca make cuts on the steel chimney to prepare for exhaust dismantled and last trip. Meeting with DCMC Gilberto Sucre for walk through.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Internal DCMC meeting with D' Alexzander González, Frances Vallejo, Raissa Borges, José Ralat, Rafael Calderón, Glorimel Torrado, Pedro Cabrera; from Lemoine Lauren Wells, and Subcontractors Shellsea Maysonet and Johanna Díaz (SMC). In this meeting we discussed the reconciliation of the PW 9510 between plants and projects, to be provided to Genera PMO as part of the federal funds' reports for each power plant, and as part of the reconciliation process with the child projects being obligated by FEMA for the BESS, Peakers and Critical Components projects.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #90234612 for TO#1 Apr 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Meeting participants TESLA (Michael Grabstein, Jorge Quintana), CSA (Franklyn Colmenares), CMD Smith PM team (Gabriel Sepulveda), Genera (Jesus Cintron), Sargent & Lundy (Mike Kuczynsky, Vincent Skochdopole), and DCMC (Rafael Calderon)
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Contract Management Meeting- Procore - DCMC Financials Tools. Reviewing Change Orders procedures and Pro-Core functionalities to manage changes on projects contract and process of submittals and acceptance of the changes. DCMC/ Lemoine Participants (Rafael Calderon, Glorimel Torrado, Gilberto Sucre, Foster Veazey, Lauren Wells, Lauren Kennedy and Tyler Scanlan)
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens / Genera Peakers biweekly meeting with project management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Reviewing status of project execution including upcoming Change Orders and Logistic in preparation for the Delivery Dates. Meeting between Siemens Energy team , CMD Smith PM team (Rafael Pabon, Carlos Palomares), Sargent & Lundy (Miguel del Valle, Mateo Agosto and Gino Sambolin) Genera (German Nunez), and DCMC (Rafael Calderon).
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #701 locations AG015 to AG024.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GC001 to GC006
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GC001 to GC006
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GC001 to GC006
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GC001 to GC006
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GC001 to GC006
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 |  | 152 | 418 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 032 000 to AA 01 040 000
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 032 000 to AA 01 040 000
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 032 000 to AA 01 040 000
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 691/700/702 locations AA 020 to AA 145 and DM 010
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 684/686/687/688/697/698/699ocations AA 020 to AA 145 and DM 010
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AA 020 to AA 145 and DM 010 at the Aguirre warehouse to start the cycle counts.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AA 020 to AA 145 and DM 010.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations AG015 to AG024 to start the cycle counts.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations AG015 to AG024 using Cycle Count List #696 and 703.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #701 for locations AG015 to AG024, totaling 192 pieces.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AG015 to AG024.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja BESS/Costa Sur Peakers/ Cambalache BESS to improve safety, efficiency, and project management skills.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Document Control -Data Management /Vega Baja BESS Coordination of Procore Submittal Data with Lauren Wells DCMC)/Luis Roman (DCMC)/Costa Sur Peakers Procore RFP Data Management/Environmental Data/SOPs Data for all Projects
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 151 | 37.75 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams call with Lauren Wells (Lemoine) and Andres Concepcion (DCMC) to discuss the reopening of RFI's after contractor addresses responses; RFI 19 was created to bring some information missing from RFI 17 responses.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Worked on unpublished drawings from Cambalache Power Plant to discuss with Design Team about issues on drawing numbers for multiple sheets drawings.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Schedule tool with Carlos De Jesus (DCMC) at the Procore Platform to discuss potential tasks to relate Schedule tool with Financials Module: Progress Completion Certification by Contractor, Workforce Management, and others.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Implementation of Project Management strategies to maximize efficiency on the Procore tools; RFI and Submittals proper workflows, drawings commentaries and revision phase, and document control for information outside the Procore platform (traditional emails).
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Documents Tool to identify potential missing information regarding Safety Documents and Submissions: documents sent via traditional email to be stored at Procore.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 |  | 151 | 113.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review contractual documents to implement response timing on the Procore Tool: Submittals and RFI's; review contractual agreements for uniform general conditions.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Tesla change order meeting with Gabriel Sepúlveda and Franklyn Colmenares (CDM), Rafael Calderón and Glorimel Torrado from DCMC and Jesús Cintrón from Genera. During this meeting the team present to Genera the change order and the items that should be discussed with Tesla in order to complete the formal request.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Internal DCMC meeting with D' Alexzander González, Frances Vallejo, Raissa Borges, José Ralat, Rafael Calderón, Glorimel Torrado, Pedro Cabrera; from Lemoine Lauren Wells, and Subcontractors Shellsea Maysonet and Johanna Díaz (SMC). In this meeting we discussed the reconciliation of the PW 9510 between plants and projects, to be provided to Genera PMO as part of the federal funds reports for each power plant, and as part of the reconciliation process with the child projects being obligated by FEMA for the BESS, Peakers and Critical Components projects.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Financial Meeting with Lauren Kennedy (Procore), Esther Rohena (DCMC), Lauren Wells (Lemoine), Rafael Calderón (DCMC) and Gilberto Sucre (DCMC). In this meeting we discuss the implementation of Procore reviewing financial aspects of the projects.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review final package for pw#9510 Pre Intervention Review for Sargent & Lundy Puerto Rico, LLC., Contract #102184_2024-G00200, TO#6,18334035_Jan2025. Prepare final package and request CPA. This invoice is pending for amendment to complete disbursement. Also, send CDM_TO6_90225264 labor notes to José Ralat (DCMC) and review a list from Black and Veatch invoices.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Create a detailed document about the 'next steps' we will take as part of our participation in the Local Committee meeting for Environmental Emergency Response Planning of the Arecibo District at the facilities of AIAC International Pharma LLC (AVARA Pharmaceutical Services) located at PR 2 Bo. Sabana Hoyos in Arecibo.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Follow-up with the Genera PR team, Rafael Rodriguez Ema, to confirm that he received the Standby statement for the Genera PR Drill at the Aguirre Generating Complex, Salinas.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria As part of my work with the community, I participated in the ordinary annual meeting of the Local Committee for Environmental Emergency Response Planning of the Arecibo District at the facilities of AIAC International Pharma LLC (AVARA Pharmaceutical Services) located at PR 2 Bo. Sabana Hoyos in Arecibo. These tasks included completing the registration process to enter the meeting. The meetings are aimed at organizations, entities, industries, agencies, and community members interested in learning and planning for incidents related to hazardous materials. In the meeting participated the team from DCMC Partners, Jean Pierre Menay. Team from the Department of Natural and Environmental Resources (DRNA): Carmen L. Fuster Ramos and Vanessa Suárez López. Team from Genera PR: Roseanne Pérez Ruiz, Osvaldo De Jesus Olan, and Miguel A. Ortiz. Team from IAC International Pharma (AVARA), Adalberto Maysonet.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continued translating the Safety Manual from English to Spanish. Focused on reviewing for consistency, technical accuracy, and correct use of terminology. Also worked on aligning the formatting and structure with the original document to ensure that the final Spanish version meets quality standards and remains clear and accessible for Spanish-speaking personnel. Completed the translation and formatting of Chapter 6.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 134 | 469 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review Warehouse new parking area erosion control plan for 4339_9510 BESS_Cambalache project.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule information in Tesla guides for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on Teams meetings BESS&Peakers Weekly Schedule Meeting with CD Smith employee Carlos Palomares and Manuely Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on information of contract procurement, notice to proceed, designer pending, RFP schedule and summary dates report for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule information considering construction Tesla specifications for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue with revising project documentation (RFP 229760- Genera PR RFP 4900 Civil and Structure Works for 158 MW Battery Energy Storage System at Aguirre) BESS Genera Aguirre projects to track process and coordination with the team, identify risks, and ensure accountability.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin with revising project documentation (RFP 229760- Genera PR RFP 4900 Civil and Structure Works for 158 MW Battery Energy Storage System at Aguirre) BESS Genera Aguirre projects to track process and coordination with the team, identify risks, and ensure accountability.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache-BESS Technical Meeting meeting with Andres Concepcion (DCMC) and Angel Cruz (RG Engineering and Jesse Richins (MRCE) for the 4339_9510 BESS_Cambalache project.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Warehouse new parking area erosion control plan for 4339_9510 BESS_Cambalache project.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 122 | 396.5 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Managing project tracker and developing project progress dashboard on Power BI platform for May 2025 report to improve visibility of project progress, milestones achieved, and potential roadblocks.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Oversaw updates to the project tracker and worked on building a Power BI dashboard to visualize project progress for the May 2025 reporting period. Focused on integrating current data to reflect key milestones, task status, and performance indicators.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez, Gilberto Sucre, Frances Vallejo; and CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.25 |  | 122 | 152.5 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Managing project tracker and developing project progress dashboard on Power BI platform for May 2025 report.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Genera PR ¦ Deliverable 11 ¦ DR4339 - Internal DCMC meeting with D' Alexzander González, Frances Vallejo, Raissa Borges, José Ralat, Rafael Calderón, Glorimel Torrado, Pedro Cabrera; from Lemoine Lauren Wells, and Subcontractors Shellsea Maysonet and Johanna Díaz (SMC). In this meeting we discussed the reconciliation of the PW 9510 between plants and projects, to be provided to Genera PMO as part of the federal fund's reports for each power plant, and as part of the reconciliation process with the child projects being obligated by FEMA for the BESS, Peakers and Critical Components projects.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 74.2 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for project inspection from home offices San Juan to Cambalache and Vega Baja Genera Site (18.47 Purpose Genera PR - Metting with Osvaldo de Jesus, (GENERA), Junta Respuesta Emergencia and Emergency Managment North Zone in Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they me Total Distance 106 miles
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.37 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - After completing inventory support activities at the Costa Sur warehouse in collaboration with Mr. Hernan Machado from DCMC, returned home to Guaynabo. The visit was part of a broader initiative to oversee inventory process, address system discrepancies, and reinforce best practices in stock control. Observation gathered during the visit will contribute to future improvement plans and reporting accuracy.
2025-05-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.3 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -traveled directly from home in Guaynabo to Costa Sur to support Mr. Hernan Machado from DCMC. The purpose of the visit is to assist in the verification of physical inventory counts and ensure data accuracy within the system. Collaborate with Mr. Hernan and local staff to align on procedures and validate ongoing inventory task.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of weeks meetings, agendas and schedules. Reviewed agendas for next weeks meetings and coordinated site walk through with contractors
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Peakers update weekly meeting. Reviewed past weeks deliverables, status on RFP responses, reviewed revised site plan for Costa Sur demolition phase of project. German Nunez, GENERA Harry Del Valle DCMC Gilberto Sucre DCMC Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Frances Vallejo DCMC
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 225 | 562.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordination of next weekend and next weeks' activities at Vega Baja: Transit closure of marginal street to allow truck entrance/exit for the turbo compressor transfer to Central San Juan and Diesel transfer during the entire week. Emergency power works and Luma Coordination. Verification of RFC responses to ARG Ceres required to finalized contract. Kick-off meeting agenda verification. Coordination of BESS and Peakers shared staff roles & responsibilities.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria The PMO Team Catch Up meeting focused on key topics including staffing, overtime policy, and project management updates. The team discussed the upcoming onboarding of new staff and the alignment between BESS and Peakers teams at Costa Sur, while plans for filling essential roles like the construction monitor remained ongoing. Resource planning efforts included updates on the Procore proposal and the near-completion status of the safety plan for Cambalache. Participants Mike Merritt, Frances Vallejo, Anneilia Holton, Jack Darnall, Barry Scanlon, Lauren Wells and Gilberto Sucre (Lemoine/ DCMC).
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Bids submission evaluations from HOMECA Phase I and ARG Ceres Phase II. Reviewed scope and pricing from both contractors in order to provide a recommendation to expedite the schedule and cost of the demolition phase upcoming.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting ARG Ceres - Vega Baja continued discussing remaining RFC responses and needs from Genera and ARG Ceres parties in order to achieve executed Contract to move on to the Site. Participants Genera, Sargent & Lundy, CDM Smith, CSA Group, ARG Ceres and DCMC Partners. Next meeting will be on Tuesday at 1 pm.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Management Project Weekly Meeting - reviewed, schedule delay change-order sample letter, project schedules and contractual values. Genera, Sargent & Lundy, CDM Smith, CSA Group, and DCMC Partners.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja evaluation remaining award of the site demolition activities to the current contractor and exclude from the Installation Phase, considering project continuity, advancing schedule and cost savings.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence review and evaluation of all e-mails related to the BESS program.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Peakers project management update meeting. Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Theresa Perez (DCMC) and Monica Ybarra and Ivette Rios with Sargent and Lundy to discuss Procore documents and the process.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up meetings for Procore items next week.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked Procore permissions for directory access.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing upcoming tasks items to prepare for Procore meeting with Franklyn Colmenares (CSA), Luis Roman (DCMC) and others.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reports.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on progress report for Mark Merritt (DCMC) to present to Jesus Cintron (Genera).
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP's for submittals before Luis Roman (DCMC) sends out for review.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial budget view information for 10710.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing invite list for Procore weekly Q&A sessions.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Frances Vallejo, Jack Darnall, Lauren Wells, Gilberto Sucre, Barry Scanlon, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 214.08 | 214.08 | 214.08 | Yes |  |  | Prepa Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 Hurricane Maria Puchase of Personal Protective Equipment (PPE) at the Tomcas store in Caguas, Puerto Rico. High electrical hazard safety boots, safety helmet, chin strap with chin guard, safety glasses and safety hand gloves.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: On-site inspection of EHS topics at the Vega¿Baja Genera site. Training in Genera EHS presentation to Jesus Gonzalez, Fernando Maldonado, Jose Davila, Abner Romero by Advance Diesel company in charge to move the diesel from Vega Baja to Palo Seco.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: On-site inspection of EHS topics at the Vega¿Baja Genera site. Meeting with Commissioner Ramos by Vega Baja City Police and Osvaldo de Jesus (GENERA) about the diesel transfer activity May 19 2025 from Vega Baja to Palo Seco Genera Site.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss BESS and Peaker projects update. We discussed trailer coordination between sites, staffing update, Procore trainings, and other logistics. Participants: Mark Merritt, Gilberto Sucre, Anneilia Holton (DCMC) and Jack Darnall (Lemoine)
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting regarding Peakers Management Plan to discuss tasks, schedule and need for the Peaker project. Participants: German Nunez (Genera), Carlos Palomares (CDM), Rafael Pabon (CDM) and Abraham Velazquez (DCMC).
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting with Rafael Calderon and Sheila Torres (DCMC) to discuss contract management update for Tesla and Siemens contracts and discuss RFP status.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting to discuss Community engagement reporting to integrate the information in the monthly dashboard report. Participants: Raissa Borges and Paola Arroyo (DCMC).
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4826 52 MW Battery Energy Storage System Installation at Cambalache – Reviewed the Award Memo. Then, proceeded to review individual scores submitted by all four voting members of the evaluation committee. Calculated the average scores and applied the appropriate weighting based on the established evaluation criteria. Updated the evaluation memorandum to reflect the final scoring results and ensure alignment with the procurement process and documentation standards.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4898 49 MW Battery Energy Storage System Installation at Vega Baja – Reviewed the RFI submitted by ARG regarding the Buy American Act. Drafted a formal response addressing the inquiry and shared it with Ricardo Palléns, Jesús Cintrón (Genera), and the Sargent & Lundy team.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4898 49 MW Battery Energy Storage System Installation at Vega Baja – Reviewed the Award Memo. Then, proceeded to review individual scores submitted by all four voting members of the evaluation committee. Calculated the average scores and applied the appropriate weighting based on the established evaluation criteria. Updated the evaluation memorandum to reflect the final scoring results and ensure alignment with the procurement process and documentation standards.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 17 Homeca make cuts on the steel chimney to prepare for rigging plan. Electrical Company installing temporary line for distribution on site.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja BESS job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform.Hurricane Maria. MST met with Gilberto Sucre (DCMC), Eduardo Rivera(DCMC), and Jaime Pesquera (DCMC) to discuss the current project Phase situation with the Demo Contractor.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja BESS job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT. I had several phone calls with the GWC (HOMECA) project manager, Carirma Sanchez, and the company administrator, Eduardo Ramos, to discuss the project contract requirements and contract progress.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Costa Sur & Central Aguirre BESS Projects. Looking for possibles discrepancies & measures. Quoting materials, potable water services & Printers for sites Office Trailer.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on Procore, reviewing drawings, Scope of Work, Scheduling & Contract Documents for the Costa Sur & Central Aguirre BESS Projects. Looking for possibles discrepancies & measures. Quoting materials, potable water services & Printers for sites Office Trailer. Define Office trailer location for Central Aguirre BESS Project.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Developing the contractor's safety plan to design training for work at heights related to the BESS Cambalache project. Training is essential to equip workers with the knowledge and skills needed to work safely at heights, resulting in a decrease in the number of accidents and injuries on the job.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued with the evaluation of the Megapack 2 XL Design and Installation Manual Revision 2.7 document for safe installation and transport according to the Tesla manufacturer. Some important notes related to the conditions of the Cambalache site will be considered.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the Megapack 2 XL Design and Installation Manual Revision 2.7 document for safe installation and transport according to the Tesla manufacturer. Some important notes related to the conditions of the Cambalache site will be considered.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Developing the contractor's safety plan to design training for daily job permits related to the BESS Cambalache project to control high-risk activities.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued review of project Technical Specifications to identify required submittals and be able to monitor contractor's (RG Engineering) submittal schedule or log when construction starts.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated a meeting to solve Procore Drawing issues with Luis Roman (DCMC Partners), Ivette Miranda and Monica Ybarra (Sargent and Lundy) for Monday 19, 2025.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project technical specifications document to identify scope of work for project General Conditions and perform a mobilization plan.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project Technical Specifications to identify required submittals and be able to monitor contractor's (RG Engineering) submittal schedule or log when construction starts.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and commented Cambalache project master schedule May 15, 2025 update. Received by Carlos Palomares (CDM Smith).
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with contractor for work activity related to Vega Baja BESS project. Contractor Homeca continues with demolition of structure at GT-2 and also working with demotion of GT-1. Field walkdown to review project condition and everything was in order. Homeca bring their electrical team JN Electrical to install new temporary for guard house and install new metering panel with an exterior power panel.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with contractor work activity related to Vega Baja BESS project. Contractor Homeca continues with demolition of structure at GT-2 and also working with demotion of GT-1. Field walkdown to review project condition and everything was in order.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with Homeca construction on site, contractor continue working demolition of GT-2 stack frame. Electrical contractor continues working with the temporary panel and pull-out installation. Working with kick off meeting agenda for Vega Baja BESS second phase, the contractor will be ARG/CERES for this project.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Meeting with Gabriel Perez and Enrique Laya of CDM, Carlos Rodriguez of ARG, Jose Lopez, Gilberto Sucre and Eduardo Rivera of DCMC, and Wilfredo Sierra, Gary Jasutis, Margolis Jordan, Robert Molner, and Vicent Skochdpole of S&L. Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Aguirre warehouse, a consolidated inventory report was developed for Mr. Anthony Vega of Genera PR. integrating data from all warehouse's locations. The report compiled catalog items counts, unit quantities, cost breakdown, and variance findings. It also included stock thresholds assessment and percentage-based metrics to illustrate the operational performance of each site. The inventory locations reviewed range from AB 001 to AB 072, AG 025 to AG 031, AF 001 to AF 015, AA 01 141 to AA 0149.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a a coordination meeting with Juan Vallejo and Giovanni Taffanelli of DCMC, along with key warehouse personnel from DCMC. The meeting focused on reviewing current inventory operations, addressing procedural inconsistencies, and aligning the team on standardized practices to ensure accuracy, continuity, and efficiency in the cycle count process.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted schedule cycle counts for the assigned inventory areas as part of the ongoing initiative to enhance inventory accuracy control. This task focused on reconciling physical stock with system data to identify and address any discrepancies. The inventory locations covered during this session ranged from AB 001 to AB 072.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed inventory operations planning and reviewed data to support upcoming cycle count activities at the Aguirre warehouse, in coordination with Mr. Juan Vallejo of DCMC. Task included verifying item locations, updating inventory documentation, and coordinating resource allocation to enhance process accuracy and ensure readiness for schedule counts. Today we focus on locations AB 001 to AB 072.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory verification at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. Activities included auditing item locations, verifying part numbers and descriptions, resolving inconsistencies in stock quantities, and cross-checking inventory data against system entries. The effort aimed to strengthen inventory control by ensuring compliance with asset management standards and improving the reliability and transparency of stock records.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a variance assessment at the Aguirre warehouse, to identify inventory discrepancies and analyze inconsistencies impacting stock accuracy. The objective was to support improvements in inventory control by addressing anomalies, ensuring data integrity, and reinforcing operational efficiency. This activity contributes directly to the timely execution of corrective actions and overall enhancement of asset management practices.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Megapack 2 XL Transportation and Storage Guidelines Topic 4 Storage 3.3.4 Trailer Off-Loading Guidance send by Andres Concepcion from DCMC.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, TESLA Manuals Megapack 2 XL Operation and Maintenance Manual Topic 5 Megapack System Maintenance send by Andres Concepcion from DCMC.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, TESLA Manuals Megapack 2 XL Design and Installation Manual Topic 2 Hazard Mitigation Features send by Andres Concepcion from DCMC.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, DCMC Construction Procurement Update Information May 15, 2025 send by Carlos De Jesus from DCMC.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Safety briefing conducted by Homeca and Gilberto Soto DCMC was present this morning. Had Meeting with Emmanuel Santos from (HOMECA ) to discuss the weekend work schedule and activities. Tacking out the bottom exhaust stack from turbine 1-2 with crane.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Meeting with Carirma Sanchez (HOMECA ) Jose Lopez Linarez DCMC to discuss the weekend work schedule. Field supervision activities briefing with Gilberto Soto from DCMC. Contractor Supervision (Homeca Recyclers) for Abatement Activities field supervision and coordination all around the site.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety and to make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca started cleaning the field housekeeping and move materials to continue dismantling areas Day 17 Homeca make cuts on the steel chimney to prepare for rigging plan. Electrical Company Continue and finish installing temporary line for distribution on site
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, EHSS, Siemens Energy, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #293566-15 for TO#1 Apr 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Continue working on Compliance Review CDM Smith Invoice #90234612 for TO#1 Apr 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC Participants: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader and others.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, EHSS, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Contractual high level Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla contract reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes and client's financial needs. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kucsinky), and DCMC (Rafael Calderon)
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations AG025 to AG031 using Cycle Count List #710.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AF001 a AF015.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AF001 a AF015.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AF001 a AF015.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AF001 a AF015.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AF001 a AF015.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 041 000 to AA 01 049 000
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 041 000 to AA 01 049 000
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 041 000 to AA 01 049 000
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AB 001 to AB 072 and at the Aguirre warehouse to start the cycle counts.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AB 001 to AB 072 using Cycle Count List # 706/07/08/16/17
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 700/14/15 locations AB 001 to AB 072
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AB 001 to AB 072
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations AG025 to AG031 to start the cycle counts.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #718, 719 and 720 locations AG025 to AG031.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #718, 719 and 720 for locations AG025 to AG031, totaling 134 pieces.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AG025 to AG031.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Incorporate SOP Drawing Tool for all projects/Establish access for Financial Management team in Procore in Financial Project Folders - all projects
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Coordination of incoming data_documents_submittals with Lauren (DCMC) Ivette Miranda (S&L) Data Management Vega Baja BESS/Cambalache BESS/ Costa Sur Peakers review of incoming data
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review different Procore tools such as Submittals, Photos and Drawings to audit non-related information uploaded to system.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Scheduling Tool implementation; overview of uploaded Schedule and Features such as reporting, workforce inclusion and two weeks look ahead reporting.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Meetings tool for the internal team assistance; guidance for Eduardo Rivera (DCMC) on conducting meetings at the Procore Platform.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Brief discussion with Carlos De Jesus (DCMC) about the Schedule Tool features: construction progress tracking and relating Financial Tool with the Schedule Tool.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.75 |  | 151 | 264.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Procore Tools execution with the DCMC staff: Jose Lopez, Carlos De Jesus, Andres Concepcion and Rafael Pabon (CDM Smith): Report Creation and Features, Submittals Performance and Scheduling implementation.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare file with all invoices from Sargent and Lundy_January 2025 and send the information to Manuely Concepción (CDM). Also, discuss with José Ralat (DCMC) about pending amendment for TO6 on Sargent and Lundy to release payment for last invoice. Review that all invoices sent corresponds to January 2025 with excel files and PDF versions.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. This is an update to the presentation for DCMC meeting.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, and Eisha Mercader from DCMC, and Shellsea Maysonet (SM Consulting); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with DCMC Partners Frances Vallejo and Raissa Borges team to work on the Community Engagement Report.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Call meeting with Genera PR Jorge Bracero team to offer an update on the work carried out during this week along with a work continuity plan for next week.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Developed a report for the Genera PR team on findings, key contacts, and opportunities for community collaboration, to align the development of the BESS project with the environmental and social context of the area following yesterday's meeting with the Local Committee for Environmental Emergency Response Planning in Arecibo.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.25 |  | 139 | 312.75 | 139 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue working in the development of newsletter design in Canva for the Bess and Peakers community outreach, refining content placement and adjusting graphics for a better readability and engagement.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Update the COMMUNITY OUTREACH DCMC 2025 annual plan to be delivered to Jorge Bracero from Genera Team's on Monday along with the key tasks of the week.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -Continued translating the Safety Manual from English to Spanish. Focused on reviewing for consistency, technical accuracy, and correct use of terminology. Also worked on aligning the formatting and structure with the original document to ensure that the final Spanish version meets quality standards and remains clear and accessible for Spanish-speaking personnel. Completed the translation and formatting of Chapter 7 and 8.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.25 |  | 139 | 34.75 | 139 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Completed the 4 pages of translation of Chapter 8 of the Safety Manual from English to Spanish. Focused on reviewing the content for consistency, technical accuracy, and the correct use of safety and regulatory terminology. Ensured the final version aligns with quality standards and is clear and accessible for Spanish-speaking personnel.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review Warehouse new parking area erosion control plan for 4339_9510 BESS_Cambalache project.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on invoice information considering PROCORE settings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule information considering PROCORE settings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review Warehouse new parking area erosion control plan for 4339_9510 BESS_Cambalache project.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Developing effective visuals for BESS and Peakers request for proposal, project progress and project risks to make data more accessible and easier to interpret, allowing users to quickly identify issues and solution and providing clear insights, that can guide to decisions and strategies.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Frances Vallejo and Paola Arroyo from DCMC to discuss Community Engagement reports.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Managing and developing visuals for safety and security activities on BESS and Peakers projects to make data more accessible and easier to interpret.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 122 | 366 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339.Continue creating visuals for BESS and Peakers requests for proposals, project progress, and risk assessments to enhance data accessibility and interpretation. These visuals enable users to quickly identify issues and solutions while providing clear insights that support informed decision-making and strategic planning.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 33.66 | 33.66 | 33.66 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Project, Office Supply for the Job Site Office Trailer. 1. Printer Paper 2. Desktop Stapler 3. Staples 4. Clipboard.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel receipt dated 5/13 for site visit to costa sur site walk through omitted from last expense pay period.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 25 | 25 | 25 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 fuel for multiple peaker sites
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. 64.0 miles
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- traveled directly from home in Guaynabo to Aguirre to support inventory operations alongside Mr. Juan Vallejo from DCMC. The purpose of the visit is to monitor inventory workflows, review ongoing counting procedures, validate process accuracy, and ensure that operational practices align with established inventory control standards.
2025-05-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.2 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- after completing the meeting at the Aguirre warehouse with Mr. Juan Vallejo from DCMC, returned back home in Guaynabo. The purpose of the visit was to monitor inventory workflows, review ongoing counting procedures, validate process accuracy, and ensure that operational practices align with established inventory control standards
2025-05-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for safety and to make sure they comply with the safety measures while conducting Demolition and cleaning the areas by Homeca. Homeca resumed cleaning the field housekeeping and moving materials to continue dismantling areas Day 18 Homeca make cuts on the steel chimney to prepare for rigging plan. Rigging plans continue to dismantle GT 1 2 to have control, establish safety precautions. and identify all hazardous situations that might be encountered during lifting.
2025-05-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja BESS job site. Daily project coordination and project management. Project Documents Overview and analyzing the project documents' status in the Procore platform for revisions and updates to maintain accountability and ensure project success.
2025-05-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS - Supervise Contractor's (HOMECA) Daily activities of Demolition and cleaning the areas. Overview to report the progress of the tasks, number of hours worked by staff, materials used, and any delays or incidents in the project which is vital for improving safety protocols and mitigating future risks.
2025-05-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 18 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans continue to dismantle GT 1 2.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 site walk through with contractors to proactively identify potential risks and foster a culture of safety awareness among your team. held a Q/A session afterward and safety clarification and expectations. Homeca Recycling, and Gator Demolition.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 performed a site walk through with potential General contractors for the demolition portion of the costa sur project, walked the site marked up structures to be demolished. Gator demolition, and Homeca Recycling.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Progress data gathering in preparation of BESS Check in project status.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM Weekly Agenda Review, Update, Needs and Goals for the week. Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group, and Gilberto Sucre - DCMC Partners.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Dashboard review with Raissa Borges, Frances Vallejo, Gilberto Sucre DCMC Partners
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting to discuss Document Current Process Intake for Subcontractor and Material Invoices to upload in Procore until Procore Financial Module is fully implemented. CSA Group, and DCMC Partners participated.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check in Weekly Meeting, led by Gabriel Perez CDM Smith provided update on RFC and RFP Status, Veba Baja Demolition, Palo Seco Pre-Demolitions, Global Topics Permitting, Design Drawings, Procore, Interconnection Studies, Tesla Contract, Document Control, Land Use and Transformer Studies. Genera, CDM Smith, CSA Group, Sargent & Lundy, & DCMC Partnership.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja RFC Meeting with ARG Ceres continuation meeting to discuss RFC's status, Value Engineering information exchange, contract status meeting, and schedule. CDM Smith, Sargent & Lundy, ARG Ceres and DCMC Partners participated.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Internal Meeting PM/CM Team. Purpose to align BESS project needs with Sargent & Lundy design deliverables and schedule goals. Cambalache - RGE Vega Baja - ARG Ceres Costa Sur - RGE Aguirre - RGE Yabucoa - TBD CDM Smith, CSA Group, Sargent & Lundy and DCMC Partners
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Projects Coordination, Agenda and Correspondence Update. Vega Baja demolition recommendation to Genera.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting to foster collaboration and informed decision-making among all stakeholders. Meeting attendees were Jesus Cintron, Nelson Rosado, Ricardo Pallens, Carlos Palomares, Joaquin Quinoy, Gabriel Perez, Mike Kuczynski, Franklyn Colmenares (Genera), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore summary report.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss Procore items.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items for clarification on saving documents, worked on calendar invites for Q&A sessions.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks tracker
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Manuely Concepcion (CDM Smith), Franklyn Colmenares (CSA), Luis Roman, Theresa Perez, Gilberto Sucre (DCMC), Rafael Pabon (CDM Smith) to discuss and document the current processes for invoice intake.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on putting together Procore Weekly Q&A email and link for signing up for users.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Gabriel Perez (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Continued working on putting together Procore Weekly Q&A email and link for signing up for users.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more Procore correspondence items for documents tool.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP review.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Supervise the Turbo Compresor travel form Vega Baja to Palo Seco Genera Site.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Supervise the Turbo Compresor travel form Vega Baja to Palo Seco Genera Site process. Training Javier Baez, David Figueroa, David Lebron, Jose Flores, Ramon Velez and Javier del Valle from Charlie Towing about EHS Genera presentation.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3.25 |  | 184 | 598 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Supervise the Turbo Compresor travel form Vega Baja to Palo Seco Genera Site process.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Attended meeting with Jesus Cintron regarding BESS and Peakers project needs. Participants: Jesus Cintron (Genera), Gilberto Sucre (DCMC), Gabriel Perez (CDM), Franklyn Colmenares (CSA), German Nunez (Genera) and Abraham Velazquez (DCMC).
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting to discuss Procore Dashboard Discussion. Participants: Raissa Borges and Gilberto Sucre (DCMC)
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended BESS and Peakers Check In meetings with Project management teams for both projects. Participants: Gabriel Perez, Carlos Palomares (CDM), German Nunez, and Jesus Cintron (Genera), Franklyn Colmenares (CSA), Gilberto Sucre, Rafael Calderon, Sheila Torres, Raissa Borges, Abraham Velazquez (DCMC).
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Continued reviewing proposals for compliance with Section 6.4.1 of the RFP, which outlines 13 mandatory requirements that all proponents must meet. Conducted a detailed review of two proposals(CSA and Elementz) to verify adherence to these criteria and identify any deficiencies.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Began reviewing proposals for compliance with Section 6.4.1 of the RFP, which outlines 13 mandatory requirements that all proponents must meet. Conducted a detailed review of two (AVA & CPM) proposals to verify adherence to these criteria and identify any deficiencies.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Continued reviewing proposals for compliance with Section 6.4.1 of the RFP, which outlines 13 mandatory requirements that all proponents must meet. Conducted a detailed review of two proposals(Integra & Lord) to verify adherence to these criteria and identify any deficiencies.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Continued reviewing proposals for compliance with Section 6.4.1 of the RFP, which outlines 13 mandatory requirements that all proponents must meet. Conducted a detailed review of two proposals(E&RC and HGE) to verify adherence to these criteria and identify any deficiencies.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, and Glorimel Torrado; and Marc Maceira (HONRA LLC) Subcontractors: Shellsea Maysonet, Johanna Díaz (SM Consulting), Carlos González and Ginnell Torres ( Integrum)
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.75 |  | 184 | 690 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued gathering information for the development of the sourcing integration Scope of Work, with a focus on evaluating the capabilities of Asset Suite to inform integration planning. Finalized the Genera Connect communication plan and submitted the initial communication draft to Alejandro Maymi from Genera PR for approval. Additionally, delivered the weekly projects update during the Genera PR projects meeting, with participation from Alejandro Maymi (Genera PR) and DCMC team members Rafael Calderon, Jose Ralat, Eisha Mercader, Esther Rohena, and D'Alexzander Gonzalez.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Initiated the removal of unused resources from the Genera Connect Azure environment to optimize infrastructure and reduce operational overhead. Additionally, began drafting the Scope of Work for the sourcing integration, incorporating the gathered requirements and focusing on defining the project background, goals, and objectives to establish a clear foundation for the integration effort.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 19 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started by Charlie Towing who arrived to install crane for mobilization.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS - Dismantling, Decommissioning and demolition works planning for phase II. Homeca Recycling should submit an LED abatement removal and recycling material manifest and certification to safely handle and remove lead hazards, protecting workers and staff from lead exposure.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria—VEGA BAJA BESS - Weekly look-ahead schedule review and discussion with the DCMC team, Gilberto Soto, Jaime Persquera, and Gilberto Sucre: Coordination and logistics for Homeca's week work plan to coordinate labor is performed in a way that minimizes disruptions and ensures that every aspect of the project is executed efficiently.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on trailer offices layout for Costa Sur (BESS project), Central Cambalache and Central Aguirre. Desing offices and conference areas. Coordinate trailer's location and space available by phone with plant managers and site managers. Coordinate with Danny Duenas (Duenas Trailers) quotes. Sent Email to Frances Vallejo (DCMC) and Gilberto Sucre (DCMC) with quotes and Layouts. Received COI for BESS Yabucoa RFP 231175 by Franklyn Colmenares (Genera) COI was signed and sent to Alex Velez and Franklyn Colmenares (Genera) as requested.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on trailer offices layout for Costa Sur (BESS project), Central Cambalache and Central Aguirre. Desing offices and conference areas. Coordinate trailer's location and space available by phone with plant manager Herminio Arroyo (GENERA) and Andres Concepcion (DCMC) site manager Cambalache BESS Project and in Cental Aguirre Francisco Mari (GENERA) Security Manager and Jose M Lopez (DCMC) Site Manager BESS Project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is being done to create safety guidelines for the safe use and handling of tools for the BESS CAMBALACHE project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is being done to create safety guidelines for work involving the use and handling of cranes and rigging systems for the BESS CAMBALACHE project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated a site plan with a proposal of locations for the management (owner's representative - DCMC Partners) office trailer to be presented to Genera PR (Herminio Arroyo).
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Gilberto Sucre (DCMC) to review Cambalache site readiness plan. Performed revisions on the plan and updated documents to be provided to Genera PR. (Jesus Cintron)
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - performed quality control (Q/C) for Procore Platform pending actions and data. Drafted an SOP for Procore in order for Contractors processes to be implemented during Construction.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Cambalache MSA and contract additions by Contractor RG Engineering (Jose Robles). Provided comments to Gilberto Sucre (DCMC) for the considerations of the team evaluating the contract agreement.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Contractor Homeca continue working in preparation of GT-1 for rigging, they had installed the rigging sling for the lift of GT-1 turbine section, also at Palo Seco there is another crew waiting for the GT-1 to bring it down from platform, the delay on this work was in regard of the heavy rain.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with contractor Homeca, work activity related to Vega Baja BESS project. Contractor Homeca continues with demolition of structure at GT-2 and also working with demolition of GT-1. Crane arrive at site for the rigging of GT-2 and GT-1, also in rigging will include the generator winding mass.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue with the contractor Homeca demolition of structure at GT-2 and preparation of GT-1 for rigging, crane has been set on place as soon contractor prepare crane for lifting, they will start with the work. Reviewing Vega Baja BESS drawing on Procore for tomorrow pre-kick off meeting.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Meeting with Enrique Laya and Gabriel Sepulveda of CDM, Carlos Hernandez of ARG, Gilberto Sucre and Eduardo Rivera of DCMC, and Wilfredo Sierra, Gary Jasutis, Regina Amirova, Margolis Jordan, and Angel Alicea of S&L. Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - provided field support on rigging of generator 2 and rotor segment. Homeca also will send to Caguas the turbine section housing, generator and stator of GT-2.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Contractor Homeca is working in preparation of GT-1 for rigging, crane has been set on place as soon contractor prepare crane for lifting, they will start with the work. Reviewing Vega Baja BESS drawing on Procore for tomorrow pre-kick off meeting. Rain starts at 12pm may delay the rigging of GT-1.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC to verify inventory accuracy. This activity was essential to validate previous cycle count results, resolve identified discrepancies, and enhance the reliability and consistency of inventory records. Locations schedule for the day, specifically from AI 001 to AI 012.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an early morning job briefing with Milton Flores, Hernan Machado and key DCMC warehouse personnel to address and review discrepancies observed during the prior week operations. The session emphasized the importance of accurate data entry, adherence to procedural standards, and maintaining inventory integrity. Additionally, discussions included corrective actions, process improvements, and preventive measure to avoid recurring issues and enhance operational consistency.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle counts for the designated inventory locations schedule for the day, specifically from AI 001 to AI 012. This task was part of an ongoing initiative aimed at enhancing inventory accuracy and improving alignment between physical stock and system records. Activities included validating items quantities, inspecting labeling and storage conditions, and documenting discrepancies to support corrective actions and maintain data integrity within the inventory system
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed inventory data analysis and prepare cycle count sheets to support schedule activities at the Palo Seco warehouse, in coordination with DCMC Mr. Giovanni Taffanelli. Task included verifying item locations, ensuring stock accuracy, and organizing necessary materials to facilitate a streamlined and efficient inventory process.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- attended a virtual meeting via Microsoft Teams with Ms. Maria Sanchez from Genera PR and DCMC project staff to review and assess the weekly progress of ongoing project activities. Discussions included status updates on inventory operations and identified challenges.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a targeted variance analysis to identify systematic discrepancies between physical inventory and digital records within high-impact locations. Assessed root causes of inventory mismatches by cross-referencing item master data, transactional history, and location-specific stock movements. The objective was to enhance data accuracy, reinforce inventory traceability, and support compliance with asset management protocols. Activities included validating stock quantities, reviewing historical adjustment, and flagging unresolved variances for corrective action. Efforts directly contributed to improved system reliability and readiness for audit and regulatory review. Locations schedule for the day, specifically from AI 001 to AI 012.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the Palo Seco warehouse, developed a consolidated inventory performance report for Mr. Anthony Vega of Genera PR. The report integrated data from all warehouse locations and included catalog ID analysis, unit balances, cost summaries, discrepancy tracking, and evaluation against authorized maximum/minimum thresholds. Percentage-based indicators were used to illustrate inventory accuracy and stock health across sites. Locations reviewed included AI 001 to AI 012, AF 016 to AF 029, AB 072 to AB 145, AC 001 to AC 072, BJ 001 to BJ 008, BK 001 to BK 009, BL 001 to BL 007, BM 001 to BM 006.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review current list of Fuel Efficiency to verify which components already have Tech Spec completed.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of the CCL Tracker to identify cases with discrepancies in purchase orders or contract information. The CCL Tracker was reviewed to determine which cases have issued purchase orders or executed contracts that present inconsistencies or conflicting information in the documented records.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Revision Proyectos Federales Status meeting with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz, and Roberto Bosch; from MSC Shellsea Maysonet;, to discuss priorities and deliverables, status updates, identify next steps for projects under Federal Grant.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review current list of Fuel Efficiency to verify which components already have Tech Spec completed.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Megapack 2 XL Design and Installation Manual Topic 7 Accessing the Megapack Enclosure send by Andres Concepcion from DCMC.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Comments at Cambalache updated Schedule in Procurement by CDM SMITH May 15, 2025 send by Carlos De Jesus from DCMC.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document PROCORE Platform Cambalache BESS Project - Update y 3WLA procurement pending works updated by CDM Smith, 15 May, 2025 send by Carlos De Jesus (DCMC)
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Cambalache BESS Project - schedule update May 15, 2025 - Update y 3WLA Procurement process sends by Carlos De Jesus from DCMC.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform. Coordination of turbine number 1 to be taken out today to Palo Seco.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Continued Vega Baja Contractor Homeca Recyclers field supervision with Gilberto Soto DCMC. Overview to and frequent briefings ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution and with safety in mind. Turbine #1 was taken out today.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 19 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started by Charlie Towing Continue to install crane for mobilization.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 19 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started by Charlie Towing Completed mobilization towards Central San Juan. Uploaded information to ProCore App. Notified Rodolfo Vazquez from Genera of arrival.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 164 | 656 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on CDM invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder. I started today working on CDM.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC & Genera- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz, Christian Cruz, Carlos Gonzalez) and MSC Shellsea Maysonet; from Genera (Alejandro Maymi and Maria Sanchez)
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 730 and 731 locations AI001 to AI012
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AF016 to AF029
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AF016 to AF029
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AF016 to AF029
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AF016 to AF029
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AF016 to AF029
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BJ 00 001 000 to BM 00 006 000
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BJ 00 001 000 to BM 00 006 000.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BJ 00 001 000 to BM 00 006 000
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 734 locations AB 072 to 145 and AC 001 to DM 072.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AB 072 to 145 and AC 001 to DM 072.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AB 072 to 145 and AC 001 to DM 072 at the Aguirre warehouse to start the cycle counts.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AB 072 to 145 and AC 001 to DM 072 using Cycle Count List # 725/726//36/37
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #379, 380, and 381 from locations AI001 to AI012 for a total of 90 pcs.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AI001 to AI012 Cycle Count List # 724.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AI001 to AI012
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AI001 to AI012 to begin the cycle counts.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Vega Baja BESS Incoming Certifications for Work Performed/Receipts
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja BESS ARES Incoming Documentation Process/Costa Sur Peakers GENERA Incoming Processing Documents/Procore Coordination for Intake of Invoice Data for all Projects with Lauren Wells (Lemoine)
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control - Data Management Vega Baja BESS Processing Incoming Documents _Certificates _Waste Manifest Documents
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Run Procore analysis for the Schedule Tool concerning external users (Contractors/Vendors) permissions and capabilities inside the Tool.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with DCMC Staff Andres Concepcion and Luis Duque, along with design team representants Monica Ybarra and Ivette Miranda (Sargent & Lundy) to discuss issues encountered while publishing drawings on Procore: repeated drawing numbers have been found: total of 36 drawings needs to be edited.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review contractual agreement for Cambalache and Costa Sur Projects: Owner's Requirement for invoicing and certifications for payment.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine), Franklyn Colmenares (CSA), Rafael Pabon and Manuelly Concepcion (CDM Smith) and DCMC Staff (Gilberto Sucre, Theresa Perez); discussing the invoicing current process for vendors and contractors and what is expected to get from the Procore Financial Tools related to invoicing and budgeting.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform Drawings Tool Audit to report repeated drawing numbers on Issue for Bid Construction Drawing Plans for the Cambalache Project: creation of spreadsheet to share with the design team (Sargent & Lundy); POC Ivette Miranda.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform testing and QA/QC on new form implemented for Procore QA/QC Weekly Meetings with users to satisfy internal staff inquiries on platform and ensure external users proper execution.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on final version for publishing of RFI's, Schedule and Drawing Tools; Drawing Tools was reviewed by Team with commentaries.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review pending correspondence, save important documents in files and review pending action items for this week (invoicing and contract management).
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Genera and DCMC Weekly Meeting with participation from DCMC: D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and Victor Maldonado. Also, Shellsea Maysonet (SM Consulting) and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 149 | 596 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on CDM invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder. I started today working on CDM and prepare an email to Rafael Calderón DCMC with the missing invoices or issues found for this vendor.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Sandra Miranda, the director of the childcare center in Toa Baja Choo Choo Train Day Care and Learning Center and the Genera PR team, Jorge Bracero in order to determine the date of visit to the educational center, logistics and plan to present the BESS and Peakers project to the school community.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Hurricane Maria-meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey. In the meeting was the Genera PR Team: Jesus Cintron, Joaquin A Quinoy, Ricardo Pallens, Maria Sanchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczinsky and Nelson Rosado. The meeting was about the Bess Project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Worked on compiling and analyzing data for the Community Outreach Report in Excel. This task involved collecting input from multiple stakeholders, organizing outreach activities by category and region, and tracking key performance indicators such as event participation, total hours, total communities reached, and estimated people reached.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Create an Excel report related to the PMO Community Outreach Report that would be delivered to the Genera PR team, Jesús Cintron, in order to evidence the impact of the program BESS and Peakers.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Kroma and Genera Weekly Meeting in the meeting was the Genera's PR Team: Ivan Baez, Jorge Bracero and Rafael Rodriguez. In the meeting was the Kroma team: Amarilys Torres and Victoria Flores
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Raissa Borges Almodóvar from DCMC Partners Team with the purpose of presenting my Excel report related to the PMO Community Outreach Report that would be delivered to the Genera PR team, Jesús Cintron, in order to evidence the impact of the program
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continuing the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. I am drafting the document using the correct format while maintaining the original English version’s structure and style. This ensures consistency, technical accuracy, and compliance with established standards. The draft incorporates precise terminology and linguistic adaptations to preserve clarity and intent, all while retaining formal sections, headings, numbering, and references. Chapters 12 through 15 have been completed.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continuing the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The document is being drafted using the correct format while maintaining the original English version’s structure and style. This approach ensures consistency, technical accuracy, and compliance with established standards. The draft incorporates precise terminology and appropriate linguistic adaptations to preserve clarity and intent, all while retaining formal sections, headings, numbering, and references. Completed Volumen 2 - Chapter 1.1 to 1.15
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continuing the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. I am drafting the document in the correct format while preserving the original English version’s structure and style to ensure consistency, technical accuracy, and compliance with established standards. This draft incorporates precise terminology and linguistic adaptations to maintain clarity and intent while retaining formal sections, headings, numbering, and references. Chapters 9 through 12 have been completed.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continuing the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The document is being drafted using the correct format while maintaining the original English version’s structure and style. This approach ensures consistency, technical accuracy, and compliance with established standards. The draft incorporates precise terminology and linguistic adaptations to preserve clarity and intent, all while retaining formal sections, headings, numbering, and references. Completed: Volume 2 – Chapters 2.1 through 2.11.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 134 | 201 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review BESS Grading and Drainage plan for 4339_9510 BESS_Cambalache project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule update in procurement information considering PROCORE two week look ahead settings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule update in procurement information considering PROCORE settings for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule) Identify areas to improve the timeline and identify logic to improve. Reviewed BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (PART 2) Continue review BESS Grading and Drainage plan for 4339_9510 BESS_Cambalache project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procore Drawings meeting with Andres Concepcion (DCMC), Ivette Miranda (Sargent and Lundy), Monica Ybarra (Sargent and Lundy) and Luis Roman (DCMC) for the 4339_9510 BESS_Cambalache project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review BESS Grading and Drainage plan for 4339_9510 BESS_Cambalache project.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. In person meeting with Frances Vallejo and Gilberto Sucre from DCMC to discuss Procore Dashboard report.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 122 | 183 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Keep systematically reviewing Inventory Management project updates to enhance the accuracy of progress tracking.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue collecting and evaluating inventory project updates to optimize the visual depiction of progress ensuring data is more accessible and understandable.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Paola Arroyo from DCMC to discuss Community Outreach status and updates for reporting purposes.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue conducting a structured review of inventory project data and updates to refine progress tracking.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC).
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 122 | 183 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Conducting a comprehensive compilation and analysis of Inventory Management project data, including status updates, to enhance the visual representation of progress and potential risks. This process aims to improve data accessibility and facilitate more effective interpretation.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 16.82 | 16.82 | 16.82 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Purchase a computer mouse for a more appropriate use of my computer
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.42 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria - following the site visit at the San Juan warehouse with Mr. Giovanni Taffanelli from DCMC, returned back home in Guaynabo. The purpose of the visit was to provide on-site oversight of warehouse operations, evaluate current inventory control measure, and collaborate with Mr. Taffanelli on improving process efficiency. Engaged with Mr. Taffanelli to identify opportunities for enhancing process efficiency and operational alignment.
2025-05-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.91 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria - traveled directly from Guaynabo to Central Palo Seco to meet with Mr. Giovanni Taffanelli from DCMC. The purpose of the visit is to provide on-site support and oversight of warehouse operations, asses current inventory control practices, and collaborate with Mr. Taffanelli on enhancing process efficiency. Additionally, the visit aimed to identifying operational gaps and ensure alignment with project deliverables
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of documents and preparation for meetings later in the afternoon. Verified Peakers project management plan, and staffing plans.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in meeting: Costa Sur materials & equipment relocations. Discussed highlighted areas with Genera reps to confirm when the equipment and material currently on site will be relocated allowing for the site preparation of the project demolition portion only German Nunez, GENERA; Rafael Pabon, and Carlos Palomares CDM Smith; Frances Vallejo, DCMC, and Jesus. Cintron, Genera.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur Preparation for Costa Sur RFC meeting with RGE and Permit requirements evaluation with Sargent & Lundy and CDM Smith team for Lead Abatement scope to be added to Project. Provide new location of Emergency Generator selected by Genera to Sargent & Lundy for their design.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Initial RFC Meeting with RG Engineering for the CSA Construction Phase. Gabriel Perez CDM Smith led the meeting and establish the process expectations for the RFC's, Pricing, Schedule and Contract Negotiations. Participants Companies: CDM Smith, Sargent & Lundy, RG Engineering, & DCMC Partners.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Review of latest RGE Contract and Attachments submittal of May 19, 2025.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RFC Meeting RGE / Costa Sur Site to review updated tracker and information exchange. Lead Abatement Proposal to be included as part of the scope inclusive of the permitting process for compliance record. Stressed importance to the group to complete this cycle by next week. Participants CDM Smith, CSA Group, Sargent & Lundy, RG Engineering & DCMC Partners.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Weekly DCMC Internal Project Team Meeting. Discussed current project status, Site readiness plan and actions items to work with Genera Plant Management for resolution. and upcoming Mobilization Activities. Frances Vallejo, Andres Concepcion, Luis Damudt, Luis Duque, Jorge Mercado, Carlos de Jesus and Gilberto Sucre - DCMC Partners.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Veba Baja Construction Meeting Agenda Preparation of topics to cover for Installation Phase,
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO Team Catch Up meeting focused staffing introduced Sylvia Franco as a potential candidate for the Cambalache position, with discussions on establishing a fixed hybrid work schedule. The team is considering converting hourly positions to salaried ones, influenced by overtime expectations and billing efficiency, which would affect six staff members and will be finalized for immediate implementation. Procore implementation was also a significant topic, with Lauren reporting the signing of the services agreement and the necessity for leadership alignment on Procore capabilities. Project updates highlighted ongoing progress on various site installations and the PMO RFP, which has had its deadline extended for further clarification from potential proponents. Mark Merritt, Michael Merritt, Frances Vallejo, Jack Darnall, Foster Veazey, Anneilia Holton, Lauren Wells, and Gilberto Sucre - DCMC Partners
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria EHS Draft Manual Review including Spanish translation for Genera.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Installation Phase - Construction Weekly Meeting Kickoff. Meeting Started with Team Introductions from Genera, CDM Smith, CSA Group, DCMC Partners, Sargent & Lundy and ARG Ceres all participants fo the Construction Installation Phase. Topics Covered: Organizational Chart RFC Negotiation Status Value Engineering Scope of Services DOR Communications RFI's and Submittals Project Execution Plan EHS Requirements Quality Requirements Schedule Site Logistics, laydown, storage & parking Payment Breakdown
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Mark Merritt (DCMC), Jack Darnall (Lemoine), Foster Veazey (Lemoine) to discuss Procore Financial Personnel.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on SOP for Incidents Tool.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Procore support to figure out about files being uploaded from Customer Support.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences with Luis Roman (DCMC) for various items.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore documentation of processes for Master document of use.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP outline for Meetings for Luis Roman (DCMC) to work on.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences for support.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing comments from Luis Roman (DCMC) for RGE training document.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) to discuss open Procore items to tackle as a team.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of document for training that Andres Concepcion (DCMC) sent for review.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding users to the Procore Weekly Q&A invite and commenting on questions asked.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), GIlberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Powerpoint for RGE training for next week.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions matrix and making adjustments to Photos tool.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Frances Vallejo, Jack Darnall, Lauren Wells, Gilberto Sucre, Barry Scanlon, Foster Veazey, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Inspection Diesel travel from Vega Baja to Palo Seco Genera Site process.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Supervise the Turbo Compresor travel form Vega Baja to Palo Seco Genera Site process. Review the rain meter, inspection crane used to another turbo compressor. Dispatch the teams by local flood.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Supervise the Diesel travel from Vega Baja to Palo Seco Genera Site process.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended the construction Kick off meeting with ARG, contractor for Vega Baja demolition phase 2. Participants: Gilberto Sucre (DCMC), Jesus Cintron (Genera), Eduardo Rivera (DCMC), Jaime Pesquera (DCMC), Manuelly Concepcion (CDM), Miguel Ramos (AG) and Mike Kuczynski (S&L).
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Peakers Management team to discuss Costa Sur material and equipment relocation. Participants: Abraham Velazquez (DCMC), German Nunez (Genera) and Rafael Pabon (CDM)
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss program status, Procore training and financials, Lean management plan, safety plan translation status, trailer update and inventory management needs. Participants: Michael Merritt, Mark Merritt, Ada Diaz, Anneilia Holton, Gilberto Sucre, Lauren Wells (DCMC).
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and analyze the Duenas trailer quote, Ipad quote and other supply needed for trailers at the sites. Create a list of the needed supply and send approval email to Mark Merritt (DCMC).
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Call with Jesus Cintron (Genera) to discuss staffing update for the PMO program.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Carlos Palomares (CDM) and Raissa Borges (DCMC) to discuss one pager reports per site in order to send biweekly reports to the client.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Cambalache on site team to discuss status on RFP and contractor, also discussed trailer installation status. Participants: Gilberto Sucre, Andres Concepcion, Jorge Mercado and Carlos de Jesus (DCMC)
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Began drafting the Technical Evaluation Memorandum. Completed the Overview section and the Minimum Criteria analysis, which included defining each requirement and creating a summary table detailing compliance for all 14 bidders. Also began drafting the Evaluation Criteria section and developed a scoring table that presents the evaluation panel’s scores alongside their corresponding weighted values, providing a clear and structured overview of the results.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Finalized reviewing proposals for compliance with Section 6.4.1 of the RFP, which outlines 13 mandatory requirements that all proponents must meet. Conducted a detailed review of two proposals (Stantec & TRC) to verify adherence to these criteria and identify any deficiencies.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Continued reviewing proposals for compliance with Section 6.4.1 of the RFP, which outlines 13 mandatory requirements that all proponents must meet. Conducted a detailed review of four proposals (NEI, Phasor, ShareTech, Sherpa) to verify adherence to these criteria and identify any deficiencies.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued refining the sourcing integration Scope of Work by defining additional requirements, with a particular focus on the acceptance criteria. In preparation for the upcoming FortiNAC session, assisted Michael Silva from Genera PR in defining and installing a self-signed certificate to enable encrypted communications for the Genera Connect Financial Tracker, supporting secure data transmission and compliance with internal cybersecurity standards.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued supporting Michael Silva from Genera PR in testing secure communications for the Genera Connect Financial Tracker, validating the implementation of encryption protocols to ensure data protection. Additionally, reviewed Genera PR’s procurement standard operating procedures to ensure alignment with the sourcing integration Scope of Work, facilitating consistency between existing practices and planned integration requirements.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 20 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started Charlie towing Comtinue to install crane for mobilization of the second generator. ADS diesel removal continued Day 2, dismantled platforms work stoped due to rain submitted information to Procore.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega baja BESS Project. Diesel Transfer activity supervising from the Vega Baja site to Central Palo Seco. Record keeping of all the diesel tanquers tranfered to the R-1 Tank.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Project. Supervising Diesel Transfer activity from the Vega Baja site to Central Palo Seco. Working on record keeping of all the diesel tanquers transferred to the R-1 Tank.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Project. Oversight diesel transfer activity from Vega Baja site to Central Palo Seco and maintained transfer records for all deliveries to R-1 Tank.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working with the proposals for BESS Yabucoa RFP 231175 submitted last Friday. Verify that the proposals are complete according to the project documents. Coordinate with Danny Duenas (Duenas Trailers) the availability of Office Trailer available for Delivery next week in Costa Sur (BESS Project).
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working with the proposals for BESS Yabucoa RFP 231175 submitted last Friday. Download & Review documents to verify all the scope is included in proposals. Drawing was sent by Email to Gilberto Sucre (DCMC), showing the new area for the generator to relocate in Costa Sur BESS Project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is being done to create safety guidelines for traffic control that are being implemented with contractors in the BESS CAMBALACHE project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is being done to create safety guidelines for risk identification and pedestrian protection, which are being implemented with contractors in the BESS CAMBALACHE project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Cambalache site team for weekly project updates and coordination. Meeting with Gilberto Sucre, Frances Vallejo, Luis Damudt, Luis Duque, Carlos De Jesus, Jorge Mercado.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - generated Procore Meeting for Contractor content and agenda and forwarded to Lauren Wells (Lemoine) for meeting coordination. This meeting will align contractor (RG Engineering) with DCMC Procore management process.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Cambalache site team for weekly project updates and coordination. Meeting with Gilberto Sucre, Frances Vallejo, Luis Damudt, Luis Duque, Carlos De Jesus, Jorge Mercado)
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Attended BESS program weekly design management meeting to review drawings progress with Sargent and Lundy (Robert Molner, CDM Smith (Carlos Palomares, Gabriel Perez), CSA Group (Franklyn Colmenares).
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued to Developing in Procore meetings tool the Cambalache Construction Weekly agenda with project action items for discussion with the contractor team. Distributed agenda via Procore to the complete project team.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and commented Cambalache contract pending attachements and construction schedule to be closed in order to finalize construction contract with RG Engineering.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Consolidated project updates and actions list to be discussed within the team in the Cambalache internal site team meeting to provide direction to team.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed in Procore meetings tool the Cambalache Construction Weekly agenda with project action items for discussion with the contractor team. Distributed agenda via Procore to the complete project team.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with construction activity ay Vega Baja Site, Homeca continue with cutting and demolition of GT-2 for then rigging of unit. 150-ton Crane has dismantled the weight and then move the crane to new position for lifting of GT-2. ADS. Continue working with the relocation of the second container of Diesel to Palo Seco. Preparing agenda for construction pre kick off meeting at 1PM.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working supervising construction activity ay Vega Baja Site, Homeca has completed the removal of turbine 2 section and rigging was completed, Rain has delay work of Crane counterweight.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with construction activity ay Vega Baja Site, Homeca continue with cutting and demolition of GT-2 for then rigging of unit. They are relocating the 150-ton crane near GT-2 for rigging of unit they crane will take time to install all contra weight for rigging preparation. ADS continue with Diesel removal they had ready a third container.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Kick Off Meeting with ARG/CERES Contractor - ARG/CERES: Carlos Hernandez, Pedro Marrero, Adrian Iglesia, Denise Manzano and Ludgardo Gonzalez. DCMC: Gilberto Sucre, Frances Vallejo, Jean Pierre Menay and Eduardo Rivera, CDM Smith: Manueli Concepcion, S&L: Mike Kuczynski, and CSA: Franklyn Colmenares. Meeting was to discuss and introduce all key player, stake holder for the pre-construction kickoff meeting for items to be deliver before project start.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with contractor Homeca, work activity related to Vega Baja BESS project. Contractor Homeca continues with demolition of GT-1 for today rigging of turbine section and turbine housing. Homeca continues working in cutting de frame of GT-2. Today we also have on site contractor ADS on the removal of Diesel from Genera Diesel Container to be transport to Palo Seco. First Diesel tanker has left Vega Baja facilities to Palo Seco.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory verification at the Aguirre warehouse in collaboration with Mr. Juan Vallejo from DCMC. The scope of work included validating item locations, confirming part numbers and descriptions, resolving quantity discrepancies, and reconciling physical inventory with system records. This initiative aimed to reinforce inventory control by ensuring alignment with asset management standards and enhancing the accuracy, traceability, and transparency of inventory data. Locations addressed during this session range from AC 072 to AC 136.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on-sit at the Aguirre warehouse, a consolidated inventory performance report was developed for Mr. Anthony Vega of Genera PR. The report compiled and analyzed data from all warehouse locations and included catalog ID validation, unit count verification, cost breakdown and discrepancy tracking. Additionally, the report assessed inventory levels against authorized maximum and minimum thresholds. Percentage-based metrics were applied to visualized stock accuracy, coverage, and overall inventory health across sites. Locations reviewed included AA 150 to AA 153, AC 072 to AC 136, AI 013 to AI 022, GC 007 to GC 013.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed scheduled cycle counts for designated inventory zones as part of the ongoing initiative to improve inventory accuracy and system alignment. The operation involved reconciling physical inventory against system records to detect and resolve quantity variances, identify data integrity issues, and ensure compliance with the established protocols. Inventory locations addressed during this session range from AC 072 to AC 136.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory operations planning and reviewed data to support upcoming cycle count activities at the Aguirre warehouse, in coordination with Mr. Juan Vallejo of DCMC. Task included validating item locations, updating inventory records, and coordinating resource allocation to improve process accuracy and ensure operational readiness.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a a coordination meeting with Hernan Machado and Giovanni Taffanelli of DCMC, along with key warehouse personnel from DCMC. The purpose of the meeting was to assess current inventory operations, identify procedural discrepancies, and align the team on standardized practices. Emphasis was placed on ensuring accuracy, continuity, and operational efficiency within the cycle count process.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a variance analysis at the Aguirre warehouse to identify inventory discrepancies and evaluate data inconsistencies affecting stock accuracy. The assessment aimed to strengthen inventory control by resolving anomalies, improving data reliability, and enhancing procedural compliance. This effort directly7 supports the timely implementation of corrective measures and the continuous advancement of asset management standards. Locations addressed during this session range from AC 072 to AC 136.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Cambalache Attachment J - HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES send by Jean Pierre Menay from DCMC.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Cambalache BESS - Site Readiness for Construction Start send by Andres Concepcion from DCMC.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, TESLA Manuals Megapack 2 XL Operation and Maintenance Manual Topic 4 Civil Design, 4.2.1 Foundation Design send by Andres Concepcion from DCMC.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, TESLA Manuals Megapack 2 XL Operation and Maintenance Manual Topic 4 Civil Design, 4.1 Routes and Zones send by Andres Concepcion from DCMC.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, RFI #18 - Discrepancies between drawing CAB99-JN-BSS-0003 (Rev 0) and CAB99-JN-BSS-0003 (Rev 0.1).
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Continued to dismantle, decommissioning and demolition works. We Finally started taking diesel fuel to San Juan, so far 2 truck loads.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Continued to dismantle, decommissioning and demolition works. We Finally started taking diesel fuel to San Juan, so far 3 more truck loads went out & the other turbine from the #2 side, Boths turbine housings are out now.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Contractor Supervision (Homeca Recyclers) for Abatement Activities field supervision and coordination all around the site. Meeting with Carirma Sanchez (HOMECA ) Jose Lopez Linares DCMC to discuss the weekend work schedule. Field supervision activities briefing with Gilberto Soto from DCMC.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 20 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started Charlie Towing. Continue to install crane for mobilization of the second generator. ADS diesel removal continued Day 2
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 20 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started by Charlie Towing. Continue to install crane for mobilization of the second generator.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 164 | 574 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 164 | 656 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on CDM invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder. I started today working on CDM.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GC007 to GC013
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GC007 to GC013
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GC007 to GC013
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GC007 to GC013
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GC007 to GC013
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 050 000 to AA 01 053 000
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 050 000 to AA 01 053 000
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 050 000 to AA 01 053 000
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AC072 to AC 136
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 740/ 744 locations AC072 to AC 136.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AC 072 to AC 136 at the Aguirre warehouse to start the cycle counts.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AC072 to AC 136 using Cycle Count List # 735/741/742
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AI013 to AI022 to begin the cycle counts.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #748 and 749 from locations AI013 to AI022 for a total of 87 pcs.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 792, 793 and 794 locations AI013 to AI022
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AI013 to AI022.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AI013 to AI022 Cycle Count List # 743.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management Vega Baja BESS/Cambalache BESS/Costa Sur Peakers review and manage current documentation and uploaded/Coordination of Procore Documents with Lauren Wells (Lemoine) Luis Roman (DCMC)
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control - Document Management - Costa Sur Peakers Coordination of incoming documents with Rafael Pabon (CDM) for review and processing
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review contractual agreement from Vega Baja to determine Procore setup on tools timing and contractor's obligations.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the implementation of Project Management process in the Procore Platform: timing for responses on different tools, standard specifications for works, RFP and contractual agreements status, actual status of project documentation and the implementation of metrics for the measurement of project progression.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Conduct meeting agenda for the Procore Construction Kick-off at Cambalache; preparing meeting agenda and the discussion of items to set the tone on the use of Procore Platform for both internal and external users, their roles and responsibilities.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Weekly Catch-up Meeting with Lauren Wells (Lemoine) and Theresa Perez (DCMC): discussing yesterday's meeting related to invoicing procedures in and out of Procore, reviewing the potential agenda for Construction Kick-off on Procore for Cambalache, and touching base on potential upcoming workload.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Meetings Tool for the inclusion of new meetings templates to be used on sites for internal and overall meetings.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on CPM, and Homeca invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on Siemens and Javier Bidot invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder. Also, verify on Tesla, Jaca y Sierra, King and Spalding and RGE.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 149 | 372.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on Black and Veatch, CAPTA and EHSS invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Rafael Calderón (DCMC) to discuss RGE contract. During this meeting we review the contract milestones and payment schedule and identify discrepancies that affects the invoicing process. Findings will be discussed with Rafael Pabón (CDM) and review will continue.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Visit to the University of Mayagüez Campus (RUM) to sign a collaborative agreement with the university community and educate about the BESS and Peakers projects. The meeting was attended by the RUM team: Carmen Patricia Pares and Humberto Nieves Martinez. The General Pr team: Jorge Bracero, William Sanchez, and Waldo Cordova. DCMC Partners supports Genera in efforts to promote the Genera PR internship so that future engineers can work on the BESS and Peakers project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Get ready for the meeting as part of the community efforts being made with the engineering student community who will be collaborating on the BESS and Peakers project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 139 | 243.25 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Work has begun on Chapter 3 (Sections 3.1 through 3.10) of the Safety, Health, and Environment (SHE) Manual translation from English to Spanish. The translation is being carried out using the required format, maintaining the original structure and style to ensure consistency, technical accuracy, and adherence to established standards. The draft incorporates precise terminology and thoughtful linguistic adaptations to preserve clarity and intent, while retaining all formal sections, headings, numbering, and references.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 139 | 243.25 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Work has continued on Chapter 3 (Sections 3.1 through 3.10) of the Safety, Health, and Environment (SHE) Manual translation from English to Spanish. The translation is being carried out using the required format, maintaining the original structure and style to ensure consistency, technical accuracy, and adherence to established standards. The draft incorporates precise terminology and thoughtful linguistic adaptations to preserve clarity and intent, while retaining all formal sections, headings, numbering, and references.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: The translation of Chapter 5 (Sections 5.10 through 5.13) of the Safety, Health, and Environment (SHE) Manual from English to Spanish is currently in progress. This work follows the required formatting guidelines, ensuring the original structure and style are maintained for consistency, technical accuracy, and compliance with established standards. The draft reflects the use of precise terminology and carefully refined language to ensure clarity and preserve the original intent, while maintaining all formal elements such as section titles, numbering, and references.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Working on Chapter 5 (Sections 5.1 through 5.10) of the Safety, Health, and Environment (SHE) Manual translation from English to Spanish is ongoing. The translation is being developed in compliance with the required format, preserving the original structure and style to ensure consistency, technical accuracy, and alignment with established standards. The draft includes precise terminology and carefully adapted language to maintain clarity and intent, while preserving all formal sections, headings, numbering, and references.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Work is ongoing for the translation of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The document is being translated using the required format while maintaining the original structure and style to ensure consistency, technical accuracy, and compliance with established standards. The draft incorporates precise terminology and appropriate linguistic adaptations to preserve clarity and intent, while retaining formal sections, headings, numbering, and references. Status: Completed – Volume 2, Chapters 2.12 through 2.20.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review BESS Grading and Drainage plan for 4339_9510 BESS_Cambalache project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on comments on schedule update in procurement considering PROCORE bid and GENERA process for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create report with comments on design and construction schedule of administration GENERA for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on create reports with comments on RFP schedule version 6 considering logical construction and GENERA guides for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache participated in Cambalache internal TEAMS meeting discussing Project contract status, special meetings with contractor and next power Plants in process of sign contracts with employees Luis Damudt, Luis Duque, Jorge Mercado, Andres Concepcion, Gilberto Sucre and Frances Vallejo (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule) BESS Genera Aguirre projects to track progress, identify risks, and ensure accountability.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin revise project documentation (Genera BESS State of Design and Milestone Schedule) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review BESS Grading and Drainage plan for 4339_9510 BESS_Cambalache project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache Internal Weekly meeting with Andres Concepcion (DCMC), Frances Vallejo (DCMC) and Gilberto Sucre (DCMC) for the 4339_9510 BESS_Cambalache project for weekly project updates and coordination
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Completed review BESS Grading and Drainage plan for 4339_9510 BESS_Cambalache project.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue compiling and assessing Critical Components project updates to enhance data visualization, improve accessibility, and facilitate clearer interpretation of progress and risks.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Systematically compiling and assessing Critical Components project updates to enhance data visualization, improve accessibility, and facilitate clearer interpretation of progress and risks.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue collecting and evaluating Critical Components project updates to optimize the visual depiction of progress ensuring data is more accessible and understandable.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Frances Vallejo, DCMC and Carlos Palomares, CDM Smith to discuss Genera projects One Pager Report structure, data and frequency.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes |  |  | Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Transfer Diesel from Vega Baja to Palo Seco (GENERA) Sites. Total Distance 64.0miles
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-following the completion at the Aguirre warehouse with Mr. Juan Vallejo from DCMC, returned to residence in Guaynabo. The objective of the visit was to support the implementation of corrective actions previously identified during cycle counts, assist Mr. Juan Vallejo from DCMC in reviewing inventory variances, and ensure compliance with update inventory management protocols. The visit also included reinforcement of best practices for inventory accuracy.
2025-05-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from home in Guaynabo to Aguirre warehouse to assist with inventory operations and provide on-site project oversight. The objective of the visit is to support the implementation of corrective actions previously identified during cycle counts, assist Mr. Juan Vallejo from DCMC in reviewing inventory variances, and ensure compliance with update inventory management protocols. The visit also included reinforcement of best practices for inventory accuracy.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 466.8 | 466.8 | 466.8 | Yes |  |  | T-Mobile for Business. May charges for hotspots and cellphones for Genera Deliverable 11 project.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) finalized Powerpoint for RGE training next week. Have sent to Luis Roman (DCMC) for comments will review with Andres Concepcion ( DCMC) on 5/23.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in meeting: Bess and Peakers 2025 RFP update items discussed were the clarifications to the scope of work at Costa Sur demolition portion of the project various areas requiring more detailed information from the engineers. Attendees: German Nunez, GENERA Rafael Pabon, CDM smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC Harry Del Valle DCMC Gilberto Sucre DCMC.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended S&L Peaker's PM weekly drawings review. Items discussed: Costa Sur Bunker Tank containment matting to be replaced or protected, updating the revised portion of the demolition portion of the project and differentiating the alternate building to possibly be demolished at a later date. Attendees: German Nunez, GENERA Rafael Pabon, CDM smith Carlos Palomares CDM Smith Chris Mateo Sargent & Lundy Gino Sambolin Sargent & Lundy William Crespo Sargent & Lundy Lemuel Nieves Sargent & Lundy.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 225 | 393.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache - Meeting to review and respond to RGE final Contract Submission and Attachments. Legal & Financial completed including schedule revisions required. Attachments and Scope Final verification pending from Sargent & Lundy as data was not received. Participants Genera, DCMC Partners, CSA Group, CDM Smith & Sargent and Lundy.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting ARG Ceres Vega Baja. Continued discussions on RFC between ARG Ceres, Sargent & Lundy, CDM Smith and DCMC Partners. Geopiers Submittal expected by Thursday afternoon, next meeting to be held on Friday at 9:30 am
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera Tesla Weekly Design Update for BESS Program between Telsa, Sargent & Lundy, Genera, CDM Smith, CSA Group, DCMC Partners. Rigging activities also discussed but no clear guidance was obtained on the use of dollies for Mega Packs placement to final position.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache - Update discussion with Andres Concepcion - DCMC of PreCon activities and Contractor Permit Requirements.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Weekly Construction Meeting with Homeca Recycling. Review update and work plan for Demolition Stage and Diesel Transfer activities to Palo Seco. CDM Smith, Homeca Recycling, CSA Group, & DCMC Partners.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - ARG Ceres T & C's Legal Review between Genera and ARG Ceres Legal Counsel, DCMC Partners also aprticpicated.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Demolition Phase II discussion with Jose Lopez - DCMC and Progress and Update status of Diesel Transfer activities to Palo Seco.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence review and response of e-mails, Procore Submittals and reports for BESS Program.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prep for weekly meeting with Joaquin Quinoy (Genera) and email follow-up. worked to update the Genera's new standard Glossary of Lean terms based on the input and feedback from Joaquin, since Joaquin did not attend or communicate that he was not able to attend the weekly check-in call.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Powerpoint for RGE training for next week.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on final version of SOP for Incidents tool to share with Jean Menay (DCMC).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Luis Roman (DCMC) for various Procore items from SOP's to weekly Q&A meeting items.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial tool.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore submittal for when an approver is out and only 1 user is checked to approve.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meeting for purpose of Procore alignment with leadership, S&L and DCMC Teams.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks management for open items.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching information about Procore schedule tool to further discussions with Carlos De Jesus (DCMC).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Procore Weekly Q&A with Luis Roman (DCMC), Carlos De Jesus (DCMC), Rafael Pabon (CDM Smith).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Photos tool settings.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding Financial users to Procore for preparing tools for use.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore RACI matrix.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1.25 |  | 184 | 230 | 184 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339 – Hurricane Maria: Continuing site inspections and safety evaluations at the Vega Baja site to identify potential hazards in equipment and facilities, ensuring compliance with established safety standards. The scope also continues to include oversight of the diesel transportation process from Vega Baja to the Genera site in Palo Seco.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Inspection Diesel travel from Vega Baja to Palo Seco Genera Site process. Meeting about the Vega Baja Project, Carirma Sanchez (Homeca), Jaime Pesquera, Jose Lopez (DCMC), Franklyn Colmenares, Manuelly Concepcion and Enrique Laya (CDSMITH).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Inspection Diesel travel from Vega Baja to Palo Seco Genera Site process.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Paul Browne (DCMC) to discuss inventory management project and needs, Also discuss the report that was submitted to Genera.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Raissa Borges (DCMC) to discuss site reports for BESS and Peakers divided in separate pdf files. Also discuss status of monhtly report.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 184 | 46 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Sent email to Andres Concepcion (DCMC) attaching the construction manager job description updated to the Aguirre site and requirements.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Jesus Cintron (Genera) and Gilberto Sucre (DCMC) regarding trailer request for Aguirre and Costa Sur.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya, Carlos Palomares (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Prepared for the weekly BESS and Peakers catch-up call by reviewing and updating the project tracking spreadsheet. Incorporated feedback and updates received on 05/20 from the Genera procurement team, including changes to documentation status, and contractor communications. Ensured the tracker reflected accurate, real-time information to support productive discussion, alignment across teams, and timely follow-up during the coordination meeting.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Continued drafting the Technical Evaluation Memorandum. Developed brief narrative summaries explaining the evaluation panel’s scoring for Lord, NEI, Phasor, HGE, ShareTech, Sherpa, Stantec & TRC highlighting each proponent’s strengths, weaknesses, and overall alignment with the RFP criteria. Ensured that the justifications were clear, consistent, and supported by the evaluation record.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Continued drafting the Technical Evaluation Memorandum. Developed brief narrative summaries explaining the evaluation panel’s scoring for AVA, CPM, CSA,Elementz, E&RG and Integra highlighting each proponent’s strengths, weaknesses, and overall alignment with the RFP criteria. Ensured that the justifications were clear, consistent, and supported by the evaluation record.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Continued the weekly FortiNAC session in support of Mario Gomez and Michael Silva from Genera PR, with a focus on installing security certificates to prevent untrusted devices from accessing critical systems such as Asset Suite, Oracle Fusion, and Genera Connect. Additionally, continued evaluating the integration capabilities of PowerAdvocate Sourcing Intelligence to ensure its suitability and alignment with the requirements defined in the sourcing integration Scope of Work.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Researched the integration capabilities of PowerAdvocate Sourcing Intelligence to support the development of the sourcing integration Scope of Work, focusing on compatibility and functional alignment with Genera PR’s procurement processes. Additionally, provided support to Mario Gomez and Michael Silva from Genera PR during the weekly FortiNAC session, continuing efforts to enhance secure access to key internal systems.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 21 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans were started by Charlie Towing. Continue to install crane for mobilization of the second generator. ADS diesel removal continued Day 3, Charlie towing Removed Crane from site.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega baja BESS Project. Diesel Transfer activity supervising from the Vega Baja site to Central Palo Seco. Record keeping of all the diesel tanquers tranfered to the R-1 Tank.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Project. Supervision of diesel tanker movement from Vega Baja to Central Palo Seco, with comprehensive logs of each transfer to the R-1 Tank.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Project, continue with Diesel Transfer activity supervision from the Vega Baja site to Central Palo Seco. Record keeping of all the diesel tanquers transferred to the R-1 Tank.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working with the proposals for BESS Yabucoa RFP 231175 submitted last Friday. Verify that the proposals are complete according to the project documents. Review Proposals to make recommendations. Starting coordination with Danny Duenas (Duenas Trailers) the Delivery next Tuesday 27th in Costa Sur (BESS Project). Additionally, the deliveries for the Aguirre BESS Project and Yabucoa BESS Project in the first week of June.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working with the proposals for BESS Yabucoa RFP 231175 submitted last Friday. Verify that the proposals are complete according to the project documents. Review Proposals to make recommendations. Coordinating with Danny Duenas (Duenas Trailers) the Delivery next week in Costa Sur (BESS Project).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RFC Meeting RGE Cambalache. Meeting to review and respond to RGE final Contract Submission and Attachments. Legal & Financial completed including schedule revisions required. Attachments and Scope Final verification pending from Sargent & Lundy as data was not received. Attendees: Gilberto Sucre (DCMC) and participants from Genera, CSA Group, CDM Smith & Sargent and Lundy.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is underway to create safety guidelines for risk communication and the chemical materials that will be used on the site.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Work is being done to create safety guidelines and recognize global harmonization systems for risk communication involving chemical agents for the BESS CAMBALACHE project
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and generated emails regarding project permitting follow ups and questions to Franklyn Colmenares. Reviewed Gilberto Sucre (DCMC) email with comments regarding the contract agreement.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued review of the Cambalache site survey and existing conditions report and drawings from surveyor Javier Bidot. Evaluated underground lines for coordination prior demolition activities. This information will be discussed in a site visit with the contractor (RG Engineering).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Conducted Cambalache Week Construction meeting for weekly follow ups and action items. Meeting attendance was RG Engineering - Contractor (Jose Segarra), Sargent and Lundy - Designer (Dean Ennes) and DCMC Team (Luis Damudt, Jorge Mercado, Luis Duque and Carlos de Jesus) and CSA Group (Franklyn Colmenares) .
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Finalized and completed Cambalache Weekly Construction Meeting agenda and actions items for discussion with the contractor (RG Engineering) and Designer (Sargent and Lundy) for important project follow ups.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project Invoice Format and process to be followed. Exhibit I - Exhibit I - Invoice Format that will be used in the construction contract with contractor (RG Engineering)
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed pending RFIs in Procore platform and followed up with designer to request a timeline for its review and approval. Followed up by email with Sargent & Lundy (Robert Molner).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Cambalache site survey and existing conditions report from surveyor Javier Bidot. Evaluated underground lines for coordination prior demolition activities.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed an in-depth analysis of inventory data and developed cycle count documentation to support scheduled operational activities at the Costa Sur warehouse. Work was carried out in coordination with Mr. Hernan Machado from DCMC. Additional responsibilities involved preparing materials, aligning task with cycle count objectives, and reinforcing procedural compliance to ensure a streamlined and reliable inventory management process. Today locations range from AA 154 to AA 155.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled cycle counts for designated inventory locations, specifically covering AA 154 to AA 155. This task formed part of the operational efforts to strengthen inventory control and maintain synchronization between physical stock and system records. Additional efforts focused on identifying recurring issues, ensuring procedural compliance, and providing recommendations to enhance future inventory accuracy.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a job briefing with Juan Vallejo, Giovanni Taffanelli and key DCMC warehouse personnel to evaluate the effectiveness of current inventory practices and discuss strategies for standardization across all warehouses. The focus shifted toward aligning operational procedures with system requirements, ensuring consistent data entry practices, and addressing gaps in inventory visibility.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC to validate inventory data and confirm accuracy. This initiative was essential for reconciling prior cycle count results, investigating unresolved variances, and verifying system record alignment. Key activities included cross checking item quantities, documenting deviations, and recommending corrective measures to enhance data integrity and support audit readiness Locations range from AA 154 to AA 155.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while station at the Costa Sur warehouse, prepared and delivered a comprehensive inventory report to Mr. Anthony Vega of Genera PR. The report integrated data from all warehouse locations and included a strategic summary of catalog records, unit volumes, cost evaluations, discrepancies, and stock level thresholds maximum/minimum. It also incorporated key performance indicators to assess the overall condition of current inventory. Locations reviewed included AD 001 to AD 135, AA 154 to AA 155, GC 014 to GC 019, HL 008 to HL 017.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an in depth evaluation of inventory discrepancies to enhance internal controls and ensure compliance with inventory management protocols. The activity focused on identifying root causes of inconsistencies, validating system records, and implementing corrective measures to improve data accuracy, operational performance, and audit readiness. Locations range from AA 154 to AA 155.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Construction Weekly, Franklyn Colmenares, Andres Concepcion, Luis O. Damudt and Jorge Mercado, Carlos De Jesus, Luis Duque, Jean Pierre Menay DCMC Partners, Jose Segarra, Alberto Jose Borrelli, Javier Reyes from RGE.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | General Deliverable PR 11 - Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS received and reviewed COMMENTS from DCMC on April 17, 2025. 8. Appendix D.3 - Demolition Specifications.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Cambalache BESS- Existing Conditions Survey by Andres Concepcion from DCMC.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document Comments at Cambalache proponent Schedule by RGE Schedule VE proposal Accelerated Critical 140525 May 20, 2025 by Carlos De Jesus from DCMC.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Contractor Supervision (Homeca Recyclers) for demolition activities field supervision and coordination all around the site. Meeting with Emmanuel Santos (HOMECA )and Nelson Soler (CDM-Smith) to discuss the weekend work schedule. Field supervision activities briefing with Gilberto Soto from DCMC.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Homeca Recycling continued dismantling, decommissioning and continued demolition works and planning for phase II. Kept turbine 2 base dismantling and turbine base 1 almost completely finished.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Homeca Recycling keeps dismantling, Decommissioning and demolition works and planning for phase II. Turbine 2 base dismantling and turbine base 1 almost completely finished.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 21 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started Charlie towing Continue to install crane for mobilization of the second generator. ADS diesel removal continued Day 3, Charlie towing dismantled Crane corrected crane fault.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 21 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started Charlie towing Comtinue to install crane for mobilization of the second generator. ADS diesel removal continued Day 3, Charlie towing Continue removed Crane from site.waiting for ADS last truck trailer number 509, adding information to ProCore, verifying submittals and Managing Daily Logs.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Glorimel Torrado, Esther Rohena and José Ralat from DCMC, and representing CDM Rafael Pabón. This meeting was to discuss all the research that we prepare on the morning working session according to the invoice review. We discuss findings and modifications needed on the invoice in order to comply with FEMA.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 164 | 574 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Glorimel Torrado (DCMC) reviewing RG Engineering_109403 contract (876 pages long) and start preparing RFI for RGE. During this working session we review the contract terms that affects the invoice. We review the invoice and identify missing information and clarification; also, we prepare a schedule of value based on the contract for this vendor.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Start reviewing RG Engineering_109403 contract prior working session with Glorimel Torrado (DCMC). During this hour I research on the contract for important payment terms, documents conditions precedent to payment, milestone schedule and overview reading. This review is important to evaluate the invoice for Milestone #1 that needs to be initially reviewed today.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review-based contract development. Meeting between Tesla team , CMD Smith PM team (Gabriel Sepulveda), Sargent & Lundy (Mike Kuszynski., Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Pro-Core (Lauren Wells).
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on Black and Veatch invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder. I started today working on Black and Veatch.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GC014 to GC019
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GC014 to GC019
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GC014 to GC019
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GC014 to GC019
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GC014 to GC019
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 054 000 to AA 01 055 000
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 054 000 to AA 01 055 000
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 054 000 to AA 01 055 000
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 760/765 location AD 001 to AD 135.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AD 001 to AD 135.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AD 001 to AD 135 at the Aguirre warehouse to start the cycle counts.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with location AD 001 to AD 135 using Cycle Count List # 752/753/761/762
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations HL008 to HL017 to begin the cycle counts.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #767 and 768 from locations HL008 to HL017 for a total of 113 items.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations HL008 to HL017.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 767 and 768 locations HL008 to HL017
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations HL008 to HL017 Cycle Count List # 756.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Vega Baja BESS Review & Process Incoming Documents/ Costa Sur Peakers Review & Process Incoming Documents/ Coordination with Rafael Pabon (CDM) on RFP Data for Costa Sur Peakers/ Coordination with Manuely Concepcion (CDM) on all old and new Data for Vega Baja BESS & Costa Sur BESS
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the final draft version for Procore Tools SOP's (Incidents and Meetings). Review Permissions information, configurate to standard template and forward for publishing.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Project Weekly Meeting for Cambalache Power Plant. Hosted by Andres Concepcion (DCMC), including representatives from RGE (General Contractor) such as Jose Segarra and Alberto Borelli, representatives from the Design Team (Sargent & Lundy) and DCMC Staff (Luis Duque, Luis Damudt, Jorge Mercado, Jean Menay). Discussion of topics prior construction kick-off scheduled for June 2025. Relevant information that needs to be submitted, establishment of project schedule and expectations for the project life cycle.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 151 | 188.75 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Testing for the Schedule Tool at the Training Project: Review process for certifying progress completion on a Schedule Task: requested progress change, assigned it to myself and approve the request. Pending feedback from Schedule Uploader to run Updated Schedule.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the final versions for SOP (Schedule, Drawings and RFI tools): Review final draft version and perform corrections based on users feedback.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the uploading process for Incidents and Observations to perform SOPs review and updates: incorporation of new items at the Observation Type Categories, review of Incidents final SOP and the implementation of new potential forms for Inspections and Forms Tools.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 151 | 113.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – First Procore Q&A Session Meeting hosted by Lauren Wells (Lemoine) and myself; Carlos de Jesus (DCMC) and Rafael Pabon (CDM Smith) assisted to the session bringing out inquiries from the Schedule Tool and the capabilities of the tool compared to other Scheduling Tools (Primavera, Microsoft Project, etc.)
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 149 | 521.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón (DCMC) reviewing RG Engineering_109403 contract (876 pages long) and start preparing RFI for RGE. During this working session we review the contract terms that affects the invoice. We review the invoice and identify missing information and clarification; also, we prepare a schedule of value based on the contract for this vendor.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Pre-intervention Tasks Update and Review. Reviewing pending action items from all vendors, Pending RFIs, Pending CPA and Email Follow-ups to vendors.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Rafael Calderón, Esther Rohena and José Ralat from DCMC, and representing CDM Rafael Pabón. This meeting was to discuss all the research that we prepare on the morning working session according to the invoice review. We discuss findings and modifications needed on the invoice in order to comply with FEMA.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Start reviewing RG Engineering_109403 contract prior working session with Rafael Calderón (DCMC). During this hour I research on the contract for important payment terms, documents conditions precedent to payment, milestone schedule and overview reading. This review is important to evaluate the invoice for Milestone #1 that needs to be initially reviewed today.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón (DCMC) reviewing RG Engineering_109403 invoice. During this working session we edit the information that needs correction (total amount, contract #, etc. We include the information that was missing on the invoice and make the corrections. These corrections were sent to RGE for their final approval. Also, we discuss and review the deliverables for this milestone. Pending to receive the Parent Guarantee. A formal email with the Pre Intervention review information was sent to Finance team and shared with RGE.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Informative visit to learn about the BESS project through the field visit to Costa Sur in Guayanilla.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Informative visit to learn about the BESS and Peakers project through the field visit to Aguirre, Salinas.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Initiated the translation of Volume 3, Chapters 1 and 2 of the Safety, Health, and Environment (SHE) Manual from English to Spanish. This work is being carried out by the established formatting requirements, ensuring the preservation of the original structure and style for consistency, technical precision, and compliance with applicable standards. The draft features accurate terminology and thoughtfully adapted language to ensure clarity and faithfully reflect the original intent, while maintaining all formal elements, including section headings, numbering, and references.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Began translating Volume 2, Chapters 1 and 2 of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The translation follows the required formatting guidelines, preserving the original structure and style to ensure consistency, technical accuracy, and alignment with established standards. The draft uses precise terminology and carefully refined language to maintain clarity and convey the original intent, while retaining all formal elements such as section titles, numbering, and references.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Currently working on translating Chapters 6, 7, and 8 of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The translation adheres to the required formatting guidelines, maintaining the original structure and style to ensure consistency, technical accuracy, and compliance with established standards. The draft incorporates precise terminology and refined language to preserve clarity and intent, while retaining all formal elements such as section titles, numbering, and references.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Construction Weekly meeting with Andres Concepcion (DCMC), Rober Molner (Sargent and Lundy) and Jose Segarra (RGE) for the 4339_9510 BESS_Cambalache project.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on teams meeting related to Cambalache BESS - Construction Weekly with stablish next meeting, status of next submittals and status of starting initial process with DCMC employees Andres Concepcion, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Jose Borreli, Vernadee Ortiz, Xiomara Pérez Álvarez, Juan Alvarez, employees of Sargent and Lundy Dean A Ennes, , Javier Reyes, Robert D Molner, employee of CD Smith Franklyn Colmenares, due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work-related on-site Costa Sur worked on schedule update in procurement considering status of RFI, Submittals and remaining projected durations for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on teams meeting related to Procore Weekly Q&A Session considering works on scheduling and setting in PROCORE with Lauren Wells ( Lemoine), Luis Roman (DCMC) and employee of CDM Smith Rafael Pabon due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on schedule update in procurement considering PROCORE bid and GENERA process for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule). Project Civil and Earth Works Drawings. BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Began revising project documentation (Genera BESS State of Design and Milestone Schedule) Scope of work and project materials take off. BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – (Part 2) Ongoing technical review of the proposed stormwater infrastructure, including retention pond, culvert system, and pump inlet layout for the 4339_9510 BESS Cambalache project. Focused on confirming hydraulic connectivity, evaluating erosion control measures, and verifying alignment with local permitting requirements and FEMA public assistance engineering standards.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Start reviewing BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Transforming BESS projects schedule data into charts, graphs, and other visual formats that make it easier to grasp at a glance. This approach helps stakeholders quickly identify milestones, delays, trends, and overall performance, improving communication and decision-making.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting with Frances Vallejo, DCMC. The purpose of this meeting is to discuss Genera project reports status and updates.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 122 | 183 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue transforming BESS projects schedule data into a Gant charts graphs to make it easier to grasp at a glance. This approach helps stakeholders quickly identify milestones, delays, trends, and overall performance, improving communication and decision-making.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Transforming Peakers projects schedule data into a graphic format to make it easier to visualize them and to helps stakeholders quickly identify milestones, delays, trends, and overall performance for the decision-making.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.3 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane- Maria-traveled directly from home in Guaynabo to Costa Sur warehouse to conduct a targeted assessment of inventory control procedures and evaluate compliance with established data management standards. Also, will be collaborating with Mr. Hernan Machado reinforcing cycle count methodology in accordance with operational guidelines.
2025-05-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.23 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled back home in Guaynabo from Costa Sur warehouse. The purpose of the visit was to conduct a targeted assessment of inventory control procedures and evaluate compliance with established data management standards. Also, we collaborated with Mr. Hernan Machado reinforcing cycle count methodology in accordance with operational guidelines.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore workflows for RFI's.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in project schedule meeting and budget update. Reviewed the current schedule and budget based on recent revisions and procurement date of equipment. Attendees: German Nunez, GENERA, Rafael Pabo, and Carlos Palomares CDM Smith.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710. Attended weekly Peakers permitting discussion, reviewed up to date status of permitting and the responsibilities of the new contractors and roles they will have in obtaining their own permits for us to monitor and review. German Nunez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - met with Harry del Valle to discuss the need for Genera to confirm in writing desired location for Emergency Diesel Generator and Tank Relocation and Office Trailer location to serve BESS project. Quality Plan reviewed procedure status and instructed to get Luis Duque DCMC involved in procedure development for BESS / Peaker's Program.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's worked with Carlos de Jesus DCMC to prepare manpower loading curve by site across both programs.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Project Schedule & Budget Weekly Meeting. Led by Carlos Palomares CDM Smith provides weekly update of projects schedule and vendor procurement and delivery dates. Participants CDM Smith, CSA Group, Genera and DCMC partners.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review correspondence and responded as required for related to the project management Construction Overview among all sites.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Permitting Status Update Call for Genera BESS / Peaker Projects led by Anna Rausch - Sargent & Lundy Participants: CDM Smith, CSA Group, Genera, Sargent & Lundy and DCMC Partners.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review RFC Status in details with: RGE - Cambalache ARG Ceres - Vega Baja RGE - Costa Sur RGE - Aguirre TBD - Yabucoa
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.25 |  | 225 | 56.25 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Scheduled meeting with Jorge E. Sanchez (Genera) for lean training for his department to support Lean tool utilization in support of improving outcomes for grant projects.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Worked on cleaning up old legacy projects and making them inactive.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences with the DCMC Procore team for upcoming tasks.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Powerpoint to show stats for Procore leadership alignment meeting next week.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence with Procore support to address an issue with file upload.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on SOP for Observations for Internal and External use cases.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Powerpoint to show stats for Procore leadership alignment meeting next week.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on running reports in Procore to see usage stats on users and project site metrics.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOP's for latest updates on comments.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updates/changes to the PPT for RGE review.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences discussing meeting agenda for next week for Cambalache meeting with RGE.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore schedule tool. Researched questions that Carlos De Jesus (DCMC) had for us.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Inspection Diesel travel from Vega Baja to Palo Seco Genera Site process. Inspection Diesel Truck Tank and process. Review the Local and Federal Government Regulation for transport diesel.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Inspection Diesel travel from Vega Baja to Palo Seco Genera Site process. Inspection Diesel Truck Tank and process.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11¦ DR 4339 - Hurricane Maria- Call with Harry del Valle (DCMC) to discuss Costa Sur trailer installation and needs.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Assisted Costa Sur Equipment Assessment meeting to discuss material and equipment removal at the site. Participants: Rafael Pabon (CDM), German Ojeda (Genera), Abraham Velazquez (DCMC).
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in meeting at the Casa Ronald Visit at Palo Seco site to discuss project. Participants: Jorge Bracero (Genera).
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended catch up meeting to discuss contract/legal management for BESS project. Participants: Sheila Torres (DCMC) and Rafael Calderon (DCMC).
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers Project Schedule & Budget Meeting. Participants: Gilberto Sucre (DCMC), Carlos Palomares (CDM), Rafael Pabon (CDM), Franklyn Colmenares (CSA).
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS TESLA - Reviewed the TESLA contract with a particular focus on the sections related to payment milestones and invoicing procedures. This review was conducted in preparation for an upcoming meeting, with the goal of identifying any potential issues, confirming alignment with project cash flow needs, and supporting informed discussion with stakeholders.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFI 234479 – 228MW BESS Installation: Drafted the announcement language for publication on social media to promote the Request for Information. Focused on crafting clear, engaging, and informative content to encourage participation from qualified vendors and enhance visibility of the procurement opportunity.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4826 BESS Installation at Cambalache - Contract negotiation update discussion with Francisco Feliú and Gabriel Sepulveda (CDMSmith).
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in a BESS TESLA contract discussion with Rafa Calderón and Glorimel Torrado (DCMC), focusing on the status and details of pending change orders. Discussed the scope, justification, and potential impact of the proposed modifications to ensure alignment with contract terms and project objectives.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed LEMOINE Safety Manual Legal Disclaimer to ensure clarity, legal sufficiency, and alignment with standard risk management language. Provided detailed feedback to Gilberto Sucre (DCMC), highlighting areas that may require clarification or revision to mitigate potential liability and ensure compliance with applicable legal standards and best practices.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP231302 - Completed drafting the Technical Evaluation Memorandum. Finalized the conclusion section, summarizing the evaluation panel’s findings and recommendation based on the scoring and analysis of all proposals. Conducted a full review of the document to ensure clarity, consistency, and alignment with the RFP requirements. Submitted the completed draft to Jesús Cintrón (Genera) for feedback and further input prior to finalization.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued developing the sourcing integration Scope of Work by incorporating specific use cases, detailed technical requirements, and a phased implementation approach to guide project execution. Presented the initial draft to Sulinnette Perez from Genera PR to gather feedback and ensure alignment with organizational needs and expectations.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Coordinated the setup of a SharePoint site to securely manage and store BESS project information related to Tesla, including NDAs, the access authorization list, and proprietary documents. Collaborated with Michael Silva from Genera PR to finalize the routing configuration between Genera PR headquarters and the Genera Connect Azure environment, resolving the remaining connectivity issue. Subsequently, tested access and functionality of the Genera Connect Financial Tracker and Timesheets applications from within the Genera PR network.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 22 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the lifting operation. Rigging plans started Charlie towing Comtinue to install crane for mobilization of the second generator. ADS diesel removal forth truck was disposed.diesel Question leak was requested.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewing the Genera Manual for corrections, checking and responding to email of Carolyn Baez, call with Jean Pierre to learn about the progress of the revision of the Genera Safety Manual
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Safety Manual Review Learning Module: Safety Manual Fundamentals Objective: Understand the company’s expectations and protocols around safety. Key Elements to Study: General Safety Rules, Personal Protective Equipment (PPE) standards, Emergency Procedures (Fire, First Aid, Spill Response), Equipment operation and lockout/tagout protocols
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Project. Oversight of diesel transfer operations from the Vega Baja site to Central Palo Seco, including detailed record-keeping of all tankers delivered to R-1 Tank.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja BESS Project. Diesel Transfer activity supervising from the Vega Baja site to Central Palo Seco. Record keeping of all the diesel tanquers transferred to the R-1 Tank.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 167 | 292.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Cambalache Power Plant. Attendees, Luis Damudt (DCMC), Andres Concepcion (DCMC) & Harry Del Valle (DCMC). Topics discussed, Preparation for the DCMC Quality Control Plan, Quality Control needs, walk through BESS Project Site, discussed Office trailer's location, for DCMC and Subcontractor Office Trailer and Laydown area. Measured areas.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Yabucoa Gas Turbine Plant. Attendees, Axel Rivera (Genera) by phone & Harry Del Valle (DCMC). Topics discussed, Office trailer's location, for DCMC and Subcontractor Office Trailer and Laydown area. Measured areas. Took Pictures and review utilities facilities for the Office Trailer's.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinating with Gilberto Sucre (DCMC) the schedule for the deliveries Office Trailers starting next in Costa Sur (BESS Project) & Cambalache Power Plant (BESS Project) and for the week start on June 2nd, 2025, for Aguirre (BESS Project) & Yabucoa (BESS Project). Review List for Equipment & Materials Needed for Office Trailers.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Evaluation of accident reporting formats and procedures. The evaluation focused on improving safety documentation, streamlining response protocols, and standardizing reporting formats across operational teams.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visit to the cambalache site where pre-project coordination is carried out. Impact zones and existing site conditions are verified to inform the contractor and client.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RGE Cambalache Visit, walkthrough with RGE Jose Sarraga on the construction site, also with DCMC team, Andres Concepcion and Luis Damudt to proactively identify potential risks, and foster a culture of safety awareness among the team.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Meeting with GeneraPR Herminio Arroyo to discuss project status and required site logistics and office trailers location coordination with the facility.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Site visit meeting and walktrough with contractor RG Engineering (Jose Segarra) to evaluate site for mobilization and laydown areas. Attended with Herminio Arroyo (Genera PR), and DCMC Partners site team Jorge Mercado, Luis Damudt, Luis Duque.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed with DCMC project safety officer (Jorge Mercado) the Lemoine's Safety Manual to seek incorporation in the project.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed construction disturbance estimate to determine permitting requirements for NPDES permit. Coordinated with Gilberto Sucre (DCMC Partners) next steps and actions to confirm permit requirements. Also, coordinated Procore Kickoff meeting with contractor RG Engineering, and Designer Sargent and Lundy.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting and site walkthrough with DCMC Harry del Valle to confirm office trailer location and installation. Also met to discuss DCMC Partners Construction Quality Assurance plan and its development.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Coordinated DCMC Partners office trailer location and generated correspondence to formalize request with Genera PR (Herminio Arroyo).
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with contractor Homeca, work activity of demolition of turbine frame of GT-2. Contractor ADS continue extracting Diesel for Genera Diesel tank to be transfer to Palo Seco (3) has already travel to Palo Seco with Diesel. Generate an RFI to Mike Kuczynski of S&L for the demolition of the Diesel containment dike wall where 3 should remain as per demolition SOW but these 3 wall interfere with the construction of the second phase.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continued working plan for the demolition on remaining parts of the GT-2 support. Homeca continued to work with the removal a metal parts at GT-1 dike. ADS has decided to stop all work related to the Diesel transfer and this was communicated to Gilberto Sucre and Jose Lopez of DCMC.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working plan for the demolition on remaining parts of the GT-2 support. Homeca continue to work with the removal a metal parts at GT-1 dike. ADS continue with the removal of Diesel of Genera Diesel tank approximate 80k gallon has been transfer to Palo Seco. Carlos Hernandez and Ludgardo Gonzalez of ARG has arrive to the project under a visit with Homeca to review some work plan for the Crane location during second phase of project. There was an issue with some leak drops from one of the valves of the Diesel container that required to be mitigated and repaired before the truck leave our facilities. ADA owners arrived at site and identified an issue. After the issue was resolved he stopped all work.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued execution of cycle counting activities for designated inventory locations, specifically covering ares GC 020 to GC 023. The objective was to validate physical inventory counts, reconcile discrepancies against Asset Suite records, and ensure data integrity. Task also included documenting findings and updating counts logs.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed variance analysis by identifying and categorizing inventory inconsistencies, and validating system recorded data against physical stock. This initiative aimed to strengthen overall inventory governance, increase data integrity, and improve process efficiency. Today's work specifically targeted inventory locations AL 013 to AL 023. The scope of work for the day specifically focused on inventory locations GC 020 to GC 023.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-provided support for inventory data validation and the development of cycle count documentation to facilitate scheduled counting activities at the San Juan warehouse. Collaborated with Mr. Milton Flores from DCMC. to verify bin-level item accuracy, reconcile stock variances, and update system records as needed. Task also included validating storage location assignments, cross-referencing physical counts against Asset Suite records, and coordinating the staging of materials to streamline warehouse workflow.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed physical inventory counts for the assigned locations scheduled for the day, specifically focusing on sections GC 020 to GC 023. Activities included validating item quantities against system records, documenting variances, and updating count sheets to support data integrity. This task contributes to ongoing efforts to maintain inventory accuracy, identify systemic discrepancies, and ensure alignment with Asset Suite records.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted recount at the San Juan warehouse with Mr. Milton Flores from DCMC to validate inventory accuracy and confirm the integrity of previously recorded data. Activities included cross-verifying physical stock with Asset Suite entries, documenting variances, and implementing corrective measure. This effort was critical for finalizing count results, resolving outstanding discrepancies, and reinforcing the consistency. Today's work specifically targeted inventory locations AL 013 to AL 023.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a morning job briefing with Hernan Machado, Juan Vallejo and key DCMC warehouse personnel to discuss previous day cycle count operations. Discussion center on root cause of discrepancies, corrective action planning, and the enforcement of standardize data entry to improve inventory accuracy, and overall compliance with inventory control procedure.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the San Juan warehouse, compiled and submitted and submitted a consolidated inventory report for Mr. Anthony Vega of Genera PR. The report integrated data from all warehouse sites and included catalog inventory breakdowns, location-specific details, units count, cost summaries, identified discrepancies, stock threshold levels, and key performance indicators. The report focused on inventory locations ranging from GC 020 to GC 023, AA 156 to AA 158,
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting RGE Cambalache Site Visit for taking measurements and coordination and mobilization with Jorge A. Mercado, Andres Concepcion, and Luis Duque DCMC Partners Cambalache Power Plant team and Herminio Arroyo from Genera PR.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Continue to Review Lemoine POLICY & PROCEDURE MANUAL.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Lemoine POLICY & PROCEDURE MANUAL.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Discussion of topics and pending issue before RGE Cambalache Site Visit for taking measurements and coordination and mobilization with Andres Concepcion, and Luis O. Damudt DCMC Partners Cambalache Power Plant team and Herminio Arroyo from Genera PR.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Continued Vega Baja Contractor Homeca Recyclers field supervision with Gilberto Soto DCMC. Overview to and frequent briefings ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution and with safety in mind.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Contractor Supervision (Homeca Recyclers) for Abatement Activities field supervision and coordination all around the site. Meet with Carirma Sanchez (HOMECA) Jose Lopez Linares DCMC to discuss the weekend work schedule. Field supervision activities briefing with Gilberto Soto from DCMC.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Homeca Recycling continued dismantling, decommissioning and continued their demolition works and planning for phase II.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria_PW9510 Compliance Review CDM Smith Invoice #90235059 for TO#2 Dec 2024. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Team preparation with Glorimel Torrado (DCMC) for the meeting with DCMC Sheila Torres. During this working session we identify all the items we need to clarify with Sheila Torres that are critical for Tesla Contract. We also prepare a timeline to explain actions and contract management changes.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on Sargent & Lundy invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder. I started today working on Sargent & Lundy.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AG032 to AG047 to begin the cycle counts.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GC020 to GC023
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GC020 to GC023
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GC020 to GC023
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GC020 to GC023
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GC020 to GC023
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 056 000 to AA 01 058 000
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 056 000 to AA 01 058 000
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 056 000 to AA 01 058 000
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.25 |  | 152 | 38 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location. localization CR 001 to CR 136 cycle count 4
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 772 and 774 localization CR 001 to CR 136
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with location CR 001 to CR 136 using Cycle Count List # 763/764
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AD 001 to Ad 135 Cicle /Count type 4 and C at the Aguirre warehouse to start the cycle counts.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AG032 to AG047 Cycle Count List # 770
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 152 | 342 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #777, 778 and 779 from locations AG032 to AG047 for a total of 1,352 pcs.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 777, 778 AND 779 locations AG032 to AG047
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AG032 to AG047
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management / Incorporate SOP for Incidents for all projects /Incorporate Additional Users in Procore for all BESS Projects/Costa Sur BESS Review & Process Incoming Documents/Cambalache BESS Review & Process Incoming Documents/Procore - Removal of CDM Personnel no longer on Projects/
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Document Control - Data Management / Request an Update on Community Outreach Paola Arroyo (DCMC)/ Costa Sur BESS Review and Process Incoming Documents.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Analyzed the contractual documentation for the Cambalache Project to identify the accurate response timelines. Evaluated project management aspects including Submittals, RFIs, contractor duties, and the established procedures for addressing time and cost claims.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Reviewed the Cambalache Project’s contract to confirm response schedules and initiate follow-up actions related to project management activities such as handling Submittals, RFIs, defining contractor obligations, and applying protocols for managing time and cost-related claims.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Procore Analytics performance to combine PMO reporting to client into a complete informative summary; combine reporting from active project management tasks and their progress, time for completion and budgeting scaling.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Implementation of Schedule Tool on Full Scale for Cambalache Project: removal of invalid Schedule files, review of tool features and discuss the actual exposition for the tool as for internal purposes or project progress tracking by contractor.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ PW#9510 - Working on the with Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Start reviewing narratives for this invoice. The invoice has a total of 325 lines. Continue reviewing lines and identify missing information or aligned with SOW lines.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Team preparation with Rafael Calderón (DCMC) for the meeting with DCMC Sheila Torres. During this working session we identify all the items we need to clarify with Sheila that are critical for Tesla Contract. We also prepare a timeline to explain actions and contract management changes.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. I also identify CDM invoice pending that needs attention and organize to start with this invoice.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ PW#9510 - Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Preparing master excel to review the invoice and identify mistakes. Read contract and task order, also verify the invoice rates with the contract rates. I request amendment to TO in order to comply with invoice dates.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Contract meeting with Sheila Torres (DCMC) and Rafael Calderón (DCMC) Contract management to discuss important points regarding Tesla contract and change orders. In this meeting we review change orders and money impact on the contract, Discrepancies on MVT units, tariff impact letter, owner cost delay, 15% margin for direct costs. This meeting will continue tomorrow.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ PW#9510 - Continue with Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Start reviewing narratives for this invoice. The invoice has a total of 325 lines. I started working on administrative lines and identify them.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Coordinate a meeting with the DCMC Partners team, Jean Pierre Menay and the Genera PR team, Jorge Bracero in order to address community challenges at the safety level in Arecibo, Cambalache.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Read, organize, and corroborate communications plans by region: Costa Sur, Aguirre, Yabucoa, Jobos and Daguao.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 Update the PMO Community Outreach report's Excel document.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Creation of an excel sheet of the hours invested in the Bess and Peakers project to deliver to the Genera PR team to Jorge Bracero.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting with Genera Team's Jorge Bracero and the Ronald McDonald Children's Foundation team Mariela Jorge to get to know the organization and understand its functions.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translating Volume 3, Chapters 4 and 5 of the Safety, Health, and Environment (SHE) Manual from English to Spanish. Applied required formatting, preserving the original structure and style to ensure consistency, technical precision, and compliance with standards. Maintained accurate terminology and adapted language to reflect the original intent, keeping all formal elements such as section headings, numbering, and references.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on schedule resources considering quantity of resources hours for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule resources considering quantity of resources hours for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule) Fire Sprinkler system and Duct banks Drawings. BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule) Electrical and Grounding Drawings. BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) (PART 2) Continue review BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFC initial pre-construction coordination meeting with Andres Concepcion (DCMC) and Jose Segarra (RG Engineering Team) for the 4339_9510 BESS_Cambalache project.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Managing BESS projects Milestones data to show task dependencies, progress bars and completion percentages ensuring that project status updates are more understandable and actionable for the stakeholders.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Managing Peakers projects Milestones data to Assess Task Completion Rates, Identify Critical Path Activities, Detect Trends & Risks and Monitor Milestone Progress
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Overseeing BESS project milestone data to illustrate task dependencies, progress indicators, and completion percentages, ensuring that status updates are clear, actionable, and meaningful for client.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez, Gilberto Sucre CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares, Enrique Laya
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 45 | 45 | 45 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits with rental vehicle, Jobos and Aguierre
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Duque, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 68.18 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Route Guaynabo to Arecibo, roundtrip to Guaynabo. Drive 97.4 miles, 1 hr 57 min Claiming Mileage for this route Travel from Guaynabo (18.392607 -66.123698) roundtrip to Cambalache Power Plant, Arecibo (18.471729, -66.700701) back to Guaynabo (18.392607 -66.123698) Purpose project meeting and site walkthrough for initial pre-construction coordination with Genera and RGE for 4339 9510 BESS Cambalache project. TOTAL MILEAGE 97.4 miles
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 106.4 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from CPV Guaynabo to Cambalache Power Plant (18.470985, -66.699693) to Yabucoa Gas Turbine (18.106216, -65.823685) to Home Office Luquillo. Purpose, Cambalache Power Plant & Yabucoa Gas Turbine Plant, Topics discussed, Office trailer's location, for DCMC and Subcontractor Office Trailer and Laydown area. Measured areas. Took Pictures and review utilities facilities for the Office Trailer's. Attendees Cambalache, Luis Damudt (DCMC), Andres Concepcion (DCMC) & Harry Del Valle (DCMC). Attendees Yabucoa, Axel Rivera (Genera) by phone & Harry Del Valle (DCMC). TOTAL MILEAGE 152 miles
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.97 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- traveled back home in Guaynabo from Central San Juan where I meet with Mr. Milton Flores from DCMC. The purpose of the visit was to provide operational support, ensure alignment of warehouse activities with project objectives, and assist with inventory cycle count process
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 5.32 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from home in Guaynabo to Central San Juan to meet with Mr. Milton Flores from DCMC. The purpose of the visit is to provide operational support, ensure alignment of warehouse activities with project objectives, and assist with inventory.
2025-05-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes |  |  | 2025Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Review the diesel transport process.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Site visit to Jobos facility. Took pictures and walked site for layout locations to ensure efficient workflow, and improve safety.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in weekly Peakers Project Management Update meetings. Discussed how the walkthrough with the contractors went, the turnout was above expectations. Discussed some clarifications the contractors were asking and will be formalizing via RFI and clarification questions to follow for next week review. Attendees: German Nunez, GENERA, Rafael Pabon, CDM Smith, Carlos Palomares CDM Smith, and Frances Vallejo Rosich DCMC.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly agenda update and action items for the Construction Project Management Overview.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre RFC Meeting with RG Engineering - reviewed tracker with outstanding items to compete award contractual negotiations. RGE present revised project schedule, accelerated schedule and revised pricing still pending. RGE, CDM Smith, CSA Group, Sargent & Lundy and DCMC Partners participated.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting ARG Ceres Vega Baja Site - Installation Phase Reviewed Tracker and Outstanding Items list. ARG presented Geo-Piers Foundation Layout to be used under the VE Option. Participants ARG Ceres, CDM Smith, CSA Group, Sargent & Lundy, and DCMC Partners.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peakers - Developed with Carlos Palomares CDM Smith and Frankly Colmenares - CSA Group One Page Format for weekly reporting to Genera.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja reviewed Demolition Phase II Execution with schedule continuation using optional pricing on current contract with the exception of the asphalt paving removal.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up Meeting - Review Staffing Update, Upcoming new Hires for projects and employee benefits, Project Safety, Upcoming Trailers Installation Schedule for four sites, i-pads use among project sites, Procore status and next weeks' meetings with Genera. Frances Vallejo, Michael Merritt, Mark Merritt, Jack Darnall, Lauren Wells, Anneilia Holton and Gilberto Sucre DCMC Partners.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Met with Francisco Feliu - Genera on status and response to RG Engineering to closeout contractual agreement.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 225 | 281.25 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - discussion and coordination to renew Diesel Transfer over the weekend and procedures to be used with Homeca supervision. CDM Smith, CSA Group, Homeca Recycling and DCMC Partners
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for addressing questions for users with Procore tools such as Submittals.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meetings for next week in Puerto Rico.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences to answer questions about Procore tools.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Andres Concepcion, Luis Roman, Luis Duque, Luis Gonzalez and others, all from DCMC to discuss agenda and content for upcoming meeting with RGE.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financials settings.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on gathering Procore Project Id's for purpose of providing to Raissa Borges (DCMC) for purpose of analytics tables.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Procore weekly Q&A session with users. Luis Roman (DCMC), Andres Concepcion (DCMC), Raissa Borges (DCMC), Theresa Perez (DCMC), Rafael Pabon (CDM Smith) and others.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for Permissions.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore schedule tool settings and research on file upload.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on getting schedules deleted from certain projects that were uploaded and the system posted them to Documents tool.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating RGE PPT comments from Luis Roman (DCMC) for our call with the team today.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating schedule invites for Weekly Q&A.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Remote | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Frances Vallejo, Jack Darnall, Lauren Wells, Gilberto Sucre, Barry Scanlon, Foster Veazey, Ada Diaz, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Site Inspection of jobs in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Review the cyber security information for make BCP Plan in Genera.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2.25 |  | 184 | 414 | 184 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339 – Hurricane Maria: Continuing site inspections and on-site tasks at the Vega Baja location to evaluate and identify potential hazards in equipment and facilities, ensuring compliance with established safety standards. Additionally, reviewed cybersecurity information to support the development of the Business Continuity Plan (BCP) for Genera.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss staffing update, vacant positions at Costa Sur, Aguirre and Yabucoa, Procore financial candidate needed, trailer installation update and equipment needed coordination. Participants: Michael Merritt, Mark Merritt, Ada Diaz, Anneilia Holton, Gilberto Sucre, Lauren Wells (DCMC).
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review and analyze peaker staffing plan for Costa Sur, Yabucoa, Daguao and Jobos sites.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Paola Arroyo (DCMC) to discuss site visits at Mayaguez and Costa Sur.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Continued discussions with Rafa Calderón and Glorimel Torrado (DCMC) regarding the BESS TESLA contract. The conversation focused on invoice notes, pending invoice credits, and identifying specific items to be incorporated into upcoming change orders. Also addressed proposed modifications from Sargent & Lundy to ensure alignment across all contract adjustments and maintain consistency with project and contractual requirements.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP No. 220871 - Cooling Tower Motors for Aguirre Power Plant - Began assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Held a discussion with Cristina Ribas and Ricardo Pallens (Genera) regarding the FOMB Federally Funded contract approval packages. Addressed current procurement challenges, including incomplete submissions and disorganized documentation. The conversation focused on identifying ways to improve consistency, structure, and compliance to support a more efficient review and approval process.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Held a meeting with Rafa Calderón and Glorimel Torrado (DCMC) to provide Frances Vallejo (DCMC) with an update on the ongoing BESS TESLA contract discussions. Recapped key points related to invoice notes, pending credits, proposed change orders, and contract modifications involving Sargent & Lundy (S&L). Ensured Frances was aligned on the current status, next steps, and any decisions requiring executive input.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 -Held a discussion with Ricardo Pallens and Jesús Cintrón (Genera) regarding the current procurement process, including its challenges, setbacks, and potential areas for improvement. Drafted a list of identified opportunities to strengthen efficiency, organization, and compliance. Also discussed the development and implementation of a Standard Operating Procedure (SOP) to formalize and streamline procurement workflows.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Collaborated with Mario Gomez from Genera PR to add the missing Genera Connect Timesheets domain to the organization’s DNS, ensuring proper domain resolution and enabling stable access to the application within the Genera PR network environment.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Conducted in-depth testing of the Genera Connect Financial Tracker from within the Genera PR headquarters network to validate system performance and functionality in the finalized environment. Engaged in discussions with Ginell Torres and Saul Falcon from DCMC to explore additional use cases for enhancing the Genera PR procurement process, contributing to the sourcing intelligence integration Scope of Work. Coordinated a follow-up meeting with both participants to continue refining use cases and better understand procurement workflows. Additionally, prepared updated presentation slides for the upcoming weekly DCMC preparation meeting.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 |  | 184 | 598 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Corrected the formatting of Financial Tracker reports to ensure successful upload and accurate data presentation within the Genera Connect Financial Tracker, aligning with stakeholder requirements from Genera PR. Additionally, generated and provisioned user credentials for the platform for Genera PR employees Dimaries Diaz, Jose Roque, Lilliam Ortiz, Gerardo Sanchez, Alejandro Maymi, Maria Rodriguez, and Maria Sanchez to support initial access and system onboarding.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 23 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the work performed. Receive excavator for house demolition on site. House demolished as planned by Homeca.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue the review and learning of the Safety Manual at Genera: Key Safety Policies and Procedures, Incident Reporting and Response, Safety Training and Development,
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue the review and learning of the Safety Manual at Genera: Introduction to Safety Policies, Emergency Preparedness and Response, Hazard Identification and Risk Assessment
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue review the Safety Manual at Genera
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Jobos Pickers Pant at Guayama Puerto Rico. Site Visit to coordinate DCMC Staff and Contractor (RG Engineering) Office Trailers Location and inspection of the project entrance, and project battery delivery route logistic. Meeting with Harry Del Valle (DCMC) to have an interview meeting with the Genera First Safety Officer Francisco Marí.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Central Aguirre _BESS Project at Salinas Puerto Rico. Site Visit to coordinate DCMC Staff and Contractor (RG Engineering) Office Trailers Location and inspection of the project entrance, project battery delivery route logistic. Meet with Harry Del Valle (DCMC) on site to have a short interview meeting with the Genera First Safety Officer Francisco Marí.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Jobos Gas Turbine Plant. Attendees, Francisco Vazquez (Genera), Jose M Lopez (DCMC), Abraham Velazquez (DCMC) & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work, project needs, construction Office Trailers (DCMC) areas & Subcontractor Laydown & Office Trailers Area. Measured areas.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Central Aguirre Plant. Attendees, Jose M Lopez (DCMC), Abraham Velazquez (DCMC) & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed scope of work, project needs, construction Office Trailers (DCMC) areas & Subcontractor Laydown & Office Trailers Area. Measured areas.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review documents to prepare Quality Control Plan for BESS Projects. Coordinate and discussed by phone the Quality Control Plan draft whit Luis Damudt (DCMC), Sent by Email Duenas Trailers quotes to approval and finished Office trailers deliveries coordination.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Evaluation of accident reporting formats and procedures. Activities included a comprehensive review and assessment of existing incident reporting systems to ensure compliance with FEMA and OSHA requirements. The evaluation focused on improving safety documentation, streamlining response protocols, and standardizing reporting formats across operational teams.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Development of safety guidelines for the standardized reporting of accidents, fatalities, and first aid incidents. This task includes drafting procedures aligned with FEMA, OSHA, and local regulatory requirements to improve incident documentation, promote personnel safety, and ensure consistent reporting across recovery operations. The work supports risk management efforts and enhances operational readiness during ongoing hurricane recovery activities.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is being done to create safety guidelines for work involving the use and handling of cranes and rigging systems for the BESS CAMBALACHE project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project drawing set to plan solving publishing issues into de Procore platform. There has been inconsistencies within drawing numbering and content.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Internal alignment meeting to preapre the Procore contractor kickoff meeting by next week (5/29/2025). Meeeting with Lauren Wells (Lemoine) and Luis Roman, Luis Duque and Carlos De Jesus (DCMC).
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Continued Reviewing project Contract attachments on Technical Specifications and Scope of Work that will be finalized in contract. Project planning will depend on the agreement in the attachments.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Attended meeting for Procore Weekly Q&A Session by Lauren Wells (Lemoine) for Procore training.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed the provided Revised Technical Specifications by RG Engineering (Received by Jose Robles) that are proposed to be agreed in construction contract. Addressed proposed revisions and commented for its acceptance in contract.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated and sent correspondence by email to request approval for office trailer location and install to Genera PR (Herminio Arroyo).
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing email sent by Nelson Soler of CDM Smith in regard of pending contract item of Homeca.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing email and RFI on Procore related to project Vega Baja BESS project. Read email in regard of Diesel fuel work stop by subcontractor of Homeca, email was sent by Carirma Sanchez of Homeca. Preparing for RFC meeting at 9:30am.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Meeting with Enrique Laya and Gabriel Sepulveda of CDM, Carlos Hernandez of ARG, Gilberto Sucre and Eduardo Rivera of DCMC, and Wilfredo Sierra, Gary Jasutis, Regina Amirova, Margolis Jordan, and Angel Alicea of S&L. Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the Palo Seco warehouse, compiled a consolidated inventory performance report for Mr. Anthony Vega of Genera PR. The report synthesized data from all warehouse sites, incorporating catalog ID analysis, stock balances, cost breakdowns, variance tracking, and compliance with maximum/minimum thresholds. Performance metrics were presented using percentage-based indicators to evaluate accuracy across multiple storage zones, including AI 023 to AI 031, AF 030 to AF 043, AE 001 to AE 020, AA159 to AA 163.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted technical briefing with Giovanni Taffanelli, Hernan Machado and key DCMC warehouse personnel to analyze inventory discrepancies recorded during prior cycle count activities. The session focused on system level diagnostics, including transactional traceability within Asset Suite, identification of data entry inconsistencies, and evaluation of procedural nonconformance. Discussions covered root cause classification, deployment of corrective control measures and implementation of standardized workflow.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed detailed inventory data validation and generated structured cycle count sheets to support scheduled inventory operations at the Palo Seco warehouse, in coordination with Mr. Giovanni Taffanelli from DCMC. Activities involved cross-referencing item master records, verifying system to physical stock alignment at the bin location level, and prepositioning materials required for count execution.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC to verify data integrity and validate prior cycle count results. The activity focused on reconciling discrepancies between physical stock and system records, ensuring transactional accuracy within Asset Suite, and reinforcing the reliability, traceability, and consistency of recorded inventory balances.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory integrity assessment to isolate inconsistencies between physical counts and digital records at priority storage areas. The process involved analyzing transactional anomalies, evaluating item lifecycle data, and tracking stocks movements to detect system errors. Emphasis was placed on verifying on hand balances, identifying deviations from baseline figures, and capturing data gaps for escalation.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled cycle counting for designated inventory zones. This task was part of a broader initiative focused on improving inventory data fidelity and enhancing synchronization between physical stock and system records. Operational activities included validating item quantities against Asset Suite entries, inspecting labeling compliance and storage conditions. Findings were documented to drive corrective actions and support ongoing efforts to maintain data integrity. Today locations range from AI 023 to AI 031.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Partners Cambalache Power Plant BESS Program Quality Control Plan, Topic 4. Follow Up Inspections, 5. QCP Deficiency Log, 6. Concealed Work Inspection.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Partners Cambalache Power Plant BESS Program Quality Control Plan, Topic 7. Progress Photographs, 8. Punch List, 9. Mock Up Inspections, 10. Start Up Inspections of Equipment, 11. Final Inspection and Acceptance, 12. Superintendent Daily Reports, 13. Owner Furnished Equipment Matrix.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Partners Cambalache Power Plant BESS Program Quality Control Plan, Topic 1. Quality Control Plan - Objective, 2. Subcontractor Participation in Quality Control Plan, 3. Pre Installation Meetings (PI).
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Safety briefing conducted by Homeca and Gilberto Soto DCMC was present. Had Meeting with Carirma Sanchez (HOMECA) to discuss the weekly & weekend work schedule.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervising works at the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform so everyone on the team can work in the proper context and achieve tasks efficiently.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 23 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the work performed. Receive excavator for house demolition on site.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 23 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the work performed. Receive excavator for house demolition on site. House demolished as planned by Homeca.Uploaded missing Documents to ProCore JHA and photos Homeca send after labors were performed.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Continue meeting with Sheila Torres (DCMC) to finish the discussion on Tesla contract. In this contract we agree that a formal request order should be executed to have all the payment changes clear. Also, in this meeting we discuss about Procore change order format.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Meeting participants TESLA (Michael Grabstein, Elizabeth Arentsen, Allin Luong), CSA (Franklyn Colmenares), and DCMC (Rafael Calderon and Glorimel Torrado)
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz, Christian Cruz, Carlos Gonzalez) Marc Maceira (HONRA LLC) and SM Consulting Shellsea Maysonet)
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AI023 to AI031 to begin the cycle counts.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AF030 to AF043